## MSP
WBS | Task Mode | % Complete | Task Name | Show on timeline | Duration | Start | Finish | Resource Names | Predecessors | Successors | Business Validation Owner | Actual Start | Task Summary Name | Baseline10 Start | Baseline10 Finish | WBS Predecessors | Baseline Start | Baseline Finish | Constraint Type | WBS Successors | Constraint Date | Unique ID | Unique ID Predecessors | Unique ID Successors | Total Slack | Summary | Active | Critical | Milestone | Linked Fields | Outline Number | Outline Level | Placeholder | Priority | Status | Warning | Free Slack | Error Message
1 | Auto Scheduled | 50% | AMETEK Release-1, 3-Deployment Plan | No | 451d? | Mon 2/17/25 | Mon 11/9/26 |  |  |  |  | Mon 2/17/25 |  | Mon 2/17/25 | Mon 11/9/26 |  | Mon 2/17/25 | Fri 10/16/26 | As Soon As Possible |  | NA | 1 |  |  | 0d? | Yes | Yes | Yes | No | No | 1 | 1 | No | 500 | On Schedule | No | 0d?
1.1 | Auto Scheduled | 82% | System Readiness | No | 439d? | Mon 2/17/25 | Thu 10/22/26 |  |  |  |  | Mon 2/17/25 | AMETEK Release-1, 3-Deployment Plan | Mon 2/17/25 | Thu 10/22/26 |  | Mon 2/17/25 | Thu 7/16/26 | As Soon As Possible |  | NA | 2 |  |  | 12d? | Yes | Yes | No | No | No | 1.1 | 2 | No | 500 | On Schedule | No | 12d?
1.1.1 | Auto Scheduled | 25% | Environment Schedule | No | 404d? | Thu 3/13/25 | Tue 9/29/26 |  |  |  |  | Thu 3/13/25 | System Readiness | Thu 3/13/25 | Tue 9/29/26 |  | Thu 3/13/25 | Thu 7/16/26 | As Soon As Possible |  | NA | 5 |  |  | 29d? | Yes | Yes | No | No | No | 1.1.1 | 3 | No | 500 | On Schedule | No | 29d?
1.1.1.1 | Auto Scheduled | 100% | DS4-100 Config / Development Client | No | 0.75d | Wed 5/7/25 | Wed 5/7/25 |  |  |  |  | Wed 5/7/25 | Environment Schedule | Wed 5/7/25 | Wed 5/7/25 |  | Wed 5/7/25 | Wed 5/7/25 | As Soon As Possible |  | NA | 85 |  |  | 0d | Yes | Yes | No | No | No | 1.1.1.1 | 4 | No | 500 | Complete | No | 0d
1.1.1.1.1 | Auto Scheduled | 100% | Copy DS4-100 to DS4-110 Dev | No | 6h | Wed 5/7/25 | Wed 5/7/25 |  |  | 10,7 |  | Wed 5/7/25 | DS4-100 Config / Development Client | Wed 5/7/25 | Wed 5/7/25 |  | Wed 5/7/25 | Wed 5/7/25 | Finish No Earlier Than | 1.1.1.3.1,1.1.1.2.1 | Wed 5/7/25 | 100 |  | 107106 | 0h | No | Yes | No | No | No | 1.1.1.1.1 | 5 | No | 500 | Complete | No | 0h
1.1.1.2 | Auto Scheduled | 100% | DS4-110 Unit Test Client | No | 0.5d | Thu 5/8/25 | Thu 5/8/25 |  |  |  |  | Thu 5/8/25 | Environment Schedule | Thu 5/8/25 | Thu 5/8/25 |  | Thu 5/8/25 | Thu 5/8/25 | As Soon As Possible |  | NA | 86 |  |  | 0d | Yes | Yes | No | No | No | 1.1.1.2 | 4 | No | 500 | Complete | No | 0d
1.1.1.2.1 | Auto Scheduled | 100% | List of functional users | No | 2h | Thu 5/8/25 | Thu 5/8/25 |  | 5 | 8 |  | Thu 5/8/25 | DS4-110 Unit Test Client | Thu 5/8/25 | Thu 5/8/25 | 1.1.1.1.1 | Thu 5/8/25 | Thu 5/8/25 | As Soon As Possible | 1.1.1.2.2 | NA | 106 | 100 | 101 | 0h | No | Yes | No | No | No | 1.1.1.2.1 | 5 | No | 500 | Complete | No | 0h
1.1.1.2.2 | Auto Scheduled | 100% | Security Role for Functional Team | No | 2h | Thu 5/8/25 | Thu 5/8/25 |  | 7 |  |  | Thu 5/8/25 | DS4-110 Unit Test Client | Thu 5/8/25 | Thu 5/8/25 | 1.1.1.2.1 | Thu 5/8/25 | Thu 5/8/25 | As Soon As Possible |  | NA | 101 | 106 |  | 0h | No | Yes | No | No | No | 1.1.1.2.2 | 5 | No | 500 | Complete | No | 0h
1.1.1.3 | Auto Scheduled | 100% | DS4-120 Data Dev Client | No | 0.5d | Thu 5/8/25 | Thu 5/8/25 |  |  |  |  | Thu 5/8/25 | Environment Schedule | Thu 5/8/25 | Thu 5/8/25 |  | Thu 5/8/25 | Thu 5/8/25 | As Soon As Possible |  | NA | 87 |  |  | 0d | Yes | Yes | No | No | No | 1.1.1.3 | 4 | No | 500 | Complete | No | 0d
1.1.1.3.1 | Auto Scheduled | 100% | List of functional users | No | 2h | Thu 5/8/25 | Thu 5/8/25 |  | 5 | 11 |  | Thu 5/8/25 | DS4-120 Data Dev Client | Thu 5/8/25 | Thu 5/8/25 | 1.1.1.1.1 | Thu 5/8/25 | Thu 5/8/25 | As Soon As Possible | 1.1.1.3.2 | NA | 107 | 100 | 104 | 0h | No | Yes | No | No | No | 1.1.1.3.1 | 5 | No | 500 | Complete | No | 0h
1.1.1.3.2 | Auto Scheduled | 100% | Security Role for Data Team | No | 2h | Thu 5/8/25 | Thu 5/8/25 |  | 10 |  |  | Thu 5/8/25 | DS4-120 Data Dev Client | Thu 5/8/25 | Thu 5/8/25 | 1.1.1.3.1 | Thu 5/8/25 | Thu 5/8/25 | As Soon As Possible |  | NA | 104 | 107 |  | 0h | No | Yes | No | No | No | 1.1.1.3.2 | 5 | No | 500 | Complete | No | 0h
1.1.1.4 | Auto Scheduled | 100% | QS5 ITC-1 Refresh | No | 277.5d? | Thu 3/13/25 | Mon 4/6/26 |  |  |  |  | Thu 3/13/25 | Environment Schedule | Thu 3/13/25 | Mon 4/6/26 |  | Thu 3/13/25 | Mon 4/6/26 | As Soon As Possible |  | NA | 88 |  |  | 0d? | Yes | Yes | No | No | No | 1.1.1.4 | 4 | No | 500 | Complete | No | 0d?
1.1.1.4.1 | Auto Scheduled | 100% | Change Request to NS2 | No | 1h | Thu 3/13/25 | Thu 3/13/25 | Basis |  |  |  | Thu 3/13/25 | QS5 ITC-1 Refresh | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 830 |  |  | 0h | No | Yes | No | No | No | 1.1.1.4.1 | 5 | No | 500 | Complete | No | 0h
1.1.1.4.2 | Auto Scheduled | 100% | Dev Environment Release from SAP | No | 0d | Thu 1/8/26 | Thu 1/8/26 | NS2 |  | 15 |  | Thu 1/8/26 | QS5 ITC-1 Refresh | Thu 1/8/26 | Thu 1/8/26 |  | Thu 1/8/26 | Thu 1/8/26 | Start No Earlier Than | 1.1.1.4.3 | Thu 1/8/26 | 669 |  | 670 | 0d | No | Yes | No | Yes | No | 1.1.1.4.2 | 5 | No | 500 | Complete | No | 0d
1.1.1.4.3 | Auto Scheduled | 100% | Release Setup ID's and Access | No | 1h | Thu 1/8/26 | Thu 1/8/26 | Security | 14 | 16 |  | Thu 1/8/26 | QS5 ITC-1 Refresh | Thu 1/8/26 | Thu 1/8/26 | 1.1.1.4.2 | Thu 1/8/26 | Thu 1/8/26 | As Soon As Possible | 1.1.1.4.4 | NA | 670 | 669 | 654 | 0h | No | Yes | No | No | No | 1.1.1.4.3 | 5 | No | 500 | Complete | No | 0h
1.1.1.4.4 | Auto Scheduled | 100% | Client Config / Validation | No | 1d | Mon 2/2/26 | Mon 2/2/26 | Basis | 15 | 18 |  | Mon 2/2/26 | QS5 ITC-1 Refresh | Mon 2/2/26 | Mon 2/2/26 | 1.1.1.4.3 | Mon 2/2/26 | Mon 2/2/26 | As Soon As Possible | 1.1.1.4.6 | NA | 654 | 670 | 655 | 0d | No | Yes | No | No | No | 1.1.1.4.4 | 5 | No | 500 | Complete | No | 0d
1.1.1.4.5 | Auto Scheduled | 100% | Technical Transports / BP Setup | No | 1d | Wed 2/4/26 | Wed 2/4/26 | Basis |  | 19,21,20 |  | Wed 2/4/26 | QS5 ITC-1 Refresh | Wed 2/4/26 | Wed 2/4/26 |  | Wed 2/4/26 | Wed 2/4/26 | As Soon As Possible | 1.1.1.4.7,1.1.1.4.9,1.1.1.4.8 | NA | 640 |  | 641642674 | 0d | No | Yes | No | No | No | 1.1.1.4.5 | 5 | No | 500 | Complete | No | 0d
1.1.1.4.6 | Auto Scheduled | 100% | Best Practice / Country Validation | No | 1d? | Tue 2/3/26 | Tue 2/3/26 | Basis | 16 |  |  | Tue 2/3/26 | QS5 ITC-1 Refresh | Tue 2/3/26 | Tue 2/3/26 | 1.1.1.4.4 | Tue 2/3/26 | Tue 2/3/26 | As Soon As Possible |  | NA | 655 | 654 |  | 0d? | No | Yes | No | No | No | 1.1.1.4.6 | 5 | No | 500 | Complete | No | 0d?
1.1.1.4.7 | Auto Scheduled | 100% | Connect Systems and Validate | No | 1d | Thu 2/5/26 | Thu 2/5/26 | Basis | 17 |  |  | Thu 2/5/26 | QS5 ITC-1 Refresh | Thu 2/5/26 | Thu 2/5/26 | 1.1.1.4.5 | Thu 2/5/26 | Thu 2/5/26 | As Soon As Possible |  | NA | 641 | 640 |  | 0d | No | Yes | No | No | No | 1.1.1.4.7 | 5 | No | 500 | Complete | No | 0d
1.1.1.4.8 | Auto Scheduled | 100% | Validate Syniti Connections to QS5 | No | 1d | Thu 2/5/26 | Thu 2/5/26 | Data | 17 |  |  | Thu 2/5/26 | QS5 ITC-1 Refresh | Thu 2/5/26 | Thu 2/5/26 | 1.1.1.4.5 | Thu 2/5/26 | Thu 2/5/26 | As Soon As Possible |  | NA | 674 | 640 |  | 0d | No | Yes | No | No | No | 1.1.1.4.8 | 5 | No | 500 | Complete | No | 0d
1.1.1.4.9 | Auto Scheduled | 100% | Security Transports | No | 4h | Thu 2/5/26 | Thu 2/5/26 | Security | 17 | 23,22 |  | Thu 2/5/26 | QS5 ITC-1 Refresh | Thu 2/5/26 | Thu 2/5/26 | 1.1.1.4.5 | Thu 2/5/26 | Thu 2/5/26 | As Soon As Possible | 1.1.1.4.11,1.1.1.4.10 | NA | 642 | 640 | 643671 | 0h | No | Yes | No | No | No | 1.1.1.4.9 | 5 | No | 500 | Complete | No | 0h
1.1.1.4.10 | Auto Scheduled | 100% | Security Manual Tasks | No | 1d | Thu 2/5/26 | Fri 2/6/26 | Security | 21 |  |  | Thu 2/5/26 | QS5 ITC-1 Refresh | Thu 2/5/26 | Fri 2/6/26 | 1.1.1.4.9 | Thu 2/5/26 | Fri 2/6/26 | As Soon As Possible |  | NA | 671 | 642 |  | 0d | No | Yes | No | No | No | 1.1.1.4.10 | 5 | No | 500 | Complete | No | 0d
1.1.1.4.11 | Auto Scheduled | 100% | Manual Technical Tasks | No | 1d | Thu 2/5/26 | Fri 2/6/26 | Basis | 21 | 24 |  | Thu 2/5/26 | QS5 ITC-1 Refresh | Thu 2/5/26 | Fri 2/6/26 | 1.1.1.4.9 | Thu 2/5/26 | Fri 2/6/26 | As Soon As Possible | 1.1.1.4.12 | NA | 643 | 642 | 644 | 0d | No | Yes | No | No | No | 1.1.1.4.11 | 5 | No | 500 | Complete | No | 0d
1.1.1.4.12 | Auto Scheduled | 100% | Validate Fiori | No | 4h | Fri 2/6/26 | Fri 2/6/26 | Basis | 23 | 26,27,25 |  | Fri 2/6/26 | QS5 ITC-1 Refresh | Fri 2/6/26 | Fri 2/6/26 | 1.1.1.4.11 | Fri 2/6/26 | Fri 2/6/26 | As Soon As Possible | 1.1.1.4.14,1.1.1.4.15,1.1.1.4.13 | NA | 644 | 643 | 645653672 | 0h | No | Yes | No | No | No | 1.1.1.4.12 | 5 | No | 500 | Complete | No | 0h
1.1.1.4.13 | Auto Scheduled | 100% | Fiori App Activation | No | 6h | Mon 2/9/26 | Mon 2/9/26 | Dev Team | 24 |  |  | Mon 2/9/26 | QS5 ITC-1 Refresh | Mon 2/9/26 | Mon 2/9/26 | 1.1.1.4.12 | Mon 2/9/26 | Mon 2/9/26 | As Soon As Possible |  | NA | 672 | 644 |  | 0h | No | Yes | No | No | No | 1.1.1.4.13 | 5 | No | 500 | Complete | No | 0h
1.1.1.4.14 | Auto Scheduled | 100% | Download Transport List | No | 1h | Mon 2/9/26 | Mon 2/9/26 | Basis | 24 | 28 |  | Mon 2/9/26 | QS5 ITC-1 Refresh | Mon 2/9/26 | Mon 2/9/26 | 1.1.1.4.12 | Mon 2/9/26 | Mon 2/9/26 | As Soon As Possible | 1.1.1.4.16 | NA | 645 | 644 | 646 | 0h | No | Yes | No | No | No | 1.1.1.4.14 | 5 | No | 500 | Complete | No | 0h
1.1.1.4.15 | Auto Scheduled | 100% | Business Functions Validation | No | 1d | Mon 2/9/26 | Mon 2/9/26 | Basis | 24 |  |  | Mon 2/9/26 | QS5 ITC-1 Refresh | Mon 2/9/26 | Mon 2/9/26 | 1.1.1.4.12 | Mon 2/9/26 | Mon 2/9/26 | Start No Earlier Than |  | Mon 1/5/26 | 653 | 644 |  | 0d | No | Yes | No | No | No | 1.1.1.4.15 | 5 | No | 500 | Complete | No | 0d
1.1.1.4.16 | Auto Scheduled | 100% | Functional Leads Validation of Transport List | No | 1h | Mon 2/9/26 | Mon 2/9/26 | Functional Leads | 26 | 31,29 |  | Mon 2/9/26 | QS5 ITC-1 Refresh | Mon 2/9/26 | Mon 2/9/26 | 1.1.1.4.14 | Mon 2/9/26 | Mon 2/9/26 | As Soon As Possible | 1.1.1.4.18.1,1.1.1.4.17 | NA | 646 | 645 | 657673 | 0h | No | Yes | No | No | No | 1.1.1.4.16 | 5 | No | 500 | Complete | No | 0h
1.1.1.4.17 | Auto Scheduled | 100% | Release Security roles to Functional Team | No | 1h | Mon 2/9/26 | Mon 2/9/26 | Security | 28 |  |  | Mon 2/9/26 | QS5 ITC-1 Refresh | Mon 2/9/26 | Mon 2/9/26 | 1.1.1.4.16 | Mon 2/9/26 | Mon 2/9/26 | As Soon As Possible |  | NA | 673 | 646 |  | 0h | No | Yes | No | No | No | 1.1.1.4.17 | 5 | No | 500 | Complete | No | 0h
1.1.1.4.18 | Auto Scheduled | 100% | Release Transports to Client | No | 32.75d | Mon 2/9/26 | Wed 3/25/26 |  |  |  |  | Mon 2/9/26 | QS5 ITC-1 Refresh | Mon 2/9/26 | Wed 3/25/26 |  | Mon 2/9/26 | Wed 3/25/26 | As Soon As Possible |  | NA | 647 |  |  | 0d | Yes | Yes | No | No | No | 1.1.1.4.18 | 5 | No | 500 | Complete | No | 0d
1.1.1.4.18.1 | Auto Scheduled | 100% | Import Group 1 - Ent Structure | No | 2h | Mon 2/9/26 | Mon 2/9/26 | Functional Leads | 28 | 32 |  | Mon 2/9/26 | Release Transports to Client | Mon 2/9/26 | Mon 2/9/26 | 1.1.1.4.16 | Mon 2/9/26 | Mon 2/9/26 | As Soon As Possible | 1.1.1.4.18.2 | NA | 657 | 646 | 658 | 0h | No | Yes | No | No | No | 1.1.1.4.18.1 | 6 | No | 500 | Complete | No | 0h
1.1.1.4.18.2 | Auto Scheduled | 100% | Manual activities group 1 | No | 20h | Thu 3/19/26 | Mon 3/23/26 | Functional Leads | 31 | 33 |  | Thu 3/19/26 | Release Transports to Client | Thu 3/19/26 | Mon 3/23/26 | 1.1.1.4.18.1 | Thu 3/19/26 | Mon 3/23/26 | Finish No Earlier Than | 1.1.1.4.18.3 | Wed 2/11/26 | 658 | 657 | 659 | 0h | No | Yes | No | No | No | 1.1.1.4.18.2 | 6 | No | 500 | Complete | No | 0h
1.1.1.4.18.3 | Auto Scheduled | 100% | Import Group 2 - Core Transports | No | 2h | Mon 3/23/26 | Mon 3/23/26 | Functional Leads | 32 | 34 |  | Mon 3/23/26 | Release Transports to Client | Mon 3/23/26 | Mon 3/23/26 | 1.1.1.4.18.2 | Mon 3/23/26 | Mon 3/23/26 | As Soon As Possible | 1.1.1.4.18.4 | NA | 659 | 658 | 660 | 0h | No | Yes | No | No | No | 1.1.1.4.18.3 | 6 | No | 500 | Complete | No | 0h
1.1.1.4.18.4 | Auto Scheduled | 100% | Manual activities group 2 | No | 1d | Mon 3/23/26 | Tue 3/24/26 | Functional Leads | 33 | 35 |  | Mon 3/23/26 | Release Transports to Client | Mon 3/23/26 | Tue 3/24/26 | 1.1.1.4.18.3 | Mon 3/23/26 | Tue 3/24/26 | As Soon As Possible | 1.1.1.4.18.5 | NA | 660 | 659 | 661 | 0d | No | Yes | No | No | No | 1.1.1.4.18.4 | 6 | No | 500 | Complete | No | 0d
1.1.1.4.18.5 | Auto Scheduled | 100% | Import Group 3 - prior to transactions | No | 2h | Tue 3/24/26 | Tue 3/24/26 | Functional Leads | 34 | 36 |  | Tue 3/24/26 | Release Transports to Client | Tue 3/24/26 | Tue 3/24/26 | 1.1.1.4.18.4 | Tue 3/24/26 | Tue 3/24/26 | As Soon As Possible | 1.1.1.4.18.6 | NA | 661 | 660 | 831 | 0h | No | Yes | No | No | No | 1.1.1.4.18.5 | 6 | No | 500 | Complete | No | 0h
1.1.1.4.18.6 | Auto Scheduled | 100% | Manual Activities Group 3 | No | 1d | Wed 3/25/26 | Wed 3/25/26 | Functional Leads | 35 |  |  | Wed 3/25/26 | Release Transports to Client | Wed 3/25/26 | Wed 3/25/26 | 1.1.1.4.18.5 | Wed 3/25/26 | Wed 3/25/26 | As Soon As Possible |  | NA | 831 | 661 |  | 0d | No | Yes | No | No | No | 1.1.1.4.18.6 | 6 | No | 500 | Complete | No | 0d
1.1.1.4.19 | Auto Scheduled | 100% | Import Group 4 - workbench / dev work | No | 2h | Fri 4/3/26 | Fri 4/3/26 | Dev Team |  | 38 |  | Fri 4/3/26 | QS5 ITC-1 Refresh | Fri 4/3/26 | Fri 4/3/26 |  | Fri 4/3/26 | Fri 4/3/26 | Start No Earlier Than | 1.1.1.4.20 | Fri 4/3/26 | 662 |  | 663 | 0h | No | Yes | No | No | No | 1.1.1.4.19 | 5 | No | 500 | Complete | No | 0h
1.1.1.4.20 | Auto Scheduled | 100% | Import Group 5 - Config to support dev workbench | No | 2h | Fri 4/3/26 | Fri 4/3/26 | Dev Team | 37 | 39 |  | Fri 4/3/26 | QS5 ITC-1 Refresh | Fri 4/3/26 | Fri 4/3/26 | 1.1.1.4.19 | Fri 4/3/26 | Fri 4/3/26 | As Soon As Possible | 1.1.1.4.21 | NA | 663 | 662 | 833 | 0h | No | Yes | No | No | No | 1.1.1.4.20 | 5 | No | 500 | Complete | No | 0h
1.1.1.4.21 | Auto Scheduled | 100% | Create Migration Data Project in DMC | No | 1d | Fri 4/3/26 | Mon 4/6/26 | Data Migration Team | 38 | 40 |  | Fri 4/3/26 | QS5 ITC-1 Refresh | Fri 4/3/26 | Mon 4/6/26 | 1.1.1.4.20 | Fri 4/3/26 | Mon 4/6/26 | As Soon As Possible | 1.1.1.4.22 | NA | 833 | 663 | 652 | 0d | No | Yes | No | No | No | 1.1.1.4.21 | 5 | No | 500 | Complete | No | 0d
1.1.1.4.22 | Auto Scheduled | 100% | Environment Ready for Build | No | 0d | Mon 4/6/26 | Mon 4/6/26 | PMO | 39 | 1423,44,42,1804 |  | Mon 4/6/26 | QS5 ITC-1 Refresh | Mon 4/6/26 | Mon 4/6/26 | 1.1.1.4.21 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.4.2.6,1.1.1.5.1.2,1.1.1.5.1,1.2.5.2.6 | NA | 652 | 833 | 245585333404194 | 0d | No | Yes | No | Yes | No | 1.1.1.4.22 | 5 | No | 500 | Complete | No | 0d
1.1.1.5 | Auto Scheduled | 62% | QS4 ITC-2 Refresh | No | 13.13d | Mon 4/27/26 | Thu 5/14/26 |  |  | 629630 |  | Mon 4/27/26 | Environment Schedule | Mon 4/27/26 | Thu 5/14/26 |  | Fri 5/1/26 | Thu 7/16/26 | Start No Earlier Than | 1.2.2,1.2.2.1 | Mon 4/27/26 | 849 |  | 28091685 | -1.88d | Yes | Yes | Yes | No | No | 1.1.1.5 | 4 | No | 500 | Future Task | No | 0d
1.1.1.5.1 | Auto Scheduled | 87% | System Setup | No | 6d | Mon 4/27/26 | Mon 5/4/26 |  | 40 | 58 |  | Mon 4/27/26 | QS4 ITC-2 Refresh | Mon 4/27/26 | Mon 5/4/26 | 1.1.1.4.22 | NA | NA | As Soon As Possible | 1.1.1.5.2 | NA | 3340 | 652 | 867 | 0d | Yes | Yes | Yes | No | No | 1.1.1.5.1 | 5 | No | 500 | Future Task | No | 0d
1.1.1.5.1.1 | Auto Scheduled | 100% | Dev Refresh Basis(Workinig with NS2) | No | 2d | Mon 4/27/26 | Tue 4/28/26 | Basis |  |  |  | Mon 4/27/26 | System Setup | Mon 4/27/26 | Tue 4/28/26 |  | Fri 5/1/26 | Fri 5/1/26 | Start No Earlier Than |  | Mon 4/27/26 | 850 |  |  | 0d | No | Yes | No | No | No | 1.1.1.5.1.1 | 6 | No | 500 | Complete | No | 0d
1.1.1.5.1.2 | Auto Scheduled | 100% | Client Config / Validation | No | 1d | Mon 4/27/26 | Mon 4/27/26 | Basis | 40 | 45 |  | Mon 4/27/26 | System Setup | Mon 4/27/26 | Mon 4/27/26 | 1.1.1.4.22 | Fri 5/8/26 | Mon 5/11/26 | As Soon As Possible | 1.1.1.5.1.3 | NA | 853 | 652 | 854 | 0d | No | Yes | No | No | No | 1.1.1.5.1.2 | 6 | No | 500 | Complete | No | 0d
1.1.1.5.1.3 | Auto Scheduled | 100% | Technical Transports / BP Setup | No | 1d | Tue 4/28/26 | Tue 4/28/26 | Basis | 44 | 46 |  | Tue 4/28/26 | System Setup | Tue 4/28/26 | Tue 4/28/26 | 1.1.1.5.1.2 | Mon 5/11/26 | Tue 5/12/26 | As Soon As Possible | 1.1.1.5.1.4 | NA | 854 | 853 | 855 | 0d | No | Yes | No | No | No | 1.1.1.5.1.3 | 6 | No | 500 | Complete | No | 0d
1.1.1.5.1.4 | Auto Scheduled | 100% | Best Practice / Country Validation | No | 1d | Wed 4/29/26 | Wed 4/29/26 | Basis | 45 | 47 |  | Wed 4/29/26 | System Setup | Wed 4/29/26 | Wed 4/29/26 | 1.1.1.5.1.3 | Tue 5/12/26 | Wed 5/13/26 | As Soon As Possible | 1.1.1.5.1.5 | NA | 855 | 854 | 856 | 0d | No | Yes | No | No | No | 1.1.1.5.1.4 | 6 | No | 500 | Complete | No | 0d
1.1.1.5.1.5 | Auto Scheduled | 100% | Connect Systems and Validate | No | 1d | Thu 4/30/26 | Thu 4/30/26 | Basis | 46 | 48 |  | Thu 4/30/26 | System Setup | Thu 4/30/26 | Thu 4/30/26 | 1.1.1.5.1.4 | Wed 5/13/26 | Thu 5/14/26 | As Soon As Possible | 1.1.1.5.1.6 | NA | 856 | 855 | 857 | 0d | No | Yes | No | No | No | 1.1.1.5.1.5 | 6 | No | 500 | Complete | No | 0d
1.1.1.5.1.6 | Auto Scheduled | 100% | Validate Syniti Connections to QS5 | No | 1d | Fri 5/1/26 | Fri 5/1/26 | Data | 47 | 49 |  | Fri 5/1/26 | System Setup | Fri 5/1/26 | Fri 5/1/26 | 1.1.1.5.1.5 | Thu 5/14/26 | Fri 5/15/26 | As Soon As Possible | 1.1.1.5.1.7 | NA | 857 | 856 | 858 | 0d | No | Yes | No | No | No | 1.1.1.5.1.6 | 6 | No | 500 | Complete | No | 0d
1.1.1.5.1.7 | Auto Scheduled | 100% | Security Transports | No | 4h | Mon 5/4/26 | Mon 5/4/26 | Security | 48 | 50SS |  | Mon 5/4/26 | System Setup | Mon 5/4/26 | Mon 5/4/26 | 1.1.1.5.1.6 | Fri 5/15/26 | Fri 5/15/26 | As Soon As Possible | 1.1.1.5.1.8[SS] | NA | 858 | 857 | 859SS | 0h | No | Yes | No | No | No | 1.1.1.5.1.7 | 6 | No | 500 | Complete | No | 0h
1.1.1.5.1.8 | Auto Scheduled | 100% | Security Manual Tasks | No | 1d | Mon 5/4/26 | Mon 5/4/26 | Security | 49SS | 51SS,52SS |  | Mon 5/4/26 | System Setup | Mon 5/4/26 | Mon 5/4/26 | 1.1.1.5.1.7[SS] | Fri 5/15/26 | Mon 5/18/26 | As Soon As Possible | 1.1.1.5.1.9[SS],1.1.1.5.1.10[SS] | NA | 859 | 858SS | 860SS,861SS | 0d | No | Yes | No | No | No | 1.1.1.5.1.8 | 6 | No | 500 | Complete | No | 0d
1.1.1.5.1.9 | Auto Scheduled | 100% | Manual Technical Tasks | No | 1d | Mon 5/4/26 | Mon 5/4/26 | Basis | 50SS |  |  | Mon 5/4/26 | System Setup | Mon 5/4/26 | Mon 5/4/26 | 1.1.1.5.1.8[SS] | Fri 5/15/26 | Mon 5/18/26 | As Soon As Possible |  | NA | 860 | 859SS |  | 0d | No | Yes | No | No | No | 1.1.1.5.1.9 | 6 | No | 500 | Complete | No | 0d
1.1.1.5.1.10 | Auto Scheduled | 100% | Validate Fiori | No | 4h | Mon 5/4/26 | Mon 5/4/26 | Basis | 50SS | 55SS,53SS |  | Mon 5/4/26 | System Setup | Mon 5/4/26 | Mon 5/4/26 | 1.1.1.5.1.8[SS] | Mon 5/18/26 | Tue 5/19/26 | As Soon As Possible | 1.1.1.5.1.13[SS],1.1.1.5.1.11[SS] | NA | 861 | 859SS | 864SS,862SS | 0h | No | Yes | No | No | No | 1.1.1.5.1.10 | 6 | No | 500 | Complete | No | 0h
1.1.1.5.1.11 | Auto Scheduled | 25% | Fiori App Activation | No | 6h | Mon 5/4/26 | Mon 5/4/26 | Dev Team | 52SS | 54SS,56SS |  | Mon 5/4/26 | System Setup | Mon 5/4/26 | Mon 5/4/26 | 1.1.1.5.1.10[SS] | Tue 5/19/26 | Tue 5/19/26 | As Soon As Possible | 1.1.1.5.1.12[SS],1.1.1.5.1.14[SS] | NA | 862 | 861SS | 863SS,865SS | -138.02h | No | Yes | Yes | No | No | 1.1.1.5.1.11 | 6 | No | 500 | Future Task | No | 0h
1.1.1.5.1.12 | Auto Scheduled | 25% | Download Transport List | No | 1h | Mon 5/4/26 | Mon 5/4/26 | Basis | 53SS |  |  | Mon 5/4/26 | System Setup | Mon 5/4/26 | Mon 5/4/26 | 1.1.1.5.1.11[SS] | Tue 5/19/26 | Tue 5/19/26 | As Soon As Possible |  | NA | 863 | 862SS |  | -133.02h | No | Yes | Yes | No | No | 1.1.1.5.1.12 | 6 | No | 500 | Future Task | No | 0h
1.1.1.5.1.13 | Auto Scheduled | 25% | Business Functions Validation | No | 8h | Mon 5/4/26 | Mon 5/4/26 | Basis | 52SS |  |  | Mon 5/4/26 | System Setup | Mon 5/4/26 | Mon 5/4/26 | 1.1.1.5.1.10[SS] | Tue 5/19/26 | Wed 5/20/26 | As Soon As Possible |  | NA | 864 | 861SS |  | -140.02h | No | Yes | Yes | No | No | 1.1.1.5.1.13 | 6 | No | 500 | Future Task | No | 0h
1.1.1.5.1.14 | Auto Scheduled | 25% | Functional Leads Validation of Transport List | No | 1h | Mon 5/4/26 | Mon 5/4/26 | Functional Leads | 53SS | 59,57 |  | Mon 5/4/26 | System Setup | Mon 5/4/26 | Mon 5/4/26 | 1.1.1.5.1.11[SS] | Tue 5/19/26 | Tue 5/19/26 | As Soon As Possible | 1.1.1.5.2.1,1.1.1.5.1.15 | NA | 865 | 862SS | 868866 | -133.02h | No | Yes | Yes | No | No | 1.1.1.5.1.14 | 6 | No | 500 | Future Task | No | 0h
1.1.1.5.1.15 | Auto Scheduled | 25% | Release Security roles to Functional Team | No | 1h | Mon 5/4/26 | Mon 5/4/26 | Security | 56 |  |  | Mon 5/4/26 | System Setup | Mon 5/4/26 | Mon 5/4/26 | 1.1.1.5.1.14 | Tue 5/19/26 | Tue 5/19/26 | As Soon As Possible |  | NA | 866 | 865 |  | -134.02h | No | Yes | Yes | No | No | 1.1.1.5.1.15 | 6 | No | 500 | Future Task | No | 0h
1.1.1.5.2 | Auto Scheduled | 20% | Release Transports to Client | No | 6.56d | Tue 5/5/26 | Wed 5/13/26 |  | 42 | 73 |  | Tue 5/5/26 | QS4 ITC-2 Refresh | Tue 5/5/26 | Wed 5/13/26 | 1.1.1.5.1 | Tue 5/19/26 | Tue 5/26/26 | As Soon As Possible | 1.1.1.6.1 | NA | 867 | 3340 | 3339 | -1.31d | Yes | Yes | Yes | No | No | 1.1.1.5.2 | 5 | No | 500 | Future Task | No | 0d
1.1.1.5.2.1 | Auto Scheduled | 25% | Import Group 1 - Ent Structure | No | 2h | Tue 5/5/26 | Tue 5/5/26 | Functional Leads | 56 | 60 |  | Tue 5/5/26 | Release Transports to Client | Tue 5/5/26 | Tue 5/5/26 | 1.1.1.5.1.14 | Tue 5/19/26 | Tue 5/19/26 | As Soon As Possible | 1.1.1.5.2.2 | NA | 868 | 865 | 869 | -131.52h | No | Yes | Yes | No | No | 1.1.1.5.2.1 | 6 | No | 500 | Future Task | No | 0h
1.1.1.5.2.2 | Auto Scheduled | 25% | Manual activities group 1 | No | 20h | Tue 5/5/26 | Thu 5/7/26 | Functional Leads | 59 | 61 |  | Tue 5/5/26 | Release Transports to Client | Tue 5/5/26 | Thu 5/7/26 | 1.1.1.5.2.1 | Tue 5/19/26 | Fri 5/22/26 | As Soon As Possible | 1.1.1.5.2.3 | NA | 869 | 868 | 870 | -151.52h | No | Yes | Yes | No | No | 1.1.1.5.2.2 | 6 | No | 500 | Future Task | No | 0h
1.1.1.5.2.3 | Auto Scheduled | 25% | Import Group 2 - Core Transports | No | 2h | Thu 5/7/26 | Thu 5/7/26 | Functional Leads | 60 | 62 |  | Thu 5/7/26 | Release Transports to Client | Thu 5/7/26 | Thu 5/7/26 | 1.1.1.5.2.2 | Fri 5/22/26 | Fri 5/22/26 | As Soon As Possible | 1.1.1.5.2.4 | NA | 870 | 869 | 871 | -153.52h | No | Yes | Yes | No | No | 1.1.1.5.2.3 | 6 | No | 500 | Future Task | No | 0h
1.1.1.5.2.4 | Auto Scheduled | 25% | Manual activities group 2 | No | 1d | Fri 5/8/26 | Fri 5/8/26 | Functional Leads | 61 | 63 |  | Fri 5/8/26 | Release Transports to Client | Fri 5/8/26 | Fri 5/8/26 | 1.1.1.5.2.3 | Fri 5/22/26 | Mon 5/25/26 | As Soon As Possible | 1.1.1.5.2.5 | NA | 871 | 870 | 872 | -20.19d | No | Yes | Yes | No | No | 1.1.1.5.2.4 | 6 | No | 500 | Future Task | No | 0d
1.1.1.5.2.5 | Auto Scheduled | 25% | Import Group 3 - prior to transactions | No | 2h | Mon 5/11/26 | Mon 5/11/26 | Functional Leads | 62 | 64 |  | Mon 5/11/26 | Release Transports to Client | Mon 5/11/26 | Mon 5/11/26 | 1.1.1.5.2.4 | Mon 5/25/26 | Mon 5/25/26 | As Soon As Possible | 1.1.1.5.2.6 | NA | 872 | 871 | 873 | -163.52h | No | Yes | Yes | No | No | 1.1.1.5.2.5 | 6 | No | 500 | Future Task | No | 0h
1.1.1.5.2.6 | Auto Scheduled | 25% | Manual Activities Group 3 | No | 1d | Mon 5/11/26 | Tue 5/12/26 | Functional Leads | 63 | 65 |  | Mon 5/11/26 | Release Transports to Client | Mon 5/11/26 | Tue 5/12/26 | 1.1.1.5.2.5 | Mon 5/25/26 | Tue 5/26/26 | As Soon As Possible | 1.1.1.5.2.7 | NA | 873 | 872 | 874 | -22.75d | No | Yes | Yes | No | No | 1.1.1.5.2.6 | 6 | No | 500 | Future Task | No | 0d
1.1.1.5.2.7 | Auto Scheduled | 0% | Import Group 4 - workbench / dev work | No | 2h | Tue 5/12/26 | Tue 5/12/26 | Dev Team | 64 | 66 |  | NA | Release Transports to Client | Tue 5/12/26 | Tue 5/12/26 | 1.1.1.5.2.6 | Tue 5/26/26 | Tue 5/26/26 | As Soon As Possible | 1.1.1.5.2.8 | NA | 874 | 873 | 875 | -182.02h | No | Yes | Yes | No | No | 1.1.1.5.2.7 | 6 | No | 500 | Future Task | No | 0h
1.1.1.5.2.8 | Auto Scheduled | 0% | Import Group 5 - Config to support dev workbench | No | 8.5h | Tue 5/12/26 | Wed 5/13/26 | Dev Team | 65 | 68,67SS |  | NA | Release Transports to Client | Tue 5/12/26 | Wed 5/13/26 | 1.1.1.5.2.7 | Wed 5/27/26 | Thu 5/28/26 | As Soon As Possible | 1.1.1.5.3.1,1.1.1.5.3[SS] | NA | 875 | 874 | 1221,1226SS | -182.02h | No | Yes | Yes | No | No | 1.1.1.5.2.8 | 6 | No | 500 | Future Task | No | 0h
1.1.1.5.3 | Auto Scheduled | 0% | Data Project Create | No | 0.56d | Wed 5/13/26 | Thu 5/14/26 |  | 66SS |  |  | NA | QS4 ITC-2 Refresh | Wed 5/13/26 | Thu 5/14/26 | 1.1.1.5.2.8[SS] | Wed 5/27/26 | Thu 5/28/26 | As Soon As Possible |  | NA | 1226 | 875SS |  | -7.44d | Yes | Yes | Yes | No | No | 1.1.1.5.3 | 5 | No | 500 | Future Task | No | 0d
1.1.1.5.3.1 | Auto Scheduled | 0% | Open Client | No | 15m | Wed 5/13/26 | Wed 5/13/26 | Basis | 66 | 69 |  | NA | Data Project Create | Wed 5/13/26 | Wed 5/13/26 | 1.1.1.5.2.8 | Wed 5/27/26 | Wed 5/27/26 | As Soon As Possible | 1.1.1.5.3.2 | NA | 1221 | 875 | 876 | -3571m | No | Yes | Yes | No | No | 1.1.1.5.3.1 | 6 | No | 500 | Future Task | No | 0m
1.1.1.5.3.2 | Auto Scheduled | 0% | Create Migration Data Project in DMC | No | 4h | Wed 5/13/26 | Thu 5/14/26 | Data Migration Team | 68 | 70 |  | NA | Data Project Create | Wed 5/13/26 | Thu 5/14/26 | 1.1.1.5.3.1 | Wed 5/27/26 | Thu 5/28/26 | As Soon As Possible | 1.1.1.5.3.3 | NA | 876 | 1221 | 1222 | -59.52h | No | Yes | Yes | No | No | 1.1.1.5.3.2 | 6 | No | 500 | Future Task | No | 0h
1.1.1.5.3.3 | Auto Scheduled | 0% | Close Client | No | 15m | Thu 5/14/26 | Thu 5/14/26 | Basis | 69 | 71 |  | NA | Data Project Create | Thu 5/14/26 | Thu 5/14/26 | 1.1.1.5.3.2 | Thu 5/28/26 | Thu 5/28/26 | As Soon As Possible | 1.1.1.5.4 | NA | 1222 | 876 | 877 | -3571m | No | Yes | Yes | No | No | 1.1.1.5.3.3 | 6 | No | 500 | Future Task | No | 0m
1.1.1.5.4 | Auto Scheduled | 0% | Environment Ready for Test | No | 0m | Thu 5/14/26 | Thu 5/14/26 | PMO | 70 |  |  | NA | QS4 ITC-2 Refresh | Thu 5/14/26 | Thu 5/14/26 | 1.1.1.5.3.3 | Thu 7/16/26 | Thu 7/16/26 | As Soon As Possible |  | NA | 877 | 1222 |  | -3571m | No | Yes | Yes | Yes | No | 1.1.1.5.4 | 5 | No | 500 | Future Task | No | 0m
1.1.1.6 | Auto Scheduled | 0% | QS5 ITC-3 Refresh | No | 9.44d | Mon 5/18/26 | Fri 5/29/26 |  |  | 1010 |  | NA | Environment Schedule | Mon 5/18/26 | Fri 5/29/26 |  | Fri 5/1/26 | Thu 7/16/26 | As Soon As Possible | 1.2.3.1 | NA | 1284 |  | 2054 | -25.19d | Yes | Yes | Yes | No | No | 1.1.1.6 | 4 | No | 500 | Future Task | No | 0d
1.1.1.6.1 | Auto Scheduled | 0% | System Setup | No | 8d | Mon 5/18/26 | Wed 5/27/26 |  | 58 |  |  | NA | QS5 ITC-3 Refresh | Mon 5/18/26 | Wed 5/27/26 | 1.1.1.5.2 | NA | NA | As Soon As Possible |  | NA | 3339 | 867 |  | -25.19d | Yes | Yes | Yes | No | No | 1.1.1.6.1 | 5 | No | 500 | Future Task | No | 0d
1.1.1.6.1.1 | Auto Scheduled | 0% | System Refresh Basis(Workinig with NS2) | No | 3d | Mon 5/18/26 | Wed 5/20/26 | Basis |  | 75 |  | NA | System Setup | Mon 5/18/26 | Wed 5/20/26 |  | Fri 5/1/26 | Fri 5/1/26 | Must Start On | 1.1.1.6.1.2 | Mon 5/18/26 | 1285 |  | 1288 | 0d | No | Yes | Yes | No | No | 1.1.1.6.1.1 | 6 | No | 500 | Future Task | No | 0d
1.1.1.6.1.2 | Auto Scheduled | 0% | Client Config / Validation | No | 1d | Thu 5/21/26 | Thu 5/21/26 | Basis | 74 | 76,80SS |  | NA | System Setup | Thu 5/21/26 | Thu 5/21/26 | 1.1.1.6.1.1 | Fri 5/8/26 | Mon 5/11/26 | As Soon As Possible | 1.1.1.6.1.3,1.1.1.6.1.7[SS] | NA | 1288 | 1285 | 1289,1293SS | -28.19d | No | Yes | Yes | No | No | 1.1.1.6.1.2 | 6 | No | 500 | Future Task | No | 0d
1.1.1.6.1.3 | Auto Scheduled | 0% | Technical Transports / BP Setup | No | 1d | Fri 5/22/26 | Fri 5/22/26 | Basis | 75 | 77 |  | NA | System Setup | Fri 5/22/26 | Fri 5/22/26 | 1.1.1.6.1.2 | Mon 5/11/26 | Tue 5/12/26 | As Soon As Possible | 1.1.1.6.1.4 | NA | 1289 | 1288 | 1290 | 7d | No | Yes | No | No | No | 1.1.1.6.1.3 | 6 | No | 500 | Future Task | No | 0d
1.1.1.6.1.4 | Auto Scheduled | 0% | Best Practice / Country Validation | No | 1d | Mon 5/25/26 | Mon 5/25/26 | Basis | 76 | 78 |  | NA | System Setup | Mon 5/25/26 | Mon 5/25/26 | 1.1.1.6.1.3 | Tue 5/12/26 | Wed 5/13/26 | As Soon As Possible | 1.1.1.6.1.5 | NA | 1290 | 1289 | 1291 | 7d | No | Yes | No | No | No | 1.1.1.6.1.4 | 6 | No | 500 | Future Task | No | 0d
1.1.1.6.1.5 | Auto Scheduled | 0% | Connect Systems and Validate | No | 1d | Tue 5/26/26 | Tue 5/26/26 | Basis | 77 | 79 |  | NA | System Setup | Tue 5/26/26 | Tue 5/26/26 | 1.1.1.6.1.4 | Wed 5/13/26 | Thu 5/14/26 | As Soon As Possible | 1.1.1.6.1.6 | NA | 1291 | 1290 | 1292 | 7d | No | Yes | No | No | No | 1.1.1.6.1.5 | 6 | No | 500 | Future Task | No | 0d
1.1.1.6.1.6 | Auto Scheduled | 0% | Validate Syniti Connections to QS5 | No | 1d | Wed 5/27/26 | Wed 5/27/26 | Data | 78 |  |  | NA | System Setup | Wed 5/27/26 | Wed 5/27/26 | 1.1.1.6.1.5 | Thu 5/14/26 | Fri 5/15/26 | As Soon As Possible |  | NA | 1292 | 1291 |  | 7d | No | Yes | No | No | No | 1.1.1.6.1.6 | 6 | No | 500 | Future Task | No | 7d
1.1.1.6.1.7 | Auto Scheduled | 0% | Security Transports | No | 4h | Thu 5/21/26 | Thu 5/21/26 | Security | 75SS | 81,82SS |  | NA | System Setup | Thu 5/21/26 | Thu 5/21/26 | 1.1.1.6.1.2[SS] | Fri 5/15/26 | Fri 5/15/26 | As Soon As Possible | 1.1.1.6.1.8,1.1.1.6.1.9[SS] | NA | 1293 | 1288SS | 1294,1295SS | -225.52h | No | Yes | Yes | No | No | 1.1.1.6.1.7 | 6 | No | 500 | Future Task | No | 0h
1.1.1.6.1.8 | Auto Scheduled | 0% | Security Manual Tasks | No | 1d | Thu 5/21/26 | Fri 5/22/26 | Security | 80 |  |  | NA | System Setup | Thu 5/21/26 | Fri 5/22/26 | 1.1.1.6.1.7 | Fri 5/15/26 | Mon 5/18/26 | As Soon As Possible |  | NA | 1294 | 1293 |  | 10.5d | No | Yes | No | No | No | 1.1.1.6.1.8 | 6 | No | 500 | Future Task | No | 10.5d
1.1.1.6.1.9 | Auto Scheduled | 0% | Manual Technical Tasks | No | 1d | Thu 5/21/26 | Thu 5/21/26 | Basis | 80SS | 83SS,84SS |  | NA | System Setup | Thu 5/21/26 | Thu 5/21/26 | 1.1.1.6.1.7[SS] | Fri 5/15/26 | Mon 5/18/26 | As Soon As Possible | 1.1.1.6.1.10[SS],1.1.1.6.1.11[SS] | NA | 1295 | 1293SS | 1296SS,1297SS | -28.19d | No | Yes | Yes | No | No | 1.1.1.6.1.9 | 6 | No | 500 | Future Task | No | 0d
1.1.1.6.1.10 | Auto Scheduled | 0% | Validate Fiori | No | 4h | Thu 5/21/26 | Thu 5/21/26 | Basis | 82SS |  |  | NA | System Setup | Thu 5/21/26 | Thu 5/21/26 | 1.1.1.6.1.9[SS] | Mon 5/18/26 | Tue 5/19/26 | As Soon As Possible |  | NA | 1296 | 1295SS |  | 92h | No | Yes | No | No | No | 1.1.1.6.1.10 | 6 | No | 500 | Future Task | No | 92h
1.1.1.6.1.11 | Auto Scheduled | 0% | Fiori App Activation | No | 6h | Thu 5/21/26 | Thu 5/21/26 | Dev Team | 82SS | 85SS |  | NA | System Setup | Thu 5/21/26 | Thu 5/21/26 | 1.1.1.6.1.9[SS] | Tue 5/19/26 | Tue 5/19/26 | As Soon As Possible | 1.1.1.6.1.12[SS] | NA | 1297 | 1295SS | 1298SS | -225.52h | No | Yes | Yes | No | No | 1.1.1.6.1.11 | 6 | No | 500 | Future Task | No | 0h
1.1.1.6.1.12 | Auto Scheduled | 0% | Download Transport List | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Basis | 84SS | 86SS,87SS |  | NA | System Setup | Thu 5/21/26 | Thu 5/21/26 | 1.1.1.6.1.11[SS] | Tue 5/19/26 | Tue 5/19/26 | As Soon As Possible | 1.1.1.6.1.13[SS],1.1.1.6.1.14[SS] | NA | 1298 | 1297SS | 1299SS,1300SS | -225.52h | No | Yes | Yes | No | No | 1.1.1.6.1.12 | 6 | No | 500 | Future Task | No | 0h
1.1.1.6.1.13 | Auto Scheduled | 0% | Business Functions Validation | No | 8h | Thu 5/21/26 | Thu 5/21/26 | Basis | 85SS |  |  | NA | System Setup | Thu 5/21/26 | Thu 5/21/26 | 1.1.1.6.1.12[SS] | Tue 5/19/26 | Wed 5/20/26 | Start No Earlier Than |  | Mon 1/5/26 | 1299 | 1298SS |  | 88h | No | Yes | No | No | No | 1.1.1.6.1.13 | 6 | No | 500 | Future Task | No | 88h
1.1.1.6.1.14 | Auto Scheduled | 0% | Functional Leads Validation of Transport | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Functional Leads | 85SS | 90,89,88SS |  | NA | System Setup | Thu 5/21/26 | Thu 5/21/26 | 1.1.1.6.1.12[SS] | Tue 5/19/26 | Tue 5/19/26 | As Soon As Possible | 1.1.1.6.2.1,1.1.1.6.2,1.1.1.6.1.15[SS] | NA | 1300 | 1298SS | 1303,1302,1301SS | -225.52h | No | Yes | Yes | No | No | 1.1.1.6.1.14 | 6 | No | 500 | Future Task | No | 0h
1.1.1.6.1.15 | Auto Scheduled | 0% | Release Security roles to Functional Team | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Security | 87SS |  |  | NA | System Setup | Thu 5/21/26 | Thu 5/21/26 | 1.1.1.6.1.14[SS] | Tue 5/19/26 | Tue 5/19/26 | As Soon As Possible |  | NA | 1301 | 1300SS |  | 95h | No | Yes | No | No | No | 1.1.1.6.1.15 | 6 | No | 500 | Future Task | No | 95h
1.1.1.6.2 | Auto Scheduled | 0% | Release Transports to Client | No | 6.31d | Thu 5/21/26 | Fri 5/29/26 |  | 87 |  |  | NA | QS5 ITC-3 Refresh | Thu 5/21/26 | Fri 5/29/26 | 1.1.1.6.1.14 | Tue 5/19/26 | Tue 5/26/26 | As Soon As Possible |  | NA | 1302 | 1300 |  | -28.19d | Yes | Yes | Yes | No | No | 1.1.1.6.2 | 5 | No | 500 | Future Task | No | 0d
1.1.1.6.2.1 | Auto Scheduled | 0% | Import Group 1 - Ent Structure | No | 2h | Thu 5/21/26 | Thu 5/21/26 | Functional Leads | 87 | 91 |  | NA | Release Transports to Client | Thu 5/21/26 | Thu 5/21/26 | 1.1.1.6.1.14 | Tue 5/19/26 | Tue 5/19/26 | As Soon As Possible | 1.1.1.6.2.2 | NA | 1303 | 1300 | 1304 | -225.52h | No | Yes | Yes | No | No | 1.1.1.6.2.1 | 6 | No | 500 | Future Task | No | 0h
1.1.1.6.2.2 | Auto Scheduled | 0% | Manual activities group 1 | No | 20h | Thu 5/21/26 | Mon 5/25/26 | Functional Leads | 90 | 92 |  | NA | Release Transports to Client | Thu 5/21/26 | Mon 5/25/26 | 1.1.1.6.2.1 | Tue 5/19/26 | Fri 5/22/26 | Finish No Earlier Than | 1.1.1.6.2.3 | Wed 2/11/26 | 1304 | 1303 | 1305 | -225.52h | No | Yes | Yes | No | No | 1.1.1.6.2.2 | 6 | No | 500 | Future Task | No | 0h
1.1.1.6.2.3 | Auto Scheduled | 0% | Import Group 2 - Core Transports | No | 2h | Mon 5/25/26 | Tue 5/26/26 | Functional Leads | 91 | 93 |  | NA | Release Transports to Client | Mon 5/25/26 | Tue 5/26/26 | 1.1.1.6.2.2 | Fri 5/22/26 | Fri 5/22/26 | As Soon As Possible | 1.1.1.6.2.4 | NA | 1305 | 1304 | 1306 | -225.52h | No | Yes | Yes | No | No | 1.1.1.6.2.3 | 6 | No | 500 | Future Task | No | 0h
1.1.1.6.2.4 | Auto Scheduled | 0% | Manual activities group 2 | No | 1d | Tue 5/26/26 | Wed 5/27/26 | Functional Leads | 92 | 94 |  | NA | Release Transports to Client | Tue 5/26/26 | Wed 5/27/26 | 1.1.1.6.2.3 | Fri 5/22/26 | Mon 5/25/26 | As Soon As Possible | 1.1.1.6.2.5 | NA | 1306 | 1305 | 1307 | -28.19d | No | Yes | Yes | No | No | 1.1.1.6.2.4 | 6 | No | 500 | Future Task | No | 0d
1.1.1.6.2.5 | Auto Scheduled | 0% | Import Group 3 - prior to transactions | No | 2h | Wed 5/27/26 | Wed 5/27/26 | Functional Leads | 93 | 95 |  | NA | Release Transports to Client | Wed 5/27/26 | Wed 5/27/26 | 1.1.1.6.2.4 | Mon 5/25/26 | Mon 5/25/26 | As Soon As Possible | 1.1.1.6.2.6 | NA | 1307 | 1306 | 1308 | -225.52h | No | Yes | Yes | No | No | 1.1.1.6.2.5 | 6 | No | 500 | Future Task | No | 0h
1.1.1.6.2.6 | Auto Scheduled | 0% | Manual Activities Group 3 | No | 1d | Wed 5/27/26 | Thu 5/28/26 | Functional Leads | 94 | 96,98,99 |  | NA | Release Transports to Client | Wed 5/27/26 | Thu 5/28/26 | 1.1.1.6.2.5 | Mon 5/25/26 | Tue 5/26/26 | As Soon As Possible | 1.1.1.6.2.7,1.1.1.6.3,1.1.1.6.3.1 | NA | 1308 | 1307 | 130913111312 | -28.19d | No | Yes | Yes | No | No | 1.1.1.6.2.6 | 6 | No | 500 | Future Task | No | 0d
1.1.1.6.2.7 | Auto Scheduled | 0% | Import Group 4 - workbench / dev work | No | 2h | Thu 5/28/26 | Thu 5/28/26 | Dev Team | 95 | 97SS |  | NA | Release Transports to Client | Thu 5/28/26 | Thu 5/28/26 | 1.1.1.6.2.6 | Tue 5/26/26 | Tue 5/26/26 | As Soon As Possible | 1.1.1.6.2.8[SS] | NA | 1309 | 1308 | 1310SS | 44.5h | No | Yes | No | No | No | 1.1.1.6.2.7 | 6 | No | 500 | Future Task | No | 0h
1.1.1.6.2.8 | Auto Scheduled | 0% | Import Group 5 - Config to support dev workbench | No | 8.5h | Thu 5/28/26 | Fri 5/29/26 | Dev Team | 96SS |  |  | NA | Release Transports to Client | Thu 5/28/26 | Fri 5/29/26 | 1.1.1.6.2.7[SS] | Wed 5/27/26 | Thu 5/28/26 | As Soon As Possible |  | NA | 1310 | 1309SS |  | 44.5h | No | Yes | No | No | No | 1.1.1.6.2.8 | 6 | No | 500 | Future Task | No | 44.5h
1.1.1.6.3 | Auto Scheduled | 0% | Data Project Create | No | 0.56d | Thu 5/28/26 | Thu 5/28/26 |  | 95 |  |  | NA | QS5 ITC-3 Refresh | Thu 5/28/26 | Thu 5/28/26 | 1.1.1.6.2.6 | Wed 5/27/26 | Thu 5/28/26 | As Soon As Possible |  | NA | 1311 | 1308 |  | -28.19d | Yes | Yes | Yes | No | No | 1.1.1.6.3 | 5 | No | 500 | Future Task | No | 0d
1.1.1.6.3.1 | Auto Scheduled | 0% | Open Client | No | 15m | Thu 5/28/26 | Thu 5/28/26 | Basis | 95 | 100 |  | NA | Data Project Create | Thu 5/28/26 | Thu 5/28/26 | 1.1.1.6.2.6 | Wed 5/27/26 | Wed 5/27/26 | As Soon As Possible | 1.1.1.6.3.2 | NA | 1312 | 1308 | 1313 | -13531m | No | Yes | Yes | No | No | 1.1.1.6.3.1 | 6 | No | 500 | Future Task | No | 0m
1.1.1.6.3.2 | Auto Scheduled | 0% | Create Migration Data Project in DMC | No | 4h | Thu 5/28/26 | Thu 5/28/26 | Data Migration Team | 99 | 101 |  | NA | Data Project Create | Thu 5/28/26 | Thu 5/28/26 | 1.1.1.6.3.1 | Wed 5/27/26 | Thu 5/28/26 | As Soon As Possible | 1.1.1.6.3.3 | NA | 1313 | 1312 | 1314 | -225.52h | No | Yes | Yes | No | No | 1.1.1.6.3.2 | 6 | No | 500 | Future Task | No | 0h
1.1.1.6.3.3 | Auto Scheduled | 0% | Close Client | No | 15m | Thu 5/28/26 | Thu 5/28/26 | Basis | 100 | 102 |  | NA | Data Project Create | Thu 5/28/26 | Thu 5/28/26 | 1.1.1.6.3.2 | Thu 5/28/26 | Thu 5/28/26 | As Soon As Possible | 1.1.1.6.4 | NA | 1314 | 1313 | 1315 | -13531m | No | Yes | Yes | No | No | 1.1.1.6.3.3 | 6 | No | 500 | Future Task | No | 0m
1.1.1.6.4 | Auto Scheduled | 0% | Environment Ready for Test | No | 0m | Thu 5/28/26 | Thu 5/28/26 | PMO | 101 | 104 |  | NA | QS5 ITC-3 Refresh | Thu 5/28/26 | Thu 5/28/26 | 1.1.1.6.3.3 | Thu 7/16/26 | Thu 7/16/26 | As Soon As Possible | 1.1.1.7.1 | NA | 1315 | 1314 | 3338 | -13531m | No | Yes | Yes | Yes | No | 1.1.1.6.4 | 5 | No | 500 | Future Task | No | 0m
1.1.1.7 | Auto Scheduled | 0% | QS4 UAT Refresh | No | 13d | Mon 6/8/26 | Wed 6/24/26 |  |  | 13891390 |  | NA | Environment Schedule | Mon 6/8/26 | Wed 6/24/26 |  | Thu 3/13/25 | Thu 7/16/26 | As Soon As Possible | 1.2.4,1.2.4.1 | NA | 884 |  | 24222423 | -34.25d | Yes | Yes | Yes | No | No | 1.1.1.7 | 4 | No | 500 | Future Task | No | 0d
1.1.1.7.1 | Auto Scheduled | 0% | System Setup | No | 8d | Mon 6/8/26 | Wed 6/17/26 |  | 102 |  |  | NA | QS4 UAT Refresh | Mon 6/8/26 | Wed 6/17/26 | 1.1.1.6.4 | NA | NA | As Soon As Possible |  | NA | 3338 | 1315 |  | -34.25d | Yes | Yes | Yes | No | No | 1.1.1.7.1 | 5 | No | 500 | Future Task | No | 0d
1.1.1.7.1.1 | Auto Scheduled | 0% | System Refresh Basis(Workinig with NS2) | No | 2d | Mon 6/8/26 | Tue 6/9/26 | Basis |  | 106 |  | NA | System Setup | Mon 6/8/26 | Tue 6/9/26 |  | Fri 6/19/26 | Fri 6/19/26 | Must Start On | 1.1.1.7.1.2 | Mon 6/8/26 | 885 |  | 888 | 0d | No | Yes | Yes | No | No | 1.1.1.7.1.1 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.2 | Auto Scheduled | 0% | Client Config / Validation | No | 2d | Wed 6/10/26 | Thu 6/11/26 | Basis | 105 | 107108 |  | NA | System Setup | Wed 6/10/26 | Thu 6/11/26 | 1.1.1.7.1.1 | Fri 6/26/26 | Mon 6/29/26 | As Soon As Possible | 1.1.1.7.1.3,1.1.1.7.1.4 | NA | 888 | 885 | 889890 | -36.25d | No | Yes | Yes | No | No | 1.1.1.7.1.2 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.3 | Auto Scheduled | 0% | Technical Transports / BP Setup | No | 1d | Fri 6/12/26 | Fri 6/12/26 | Basis | 106 | 111 |  | NA | System Setup | Fri 6/12/26 | Fri 6/12/26 | 1.1.1.7.1.2 | Mon 6/29/26 | Tue 6/30/26 | As Soon As Possible | 1.1.1.7.1.7 | NA | 889 | 888 | 893 | -36.25d | No | Yes | Yes | No | No | 1.1.1.7.1.3 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.4 | Auto Scheduled | 0% | Best Practice / Country Validation | No | 1d | Fri 6/12/26 | Fri 6/12/26 | Basis | 106 | 109111 |  | NA | System Setup | Fri 6/12/26 | Fri 6/12/26 | 1.1.1.7.1.2 | Tue 6/30/26 | Wed 7/1/26 | As Soon As Possible | 1.1.1.7.1.5,1.1.1.7.1.7 | NA | 890 | 888 | 891893 | -36.25d | No | Yes | Yes | No | No | 1.1.1.7.1.4 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.5 | Auto Scheduled | 0% | Connect Systems and Validate | No | 2d | Mon 6/15/26 | Tue 6/16/26 | Basis | 108 | 110 |  | NA | System Setup | Mon 6/15/26 | Tue 6/16/26 | 1.1.1.7.1.4 | Wed 7/1/26 | Thu 7/2/26 | As Soon As Possible | 1.1.1.7.1.6 | NA | 891 | 890 | 892 | -20.69d | No | Yes | Yes | No | No | 1.1.1.7.1.5 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.6 | Auto Scheduled | 0% | Validate Syniti Connections to QS5 | No | 1d | Wed 6/17/26 | Wed 6/17/26 | Data | 109 |  |  | NA | System Setup | Wed 6/17/26 | Wed 6/17/26 | 1.1.1.7.1.5 | Thu 7/2/26 | Fri 7/3/26 | As Soon As Possible |  | NA | 892 | 891 |  | -20.69d | No | Yes | Yes | No | No | 1.1.1.7.1.6 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.7 | Auto Scheduled | 0% | Security Transports | No | 1d | Mon 6/15/26 | Mon 6/15/26 | Security | 108107 | 113SS,112 |  | NA | System Setup | Mon 6/15/26 | Mon 6/15/26 | 1.1.1.7.1.4,1.1.1.7.1.3 | Fri 7/3/26 | Fri 7/3/26 | As Soon As Possible | 1.1.1.7.1.9[SS],1.1.1.7.1.8 | NA | 893 | 890889 | 895SS,894 | -36.25d | No | Yes | Yes | No | No | 1.1.1.7.1.7 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.8 | Auto Scheduled | 0% | Security Manual Tasks | No | 1d | Tue 6/16/26 | Tue 6/16/26 | Security | 111 |  |  | NA | System Setup | Tue 6/16/26 | Tue 6/16/26 | 1.1.1.7.1.7 | Fri 7/3/26 | Mon 7/6/26 | As Soon As Possible |  | NA | 894 | 893 |  | -19.69d | No | Yes | Yes | No | No | 1.1.1.7.1.8 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.9 | Auto Scheduled | 0% | Manual Technical Tasks | No | 1d | Mon 6/15/26 | Mon 6/15/26 | Basis | 111SS | 114 |  | NA | System Setup | Mon 6/15/26 | Mon 6/15/26 | 1.1.1.7.1.7[SS] | Fri 7/3/26 | Mon 7/6/26 | As Soon As Possible | 1.1.1.7.1.10 | NA | 895 | 893SS | 896 | -36.25d | No | Yes | Yes | No | No | 1.1.1.7.1.9 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.10 | Auto Scheduled | 0% | Validate Fiori | No | 1d | Tue 6/16/26 | Tue 6/16/26 | Basis | 113 | 116SS,117SS,115SS |  | NA | System Setup | Tue 6/16/26 | Tue 6/16/26 | 1.1.1.7.1.9 | Mon 7/6/26 | Tue 7/7/26 | As Soon As Possible | 1.1.1.7.1.12[SS],1.1.1.7.1.13[SS],1.1.1.7.1.11[SS] | NA | 896 | 895 | 898SS,899SS,897SS | -36.25d | No | Yes | Yes | No | No | 1.1.1.7.1.10 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.11 | Auto Scheduled | 0% | Fiori App Activation | No | 1d | Tue 6/16/26 | Tue 6/16/26 | Dev Team | 114SS |  |  | NA | System Setup | Tue 6/16/26 | Tue 6/16/26 | 1.1.1.7.1.10[SS] | Tue 7/7/26 | Tue 7/7/26 | As Soon As Possible |  | NA | 897 | 896SS |  | -19.69d | No | Yes | Yes | No | No | 1.1.1.7.1.11 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.12 | Auto Scheduled | 0% | Download Transport List | No | 1h | Tue 6/16/26 | Tue 6/16/26 | Basis | 114SS |  |  | NA | System Setup | Tue 6/16/26 | Tue 6/16/26 | 1.1.1.7.1.10[SS] | Tue 7/7/26 | Tue 7/7/26 | As Soon As Possible |  | NA | 898 | 896SS |  | -150.52h | No | Yes | Yes | No | No | 1.1.1.7.1.12 | 6 | No | 500 | Future Task | No | 0h
1.1.1.7.1.13 | Auto Scheduled | 0% | Business Functions Validation | No | 1d | Tue 6/16/26 | Tue 6/16/26 | Basis | 114SS | 118SS,120SS |  | NA | System Setup | Tue 6/16/26 | Tue 6/16/26 | 1.1.1.7.1.10[SS] | Tue 7/7/26 | Wed 7/8/26 | Start No Earlier Than | 1.1.1.7.1.14[SS],1.1.1.7.2[SS] | Mon 1/5/26 | 899 | 896SS | 900SS,902SS | -36.25d | No | Yes | Yes | No | No | 1.1.1.7.1.13 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.14 | Auto Scheduled | 0% | Functional Leads Validation of Transport List | No | 1d | Tue 6/16/26 | Tue 6/16/26 | Functional Leads | 117SS | 119 |  | NA | System Setup | Tue 6/16/26 | Tue 6/16/26 | 1.1.1.7.1.13[SS] | Tue 7/7/26 | Tue 7/7/26 | As Soon As Possible | 1.1.1.7.1.15 | NA | 900 | 899SS | 901 | -36.25d | No | Yes | Yes | No | No | 1.1.1.7.1.14 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.1.15 | Auto Scheduled | 0% | Release Security roles to Functional Team | No | 1h | Wed 6/17/26 | Wed 6/17/26 | Security | 118 | 121SS |  | NA | System Setup | Wed 6/17/26 | Wed 6/17/26 | 1.1.1.7.1.14 | Tue 7/7/26 | Tue 7/7/26 | As Soon As Possible | 1.1.1.7.2.1[SS] | NA | 901 | 900 | 903SS | -290.02h | No | Yes | Yes | No | No | 1.1.1.7.1.15 | 6 | No | 500 | Future Task | No | 0h
1.1.1.7.2 | Auto Scheduled | 0% | Release Transports to Client | No | 5.5d | Wed 6/17/26 | Wed 6/24/26 |  | 117SS | 135 |  | NA | QS4 UAT Refresh | Wed 6/17/26 | Wed 6/24/26 | 1.1.1.7.1.13[SS] | Tue 7/7/26 | Tue 7/14/26 | As Soon As Possible | 1.1.1.8.1 | NA | 902 | 899SS | 3368 | -36.25d | Yes | Yes | Yes | No | No | 1.1.1.7.2 | 5 | No | 500 | Future Task | No | 0d
1.1.1.7.2.1 | Auto Scheduled | 0% | Import Group 1 - Ent Structure | No | 2h | Wed 6/17/26 | Wed 6/17/26 | Functional Leads | 119SS | 122 |  | NA | Release Transports to Client | Wed 6/17/26 | Wed 6/17/26 | 1.1.1.7.1.15[SS] | Tue 7/7/26 | Tue 7/7/26 | As Soon As Possible | 1.1.1.7.2.2 | NA | 903 | 901SS | 904 | -290.02h | No | Yes | Yes | No | No | 1.1.1.7.2.1 | 6 | No | 500 | Future Task | No | 0h
1.1.1.7.2.2 | Auto Scheduled | 0% | Manual activities group 1 | No | 20h | Wed 6/17/26 | Fri 6/19/26 | Functional Leads | 121 | 123 |  | NA | Release Transports to Client | Wed 6/17/26 | Fri 6/19/26 | 1.1.1.7.2.1 | Tue 7/7/26 | Fri 7/10/26 | As Soon As Possible | 1.1.1.7.2.3 | NA | 904 | 903 | 905 | -290.02h | No | Yes | Yes | No | No | 1.1.1.7.2.2 | 6 | No | 500 | Future Task | No | 0h
1.1.1.7.2.3 | Auto Scheduled | 0% | Import Group 2 - Core Transports | No | 2h | Fri 6/19/26 | Fri 6/19/26 | Functional Leads | 122 | 124 |  | NA | Release Transports to Client | Fri 6/19/26 | Fri 6/19/26 | 1.1.1.7.2.2 | Fri 7/10/26 | Fri 7/10/26 | As Soon As Possible | 1.1.1.7.2.4 | NA | 905 | 904 | 906 | -290.02h | No | Yes | Yes | No | No | 1.1.1.7.2.3 | 6 | No | 500 | Future Task | No | 0h
1.1.1.7.2.4 | Auto Scheduled | 0% | Manual activities group 2 | No | 1d | Mon 6/22/26 | Mon 6/22/26 | Functional Leads | 123 | 125 |  | NA | Release Transports to Client | Mon 6/22/26 | Mon 6/22/26 | 1.1.1.7.2.3 | Fri 7/10/26 | Mon 7/13/26 | As Soon As Possible | 1.1.1.7.2.5 | NA | 906 | 905 | 907 | -36.25d | No | Yes | Yes | No | No | 1.1.1.7.2.4 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.2.5 | Auto Scheduled | 0% | Import Group 3 - prior to transactions | No | 2h | Tue 6/23/26 | Tue 6/23/26 | Functional Leads | 124 | 126 |  | NA | Release Transports to Client | Tue 6/23/26 | Tue 6/23/26 | 1.1.1.7.2.4 | Mon 7/13/26 | Mon 7/13/26 | As Soon As Possible | 1.1.1.7.2.6 | NA | 907 | 906 | 908 | -290.02h | No | Yes | Yes | No | No | 1.1.1.7.2.5 | 6 | No | 500 | Future Task | No | 0h
1.1.1.7.2.6 | Auto Scheduled | 0% | Manual Activities Group 3 | No | 1d | Tue 6/23/26 | Wed 6/24/26 | Functional Leads | 125 | 127 |  | NA | Release Transports to Client | Tue 6/23/26 | Wed 6/24/26 | 1.1.1.7.2.5 | Mon 7/13/26 | Tue 7/14/26 | As Soon As Possible | 1.1.1.7.2.7 | NA | 908 | 907 | 909 | -36.25d | No | Yes | Yes | No | No | 1.1.1.7.2.6 | 6 | No | 500 | Future Task | No | 0d
1.1.1.7.2.7 | Auto Scheduled | 0% | Import Group 4 - workbench / dev work | No | 2h | Wed 6/24/26 | Wed 6/24/26 | Dev Team | 126 | 128SS |  | NA | Release Transports to Client | Wed 6/24/26 | Wed 6/24/26 | 1.1.1.7.2.6 | Tue 7/14/26 | Tue 7/14/26 | As Soon As Possible | 1.1.1.7.2.8[SS] | NA | 909 | 908 | 910SS | -290.02h | No | Yes | Yes | No | No | 1.1.1.7.2.7 | 6 | No | 500 | Future Task | No | 0h
1.1.1.7.2.8 | Auto Scheduled | 0% | Import Group 5 - Config to support dev workbench | No | 2h | Wed 6/24/26 | Wed 6/24/26 | Dev Team | 127SS | 130 |  | NA | Release Transports to Client | Wed 6/24/26 | Wed 6/24/26 | 1.1.1.7.2.7[SS] | Wed 7/15/26 | Wed 7/15/26 | As Soon As Possible | 1.1.1.7.3.1 | NA | 910 | 909SS | 1228 | -290.02h | No | Yes | Yes | No | No | 1.1.1.7.2.8 | 6 | No | 500 | Future Task | No | 0h
1.1.1.7.3 | Auto Scheduled | 0% | Data Project Create | No | 0.5d | Wed 6/24/26 | Wed 6/24/26 |  |  |  |  | NA | QS4 UAT Refresh | Wed 6/24/26 | Wed 6/24/26 |  | Wed 7/15/26 | Thu 7/16/26 | As Soon As Possible |  | NA | 1227 |  |  | -25.69d | Yes | Yes | Yes | No | No | 1.1.1.7.3 | 5 | No | 500 | Future Task | No | 0d
1.1.1.7.3.1 | Auto Scheduled | 0% | Open Client | No | 15m | Wed 6/24/26 | Wed 6/24/26 | Basis | 128 | 131SS,132 |  | NA | Data Project Create | Wed 6/24/26 | Wed 6/24/26 | 1.1.1.7.2.8 | Wed 7/15/26 | Wed 7/15/26 | As Soon As Possible | 1.1.1.7.3.2[SS],1.1.1.7.3.3 | NA | 1228 | 910 | 1229SS,1230 | -12331m | No | Yes | Yes | No | No | 1.1.1.7.3.1 | 6 | No | 500 | Future Task | No | 0m
1.1.1.7.3.2 | Auto Scheduled | 0% | Create Migration Data Project in DMC | No | 4h | Wed 6/24/26 | Wed 6/24/26 | Data Migration Team | 130SS |  |  | NA | Data Project Create | Wed 6/24/26 | Wed 6/24/26 | 1.1.1.7.3.1[SS] | Wed 7/15/26 | Thu 7/16/26 | As Soon As Possible |  | NA | 1229 | 1228SS |  | -205.52h | No | Yes | Yes | No | No | 1.1.1.7.3.2 | 6 | No | 500 | Future Task | No | 0h
1.1.1.7.3.3 | Auto Scheduled | 0% | Close Client | No | 15m | Wed 6/24/26 | Wed 6/24/26 | Basis | 130 | 133 |  | NA | Data Project Create | Wed 6/24/26 | Wed 6/24/26 | 1.1.1.7.3.1 | Thu 7/16/26 | Thu 7/16/26 | As Soon As Possible | 1.1.1.7.4 | NA | 1230 | 1228 | 912 | -12121m | No | Yes | Yes | No | No | 1.1.1.7.3.3 | 6 | No | 500 | Future Task | No | 0m
1.1.1.7.4 | Auto Scheduled | 0% | Environment Ready for Build | No | 0m | Wed 6/24/26 | Wed 6/24/26 | PMO | 132 |  |  | NA | QS4 UAT Refresh | Wed 6/24/26 | Wed 6/24/26 | 1.1.1.7.3.3 | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 912 | 1230 |  | -12121m | No | Yes | Yes | Yes | No | 1.1.1.7.4 | 5 | No | 500 | Future Task | No | 0m
1.1.1.8 | Auto Scheduled | 0% | P? Production System | No | 13.06d | Mon 9/7/26 | Thu 9/24/26 |  |  | 1.3891e+18 |  | NA | Environment Schedule | Mon 9/7/26 | Thu 9/24/26 |  | Thu 3/13/25 | Thu 7/16/26 | As Soon As Possible | 1.2.4,1.2.4.1,1.1.2.8.1,1.2.5,1.2.5.1 | NA | 3367 |  | 2.4222e+18 | -88.75d | Yes | Yes | Yes | No | No | 1.1.1.8 | 4 | No | 500 | Future Task | No | 0d
1.1.1.8.1 | Auto Scheduled | 0% | System Setup | No | 8d | Mon 9/7/26 | Wed 9/16/26 |  | 120 |  |  | NA | P? Production System | Mon 9/7/26 | Wed 9/16/26 | 1.1.1.7.2 | NA | NA | As Soon As Possible |  | NA | 3368 | 902 |  | -88.75d | Yes | Yes | Yes | No | No | 1.1.1.8.1 | 5 | No | 500 | Future Task | No | 0d
1.1.1.8.1.1 | Auto Scheduled | 0% | System Refresh Basis(Workinig with NS2) | No | 2d | Mon 9/7/26 | Tue 9/8/26 | Basis |  | 137 |  | NA | System Setup | Mon 9/7/26 | Tue 9/8/26 |  | Fri 6/19/26 | Fri 6/19/26 | Must Start On | 1.1.1.8.1.2 | Mon 9/7/26 | 3369 |  | 3370 | 0d | No | Yes | Yes | No | No | 1.1.1.8.1.1 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.2 | Auto Scheduled | 0% | Client Config / Validation | No | 2d | Wed 9/9/26 | Thu 9/10/26 | Basis | 136 | 138139 |  | NA | System Setup | Wed 9/9/26 | Thu 9/10/26 | 1.1.1.8.1.1 | Fri 6/26/26 | Mon 6/29/26 | As Soon As Possible | 1.1.1.8.1.3,1.1.1.8.1.4 | NA | 3370 | 3369 | 33713372 | -90.75d | No | Yes | Yes | No | No | 1.1.1.8.1.2 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.3 | Auto Scheduled | 0% | Technical Transports / BP Setup | No | 1d | Fri 9/11/26 | Fri 9/11/26 | Basis | 137 | 142 |  | NA | System Setup | Fri 9/11/26 | Fri 9/11/26 | 1.1.1.8.1.2 | Mon 6/29/26 | Tue 6/30/26 | As Soon As Possible | 1.1.1.8.1.7 | NA | 3371 | 3370 | 3375 | -90.75d | No | Yes | Yes | No | No | 1.1.1.8.1.3 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.4 | Auto Scheduled | 0% | Best Practice / Country Validation | No | 1d | Fri 9/11/26 | Fri 9/11/26 | Basis | 137 | 140142 |  | NA | System Setup | Fri 9/11/26 | Fri 9/11/26 | 1.1.1.8.1.2 | Tue 6/30/26 | Wed 7/1/26 | As Soon As Possible | 1.1.1.8.1.5,1.1.1.8.1.7 | NA | 3372 | 3370 | 33733375 | -90.75d | No | Yes | Yes | No | No | 1.1.1.8.1.4 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.5 | Auto Scheduled | 0% | Connect Systems and Validate | No | 2d | Mon 9/14/26 | Tue 9/15/26 | Basis | 139 | 141 |  | NA | System Setup | Mon 9/14/26 | Tue 9/15/26 | 1.1.1.8.1.4 | Wed 7/1/26 | Thu 7/2/26 | As Soon As Possible | 1.1.1.8.1.6 | NA | 3373 | 3372 | 3374 | -85.69d | No | Yes | Yes | No | No | 1.1.1.8.1.5 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.6 | Auto Scheduled | 0% | Validate Syniti Connections to QS5 | No | 1d | Wed 9/16/26 | Wed 9/16/26 | Data | 140 |  |  | NA | System Setup | Wed 9/16/26 | Wed 9/16/26 | 1.1.1.8.1.5 | Thu 7/2/26 | Fri 7/3/26 | As Soon As Possible |  | NA | 3374 | 3373 |  | -85.69d | No | Yes | Yes | No | No | 1.1.1.8.1.6 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.7 | Auto Scheduled | 0% | Security Transports | No | 1d | Mon 9/14/26 | Mon 9/14/26 | Security | 138139 | 144SS,143 |  | NA | System Setup | Mon 9/14/26 | Mon 9/14/26 | 1.1.1.8.1.3,1.1.1.8.1.4 | Fri 7/3/26 | Fri 7/3/26 | As Soon As Possible | 1.1.1.8.1.9[SS],1.1.1.8.1.8 | NA | 3375 | 33713372 | 3377SS,3376 | -90.75d | No | Yes | Yes | No | No | 1.1.1.8.1.7 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.8 | Auto Scheduled | 0% | Security Manual Tasks | No | 1d | Tue 9/15/26 | Tue 9/15/26 | Security | 142 |  |  | NA | System Setup | Tue 9/15/26 | Tue 9/15/26 | 1.1.1.8.1.7 | Fri 7/3/26 | Mon 7/6/26 | As Soon As Possible |  | NA | 3376 | 3375 |  | -84.69d | No | Yes | Yes | No | No | 1.1.1.8.1.8 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.9 | Auto Scheduled | 0% | Manual Technical Tasks | No | 1d | Mon 9/14/26 | Mon 9/14/26 | Basis | 142SS | 145 |  | NA | System Setup | Mon 9/14/26 | Mon 9/14/26 | 1.1.1.8.1.7[SS] | Fri 7/3/26 | Mon 7/6/26 | As Soon As Possible | 1.1.1.8.1.10 | NA | 3377 | 3375SS | 3378 | -90.75d | No | Yes | Yes | No | No | 1.1.1.8.1.9 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.10 | Auto Scheduled | 0% | Validate Fiori | No | 1d | Tue 9/15/26 | Tue 9/15/26 | Basis | 144 | 147,148SS,146SS,149SS |  | NA | System Setup | Tue 9/15/26 | Tue 9/15/26 | 1.1.1.8.1.9 | Mon 7/6/26 | Tue 7/7/26 | As Soon As Possible | 1.1.1.8.1.12,1.1.1.8.1.13[SS],1.1.1.8.1.11[SS],1.1.1.8.1.14[SS] | NA | 3378 | 3377 | 3380,3381SS,3379SS,3382SS | -90.75d | No | Yes | Yes | No | No | 1.1.1.8.1.10 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.11 | Auto Scheduled | 0% | Fiori App Activation | No | 1d | Tue 9/15/26 | Tue 9/15/26 | Dev Team | 145SS |  |  | NA | System Setup | Tue 9/15/26 | Tue 9/15/26 | 1.1.1.8.1.10[SS] | Tue 7/7/26 | Tue 7/7/26 | As Soon As Possible |  | NA | 3379 | 3378SS |  | -84.69d | No | Yes | Yes | No | No | 1.1.1.8.1.11 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.12 | Auto Scheduled | 0% | Download Transport List | No | 1h | Wed 9/16/26 | Wed 9/16/26 | Basis | 145 |  |  | NA | System Setup | Wed 9/16/26 | Wed 9/16/26 | 1.1.1.8.1.10 | Tue 7/7/26 | Tue 7/7/26 | As Soon As Possible |  | NA | 3380 | 3378 |  | -678.52h | No | Yes | Yes | No | No | 1.1.1.8.1.12 | 6 | No | 500 | Future Task | No | 0h
1.1.1.8.1.13 | Auto Scheduled | 0% | Business Functions Validation | No | 1d | Tue 9/15/26 | Tue 9/15/26 | Basis | 145SS |  |  | NA | System Setup | Tue 9/15/26 | Tue 9/15/26 | 1.1.1.8.1.10[SS] | Tue 7/7/26 | Wed 7/8/26 | Start No Earlier Than |  | Mon 1/5/26 | 3381 | 3378SS |  | -84.69d | No | Yes | Yes | No | No | 1.1.1.8.1.13 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.14 | Auto Scheduled | 0% | Functional Leads Validation of Transport List | No | 1d | Tue 9/15/26 | Tue 9/15/26 | Functional Leads | 145SS | 151152150 |  | NA | System Setup | Tue 9/15/26 | Tue 9/15/26 | 1.1.1.8.1.10[SS] | Tue 7/7/26 | Tue 7/7/26 | As Soon As Possible | 1.1.1.8.2,1.1.1.8.2.1,1.1.1.8.1.15 | NA | 3382 | 3378SS | 338433853383 | -90.75d | No | Yes | Yes | No | No | 1.1.1.8.1.14 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.1.15 | Auto Scheduled | 0% | Release Security roles to Functional Team | No | 1h | Wed 9/16/26 | Wed 9/16/26 | Security | 149 |  |  | NA | System Setup | Wed 9/16/26 | Wed 9/16/26 | 1.1.1.8.1.14 | Tue 7/7/26 | Tue 7/7/26 | As Soon As Possible |  | NA | 3383 | 3382 |  | -678.52h | No | Yes | Yes | No | No | 1.1.1.8.1.15 | 6 | No | 500 | Future Task | No | 0h
1.1.1.8.2 | Auto Scheduled | 0% | Release Transports to Client | No | 5.5d | Wed 9/16/26 | Wed 9/23/26 |  | 149 |  |  | NA | P? Production System | Wed 9/16/26 | Wed 9/23/26 | 1.1.1.8.1.14 | Tue 7/7/26 | Tue 7/14/26 | As Soon As Possible |  | NA | 3384 | 3382 |  | -90.75d | Yes | Yes | Yes | No | No | 1.1.1.8.2 | 5 | No | 500 | Future Task | No | 0d
1.1.1.8.2.1 | Auto Scheduled | 0% | Import Group 1 - Ent Structure | No | 2h | Wed 9/16/26 | Wed 9/16/26 | Functional Leads | 149 | 153 |  | NA | Release Transports to Client | Wed 9/16/26 | Wed 9/16/26 | 1.1.1.8.1.14 | Tue 7/7/26 | Tue 7/7/26 | As Soon As Possible | 1.1.1.8.2.2 | NA | 3385 | 3382 | 3386 | -726.02h | No | Yes | Yes | No | No | 1.1.1.8.2.1 | 6 | No | 500 | Future Task | No | 0h
1.1.1.8.2.2 | Auto Scheduled | 0% | Manual activities group 1 | No | 20h | Wed 9/16/26 | Fri 9/18/26 | Functional Leads | 152 | 154 |  | NA | Release Transports to Client | Wed 9/16/26 | Fri 9/18/26 | 1.1.1.8.2.1 | Tue 7/7/26 | Fri 7/10/26 | Finish No Earlier Than | 1.1.1.8.2.3 | Wed 2/11/26 | 3386 | 3385 | 3387 | -726.02h | No | Yes | Yes | No | No | 1.1.1.8.2.2 | 6 | No | 500 | Future Task | No | 0h
1.1.1.8.2.3 | Auto Scheduled | 0% | Import Group 2 - Core Transports | No | 2h | Fri 9/18/26 | Fri 9/18/26 | Functional Leads | 153 | 155 |  | NA | Release Transports to Client | Fri 9/18/26 | Fri 9/18/26 | 1.1.1.8.2.2 | Fri 7/10/26 | Fri 7/10/26 | As Soon As Possible | 1.1.1.8.2.4 | NA | 3387 | 3386 | 3388 | -726.02h | No | Yes | Yes | No | No | 1.1.1.8.2.3 | 6 | No | 500 | Future Task | No | 0h
1.1.1.8.2.4 | Auto Scheduled | 0% | Manual activities group 2 | No | 1d | Mon 9/21/26 | Mon 9/21/26 | Functional Leads | 154 | 156 |  | NA | Release Transports to Client | Mon 9/21/26 | Mon 9/21/26 | 1.1.1.8.2.3 | Fri 7/10/26 | Mon 7/13/26 | As Soon As Possible | 1.1.1.8.2.5 | NA | 3388 | 3387 | 3389 | -90.75d | No | Yes | Yes | No | No | 1.1.1.8.2.4 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.2.5 | Auto Scheduled | 0% | Import Group 3 - prior to transactions | No | 2h | Tue 9/22/26 | Tue 9/22/26 | Functional Leads | 155 | 157 |  | NA | Release Transports to Client | Tue 9/22/26 | Tue 9/22/26 | 1.1.1.8.2.4 | Mon 7/13/26 | Mon 7/13/26 | As Soon As Possible | 1.1.1.8.2.6 | NA | 3389 | 3388 | 3390 | -726.02h | No | Yes | Yes | No | No | 1.1.1.8.2.5 | 6 | No | 500 | Future Task | No | 0h
1.1.1.8.2.6 | Auto Scheduled | 0% | Manual Activities Group 3 | No | 1d | Tue 9/22/26 | Wed 9/23/26 | Functional Leads | 156 | 158 |  | NA | Release Transports to Client | Tue 9/22/26 | Wed 9/23/26 | 1.1.1.8.2.5 | Mon 7/13/26 | Tue 7/14/26 | As Soon As Possible | 1.1.1.8.2.7 | NA | 3390 | 3389 | 3391 | -90.75d | No | Yes | Yes | No | No | 1.1.1.8.2.6 | 6 | No | 500 | Future Task | No | 0d
1.1.1.8.2.7 | Auto Scheduled | 0% | Import Group 4 - workbench / dev work | No | 2h | Wed 9/23/26 | Wed 9/23/26 | Dev Team | 157 | 159SS |  | NA | Release Transports to Client | Wed 9/23/26 | Wed 9/23/26 | 1.1.1.8.2.6 | Tue 7/14/26 | Tue 7/14/26 | Start No Earlier Than | 1.1.1.8.2.8[SS] | Thu 4/3/25 | 3391 | 3390 | 3392SS | -726.02h | No | Yes | Yes | No | No | 1.1.1.8.2.7 | 6 | No | 500 | Future Task | No | 0h
1.1.1.8.2.8 | Auto Scheduled | 0% | Import Group 5 - Config to support dev workbench | No | 2h | Wed 9/23/26 | Wed 9/23/26 | Dev Team | 158SS | 161 |  | NA | Release Transports to Client | Wed 9/23/26 | Wed 9/23/26 | 1.1.1.8.2.7[SS] | Wed 7/15/26 | Wed 7/15/26 | As Soon As Possible | 1.1.1.8.3.1 | NA | 3392 | 3391SS | 3394 | -726.02h | No | Yes | Yes | No | No | 1.1.1.8.2.8 | 6 | No | 500 | Future Task | No | 0h
1.1.1.8.3 | Auto Scheduled | 0% | Data Project Create | No | 0.56d | Wed 9/23/26 | Thu 9/24/26 |  |  | 164 |  | NA | P? Production System | Wed 9/23/26 | Thu 9/24/26 |  | Wed 7/15/26 | Thu 7/16/26 | As Soon As Possible | 1.1.1.8.4 | NA | 3393 |  | 3397 | -90.75d | Yes | Yes | Yes | No | No | 1.1.1.8.3 | 5 | No | 500 | Future Task | No | 0d
1.1.1.8.3.1 | Auto Scheduled | 0% | Open Client | No | 15m | Wed 9/23/26 | Wed 9/23/26 | Basis | 159 | 162 |  | NA | Data Project Create | Wed 9/23/26 | Wed 9/23/26 | 1.1.1.8.2.8 | Wed 7/15/26 | Wed 7/15/26 | As Soon As Possible | 1.1.1.8.3.2 | NA | 3394 | 3392 | 3395 | -43561m | No | Yes | Yes | No | No | 1.1.1.8.3.1 | 6 | No | 500 | Future Task | No | 0m
1.1.1.8.3.2 | Auto Scheduled | 0% | Create Migration Data Project in DMC | No | 4h | Wed 9/23/26 | Thu 9/24/26 | Data Migration Team | 161 | 163 |  | NA | Data Project Create | Wed 9/23/26 | Thu 9/24/26 | 1.1.1.8.3.1 | Wed 7/15/26 | Thu 7/16/26 | As Soon As Possible | 1.1.1.8.3.3 | NA | 3395 | 3394 | 3396 | -726.02h | No | Yes | Yes | No | No | 1.1.1.8.3.2 | 6 | No | 500 | Future Task | No | 0h
1.1.1.8.3.3 | Auto Scheduled | 0% | Close Client | No | 15m | Thu 9/24/26 | Thu 9/24/26 | Basis | 162 |  |  | NA | Data Project Create | Thu 9/24/26 | Thu 9/24/26 | 1.1.1.8.3.2 | Thu 7/16/26 | Thu 7/16/26 | As Soon As Possible |  | NA | 3396 | 3395 |  | -43561m | No | Yes | Yes | No | No | 1.1.1.8.3.3 | 6 | No | 500 | Future Task | No | 0m
1.1.1.8.4 | Auto Scheduled | 0% | Environment Ready for Build | No | 0m | Thu 9/24/26 | Thu 9/24/26 | PMO | 160 |  |  | NA | P? Production System | Thu 9/24/26 | Thu 9/24/26 | 1.1.1.8.3 | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 3397 | 3393 |  | -43561m | No | Yes | Yes | Yes | No | 1.1.1.8.4 | 5 | No | 500 | Future Task | No | 0m
1.1.1.9 | Auto Scheduled | 0% | Prod (PS4) Setup | No | 17d | Mon 9/7/26 | Tue 9/29/26 |  |  |  |  | NA | Environment Schedule | Mon 9/7/26 | Tue 9/29/26 |  | Thu 3/13/25 | Mon 4/7/25 | Start No Earlier Than |  | Mon 9/7/26 | 201 |  |  | 29d | No | Yes | No | No | No | 1.1.1.9 | 4 | No | 500 | Future Task | No | 29d
1.1.2 | Auto Scheduled | 88% | GRC Security Utility | No | 439d? | Mon 2/17/25 | Thu 10/22/26 |  |  |  |  | Mon 2/17/25 | System Readiness | Mon 2/17/25 | Thu 10/22/26 |  | Mon 2/17/25 | Mon 4/6/26 | As Soon As Possible |  | NA | 248 |  |  | 12d? | Yes | Yes | No | No | No | 1.1.2 | 3 | No | 500 | Complete | No | 12d?
1.1.2.1 | Auto Scheduled | 100% | Initiation & Planning | No | 262d | Mon 2/17/25 | Tue 2/17/26 |  |  |  |  | Mon 2/17/25 | GRC Security Utility | Mon 2/17/25 | Tue 2/17/26 |  | Mon 2/17/25 | Tue 2/17/26 | As Soon As Possible |  | NA | 299 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.1 | 4 | No | 500 | Complete | No | 0d
1.1.2.1.1 | Auto Scheduled | 100% | Project kickoff | No | 1d | Wed 7/16/25 | Wed 7/16/25 |  |  |  |  | Wed 7/16/25 | Initiation & Planning | Wed 7/16/25 | Wed 7/16/25 |  | Wed 7/16/25 | Wed 7/16/25 | Start No Earlier Than |  | Wed 7/16/25 | 249 |  |  | 0d | No | Yes | No | No | No | 1.1.2.1.1 | 5 | No | 500 | Complete | No | 0d
1.1.2.1.2 | Auto Scheduled | 100% | Requirement gathering | No | 130d | Mon 2/17/25 | Fri 8/15/25 |  |  | 170 |  | Mon 2/17/25 | Initiation & Planning | Mon 2/17/25 | Fri 8/15/25 |  | Mon 2/17/25 | Fri 8/15/25 | Start No Earlier Than | 1.1.2.1.3 | Sun 2/16/25 | 250 |  | 251 | 0d | No | Yes | No | No | No | 1.1.2.1.2 | 5 | No | 500 | Complete | No | 0d
1.1.2.1.3 | Auto Scheduled | 100% | Landscape design | No | 2d | Mon 8/18/25 | Tue 8/19/25 |  | 169 |  |  | Mon 8/18/25 | Initiation & Planning | Mon 8/18/25 | Tue 8/19/25 | 1.1.2.1.2 | Mon 8/18/25 | Tue 8/19/25 | Finish No Earlier Than |  | Tue 8/19/25 | 251 | 250 |  | 0d | No | Yes | No | No | No | 1.1.2.1.3 | 5 | No | 500 | Complete | No | 0d
1.1.2.1.4 | Auto Scheduled | 100% | Project plan finalization | No | 2d | Mon 2/16/26 | Tue 2/17/26 |  |  | 174 |  | Mon 2/16/26 | Initiation & Planning | Mon 2/16/26 | Tue 2/17/26 |  | Mon 2/16/26 | Tue 2/17/26 | Start No Earlier Than | 1.1.2.2.2 | Mon 2/16/26 | 252 |  | 258 | 0d | No | Yes | No | No | No | 1.1.2.1.4 | 5 | No | 500 | Complete | No | 0d
1.1.2.2 | Auto Scheduled | 100% | System Setup & Connectivity | No | 171d | Mon 7/28/25 | Mon 3/23/26 |  |  |  |  | Mon 7/28/25 | GRC Security Utility | Mon 7/28/25 | Mon 3/23/26 |  | Mon 7/28/25 | Mon 3/23/26 | As Soon As Possible |  | NA | 253 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.2 | 4 | No | 500 | Complete | No | 0d
1.1.2.2.1 | Auto Scheduled | 100% | Install GRC AC components | No | 5d | Mon 7/28/25 | Fri 8/1/25 |  |  |  |  | Mon 7/28/25 | System Setup & Connectivity | Mon 7/28/25 | Fri 8/1/25 |  | Mon 7/28/25 | Fri 8/1/25 | Start No Earlier Than |  | Mon 7/28/25 | 254 |  |  | 0d | No | Yes | No | No | No | 1.1.2.2.1 | 5 | No | 500 | Complete | No | 0d
1.1.2.2.2 | Auto Scheduled | 100% | Install plug-ins on target systems | No | 5d | Wed 2/18/26 | Tue 2/24/26 |  | 171 | 175 |  | Wed 2/18/26 | System Setup & Connectivity | Wed 2/18/26 | Tue 2/24/26 | 1.1.2.1.4 | Wed 2/18/26 | Tue 2/24/26 | As Soon As Possible | 1.1.2.2.3 | NA | 258 | 252 | 259 | 0d | No | Yes | No | No | No | 1.1.2.2.2 | 5 | No | 500 | Complete | No | 0d
1.1.2.2.3 | Auto Scheduled | 100% | Post installation Steps | No | 5d | Wed 2/25/26 | Tue 3/3/26 |  | 174 | 176 |  | Wed 2/25/26 | System Setup & Connectivity | Wed 2/25/26 | Tue 3/3/26 | 1.1.2.2.2 | Wed 2/25/26 | Tue 3/3/26 | As Soon As Possible | 1.1.2.2.4 | NA | 259 | 258 | 260 | 0d | No | Yes | No | No | No | 1.1.2.2.3 | 5 | No | 500 | Complete | No | 0d
1.1.2.2.4 | Auto Scheduled | 100% | Activate BC Sets | No | 2d | Wed 3/4/26 | Thu 3/5/26 |  | 175 | 177 |  | Wed 3/4/26 | System Setup & Connectivity | Wed 3/4/26 | Thu 3/5/26 | 1.1.2.2.3 | Wed 3/4/26 | Thu 3/5/26 | As Soon As Possible | 1.1.2.2.5 | NA | 260 | 259 | 261 | 0d | No | Yes | No | No | No | 1.1.2.2.4 | 5 | No | 500 | Complete | No | 0d
1.1.2.2.5 | Auto Scheduled | 100% | Connector configuration (S4 / LDAP Connector) | No | 5d | Fri 3/6/26 | Thu 3/12/26 |  | 176 | 178 |  | Fri 3/6/26 | System Setup & Connectivity | Fri 3/6/26 | Thu 3/12/26 | 1.1.2.2.4 | Fri 3/6/26 | Thu 3/12/26 | As Soon As Possible | 1.1.2.2.6 | NA | 261 | 260 | 262 | 0d | No | Yes | No | No | No | 1.1.2.2.5 | 5 | No | 500 | Complete | No | 0d
1.1.2.2.6 | Auto Scheduled | 100% | Initial configuration [GRC Parameter/Business Process/Sub Process and system Configuration] | No | 6d | Fri 3/13/26 | Fri 3/20/26 |  | 177 | 179 |  | Fri 3/13/26 | System Setup & Connectivity | Fri 3/13/26 | Fri 3/20/26 | 1.1.2.2.5 | Fri 3/13/26 | Fri 3/20/26 | As Soon As Possible | 1.1.2.2.7 | NA | 262 | 261 | 263 | 0d | No | Yes | No | No | No | 1.1.2.2.6 | 5 | No | 500 | Complete | No | 0d
1.1.2.2.7 | Auto Scheduled | 100% | Transport setup | No | 1d | Mon 3/23/26 | Mon 3/23/26 |  | 178 | 181 |  | Mon 3/23/26 | System Setup & Connectivity | Mon 3/23/26 | Mon 3/23/26 | 1.1.2.2.6 | Mon 3/23/26 | Mon 3/23/26 | As Soon As Possible | 1.1.2.3.1 | NA | 263 | 262 | 265 | 0d | No | Yes | No | No | No | 1.1.2.2.7 | 5 | No | 500 | Complete | No | 0d
1.1.2.3 | Auto Scheduled | 100% | Workflow setup | No | 10d | Tue 3/24/26 | Mon 4/6/26 |  |  |  |  | Tue 3/24/26 | GRC Security Utility | Tue 3/24/26 | Mon 4/6/26 |  | Tue 3/24/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 264 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.3 | 4 | No | 500 | Complete | No | 0d
1.1.2.3.1 | Auto Scheduled | 100% | MSMP workflow configuration | No | 5d | Tue 3/24/26 | Mon 3/30/26 |  | 179 | 182 |  | Tue 3/24/26 | Workflow setup | Tue 3/24/26 | Mon 3/30/26 | 1.1.2.2.7 | Tue 3/24/26 | Mon 3/30/26 | As Soon As Possible | 1.1.2.3.2 | NA | 265 | 263 | 266 | 0d | No | Yes | No | No | No | 1.1.2.3.1 | 5 | No | 500 | Complete | No | 0d
1.1.2.3.2 | Auto Scheduled | 100% | BRF+ decision tables | No | 5d | Tue 3/31/26 | Mon 4/6/26 |  | 181 |  |  | Tue 3/31/26 | Workflow setup | Tue 3/31/26 | Mon 4/6/26 | 1.1.2.3.1 | Tue 3/31/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 266 | 265 |  | 0d | No | Yes | No | No | No | 1.1.2.3.2 | 5 | No | 500 | Complete | No | 0d
1.1.2.4 | Auto Scheduled | 77% | Rule Set & Role Design | No | 311d? | Thu 3/13/25 | Thu 5/21/26 |  |  |  |  | Thu 3/13/25 | GRC Security Utility | Thu 3/13/25 | Thu 5/21/26 |  | Thu 3/13/25 | Wed 12/10/25 | As Soon As Possible |  | NA | 267 |  |  | 122d? | Yes | Yes | No | No | No | 1.1.2.4 | 4 | No | 500 | Complete | No | 122d?
1.1.2.4.1 | Auto Scheduled | 100% | Extract the default Global Ruleset from SAP | No | 4d | Tue 9/2/25 | Fri 9/5/25 |  |  | 185 |  | Tue 9/2/25 | Rule Set & Role Design | Tue 9/2/25 | Fri 9/5/25 |  | Tue 9/2/25 | Fri 9/5/25 | Start No Earlier Than | 1.1.2.4.2 | Tue 9/2/25 | 268 |  | 269 | 0d | No | Yes | No | No | No | 1.1.2.4.1 | 5 | No | 500 | Complete | No | 0d
1.1.2.4.2 | Auto Scheduled | 100% | Extract SU24 Details of transactions from global ruleset and Custom Transactions | No | 7d | Mon 9/8/25 | Tue 9/16/25 |  | 184 | 186 |  | Mon 9/8/25 | Rule Set & Role Design | Mon 9/8/25 | Tue 9/16/25 | 1.1.2.4.1 | Mon 9/8/25 | Tue 9/16/25 | As Soon As Possible | 1.1.2.4.3 | NA | 269 | 268 | 281 | 0d | No | Yes | No | No | No | 1.1.2.4.2 | 5 | No | 500 | Complete | No | 0d
1.1.2.4.3 | Auto Scheduled | 100% | Prepare/Share the Ruleset Draft with all the functional leads for inputs | No | 6d | Wed 9/17/25 | Wed 9/24/25 |  | 185 | 187 |  | Wed 9/17/25 | Rule Set & Role Design | Wed 9/17/25 | Wed 9/24/25 | 1.1.2.4.2 | Wed 9/17/25 | Wed 9/24/25 | As Soon As Possible | 1.1.2.4.4 | NA | 281 | 269 | 282 | 0d | No | Yes | No | No | No | 1.1.2.4.3 | 5 | No | 500 | Complete | No | 0d
1.1.2.4.4 | Auto Scheduled | 100% | Schedule workshops to collect complete details of ruleset module wise and close the gaps | No | 26d | Thu 9/25/25 | Thu 10/30/25 |  | 186 | 188 |  | Thu 9/25/25 | Rule Set & Role Design | Thu 9/25/25 | Thu 10/30/25 | 1.1.2.4.3 | Thu 9/25/25 | Thu 10/30/25 | As Soon As Possible | 1.1.2.4.5 | NA | 282 | 281 | 283 | 0d | No | Yes | No | No | No | 1.1.2.4.4 | 5 | No | 500 | Complete | No | 0d
1.1.2.4.5 | Auto Scheduled | 60% | Final Review Rule Set and update the recommendations | No | 4d | Fri 10/31/25 | Wed 1/7/26 |  | 187 | 189 |  | Fri 10/31/25 | Rule Set & Role Design | Fri 10/31/25 | Wed 1/7/26 | 1.1.2.4.4 | Fri 10/31/25 | Wed 11/5/25 | As Soon As Possible | 1.1.2.4.6 | NA | 283 | 282 | 284 | 218.4d | No | Yes | No | No | No | 1.1.2.4.5 | 5 | No | 500 | Late | No | 218.4d
1.1.2.4.6 | Auto Scheduled | 100% | Import rulesets into system | No | 4d | Thu 11/6/25 | Tue 11/11/25 |  | 188 | 191 |  | Thu 11/6/25 | Rule Set & Role Design | Thu 11/6/25 | Tue 11/11/25 | 1.1.2.4.5 | Thu 11/6/25 | Tue 11/11/25 | As Soon As Possible | 1.1.2.4.8 | NA | 284 | 283 | 285 | 0d | No | Yes | No | No | No | 1.1.2.4.6 | 5 | No | 500 | Complete | No | 0d
1.1.2.4.7 | Auto Scheduled | 100% | RCM Development | No | 1d? | Thu 3/13/25 | Thu 3/13/25 | Controlling Team |  |  |  | Thu 3/13/25 | Rule Set & Role Design | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 303 |  |  | 0d? | No | Yes | No | No | No | 1.1.2.4.7 | 5 | No | 500 | Complete | No | 0d?
1.1.2.4.8 | Auto Scheduled | 100% | Setup Mitigation controls | No | 6d | Wed 11/12/25 | Wed 11/19/25 |  | 189 | 192 |  | Wed 11/12/25 | Rule Set & Role Design | Wed 11/12/25 | Wed 11/19/25 | 1.1.2.4.6 | Wed 11/12/25 | Wed 11/19/25 | As Soon As Possible | 1.1.2.4.9 | NA | 285 | 284 | 286 | 0d | No | Yes | No | No | No | 1.1.2.4.8 | 5 | No | 500 | Complete | No | 0d
1.1.2.4.9 | Auto Scheduled | 0% | Risk analysis on existing roles | No | 5d | Fri 5/1/26 | Thu 5/7/26 |  | 191 | 193195 |  | NA | Rule Set & Role Design | Fri 5/1/26 | Thu 5/7/26 | 1.1.2.4.8 | Thu 11/20/25 | Wed 11/26/25 | Start No Earlier Than | 1.1.2.4.10,1.1.2.5.1 | Thu 4/30/26 | 286 | 285 | 270272 | 122d | No | Yes | No | No | No | 1.1.2.4.9 | 5 | No | 500 | Future Task | No | 0d
1.1.2.4.10 | Auto Scheduled | 0% | Role remediation planning - Can impact role design & Possible of retesting. | No | 10d | Fri 5/8/26 | Thu 5/21/26 |  | 192 |  |  | NA | Rule Set & Role Design | Fri 5/8/26 | Thu 5/21/26 | 1.1.2.4.9 | Thu 11/27/25 | Wed 12/10/25 | Start No Earlier Than |  | Thu 4/30/26 | 270 | 286 |  | 122d | No | Yes | No | No | No | 1.1.2.4.10 | 5 | No | 500 | Future Task | No | 122d
1.1.2.5 | Auto Scheduled | 0% | Business Role Management | No | 10d | Fri 5/8/26 | Thu 5/21/26 |  |  |  |  | NA | GRC Security Utility | Fri 5/8/26 | Thu 5/21/26 |  | Thu 11/27/25 | Wed 12/10/25 | As Soon As Possible |  | NA | 271 |  |  | 122d | Yes | Yes | No | No | No | 1.1.2.5 | 4 | No | 500 | Future Task | No | 122d
1.1.2.5.1 | Auto Scheduled | 0% | Role Mapping with Business Process and Sub-Process /Functional Area | No | 5d | Fri 5/8/26 | Thu 5/14/26 |  | 192 | 196 |  | NA | Business Role Management | Fri 5/8/26 | Thu 5/14/26 | 1.1.2.4.9 | Thu 11/27/25 | Wed 12/3/25 | Start No Earlier Than | 1.1.2.5.2 | Thu 4/30/26 | 272 | 286 | 273 | 122d | No | Yes | No | No | No | 1.1.2.5.1 | 5 | No | 500 | Future Task | No | 0d
1.1.2.5.2 | Auto Scheduled | 0% | Role Upload to SAP GRC | No | 5d | Fri 5/15/26 | Thu 5/21/26 |  | 195 |  |  | NA | Business Role Management | Fri 5/15/26 | Thu 5/21/26 | 1.1.2.5.1 | Thu 12/4/25 | Wed 12/10/25 | Start No Earlier Than |  | Thu 4/30/26 | 273 | 272 |  | 122d | No | Yes | No | No | No | 1.1.2.5.2 | 5 | No | 500 | Future Task | No | 122d
1.1.2.6 | Auto Scheduled | 0% | Firefighter Configuration | No | 15d | Fri 5/1/26 | Thu 5/21/26 |  |  |  |  | NA | GRC Security Utility | Fri 5/1/26 | Thu 5/21/26 |  | Mon 10/20/25 | Fri 11/7/25 | As Soon As Possible |  | NA | 274 |  |  | 122d | Yes | Yes | No | No | No | 1.1.2.6 | 4 | No | 500 | Future Task | No | 122d
1.1.2.6.1 | Auto Scheduled | 0% | Firefighter ID setup | No | 5d | Fri 5/1/26 | Thu 5/7/26 |  |  | 199 |  | NA | Firefighter Configuration | Fri 5/1/26 | Thu 5/7/26 |  | Mon 10/20/25 | Fri 10/24/25 | Start No Earlier Than | 1.1.2.6.2 | Thu 4/30/26 | 275 |  | 276 | 122d | No | Yes | No | No | No | 1.1.2.6.1 | 5 | No | 500 | Future Task | No | 0d
1.1.2.6.2 | Auto Scheduled | 0% | Firefighter log settings | No | 5d | Fri 5/8/26 | Thu 5/14/26 |  | 198 | 200 |  | NA | Firefighter Configuration | Fri 5/8/26 | Thu 5/14/26 | 1.1.2.6.1 | Mon 10/27/25 | Fri 10/31/25 | Start No Earlier Than | 1.1.2.6.3 | Thu 4/30/26 | 276 | 275 | 277 | 122d | No | Yes | No | No | No | 1.1.2.6.2 | 5 | No | 500 | Future Task | No | 0d
1.1.2.6.3 | Auto Scheduled | 0% | Functional validation | No | 5d | Fri 5/15/26 | Thu 5/21/26 |  | 199 |  |  | NA | Firefighter Configuration | Fri 5/15/26 | Thu 5/21/26 | 1.1.2.6.2 | Mon 11/3/25 | Fri 11/7/25 | Start No Earlier Than |  | Thu 4/30/26 | 277 | 276 |  | 122d | No | Yes | No | No | No | 1.1.2.6.3 | 5 | No | 500 | Future Task | No | 122d
1.1.2.7 | Auto Scheduled | 0% | Testing & Training | No | 69d | Fri 5/1/26 | Wed 8/5/26 |  |  |  |  | NA | GRC Security Utility | Fri 5/1/26 | Wed 8/5/26 |  | Mon 11/10/25 | Thu 2/12/26 | As Soon As Possible |  | NA | 278 |  |  | 68d | Yes | Yes | No | No | No | 1.1.2.7 | 4 | No | 500 | Future Task | No | 68d
1.1.2.7.1 | Auto Scheduled | 0% | Unit testing | No | 9d | Fri 5/1/26 | Wed 5/13/26 |  |  | 203 |  | NA | Testing & Training | Fri 5/1/26 | Wed 5/13/26 |  | Mon 11/10/25 | Thu 11/20/25 | Start No Earlier Than | 1.1.2.7.2 | Thu 4/30/26 | 279 |  | 280 | 68d | No | Yes | No | No | No | 1.1.2.7.1 | 5 | No | 500 | Future Task | No | 0d
1.1.2.7.2 | Auto Scheduled | 0% | Changes moved to Test System | No | 3d | Thu 5/14/26 | Mon 5/18/26 |  | 202 | 204 |  | NA | Testing & Training | Thu 5/14/26 | Mon 5/18/26 | 1.1.2.7.1 | Fri 11/21/25 | Tue 11/25/25 | Start No Earlier Than | 1.1.2.7.3 | Thu 4/30/26 | 280 | 279 | 287 | 68d | No | Yes | No | No | No | 1.1.2.7.2 | 5 | No | 500 | Future Task | No | 0d
1.1.2.7.3 | Auto Scheduled | 0% | Connector configuration (S4 / LDAP Connector) | No | 3d | Tue 5/19/26 | Thu 5/21/26 |  | 203 | 205 |  | NA | Testing & Training | Tue 5/19/26 | Thu 5/21/26 | 1.1.2.7.2 | Wed 11/26/25 | Fri 11/28/25 | Start No Earlier Than | 1.1.2.7.4 | Thu 4/30/26 | 287 | 280 | 288 | 68d | No | Yes | No | No | No | 1.1.2.7.3 | 5 | No | 500 | Future Task | No | 0d
1.1.2.7.4 | Auto Scheduled | 0% | Workflow Activation / Data load in Test System | No | 5d | Fri 5/22/26 | Thu 5/28/26 |  | 204 | 206 |  | NA | Testing & Training | Fri 5/22/26 | Thu 5/28/26 | 1.1.2.7.3 | Mon 12/1/25 | Fri 12/5/25 | Start No Earlier Than | 1.1.2.7.5 | Thu 4/30/26 | 288 | 287 | 289 | 68d | No | Yes | No | No | No | 1.1.2.7.4 | 5 | No | 500 | Future Task | No | 0d
1.1.2.7.5 | Auto Scheduled | 0% | Integration testing - Smoke Test | No | 9d | Fri 5/29/26 | Wed 6/10/26 |  | 205 | 207 |  | NA | Testing & Training | Fri 5/29/26 | Wed 6/10/26 | 1.1.2.7.4 | Mon 12/8/25 | Thu 12/18/25 | Start No Earlier Than | 1.1.2.7.6 | Thu 4/30/26 | 289 | 288 | 290 | 68d | No | Yes | No | No | No | 1.1.2.7.5 | 5 | No | 500 | Future Task | No | 0d
1.1.2.7.6 | Auto Scheduled | 0% | UAT (User Acceptance Testing) - ITC-3 - with roles | No | 16d | Thu 6/11/26 | Thu 7/2/26 |  | 206 | 208 |  | NA | Testing & Training | Thu 6/11/26 | Thu 7/2/26 | 1.1.2.7.5 | Fri 12/19/25 | Fri 1/9/26 | Start No Earlier Than | 1.1.2.7.7 | Thu 4/30/26 | 290 | 289 | 291 | 68d | No | Yes | No | No | No | 1.1.2.7.6 | 5 | No | 500 | Future Task | No | 0d
1.1.2.7.7 | Auto Scheduled | 0% | Issue resolution | No | 10d | Fri 7/3/26 | Thu 7/16/26 |  | 207 | 209 |  | NA | Testing & Training | Fri 7/3/26 | Thu 7/16/26 | 1.1.2.7.6 | Mon 1/12/26 | Fri 1/23/26 | Start No Earlier Than | 1.1.2.7.8 | Thu 4/30/26 | 291 | 290 | 292 | 68d | No | Yes | No | No | No | 1.1.2.7.7 | 5 | No | 500 | Future Task | No | 0d
1.1.2.7.8 | Auto Scheduled | 0% | End-user training | No | 6d | Fri 7/17/26 | Fri 7/24/26 |  | 208 | 210 |  | NA | Testing & Training | Fri 7/17/26 | Fri 7/24/26 | 1.1.2.7.7 | Mon 1/26/26 | Mon 2/2/26 | Start No Earlier Than | 1.1.2.7.9 | Thu 4/30/26 | 292 | 291 | 293 | 68d | No | Yes | No | No | No | 1.1.2.7.8 | 5 | No | 500 | Future Task | No | 0d
1.1.2.7.9 | Auto Scheduled | 0% | Initiate Preparation of Cutover Plans | No | 8d | Mon 7/27/26 | Wed 8/5/26 |  | 209 |  |  | NA | Testing & Training | Mon 7/27/26 | Wed 8/5/26 | 1.1.2.7.8 | Tue 2/3/26 | Thu 2/12/26 | Start No Earlier Than |  | Thu 4/30/26 | 293 | 292 |  | 68d | No | Yes | No | No | No | 1.1.2.7.9 | 5 | No | 500 | Future Task | No | 68d
1.1.2.8 | Auto Scheduled | 0% | Go-Live | No | 16d | Thu 10/1/26 | Thu 10/22/26 |  |  |  |  | NA | GRC Security Utility | Thu 10/1/26 | Thu 10/22/26 |  | Thu 1/1/26 | Thu 1/22/26 | Start No Earlier Than |  | Thu 9/24/26 | 294 |  |  | 0d | Yes | Yes | Yes | No | No | 1.1.2.8 | 4 | No | 500 | Future Task | No | 0d
1.1.2.8.1 | Auto Scheduled | 0% | Production deployment | No | 7d | Thu 10/1/26 | Fri 10/9/26 |  | 134 | 213SS |  | NA | Go-Live | Thu 10/1/26 | Fri 10/9/26 | 1.1.1.8 | Thu 1/1/26 | Fri 1/9/26 | Must Start On | 1.1.2.8.2[SS] | Thu 10/1/26 | 297 | 3367 | 295SS | 0d | No | Yes | Yes | No | No | 1.1.2.8.1 | 5 | No | 500 | Future Task | No | 0d
1.1.2.8.2 | Auto Scheduled | 0% | Execution of Cutover Plan(Business and Technical) | No | 7d | Thu 10/1/26 | Fri 10/9/26 |  | 212SS | 214 |  | NA | Go-Live | Thu 10/1/26 | Fri 10/9/26 | 1.1.2.8.1[SS] | Thu 1/1/26 | Fri 1/9/26 | As Soon As Possible | 1.1.2.8.3 | NA | 295 | 297SS | 296 | 12d | No | Yes | No | No | No | 1.1.2.8.2 | 5 | No | 500 | Future Task | No | 0d
1.1.2.8.3 | Auto Scheduled | 0% | Final risk analysis | No | 7d | Mon 10/12/26 | Tue 10/20/26 |  | 213 | 215 |  | NA | Go-Live | Mon 10/12/26 | Tue 10/20/26 | 1.1.2.8.2 | Mon 1/12/26 | Tue 1/20/26 | As Soon As Possible | 1.1.2.8.4 | NA | 296 | 295 | 298 | 12d | No | Yes | No | No | No | 1.1.2.8.3 | 5 | No | 500 | Future Task | No | 0d
1.1.2.8.4 | Auto Scheduled | 0% | Go-live (Technical) | No | 2d | Wed 10/21/26 | Thu 10/22/26 |  | 214 |  |  | NA | Go-Live | Wed 10/21/26 | Thu 10/22/26 | 1.1.2.8.3 | Wed 1/21/26 | Thu 1/22/26 | As Soon As Possible |  | NA | 298 | 296 |  | 12d | No | Yes | No | No | No | 1.1.2.8.4 | 5 | No | 500 | Future Task | No | 12d
1.1.2.9 | Auto Scheduled | 100% | Functional Build Tasks | No | 119d | Mon 4/7/25 | Thu 9/18/25 |  |  |  |  | Mon 4/7/25 | GRC Security Utility | Mon 4/7/25 | Thu 9/18/25 |  | Mon 4/7/25 | Thu 9/18/25 | As Soon As Possible |  | NA | 24 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.9 | 4 | No | 500 | Complete | No | 0d
1.1.2.9.1 | Auto Scheduled | 100% | BPD Development / Configuration Specs | No | 119d | Mon 4/7/25 | Thu 9/18/25 |  |  |  |  | Mon 4/7/25 | Functional Build Tasks | Mon 4/7/25 | Thu 9/18/25 |  | Mon 4/7/25 | Thu 9/18/25 | As Soon As Possible |  | NA | 25 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.9.1 | 5 | No | 500 | Complete | No | 0d
1.1.2.9.1.1 | Auto Scheduled | 100% | Master Data | No | 59d | Mon 6/16/25 | Thu 9/4/25 |  |  |  |  | Mon 6/16/25 | BPD Development / Configuration Specs | Mon 6/16/25 | Thu 9/4/25 |  | Mon 6/16/25 | Thu 9/4/25 | As Soon As Possible |  | NA | 56 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.9.1.1 | 6 | No | 500 | Complete | No | 0d
1.1.2.9.1.1.1 | Auto Scheduled | 100% | In Draft | No | 22d | Mon 6/16/25 | Tue 7/15/25 |  |  |  |  | Mon 6/16/25 | Master Data | Mon 6/16/25 | Tue 7/15/25 |  | Mon 6/16/25 | Tue 7/15/25 | Finish No Earlier Than |  | Tue 7/15/25 | 57 |  |  | 0d | No | Yes | No | No | No | 1.1.2.9.1.1.1 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.1.2 | Auto Scheduled | 100% | Complete - Ready for Security Review | No | 30d | Mon 7/7/25 | Fri 8/15/25 |  |  | 221 |  | Mon 7/7/25 | Master Data | Mon 7/7/25 | Fri 8/15/25 |  | Mon 7/7/25 | Fri 8/15/25 | Finish No Earlier Than | 1.1.2.9.1.1.3 | Fri 8/15/25 | 58 |  | 133 | 0d | No | Yes | No | No | No | 1.1.2.9.1.1.2 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.1.3 | Auto Scheduled | 100% | Complete - Audit and Controls Review | No | 14d | Mon 8/18/25 | Thu 9/4/25 |  | 220 |  |  | Mon 8/18/25 | Master Data | Mon 8/18/25 | Thu 9/4/25 | 1.1.2.9.1.1.2 | Mon 8/18/25 | Thu 9/4/25 | As Soon As Possible |  | NA | 133 | 58 |  | 0d | No | Yes | No | No | No | 1.1.2.9.1.1.3 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.2 | Auto Scheduled | 100% | Finance | No | 104d | Mon 4/7/25 | Thu 8/28/25 |  |  |  |  | Mon 4/7/25 | BPD Development / Configuration Specs | Mon 4/7/25 | Thu 8/28/25 |  | Mon 4/7/25 | Thu 8/28/25 | As Soon As Possible |  | NA | 26 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.9.1.2 | 6 | No | 500 | Complete | No | 0d
1.1.2.9.1.2.1 | Auto Scheduled | 100% | In Draft | No | 60d | Mon 4/7/25 | Fri 6/27/25 |  |  |  |  | Mon 4/7/25 | Finance | Mon 4/7/25 | Fri 6/27/25 |  | Mon 4/7/25 | Fri 6/27/25 | Finish No Earlier Than |  | Fri 6/27/25 | 31 |  |  | 0d | No | Yes | No | No | No | 1.1.2.9.1.2.1 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.2.2 | Auto Scheduled | 100% | Complete - Ready for Security Review | No | 80d | Mon 4/21/25 | Fri 8/8/25 |  |  | 225 |  | Mon 4/21/25 | Finance | Mon 4/21/25 | Fri 8/8/25 |  | Mon 4/21/25 | Fri 8/8/25 | Start No Earlier Than | 1.1.2.9.1.2.3 | Mon 4/21/25 | 32 |  | 134 | 0d | No | Yes | No | No | No | 1.1.2.9.1.2.2 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.2.3 | Auto Scheduled | 100% | Complete - Ready for Audit and Controls Review | No | 14d | Mon 8/11/25 | Thu 8/28/25 |  | 224 |  |  | Mon 8/11/25 | Finance | Mon 8/11/25 | Thu 8/28/25 | 1.1.2.9.1.2.2 | Mon 8/11/25 | Thu 8/28/25 | As Soon As Possible |  | NA | 134 | 32 |  | 0d | No | Yes | No | No | No | 1.1.2.9.1.2.3 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.3 | Auto Scheduled | 100% | Plan to Make | No | 108d | Tue 4/8/25 | Thu 9/4/25 |  |  |  |  | Tue 4/8/25 | BPD Development / Configuration Specs | Tue 4/8/25 | Thu 9/4/25 |  | Mon 4/7/25 | Thu 9/4/25 | As Soon As Possible |  | NA | 27 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.9.1.3 | 6 | No | 500 | Complete | No | 0d
1.1.2.9.1.3.1 | Auto Scheduled | 100% | In Draft | No | 75d | Tue 4/8/25 | Mon 7/21/25 |  |  |  |  | Tue 4/8/25 | Plan to Make | Tue 4/8/25 | Mon 7/21/25 |  | Mon 4/7/25 | Mon 7/21/25 | Finish No Earlier Than |  | Mon 7/21/25 | 33 |  |  | 0d | No | Yes | No | No | No | 1.1.2.9.1.3.1 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.3.2 | Auto Scheduled | 100% | Complete - Ready for Security Review | No | 85d | Mon 4/21/25 | Fri 8/15/25 |  |  | 229 |  | Mon 4/21/25 | Plan to Make | Mon 4/21/25 | Fri 8/15/25 |  | Mon 4/21/25 | Fri 8/15/25 | Start No Earlier Than | 1.1.2.9.1.3.3 | Mon 4/21/25 | 34 |  | 135 | 0d | No | Yes | No | No | No | 1.1.2.9.1.3.2 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.3.3 | Auto Scheduled | 100% | Complete - Ready for Audit and Controls Review | No | 14d | Mon 8/18/25 | Thu 9/4/25 |  | 228 |  |  | Mon 8/18/25 | Plan to Make | Mon 8/18/25 | Thu 9/4/25 | 1.1.2.9.1.3.2 | Mon 8/18/25 | Thu 9/4/25 | As Soon As Possible |  | NA | 135 | 34 |  | 0d | No | Yes | No | No | No | 1.1.2.9.1.3.3 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.4 | Auto Scheduled | 100% | Procure to Pay | No | 119d | Mon 4/7/25 | Thu 9/18/25 |  |  |  |  | Mon 4/7/25 | BPD Development / Configuration Specs | Mon 4/7/25 | Thu 9/18/25 |  | Mon 4/7/25 | Thu 9/18/25 | As Soon As Possible |  | NA | 28 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.9.1.4 | 6 | No | 500 | Complete | No | 0d
1.1.2.9.1.4.1 | Auto Scheduled | 100% | In Draft | No | 96d | Mon 4/7/25 | Mon 8/18/25 |  |  |  |  | Mon 4/7/25 | Procure to Pay | Mon 4/7/25 | Mon 8/18/25 |  | Mon 4/7/25 | Mon 8/18/25 | Finish No Earlier Than |  | Mon 8/18/25 | 35 |  |  | 0d | No | Yes | No | No | No | 1.1.2.9.1.4.1 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.4.2 | Auto Scheduled | 100% | Complete - Ready for Security Review | No | 95d | Mon 4/21/25 | Fri 8/29/25 |  |  | 233 |  | Mon 4/21/25 | Procure to Pay | Mon 4/21/25 | Fri 8/29/25 |  | Mon 4/21/25 | Fri 8/29/25 | Start No Earlier Than | 1.1.2.9.1.4.3 | Mon 4/21/25 | 36 |  | 136 | 0d | No | Yes | No | No | No | 1.1.2.9.1.4.2 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.4.3 | Auto Scheduled | 100% | Complete - Ready for Audit and Controls Review | No | 14d | Mon 9/1/25 | Thu 9/18/25 |  | 232 |  |  | Mon 9/1/25 | Procure to Pay | Mon 9/1/25 | Thu 9/18/25 | 1.1.2.9.1.4.2 | Mon 9/1/25 | Thu 9/18/25 | As Soon As Possible |  | NA | 136 | 36 |  | 0d | No | Yes | No | No | No | 1.1.2.9.1.4.3 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.5 | Auto Scheduled | 100% | Order to Cash | No | 99d | Mon 4/7/25 | Thu 8/21/25 |  |  |  |  | Mon 4/7/25 | BPD Development / Configuration Specs | Mon 4/7/25 | Thu 8/21/25 |  | Mon 4/7/25 | Thu 8/21/25 | As Soon As Possible |  | NA | 29 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.9.1.5 | 6 | No | 500 | Complete | No | 0d
1.1.2.9.1.5.1 | Auto Scheduled | 100% | In Draft | No | 76d | Mon 4/7/25 | Mon 7/21/25 |  |  |  |  | Mon 4/7/25 | Order to Cash | Mon 4/7/25 | Mon 7/21/25 |  | Mon 4/7/25 | Mon 7/21/25 | Finish No Earlier Than |  | Mon 7/21/25 | 37 |  |  | 0d | No | Yes | No | No | No | 1.1.2.9.1.5.1 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.5.2 | Auto Scheduled | 100% | Complete - Ready for Security Review | No | 75d | Mon 4/21/25 | Fri 8/1/25 |  |  | 237 |  | Mon 4/21/25 | Order to Cash | Mon 4/21/25 | Fri 8/1/25 |  | Mon 4/21/25 | Fri 8/1/25 | Start No Earlier Than | 1.1.2.9.1.5.3 | Mon 4/21/25 | 38 |  | 137 | 0d | No | Yes | No | No | No | 1.1.2.9.1.5.2 | 7 | No | 500 | Complete | No | 0d
1.1.2.9.1.5.3 | Auto Scheduled | 100% | Complete - Ready for Audit and Controls Review | No | 14d | Mon 8/4/25 | Thu 8/21/25 |  | 236 |  |  | Mon 8/4/25 | Order to Cash | Mon 8/4/25 | Thu 8/21/25 | 1.1.2.9.1.5.2 | Mon 8/4/25 | Thu 8/21/25 | As Soon As Possible |  | NA | 137 | 38 |  | 0d | No | Yes | No | No | No | 1.1.2.9.1.5.3 | 7 | No | 500 | Complete | No | 0d
1.1.2.10 | Auto Scheduled | 100% | RICEFW Development Tasks (RICEFW Tracker) | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | GRC Security Utility | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 55 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.10 | 4 | No | 500 | Complete | No | 0d
1.1.2.10.1 | Auto Scheduled | 100% | Finance and Controlling | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | RICEFW Development Tasks (RICEFW Tracker) | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 59 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.10.1 | 5 | No | 500 | Complete | No | 0d
1.1.2.10.1.1 | Auto Scheduled | 100% | Specs Completed | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Finance and Controlling | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 60 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.1.1 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.1.2 | Auto Scheduled | 100% | Specs Assigned to Developer | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Finance and Controlling | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 61 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.1.2 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.1.3 | Auto Scheduled | 100% | Testing Complete | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Finance and Controlling | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 71 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.1.3 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.1.4 | Auto Scheduled | 100% | Assigned to Testing Cycle | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Finance and Controlling | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 72 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.1.4 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.2 | Auto Scheduled | 100% | Plan to Make | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | RICEFW Development Tasks (RICEFW Tracker) | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 62 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.10.2 | 5 | No | 500 | Complete | No | 0d
1.1.2.10.2.1 | Auto Scheduled | 100% | Specs Completed | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Plan to Make | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 73 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.2.1 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.2.2 | Auto Scheduled | 100% | Specs Assigned to Developer | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Plan to Make | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 74 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.2.2 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.2.3 | Auto Scheduled | 100% | Testing Complete | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Plan to Make | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 75 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.2.3 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.2.4 | Auto Scheduled | 100% | Assigned to Testing Cycle | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Plan to Make | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 76 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.2.4 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.3 | Auto Scheduled | 100% | Procure to Pay | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | RICEFW Development Tasks (RICEFW Tracker) | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 65 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.10.3 | 5 | No | 500 | Complete | No | 0d
1.1.2.10.3.1 | Auto Scheduled | 100% | Specs Completed | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Procure to Pay | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 77 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.3.1 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.3.2 | Auto Scheduled | 100% | Specs Assigned to Developer | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Procure to Pay | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 78 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.3.2 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.3.3 | Auto Scheduled | 100% | Testing Complete | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Procure to Pay | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 79 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.3.3 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.3.4 | Auto Scheduled | 100% | Assigned to Testing Cycle | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Procure to Pay | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 80 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.3.4 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.4 | Auto Scheduled | 100% | Order to Cash | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | RICEFW Development Tasks (RICEFW Tracker) | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 68 |  |  | 0d | Yes | Yes | No | No | No | 1.1.2.10.4 | 5 | No | 500 | Complete | No | 0d
1.1.2.10.4.1 | Auto Scheduled | 100% | Specs Completed | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Order to Cash | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 81 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.4.1 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.4.2 | Auto Scheduled | 100% | Specs Assigned to Developer | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Order to Cash | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 82 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.4.2 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.4.3 | Auto Scheduled | 100% | Testing Complete | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Order to Cash | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 83 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.4.3 | 6 | No | 500 | Complete | No | 0d
1.1.2.10.4.4 | Auto Scheduled | 100% | Assigned to Testing Cycle | No | 1d | Thu 3/13/25 | Thu 3/13/25 |  |  |  |  | Thu 3/13/25 | Order to Cash | Thu 3/13/25 | Thu 3/13/25 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 84 |  |  | 0d | No | Yes | No | No | No | 1.1.2.10.4.4 | 6 | No | 500 | Complete | No | 0d
1.2 | Auto Scheduled | 20% | Data Readiness | No | 135.66d | Mon 4/6/26 | Mon 10/12/26 |  |  |  |  | Mon 4/6/26 | AMETEK Release-1, 3-Deployment Plan | Mon 4/6/26 | Mon 10/12/26 |  | Thu 3/13/25 | Tue 4/21/26 | As Soon As Possible |  | NA | 682 |  |  | -2.03d | Yes | Yes | Yes | No | No | 1.2 | 2 | No | 500 | Future Task | No | 0d
1.2.1 | Auto Scheduled | 100% | ITC1 Data Load Tasks QS5 | No | 13.66d | Mon 4/6/26 | Thu 4/23/26 |  |  | 629 |  | Mon 4/6/26 | Data Readiness | Mon 4/6/26 | Thu 4/23/26 |  | Thu 3/13/25 | Tue 4/21/26 | As Soon As Possible | 1.2.2 | NA | 425 |  | 2809 | 0d | Yes | Yes | No | No | No | 1.2.1 | 3 | No | 500 | Complete | No | 0d
1.2.1.1 | Auto Scheduled | 100% | PMO Authorization to Start Data Loads | No | 15m | Mon 4/6/26 | Mon 4/6/26 | Mark George |  | 263500587593 |  | Mon 4/6/26 | ITC1 Data Load Tasks QS5 | Mon 4/6/26 | Mon 4/6/26 |  | Mon 4/6/26 | Mon 4/6/26 | Start No Earlier Than | 1.2.1.2.1,1.2.1.38.1,1.2.1.59.1,1.2.1.61.1 | Mon 4/6/26 | 956 |  | 777115111781182 | 0m | No | Yes | No | No | No | 1.2.1.1 | 4 | No | 500 | Complete | No | 0m
1.2.1.2 | Auto Scheduled | 100% | RTR_CM02_Profit Center Hierarchy | No | 0.75d | Mon 4/6/26 | Mon 4/6/26 |  |  | 295297266 |  | Mon 4/6/26 | ITC1 Data Load Tasks QS5 | Mon 4/6/26 | Mon 4/6/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.1.7.2,1.2.1.7.4,1.2.1.3 | NA | 755 |  | 882883756 | 0d | Yes | Yes | No | No | No | 1.2.1.2 | 4 | No | 500 | Complete | No | 0d
1.2.1.2.1 | Auto Scheduled | 100% | Manual File Staged and Posted "Ready" | No | 1h | Mon 4/6/26 | Mon 4/6/26 | Kasey Hughes | 261 | 264 |  | Mon 4/6/26 | RTR_CM02_Profit Center Hierarchy | Mon 4/6/26 | Mon 4/6/26 | 1.2.1.1 | Mon 4/6/26 | Mon 4/6/26 | Start No Earlier Than | 1.2.1.2.2 | Mon 4/6/26 | 777 | 956 | 780 | 0h | No | Yes | No | No | No | 1.2.1.2.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.2.2 | Auto Scheduled | 100% | Load | No | 2h | Mon 4/6/26 | Mon 4/6/26 | Kasey Hughes | 263 | 265 |  | Mon 4/6/26 | RTR_CM02_Profit Center Hierarchy | Mon 4/6/26 | Mon 4/6/26 | 1.2.1.2.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.1.2.3 | NA | 780 | 777 | 781 | 0h | No | Yes | No | No | No | 1.2.1.2.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.2.3 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Mon 4/6/26 | Mon 4/6/26 | Kasey Hughes | 264 | 267280 | Brian Wagner | Mon 4/6/26 | RTR_CM02_Profit Center Hierarchy | Mon 4/6/26 | Mon 4/6/26 | 1.2.1.2.2 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.1.3.1,1.2.1.5.1 | NA | 781 | 780 | 783802 | 0h | No | Yes | No | No | No | 1.2.1.2.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.3 | Auto Scheduled | 100% | RTR_CM03_Cost Center Hierarchy | No | 0.75d | Mon 4/6/26 | Tue 4/7/26 |  | 262 | 295297270 |  | Mon 4/6/26 | ITC1 Data Load Tasks QS5 | Mon 4/6/26 | Tue 4/7/26 | 1.2.1.2 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.7.2,1.2.1.7.4,1.2.1.4 | NA | 756 | 755 | 882883740 | 0d | Yes | Yes | No | No | No | 1.2.1.3 | 4 | No | 500 | Complete | No | 0d
1.2.1.3.1 | Auto Scheduled | 100% | Manual File Staged and Posted "Ready" | No | 1h | Mon 4/6/26 | Mon 4/6/26 | Kasey Hughes | 265 | 268 |  | Mon 4/6/26 | RTR_CM03_Cost Center Hierarchy | Mon 4/6/26 | Mon 4/6/26 | 1.2.1.2.3 | Mon 4/6/26 | Mon 4/6/26 | Start No Earlier Than | 1.2.1.3.2 | Mon 4/6/26 | 783 | 781 | 786 | 0h | No | Yes | No | No | No | 1.2.1.3.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.3.2 | Auto Scheduled | 100% | Load | No | 2h | Mon 4/6/26 | Tue 4/7/26 | Kasey Hughes | 267 | 269 |  | Mon 4/6/26 | RTR_CM03_Cost Center Hierarchy | Mon 4/6/26 | Tue 4/7/26 | 1.2.1.3.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.3.3 | NA | 786 | 783 | 787 | 0h | No | Yes | No | No | No | 1.2.1.3.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.3.3 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Tue 4/7/26 | Tue 4/7/26 | Kasey Hughes | 268 | 271306 | Brian Wagner | Tue 4/7/26 | RTR_CM03_Cost Center Hierarchy | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.3.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.4.1,1.2.1.9.1 | NA | 787 | 786 | 958965 | 0h | No | Yes | No | No | No | 1.2.1.3.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.4 | Auto Scheduled | 100% | RTR_CM01_GL_Account_Master to CC 1000 | No | 1.81d | Tue 4/7/26 | Thu 4/9/26 |  | 266 | 295279 |  | Tue 4/7/26 | ITC1 Data Load Tasks QS5 | Tue 4/7/26 | Thu 4/9/26 | 1.2.1.3 | Tue 4/7/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.7.2,1.2.1.5 | NA | 740 | 756 | 882759 | 0d | Yes | Yes | No | No | No | 1.2.1.4 | 4 | No | 500 | Complete | No | 0d
1.2.1.4.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 1h | Tue 4/7/26 | Tue 4/7/26 | Kasey Hughes | 269 | 272 |  | Tue 4/7/26 | RTR_CM01_GL_Account_Master to CC 1000 | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.3.3 | Tue 4/7/26 | Tue 4/7/26 | Start No Earlier Than | 1.2.1.4.2 | Mon 4/6/26 | 958 | 787 | 773 | 0h | No | Yes | No | No | No | 1.2.1.4.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.4.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Tue 4/7/26 | Tue 4/7/26 | Kasey Hughes | 271 | 273 | Brian Wagner | Tue 4/7/26 | RTR_CM01_GL_Account_Master to CC 1000 | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.4.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.4.3 | NA | 773 | 958 | 774 | 0h | No | Yes | No | No | No | 1.2.1.4.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.4.3 | Auto Scheduled | 100% | Simulate Load | No | 6h | Tue 4/7/26 | Wed 4/8/26 | Data Migration Team | 272 | 274 |  | Tue 4/7/26 | RTR_CM01_GL_Account_Master to CC 1000 | Tue 4/7/26 | Wed 4/8/26 | 1.2.1.4.2 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.4.4 | NA | 774 | 773 | 775 | 0h | No | Yes | No | No | No | 1.2.1.4.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.4.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Wed 4/8/26 | Wed 4/8/26 | Kasey Hughes | 273 | 275 | Brian Wagner | Wed 4/8/26 | RTR_CM01_GL_Account_Master to CC 1000 | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.4.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.4.5 | NA | 775 | 774 | 795 | 0h | No | Yes | No | No | No | 1.2.1.4.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.4.5 | Auto Scheduled | 100% | Load | No | 1h | Wed 4/8/26 | Wed 4/8/26 | Data Migration Team | 274 | 276 |  | Wed 4/8/26 | RTR_CM01_GL_Account_Master to CC 1000 | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.4.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.4.6 | NA | 795 | 775 | 776 | 0h | No | Yes | No | No | No | 1.2.1.4.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.4.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Wed 4/8/26 | Wed 4/8/26 | Kasey Hughes | 275 | 299313327332277 | Brian Wagner | Wed 4/8/26 | RTR_CM01_GL_Account_Master to CC 1000 | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.4.5 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.8.1,1.2.1.10.1,1.2.1.12.1,1.2.1.14.1,1.2.1.4.7 | NA | 776 | 795 | 8087898148231240 | 0h | No | Yes | No | No | No | 1.2.1.4.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.4.7 | Auto Scheduled | 100% | Extend GL to all Company Codes | No | 2h | Wed 4/8/26 | Thu 4/9/26 | Kasey Hughes | 276 | 278 |  | Wed 4/8/26 | RTR_CM01_GL_Account_Master to CC 1000 | Wed 4/8/26 | Thu 4/9/26 | 1.2.1.4.6 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.4.8 | NA | 1243 | 776 | 1244 | 0h | No | Yes | No | No | No | 1.2.1.4.7 | 5 | No | 500 | Complete | No | 0h
1.2.1.4.8 | Auto Scheduled | 100% | Post GL Extention Validation | No | 2h | Thu 4/9/26 | Thu 4/9/26 |  | 277 | 344297 |  | Thu 4/9/26 | RTR_CM01_GL_Account_Master to CC 1000 | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.4.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.15.3,1.2.1.7.4 | NA | 1244 | 1243 | 819883 | 0h | No | Yes | No | No | No | 1.2.1.4.8 | 5 | No | 500 | Complete | No | 0h
1.2.1.5 | Auto Scheduled | 100% | RTR_CM05_Profit_Center | No | 1.13d | Mon 4/6/26 | Tue 4/7/26 |  | 270 | 286 |  | Mon 4/6/26 | ITC1 Data Load Tasks QS5 | Mon 4/6/26 | Tue 4/7/26 | 1.2.1.4 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.6 | NA | 759 | 740 | 767 | 0d | Yes | Yes | No | No | No | 1.2.1.5 | 4 | No | 500 | Complete | No | 0d
1.2.1.5.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 1h | Mon 4/6/26 | Mon 4/6/26 | Kasey Hughes | 265 | 281 |  | Mon 4/6/26 | RTR_CM05_Profit_Center | Mon 4/6/26 | Mon 4/6/26 | 1.2.1.2.3 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.1.5.2 | NA | 802 | 781 | 803 | 0h | No | Yes | No | No | No | 1.2.1.5.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.5.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Mon 4/6/26 | Tue 4/7/26 | Kasey Hughes | 280 | 282 | Brian Wagner | Mon 4/6/26 | RTR_CM05_Profit_Center | Mon 4/6/26 | Tue 4/7/26 | 1.2.1.5.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.5.3 | NA | 803 | 802 | 804 | 0h | No | Yes | No | No | No | 1.2.1.5.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.5.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Tue 4/7/26 | Tue 4/7/26 | Data Migration Team | 281 | 283 |  | Tue 4/7/26 | RTR_CM05_Profit_Center | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.5.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.5.4 | NA | 804 | 803 | 805 | 0h | No | Yes | No | No | No | 1.2.1.5.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.5.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Tue 4/7/26 | Tue 4/7/26 | Kasey Hughes | 282 | 284 | Brian Wagner | Tue 4/7/26 | RTR_CM05_Profit_Center | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.5.3 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.5.5 | NA | 805 | 804 | 806 | 0h | No | Yes | No | No | No | 1.2.1.5.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.5.5 | Auto Scheduled | 100% | Load | No | 1h | Tue 4/7/26 | Tue 4/7/26 | Data Migration Team | 283 | 285 |  | Tue 4/7/26 | RTR_CM05_Profit_Center | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.5.4 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.5.6 | NA | 806 | 805 | 807 | 0h | No | Yes | No | No | No | 1.2.1.5.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.5.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Tue 4/7/26 | Tue 4/7/26 | Kasey Hughes | 284 | 287416423 | Brian Wagner | Tue 4/7/26 | RTR_CM05_Profit_Center | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.5.5 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.6.1,1.2.1.26.1,1.2.1.27.1 | NA | 807 | 806 | 95910261032 | 0h | No | Yes | No | No | No | 1.2.1.5.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.6 | Auto Scheduled | 100% | RTR_CM04_Cost_Center | No | 1.13d | Tue 4/7/26 | Thu 4/9/26 |  | 279 | 293298 |  | Tue 4/7/26 | ITC1 Data Load Tasks QS5 | Tue 4/7/26 | Thu 4/9/26 | 1.2.1.5 | Tue 4/7/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.7,1.2.1.8 | NA | 767 | 759 | 881760 | 0d | Yes | Yes | No | No | No | 1.2.1.6 | 4 | No | 500 | Complete | No | 0d
1.2.1.6.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 1h | Tue 4/7/26 | Wed 4/8/26 | Kasey Hughes | 285 | 288 |  | Tue 4/7/26 | RTR_CM04_Cost_Center | Tue 4/7/26 | Wed 4/8/26 | 1.2.1.5.6 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.6.2 | NA | 959 | 807 | 960 | 0h | No | Yes | No | No | No | 1.2.1.6.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.6.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Wed 4/8/26 | Wed 4/8/26 | Kasey Hughes | 287 | 289 | Brian Wagner | Wed 4/8/26 | RTR_CM04_Cost_Center | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.6.1 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.6.3 | NA | 960 | 959 | 961 | 0h | No | Yes | No | No | No | 1.2.1.6.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.6.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Wed 4/8/26 | Wed 4/8/26 | Data Migration Team | 288 | 290 |  | Wed 4/8/26 | RTR_CM04_Cost_Center | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.6.2 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.6.4 | NA | 961 | 960 | 962 | 0h | No | Yes | No | No | No | 1.2.1.6.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.6.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Wed 4/8/26 | Wed 4/8/26 | Kasey Hughes | 289 | 291 | Brian Wagner | Wed 4/8/26 | RTR_CM04_Cost_Center | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.6.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.6.5 | NA | 962 | 961 | 963 | 0h | No | Yes | No | No | No | 1.2.1.6.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.6.5 | Auto Scheduled | 100% | Load | No | 1h | Wed 4/8/26 | Wed 4/8/26 | Data Migration Team | 290 | 292 |  | Wed 4/8/26 | RTR_CM04_Cost_Center | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.6.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.6.6 | NA | 963 | 962 | 964 | 0h | No | Yes | No | No | No | 1.2.1.6.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.6.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Wed 4/8/26 | Thu 4/9/26 | Kasey Hughes | 291 |  | Brian Wagner | Wed 4/8/26 | RTR_CM04_Cost_Center | Wed 4/8/26 | Thu 4/9/26 | 1.2.1.6.5 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 964 | 963 |  | 0h | No | Yes | No | No | No | 1.2.1.6.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.7 | Auto Scheduled | 100% | Manual Configuration Activities in QS5 | No | 7.16d | Mon 4/6/26 | Wed 4/15/26 |  | 286 |  |  | Mon 4/6/26 | ITC1 Data Load Tasks QS5 | Mon 4/6/26 | Wed 4/15/26 | 1.2.1.6 | Mon 4/6/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 881 | 767 |  | 0d | Yes | Yes | No | No | No | 1.2.1.7 | 4 | No | 500 | Complete | No | 0d
1.2.1.7.1 | Auto Scheduled | 100% | Open Client | No | 30m | Mon 4/6/26 | Mon 4/6/26 | Basis |  |  |  | Mon 4/6/26 | Manual Configuration Activities in QS5 | Mon 4/6/26 | Mon 4/6/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 1219 |  |  | 0m | No | Yes | No | No | No | 1.2.1.7.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.7.2 | Auto Scheduled | 100% | Service Enterprise Setup | No | 5d | Wed 4/8/26 | Wed 4/15/26 | Keith Riley | 270262266 |  |  | Wed 4/8/26 | Manual Configuration Activities in QS5 | Wed 4/8/26 | Wed 4/15/26 | 1.2.1.4,1.2.1.2,1.2.1.3 | Wed 4/8/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 882 | 740755756 |  | 0d | No | Yes | No | No | No | 1.2.1.7.2 | 5 | No | 500 | Complete | No | 0d
1.2.1.7.3 | Auto Scheduled | 100% | Close Client | No | 30m | Mon 4/6/26 | Mon 4/6/26 | Basis |  |  |  | Mon 4/6/26 | Manual Configuration Activities in QS5 | Mon 4/6/26 | Mon 4/6/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 1220 |  |  | 0m | No | Yes | No | No | No | 1.2.1.7.3 | 5 | No | 500 | Complete | No | 0m
1.2.1.7.4 | Auto Scheduled | 100% | Intercompany Business Partner Setup | No | 2h | Wed 4/8/26 | Thu 4/9/26 | Functional Leads | 262266278 |  |  | Wed 4/8/26 | Manual Configuration Activities in QS5 | Wed 4/8/26 | Thu 4/9/26 | 1.2.1.2,1.2.1.3,1.2.1.4.8 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 883 | 7557561244 |  | 0h | No | Yes | No | No | No | 1.2.1.7.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.8 | Auto Scheduled | 100% | RTR_CM09_Activity_Type | No | 1.22d | Wed 4/8/26 | Thu 4/9/26 |  | 286 | 305 |  | Wed 4/8/26 | ITC1 Data Load Tasks QS5 | Wed 4/8/26 | Thu 4/9/26 | 1.2.1.6 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.9 | NA | 760 | 767 | 753 | 0d | Yes | Yes | No | No | No | 1.2.1.8 | 4 | No | 500 | Complete | No | 0d
1.2.1.8.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 1h | Wed 4/8/26 | Wed 4/8/26 | Kasey Hughes | 276 | 300 |  | Wed 4/8/26 | RTR_CM09_Activity_Type | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.4.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.8.2 | NA | 808 | 776 | 809 | 0h | No | Yes | No | No | No | 1.2.1.8.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.8.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Wed 4/8/26 | Thu 4/9/26 | Kasey Hughes | 299 | 301 | Brian Wagner | Wed 4/8/26 | RTR_CM09_Activity_Type | Wed 4/8/26 | Thu 4/9/26 | 1.2.1.8.1 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.8.3 | NA | 809 | 808 | 810 | 0h | No | Yes | No | No | No | 1.2.1.8.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.8.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Thu 4/9/26 | Thu 4/9/26 | Data Migration Team | 300 | 302 |  | Thu 4/9/26 | RTR_CM09_Activity_Type | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.8.2 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.8.4 | NA | 810 | 809 | 811 | 0h | No | Yes | No | No | No | 1.2.1.8.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.8.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Thu 4/9/26 | Thu 4/9/26 | Kasey Hughes | 301 | 303 | Brian Wagner | Thu 4/9/26 | RTR_CM09_Activity_Type | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.8.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.8.5 | NA | 811 | 810 | 812 | 0h | No | Yes | No | No | No | 1.2.1.8.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.8.5 | Auto Scheduled | 100% | Load | No | 1h | Thu 4/9/26 | Thu 4/9/26 | Data Migration Team | 302 | 304 |  | Thu 4/9/26 | RTR_CM09_Activity_Type | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.8.4 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.8.6 | NA | 812 | 811 | 813 | 0h | No | Yes | No | No | No | 1.2.1.8.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.8.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Thu 4/9/26 | Thu 4/9/26 | Kasey Hughes | 303 |  | Brian Wagner | Thu 4/9/26 | RTR_CM09_Activity_Type | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.8.5 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 813 | 812 |  | 0h | No | Yes | No | No | No | 1.2.1.8.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.9 | Auto Scheduled | 100% | RTR_CM12_Activity Rates | No | 1.13d | Tue 4/7/26 | Wed 4/8/26 |  | 298 | 312 |  | Tue 4/7/26 | ITC1 Data Load Tasks QS5 | Tue 4/7/26 | Wed 4/8/26 | 1.2.1.8 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.10 | NA | 753 | 760 | 757 | 0d | Yes | Yes | No | No | No | 1.2.1.9 | 4 | No | 500 | Complete | No | 0d
1.2.1.9.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 1h | Tue 4/7/26 | Tue 4/7/26 | Kasey Hughes | 269 | 307 |  | Tue 4/7/26 | RTR_CM12_Activity Rates | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.3.3 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.9.2 | NA | 965 | 787 | 966 | 0h | No | Yes | No | No | No | 1.2.1.9.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.9.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Tue 4/7/26 | Tue 4/7/26 | Kasey Hughes | 306 | 308 | Brian Wagner | Tue 4/7/26 | RTR_CM12_Activity Rates | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.9.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.9.3 | NA | 966 | 965 | 967 | 0h | No | Yes | No | No | No | 1.2.1.9.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.9.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Tue 4/7/26 | Wed 4/8/26 | Data Migration Team | 307 | 309 |  | Tue 4/7/26 | RTR_CM12_Activity Rates | Tue 4/7/26 | Wed 4/8/26 | 1.2.1.9.2 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.9.4 | NA | 967 | 966 | 968 | 0h | No | Yes | No | No | No | 1.2.1.9.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.9.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Wed 4/8/26 | Wed 4/8/26 | Kasey Hughes | 308 | 310 | Brian Wagner | Wed 4/8/26 | RTR_CM12_Activity Rates | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.9.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.9.5 | NA | 968 | 967 | 969 | 0h | No | Yes | No | No | No | 1.2.1.9.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.9.5 | Auto Scheduled | 100% | Load | No | 1h | Wed 4/8/26 | Wed 4/8/26 | Data Migration Team | 309 | 311 |  | Wed 4/8/26 | RTR_CM12_Activity Rates | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.9.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.9.6 | NA | 969 | 968 | 970 | 0h | No | Yes | No | No | No | 1.2.1.9.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.9.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Wed 4/8/26 | Wed 4/8/26 | Kasey Hughes | 310 |  | Brian Wagner | Wed 4/8/26 | RTR_CM12_Activity Rates | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.9.5 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible |  | NA | 970 | 969 |  | 0h | No | Yes | No | No | No | 1.2.1.9.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.10 | Auto Scheduled | 100% | RTR_CM06_Bank_master | No | 2.19d | Tue 4/14/26 | Thu 4/16/26 |  | 305 | 319 |  | Tue 4/14/26 | ITC1 Data Load Tasks QS5 | Tue 4/14/26 | Thu 4/16/26 | 1.2.1.9 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.11 | NA | 757 | 753 | 758 | 0d | Yes | Yes | No | No | No | 1.2.1.10 | 4 | No | 500 | Complete | No | 0d
1.2.1.10.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 1h | Tue 4/14/26 | Tue 4/14/26 | Data Migration Team | 276 | 314 |  | Tue 4/14/26 | RTR_CM06_Bank_master | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.4.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.10.2 | NA | 789 | 776 | 790 | 0h | No | Yes | No | No | No | 1.2.1.10.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.10.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Tue 4/14/26 | Tue 4/14/26 | Kasey Hughes | 313 |  | Brian Wagner | Tue 4/14/26 | RTR_CM06_Bank_master | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.10.1 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 790 | 789 |  | 0h | No | Yes | No | No | No | 1.2.1.10.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.10.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Wed 4/15/26 | Wed 4/15/26 | Data Migration Team |  | 316 |  | Wed 4/15/26 | RTR_CM06_Bank_master | Wed 4/15/26 | Wed 4/15/26 |  | Thu 4/9/26 | Thu 4/9/26 | Start No Earlier Than | 1.2.1.10.4 | Wed 4/15/26 | 791 |  | 792 | 0h | No | Yes | No | No | No | 1.2.1.10.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.10.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Wed 4/15/26 | Wed 4/15/26 | Kasey Hughes | 315 | 317 | Brian Wagner | Wed 4/15/26 | RTR_CM06_Bank_master | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.10.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.10.5 | NA | 792 | 791 | 793 | 0h | No | Yes | No | No | No | 1.2.1.10.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.10.5 | Auto Scheduled | 100% | Load | No | 5h | Wed 4/15/26 | Wed 4/15/26 | Data Migration Team | 316 | 318320 |  | Wed 4/15/26 | RTR_CM06_Bank_master | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.10.4 | Thu 4/9/26 | Thu 4/9/26 | Finish No Earlier Than | 1.2.1.10.6,1.2.1.11.1 | Wed 4/15/26 | 793 | 792 | 794796 | 0h | No | Yes | No | No | No | 1.2.1.10.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.10.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Wed 4/15/26 | Thu 4/16/26 | Kasey Hughes | 317 | 354365 | Brian Wagner | Wed 4/15/26 | RTR_CM06_Bank_master | Wed 4/15/26 | Thu 4/16/26 | 1.2.1.10.5 | Thu 4/9/26 | Thu 4/9/26 | Finish No Earlier Than | 1.2.1.16.3,1.2.1.18.3 | Tue 4/14/26 | 794 | 793 | 974989 | 0h | No | Yes | No | No | No | 1.2.1.10.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.11 | Auto Scheduled | 100% | RTR_CM08_Exchange_Rates | No | 1.13d | Thu 4/9/26 | Fri 4/10/26 |  | 312 | 326 |  | Thu 4/9/26 | ITC1 Data Load Tasks QS5 | Thu 4/9/26 | Fri 4/10/26 | 1.2.1.10 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.12 | NA | 758 | 757 | 761 | 0d | Yes | Yes | No | No | No | 1.2.1.11 | 4 | No | 500 | Complete | No | 0d
1.2.1.11.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 1h | Thu 4/9/26 | Thu 4/9/26 | Kasey Hughes | 317 | 321 |  | Thu 4/9/26 | RTR_CM08_Exchange_Rates | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.10.5 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.11.2 | NA | 796 | 793 | 797 | 0h | No | Yes | No | No | No | 1.2.1.11.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.11.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Thu 4/9/26 | Fri 4/10/26 | Kasey Hughes | 320 | 322 | Brian Wagner | Thu 4/9/26 | RTR_CM08_Exchange_Rates | Thu 4/9/26 | Fri 4/10/26 | 1.2.1.11.1 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.11.3 | NA | 797 | 796 | 798 | 0h | No | Yes | No | No | No | 1.2.1.11.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.11.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Fri 4/10/26 | Fri 4/10/26 | Data Migration Team | 321 | 323 |  | Fri 4/10/26 | RTR_CM08_Exchange_Rates | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.11.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.11.4 | NA | 798 | 797 | 799 | 0h | No | Yes | No | No | No | 1.2.1.11.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.11.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Fri 4/10/26 | Fri 4/10/26 | Kasey Hughes | 322 | 324 | Brian Wagner | Fri 4/10/26 | RTR_CM08_Exchange_Rates | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.11.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.11.5 | NA | 799 | 798 | 800 | 0h | No | Yes | No | No | No | 1.2.1.11.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.11.5 | Auto Scheduled | 100% | Load | No | 1h | Fri 4/10/26 | Fri 4/10/26 | Data Migration Team | 323 | 325 |  | Fri 4/10/26 | RTR_CM08_Exchange_Rates | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.11.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.11.6 | NA | 800 | 799 | 801 | 0h | No | Yes | No | No | No | 1.2.1.11.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.11.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Fri 4/10/26 | Fri 4/10/26 | Kasey Hughes | 324 |  | Brian Wagner | Fri 4/10/26 | RTR_CM08_Exchange_Rates | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.11.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 801 | 800 |  | 0h | No | Yes | No | No | No | 1.2.1.11.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.12 | Auto Scheduled | 100% | RTR_CM14_Cost Element_Group | No | 5.38d | Wed 4/15/26 | Wed 4/22/26 | Kasey Hughes | 319 | 330 | Brian Wagner | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Wed 4/22/26 | 1.2.1.11 | Wed 4/8/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.13 | NA | 761 | 758 | 764 | 0d | Yes | Yes | No | No | No | 1.2.1.12 | 4 | No | 500 | Complete | No | 0d
1.2.1.12.1 | Auto Scheduled | 100% | Manual File Staged and Posted "Ready" | No | 30m | Wed 4/15/26 | Wed 4/15/26 | Kasey Hughes | 276 | 328 |  | Wed 4/15/26 | RTR_CM14_Cost Element_Group | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.4.6 | Wed 4/8/26 | Tue 4/14/26 | Finish No Earlier Than | 1.2.1.12.2 | Tue 4/14/26 | 814 | 776 | 815 | 0m | No | Yes | No | No | No | 1.2.1.12.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.12.2 | Auto Scheduled | 100% | Load | No | 32h | Thu 4/16/26 | Tue 4/21/26 | Kasey Hughes | 327 | 329 |  | Thu 4/16/26 | RTR_CM14_Cost Element_Group | Thu 4/16/26 | Tue 4/21/26 | 1.2.1.12.1 | Wed 4/15/26 | Wed 4/15/26 | Finish No Earlier Than | 1.2.1.12.3 | Tue 4/21/26 | 815 | 814 | 816 | 0h | No | Yes | No | No | No | 1.2.1.12.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.12.3 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Wed 4/22/26 | Wed 4/22/26 | Kasey Hughes | 328 |  | Brian Wagner | Wed 4/22/26 | RTR_CM14_Cost Element_Group | Wed 4/22/26 | Wed 4/22/26 | 1.2.1.12.2 | Wed 4/15/26 | Wed 4/15/26 | Start No Earlier Than |  | Fri 4/17/26 | 816 | 815 |  | 0h | No | Yes | No | No | No | 1.2.1.12.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.13 | Auto Scheduled | 100% | OTC_CM19_Customer_Master - Bill-To | No | 2h | Thu 4/16/26 | Thu 4/16/26 |  | 326 | 331 |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.12 | Wed 4/16/25 | Wed 4/16/25 | As Soon As Possible | 1.2.1.14 | NA | 764 | 761 | 763 | 0h | No | Yes | No | No | No | 1.2.1.13 | 4 | No | 500 | Complete | No | 0h
1.2.1.14 | Auto Scheduled | 100% | OTC_CM19_Customer_Master - Ship-To | No | 2.16d | Wed 4/8/26 | Fri 4/10/26 |  | 330 | 341 |  | Wed 4/8/26 | ITC1 Data Load Tasks QS5 | Wed 4/8/26 | Fri 4/10/26 | 1.2.1.13 | Wed 4/8/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.15 | NA | 763 | 764 | 762 | 0d | Yes | Yes | No | No | No | 1.2.1.14 | 4 | No | 500 | Complete | No | 0d
1.2.1.14.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Wed 4/8/26 | Wed 4/8/26 | Ric Haraida | 276 | 333 |  | Wed 4/8/26 | OTC_CM19_Customer_Master - Ship-To | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.4.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.14.2 | NA | 823 | 776 | 824 | 0m | No | Yes | No | No | No | 1.2.1.14.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.14.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Wed 4/8/26 | Wed 4/8/26 | Ric Haraida | 332 | 337342334 | Kim Kolesar | Wed 4/8/26 | OTC_CM19_Customer_Master - Ship-To | Wed 4/8/26 | Wed 4/8/26 | 1.2.1.14.1 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.1.14.6,1.2.1.15.1,1.2.1.14.3 | NA | 824 | 823 | 8258171231 | 0m | No | Yes | No | No | No | 1.2.1.14.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.14.3 | Auto Scheduled | 100% | Open client for BP number range update | No | 30m | Wed 4/8/26 | Thu 4/9/26 | Basis | 333 | 335 |  | Wed 4/8/26 | OTC_CM19_Customer_Master - Ship-To | Wed 4/8/26 | Thu 4/9/26 | 1.2.1.14.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.14.4 | NA | 1231 | 824 | 1232 | 0m | No | Yes | No | No | No | 1.2.1.14.3 | 5 | No | 500 | Complete | No | 0m
1.2.1.14.4 | Auto Scheduled | 100% | Update number range BP02 from Internal to External | No | 30m | Thu 4/9/26 | Fri 4/10/26 | Ric Haraida | 334 | 336 |  | Thu 4/9/26 | OTC_CM19_Customer_Master - Ship-To | Thu 4/9/26 | Fri 4/10/26 | 1.2.1.14.3 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.14.5 | NA | 1232 | 1231 | 1233 | 0m | No | Yes | No | No | No | 1.2.1.14.4 | 5 | No | 500 | Complete | No | 0m
1.2.1.14.5 | Auto Scheduled | 100% | Close Client | No | 15m | Fri 4/10/26 | Fri 4/10/26 | Basis | 335 |  |  | Fri 4/10/26 | OTC_CM19_Customer_Master - Ship-To | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.14.4 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1233 | 1232 |  | 0m | No | Yes | No | No | No | 1.2.1.14.5 | 5 | No | 500 | Complete | No | 0m
1.2.1.14.6 | Auto Scheduled | 100% | Simulate Load | No | 1h | Wed 4/8/26 | Thu 4/9/26 | Data Migration Team | 333 | 338344348 |  | Wed 4/8/26 | OTC_CM19_Customer_Master - Ship-To | Wed 4/8/26 | Thu 4/9/26 | 1.2.1.14.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.14.7,1.2.1.15.3,1.2.1.15.7 | NA | 825 | 824 | 8268191240 | 0h | No | Yes | No | No | No | 1.2.1.14.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.14.7 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 4h | Thu 4/9/26 | Thu 4/9/26 | Ric Haraida | 337 | 339 | Kim Kolesar | Thu 4/9/26 | OTC_CM19_Customer_Master - Ship-To | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.14.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.14.8 | NA | 826 | 825 | 827 | 0h | No | Yes | No | No | No | 1.2.1.14.7 | 5 | No | 500 | Complete | No | 0h
1.2.1.14.8 | Auto Scheduled | 100% | Load | No | 3h | Thu 4/9/26 | Thu 4/9/26 | Data Migration Team | 338 | 340 |  | Thu 4/9/26 | OTC_CM19_Customer_Master - Ship-To | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.14.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.14.9 | NA | 827 | 826 | 828 | 0h | No | Yes | No | No | No | 1.2.1.14.8 | 5 | No | 500 | Complete | No | 0h
1.2.1.14.9 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Thu 4/9/26 | Fri 4/10/26 | Ric Haraida | 339 |  | Kim Kolesar | Thu 4/9/26 | OTC_CM19_Customer_Master - Ship-To | Thu 4/9/26 | Fri 4/10/26 | 1.2.1.14.8 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 828 | 827 |  | 0h | No | Yes | No | No | No | 1.2.1.14.9 | 5 | No | 500 | Complete | No | 0h
1.2.1.15 | Auto Scheduled | 100% | OTC_CM19_Customer_Master - Sold-To | No | 1.63d | Wed 4/8/26 | Fri 4/10/26 |  | 331 | 351 |  | Wed 4/8/26 | ITC1 Data Load Tasks QS5 | Wed 4/8/26 | Fri 4/10/26 | 1.2.1.14 | Wed 4/8/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.16 | NA | 762 | 763 | 765 | 0d | Yes | Yes | No | No | No | 1.2.1.15 | 4 | No | 500 | Complete | No | 0d
1.2.1.15.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Wed 4/8/26 | Thu 4/9/26 | Ric Haraida | 333 | 343 |  | Wed 4/8/26 | OTC_CM19_Customer_Master - Sold-To | Wed 4/8/26 | Thu 4/9/26 | 1.2.1.14.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.15.2 | NA | 817 | 824 | 818 | 0m | No | Yes | No | No | No | 1.2.1.15.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.15.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Thu 4/9/26 | Thu 4/9/26 | Ric Haraida | 342 |  | Kim Kolesar | Thu 4/9/26 | OTC_CM19_Customer_Master - Sold-To | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.15.1 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 818 | 817 |  | 0m | No | Yes | No | No | No | 1.2.1.15.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.15.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Thu 4/9/26 | Thu 4/9/26 | Data Migration Team | 337278 | 345 |  | Thu 4/9/26 | OTC_CM19_Customer_Master - Sold-To | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.14.6,1.2.1.4.8 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.15.4 | NA | 819 | 8251244 | 820 | 0h | No | Yes | No | No | No | 1.2.1.15.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.15.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 3h | Thu 4/9/26 | Thu 4/9/26 | Ric Haraida | 344 | 346 | Kim Kolesar | Thu 4/9/26 | OTC_CM19_Customer_Master - Sold-To | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.15.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.15.5 | NA | 820 | 819 | 821 | 0h | No | Yes | No | No | No | 1.2.1.15.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.15.5 | Auto Scheduled | 100% | Load | No | 3h | Thu 4/9/26 | Fri 4/10/26 | Data Migration Team | 345 | 347352359363370 |  | Thu 4/9/26 | OTC_CM19_Customer_Master - Sold-To | Thu 4/9/26 | Fri 4/10/26 | 1.2.1.15.4 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.15.6,1.2.1.16.1,1.2.1.17.1,1.2.1.18.1,1.2.1.19.1 | NA | 821 | 820 | 822972984987993 | 0h | No | Yes | No | No | No | 1.2.1.15.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.15.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Fri 4/10/26 | Fri 4/10/26 | Ric Haraida | 346 |  | Kim Kolesar | Fri 4/10/26 | OTC_CM19_Customer_Master - Sold-To | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.15.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 822 | 821 |  | 0h | No | Yes | No | No | No | 1.2.1.15.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.15.7 | Auto Scheduled | 100% | Open client for BP number range update | No | 15m | Thu 4/9/26 | Thu 4/9/26 | Basis | 337 | 349 |  | Thu 4/9/26 | OTC_CM19_Customer_Master - Sold-To | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.14.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.15.8 | NA | 1240 | 825 | 1241 | 0m | No | Yes | No | No | No | 1.2.1.15.7 | 5 | No | 500 | Complete | No | 0m
1.2.1.15.8 | Auto Scheduled | 100% | Update number range BP02 from Internal to External | No | 15m | Thu 4/9/26 | Thu 4/9/26 | Ric Haraida | 348 | 350 |  | Thu 4/9/26 | OTC_CM19_Customer_Master - Sold-To | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.15.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.1.15.9 | NA | 1241 | 1240 | 1242 | 0m | No | Yes | No | No | No | 1.2.1.15.8 | 5 | No | 500 | Complete | No | 0m
1.2.1.15.9 | Auto Scheduled | 100% | Close Client | No | 15m | Thu 4/9/26 | Thu 4/9/26 | Basis | 349 |  |  | Thu 4/9/26 | OTC_CM19_Customer_Master - Sold-To | Thu 4/9/26 | Thu 4/9/26 | 1.2.1.15.8 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 1242 | 1241 |  | 0m | No | Yes | No | No | No | 1.2.1.15.9 | 5 | No | 500 | Complete | No | 0m
1.2.1.16 | Auto Scheduled | 100% | PTP_CM27_Vendor Master as Customer - FLCU01 | No | 2.31d | Fri 4/10/26 | Tue 4/14/26 |  | 341 | 358 |  | Fri 4/10/26 | ITC1 Data Load Tasks QS5 | Fri 4/10/26 | Tue 4/14/26 | 1.2.1.15 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.17 | NA | 765 | 762 | 771 | 0d | Yes | Yes | No | No | No | 1.2.1.16 | 4 | No | 500 | Complete | No | 0d
1.2.1.16.1 | Auto Scheduled | 100% | Extract File | No | 1h | Fri 4/10/26 | Fri 4/10/26 | Data Migration Team | 346 | 353 |  | Fri 4/10/26 | PTP_CM27_Vendor Master as Customer - FLCU01 | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.15.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.16.2 | NA | 972 | 821 | 973 | 0h | No | Yes | No | No | No | 1.2.1.16.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.16.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Fri 4/10/26 | Fri 4/10/26 | Nevin Varkey | 352 | 354 | Sam Houff | Fri 4/10/26 | PTP_CM27_Vendor Master as Customer - FLCU01 | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.16.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.16.3 | NA | 973 | 972 | 974 | 0h | No | Yes | No | No | No | 1.2.1.16.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.16.3 | Auto Scheduled | 100% | Simulate Load | No | 11.25h | Fri 4/10/26 | Mon 4/13/26 | Data Migration Team | 353318 | 355 |  | Fri 4/10/26 | PTP_CM27_Vendor Master as Customer - FLCU01 | Fri 4/10/26 | Mon 4/13/26 | 1.2.1.16.2,1.2.1.10.6 | Fri 4/10/26 | Mon 4/13/26 | Finish No Earlier Than | 1.2.1.16.4 | Mon 4/13/26 | 974 | 973794 | 975 | 0h | No | Yes | No | No | No | 1.2.1.16.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.16.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Fri 4/10/26 | Tue 4/14/26 | Nevin Varkey | 354 | 356 | Sam Houff | Fri 4/10/26 | PTP_CM27_Vendor Master as Customer - FLCU01 | Fri 4/10/26 | Tue 4/14/26 | 1.2.1.16.3 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.16.5 | NA | 975 | 974 | 976 | 0h | No | Yes | No | No | No | 1.2.1.16.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.16.5 | Auto Scheduled | 100% | Load | No | 1h | Fri 4/10/26 | Tue 4/14/26 | Data Migration Team | 355 | 357 |  | Fri 4/10/26 | PTP_CM27_Vendor Master as Customer - FLCU01 | Fri 4/10/26 | Tue 4/14/26 | 1.2.1.16.4 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.16.6 | NA | 976 | 975 | 977 | 0h | No | Yes | No | No | No | 1.2.1.16.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.16.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Tue 4/14/26 | Tue 4/14/26 | Nevin Varkey | 356 |  | Sam Houff | Tue 4/14/26 | PTP_CM27_Vendor Master as Customer - FLCU01 | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.16.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 977 | 976 |  | 0h | No | Yes | No | No | No | 1.2.1.16.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.17 | Auto Scheduled | 100% | OTC_CM23_Customer_Hierarchy | No | 3.03d | Fri 4/10/26 | Wed 4/15/26 |  | 351 | 362 |  | Fri 4/10/26 | ITC1 Data Load Tasks QS5 | Fri 4/10/26 | Wed 4/15/26 | 1.2.1.16 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.18 | NA | 771 | 765 | 766 | 0d | Yes | Yes | No | No | No | 1.2.1.17 | 4 | No | 500 | Complete | No | 0d
1.2.1.17.1 | Auto Scheduled | 100% | Manual File Staged and Posted "Ready" | No | 30m | Fri 4/10/26 | Fri 4/10/26 | Ric Haraida | 346 | 360 | Kim Kolesar | Fri 4/10/26 | OTC_CM23_Customer_Hierarchy | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.15.5 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.1.17.2 | Mon 4/6/26 | 984 | 821 | 985 | 0m | No | Yes | No | No | No | 1.2.1.17.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.17.2 | Auto Scheduled | 100% | Load | No | 2h | Wed 4/15/26 | Wed 4/15/26 | Ric Haraida | 359 | 361 |  | Wed 4/15/26 | OTC_CM23_Customer_Hierarchy | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.17.1 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.1.17.3 | Wed 4/15/26 | 985 | 984 | 986 | 0h | No | Yes | No | No | No | 1.2.1.17.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.17.3 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Fri 4/10/26 | Fri 4/10/26 | Ric Haraida | 360 |  | Kim Kolesar | Fri 4/10/26 | OTC_CM23_Customer_Hierarchy | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.17.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 986 | 985 |  | 0h | No | Yes | No | No | No | 1.2.1.17.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.18 | Auto Scheduled | 100% | PTP_CM27_Vendor Master - Z001 - External Sales Rep | No | 3.38d | Fri 4/10/26 | Wed 4/15/26 |  | 358 | 369 |  | Fri 4/10/26 | ITC1 Data Load Tasks QS5 | Fri 4/10/26 | Wed 4/15/26 | 1.2.1.17 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.19 | NA | 766 | 771 | 768 | 0d | Yes | Yes | No | No | No | 1.2.1.18 | 4 | No | 500 | Complete | No | 0d
1.2.1.18.1 | Auto Scheduled | 100% | Extract File | No | 1h | Fri 4/10/26 | Fri 4/10/26 | Data Migration Team | 346 | 364377 |  | Fri 4/10/26 | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.15.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.18.2,1.2.1.20.1 | NA | 987 | 821 | 988999 | 0h | No | Yes | No | No | No | 1.2.1.18.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.18.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Fri 4/10/26 | Fri 4/10/26 | Nevin Varkey | 363 | 365 | Sam Houff | Fri 4/10/26 | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.18.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.18.3 | NA | 988 | 987 | 989 | 0h | No | Yes | No | No | No | 1.2.1.18.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.18.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Fri 4/10/26 | Fri 4/10/26 | Data Migration Team | 364318 | 366 |  | Fri 4/10/26 | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.18.2,1.2.1.10.6 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.18.4 | NA | 989 | 988794 | 990 | 0h | No | Yes | No | No | No | 1.2.1.18.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.18.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Wed 4/15/26 | Wed 4/15/26 | Nevin Varkey | 365 | 367 | Sam Houff | Wed 4/15/26 | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.18.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.18.5 | NA | 990 | 989 | 991 | 0h | No | Yes | No | No | No | 1.2.1.18.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.18.5 | Auto Scheduled | 100% | Load | No | 1h | Fri 4/10/26 | Wed 4/15/26 | Data Migration Team | 366 | 368 |  | Fri 4/10/26 | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Fri 4/10/26 | Wed 4/15/26 | 1.2.1.18.4 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.18.6 | NA | 991 | 990 | 992 | 0h | No | Yes | No | No | No | 1.2.1.18.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.18.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Wed 4/15/26 | Wed 4/15/26 | Nevin Varkey | 367 |  | Sam Houff | Wed 4/15/26 | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.18.5 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 992 | 991 |  | 0h | No | Yes | No | No | No | 1.2.1.18.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.19 | Auto Scheduled | 100% | RTR_CM10_Credit_Management_Role | No | 5.56d | Fri 4/10/26 | Fri 4/17/26 |  | 362 | 376 |  | Fri 4/10/26 | ITC1 Data Load Tasks QS5 | Fri 4/10/26 | Fri 4/17/26 | 1.2.1.18 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.20 | NA | 768 | 766 | 752 | 0d | Yes | Yes | No | No | No | 1.2.1.19 | 4 | No | 500 | Complete | No | 0d
1.2.1.19.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Fri 4/10/26 | Fri 4/10/26 | Kasey Hughes | 346 | 371 |  | Fri 4/10/26 | RTR_CM10_Credit_Management_Role | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.15.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.19.2 | NA | 993 | 821 | 994 | 0m | No | Yes | No | No | No | 1.2.1.19.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.19.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Fri 4/10/26 | Fri 4/10/26 | Kasey Hughes | 370 | 372 | Brian Wagner | Fri 4/10/26 | RTR_CM10_Credit_Management_Role | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.19.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.19.3 | NA | 994 | 993 | 995 | 0m | No | Yes | No | No | No | 1.2.1.19.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.19.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Fri 4/17/26 | Fri 4/17/26 | Data Migration Team | 371 | 373 |  | Fri 4/17/26 | RTR_CM10_Credit_Management_Role | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.19.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.19.4 | NA | 995 | 994 | 996 | 0h | No | Yes | No | No | No | 1.2.1.19.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.19.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Fri 4/17/26 | Fri 4/17/26 | Kasey Hughes | 372 | 374391 | Brian Wagner | Fri 4/17/26 | RTR_CM10_Credit_Management_Role | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.19.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.19.5,1.2.1.22.1 | NA | 996 | 995 | 9971011 | 0h | No | Yes | No | No | No | 1.2.1.19.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.19.5 | Auto Scheduled | 100% | Load | No | 2h | Fri 4/17/26 | Fri 4/17/26 | Data Migration Team | 373 | 375 |  | Fri 4/17/26 | RTR_CM10_Credit_Management_Role | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.19.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.19.6 | NA | 997 | 996 | 998 | 0h | No | Yes | No | No | No | 1.2.1.19.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.19.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Fri 4/17/26 | Fri 4/17/26 | Kasey Hughes | 374 | 392557 | Brian Wagner | Fri 4/17/26 | RTR_CM10_Credit_Management_Role | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.19.5 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.22.2,1.2.1.52.2 | NA | 998 | 997 | 10121119 | 0h | No | Yes | No | No | No | 1.2.1.19.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.20 | Auto Scheduled | 100% | PTP_CM27_Vendor Master | No | 3.72d | Fri 4/10/26 | Thu 4/16/26 |  | 369 | 383 |  | Fri 4/10/26 | ITC1 Data Load Tasks QS5 | Fri 4/10/26 | Thu 4/16/26 | 1.2.1.19 | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.21 | NA | 752 | 768 | 692 | 0d | Yes | Yes | No | No | No | 1.2.1.20 | 4 | No | 500 | Complete | No | 0d
1.2.1.20.1 | Auto Scheduled | 100% | Extract File | No | 1h | Fri 4/10/26 | Fri 4/10/26 | Data Migration Team | 363 | 378 |  | Fri 4/10/26 | PTP_CM27_Vendor Master | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.18.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.20.2 | NA | 999 | 987 | 1000 | 0h | No | Yes | No | No | No | 1.2.1.20.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.20.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Fri 4/10/26 | Fri 4/10/26 | Nevin Varkey | 377 | 379 | Sam Houff | Fri 4/10/26 | PTP_CM27_Vendor Master | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.20.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.20.3 | NA | 1000 | 999 | 1001 | 0h | No | Yes | No | No | No | 1.2.1.20.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.20.3 | Auto Scheduled | 100% | Simulate Load | No | 2.25h | Fri 4/10/26 | Fri 4/10/26 | Data Migration Team | 378 | 380 |  | Fri 4/10/26 | PTP_CM27_Vendor Master | Fri 4/10/26 | Fri 4/10/26 | 1.2.1.20.2 | Fri 4/10/26 | Tue 4/14/26 | Finish No Earlier Than | 1.2.1.20.4 | Fri 4/10/26 | 1001 | 1000 | 1002 | 0h | No | Yes | No | No | No | 1.2.1.20.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.20.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Mon 4/13/26 | Mon 4/13/26 | Nevin Varkey | 379 |  | Sam Houff | Mon 4/13/26 | PTP_CM27_Vendor Master | Mon 4/13/26 | Mon 4/13/26 | 1.2.1.20.3 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1002 | 1001 |  | 0h | No | Yes | No | No | No | 1.2.1.20.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.20.5 | Auto Scheduled | 100% | Load | No | 1h | Wed 4/15/26 | Wed 4/15/26 | Data Migration Team |  | 382 |  | Wed 4/15/26 | PTP_CM27_Vendor Master | Wed 4/15/26 | Wed 4/15/26 |  | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.20.6 | NA | 1003 |  | 1004 | 0h | No | Yes | No | No | No | 1.2.1.20.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.20.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Wed 4/15/26 | Thu 4/16/26 | Nevin Varkey | 381 | 395410434 | Sam Houff | Wed 4/15/26 | PTP_CM27_Vendor Master | Wed 4/15/26 | Thu 4/16/26 | 1.2.1.20.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.23.1,1.2.1.25.2,1.2.1.28.5 | NA | 1004 | 1003 | 101410211042 | 0h | No | Yes | No | No | No | 1.2.1.20.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.21 | Auto Scheduled | 100% | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | No | 0.88d | Thu 4/16/26 | Thu 4/16/26 |  | 376 | 390 |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.20 | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.22 | NA | 692 | 752 | 935 | 0d | Yes | Yes | No | No | No | 1.2.1.21 | 4 | No | 500 | Complete | No | 0d
1.2.1.21.1 | Auto Scheduled | 100% | Extract File(Will Extract from LFA1) | No | 1h | Thu 4/16/26 | Thu 4/16/26 | Nevin Varkey |  | 385409 |  | Thu 4/16/26 | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 4/16/26 | Thu 4/16/26 |  | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.1.21.2,1.2.1.25.1 | Thu 4/16/26 | 1005 |  | 10061020 | 0h | No | Yes | No | No | No | 1.2.1.21.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.21.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Thu 4/16/26 | Thu 4/16/26 | Nevin Varkey | 384 | 386 | Sam Houff | Thu 4/16/26 | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.21.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.21.3 | NA | 1006 | 1005 | 1007 | 0h | No | Yes | No | No | No | 1.2.1.21.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.21.3 | Auto Scheduled | 100% | Simulate Load/ Not Needed | No | 1h | Thu 4/16/26 | Thu 4/16/26 | Nevin Varkey | 385 | 387388 |  | Thu 4/16/26 | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.21.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.21.4,1.2.1.21.5 | NA | 1007 | 1006 | 10081009 | 0h | No | Yes | No | No | No | 1.2.1.21.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.21.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Thu 4/16/26 | Thu 4/16/26 | Nevin Varkey | 386 |  | Sam Houff | Thu 4/16/26 | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.21.3 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1008 | 1007 |  | 0h | No | Yes | No | No | No | 1.2.1.21.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.21.5 | Auto Scheduled | 100% | Load | No | 1h | Thu 4/16/26 | Thu 4/16/26 | Nevin Varkkey | 386 | 389 |  | Thu 4/16/26 | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.21.3 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.21.6 | NA | 1009 | 1007 | 1010 | 0h | No | Yes | No | No | No | 1.2.1.21.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.21.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Thu 4/16/26 | Thu 4/16/26 | Nevin Varkey | 388 | 584 | Sam Houff | Thu 4/16/26 | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.21.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.58.1 | NA | 1010 | 1009 | 1176 | 0h | No | Yes | No | No | No | 1.2.1.21.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.22 | Auto Scheduled | 100% | RTR_****_Credit Hierarchy | No | 1.38d | Wed 4/15/26 | Thu 4/16/26 |  | 383 | 394 |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Thu 4/16/26 | 1.2.1.21 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.23 | NA | 935 | 692 | 693 | 0d | Yes | Yes | No | No | No | 1.2.1.22 | 4 | No | 500 | Complete | No | 0d
1.2.1.22.1 | Auto Scheduled | 100% | Manual File Staged and Posted "Ready" | No | 30m | Wed 4/15/26 | Wed 4/15/26 | Kasey Hughes | 373 |  | Brian Wagner | Wed 4/15/26 | RTR_****_Credit Hierarchy | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.19.4 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than |  | Wed 4/15/26 | 1011 | 996 |  | 0m | No | Yes | No | No | No | 1.2.1.22.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.22.2 | Auto Scheduled | 100% | Load | No | 2h | Wed 4/15/26 | Wed 4/15/26 | Kasey Hughes | 375 | 393 |  | Wed 4/15/26 | RTR_****_Credit Hierarchy | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.19.6 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.22.3 | NA | 1012 | 998 | 1013 | 0h | No | Yes | No | No | No | 1.2.1.22.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.22.3 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Thu 4/16/26 | Thu 4/16/26 | Kasey Hughes | 392 |  | Brian Wagner | Thu 4/16/26 | RTR_****_Credit Hierarchy | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.22.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1013 | 1012 |  | 0h | No | Yes | No | No | No | 1.2.1.22.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.23 | Auto Scheduled | 100% | PTP_CM27_BP_Intercompany Supplier | No | 1.13d | Mon 4/13/26 | Tue 4/14/26 |  | 390 | 401 |  | Mon 4/13/26 | ITC1 Data Load Tasks QS5 | Mon 4/13/26 | Tue 4/14/26 | 1.2.1.22 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.24 | NA | 693 | 935 | 1245 | 0d | Yes | Yes | No | No | No | 1.2.1.23 | 4 | No | 500 | Complete | No | 0d
1.2.1.23.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Mon 4/13/26 | Mon 4/13/26 | Nevin Varkey,Ric Haraida | 382 | 396 |  | Mon 4/13/26 | PTP_CM27_BP_Intercompany Supplier | Mon 4/13/26 | Mon 4/13/26 | 1.2.1.20.6 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.23.2 | NA | 1014 | 1004 | 1015 | 0m | No | Yes | No | No | No | 1.2.1.23.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.23.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Mon 4/13/26 | Mon 4/13/26 | Nevin Varkey,Ric Haraida | 395 | 397 | Sam Houff,Kim Kolesar | Mon 4/13/26 | PTP_CM27_BP_Intercompany Supplier | Mon 4/13/26 | Mon 4/13/26 | 1.2.1.23.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.23.3 | NA | 1015 | 1014 | 1016 | 0m | No | Yes | No | No | No | 1.2.1.23.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.23.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Mon 4/13/26 | Mon 4/13/26 | Data Migration Team | 396 | 398 |  | Mon 4/13/26 | PTP_CM27_BP_Intercompany Supplier | Mon 4/13/26 | Mon 4/13/26 | 1.2.1.23.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.23.4 | NA | 1016 | 1015 | 1017 | 0h | No | Yes | No | No | No | 1.2.1.23.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.23.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Mon 4/13/26 | Mon 4/13/26 | Nevin Varkey,Ric Haraida | 397 | 399 | Sam Houff,Kim Kolesar | Mon 4/13/26 | PTP_CM27_BP_Intercompany Supplier | Mon 4/13/26 | Mon 4/13/26 | 1.2.1.23.3 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.23.5 | NA | 1017 | 1016 | 1018 | 0h | No | Yes | No | No | No | 1.2.1.23.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.23.5 | Auto Scheduled | 100% | Load | No | 2h | Mon 4/13/26 | Tue 4/14/26 | Data Migration Team | 398 | 400556 |  | Mon 4/13/26 | PTP_CM27_BP_Intercompany Supplier | Mon 4/13/26 | Tue 4/14/26 | 1.2.1.23.4 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.23.6,1.2.1.52.1 | NA | 1018 | 1017 | 10191118 | 0h | No | Yes | No | No | No | 1.2.1.23.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.23.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Tue 4/14/26 | Tue 4/14/26 | Nevin Varkey,Ric Haraida | 399 |  | Sam Houff,Kim Kolesar | Tue 4/14/26 | PTP_CM27_BP_Intercompany Supplier | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.23.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1019 | 1018 |  | 0h | No | Yes | No | No | No | 1.2.1.23.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.24 | Auto Scheduled | 100% | PTP_CM27_BP_Intercompany Customer | No | 1.13d | Mon 4/13/26 | Tue 4/14/26 |  | 394 | 408 |  | Mon 4/13/26 | ITC1 Data Load Tasks QS5 | Mon 4/13/26 | Tue 4/14/26 | 1.2.1.23 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.25 | NA | 1245 | 693 | 741 | 0d | Yes | Yes | No | No | No | 1.2.1.24 | 4 | No | 500 | Complete | No | 0d
1.2.1.24.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Mon 4/13/26 | Mon 4/13/26 | Nevin Varkey,Ric Haraida |  |  |  | Mon 4/13/26 | PTP_CM27_BP_Intercompany Customer | Mon 4/13/26 | Mon 4/13/26 |  | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1246 |  |  | 0m | No | Yes | No | No | No | 1.2.1.24.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.24.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Mon 4/13/26 | Mon 4/13/26 | Nevin Varkey,Ric Haraida |  | 404 | Sam Houff,Kim Kolesar | Mon 4/13/26 | PTP_CM27_BP_Intercompany Customer | Mon 4/13/26 | Mon 4/13/26 |  | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.24.3 | NA | 1247 |  | 1248 | 0m | No | Yes | No | No | No | 1.2.1.24.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.24.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Mon 4/13/26 | Mon 4/13/26 | Data Migration Team | 403 | 405 |  | Mon 4/13/26 | PTP_CM27_BP_Intercompany Customer | Mon 4/13/26 | Mon 4/13/26 | 1.2.1.24.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.24.4 | NA | 1248 | 1247 | 1249 | 0h | No | Yes | No | No | No | 1.2.1.24.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.24.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Mon 4/13/26 | Mon 4/13/26 | Nevin Varkey,Ric Haraida | 404 | 406 | Sam Houff,Kim Kolesar | Mon 4/13/26 | PTP_CM27_BP_Intercompany Customer | Mon 4/13/26 | Mon 4/13/26 | 1.2.1.24.3 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.24.5 | NA | 1249 | 1248 | 1250 | 0h | No | Yes | No | No | No | 1.2.1.24.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.24.5 | Auto Scheduled | 100% | Load | No | 2h | Mon 4/13/26 | Tue 4/14/26 | Data Migration Team | 405 | 407556 |  | Mon 4/13/26 | PTP_CM27_BP_Intercompany Customer | Mon 4/13/26 | Tue 4/14/26 | 1.2.1.24.4 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.24.6,1.2.1.52.1 | NA | 1250 | 1249 | 12511118 | 0h | No | Yes | No | No | No | 1.2.1.24.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.24.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Tue 4/14/26 | Tue 4/14/26 | Nevin Varkey,Ric Haraida | 406 |  | Sam Houff,Kim Kolesar | Tue 4/14/26 | PTP_CM27_BP_Intercompany Customer | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.24.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1251 | 1250 |  | 0h | No | Yes | No | No | No | 1.2.1.24.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.25 | Auto Scheduled | 100% | PTP_CM26_Material_Master - All Types | No | 3.16d | Fri 4/10/26 | Wed 4/15/26 |  | 401 | 415 |  | Fri 4/10/26 | ITC1 Data Load Tasks QS5 | Fri 4/10/26 | Wed 4/15/26 | 1.2.1.24 | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.26 | NA | 741 | 1245 | 748 | 0d | Yes | Yes | No | No | No | 1.2.1.25 | 4 | No | 500 | Complete | No | 0d
1.2.1.25.1 | Auto Scheduled | 100% | Extract File | No | 5h | Fri 4/10/26 | Mon 4/13/26 | Data Migration Team | 384 |  |  | Fri 4/10/26 | PTP_CM26_Material_Master - All Types | Fri 4/10/26 | Mon 4/13/26 | 1.2.1.21.1 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1020 | 1005 |  | 0h | No | Yes | No | No | No | 1.2.1.25.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.25.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Mon 4/13/26 | Tue 4/14/26 | Nevin Varkey,Ric Haraida | 382 | 411 | Sam Houff,Kim Kolesar,Matt | Mon 4/13/26 | PTP_CM26_Material_Master - All Types | Mon 4/13/26 | Tue 4/14/26 | 1.2.1.20.6 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.25.3 | NA | 1021 | 1004 | 1022 | 0h | No | Yes | No | No | No | 1.2.1.25.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.25.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Tue 4/14/26 | Tue 4/14/26 | Data Migration Team | 410 | 412 |  | Tue 4/14/26 | PTP_CM26_Material_Master - All Types | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.25.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.25.4 | NA | 1022 | 1021 | 1023 | 0h | No | Yes | No | No | No | 1.2.1.25.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.25.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 4h | Tue 4/14/26 | Tue 4/14/26 | Nevin Varkey | 411 | 413 | Sam Houff,Kim Kolesar,Matt | Tue 4/14/26 | PTP_CM26_Material_Master - All Types | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.25.3 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.25.5 | NA | 1023 | 1022 | 1024 | 0h | No | Yes | No | No | No | 1.2.1.25.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.25.5 | Auto Scheduled | 100% | Load | No | 3h | Tue 4/14/26 | Wed 4/15/26 | Data Migration Team | 412 | 414417424 |  | Tue 4/14/26 | PTP_CM26_Material_Master - All Types | Tue 4/14/26 | Wed 4/15/26 | 1.2.1.25.4 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.25.6,1.2.1.26.2,1.2.1.27.2 | NA | 1024 | 1023 | 102510271033 | 0h | No | Yes | No | No | No | 1.2.1.25.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.25.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Wed 4/15/26 | Wed 4/15/26 | Nevin Varkey | 413 | 430437444 | Sam Houff,Kim Kolesar,Matt | Wed 4/15/26 | PTP_CM26_Material_Master - All Types | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.25.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.28.1,1.2.1.29.1,1.2.1.30.1 | NA | 1025 | 1024 | 103810441050 | 0h | No | Yes | No | No | No | 1.2.1.25.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.26 | Auto Scheduled | 100% | PTP_CM26_Material_Master - SERV - Service Materials | No | 5.88d | Tue 4/7/26 | Wed 4/15/26 |  | 408 | 422 |  | Tue 4/7/26 | ITC1 Data Load Tasks QS5 | Tue 4/7/26 | Wed 4/15/26 | 1.2.1.25 | Tue 4/7/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.27 | NA | 748 | 741 | 749 | 0d | Yes | Yes | No | No | No | 1.2.1.26 | 4 | No | 500 | Complete | No | 0d
1.2.1.26.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Tue 4/7/26 | Tue 4/7/26 | Nevin Varkey,Ric Haraida | 285 |  |  | Tue 4/7/26 | PTP_CM26_Material_Master - SERV - Service Materials | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.5.6 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 1026 | 807 |  | 0m | No | Yes | No | No | No | 1.2.1.26.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.26.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Tue 4/14/26 | Tue 4/14/26 | Nevin Varkey,Ric Haraida | 413 | 418 | Sam Houff,Kim Kolesar | Tue 4/14/26 | PTP_CM26_Material_Master - SERV - Service Materials | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.25.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.26.3 | NA | 1027 | 1024 | 1028 | 0m | No | Yes | No | No | No | 1.2.1.26.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.26.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Tue 4/14/26 | Tue 4/14/26 | Data Migration Team | 417 | 419 |  | Tue 4/14/26 | PTP_CM26_Material_Master - SERV - Service Materials | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.26.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.26.4 | NA | 1028 | 1027 | 1029 | 0h | No | Yes | No | No | No | 1.2.1.26.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.26.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Tue 4/14/26 | Wed 4/15/26 | Nevin Varkey,Ric Haraida | 418 | 420 | Sam Houff,Kim Kolesar | Tue 4/14/26 | PTP_CM26_Material_Master - SERV - Service Materials | Tue 4/14/26 | Wed 4/15/26 | 1.2.1.26.3 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.26.5 | NA | 1029 | 1028 | 1030 | 0h | No | Yes | No | No | No | 1.2.1.26.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.26.5 | Auto Scheduled | 100% | Load | No | 2h | Wed 4/15/26 | Wed 4/15/26 | Data Migration Team | 419 | 421 |  | Wed 4/15/26 | PTP_CM26_Material_Master - SERV - Service Materials | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.26.4 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.26.6 | NA | 1030 | 1029 | 1031 | 0h | No | Yes | No | No | No | 1.2.1.26.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.26.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Wed 4/15/26 | Wed 4/15/26 | Nevin Varkey,Ric Haraida | 420 |  | Sam Houff,Kim Kolesar | Wed 4/15/26 | PTP_CM26_Material_Master - SERV - Service Materials | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.26.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 1031 | 1030 |  | 0h | No | Yes | No | No | No | 1.2.1.26.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.27 | Auto Scheduled | 100% | PTP_CM26_Material_Master - KMAT - Configurable Materials | No | 5.88d | Tue 4/7/26 | Wed 4/15/26 |  | 415 | 515512 |  | Tue 4/7/26 | ITC1 Data Load Tasks QS5 | Tue 4/7/26 | Wed 4/15/26 | 1.2.1.26 | Tue 4/7/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.43.1,1.2.1.42.1 | NA | 749 | 748 | 11621160 | 0d | Yes | Yes | No | No | No | 1.2.1.27 | 4 | No | 500 | Complete | No | 0d
1.2.1.27.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Tue 4/7/26 | Tue 4/7/26 | Eric Heisler | 285 |  |  | Tue 4/7/26 | PTP_CM26_Material_Master - KMAT - Configurable Materials | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.5.6 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 1032 | 807 |  | 0m | No | Yes | No | No | No | 1.2.1.27.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.27.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Tue 4/14/26 | Tue 4/14/26 | Eric Heisler | 413 | 425 | Sam Houff,Kim Kolesar,Matt | Tue 4/14/26 | PTP_CM26_Material_Master - KMAT - Configurable Materials | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.25.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.27.3 | NA | 1033 | 1024 | 1034 | 0m | No | Yes | No | No | No | 1.2.1.27.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.27.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Tue 4/14/26 | Tue 4/14/26 | Data Migration Team | 424 | 426 |  | Tue 4/14/26 | PTP_CM26_Material_Master - KMAT - Configurable Materials | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.27.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.1.27.4 | NA | 1034 | 1033 | 1035 | 0h | No | Yes | No | No | No | 1.2.1.27.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.27.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Tue 4/14/26 | Wed 4/15/26 | Eric Heisler | 425 | 427 | Sam Houff,Kim Kolesar,Matt | Tue 4/14/26 | PTP_CM26_Material_Master - KMAT - Configurable Materials | Tue 4/14/26 | Wed 4/15/26 | 1.2.1.27.3 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.27.5 | NA | 1035 | 1034 | 1036 | 0h | No | Yes | No | No | No | 1.2.1.27.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.27.5 | Auto Scheduled | 100% | Load | No | 2h | Wed 4/15/26 | Wed 4/15/26 | Data Migration Team | 426 | 428 |  | Wed 4/15/26 | PTP_CM26_Material_Master - KMAT - Configurable Materials | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.27.4 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.27.6 | NA | 1036 | 1035 | 1037 | 0h | No | Yes | No | No | No | 1.2.1.27.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.27.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Wed 4/15/26 | Wed 4/15/26 | Eric Heisler | 427 | 430437444509527 | Sam Houff,Kim Kolesar,Matt | Wed 4/15/26 | PTP_CM26_Material_Master - KMAT - Configurable Materials | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.27.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.28.1,1.2.1.29.1,1.2.1.30.1,1.2.1.41.1,1.2.1.47.1 | NA | 1037 | 1036 | 1.0381e+19 | 0h | No | Yes | No | No | No | 1.2.1.27.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.28 | Auto Scheduled | 100% | PTP_CM28_Purchase_Info_Records | No | 1.59d | Wed 4/15/26 | Fri 4/17/26 |  |  |  |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Fri 4/17/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 703 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.28 | 4 | No | 500 | Complete | No | 0d
1.2.1.28.1 | Auto Scheduled | 100% | Extract File | No | 1h | Wed 4/15/26 | Wed 4/15/26 | Data Migration Team | 414428 | 431451 |  | Wed 4/15/26 | PTP_CM28_Purchase_Info_Records | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.25.6,1.2.1.27.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.28.2,1.2.1.31.1 | NA | 1038 | 10251037 | 10391056 | 0h | No | Yes | No | No | No | 1.2.1.28.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.28.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Wed 4/15/26 | Thu 4/16/26 | Nevin Varkey | 430 | 432 | Sam Houff | Wed 4/15/26 | PTP_CM28_Purchase_Info_Records | Wed 4/15/26 | Thu 4/16/26 | 1.2.1.28.1 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.28.3 | NA | 1039 | 1038 | 1040 | 0h | No | Yes | No | No | No | 1.2.1.28.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.28.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Thu 4/16/26 | Thu 4/16/26 | Data Migration Team | 431 | 433 |  | Thu 4/16/26 | PTP_CM28_Purchase_Info_Records | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.28.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.28.4 | NA | 1040 | 1039 | 1041 | 0h | No | Yes | No | No | No | 1.2.1.28.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.28.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Fri 4/17/26 | Fri 4/17/26 | Nevin Varkey | 432 |  | Sam Houff | Fri 4/17/26 | PTP_CM28_Purchase_Info_Records | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.28.3 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than |  | Fri 4/17/26 | 1041 | 1040 |  | 0h | No | Yes | No | No | No | 1.2.1.28.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.28.5 | Auto Scheduled | 100% | Load | No | 1h | Fri 4/17/26 | Fri 4/17/26 | Data Migration Team | 382 | 435 |  | Fri 4/17/26 | PTP_CM28_Purchase_Info_Records | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.20.6 | Wed 4/15/26 | Wed 4/15/26 | Start No Earlier Than | 1.2.1.28.6 | Fri 4/17/26 | 1042 | 1004 | 1043 | 0h | No | Yes | No | No | No | 1.2.1.28.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.28.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Fri 4/17/26 | Fri 4/17/26 | Nevin Varkey | 434 |  | Sam Houff | Fri 4/17/26 | PTP_CM28_Purchase_Info_Records | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.28.5 | Wed 4/15/26 | Wed 4/15/26 | Start No Earlier Than |  | Fri 4/17/26 | 1043 | 1042 |  | 0h | No | Yes | No | No | No | 1.2.1.28.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.29 | Auto Scheduled | 100% | PTP_CM28_Purchase_Info_Record External Processing | No | 1.47d | Wed 4/15/26 | Fri 4/17/26 |  |  |  |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Fri 4/17/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 936 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.29 | 4 | No | 500 | Complete | No | 0d
1.2.1.29.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Wed 4/15/26 | Wed 4/15/26 | Nevin Varkey | 414428 | 438 |  | Wed 4/15/26 | PTP_CM28_Purchase_Info_Record External Processing | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.25.6,1.2.1.27.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.29.2 | NA | 1044 | 10251037 | 1045 | 0m | No | Yes | No | No | No | 1.2.1.29.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.29.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Wed 4/15/26 | Wed 4/15/26 | Nevin Varkey | 437 | 439 | Sam Houff | Wed 4/15/26 | PTP_CM28_Purchase_Info_Record External Processing | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.29.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.29.3 | NA | 1045 | 1044 | 1046 | 0m | No | Yes | No | No | No | 1.2.1.29.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.29.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Thu 4/16/26 | Thu 4/16/26 | Data Migration Team | 438 | 440 |  | Thu 4/16/26 | PTP_CM28_Purchase_Info_Record External Processing | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.29.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.29.4 | NA | 1046 | 1045 | 1047 | 0h | No | Yes | No | No | No | 1.2.1.29.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.29.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Thu 4/16/26 | Thu 4/16/26 | Nevin Varkey | 439 | 441 | Sam Houff | Thu 4/16/26 | PTP_CM28_Purchase_Info_Record External Processing | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.29.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.29.5 | NA | 1047 | 1046 | 1048 | 0h | No | Yes | No | No | No | 1.2.1.29.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.29.5 | Auto Scheduled | 100% | Load | No | 2h | Fri 4/17/26 | Fri 4/17/26 | Data Migration Team | 440 | 442 |  | Fri 4/17/26 | PTP_CM28_Purchase_Info_Record External Processing | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.29.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.29.6 | NA | 1048 | 1047 | 1049 | 0h | No | Yes | No | No | No | 1.2.1.29.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.29.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Thu 4/16/26 | Thu 4/16/26 | Nevin Varkey | 441 |  | Sam Houff | Thu 4/16/26 | PTP_CM28_Purchase_Info_Record External Processing | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.29.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1049 | 1048 |  | 0h | No | Yes | No | No | No | 1.2.1.29.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.30 | Auto Scheduled | 100% | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | No | 1.13d | Wed 4/15/26 | Thu 4/16/26 |  |  |  |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Thu 4/16/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 937 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.30 | 4 | No | 500 | Complete | No | 0d
1.2.1.30.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Wed 4/15/26 | Wed 4/15/26 | Nevin Varkey | 414428 | 445 |  | Wed 4/15/26 | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.25.6,1.2.1.27.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.30.2 | NA | 1050 | 10251037 | 1051 | 0m | No | Yes | No | No | No | 1.2.1.30.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.30.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Wed 4/15/26 | Wed 4/15/26 | Nevin Varkey | 444 | 446 | Sam Houff | Wed 4/15/26 | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.30.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.30.3 | NA | 1051 | 1050 | 1052 | 0m | No | Yes | No | No | No | 1.2.1.30.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.30.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Wed 4/15/26 | Thu 4/16/26 | Data Migration Team | 445 | 447578 |  | Wed 4/15/26 | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Wed 4/15/26 | Thu 4/16/26 | 1.2.1.30.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.30.4,1.2.1.56.1 | NA | 1052 | 1051 | 10531171 | 0h | No | Yes | No | No | No | 1.2.1.30.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.30.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Thu 4/16/26 | Thu 4/16/26 | Nevin Varkey | 446 | 448 | Sam Houff | Thu 4/16/26 | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.30.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.30.5 | NA | 1053 | 1052 | 1054 | 0h | No | Yes | No | No | No | 1.2.1.30.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.30.5 | Auto Scheduled | 100% | Load | No | 2h | Thu 4/16/26 | Thu 4/16/26 | Data Migration Team | 447 | 449 |  | Thu 4/16/26 | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.30.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.30.6 | NA | 1054 | 1053 | 1055 | 0h | No | Yes | No | No | No | 1.2.1.30.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.30.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Thu 4/16/26 | Thu 4/16/26 | Nevin Varkey | 448 |  | Sam Houff | Thu 4/16/26 | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.30.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1055 | 1054 |  | 0h | No | Yes | No | No | No | 1.2.1.30.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.31 | Auto Scheduled | 100% | PTM_CM31_BOM Conversion | No | 2.09d | Wed 4/15/26 | Fri 4/17/26 |  |  |  |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Fri 4/17/26 |  | Wed 4/15/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 694 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.31 | 4 | No | 500 | Complete | No | 0d
1.2.1.31.1 | Auto Scheduled | 100% | Extract File | No | 1h | Wed 4/15/26 | Thu 4/16/26 | Data Migration Team | 430 | 452458 |  | Wed 4/15/26 | PTM_CM31_BOM Conversion | Wed 4/15/26 | Thu 4/16/26 | 1.2.1.28.1 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.31.2,1.2.1.32.1 | NA | 1056 | 1038 | 10571062 | 0h | No | Yes | No | No | No | 1.2.1.31.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.31.2 | Auto Scheduled | 100% | Pre Load Validation | No | 0.5h | Thu 4/16/26 | Thu 4/16/26 | Brad Meseck | 451 | 453 | Matt Palastro, Dave Duda | Thu 4/16/26 | PTM_CM31_BOM Conversion | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.31.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.31.3 | NA | 1057 | 1056 | 1058 | 0h | No | Yes | No | No | No | 1.2.1.31.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.31.3 | Auto Scheduled | 100% | Simulate Load | No | 15.5h | Thu 4/16/26 | Fri 4/17/26 | Data Migration Team | 452 | 454 |  | Thu 4/16/26 | PTM_CM31_BOM Conversion | Thu 4/16/26 | Fri 4/17/26 | 1.2.1.31.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.1.31.4 | Fri 4/17/26 | 1058 | 1057 | 1059 | 0h | No | Yes | No | No | No | 1.2.1.31.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.31.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 0.5h | Fri 4/17/26 | Fri 4/17/26 | Brad Meseck | 453 | 455 | Matt Palastro, Dave Duda | Fri 4/17/26 | PTM_CM31_BOM Conversion | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.31.3 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 2026-04-01 | Fri 4/17/26 | 1059 | 1058 | 1060 | 0h | No | Yes | No | No | No | 1.2.1.31.4 | 5 | No | 500 | Complete | No | 0h
2026-04-01 | Auto Scheduled | 100% | Load | No | 1h | Fri 4/17/26 | Fri 4/17/26 | Data Migration Team | 454 | 456 |  | Fri 4/17/26 | PTM_CM31_BOM Conversion | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.31.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.31.6 | NA | 1060 | 1059 | 1061 | 0h | No | Yes | No | No | No | 1.2.1.31.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.31.6 | Auto Scheduled | 100% | Post Load Validation | No | 0.5h | Fri 4/17/26 | Fri 4/17/26 | Brad Meseck | 455 | 459 | Matt Palastro, Dave Duda | Fri 4/17/26 | PTM_CM31_BOM Conversion | Fri 4/17/26 | Fri 4/17/26 | 2026-04-01 | Thu 4/16/26 | Fri 4/17/26 | Finish No Earlier Than | 1.2.1.32.2 | Thu 4/16/26 | 1061 | 1060 | 1063 | 0h | No | Yes | No | No | No | 1.2.1.31.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.32 | Auto Scheduled | 100% | PTM_CM40_Work Center Conversion | No | 0.38d | Thu 4/16/26 | Thu 4/16/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Thu 4/16/26 |  | Thu 4/16/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 695 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.32 | 4 | No | 500 | Complete | No | 0d
1.2.1.32.1 | Auto Scheduled | 100% | Extract File | No | 1h | Thu 4/16/26 | Thu 4/16/26 | Data Migration Team | 451 | 465 |  | Thu 4/16/26 | PTM_CM40_Work Center Conversion | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.31.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.33.1 | NA | 1062 | 1056 | 1075 | 0h | No | Yes | No | No | No | 1.2.1.32.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.32.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Thu 4/16/26 | Thu 4/16/26 | Brad Meseck | 456 | 460 | Matt Palastro, Dave Duda | Thu 4/16/26 | PTM_CM40_Work Center Conversion | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.31.6 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.32.3 | NA | 1063 | 1061 | 1064 | 0h | No | Yes | No | No | No | 1.2.1.32.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.32.3 | Auto Scheduled | 100% | Simulate Load | No | 0.25h | Thu 4/16/26 | Thu 4/16/26 | Data Migration Team | 459 | 461 |  | Thu 4/16/26 | PTM_CM40_Work Center Conversion | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.32.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.32.4 | NA | 1064 | 1063 | 1065 | 0h | No | Yes | No | No | No | 1.2.1.32.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.32.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 0.5h | Thu 4/16/26 | Thu 4/16/26 | Brad Meseck | 460 | 462 | Matt Palastro, Dave Duda | Thu 4/16/26 | PTM_CM40_Work Center Conversion | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.32.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.32.5 | NA | 1065 | 1064 | 1066 | 0h | No | Yes | No | No | No | 1.2.1.32.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.32.5 | Auto Scheduled | 100% | Load | No | 1h | Thu 4/16/26 | Thu 4/16/26 | Data Migration Team | 461 | 463 |  | Thu 4/16/26 | PTM_CM40_Work Center Conversion | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.32.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.32.6 | NA | 1066 | 1065 | 1067 | 0h | No | Yes | No | No | No | 1.2.1.32.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.32.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Thu 4/16/26 | Thu 4/16/26 | Brad Meseck | 462 | 466 | Matt Palastro, Dave Duda | Thu 4/16/26 | PTM_CM40_Work Center Conversion | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.32.5 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.1.33.2 | NA | 1067 | 1066 | 1076 | 0h | No | Yes | No | No | No | 1.2.1.32.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.33 | Auto Scheduled | 100% | PTM_CM38_Routing Conversion | No | 2.75d | Thu 4/16/26 | Mon 4/20/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Mon 4/20/26 |  | Thu 4/16/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 707 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.33 | 4 | No | 500 | Complete | No | 0d
1.2.1.33.1 | Auto Scheduled | 100% | Extract File | No | 1h | Thu 4/16/26 | Thu 4/16/26 | Data Migration Team | 458 | 472 |  | Thu 4/16/26 | PTM_CM38_Routing Conversion | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.32.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.34.1 | NA | 1075 | 1062 | 1081 | 0h | No | Yes | No | No | No | 1.2.1.33.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.33.2 | Auto Scheduled | 100% | Pre Load Validation | No | 2h | Thu 4/16/26 | Thu 4/16/26 | Brad Meseck | 463 | 467 | Matt Palastro, Dave Duda | Thu 4/16/26 | PTM_CM38_Routing Conversion | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.32.6 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.1.33.3 | NA | 1076 | 1067 | 1077 | 0h | No | Yes | No | No | No | 1.2.1.33.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.33.3 | Auto Scheduled | 100% | Simulate Load | No | 2h | Mon 4/20/26 | Mon 4/20/26 | Data Migration Team | 466 | 468SS |  | Mon 4/20/26 | PTM_CM38_Routing Conversion | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.33.2 | Mon 4/20/26 | Mon 4/20/26 | Finish No Earlier Than | 1.2.1.33.4[SS] | Fri 4/17/26 | 1077 | 1076 | 1078SS | 0h | No | Yes | No | No | No | 1.2.1.33.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.33.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 3h | Mon 4/20/26 | Mon 4/20/26 | Brad Meseck | 467SS | 469 | Matt Palastro, Dave Duda | Mon 4/20/26 | PTM_CM38_Routing Conversion | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.33.3[SS] | Mon 4/20/26 | Mon 4/20/26 | Start No Earlier Than | 1.2.1.33.5 | Fri 4/17/26 | 1078 | 1077SS | 1079 | 0h | No | Yes | No | No | No | 1.2.1.33.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.33.5 | Auto Scheduled | 100% | Load | No | 1h | Mon 4/20/26 | Mon 4/20/26 | Data Migration Team | 468 | 470 |  | Mon 4/20/26 | PTM_CM38_Routing Conversion | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.33.4 | Mon 4/20/26 | Mon 4/20/26 | Start No Earlier Than | 1.2.1.33.6 | Mon 4/20/26 | 1079 | 1078 | 1080 | 0h | No | Yes | No | No | No | 1.2.1.33.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.33.6 | Auto Scheduled | 100% | Post Load Validation | No | 2h | Mon 4/20/26 | Mon 4/20/26 | Brad Meseck | 469 |  | Matt Palastro, Dave Duda | Mon 4/20/26 | PTM_CM38_Routing Conversion | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.33.5 | Mon 4/20/26 | Tue 4/21/26 | Start No Earlier Than |  | Mon 4/20/26 | 1080 | 1079 |  | 0h | No | Yes | No | No | No | 1.2.1.33.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.34 | Auto Scheduled | 100% | PTM_CM36_Production Version Conversion | No | 1.13d | Mon 4/20/26 | Tue 4/21/26 |  |  |  |  | Mon 4/20/26 | ITC1 Data Load Tasks QS5 | Mon 4/20/26 | Tue 4/21/26 |  | Thu 4/16/26 | Fri 4/17/26 | Start No Earlier Than |  | Fri 4/17/26 | 709 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.34 | 4 | No | 500 | Complete | No | 0d
1.2.1.34.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Mon 4/20/26 | Mon 4/20/26 | Brad Meseck | 465 | 473567 |  | Mon 4/20/26 | PTM_CM36_Production Version Conversion | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.33.1 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than | 1.2.1.34.2,1.2.1.54.1 | Mon 4/20/26 | 1081 | 1075 | 10821127 | 0m | No | Yes | No | No | No | 1.2.1.34.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.34.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Mon 4/20/26 | Mon 4/20/26 | Brad Meseck | 472 | 474 | Matt Palastro, Dave Duda | Mon 4/20/26 | PTM_CM36_Production Version Conversion | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.34.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.34.3 | NA | 1082 | 1081 | 1083 | 0m | No | Yes | No | No | No | 1.2.1.34.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.34.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Mon 4/20/26 | Mon 4/20/26 | Data Migration Team | 473 | 475 |  | Mon 4/20/26 | PTM_CM36_Production Version Conversion | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.34.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.34.4 | NA | 1083 | 1082 | 1084 | 0h | No | Yes | No | No | No | 1.2.1.34.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.34.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Mon 4/20/26 | Mon 4/20/26 | Brad Meseck | 474 | 476 | Matt Palastro, Dave Duda | Mon 4/20/26 | PTM_CM36_Production Version Conversion | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.34.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.34.5 | NA | 1084 | 1083 | 1085 | 0h | No | Yes | No | No | No | 1.2.1.34.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.34.5 | Auto Scheduled | 100% | Load | No | 2h | Mon 4/20/26 | Mon 4/20/26 | Data Migration Team | 475 | 477 |  | Mon 4/20/26 | PTM_CM36_Production Version Conversion | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.34.4 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.34.6 | NA | 1085 | 1084 | 1086 | 0h | No | Yes | No | No | No | 1.2.1.34.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.34.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Mon 4/20/26 | Tue 4/21/26 | Brad Meseck | 476 | 479 | Matt Palastro, Dave Duda | Mon 4/20/26 | PTM_CM36_Production Version Conversion | Mon 4/20/26 | Tue 4/21/26 | 1.2.1.34.5 | Fri 4/17/26 | Fri 4/17/26 | Finish No Earlier Than | 1.2.1.35.1 | Fri 4/17/26 | 1086 | 1085 | 1088 | 0h | No | Yes | No | No | No | 1.2.1.34.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.35 | Auto Scheduled | 100% | PTM_CM35_Inspection Plan | No | 1.13d | Tue 4/21/26 | Wed 4/22/26 |  |  |  |  | Tue 4/21/26 | ITC1 Data Load Tasks QS5 | Tue 4/21/26 | Wed 4/22/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 710 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.35 | 4 | No | 500 | Complete | No | 0d
1.2.1.35.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Tue 4/21/26 | Tue 4/21/26 | Brad Meseck | 477 | 480486 |  | Tue 4/21/26 | PTM_CM35_Inspection Plan | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.34.6 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.35.2,1.2.1.36.1 | NA | 1088 | 1086 | 10891196 | 0m | No | Yes | No | No | No | 1.2.1.35.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.35.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Tue 4/21/26 | Tue 4/21/26 | Brad Meseck | 479 | 481 | Matt Palastro, Dave Duda | Tue 4/21/26 | PTM_CM35_Inspection Plan | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.35.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.35.3 | NA | 1089 | 1088 | 1090 | 0m | No | Yes | No | No | No | 1.2.1.35.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.35.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Tue 4/21/26 | Tue 4/21/26 | Data Migration Team | 480 | 482 |  | Tue 4/21/26 | PTM_CM35_Inspection Plan | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.35.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.35.4 | NA | 1090 | 1089 | 1091 | 0h | No | Yes | No | No | No | 1.2.1.35.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.35.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Tue 4/21/26 | Tue 4/21/26 | Brad Meseck | 481 | 483 | Matt Palastro, Dave Duda | Tue 4/21/26 | PTM_CM35_Inspection Plan | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.35.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.35.5 | NA | 1091 | 1090 | 1092 | 0h | No | Yes | No | No | No | 1.2.1.35.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.35.5 | Auto Scheduled | 100% | Load | No | 2h | Tue 4/21/26 | Tue 4/21/26 | Data Migration Team | 482 | 484 |  | Tue 4/21/26 | PTM_CM35_Inspection Plan | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.35.4 | Fri 4/17/26 | Mon 4/20/26 | Finish No Earlier Than | 1.2.1.35.6 | Fri 4/17/26 | 1092 | 1091 | 1093 | 0h | No | Yes | No | No | No | 1.2.1.35.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.35.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Tue 4/21/26 | Wed 4/22/26 | Brad Meseck | 483 |  | Matt Palastro, Dave Duda | Tue 4/21/26 | PTM_CM35_Inspection Plan | Tue 4/21/26 | Wed 4/22/26 | 1.2.1.35.5 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 1093 | 1092 |  | 0h | No | Yes | No | No | No | 1.2.1.35.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.36 | Auto Scheduled | 100% | PTM_CM48_Equipment_Master_Serial Numbers | No | 1.13d | Tue 4/21/26 | Wed 4/22/26 |  |  |  |  | Tue 4/21/26 | ITC1 Data Load Tasks QS5 | Tue 4/21/26 | Wed 4/22/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 1194 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.36 | 4 | No | 500 | Complete | No | 0d
1.2.1.36.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Tue 4/21/26 | Tue 4/21/26 | Brad Meseck | 479 | 487 |  | Tue 4/21/26 | PTM_CM48_Equipment_Master_Serial Numbers | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.35.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.36.2 | NA | 1196 | 1088 | 1197 | 0m | No | Yes | No | No | No | 1.2.1.36.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.36.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Tue 4/21/26 | Tue 4/21/26 | Brad Meseck | 486 | 488 | Matt Palastro, Dave Duda | Tue 4/21/26 | PTM_CM48_Equipment_Master_Serial Numbers | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.36.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.36.3 | NA | 1197 | 1196 | 1198 | 0m | No | Yes | No | No | No | 1.2.1.36.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.36.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Tue 4/21/26 | Tue 4/21/26 | Data Migration Team | 487 | 489 |  | Tue 4/21/26 | PTM_CM48_Equipment_Master_Serial Numbers | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.36.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.36.4 | NA | 1198 | 1197 | 1199 | 0h | No | Yes | No | No | No | 1.2.1.36.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.36.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Tue 4/21/26 | Tue 4/21/26 | Brad Meseck | 488 | 490 | Matt Palastro, Dave Duda | Tue 4/21/26 | PTM_CM48_Equipment_Master_Serial Numbers | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.36.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.36.5 | NA | 1199 | 1198 | 1200 | 0h | No | Yes | No | No | No | 1.2.1.36.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.36.5 | Auto Scheduled | 100% | Load | No | 2h | Tue 4/21/26 | Tue 4/21/26 | Data Migration Team | 489 | 491 |  | Tue 4/21/26 | PTM_CM48_Equipment_Master_Serial Numbers | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.36.4 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.1.36.6 | NA | 1200 | 1199 | 1201 | 0h | No | Yes | No | No | No | 1.2.1.36.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.36.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Tue 4/21/26 | Wed 4/22/26 | Brad Meseck | 490 | 493 | Matt Palastro, Dave Duda | Tue 4/21/26 | PTM_CM48_Equipment_Master_Serial Numbers | Tue 4/21/26 | Wed 4/22/26 | 1.2.1.36.5 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.1.37.1 | NA | 1201 | 1200 | 1202 | 0h | No | Yes | No | No | No | 1.2.1.36.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.37 | Auto Scheduled | 100% | PTM_CM48_Equipment_Master_Service | No | 2.06d | Tue 4/21/26 | Thu 4/23/26 |  |  |  |  | Tue 4/21/26 | ITC1 Data Load Tasks QS5 | Tue 4/21/26 | Thu 4/23/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 1195 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.37 | 4 | No | 500 | Complete | No | 0d
1.2.1.37.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Wed 4/22/26 | Wed 4/22/26 | Brad Meseck | 491 | 494 |  | Wed 4/22/26 | PTM_CM48_Equipment_Master_Service | Wed 4/22/26 | Wed 4/22/26 | 1.2.1.36.6 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.1.37.2 | NA | 1202 | 1201 | 1203 | 0m | No | Yes | No | No | No | 1.2.1.37.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.37.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Wed 4/22/26 | Wed 4/22/26 | Brad Meseck | 493 | 495 | Matt Palastro, Dave Duda | Wed 4/22/26 | PTM_CM48_Equipment_Master_Service | Wed 4/22/26 | Wed 4/22/26 | 1.2.1.37.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.1.37.3 | NA | 1203 | 1202 | 1204 | 0m | No | Yes | No | No | No | 1.2.1.37.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.37.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Wed 4/22/26 | Wed 4/22/26 | Data Migration Team | 494 | 496 |  | Wed 4/22/26 | PTM_CM48_Equipment_Master_Service | Wed 4/22/26 | Wed 4/22/26 | 1.2.1.37.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.1.37.4 | NA | 1204 | 1203 | 1205 | 0h | No | Yes | No | No | No | 1.2.1.37.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.37.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Wed 4/22/26 | Wed 4/22/26 | Brad Meseck | 495 | 497 | Matt Palastro, Dave Duda | Wed 4/22/26 | PTM_CM48_Equipment_Master_Service | Wed 4/22/26 | Wed 4/22/26 | 1.2.1.37.3 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible | 1.2.1.37.5 | NA | 1205 | 1204 | 1206 | 0h | No | Yes | No | No | No | 1.2.1.37.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.37.5 | Auto Scheduled | 100% | Load | No | 2h | Wed 4/22/26 | Thu 4/23/26 | Data Migration Team | 496 |  |  | Wed 4/22/26 | PTM_CM48_Equipment_Master_Service | Wed 4/22/26 | Thu 4/23/26 | 1.2.1.37.4 | Tue 4/21/26 | Tue 4/21/26 | Finish No Earlier Than |  | Tue 4/21/26 | 1206 | 1205 |  | 0h | No | Yes | No | No | No | 1.2.1.37.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.37.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Tue 4/21/26 | Tue 4/21/26 | Brad Meseck |  |  | Matt Palastro, Dave Duda | Tue 4/21/26 | PTM_CM48_Equipment_Master_Service | Tue 4/21/26 | Tue 4/21/26 |  | Tue 4/21/26 | Tue 4/21/26 | Start No Earlier Than |  | Tue 4/21/26 | 1207 |  |  | 0h | No | Yes | No | No | No | 1.2.1.37.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.38 | Auto Scheduled | 100% | VC_Object Dependencies | No | 0.63d | Mon 4/6/26 | Mon 4/6/26 |  |  |  |  | Mon 4/6/26 | ITC1 Data Load Tasks QS5 | Mon 4/6/26 | Mon 4/6/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 938 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.38 | 4 | No | 500 | Complete | No | 0d
1.2.1.38.1 | Auto Scheduled | 100% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Mon 4/6/26 | Mon 4/6/26 | Eric Heisler | 261 | 501 |  | Mon 4/6/26 | VC_Object Dependencies | Mon 4/6/26 | Mon 4/6/26 | 1.2.1.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.1.38.2 | NA | 1151 | 956 | 1153 | 0h | No | Yes | No | No | No | 1.2.1.38.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.38.2 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Mon 4/6/26 | Mon 4/6/26 | Eric Heisler | 500 | 503 | Matt Palastro, Dave Duda | Mon 4/6/26 | VC_Object Dependencies | Mon 4/6/26 | Mon 4/6/26 | 1.2.1.38.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.1.39.1 | NA | 1153 | 1151 | 1154 | 0h | No | Yes | No | No | No | 1.2.1.38.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.39 | Auto Scheduled | 100% | VC_Characteristics | No | 0.63d | Mon 4/6/26 | Tue 4/7/26 |  |  |  |  | Mon 4/6/26 | ITC1 Data Load Tasks QS5 | Mon 4/6/26 | Tue 4/7/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 939 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.39 | 4 | No | 500 | Complete | No | 0d
1.2.1.39.1 | Auto Scheduled | 100% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Mon 4/6/26 | Mon 4/6/26 | Eric Heisler | 501 | 504 |  | Mon 4/6/26 | VC_Characteristics | Mon 4/6/26 | Mon 4/6/26 | 1.2.1.38.2 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.1.39.2 | NA | 1154 | 1153 | 1155 | 0h | No | Yes | No | No | No | 1.2.1.39.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.39.2 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Mon 4/6/26 | Tue 4/7/26 | Eric Heisler | 503 | 506 | Matt Palastro, Dave Duda | Mon 4/6/26 | VC_Characteristics | Mon 4/6/26 | Tue 4/7/26 | 1.2.1.39.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.40.1 | NA | 1155 | 1154 | 1156 | 0h | No | Yes | No | No | No | 1.2.1.39.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.40 | Auto Scheduled | 100% | VC_Classes | No | 0.63d | Tue 4/7/26 | Tue 4/7/26 |  |  |  |  | Tue 4/7/26 | ITC1 Data Load Tasks QS5 | Tue 4/7/26 | Tue 4/7/26 |  | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 940 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.40 | 4 | No | 500 | Complete | No | 0d
1.2.1.40.1 | Auto Scheduled | 100% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Tue 4/7/26 | Tue 4/7/26 | Eric Heisler | 504 | 507 |  | Tue 4/7/26 | VC_Classes | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.39.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.40.2 | NA | 1156 | 1155 | 1157 | 0h | No | Yes | No | No | No | 1.2.1.40.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.40.2 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Tue 4/7/26 | Tue 4/7/26 | Eric Heisler | 506 | 512 | Matt Palastro, Dave Duda | Tue 4/7/26 | VC_Classes | Tue 4/7/26 | Tue 4/7/26 | 1.2.1.40.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.1.42.1 | NA | 1157 | 1156 | 1160 | 0h | No | Yes | No | No | No | 1.2.1.40.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.41 | Auto Scheduled | 100% | VC_Classification (Class Type 200) | No | 0.63d | Wed 4/15/26 | Thu 4/16/26 |  |  |  |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Thu 4/16/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 941 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.41 | 4 | No | 500 | Complete | No | 0d
1.2.1.41.1 | Auto Scheduled | 100% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Wed 4/15/26 | Thu 4/16/26 | Eric Heisler | 428 | 510 |  | Wed 4/15/26 | VC_Classification (Class Type 200) | Wed 4/15/26 | Thu 4/16/26 | 1.2.1.27.6 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.41.2 | NA | 1158 | 1037 | 1159 | 0h | No | Yes | No | No | No | 1.2.1.41.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.41.2 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Thu 4/16/26 | Thu 4/16/26 | Eric Heisler | 509 |  | Matt Palastro, Dave Duda | Thu 4/16/26 | VC_Classification (Class Type 200) | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.41.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1159 | 1158 |  | 0h | No | Yes | No | No | No | 1.2.1.41.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.42 | Auto Scheduled | 100% | VC_Dependency Nets | No | 0.63d | Wed 4/15/26 | Thu 4/16/26 |  |  |  |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Thu 4/16/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 942 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.42 | 4 | No | 500 | Complete | No | 0d
1.2.1.42.1 | Auto Scheduled | 100% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Wed 4/15/26 | Thu 4/16/26 | Eric Heisler | 507422 | 513 |  | Wed 4/15/26 | VC_Dependency Nets | Wed 4/15/26 | Thu 4/16/26 | 1.2.1.40.2,1.2.1.27 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.42.2 | NA | 1160 | 1157749 | 1161 | 0h | No | Yes | No | No | No | 1.2.1.42.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.42.2 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Thu 4/16/26 | Thu 4/16/26 | Eric Heisler | 512 |  | Matt Palastro, Dave Duda | Thu 4/16/26 | VC_Dependency Nets | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.42.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1161 | 1160 |  | 0h | No | Yes | No | No | No | 1.2.1.42.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.43 | Auto Scheduled | 100% | VC_Configuration Profiles | No | 0.63d | Wed 4/15/26 | Thu 4/16/26 |  |  |  |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Thu 4/16/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 943 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.43 | 4 | No | 500 | Complete | No | 0d
1.2.1.43.1 | Auto Scheduled | 100% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Wed 4/15/26 | Thu 4/16/26 | Eric Heisler | 422 | 516 |  | Wed 4/15/26 | VC_Configuration Profiles | Wed 4/15/26 | Thu 4/16/26 | 1.2.1.27 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.43.2 | NA | 1162 | 749 | 1163 | 0h | No | Yes | No | No | No | 1.2.1.43.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.43.2 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Thu 4/16/26 | Thu 4/16/26 | Eric Heisler | 515 | 524518 | Matt Palastro, Dave Duda | Thu 4/16/26 | VC_Configuration Profiles | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.43.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.46.1,1.2.1.44.1 | NA | 1163 | 1162 | 11681164 | 0h | No | Yes | No | No | No | 1.2.1.43.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.44 | Auto Scheduled | 100% | VC_Variant Tables | No | 0.63d | Thu 4/16/26 | Fri 4/17/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Fri 4/17/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 944 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.44 | 4 | No | 500 | Complete | No | 0d
1.2.1.44.1 | Auto Scheduled | 100% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Thu 4/16/26 | Thu 4/16/26 | Eric Heisler | 516 | 519 |  | Thu 4/16/26 | VC_Variant Tables | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.43.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.44.2 | NA | 1164 | 1163 | 1165 | 0h | No | Yes | No | No | No | 1.2.1.44.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.44.2 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Thu 4/16/26 | Fri 4/17/26 | Eric Heisler | 518 | 521 | Matt Palastro, Dave Duda | Thu 4/16/26 | VC_Variant Tables | Thu 4/16/26 | Fri 4/17/26 | 1.2.1.44.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.45.1 | NA | 1165 | 1164 | 1166 | 0h | No | Yes | No | No | No | 1.2.1.44.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.45 | Auto Scheduled | 100% | VC_Variant Tables Content | No | 0.63d | Fri 4/17/26 | Fri 4/17/26 |  |  |  |  | Fri 4/17/26 | ITC1 Data Load Tasks QS5 | Fri 4/17/26 | Fri 4/17/26 |  | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 945 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.45 | 4 | No | 500 | Complete | No | 0d
1.2.1.45.1 | Auto Scheduled | 100% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Fri 4/17/26 | Fri 4/17/26 | Eric Heisler | 519 | 522 |  | Fri 4/17/26 | VC_Variant Tables Content | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.44.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.45.2 | NA | 1166 | 1165 | 1167 | 0h | No | Yes | No | No | No | 1.2.1.45.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.45.2 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Fri 4/17/26 | Fri 4/17/26 | Eric Heisler | 521 |  | Matt Palastro, Dave Duda | Fri 4/17/26 | VC_Variant Tables Content | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.45.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1167 | 1166 |  | 0h | No | Yes | No | No | No | 1.2.1.45.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.46 | Auto Scheduled | 100% | VC_Characteristic Groups | No | 1.97d | Fri 4/17/26 | Mon 4/20/26 |  |  |  |  | Fri 4/17/26 | ITC1 Data Load Tasks QS5 | Fri 4/17/26 | Mon 4/20/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 946 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.46 | 4 | No | 500 | Complete | No | 0d
1.2.1.46.1 | Auto Scheduled | 100% | Run ALE Transaction to QS5 from DS4 130 | No | 12.75h | Fri 4/17/26 | Mon 4/20/26 | Eric Heisler | 516 | 525 |  | Fri 4/17/26 | VC_Characteristic Groups | Fri 4/17/26 | Mon 4/20/26 | 1.2.1.43.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.1.46.2 | Fri 4/17/26 | 1168 | 1163 | 1169 | 0h | No | Yes | No | No | No | 1.2.1.46.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.46.2 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Mon 4/20/26 | Mon 4/20/26 | Eric Heisler | 524 |  | Matt Palastro, Dave Duda | Mon 4/20/26 | VC_Characteristic Groups | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.46.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1169 | 1168 |  | 0h | No | Yes | No | No | No | 1.2.1.46.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.47 | Auto Scheduled | 100% | PTM_CM52_Super_BOM | No | 4.09d | Wed 4/15/26 | Tue 4/21/26 |  |  |  |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Tue 4/21/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 713 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.47 | 4 | No | 500 | Complete | No | 0d
1.2.1.47.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Wed 4/15/26 | Wed 4/15/26 | Eric Heisler | 428 | 528 |  | Wed 4/15/26 | PTM_CM52_Super_BOM | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.27.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.47.2 | NA | 1094 | 1037 | 1095 | 0m | No | Yes | No | No | No | 1.2.1.47.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.47.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Wed 4/15/26 | Wed 4/15/26 | Eric Heisler | 527 | 529 | Matt Palastro, Dave Duda | Wed 4/15/26 | PTM_CM52_Super_BOM | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.47.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.47.3 | NA | 1095 | 1094 | 1096 | 0m | No | Yes | No | No | No | 1.2.1.47.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.47.3 | Auto Scheduled | 100% | Simulate Load | No | 24.75h | Wed 4/15/26 | Mon 4/20/26 | Data Migration Team | 528 | 530 | Matt Palastro, Dave Duda | Wed 4/15/26 | PTM_CM52_Super_BOM | Wed 4/15/26 | Mon 4/20/26 | 1.2.1.47.2 | Wed 4/15/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.1.47.4 | Mon 4/20/26 | 1096 | 1095 | 1097 | 0h | No | Yes | No | No | No | 1.2.1.47.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.47.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Tue 4/21/26 | Tue 4/21/26 | Eric Heisler | 529 | 531 | Matt Palastro, Dave Duda | Tue 4/21/26 | PTM_CM52_Super_BOM | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.47.3 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.1.47.5 | Fri 4/17/26 | 1097 | 1096 | 1098 | 0h | No | Yes | No | No | No | 1.2.1.47.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.47.5 | Auto Scheduled | 100% | Load | No | 2h | Tue 4/21/26 | Tue 4/21/26 | Data Migration Team | 530 | 532 |  | Tue 4/21/26 | PTM_CM52_Super_BOM | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.47.4 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than | 1.2.1.47.6 | Fri 4/17/26 | 1098 | 1097 | 1099 | 0h | No | Yes | No | No | No | 1.2.1.47.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.47.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Tue 4/21/26 | Tue 4/21/26 | Eric Heisler | 531 | 534 | Matt Palastro, Dave Duda | Tue 4/21/26 | PTM_CM52_Super_BOM | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.47.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.48.1 | NA | 1099 | 1098 | 1100 | 0h | No | Yes | No | No | No | 1.2.1.47.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.48 | Auto Scheduled | 100% | PTM_CM53_Super_Routing | No | 2d | Thu 4/16/26 | Fri 4/17/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Fri 4/17/26 |  | Thu 4/16/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 714 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.48 | 4 | No | 500 | Complete | No | 0d
1.2.1.48.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Thu 4/16/26 | Thu 4/16/26 | Eric Heisler | 532 | 535 |  | Thu 4/16/26 | PTM_CM53_Super_Routing | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.47.6 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.48.2 | NA | 1100 | 1099 | 1101 | 0m | No | Yes | No | No | No | 1.2.1.48.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.48.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Thu 4/16/26 | Fri 4/17/26 | Eric Heisler | 534 | 536 | Matt Palastro, Dave Duda | Thu 4/16/26 | PTM_CM53_Super_Routing | Thu 4/16/26 | Fri 4/17/26 | 1.2.1.48.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.48.3 | NA | 1101 | 1100 | 1102 | 0m | No | Yes | No | No | No | 1.2.1.48.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.48.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Thu 4/16/26 | Fri 4/17/26 | Data Migration Team | 535 | 537 |  | Thu 4/16/26 | PTM_CM53_Super_Routing | Thu 4/16/26 | Fri 4/17/26 | 1.2.1.48.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.48.4 | NA | 1102 | 1101 | 1103 | 0h | No | Yes | No | No | No | 1.2.1.48.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.48.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Fri 4/17/26 | Fri 4/17/26 | Eric Heisler | 536 | 538 | Matt Palastro, Dave Duda | Fri 4/17/26 | PTM_CM53_Super_Routing | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.48.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.48.5 | NA | 1103 | 1102 | 1104 | 0h | No | Yes | No | No | No | 1.2.1.48.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.48.5 | Auto Scheduled | 100% | Load | No | 2h | Fri 4/17/26 | Fri 4/17/26 | Data Migration Team | 537 | 539541 |  | Fri 4/17/26 | PTM_CM53_Super_Routing | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.48.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.48.6,1.2.1.49.1 | NA | 1104 | 1103 | 11051106 | 0h | No | Yes | No | No | No | 1.2.1.48.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.48.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Fri 4/17/26 | Fri 4/17/26 | Eric Heisler | 538 |  | Matt Palastro, Dave Duda | Fri 4/17/26 | PTM_CM53_Super_Routing | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.48.5 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 1105 | 1104 |  | 0h | No | Yes | No | No | No | 1.2.1.48.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.49 | Auto Scheduled | 100% | VC_VK30 Pricing Variant | No | 0.38d | Thu 4/16/26 | Thu 4/16/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Thu 4/16/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 949 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.49 | 4 | No | 500 | Complete | No | 0d
1.2.1.49.1 | Auto Scheduled | 100% | Manual File Staged and Posted "Ready" | No | 30m | Thu 4/16/26 | Thu 4/16/26 | Eric Heisler | 538 | 542 | Matt Palastro, Dave Duda | Thu 4/16/26 | VC_VK30 Pricing Variant | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.48.5 | Fri 4/17/26 | Fri 4/17/26 | Start No Earlier Than | 1.2.1.49.2 | Mon 4/6/26 | 1106 | 1104 | 1107 | 0m | No | Yes | No | No | No | 1.2.1.49.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.49.2 | Auto Scheduled | 100% | Load | No | 2h | Thu 4/16/26 | Thu 4/16/26 | Eric Heisler | 541 | 543 |  | Thu 4/16/26 | VC_VK30 Pricing Variant | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.49.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.49.3 | NA | 1107 | 1106 | 1108 | 0h | No | Yes | No | No | No | 1.2.1.49.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.49.3 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Thu 4/16/26 | Thu 4/16/26 | Eric Heisler | 542 | 545 | Matt Palastro, Dave Duda | Thu 4/16/26 | VC_VK30 Pricing Variant | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.49.2 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.1.50.1 | NA | 1108 | 1107 | 1109 | 0h | No | Yes | No | No | No | 1.2.1.49.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.50 | Auto Scheduled | 100% | OTC_CM22_Pricing_Condition | No | 1.38d | Wed 4/15/26 | Thu 4/16/26 |  |  |  |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Thu 4/16/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 951 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.50 | 4 | No | 500 | Complete | No | 0d
1.2.1.50.1 | Auto Scheduled | 100% | Manual File Staged and Posted "Ready" | No | 30m | Wed 4/15/26 | Wed 4/15/26 | Ric Haraida | 543 | 546 | Matt Palastro, Dave Duda | Wed 4/15/26 | OTC_CM22_Pricing_Condition | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.49.3 | Mon 4/20/26 | Mon 4/20/26 | Start No Earlier Than | 1.2.1.50.2 | Mon 4/6/26 | 1109 | 1108 | 1110 | 0m | No | Yes | No | No | No | 1.2.1.50.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.50.2 | Auto Scheduled | 100% | Load | No | 2h | Wed 4/15/26 | Wed 4/15/26 | Ric Haraida | 545 | 547549 |  | Wed 4/15/26 | OTC_CM22_Pricing_Condition | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.50.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.1.50.3,1.2.1.51.1 | NA | 1110 | 1109 | 11111112 | 0h | No | Yes | No | No | No | 1.2.1.50.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.50.3 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Thu 4/16/26 | Thu 4/16/26 | Ric Haraida,Kim Kolesar | 546 |  | Matt Palastro, Dave Duda,kim | Thu 4/16/26 | OTC_CM22_Pricing_Condition | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.50.2 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 1111 | 1110 |  | 0h | No | Yes | No | No | No | 1.2.1.50.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.51 | Auto Scheduled | 100% | OTC_CM21_CMIR | No | 2.72d | Thu 4/16/26 | Mon 4/20/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Mon 4/20/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 691 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.51 | 4 | No | 500 | Complete | No | 0d
1.2.1.51.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Mon 4/20/26 | Mon 4/20/26 | Ric Haraida | 546557 | 550 |  | Mon 4/20/26 | OTC_CM21_CMIR | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.50.2,1.2.1.52.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.1.51.2 | NA | 1112 | 11101119 | 1113 | 0m | No | Yes | No | No | No | 1.2.1.51.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.51.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Thu 4/16/26 | Thu 4/16/26 | Ric Haraida | 549 | 551 | Kim | Thu 4/16/26 | OTC_CM21_CMIR | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.51.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.1.51.3 | NA | 1113 | 1112 | 1114 | 0m | No | Yes | No | No | No | 1.2.1.51.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.51.3 | Auto Scheduled | 100% | Simulate Load | No | 0h | Thu 4/16/26 | Thu 4/16/26 | Data Migration Team | 550 | 552 |  | Thu 4/16/26 | OTC_CM21_CMIR | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.51.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.1.51.4 | NA | 1114 | 1113 | 1115 | 0h | No | Yes | No | Yes | No | 1.2.1.51.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.51.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 0h | Thu 4/16/26 | Thu 4/16/26 | Ric Haraida | 551 | 553 | Kim | Thu 4/16/26 | OTC_CM21_CMIR | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.51.3 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible | 1.2.1.51.5 | NA | 1115 | 1114 | 1116 | 0h | No | Yes | No | Yes | No | 1.2.1.51.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.51.5 | Auto Scheduled | 100% | Load | No | 0h | Thu 4/16/26 | Thu 4/16/26 | Data Migration Team | 552 | 554 |  | Thu 4/16/26 | OTC_CM21_CMIR | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.51.4 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible | 1.2.1.51.6 | NA | 1116 | 1115 | 1117 | 0h | No | Yes | No | Yes | No | 1.2.1.51.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.51.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Thu 4/16/26 | Thu 4/16/26 | Ric Haraida | 553 |  | Kim | Thu 4/16/26 | OTC_CM21_CMIR | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.51.5 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 1117 | 1116 |  | 0h | No | Yes | No | No | No | 1.2.1.51.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.52 | Auto Scheduled | 100% | PTP_CM29_Source_List | No | 1.41d | Fri 4/17/26 | Mon 4/20/26 |  |  |  |  | Fri 4/17/26 | ITC1 Data Load Tasks QS5 | Fri 4/17/26 | Mon 4/20/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 704 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.52 | 4 | No | 500 | Complete | No | 0d
1.2.1.52.1 | Auto Scheduled | 100% | Manual File Staged and Posted "Ready" | No | 30m | Fri 4/17/26 | Fri 4/17/26 | Nevin Varkey | 399406 |  | Sam | Fri 4/17/26 | PTP_CM29_Source_List | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.23.5,1.2.1.24.5 | Tue 4/14/26 | Tue 4/14/26 | Start No Earlier Than |  | Fri 4/17/26 | 1118 | 10181250 |  | 0m | No | Yes | No | No | No | 1.2.1.52.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.52.2 | Auto Scheduled | 100% | Load | No | 2h | Fri 4/17/26 | Mon 4/20/26 | Nevin Varkey | 375 | 558549 |  | Fri 4/17/26 | PTP_CM29_Source_List | Fri 4/17/26 | Mon 4/20/26 | 1.2.1.19.6 | Mon 4/13/26 | Mon 4/13/26 | Finish No Earlier Than | 1.2.1.52.3,1.2.1.51.1 | Fri 4/17/26 | 1119 | 998 | 11201112 | 0h | No | Yes | No | No | No | 1.2.1.52.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.52.3 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Mon 4/20/26 | Mon 4/20/26 | Nevin Varkey | 557 |  | Sam | Mon 4/20/26 | PTP_CM29_Source_List | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.52.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1120 | 1119 |  | 0h | No | Yes | No | No | No | 1.2.1.52.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.53 | Auto Scheduled | 100% | RTR_CM11_Asset_Master | No | 6.63d | Wed 4/15/26 | Thu 4/23/26 |  |  |  |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Thu 4/23/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 702 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.53 | 4 | No | 500 | Complete | No | 0d
1.2.1.53.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Wed 4/15/26 | Wed 4/15/26 | Kasey Hughes |  | 561615 |  | Wed 4/15/26 | RTR_CM11_Asset_Master | Wed 4/15/26 | Wed 4/15/26 |  | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.1.53.2,1.2.1.68.1 | Wed 4/15/26 | 1121 |  | 11221139 | 0m | No | Yes | No | No | No | 1.2.1.53.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.53.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Wed 4/15/26 | Wed 4/15/26 | Kasey Hughes,Femi Oguntala | 560 | 562 | Brian Wagner | Wed 4/15/26 | RTR_CM11_Asset_Master | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.53.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.53.3 | NA | 1122 | 1121 | 1123 | 0m | No | Yes | No | No | No | 1.2.1.53.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.53.3 | Auto Scheduled | 100% | Simulate Load | No | 31h | Wed 4/15/26 | Mon 4/20/26 | Data Migration Team | 561 | 563 |  | Wed 4/15/26 | RTR_CM11_Asset_Master | Wed 4/15/26 | Mon 4/20/26 | 1.2.1.53.2 | Fri 4/10/26 | Fri 4/10/26 | Finish No Earlier Than | 1.2.1.53.4 | Mon 4/20/26 | 1123 | 1122 | 1124 | 0h | No | Yes | No | No | No | 1.2.1.53.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.53.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 16h | Tue 4/21/26 | Wed 4/22/26 | Kasey Hughes | 562 | 564 | Brian Wagner | Tue 4/21/26 | RTR_CM11_Asset_Master | Tue 4/21/26 | Wed 4/22/26 | 1.2.1.53.3 | Fri 4/10/26 | Fri 4/10/26 | Finish No Earlier Than | 1.2.1.53.5 | Fri 4/17/26 | 1124 | 1123 | 1125 | 0h | No | Yes | No | No | No | 1.2.1.53.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.53.5 | Auto Scheduled | 100% | Load | No | 2h | Thu 4/23/26 | Thu 4/23/26 | Data Migration Team | 563 | 565 |  | Thu 4/23/26 | RTR_CM11_Asset_Master | Thu 4/23/26 | Thu 4/23/26 | 1.2.1.53.4 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.1.53.6 | Fri 4/17/26 | 1125 | 1124 | 1126 | 0h | No | Yes | No | No | No | 1.2.1.53.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.53.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Thu 4/23/26 | Thu 4/23/26 | Kasey Hughes | 564 |  | Brian Wagner | Thu 4/23/26 | RTR_CM11_Asset_Master | Thu 4/23/26 | Thu 4/23/26 | 1.2.1.53.5 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1126 | 1125 |  | 0h | No | Yes | No | No | No | 1.2.1.53.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.54 | Auto Scheduled | 100% | PTM_CM50_Material Class | No | 2.66d | Thu 4/16/26 | Mon 4/20/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Mon 4/20/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 712 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.54 | 4 | No | 500 | Complete | No | 0d
1.2.1.54.1 | Auto Scheduled | 100% | Manual File Staged and Posted "Ready" | No | 30m | Thu 4/16/26 | Thu 4/16/26 | Sam | 472 | 568571 |  | Thu 4/16/26 | PTM_CM50_Material Class | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.34.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.54.2,1.2.1.55.1 | NA | 1127 | 1081 | 11281133 | 0m | No | Yes | No | No | No | 1.2.1.54.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.54.2 | Auto Scheduled | 100% | Load | No | 30m | Thu 4/16/26 | Thu 4/16/26 | Brad Meseck | 567 | 569 | Matt Palastro, Dave Duda | Thu 4/16/26 | PTM_CM50_Material Class | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.54.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.54.3 | NA | 1128 | 1127 | 1129 | 0m | No | Yes | No | No | No | 1.2.1.54.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.54.3 | Auto Scheduled | 100% | Post Load Validation | No | 16h | Fri 4/17/26 | Mon 4/20/26 | Brad | 568 |  | brad | Fri 4/17/26 | PTM_CM50_Material Class | Fri 4/17/26 | Mon 4/20/26 | 1.2.1.54.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than |  | Mon 4/20/26 | 1129 | 1128 |  | 0h | No | Yes | No | No | No | 1.2.1.54.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.55 | Auto Scheduled | 100% | PTM_CM55_Class assignment to materials | No | 1.13d | Thu 4/16/26 | Fri 4/17/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Fri 4/17/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 715 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.55 | 4 | No | 500 | Complete | No | 0d
1.2.1.55.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Thu 4/16/26 | Thu 4/16/26 | Sam | 567 | 572 |  | Thu 4/16/26 | PTM_CM55_Class assignment to materials | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.54.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.55.2 | NA | 1133 | 1127 | 1134 | 0m | No | Yes | No | No | No | 1.2.1.55.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.55.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Thu 4/16/26 | Thu 4/16/26 | Brad Meseck | 571 | 573 | Matt Palastro, Dave Duda | Thu 4/16/26 | PTM_CM55_Class assignment to materials | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.55.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.55.3 | NA | 1134 | 1133 | 1135 | 0m | No | Yes | No | No | No | 1.2.1.55.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.55.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Thu 4/16/26 | Thu 4/16/26 | Data Migration Team | 572 | 574 |  | Thu 4/16/26 | PTM_CM55_Class assignment to materials | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.55.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.55.4 | NA | 1135 | 1134 | 1136 | 0h | No | Yes | No | No | No | 1.2.1.55.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.55.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Thu 4/16/26 | Thu 4/16/26 | Brad Meseck | 573 | 575 | Matt Palastro, Dave Duda | Thu 4/16/26 | PTM_CM55_Class assignment to materials | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.55.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.55.5 | NA | 1136 | 1135 | 1137 | 0h | No | Yes | No | No | No | 1.2.1.55.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.55.5 | Auto Scheduled | 100% | Load | No | 2h | Thu 4/16/26 | Fri 4/17/26 | Data Migration Team | 574 | 576 |  | Thu 4/16/26 | PTM_CM55_Class assignment to materials | Thu 4/16/26 | Fri 4/17/26 | 1.2.1.55.4 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.55.6 | NA | 1137 | 1136 | 1138 | 0h | No | Yes | No | No | No | 1.2.1.55.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.55.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Fri 4/17/26 | Fri 4/17/26 | Brad Meseck | 575 |  | Matt Palastro, Dave Duda | Fri 4/17/26 | PTM_CM55_Class assignment to materials | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.55.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1138 | 1137 |  | 0h | No | Yes | No | No | No | 1.2.1.55.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.56 | Auto Scheduled | 100% | GTS - Material initial load from S4 (Run Interface) | No | 2.09d | Thu 4/16/26 | Mon 4/20/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Mon 4/20/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 952 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.56 | 4 | No | 500 | Complete | No | 0d
1.2.1.56.1 | Auto Scheduled | 100% | Run material interface to GTS | No | 15.75h | Thu 4/16/26 | Fri 4/17/26 | James Van Riper | 446 | 579 |  | Thu 4/16/26 | GTS - Material initial load from S4 (Run Interface) | Thu 4/16/26 | Fri 4/17/26 | 1.2.1.30.3 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.1.56.2 | Fri 4/17/26 | 1171 | 1052 | 1173 | 0h | No | Yes | No | No | No | 1.2.1.56.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.56.2 | Auto Scheduled | 100% | Post Load Validation | No | 1h | Mon 4/20/26 | Mon 4/20/26 | James Van Riper | 578 | 590 | Kim Kolesar | Mon 4/20/26 | GTS - Material initial load from S4 (Run Interface) | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.56.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.60.1 | NA | 1173 | 1171 | 1180 | 0h | No | Yes | No | No | No | 1.2.1.56.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.57 | Auto Scheduled | 100% | GTS - Customers initial load from S4 (Run Interface) | No | 4d | Wed 4/15/26 | Mon 4/20/26 |  |  |  |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Mon 4/20/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 953 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.57 | 4 | No | 500 | Complete | No | 0d
1.2.1.57.1 | Auto Scheduled | 100% | Run material interface to GTS | No | 1h | Wed 4/15/26 | Wed 4/15/26 | James Van Riper |  | 582 |  | Wed 4/15/26 | GTS - Customers initial load from S4 (Run Interface) | Wed 4/15/26 | Wed 4/15/26 |  | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.1.57.2 | Wed 4/15/26 | 1174 |  | 1175 | 0h | No | Yes | No | No | No | 1.2.1.57.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.57.2 | Auto Scheduled | 100% | Post Load Validation | No | 1h | Mon 4/20/26 | Mon 4/20/26 | James Van Riper | 581 |  | Kim Kolesar | Mon 4/20/26 | GTS - Customers initial load from S4 (Run Interface) | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.57.1 | Fri 4/10/26 | Fri 4/10/26 | Finish No Earlier Than |  | Mon 4/20/26 | 1175 | 1174 |  | 0h | No | Yes | No | No | No | 1.2.1.57.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.58 | Auto Scheduled | 100% | GTS - Vendors initial load from S4 (Run Interface) | No | 0.25d | Thu 4/16/26 | Fri 4/17/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Fri 4/17/26 |  | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 954 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.58 | 4 | No | 500 | Complete | No | 0d
1.2.1.58.1 | Auto Scheduled | 100% | Run material interface to GTS | No | 1h | Thu 4/16/26 | Thu 4/16/26 | James Van Riper | 389 | 585588 |  | Thu 4/16/26 | GTS - Vendors initial load from S4 (Run Interface) | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.21.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.1.58.2,1.2.1.59.2 | NA | 1176 | 1010 | 11771179 | 0h | No | Yes | No | No | No | 1.2.1.58.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.58.2 | Auto Scheduled | 100% | Post Load Validation | No | 1h | Fri 4/17/26 | Fri 4/17/26 | James Van Riper | 584 |  | Kim Kolesar | Fri 4/17/26 | GTS - Vendors initial load from S4 (Run Interface) | Fri 4/17/26 | Fri 4/17/26 | 1.2.1.58.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 1177 | 1176 |  | 0h | No | Yes | No | No | No | 1.2.1.58.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.59 | Auto Scheduled | 100% | GTS - ECCN - Create | No | 5.63d | Mon 4/6/26 | Mon 4/13/26 |  |  |  |  | Mon 4/6/26 | ITC1 Data Load Tasks QS5 | Mon 4/6/26 | Mon 4/13/26 |  | Mon 4/6/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 698 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.59 | 4 | No | 500 | Complete | No | 0d
1.2.1.59.1 | Auto Scheduled | 100% | Load Descartes XML File | No | 1h | Mon 4/6/26 | Mon 4/6/26 | James Van Riper | 261 |  |  | Mon 4/6/26 | GTS - ECCN - Create | Mon 4/6/26 | Mon 4/6/26 | 1.2.1.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 1178 | 956 |  | 0h | No | Yes | No | No | No | 1.2.1.59.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.59.2 | Auto Scheduled | 100% | Post Load Validation | No | 1h | Mon 4/13/26 | Mon 4/13/26 | James Van Riper | 584 | 608 | Kim Kolesar | Mon 4/13/26 | GTS - ECCN - Create | Mon 4/13/26 | Mon 4/13/26 | 1.2.1.58.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.66.1 | NA | 1179 | 1176 | 1210 | 0h | No | Yes | No | No | No | 1.2.1.59.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.60 | Auto Scheduled | 100% | GTS - ECCN - Assign | No | 0.25d | Thu 4/16/26 | Thu 4/16/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Thu 4/16/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 699 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.60 | 4 | No | 500 | Complete | No | 0d
1.2.1.60.1 | Auto Scheduled | 100% | Load Descartes XML File | No | 1h | Thu 4/16/26 | Thu 4/16/26 | James Van Riper | 579 | 591 |  | Thu 4/16/26 | GTS - ECCN - Assign | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.56.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.1.60.2 | Fri 4/17/26 | 1180 | 1173 | 1181 | 0h | No | Yes | No | No | No | 1.2.1.60.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.60.2 | Auto Scheduled | 100% | Post Load Validation | No | 1h | Thu 4/16/26 | Thu 4/16/26 | James Van Riper | 590 | 596 | Kim Kolesar | Thu 4/16/26 | GTS - ECCN - Assign | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.60.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.62.1 | NA | 1181 | 1180 | 1184 | 0h | No | Yes | No | No | No | 1.2.1.60.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.61 | Auto Scheduled | 100% | GTS - HTS - Create | No | 0.25d | Mon 4/6/26 | Mon 4/6/26 |  |  |  |  | Mon 4/6/26 | ITC1 Data Load Tasks QS5 | Mon 4/6/26 | Mon 4/6/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 700 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.61 | 4 | No | 500 | Complete | No | 0d
1.2.1.61.1 | Auto Scheduled | 100% | Load Descartes XML File | No | 1h | Mon 4/6/26 | Mon 4/6/26 | James Van Riper | 261 | 594 |  | Mon 4/6/26 | GTS - HTS - Create | Mon 4/6/26 | Mon 4/6/26 | 1.2.1.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.1.61.2 | NA | 1182 | 956 | 1183 | 0h | No | Yes | No | No | No | 1.2.1.61.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.61.2 | Auto Scheduled | 100% | Post Load Validation | No | 1h | Mon 4/6/26 | Mon 4/6/26 | James Van Riper | 593 |  | Kim Kolesar | Mon 4/6/26 | GTS - HTS - Create | Mon 4/6/26 | Mon 4/6/26 | 1.2.1.61.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 1183 | 1182 |  | 0h | No | Yes | No | No | No | 1.2.1.61.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.62 | Auto Scheduled | 100% | GTS - HTS - Assign | No | 0.25d | Thu 4/16/26 | Thu 4/16/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Thu 4/16/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 701 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.62 | 4 | No | 500 | Complete | No | 0d
1.2.1.62.1 | Auto Scheduled | 100% | Load Descartes XML File | No | 1h | Thu 4/16/26 | Thu 4/16/26 | James Van Riper | 591 | 597599605 |  | Thu 4/16/26 | GTS - HTS - Assign | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.60.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.62.2,1.2.1.63.1,1.2.1.65.1 | NA | 1184 | 1181 | 118511861217 | 0h | No | Yes | No | No | No | 1.2.1.62.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.62.2 | Auto Scheduled | 100% | Post Load Validation | No | 1h | Thu 4/16/26 | Thu 4/16/26 | James Van Riper | 596 | 612602 | Kim Kolesar | Thu 4/16/26 | GTS - HTS - Assign | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.62.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.67.1,1.2.1.64.1 | NA | 1185 | 1184 | 11881214 | 0h | No | Yes | No | No | No | 1.2.1.62.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.63 | Auto Scheduled | 100% | GTS - License - Create | No | 0.25d | Thu 4/16/26 | Thu 4/16/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Thu 4/16/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 706 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.63 | 4 | No | 500 | Complete | No | 0d
1.2.1.63.1 | Auto Scheduled | 100% | Load Descartes XML File | No | 1h | Thu 4/16/26 | Thu 4/16/26 | James Van Riper | 596612 | 600 |  | Thu 4/16/26 | GTS - License - Create | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.62.1,1.2.1.67.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.63.2 | NA | 1186 | 11841188 | 1187 | 0h | No | Yes | No | No | No | 1.2.1.63.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.63.2 | Auto Scheduled | 100% | Post Load Validation | No | 1h | Thu 4/16/26 | Thu 4/16/26 | James Van Riper | 599 |  | Kim Kolesar | Thu 4/16/26 | GTS - License - Create | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.63.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1187 | 1186 |  | 0h | No | Yes | No | No | No | 1.2.1.63.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.64 | Auto Scheduled | 100% | Commodity Code/Tarif | No | 2.78d | Thu 4/16/26 | Tue 4/21/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Tue 4/21/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1213 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.64 | 4 | No | 500 | Complete | No | 0d
1.2.1.64.1 | Auto Scheduled | 100% | Load | No | 21.25h | Thu 4/16/26 | Mon 4/20/26 | James Van Riper | 597 | 603 |  | Thu 4/16/26 | Commodity Code/Tarif | Thu 4/16/26 | Mon 4/20/26 | 1.2.1.62.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.1.64.2 | Mon 4/20/26 | 1214 | 1185 | 1215 | 0h | No | Yes | No | No | No | 1.2.1.64.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.64.2 | Auto Scheduled | 100% | Post Load Validation | No | 1h | Tue 4/21/26 | Tue 4/21/26 | James Van Riper | 602 |  | Kim Kolesar | Tue 4/21/26 | Commodity Code/Tarif | Tue 4/21/26 | Tue 4/21/26 | 1.2.1.64.1 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than |  | Fri 4/17/26 | 1215 | 1214 |  | 0h | No | Yes | No | No | No | 1.2.1.64.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.65 | Auto Scheduled | 100% | SPL Master File | No | 1.34d | Wed 4/15/26 | Thu 4/16/26 |  |  |  |  | Wed 4/15/26 | ITC1 Data Load Tasks QS5 | Wed 4/15/26 | Thu 4/16/26 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 1216 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.65 | 4 | No | 500 | Complete | No | 0d
1.2.1.65.1 | Auto Scheduled | 100% | Load | No | 1h | Thu 4/16/26 | Thu 4/16/26 | James Van Riper | 596 | 606 |  | Thu 4/16/26 | SPL Master File | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.62.1 | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible | 1.2.1.65.2 | NA | 1217 | 1184 | 1218 | 0h | No | Yes | No | No | No | 1.2.1.65.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.65.2 | Auto Scheduled | 100% | Post Load Validation | No | 1h | Wed 4/15/26 | Wed 4/15/26 | James Van Riper | 605 |  | Kim Kolesar | Wed 4/15/26 | SPL Master File | Wed 4/15/26 | Wed 4/15/26 | 1.2.1.65.1 | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 1218 | 1217 |  | 0h | No | Yes | No | No | No | 1.2.1.65.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.66 | Auto Scheduled | 100% | Initialize Embargo situation | No | 0.59d | Mon 4/13/26 | Tue 4/14/26 |  |  |  |  | Mon 4/13/26 | ITC1 Data Load Tasks QS5 | Mon 4/13/26 | Tue 4/14/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1209 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.66 | 4 | No | 500 | Complete | No | 0d
1.2.1.66.1 | Auto Scheduled | 100% | Run report /SAPSLL/EMB_CNTRY_INIT | No | 1h | Mon 4/13/26 | Mon 4/13/26 | James Van Riper | 588 | 609 |  | Mon 4/13/26 | Initialize Embargo situation | Mon 4/13/26 | Mon 4/13/26 | 1.2.1.59.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.66.2 | NA | 1210 | 1179 | 1211 | 0h | No | Yes | No | No | No | 1.2.1.66.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.66.2 | Auto Scheduled | 100% | Set Embargo situations | No | 1h | Tue 4/14/26 | Tue 4/14/26 | James Van Riper | 608 | 610 |  | Tue 4/14/26 | Initialize Embargo situation | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.66.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.1.66.3 | NA | 1211 | 1210 | 1212 | 0h | No | Yes | No | No | No | 1.2.1.66.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.66.3 | Auto Scheduled | 100% | Post Load Validation | No | 1h | Tue 4/14/26 | Tue 4/14/26 | James Van Riper | 609 |  | Kim Kolesar | Tue 4/14/26 | Initialize Embargo situation | Tue 4/14/26 | Tue 4/14/26 | 1.2.1.66.2 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1212 | 1211 |  | 0h | No | Yes | No | No | No | 1.2.1.66.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.67 | Auto Scheduled | 100% | GTS - SPL (Sanctioned party list) | No | 0.25d | Thu 4/16/26 | Thu 4/16/26 |  |  |  |  | Thu 4/16/26 | ITC1 Data Load Tasks QS5 | Thu 4/16/26 | Thu 4/16/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 955 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.67 | 4 | No | 500 | Complete | No | 0d
1.2.1.67.1 | Auto Scheduled | 100% | Load Descartes XML File | No | 1h | Thu 4/16/26 | Thu 4/16/26 | James Van Riper | 597 | 613599 |  | Thu 4/16/26 | GTS - SPL (Sanctioned party list) | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.62.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.67.2,1.2.1.63.1 | NA | 1188 | 1185 | 11891186 | 0h | No | Yes | No | No | No | 1.2.1.67.1 | 5 | No | 500 | Complete | No | 0h
1.2.1.67.2 | Auto Scheduled | 100% | Post Load Validation | No | 1h | Thu 4/16/26 | Thu 4/16/26 | James Van Riper | 612 |  | Kim Kolesar | Thu 4/16/26 | GTS - SPL (Sanctioned party list) | Thu 4/16/26 | Thu 4/16/26 | 1.2.1.67.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1189 | 1188 |  | 0h | No | Yes | No | No | No | 1.2.1.67.2 | 5 | No | 500 | Complete | No | 0h
1.2.1.68 | Auto Scheduled | 100% | RTR_CM17_Project Definition / Builder | No | 1.13d | Mon 4/20/26 | Tue 4/21/26 |  |  |  |  | Mon 4/20/26 | ITC1 Data Load Tasks QS5 | Mon 4/20/26 | Tue 4/21/26 |  | Fri 4/10/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 950 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.68 | 4 | No | 500 | Complete | No | 0d
1.2.1.68.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Mon 4/20/26 | Mon 4/20/26 | Kasey Hughes | 560 | 616622 |  | Mon 4/20/26 | RTR_CM17_Project Definition / Builder | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.53.1 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.1.68.2,1.2.1.69.1 | Mon 4/20/26 | 1139 | 1121 | 11401145 | 0m | No | Yes | No | No | No | 1.2.1.68.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.68.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Mon 4/20/26 | Mon 4/20/26 | Kasey Hughes | 615 | 617 | Brian Wagner | Mon 4/20/26 | RTR_CM17_Project Definition / Builder | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.68.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.68.3 | NA | 1140 | 1139 | 1141 | 0m | No | Yes | No | No | No | 1.2.1.68.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.68.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Mon 4/20/26 | Mon 4/20/26 | Data Migration Team | 616 | 618 |  | Mon 4/20/26 | RTR_CM17_Project Definition / Builder | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.68.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.68.4 | NA | 1141 | 1140 | 1142 | 0h | No | Yes | No | No | No | 1.2.1.68.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.68.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Mon 4/20/26 | Mon 4/20/26 | Kasey Hughes | 617 | 619 | Brian Wagner | Mon 4/20/26 | RTR_CM17_Project Definition / Builder | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.68.3 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.68.5 | NA | 1142 | 1141 | 1143 | 0h | No | Yes | No | No | No | 1.2.1.68.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.68.5 | Auto Scheduled | 100% | Load | No | 2h | Mon 4/20/26 | Mon 4/20/26 | Data Migration Team | 618 | 620 |  | Mon 4/20/26 | RTR_CM17_Project Definition / Builder | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.68.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.68.6 | NA | 1143 | 1142 | 1144 | 0h | No | Yes | No | No | No | 1.2.1.68.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.68.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Mon 4/20/26 | Tue 4/21/26 | Kasey Hughes | 619 |  | Brian Wagner | Mon 4/20/26 | RTR_CM17_Project Definition / Builder | Mon 4/20/26 | Tue 4/21/26 | 1.2.1.68.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1144 | 1143 |  | 0h | No | Yes | No | No | No | 1.2.1.68.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.69 | Auto Scheduled | 100% | RTR_CM18_WBS Element | No | 1.13d | Mon 4/20/26 | Tue 4/21/26 |  |  |  |  | Mon 4/20/26 | ITC1 Data Load Tasks QS5 | Mon 4/20/26 | Tue 4/21/26 |  | Fri 4/10/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 754 |  |  | 0d | Yes | Yes | No | No | No | 1.2.1.69 | 4 | No | 500 | Complete | No | 0d
1.2.1.69.1 | Auto Scheduled | 100% | Load File Staged and Posted "Ready" | No | 30m | Mon 4/20/26 | Mon 4/20/26 | Kasey Hughes | 615 | 623 |  | Mon 4/20/26 | RTR_CM18_WBS Element | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.68.1 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.1.69.2 | Fri 4/17/26 | 1145 | 1139 | 1146 | 0m | No | Yes | No | No | No | 1.2.1.69.1 | 5 | No | 500 | Complete | No | 0m
1.2.1.69.2 | Auto Scheduled | 100% | Pre Load Validation | No | 30m | Mon 4/20/26 | Mon 4/20/26 | Kasey Hughes | 622 | 624 | Brian Wagner | Mon 4/20/26 | RTR_CM18_WBS Element | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.69.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.1.69.3 | NA | 1146 | 1145 | 1147 | 0m | No | Yes | No | No | No | 1.2.1.69.2 | 5 | No | 500 | Complete | No | 0m
1.2.1.69.3 | Auto Scheduled | 100% | Simulate Load | No | 1h | Mon 4/20/26 | Mon 4/20/26 | Data Migration Team | 623 | 625 |  | Mon 4/20/26 | RTR_CM18_WBS Element | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.69.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.1.69.4 | NA | 1147 | 1146 | 1148 | 0h | No | Yes | No | No | No | 1.2.1.69.3 | 5 | No | 500 | Complete | No | 0h
1.2.1.69.4 | Auto Scheduled | 100% | Error and Defect Mitigation | No | 2h | Mon 4/20/26 | Mon 4/20/26 | Kasey Hughes | 624 | 626 | Brian Wagner | Mon 4/20/26 | RTR_CM18_WBS Element | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.69.3 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.69.5 | NA | 1148 | 1147 | 1149 | 0h | No | Yes | No | No | No | 1.2.1.69.4 | 5 | No | 500 | Complete | No | 0h
1.2.1.69.5 | Auto Scheduled | 100% | Load | No | 2h | Mon 4/20/26 | Mon 4/20/26 | Data Migration Team | 625 | 627 |  | Mon 4/20/26 | RTR_CM18_WBS Element | Mon 4/20/26 | Mon 4/20/26 | 1.2.1.69.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.1.69.6 | NA | 1149 | 1148 | 1150 | 0h | No | Yes | No | No | No | 1.2.1.69.5 | 5 | No | 500 | Complete | No | 0h
1.2.1.69.6 | Auto Scheduled | 100% | Post Load Validation | No | 3h | Mon 4/20/26 | Tue 4/21/26 | Kasey Hughes | 626 |  | Brian Wagner | Mon 4/20/26 | RTR_CM18_WBS Element | Mon 4/20/26 | Tue 4/21/26 | 1.2.1.69.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1150 | 1149 |  | 0h | No | Yes | No | No | No | 1.2.1.69.6 | 5 | No | 500 | Complete | No | 0h
1.2.1.70 | Auto Scheduled | 100% | ITC1 Mock Data Loads Complete | No | 15m | Thu 4/23/26 | Thu 4/23/26 | Mark George |  | 2164 |  | Thu 4/23/26 | ITC1 Data Load Tasks QS5 | Thu 4/23/26 | Thu 4/23/26 |  | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible | 1.3.3.1 | NA | 1170 |  | 932 | 0m | No | Yes | No | Yes | No | 1.2.1.70 | 4 | No | 500 | Complete | No | 0m
1.2.2 | Auto Scheduled | 0% | ITC2 Data Load Tasks QS4 | No | 105.63d | Mon 5/18/26 | Mon 10/12/26 |  | 260,41 |  |  | NA | Data Readiness | Mon 5/18/26 | Mon 10/12/26 | 1.2.1,1.1.1.5 | NA | NA | As Soon As Possible |  | NA | 2809 | 425849 |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.2 | 3 | No | 500 | Future Task | No | 0d
1.2.2.1 | Auto Scheduled | 0% | PMO Authorization to Start Data Loads | No | 2h | Mon 5/18/26 | Mon 5/18/26 | Mark George | 41 | 631 |  | NA | ITC2 Data Load Tasks QS4 | Mon 5/18/26 | Mon 5/18/26 | 1.1.1.5 | Mon 4/6/26 | Mon 4/6/26 | Must Start On | 1.2.2.2 | Mon 5/18/26 | 1685 | 849 | 2800 | 0h | No | Yes | Yes | No | No | 1.2.2.1 | 4 | No | 500 | Future Task | No | 0h
1.2.2.2 | Auto Scheduled | 0% | Master Data Loads | No | 9.63d | Mon 5/18/26 | Fri 5/29/26 |  | 630 | 998 |  | NA | ITC2 Data Load Tasks QS4 | Mon 5/18/26 | Fri 5/29/26 | 1.2.2.1 | NA | NA | As Soon As Possible | 1.2.2.3 | NA | 2800 | 1685 | 2947 | -9.56d | Yes | Yes | Yes | No | No | 1.2.2.2 | 4 | No | 500 | Future Task | No | 0d
1.2.2.2.1 | Auto Scheduled | 0% | RTR_CM02_Profit Center Hierarchy | No | 0.75d | Mon 5/18/26 | Mon 5/18/26 |  |  | 665667 |  | NA | Master Data Loads | Mon 5/18/26 | Mon 5/18/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.2.2.6.2,1.2.2.2.6.4 | NA | 1686 |  | 17191721 | -9.56d | Yes | Yes | Yes | No | No | 1.2.2.2.1 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.1.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 1h | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes |  | 634 |  | NA | RTR_CM02_Profit Center Hierarchy | Mon 5/18/26 | Mon 5/18/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.2.2.1.2 | NA | 1687 |  | 1688 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.1.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.1.2 | Auto Scheduled | 0% | Load | No | 2h | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 633 | 635 |  | NA | RTR_CM02_Profit Center Hierarchy | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.1.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.2.2.1.3 | NA | 1688 | 1687 | 1689 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.1.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.1.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 634 | 637650 | Brian Wagner | NA | RTR_CM02_Profit Center Hierarchy | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.1.2 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.2.2.2.1,1.2.2.2.4.1 | NA | 1689 | 1688 | 16911704 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.1.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.2 | Auto Scheduled | 0% | RTR_CM03_Cost Center Hierarchy | No | 0.75d | Tue 5/19/26 | Tue 5/19/26 |  |  | 665667 |  | NA | Master Data Loads | Tue 5/19/26 | Tue 5/19/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.6.2,1.2.2.2.6.4 | NA | 1690 |  | 17191721 | -9.56d | Yes | Yes | Yes | No | No | 1.2.2.2.2 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.2.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 1h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 635 | 638 |  | NA | RTR_CM03_Cost Center Hierarchy | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.1.3 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.2.2.2.2 | NA | 1691 | 1689 | 1692 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.2.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.2.2 | Auto Scheduled | 0% | Load | No | 2h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 637 | 639 |  | NA | RTR_CM03_Cost Center Hierarchy | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.2.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.2.3 | NA | 1692 | 1691 | 1693 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.2.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.2.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 638 | 641676 | Brian Wagner | NA | RTR_CM03_Cost Center Hierarchy | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.2.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.3.1,1.2.2.2.8.1 | NA | 1693 | 1692 | 16951730 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.2.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.3 | Auto Scheduled | 0% | RTR_CM01_GL_Account_Master to CC 1000 | No | 2.44d | Tue 5/19/26 | Fri 5/22/26 |  |  | 665 |  | NA | Master Data Loads | Tue 5/19/26 | Fri 5/22/26 |  | Tue 4/7/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.6.2 | NA | 1694 |  | 1719 | -9.56d | Yes | Yes | Yes | No | No | 1.2.2.2.3 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.3.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 639 | 642 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.2.3 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.3.2 | NA | 1695 | 1693 | 1696 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.3.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.3.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 5/19/26 | Wed 5/20/26 | Kasey Hughes | 641 | 643 | Brian Wagner | NA | RTR_CM01_GL_Account_Master to CC 1000 | Tue 5/19/26 | Wed 5/20/26 | 1.2.2.2.3.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.3.3 | NA | 1696 | 1695 | 1697 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.3.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.3.3 | Auto Scheduled | 0% | Simulate Load | No | 6h | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 642 | 644 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.3.2 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.3.4 | NA | 1697 | 1696 | 1698 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.3.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.3.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 5/20/26 | Thu 5/21/26 | Kasey Hughes | 643 | 645 | Brian Wagner | NA | RTR_CM01_GL_Account_Master to CC 1000 | Wed 5/20/26 | Thu 5/21/26 | 1.2.2.2.3.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.3.5 | NA | 1698 | 1697 | 1699 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.3.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.3.5 | Auto Scheduled | 0% | Load | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 644 | 646 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.3.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.3.6 | NA | 1699 | 1698 | 1700 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.3.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.3.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Thu 5/21/26 | Thu 5/21/26 | Kasey Hughes | 645 | 669683697702647 | Brian Wagner | NA | RTR_CM01_GL_Account_Master to CC 1000 | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.3.5 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.7.1,1.2.2.2.9.1,1.2.2.2.11.1,1.2.2.2.13.1,1.2.2.2.3.7 | NA | 1700 | 1699 | 1.7232e+19 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.3.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.3.7 | Auto Scheduled | 0% | Extend GL to all Company Codes | No | 2h | Thu 5/21/26 | Thu 5/21/26 | Kasey Hughes | 646 | 648 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.3.6 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.3.8 | NA | 1701 | 1700 | 1702 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.3.7 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.3.8 | Auto Scheduled | 0% | Post GL Extention Validation | No | 2h | Thu 5/21/26 | Fri 5/22/26 |  | 647 | 714667 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.3.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.14.3,1.2.2.2.6.4 | NA | 1702 | 1701 | 17681721 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.3.8 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.4 | Auto Scheduled | 0% | RTR_CM05_Profit_Center | No | 1.13d | Tue 5/19/26 | Wed 5/20/26 |  |  |  |  | NA | Master Data Loads | Tue 5/19/26 | Wed 5/20/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 1703 |  |  | -7.94d | Yes | Yes | Yes | No | No | 1.2.2.2.4 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.4.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 635 | 651 |  | NA | RTR_CM05_Profit_Center | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.1.3 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.2.2.4.2 | NA | 1704 | 1689 | 1705 | -63.52h | No | Yes | Yes | No | No | 1.2.2.2.4.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.4.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 650 | 652 | Brian Wagner | NA | RTR_CM05_Profit_Center | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.4.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.4.3 | NA | 1705 | 1704 | 1706 | -63.52h | No | Yes | Yes | No | No | 1.2.2.2.4.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.4.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 5/19/26 | Tue 5/19/26 | Data Migration Team | 651 | 653 |  | NA | RTR_CM05_Profit_Center | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.4.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.4.4 | NA | 1706 | 1705 | 1707 | -63.52h | No | Yes | Yes | No | No | 1.2.2.2.4.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.4.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 652 | 654 | Brian Wagner | NA | RTR_CM05_Profit_Center | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.4.3 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.4.5 | NA | 1707 | 1706 | 1708 | -63.52h | No | Yes | Yes | No | No | 1.2.2.2.4.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.4.5 | Auto Scheduled | 0% | Load | No | 1h | Tue 5/19/26 | Tue 5/19/26 | Data Migration Team | 653 | 655 |  | NA | RTR_CM05_Profit_Center | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.4.4 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.4.6 | NA | 1708 | 1707 | 1709 | -63.52h | No | Yes | Yes | No | No | 1.2.2.2.4.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.4.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Tue 5/19/26 | Wed 5/20/26 | Kasey Hughes | 654 | 657786793 | Brian Wagner | NA | RTR_CM05_Profit_Center | Tue 5/19/26 | Wed 5/20/26 | 1.2.2.2.4.5 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.5.1,1.2.2.2.25.1,1.2.2.2.26.1 | NA | 1709 | 1708 | 171118401847 | -63.52h | No | Yes | Yes | No | No | 1.2.2.2.4.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.5 | Auto Scheduled | 0% | RTR_CM04_Cost_Center | No | 1.13d | Wed 5/20/26 | Thu 5/21/26 |  |  | 663 |  | NA | Master Data Loads | Wed 5/20/26 | Thu 5/21/26 |  | Tue 4/7/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.6 | NA | 1710 |  | 1717 | -7.94d | Yes | Yes | Yes | No | No | 1.2.2.2.5 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.5.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Wed 5/20/26 | Wed 5/20/26 | Kasey Hughes | 655 | 658 |  | NA | RTR_CM04_Cost_Center | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.4.6 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.5.2 | NA | 1711 | 1709 | 1712 | -63.52h | No | Yes | Yes | No | No | 1.2.2.2.5.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.5.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Wed 5/20/26 | Wed 5/20/26 | Kasey Hughes | 657 | 659 | Brian Wagner | NA | RTR_CM04_Cost_Center | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.5.1 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.5.3 | NA | 1712 | 1711 | 1713 | -63.52h | No | Yes | Yes | No | No | 1.2.2.2.5.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.5.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 658 | 660 |  | NA | RTR_CM04_Cost_Center | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.5.2 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.5.4 | NA | 1713 | 1712 | 1714 | -63.52h | No | Yes | Yes | No | No | 1.2.2.2.5.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.5.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 5/20/26 | Wed 5/20/26 | Kasey Hughes | 659 | 661 | Brian Wagner | NA | RTR_CM04_Cost_Center | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.5.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.5.5 | NA | 1714 | 1713 | 1715 | -63.52h | No | Yes | Yes | No | No | 1.2.2.2.5.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.5.5 | Auto Scheduled | 0% | Load | No | 1h | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 660 | 662 |  | NA | RTR_CM04_Cost_Center | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.5.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.5.6 | NA | 1715 | 1714 | 1716 | -63.52h | No | Yes | Yes | No | No | 1.2.2.2.5.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.5.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Thu 5/21/26 | Thu 5/21/26 | Kasey Hughes | 661 |  | Brian Wagner | NA | RTR_CM04_Cost_Center | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.5.5 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 1716 | 1715 |  | -63.52h | No | Yes | Yes | No | No | 1.2.2.2.5.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.6 | Auto Scheduled | 0% | Manual Configuration Activities in QS5 | No | 5.94d | Thu 5/21/26 | Fri 5/29/26 |  | 656 |  |  | NA | Master Data Loads | Thu 5/21/26 | Fri 5/29/26 | 1.2.2.2.5 | Mon 4/6/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 1717 | 1710 |  | -8.88d | Yes | Yes | Yes | No | No | 1.2.2.2.6 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.6.1 | Auto Scheduled | 0% | Open Client | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Basis |  |  |  | NA | Manual Configuration Activities in QS5 | Thu 5/21/26 | Thu 5/21/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 1718 |  |  | -1441m | No | Yes | Yes | No | No | 1.2.2.2.6.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.6.2 | Auto Scheduled | 0% | Service Enterprise Setup | No | 5d | Fri 5/22/26 | Fri 5/29/26 | Keith Riley | 632636640 |  |  | NA | Manual Configuration Activities in QS5 | Fri 5/22/26 | Fri 5/29/26 | 1.2.2.2.1,1.2.2.2.2,1.2.2.2.3 | Wed 4/8/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 1719 | 168616901694 |  | -8.88d | No | Yes | Yes | No | No | 1.2.2.2.6.2 | 6 | No | 500 | Future Task | No | 0d
1.2.2.2.6.3 | Auto Scheduled | 0% | Close Client | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Basis |  |  |  | NA | Manual Configuration Activities in QS5 | Thu 5/21/26 | Thu 5/21/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 1720 |  |  | -1441m | No | Yes | Yes | No | No | 1.2.2.2.6.3 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.6.4 | Auto Scheduled | 0% | Intercompany Business Partner Setup | No | 2h | Fri 5/22/26 | Fri 5/22/26 | Functional Leads | 632636648 |  |  | NA | Manual Configuration Activities in QS5 | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.1,1.2.2.2.2,1.2.2.2.3.8 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 1721 | 168616901702 |  | -33.02h | No | Yes | Yes | No | No | 1.2.2.2.6.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.7 | Auto Scheduled | 0% | RTR_CM09_Activity_Type | No | 1.38d | Thu 5/21/26 | Mon 5/25/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Mon 5/25/26 |  | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 1722 |  |  | -4.75d | Yes | Yes | Yes | No | No | 1.2.2.2.7 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.7.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Kasey Hughes | 646 | 670 |  | NA | RTR_CM09_Activity_Type | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.3.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.7.2 | NA | 1723 | 1700 | 1724 | -38.02h | No | Yes | Yes | No | No | 1.2.2.2.7.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.7.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 5/21/26 | Fri 5/22/26 | Kasey Hughes | 669 | 671 | Brian Wagner | NA | RTR_CM09_Activity_Type | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.7.1 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.7.3 | NA | 1724 | 1723 | 1725 | -38.02h | No | Yes | Yes | No | No | 1.2.2.2.7.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.7.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 670 | 672 |  | NA | RTR_CM09_Activity_Type | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.7.2 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.7.4 | NA | 1725 | 1724 | 1726 | -38.02h | No | Yes | Yes | No | No | 1.2.2.2.7.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.7.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 5/22/26 | Fri 5/22/26 | Kasey Hughes | 671 | 673 | Brian Wagner | NA | RTR_CM09_Activity_Type | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.7.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.7.5 | NA | 1726 | 1725 | 1727 | -38.02h | No | Yes | Yes | No | No | 1.2.2.2.7.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.7.5 | Auto Scheduled | 0% | Load | No | 1h | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 672 | 674 |  | NA | RTR_CM09_Activity_Type | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.7.4 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.7.6 | NA | 1727 | 1726 | 1728 | -38.02h | No | Yes | Yes | No | No | 1.2.2.2.7.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.7.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Fri 5/22/26 | Mon 5/25/26 | Kasey Hughes | 673 |  | Brian Wagner | NA | RTR_CM09_Activity_Type | Fri 5/22/26 | Mon 5/25/26 | 1.2.2.2.7.5 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 1728 | 1727 |  | -38.02h | No | Yes | Yes | No | No | 1.2.2.2.7.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.8 | Auto Scheduled | 0% | RTR_CM12_Activity Rates | No | 1.13d | Tue 5/19/26 | Wed 5/20/26 |  |  |  |  | NA | Master Data Loads | Tue 5/19/26 | Wed 5/20/26 |  | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible |  | NA | 1729 |  |  | -2.56d | Yes | Yes | Yes | No | No | 1.2.2.2.8 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.8.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 639 | 677 |  | NA | RTR_CM12_Activity Rates | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.2.3 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.8.2 | NA | 1730 | 1693 | 1731 | -20.52h | No | Yes | Yes | No | No | 1.2.2.2.8.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.8.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 5/19/26 | Wed 5/20/26 | Kasey Hughes | 676 | 678 | Brian Wagner | NA | RTR_CM12_Activity Rates | Tue 5/19/26 | Wed 5/20/26 | 1.2.2.2.8.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.8.3 | NA | 1731 | 1730 | 1732 | -20.52h | No | Yes | Yes | No | No | 1.2.2.2.8.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.8.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 677 | 679 |  | NA | RTR_CM12_Activity Rates | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.8.2 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.8.4 | NA | 1732 | 1731 | 1733 | -20.52h | No | Yes | Yes | No | No | 1.2.2.2.8.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.8.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 5/20/26 | Wed 5/20/26 | Kasey Hughes | 678 | 680 | Brian Wagner | NA | RTR_CM12_Activity Rates | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.8.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.8.5 | NA | 1733 | 1732 | 1734 | -20.52h | No | Yes | Yes | No | No | 1.2.2.2.8.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.8.5 | Auto Scheduled | 0% | Load | No | 1h | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 679 | 681 |  | NA | RTR_CM12_Activity Rates | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.8.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.8.6 | NA | 1734 | 1733 | 1735 | -20.52h | No | Yes | Yes | No | No | 1.2.2.2.8.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.8.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Wed 5/20/26 | Wed 5/20/26 | Kasey Hughes | 680 |  | Brian Wagner | NA | RTR_CM12_Activity Rates | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.8.5 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible |  | NA | 1735 | 1734 |  | -20.52h | No | Yes | Yes | No | No | 1.2.2.2.8.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.9 | Auto Scheduled | 0% | RTR_CM06_Bank_master | No | 3.81d | Mon 5/18/26 | Fri 5/22/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Fri 5/22/26 |  | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 1736 |  |  | -6.06d | Yes | Yes | Yes | No | No | 1.2.2.2.9 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.9.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 646 | 684 |  | NA | RTR_CM06_Bank_master | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.3.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.9.2 | NA | 1737 | 1700 | 1738 | -30.02h | No | Yes | Yes | No | No | 1.2.2.2.9.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.9.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 5/21/26 | Fri 5/22/26 | Kasey Hughes | 683 |  | Brian Wagner | NA | RTR_CM06_Bank_master | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.9.1 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 1738 | 1737 |  | -30.02h | No | Yes | Yes | No | No | 1.2.2.2.9.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.9.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team |  | 686 |  | NA | RTR_CM06_Bank_master | Mon 5/18/26 | Mon 5/18/26 |  | Thu 4/9/26 | Thu 4/9/26 | Start No Earlier Than | 1.2.2.2.9.4 | Wed 4/15/26 | 1739 |  | 1740 | -48.52h | No | Yes | Yes | No | No | 1.2.2.2.9.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.9.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 685 | 687 | Brian Wagner | NA | RTR_CM06_Bank_master | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.9.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.9.5 | NA | 1740 | 1739 | 1741 | -48.52h | No | Yes | Yes | No | No | 1.2.2.2.9.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.9.5 | Auto Scheduled | 0% | Load | No | 5h | Mon 5/18/26 | Tue 5/19/26 | Data Migration Team | 686 | 688690 |  | NA | RTR_CM06_Bank_master | Mon 5/18/26 | Tue 5/19/26 | 1.2.2.2.9.4 | Thu 4/9/26 | Thu 4/9/26 | Finish No Earlier Than | 1.2.2.2.9.6,1.2.2.2.10.1 | Wed 4/15/26 | 1741 | 1740 | 17421744 | -48.52h | No | Yes | Yes | No | No | 1.2.2.2.9.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.9.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 687 | 724735 | Brian Wagner | NA | RTR_CM06_Bank_master | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.9.5 | Thu 4/9/26 | Thu 4/9/26 | Finish No Earlier Than | 1.2.2.2.15.3,1.2.2.2.17.3 | Tue 4/14/26 | 1742 | 1741 | 17781789 | -48.52h | No | Yes | Yes | No | No | 1.2.2.2.9.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.10 | Auto Scheduled | 0% | RTR_CM08_Exchange_Rates | No | 1.13d | Tue 5/19/26 | Wed 5/20/26 |  |  |  |  | NA | Master Data Loads | Tue 5/19/26 | Wed 5/20/26 |  | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 1743 |  |  | -2.06d | Yes | Yes | Yes | No | No | 1.2.2.2.10 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.10.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 687 | 691 |  | NA | RTR_CM08_Exchange_Rates | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.9.5 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.10.2 | NA | 1744 | 1741 | 1745 | -16.52h | No | Yes | Yes | No | No | 1.2.2.2.10.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.10.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 690 | 692 | Brian Wagner | NA | RTR_CM08_Exchange_Rates | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.10.1 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.10.3 | NA | 1745 | 1744 | 1746 | -16.52h | No | Yes | Yes | No | No | 1.2.2.2.10.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.10.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 5/19/26 | Tue 5/19/26 | Data Migration Team | 691 | 693 |  | NA | RTR_CM08_Exchange_Rates | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.10.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.10.4 | NA | 1746 | 1745 | 1747 | -16.52h | No | Yes | Yes | No | No | 1.2.2.2.10.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.10.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 692 | 694 | Brian Wagner | NA | RTR_CM08_Exchange_Rates | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.10.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.10.5 | NA | 1747 | 1746 | 1748 | -16.52h | No | Yes | Yes | No | No | 1.2.2.2.10.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.10.5 | Auto Scheduled | 0% | Load | No | 1h | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 693 | 695 |  | NA | RTR_CM08_Exchange_Rates | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.10.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.10.6 | NA | 1748 | 1747 | 1749 | -16.52h | No | Yes | Yes | No | No | 1.2.2.2.10.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.10.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Wed 5/20/26 | Wed 5/20/26 | Kasey Hughes | 694 |  | Brian Wagner | NA | RTR_CM08_Exchange_Rates | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.10.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 1749 | 1748 |  | -16.52h | No | Yes | Yes | No | No | 1.2.2.2.10.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.11 | Auto Scheduled | 0% | RTR_CM14_Cost Element_Group | No | 1.44d | Thu 5/21/26 | Mon 5/25/26 | Kasey Hughes |  |  | Brian Wagner | NA | Master Data Loads | Thu 5/21/26 | Mon 5/25/26 |  | Wed 4/8/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 1750 |  |  | -4.81d | Yes | Yes | Yes | No | No | 1.2.2.2.11 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.11.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Kasey Hughes | 646 | 698 |  | NA | RTR_CM14_Cost Element_Group | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.3.6 | Wed 4/8/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.11.2 | NA | 1751 | 1700 | 1752 | -2311m | No | Yes | Yes | No | No | 1.2.2.2.11.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.11.2 | Auto Scheduled | 0% | Load | No | 8h | Thu 5/21/26 | Fri 5/22/26 | Kasey Hughes | 697 | 699 |  | NA | RTR_CM14_Cost Element_Group | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.11.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.11.3 | NA | 1752 | 1751 | 1753 | -38.52h | No | Yes | Yes | No | No | 1.2.2.2.11.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.11.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 5/22/26 | Mon 5/25/26 | Kasey Hughes | 698 |  | Brian Wagner | NA | RTR_CM14_Cost Element_Group | Fri 5/22/26 | Mon 5/25/26 | 1.2.2.2.11.2 | Wed 4/15/26 | Wed 4/15/26 | Start No Earlier Than |  | Fri 4/17/26 | 1753 | 1752 |  | -38.52h | No | Yes | Yes | No | No | 1.2.2.2.11.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.12 | Auto Scheduled | 0% | OTC_CM19_Customer_Master - Bill-To | No | 2h | Mon 5/18/26 | Mon 5/18/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Mon 5/18/26 |  | Wed 4/16/25 | Wed 4/16/25 | As Soon As Possible |  | NA | 1754 |  |  | -1.52h | No | Yes | Yes | No | No | 1.2.2.2.12 | 5 | No | 500 | Future Task | No | 0h
1.2.2.2.13 | Auto Scheduled | 0% | OTC_CM19_Customer_Master - Ship-To | No | 1.5d | Thu 5/21/26 | Mon 5/25/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Mon 5/25/26 |  | Wed 4/8/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1755 |  |  | -9.31d | Yes | Yes | Yes | No | No | 1.2.2.2.13 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.13.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Ric Haraida | 646 | 703 |  | NA | OTC_CM19_Customer_Master - Ship-To | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.3.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.13.2 | NA | 1756 | 1700 | 1757 | -4471m | No | Yes | Yes | No | No | 1.2.2.2.13.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.13.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Ric Haraida | 702 | 707712704 | Kim Kolesar | NA | OTC_CM19_Customer_Master - Ship-To | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.13.1 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.2.2.13.6,1.2.2.2.14.1,1.2.2.2.13.3 | NA | 1757 | 1756 | 176117661758 | -4471m | No | Yes | Yes | No | No | 1.2.2.2.13.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.13.3 | Auto Scheduled | 0% | Open client for BP number range update | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Basis | 703 | 705 |  | NA | OTC_CM19_Customer_Master - Ship-To | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.13.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.13.4 | NA | 1758 | 1757 | 1759 | -1756m | No | Yes | Yes | No | No | 1.2.2.2.13.3 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.13.4 | Auto Scheduled | 0% | Update number range BP02 from Internal to External | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Ric Haraida | 704 | 706 |  | NA | OTC_CM19_Customer_Master - Ship-To | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.13.3 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.13.5 | NA | 1759 | 1758 | 1760 | -1756m | No | Yes | Yes | No | No | 1.2.2.2.13.4 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.13.5 | Auto Scheduled | 0% | Close Client | No | 15m | Thu 5/21/26 | Thu 5/21/26 | Basis | 705 |  |  | NA | OTC_CM19_Customer_Master - Ship-To | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.13.4 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1760 | 1759 |  | -1756m | No | Yes | Yes | No | No | 1.2.2.2.13.5 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.13.6 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 703 | 708714718 |  | NA | OTC_CM19_Customer_Master - Ship-To | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.13.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.13.7,1.2.2.2.14.3,1.2.2.2.14.7 | NA | 1761 | 1757 | 176217681772 | -74.52h | No | Yes | Yes | No | No | 1.2.2.2.13.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.13.7 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 4h | Thu 5/21/26 | Fri 5/22/26 | Ric Haraida | 707 | 709 | Kim Kolesar | NA | OTC_CM19_Customer_Master - Ship-To | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.13.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.13.8 | NA | 1762 | 1761 | 1763 | -39.02h | No | Yes | Yes | No | No | 1.2.2.2.13.7 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.13.8 | Auto Scheduled | 0% | Load | No | 3h | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 708 | 710 |  | NA | OTC_CM19_Customer_Master - Ship-To | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.13.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.13.9 | NA | 1763 | 1762 | 1764 | -39.02h | No | Yes | Yes | No | No | 1.2.2.2.13.8 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.13.9 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 5/22/26 | Mon 5/25/26 | Ric Haraida | 709 |  | Kim Kolesar | NA | OTC_CM19_Customer_Master - Ship-To | Fri 5/22/26 | Mon 5/25/26 | 1.2.2.2.13.8 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 1764 | 1763 |  | -39.02h | No | Yes | Yes | No | No | 1.2.2.2.13.9 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.14 | Auto Scheduled | 0% | OTC_CM19_Customer_Master - Sold-To | No | 1.63d | Thu 5/21/26 | Mon 5/25/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Mon 5/25/26 |  | Wed 4/8/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 1765 |  |  | -9.19d | Yes | Yes | Yes | No | No | 1.2.2.2.14 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.14.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Ric Haraida | 703 | 713 |  | NA | OTC_CM19_Customer_Master - Sold-To | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.13.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.14.2 | NA | 1766 | 1757 | 1767 | -1741m | No | Yes | Yes | No | No | 1.2.2.2.14.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.14.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Ric Haraida | 712 |  | Kim Kolesar | NA | OTC_CM19_Customer_Master - Sold-To | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.14.1 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 1767 | 1766 |  | -1741m | No | Yes | Yes | No | No | 1.2.2.2.14.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.14.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 648707 | 715 |  | NA | OTC_CM19_Customer_Master - Sold-To | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.3.8,1.2.2.2.13.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.14.4 | NA | 1768 | 17021761 | 1769 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.14.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.14.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 3h | Fri 5/22/26 | Fri 5/22/26 | Ric Haraida | 714 | 716 | Kim Kolesar | NA | OTC_CM19_Customer_Master - Sold-To | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.14.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.14.5 | NA | 1769 | 1768 | 1770 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.14.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.14.5 | Auto Scheduled | 0% | Load | No | 3h | Fri 5/22/26 | Mon 5/25/26 | Data Migration Team | 715 | 717722729733740 |  | NA | OTC_CM19_Customer_Master - Sold-To | Fri 5/22/26 | Mon 5/25/26 | 1.2.2.2.14.4 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.14.6,1.2.2.2.15.1,1.2.2.2.16.1,1.2.2.2.17.1,1.2.2.2.18.1 | NA | 1770 | 1769 | 1.7712e+19 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.14.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.14.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 5/25/26 | Mon 5/25/26 | Ric Haraida | 716 |  | Kim Kolesar | NA | OTC_CM19_Customer_Master - Sold-To | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 1771 | 1770 |  | -41.02h | No | Yes | Yes | No | No | 1.2.2.2.14.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.14.7 | Auto Scheduled | 0% | Open client for BP number range update | No | 15m | Thu 5/21/26 | Thu 5/21/26 | Basis | 707 | 719 |  | NA | OTC_CM19_Customer_Master - Sold-To | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.13.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.14.8 | NA | 1772 | 1761 | 1773 | -1786m | No | Yes | Yes | No | No | 1.2.2.2.14.7 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.14.8 | Auto Scheduled | 0% | Update number range BP02 from Internal to External | No | 15m | Thu 5/21/26 | Thu 5/21/26 | Ric Haraida | 718 | 720 |  | NA | OTC_CM19_Customer_Master - Sold-To | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.14.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.2.2.14.9 | NA | 1773 | 1772 | 1774 | -1786m | No | Yes | Yes | No | No | 1.2.2.2.14.8 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.14.9 | Auto Scheduled | 0% | Close Client | No | 15m | Fri 5/22/26 | Fri 5/22/26 | Basis | 719 |  |  | NA | OTC_CM19_Customer_Master - Sold-To | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.14.8 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 1774 | 1773 |  | -1786m | No | Yes | Yes | No | No | 1.2.2.2.14.9 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.15 | Auto Scheduled | 0% | PTP_CM27_Vendor Master as Customer - FLCU01 | No | 4.81d | Mon 5/25/26 | Fri 5/29/26 |  |  |  |  | NA | Master Data Loads | Mon 5/25/26 | Fri 5/29/26 |  | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1775 |  |  | -9.56d | Yes | Yes | Yes | No | No | 1.2.2.2.15 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.15.1 | Auto Scheduled | 0% | Extract File | No | 1h | Mon 5/25/26 | Mon 5/25/26 | Data Migration Team | 716 | 723 |  | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.15.2 | NA | 1776 | 1770 | 1777 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.15.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.15.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Mon 5/25/26 | Mon 5/25/26 | Nevin Varkey | 722 | 724 | Sam Houff | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.15.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.15.3 | NA | 1777 | 1776 | 1778 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.15.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.15.3 | Auto Scheduled | 0% | Simulate Load | No | 11.25h | Mon 5/25/26 | Tue 5/26/26 | Data Migration Team | 688723 | 725 |  | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Mon 5/25/26 | Tue 5/26/26 | 1.2.2.2.9.6,1.2.2.2.15.2 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.15.4 | NA | 1778 | 17421777 | 1779 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.15.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.15.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 5/26/26 | Thu 5/28/26 | Nevin Varkey | 724 | 726 | Sam Houff | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Tue 5/26/26 | Thu 5/28/26 | 1.2.2.2.15.3 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.15.5 | NA | 1779 | 1778 | 1780 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.15.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.15.5 | Auto Scheduled | 0% | Load | No | 1h | Thu 5/28/26 | Fri 5/29/26 | Data Migration Team | 725 | 727 |  | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Thu 5/28/26 | Fri 5/29/26 | 1.2.2.2.15.4 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.15.6 | NA | 1780 | 1779 | 1781 | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.15.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.15.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Fri 5/29/26 | Fri 5/29/26 | Nevin Varkey | 726 |  | Sam Houff | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Fri 5/29/26 | Fri 5/29/26 | 1.2.2.2.15.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1781 | 1780 |  | -76.52h | No | Yes | Yes | No | No | 1.2.2.2.15.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.16 | Auto Scheduled | 0% | OTC_CM23_Customer_Hierarchy | No | 0.69d | Mon 5/25/26 | Mon 5/25/26 |  |  |  |  | NA | Master Data Loads | Mon 5/25/26 | Mon 5/25/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 1782 |  |  | -5.44d | Yes | Yes | Yes | No | No | 1.2.2.2.16 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.16.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Mon 5/25/26 | Mon 5/25/26 | Ric Haraida | 716 | 730 | Kim Kolesar | NA | OTC_CM23_Customer_Hierarchy | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.16.2 | NA | 1783 | 1770 | 1784 | -2611m | No | Yes | Yes | No | No | 1.2.2.2.16.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.16.2 | Auto Scheduled | 0% | Load | No | 2h | Mon 5/25/26 | Mon 5/25/26 | Ric Haraida | 729 | 731 |  | NA | OTC_CM23_Customer_Hierarchy | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.16.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.16.3 | NA | 1784 | 1783 | 1785 | -43.52h | No | Yes | Yes | No | No | 1.2.2.2.16.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.16.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 5/25/26 | Mon 5/25/26 | Ric Haraida | 730 |  | Kim Kolesar | NA | OTC_CM23_Customer_Hierarchy | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.16.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 1785 | 1784 |  | -43.52h | No | Yes | Yes | No | No | 1.2.2.2.16.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.17 | Auto Scheduled | 0% | PTP_CM27_Vendor Master - Z001 - External Sales Rep | No | 3.38d | Mon 5/25/26 | Thu 5/28/26 |  |  |  |  | NA | Master Data Loads | Mon 5/25/26 | Thu 5/28/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1786 |  |  | -8.13d | Yes | Yes | Yes | No | No | 1.2.2.2.17 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.17.1 | Auto Scheduled | 0% | Extract File | No | 1h | Mon 5/25/26 | Mon 5/25/26 | Data Migration Team | 716 | 734747 |  | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.17.2,1.2.2.2.19.1 | NA | 1787 | 1770 | 17881801 | -65.02h | No | Yes | Yes | No | No | 1.2.2.2.17.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.17.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Mon 5/25/26 | Mon 5/25/26 | Nevin Varkey | 733 | 735 | Sam Houff | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.17.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.17.3 | NA | 1788 | 1787 | 1789 | -65.02h | No | Yes | Yes | No | No | 1.2.2.2.17.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.17.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 5/25/26 | Mon 5/25/26 | Data Migration Team | 688734 | 736 |  | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.9.6,1.2.2.2.17.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.17.4 | NA | 1789 | 17421788 | 1790 | -65.02h | No | Yes | Yes | No | No | 1.2.2.2.17.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.17.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 5/25/26 | Mon 5/25/26 | Nevin Varkey | 735 | 737 | Sam Houff | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.17.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.17.5 | NA | 1790 | 1789 | 1791 | -65.02h | No | Yes | Yes | No | No | 1.2.2.2.17.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.17.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 5/25/26 | Thu 5/28/26 | Data Migration Team | 736 | 738 |  | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Mon 5/25/26 | Thu 5/28/26 | 1.2.2.2.17.4 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.17.6 | NA | 1791 | 1790 | 1792 | -65.02h | No | Yes | Yes | No | No | 1.2.2.2.17.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.17.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Thu 5/28/26 | Thu 5/28/26 | Nevin Varkey | 737 |  | Sam Houff | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Thu 5/28/26 | Thu 5/28/26 | 1.2.2.2.17.5 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1792 | 1791 |  | -65.02h | No | Yes | Yes | No | No | 1.2.2.2.17.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.18 | Auto Scheduled | 0% | RTR_CM10_Credit_Management_Role | No | 1.84d | Mon 5/25/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Mon 5/25/26 | Tue 5/26/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1793 |  |  | -7.35d | Yes | Yes | Yes | No | No | 1.2.2.2.18 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.18.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 5/25/26 | Mon 5/25/26 | Kasey Hughes | 716 | 741 |  | NA | RTR_CM10_Credit_Management_Role | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.18.2 | NA | 1794 | 1770 | 1795 | -3526m | No | Yes | Yes | No | No | 1.2.2.2.18.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.18.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 5/25/26 | Mon 5/25/26 | Kasey Hughes | 740 | 742 | Brian Wagner | NA | RTR_CM10_Credit_Management_Role | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.18.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.18.3 | NA | 1795 | 1794 | 1796 | -3526m | No | Yes | Yes | No | No | 1.2.2.2.18.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.18.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 5/25/26 | Mon 5/25/26 | Data Migration Team | 741 | 743 |  | NA | RTR_CM10_Credit_Management_Role | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.18.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.18.4 | NA | 1796 | 1795 | 1797 | -58.77h | No | Yes | Yes | No | No | 1.2.2.2.18.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.18.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 5/25/26 | Mon 5/25/26 | Kasey Hughes | 742 | 744761 | Brian Wagner | NA | RTR_CM10_Credit_Management_Role | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.18.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.18.5,1.2.2.2.21.1 | NA | 1797 | 1796 | 17981815 | -58.77h | No | Yes | Yes | No | No | 1.2.2.2.18.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.18.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 5/25/26 | Tue 5/26/26 | Data Migration Team | 743 | 745 |  | NA | RTR_CM10_Credit_Management_Role | Mon 5/25/26 | Tue 5/26/26 | 1.2.2.2.18.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.18.6 | NA | 1798 | 1797 | 1799 | -58.77h | No | Yes | Yes | No | No | 1.2.2.2.18.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.18.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 5/26/26 | Tue 5/26/26 | Kasey Hughes | 744 | 762927 | Brian Wagner | NA | RTR_CM10_Credit_Management_Role | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.18.5 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.21.2,1.2.2.2.51.2 | NA | 1799 | 1798 | 18161981 | -58.77h | No | Yes | Yes | No | No | 1.2.2.2.18.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.19 | Auto Scheduled | 0% | PTP_CM27_Vendor Master | No | 6.28d | Mon 5/18/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Tue 5/26/26 |  | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 1800 |  |  | -8.78d | Yes | Yes | Yes | No | No | 1.2.2.2.19 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.19.1 | Auto Scheduled | 0% | Extract File | No | 1h | Mon 5/25/26 | Mon 5/25/26 | Data Migration Team | 733 | 748 |  | NA | PTP_CM27_Vendor Master | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.17.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.19.2 | NA | 1801 | 1787 | 1802 | -49.77h | No | Yes | Yes | No | No | 1.2.2.2.19.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.19.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Mon 5/25/26 | Mon 5/25/26 | Nevin Varkey | 747 | 749 | Sam Houff | NA | PTP_CM27_Vendor Master | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.19.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.19.3 | NA | 1802 | 1801 | 1803 | -49.77h | No | Yes | Yes | No | No | 1.2.2.2.19.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.19.3 | Auto Scheduled | 0% | Simulate Load | No | 2.25h | Mon 5/25/26 | Mon 5/25/26 | Data Migration Team | 748 | 750 |  | NA | PTP_CM27_Vendor Master | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.19.2 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.19.4 | NA | 1803 | 1802 | 1804 | -49.77h | No | Yes | Yes | No | No | 1.2.2.2.19.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.19.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 5/25/26 | Tue 5/26/26 | Nevin Varkey | 749 |  | Sam Houff | NA | PTP_CM27_Vendor Master | Mon 5/25/26 | Tue 5/26/26 | 1.2.2.2.19.3 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1804 | 1803 |  | -49.77h | No | Yes | Yes | No | No | 1.2.2.2.19.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.19.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team |  | 752 |  | NA | PTP_CM27_Vendor Master | Mon 5/18/26 | Mon 5/18/26 |  | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.19.6 | NA | 1805 |  | 1806 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.19.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.19.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey | 751 | 765780804 | Sam Houff | NA | PTP_CM27_Vendor Master | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.19.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.22.1,1.2.2.2.24.2,1.2.2.2.27.5 | NA | 1806 | 1805 | 181918341858 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.19.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.20 | Auto Scheduled | 0% | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | No | 0.88d | Mon 5/18/26 | Tue 5/19/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Tue 5/19/26 |  | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 1807 |  |  | -1.44d | Yes | Yes | Yes | No | No | 1.2.2.2.20 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.20.1 | Auto Scheduled | 0% | Extract File(Will Extract from LFA1) | No | 1h | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey |  | 755779 |  | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Mon 5/18/26 | Mon 5/18/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.20.2,1.2.2.2.24.1 | NA | 1808 |  | 18091833 | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.20.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.20.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey | 754 | 756 | Sam Houff | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.20.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.20.3 | NA | 1809 | 1808 | 1810 | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.20.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.20.3 | Auto Scheduled | 0% | Simulate Load/ Not Needed | No | 1h | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey | 755 | 757758 |  | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.20.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.20.4,1.2.2.2.20.5 | NA | 1810 | 1809 | 18111812 | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.20.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.20.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey | 756 |  | Sam Houff | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.20.3 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1811 | 1810 |  | -5.52h | No | Yes | Yes | No | No | 1.2.2.2.20.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.20.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkkey | 756 | 759 |  | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.20.3 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.20.6 | NA | 1812 | 1810 | 1813 | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.20.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.20.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 5/18/26 | Tue 5/19/26 | Nevin Varkey | 758 | 954 | Sam Houff | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Mon 5/18/26 | Tue 5/19/26 | 1.2.2.2.20.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.57.1 | NA | 1813 | 1812 | 2008 | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.20.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.21 | Auto Scheduled | 0% | RTR_****_Credit Hierarchy | No | 1.91d | Mon 5/25/26 | Wed 5/27/26 |  |  |  |  | NA | Master Data Loads | Mon 5/25/26 | Wed 5/27/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1814 |  |  | -7.22d | Yes | Yes | Yes | No | No | 1.2.2.2.21 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.21.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Mon 5/25/26 | Mon 5/25/26 | Kasey Hughes | 743 |  | Brian Wagner | NA | RTR_****_Credit Hierarchy | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.18.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 1815 | 1797 |  | -2581m | No | Yes | Yes | No | No | 1.2.2.2.21.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.21.2 | Auto Scheduled | 0% | Load | No | 2h | Tue 5/26/26 | Wed 5/27/26 | Kasey Hughes | 745 | 763 |  | NA | RTR_****_Credit Hierarchy | Tue 5/26/26 | Wed 5/27/26 | 1.2.2.2.18.6 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.21.3 | NA | 1816 | 1799 | 1817 | -57.77h | No | Yes | Yes | No | No | 1.2.2.2.21.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.21.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 5/27/26 | Wed 5/27/26 | Kasey Hughes | 762 |  | Brian Wagner | NA | RTR_****_Credit Hierarchy | Wed 5/27/26 | Wed 5/27/26 | 1.2.2.2.21.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1817 | 1816 |  | -57.77h | No | Yes | Yes | No | No | 1.2.2.2.21.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.22 | Auto Scheduled | 0% | PTP_CM27_BP_Intercompany Supplier | No | 1.13d | Mon 5/18/26 | Tue 5/19/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Tue 5/19/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1818 |  |  | -1.44d | Yes | Yes | Yes | No | No | 1.2.2.2.22 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.22.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey,Ric Haraida | 752 | 766 |  | NA | PTP_CM27_BP_Intercompany Supplier | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.19.6 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.22.2 | NA | 1819 | 1806 | 1820 | -691m | No | Yes | Yes | No | No | 1.2.2.2.22.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.22.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey,Ric Haraida | 765 | 767 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Supplier | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.22.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.22.3 | NA | 1820 | 1819 | 1821 | -691m | No | Yes | Yes | No | No | 1.2.2.2.22.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.22.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 766 | 768 |  | NA | PTP_CM27_BP_Intercompany Supplier | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.22.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.22.4 | NA | 1821 | 1820 | 1822 | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.22.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.22.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 5/18/26 | Tue 5/19/26 | Nevin Varkey,Ric Haraida | 767 | 769 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Supplier | Mon 5/18/26 | Tue 5/19/26 | 1.2.2.2.22.3 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.22.5 | NA | 1822 | 1821 | 1823 | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.22.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.22.5 | Auto Scheduled | 0% | Load | No | 2h | Tue 5/19/26 | Tue 5/19/26 | Data Migration Team | 768 | 770926 |  | NA | PTP_CM27_BP_Intercompany Supplier | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.22.4 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.22.6,1.2.2.2.51.1 | NA | 1823 | 1822 | 18241980 | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.22.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.22.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 5/19/26 | Tue 5/19/26 | Nevin Varkey,Ric Haraida | 769 |  | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Supplier | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.22.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1824 | 1823 |  | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.22.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.23 | Auto Scheduled | 0% | PTP_CM27_BP_Intercompany Customer | No | 1.06d | Mon 5/18/26 | Tue 5/19/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Tue 5/19/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1825 |  |  | -1d | Yes | Yes | Yes | No | No | 1.2.2.2.23 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.23.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey,Ric Haraida |  |  |  | NA | PTP_CM27_BP_Intercompany Customer | Mon 5/18/26 | Mon 5/18/26 |  | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1826 |  |  | -1m | No | Yes | Yes | No | No | 1.2.2.2.23.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.23.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey,Ric Haraida |  | 774 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Customer | Mon 5/18/26 | Mon 5/18/26 |  | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.23.3 | NA | 1827 |  | 1828 | -481m | No | Yes | Yes | No | No | 1.2.2.2.23.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.23.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 773 | 775 |  | NA | PTP_CM27_BP_Intercompany Customer | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.23.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.23.4 | NA | 1828 | 1827 | 1829 | -8.02h | No | Yes | Yes | No | No | 1.2.2.2.23.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.23.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey,Ric Haraida | 774 | 776 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Customer | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.23.3 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.23.5 | NA | 1829 | 1828 | 1830 | -8.02h | No | Yes | Yes | No | No | 1.2.2.2.23.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.23.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 775 | 777926 |  | NA | PTP_CM27_BP_Intercompany Customer | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.23.4 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.23.6,1.2.2.2.51.1 | NA | 1830 | 1829 | 18311980 | -8.02h | No | Yes | Yes | No | No | 1.2.2.2.23.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.23.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 5/18/26 | Tue 5/19/26 | Nevin Varkey,Ric Haraida | 776 |  | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Customer | Mon 5/18/26 | Tue 5/19/26 | 1.2.2.2.23.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1831 | 1830 |  | -8.02h | No | Yes | Yes | No | No | 1.2.2.2.23.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.24 | Auto Scheduled | 0% | PTP_CM26_Material_Master - All Types | No | 2.28d | Mon 5/18/26 | Wed 5/20/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Wed 5/20/26 |  | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 1832 |  |  | -8.53d | Yes | Yes | Yes | No | No | 1.2.2.2.24 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.24.1 | Auto Scheduled | 0% | Extract File | No | 5h | Mon 5/18/26 | Tue 5/19/26 | Data Migration Team | 754 |  |  | NA | PTP_CM26_Material_Master - All Types | Mon 5/18/26 | Tue 5/19/26 | 1.2.2.2.20.1 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1833 | 1808 |  | -7.27h | No | Yes | Yes | No | No | 1.2.2.2.24.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.24.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Mon 5/18/26 | Tue 5/19/26 | Nevin Varkey,Ric Haraida | 752 | 781 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - All Types | Mon 5/18/26 | Tue 5/19/26 | 1.2.2.2.19.6 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.24.3 | NA | 1834 | 1806 | 1835 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.24.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.24.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 5/19/26 | Tue 5/19/26 | Data Migration Team | 780 | 782 |  | NA | PTP_CM26_Material_Master - All Types | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.24.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.24.4 | NA | 1835 | 1834 | 1836 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.24.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.24.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 4h | Tue 5/19/26 | Wed 5/20/26 | Nevin Varkey | 781 | 783 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - All Types | Tue 5/19/26 | Wed 5/20/26 | 1.2.2.2.24.3 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.24.5 | NA | 1836 | 1835 | 1837 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.24.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.24.5 | Auto Scheduled | 0% | Load | No | 3h | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 782 | 784787794 |  | NA | PTP_CM26_Material_Master - All Types | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.24.4 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.24.6,1.2.2.2.25.2,1.2.2.2.26.2 | NA | 1837 | 1836 | 183818411848 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.24.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.24.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Wed 5/20/26 | Wed 5/20/26 | Nevin Varkey | 783 | 800807814 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - All Types | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.24.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.27.1,1.2.2.2.28.1,1.2.2.2.29.1 | NA | 1838 | 1837 | 185418611868 | -63.77h | No | Yes | Yes | No | No | 1.2.2.2.24.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.25 | Auto Scheduled | 0% | PTP_CM26_Material_Master - SERV - Service Materials | No | 1.34d | Wed 5/20/26 | Thu 5/21/26 |  |  |  |  | NA | Master Data Loads | Wed 5/20/26 | Thu 5/21/26 |  | Tue 4/7/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 1839 |  |  | -3.16d | Yes | Yes | Yes | No | No | 1.2.2.2.25 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.25.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Wed 5/20/26 | Wed 5/20/26 | Nevin Varkey,Ric Haraida | 655 |  |  | NA | PTP_CM26_Material_Master - SERV - Service Materials | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.4.6 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 1840 | 1709 |  | -901m | No | Yes | Yes | No | No | 1.2.2.2.25.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.25.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Wed 5/20/26 | Wed 5/20/26 | Nevin Varkey,Ric Haraida | 783 | 788 | Sam Houff,Kim Kolesar | NA | PTP_CM26_Material_Master - SERV - Service Materials | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.24.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.25.3 | NA | 1841 | 1837 | 1842 | -1516m | No | Yes | Yes | No | No | 1.2.2.2.25.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.25.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 787 | 789 |  | NA | PTP_CM26_Material_Master - SERV - Service Materials | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.25.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.25.4 | NA | 1842 | 1841 | 1843 | -25.27h | No | Yes | Yes | No | No | 1.2.2.2.25.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.25.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 5/20/26 | Wed 5/20/26 | Nevin Varkey,Ric Haraida | 788 | 790 | Sam Houff,Kim Kolesar | NA | PTP_CM26_Material_Master - SERV - Service Materials | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.25.3 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.25.5 | NA | 1843 | 1842 | 1844 | -25.27h | No | Yes | Yes | No | No | 1.2.2.2.25.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.25.5 | Auto Scheduled | 0% | Load | No | 2h | Wed 5/20/26 | Thu 5/21/26 | Data Migration Team | 789 | 791 |  | NA | PTP_CM26_Material_Master - SERV - Service Materials | Wed 5/20/26 | Thu 5/21/26 | 1.2.2.2.25.4 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.25.6 | NA | 1844 | 1843 | 1845 | -25.27h | No | Yes | Yes | No | No | 1.2.2.2.25.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.25.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey,Ric Haraida | 790 |  | Sam Houff,Kim Kolesar | NA | PTP_CM26_Material_Master - SERV - Service Materials | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.25.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 1845 | 1844 |  | -25.27h | No | Yes | Yes | No | No | 1.2.2.2.25.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.26 | Auto Scheduled | 0% | PTP_CM26_Material_Master - KMAT - Configurable Materials | No | 1.34d | Wed 5/20/26 | Thu 5/21/26 |  |  | 885882 |  | NA | Master Data Loads | Wed 5/20/26 | Thu 5/21/26 |  | Tue 4/7/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.42.1,1.2.2.2.41.1 | NA | 1846 |  | 19391936 | -8.5d | Yes | Yes | Yes | No | No | 1.2.2.2.26 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.26.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Wed 5/20/26 | Wed 5/20/26 | Eric Heisler | 655 |  |  | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.4.6 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 1847 | 1709 |  | -2146m | No | Yes | Yes | No | No | 1.2.2.2.26.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.26.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Wed 5/20/26 | Wed 5/20/26 | Eric Heisler | 783 | 795 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.24.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.26.3 | NA | 1848 | 1837 | 1849 | -4216m | No | Yes | Yes | No | No | 1.2.2.2.26.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.26.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 794 | 796 |  | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.26.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.2.2.26.4 | NA | 1849 | 1848 | 1850 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.26.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.26.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 5/20/26 | Wed 5/20/26 | Eric Heisler | 795 | 797 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Wed 5/20/26 | Wed 5/20/26 | 1.2.2.2.26.3 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.26.5 | NA | 1850 | 1849 | 1851 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.26.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.26.5 | Auto Scheduled | 0% | Load | No | 2h | Wed 5/20/26 | Thu 5/21/26 | Data Migration Team | 796 | 798 |  | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Wed 5/20/26 | Thu 5/21/26 | 1.2.2.2.26.4 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.26.6 | NA | 1851 | 1850 | 1852 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.26.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.26.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 5/21/26 | Thu 5/21/26 | Eric Heisler | 797 | 800807814879897 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.26.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.27.1,1.2.2.2.28.1,1.2.2.2.29.1,1.2.2.2.40.1,1.2.2.2.46.1 | NA | 1852 | 1851 | 1.8542e+19 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.26.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.27 | Auto Scheduled | 0% | PTP_CM28_Purchase_Info_Records | No | 3.59d | Mon 5/18/26 | Fri 5/22/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Fri 5/22/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1853 |  |  | -4.96d | Yes | Yes | Yes | No | No | 1.2.2.2.27 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.27.1 | Auto Scheduled | 0% | Extract File | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 784798 | 801821 |  | NA | PTP_CM28_Purchase_Info_Records | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.24.6,1.2.2.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.27.2,1.2.2.2.30.1 | NA | 1854 | 18381852 | 18551875 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.27.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.27.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 800 | 802 | Sam Houff | NA | PTP_CM28_Purchase_Info_Records | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.27.1 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.27.3 | NA | 1855 | 1854 | 1856 | -31.27h | No | Yes | Yes | No | No | 1.2.2.2.27.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.27.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 801 | 803 |  | NA | PTP_CM28_Purchase_Info_Records | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.27.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.27.4 | NA | 1856 | 1855 | 1857 | -31.27h | No | Yes | Yes | No | No | 1.2.2.2.27.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.27.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 5/21/26 | Fri 5/22/26 | Nevin Varkey | 802 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Records | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.27.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1857 | 1856 |  | -31.27h | No | Yes | Yes | No | No | 1.2.2.2.27.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.27.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 752 | 805 |  | NA | PTP_CM28_Purchase_Info_Records | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.19.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.27.6 | NA | 1858 | 1806 | 1859 | -5.52h | No | Yes | Yes | No | No | 1.2.2.2.27.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.27.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey | 804 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Records | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.27.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 1859 | 1858 |  | -5.52h | No | Yes | Yes | No | No | 1.2.2.2.27.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.28 | Auto Scheduled | 0% | PTP_CM28_Purchase_Info_Record External Processing | No | 1.13d | Thu 5/21/26 | Fri 5/22/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Fri 5/22/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1860 |  |  | -4.28d | Yes | Yes | Yes | No | No | 1.2.2.2.28 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.28.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 784798 | 808 |  | NA | PTP_CM28_Purchase_Info_Record External Processing | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.24.6,1.2.2.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.28.2 | NA | 1861 | 18381852 | 1862 | -2056m | No | Yes | Yes | No | No | 1.2.2.2.28.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.28.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 807 | 809 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record External Processing | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.28.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.28.3 | NA | 1862 | 1861 | 1863 | -2056m | No | Yes | Yes | No | No | 1.2.2.2.28.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.28.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 808 | 810 |  | NA | PTP_CM28_Purchase_Info_Record External Processing | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.28.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.28.4 | NA | 1863 | 1862 | 1864 | -34.27h | No | Yes | Yes | No | No | 1.2.2.2.28.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.28.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 809 | 811 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record External Processing | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.28.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.28.5 | NA | 1864 | 1863 | 1865 | -34.27h | No | Yes | Yes | No | No | 1.2.2.2.28.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.28.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 5/21/26 | Fri 5/22/26 | Data Migration Team | 810 | 812 |  | NA | PTP_CM28_Purchase_Info_Record External Processing | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.28.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.28.6 | NA | 1865 | 1864 | 1866 | -34.27h | No | Yes | Yes | No | No | 1.2.2.2.28.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.28.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 5/22/26 | Fri 5/22/26 | Nevin Varkey | 811 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Record External Processing | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.28.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1866 | 1865 |  | -34.27h | No | Yes | Yes | No | No | 1.2.2.2.28.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.29 | Auto Scheduled | 0% | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | No | 1.13d | Thu 5/21/26 | Fri 5/22/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Fri 5/22/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1867 |  |  | -8.78d | Yes | Yes | Yes | No | No | 1.2.2.2.29 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.29.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 784798 | 815 |  | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.24.6,1.2.2.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.29.2 | NA | 1868 | 18381852 | 1869 | -4216m | No | Yes | Yes | No | No | 1.2.2.2.29.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.29.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 814 | 816 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.29.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.29.3 | NA | 1869 | 1868 | 1870 | -4216m | No | Yes | Yes | No | No | 1.2.2.2.29.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.29.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 815 | 817948 |  | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.29.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.29.4,1.2.2.2.55.1 | NA | 1870 | 1869 | 18712002 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.29.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.29.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 816 | 818 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.29.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.29.5 | NA | 1871 | 1870 | 1872 | -34.27h | No | Yes | Yes | No | No | 1.2.2.2.29.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.29.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 5/21/26 | Fri 5/22/26 | Data Migration Team | 817 | 819 |  | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.29.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.29.6 | NA | 1872 | 1871 | 1873 | -34.27h | No | Yes | Yes | No | No | 1.2.2.2.29.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.29.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 5/22/26 | Fri 5/22/26 | Nevin Varkey | 818 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.29.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1873 | 1872 |  | -34.27h | No | Yes | Yes | No | No | 1.2.2.2.29.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.30 | Auto Scheduled | 0% | PTM_CM31_BOM Conversion | No | 2.48d | Thu 5/21/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Tue 5/26/26 |  | Wed 4/15/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1874 |  |  | -7.8d | Yes | Yes | Yes | No | No | 1.2.2.2.30 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.30.1 | Auto Scheduled | 0% | Extract File | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 800 | 822828 |  | NA | PTM_CM31_BOM Conversion | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.27.1 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.30.2,1.2.2.2.31.1 | NA | 1875 | 1854 | 18761882 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.30.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.30.2 | Auto Scheduled | 0% | Pre Load Validation | No | 0.5h | Thu 5/21/26 | Thu 5/21/26 | Brad Meseck | 821 | 823 | Matt Palastro, Dave Duda | NA | PTM_CM31_BOM Conversion | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.30.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.30.3 | NA | 1876 | 1875 | 1877 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.30.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.30.3 | Auto Scheduled | 0% | Simulate Load | No | 15.5h | Thu 5/21/26 | Mon 5/25/26 | Data Migration Team | 822 | 824 |  | NA | PTM_CM31_BOM Conversion | Thu 5/21/26 | Mon 5/25/26 | 1.2.2.2.30.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.30.4 | NA | 1877 | 1876 | 1878 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.30.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.30.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 0.5h | Mon 5/25/26 | Mon 5/25/26 | Brad Meseck | 823 | 825 | Matt Palastro, Dave Duda | NA | PTM_CM31_BOM Conversion | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.30.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 2026-04-01 | NA | 1878 | 1877 | 1879 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.30.4 | 6 | No | 500 | Future Task | No | 0h
2026-04-01 | Auto Scheduled | 0% | Load | No | 1h | Mon 5/25/26 | Mon 5/25/26 | Data Migration Team | 824 | 826 |  | NA | PTM_CM31_BOM Conversion | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.30.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.30.6 | NA | 1879 | 1878 | 1880 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.30.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.30.6 | Auto Scheduled | 0% | Post Load Validation | No | 0.5h | Tue 5/26/26 | Tue 5/26/26 | Brad Meseck | 825 | 829 | Matt Palastro, Dave Duda | NA | PTM_CM31_BOM Conversion | Tue 5/26/26 | Tue 5/26/26 | 2026-04-01 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.31.2 | NA | 1880 | 1879 | 1883 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.30.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.31 | Auto Scheduled | 0% | PTM_CM40_Work Center Conversion | No | 3.08d | Thu 5/21/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Tue 5/26/26 |  | Thu 4/16/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 1881 |  |  | -7.8d | Yes | Yes | Yes | No | No | 1.2.2.2.31 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.31.1 | Auto Scheduled | 0% | Extract File | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 821 | 835 |  | NA | PTM_CM40_Work Center Conversion | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.30.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.32.1 | NA | 1882 | 1875 | 1889 | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.31.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.31.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 5/26/26 | Tue 5/26/26 | Brad Meseck | 826 | 830 | Matt Palastro, Dave Duda | NA | PTM_CM40_Work Center Conversion | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.30.6 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.31.3 | NA | 1883 | 1880 | 1884 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.31.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.31.3 | Auto Scheduled | 0% | Simulate Load | No | 0.25h | Tue 5/26/26 | Tue 5/26/26 | Data Migration Team | 829 | 831 |  | NA | PTM_CM40_Work Center Conversion | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.31.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.31.4 | NA | 1884 | 1883 | 1885 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.31.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.31.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 0.5h | Tue 5/26/26 | Tue 5/26/26 | Brad Meseck | 830 | 832 | Matt Palastro, Dave Duda | NA | PTM_CM40_Work Center Conversion | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.31.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.31.5 | NA | 1885 | 1884 | 1886 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.31.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.31.5 | Auto Scheduled | 0% | Load | No | 1h | Tue 5/26/26 | Tue 5/26/26 | Data Migration Team | 831 | 833 |  | NA | PTM_CM40_Work Center Conversion | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.31.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.31.6 | NA | 1886 | 1885 | 1887 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.31.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.31.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Tue 5/26/26 | Tue 5/26/26 | Brad Meseck | 832 | 836 | Matt Palastro, Dave Duda | NA | PTM_CM40_Work Center Conversion | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.31.5 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.32.2 | NA | 1887 | 1886 | 1890 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.31.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.32 | Auto Scheduled | 0% | PTM_CM38_Routing Conversion | No | 4.27d | Thu 5/21/26 | Thu 5/28/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Thu 5/28/26 |  | Thu 4/16/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 1888 |  |  | -7.8d | Yes | Yes | Yes | No | No | 1.2.2.2.32 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.32.1 | Auto Scheduled | 0% | Extract File | No | 1h | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 828 | 842 |  | NA | PTM_CM38_Routing Conversion | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.31.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.33.1 | NA | 1889 | 1882 | 1896 | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.32.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.32.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 5/26/26 | Wed 5/27/26 | Brad Meseck | 833 | 837 | Matt Palastro, Dave Duda | NA | PTM_CM38_Routing Conversion | Tue 5/26/26 | Wed 5/27/26 | 1.2.2.2.31.6 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.32.3 | NA | 1890 | 1887 | 1891 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.32.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.32.3 | Auto Scheduled | 0% | Simulate Load | No | 2h | Wed 5/27/26 | Wed 5/27/26 | Data Migration Team | 836 | 838SS |  | NA | PTM_CM38_Routing Conversion | Wed 5/27/26 | Wed 5/27/26 | 1.2.2.2.32.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.32.4[SS] | NA | 1891 | 1890 | 1892SS | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.32.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.32.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 3h | Wed 5/27/26 | Wed 5/27/26 | Brad Meseck | 837SS | 839 | Matt Palastro, Dave Duda | NA | PTM_CM38_Routing Conversion | Wed 5/27/26 | Wed 5/27/26 | 1.2.2.2.32.3[SS] | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.32.5 | NA | 1892 | 1891SS | 1893 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.32.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.32.5 | Auto Scheduled | 0% | Load | No | 1h | Wed 5/27/26 | Wed 5/27/26 | Data Migration Team | 838 | 840 |  | NA | PTM_CM38_Routing Conversion | Wed 5/27/26 | Wed 5/27/26 | 1.2.2.2.32.4 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.32.6 | NA | 1893 | 1892 | 1894 | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.32.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.32.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Wed 5/27/26 | Thu 5/28/26 | Brad Meseck | 839 |  | Matt Palastro, Dave Duda | NA | PTM_CM38_Routing Conversion | Wed 5/27/26 | Thu 5/28/26 | 1.2.2.2.32.5 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 1894 | 1893 |  | -62.39h | No | Yes | Yes | No | No | 1.2.2.2.32.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.33 | Auto Scheduled | 0% | PTM_CM36_Production Version Conversion | No | 1.13d | Thu 5/21/26 | Mon 5/25/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Mon 5/25/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1895 |  |  | -6.72d | Yes | Yes | Yes | No | No | 1.2.2.2.33 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.33.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 5/21/26 | Fri 5/22/26 | Brad Meseck | 835 | 843937 |  | NA | PTM_CM36_Production Version Conversion | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.32.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.33.2,1.2.2.2.53.1 | NA | 1896 | 1889 | 18971991 | -3226m | No | Yes | Yes | No | No | 1.2.2.2.33.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.33.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Fri 5/22/26 | Fri 5/22/26 | Brad Meseck | 842 | 844 | Matt Palastro, Dave Duda | NA | PTM_CM36_Production Version Conversion | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.33.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.33.3 | NA | 1897 | 1896 | 1898 | -3226m | No | Yes | Yes | No | No | 1.2.2.2.33.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.33.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 843 | 845 |  | NA | PTM_CM36_Production Version Conversion | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.33.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.33.4 | NA | 1898 | 1897 | 1899 | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.33.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.33.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 5/22/26 | Fri 5/22/26 | Brad Meseck | 844 | 846 | Matt Palastro, Dave Duda | NA | PTM_CM36_Production Version Conversion | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.33.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.33.5 | NA | 1899 | 1898 | 1900 | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.33.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.33.5 | Auto Scheduled | 0% | Load | No | 2h | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 845 | 847 |  | NA | PTM_CM36_Production Version Conversion | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.33.4 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.33.6 | NA | 1900 | 1899 | 1901 | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.33.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.33.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 5/22/26 | Mon 5/25/26 | Brad Meseck | 846 | 849 | Matt Palastro, Dave Duda | NA | PTM_CM36_Production Version Conversion | Fri 5/22/26 | Mon 5/25/26 | 1.2.2.2.33.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.34.1 | NA | 1901 | 1900 | 1903 | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.33.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.34 | Auto Scheduled | 0% | PTM_CM35_Inspection Plan | No | 1.13d | Mon 5/25/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Mon 5/25/26 | Tue 5/26/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 1902 |  |  | -6.72d | Yes | Yes | Yes | No | No | 1.2.2.2.34 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.34.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 5/25/26 | Mon 5/25/26 | Brad Meseck | 847 | 850856 |  | NA | PTM_CM35_Inspection Plan | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.33.6 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.34.2,1.2.2.2.35.1 | NA | 1903 | 1901 | 19041910 | -3226m | No | Yes | Yes | No | No | 1.2.2.2.34.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.34.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 5/25/26 | Mon 5/25/26 | Brad Meseck | 849 | 851 | Matt Palastro, Dave Duda | NA | PTM_CM35_Inspection Plan | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.34.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.34.3 | NA | 1904 | 1903 | 1905 | -2836m | No | Yes | Yes | No | No | 1.2.2.2.34.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.34.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 5/25/26 | Mon 5/25/26 | Data Migration Team | 850 | 852 |  | NA | PTM_CM35_Inspection Plan | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.34.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.34.4 | NA | 1905 | 1904 | 1906 | -47.27h | No | Yes | Yes | No | No | 1.2.2.2.34.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.34.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 5/25/26 | Mon 5/25/26 | Brad Meseck | 851 | 853 | Matt Palastro, Dave Duda | NA | PTM_CM35_Inspection Plan | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.34.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.34.5 | NA | 1906 | 1905 | 1907 | -47.27h | No | Yes | Yes | No | No | 1.2.2.2.34.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.34.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 5/25/26 | Mon 5/25/26 | Data Migration Team | 852 | 854 |  | NA | PTM_CM35_Inspection Plan | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.34.4 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.34.6 | NA | 1907 | 1906 | 1908 | -47.27h | No | Yes | Yes | No | No | 1.2.2.2.34.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.34.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 5/25/26 | Tue 5/26/26 | Brad Meseck | 853 |  | Matt Palastro, Dave Duda | NA | PTM_CM35_Inspection Plan | Mon 5/25/26 | Tue 5/26/26 | 1.2.2.2.34.5 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 1908 | 1907 |  | -47.27h | No | Yes | Yes | No | No | 1.2.2.2.34.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.35 | Auto Scheduled | 0% | PTM_CM48_Equipment_Master_Serial Numbers | No | 1.13d | Mon 5/25/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Mon 5/25/26 | Tue 5/26/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 1909 |  |  | -6.72d | Yes | Yes | Yes | No | No | 1.2.2.2.35 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.35.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 5/25/26 | Mon 5/25/26 | Brad Meseck | 849 | 857 |  | NA | PTM_CM48_Equipment_Master_Serial Numbers | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.34.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.35.2 | NA | 1910 | 1903 | 1911 | -3226m | No | Yes | Yes | No | No | 1.2.2.2.35.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.35.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 5/25/26 | Mon 5/25/26 | Brad Meseck | 856 | 858 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Serial Numbers | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.35.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.35.3 | NA | 1911 | 1910 | 1912 | -3226m | No | Yes | Yes | No | No | 1.2.2.2.35.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.35.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 5/25/26 | Mon 5/25/26 | Data Migration Team | 857 | 859 |  | NA | PTM_CM48_Equipment_Master_Serial Numbers | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.35.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.35.4 | NA | 1912 | 1911 | 1913 | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.35.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.35.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 5/25/26 | Mon 5/25/26 | Brad Meseck | 858 | 860 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Serial Numbers | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.35.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.35.5 | NA | 1913 | 1912 | 1914 | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.35.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.35.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 5/25/26 | Mon 5/25/26 | Data Migration Team | 859 | 861 |  | NA | PTM_CM48_Equipment_Master_Serial Numbers | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.35.4 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.35.6 | NA | 1914 | 1913 | 1915 | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.35.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.35.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 5/25/26 | Tue 5/26/26 | Brad Meseck | 860 | 863 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Serial Numbers | Mon 5/25/26 | Tue 5/26/26 | 1.2.2.2.35.5 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.36.1 | NA | 1915 | 1914 | 1917 | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.35.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.36 | Auto Scheduled | 0% | PTM_CM48_Equipment_Master_Service | No | 6.78d | Mon 5/18/26 | Wed 5/27/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Wed 5/27/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 1916 |  |  | -6.72d | Yes | Yes | Yes | No | No | 1.2.2.2.36 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.36.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 5/26/26 | Tue 5/26/26 | Brad Meseck | 861 | 864 |  | NA | PTM_CM48_Equipment_Master_Service | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.35.6 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.36.2 | NA | 1917 | 1915 | 1918 | -3226m | No | Yes | Yes | No | No | 1.2.2.2.36.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.36.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 5/26/26 | Tue 5/26/26 | Brad Meseck | 863 | 865 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Service | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.36.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.36.3 | NA | 1918 | 1917 | 1919 | -3226m | No | Yes | Yes | No | No | 1.2.2.2.36.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.36.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 5/26/26 | Tue 5/26/26 | Data Migration Team | 864 | 866 |  | NA | PTM_CM48_Equipment_Master_Service | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.36.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.36.4 | NA | 1919 | 1918 | 1920 | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.36.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.36.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 5/26/26 | Tue 5/26/26 | Brad Meseck | 865 | 867 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Service | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.36.3 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible | 1.2.2.2.36.5 | NA | 1920 | 1919 | 1921 | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.36.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.36.5 | Auto Scheduled | 0% | Load | No | 2h | Tue 5/26/26 | Wed 5/27/26 | Data Migration Team | 866 |  |  | NA | PTM_CM48_Equipment_Master_Service | Tue 5/26/26 | Wed 5/27/26 | 1.2.2.2.36.4 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 1921 | 1920 |  | -53.77h | No | Yes | Yes | No | No | 1.2.2.2.36.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.36.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 5/18/26 | Mon 5/18/26 | Brad Meseck |  |  | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Service | Mon 5/18/26 | Mon 5/18/26 |  | Tue 4/21/26 | Tue 4/21/26 | Start No Earlier Than |  | Tue 4/21/26 | 1922 |  |  | -2.52h | No | Yes | Yes | No | No | 1.2.2.2.36.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.37 | Auto Scheduled | 0% | VC_Object Dependencies | No | 0.63d | Mon 5/18/26 | Mon 5/18/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Mon 5/18/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 1923 |  |  | -2.44d | Yes | Yes | Yes | No | No | 1.2.2.2.37 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.37.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Mon 5/18/26 | Mon 5/18/26 | Eric Heisler |  | 871 |  | NA | VC_Object Dependencies | Mon 5/18/26 | Mon 5/18/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.2.2.37.2 | NA | 1924 |  | 1925 | -19.52h | No | Yes | Yes | No | No | 1.2.2.2.37.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.37.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 5/18/26 | Mon 5/18/26 | Eric Heisler | 870 | 873 | Matt Palastro, Dave Duda | NA | VC_Object Dependencies | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.37.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.2.2.38.1 | NA | 1925 | 1924 | 1927 | -19.52h | No | Yes | Yes | No | No | 1.2.2.2.37.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.38 | Auto Scheduled | 0% | VC_Characteristics | No | 0.63d | Mon 5/18/26 | Tue 5/19/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Tue 5/19/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 1926 |  |  | -2.44d | Yes | Yes | Yes | No | No | 1.2.2.2.38 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.38.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Mon 5/18/26 | Tue 5/19/26 | Eric Heisler | 871 | 874 |  | NA | VC_Characteristics | Mon 5/18/26 | Tue 5/19/26 | 1.2.2.2.37.2 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.2.2.38.2 | NA | 1927 | 1925 | 1928 | -19.52h | No | Yes | Yes | No | No | 1.2.2.2.38.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.38.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 5/19/26 | Tue 5/19/26 | Eric Heisler | 873 | 876 | Matt Palastro, Dave Duda | NA | VC_Characteristics | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.38.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.39.1 | NA | 1928 | 1927 | 1930 | -19.52h | No | Yes | Yes | No | No | 1.2.2.2.38.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.39 | Auto Scheduled | 0% | VC_Classes | No | 0.63d | Tue 5/19/26 | Wed 5/20/26 |  |  |  |  | NA | Master Data Loads | Tue 5/19/26 | Wed 5/20/26 |  | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 1929 |  |  | -2.44d | Yes | Yes | Yes | No | No | 1.2.2.2.39 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.39.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Tue 5/19/26 | Tue 5/19/26 | Eric Heisler | 874 | 877 |  | NA | VC_Classes | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.38.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.39.2 | NA | 1930 | 1928 | 1931 | -19.52h | No | Yes | Yes | No | No | 1.2.2.2.39.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.39.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 5/19/26 | Wed 5/20/26 | Eric Heisler | 876 | 882 | Matt Palastro, Dave Duda | NA | VC_Classes | Tue 5/19/26 | Wed 5/20/26 | 1.2.2.2.39.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.2.2.41.1 | NA | 1931 | 1930 | 1936 | -19.52h | No | Yes | Yes | No | No | 1.2.2.2.39.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.40 | Auto Scheduled | 0% | VC_Classification (Class Type 200) | No | 0.63d | Thu 5/21/26 | Fri 5/22/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Fri 5/22/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1932 |  |  | -3.78d | Yes | Yes | Yes | No | No | 1.2.2.2.40 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.40.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Thu 5/21/26 | Thu 5/21/26 | Eric Heisler | 798 | 880 |  | NA | VC_Classification (Class Type 200) | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.26.6 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.40.2 | NA | 1933 | 1852 | 1934 | -30.27h | No | Yes | Yes | No | No | 1.2.2.2.40.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.40.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 5/21/26 | Fri 5/22/26 | Eric Heisler | 879 |  | Matt Palastro, Dave Duda | NA | VC_Classification (Class Type 200) | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.40.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1934 | 1933 |  | -30.27h | No | Yes | Yes | No | No | 1.2.2.2.40.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.41 | Auto Scheduled | 0% | VC_Dependency Nets | No | 0.63d | Thu 5/21/26 | Fri 5/22/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Fri 5/22/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1935 |  |  | -3.78d | Yes | Yes | Yes | No | No | 1.2.2.2.41 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.41.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Thu 5/21/26 | Thu 5/21/26 | Eric Heisler | 792877 | 883 |  | NA | VC_Dependency Nets | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.26,1.2.2.2.39.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.41.2 | NA | 1936 | 18461931 | 1937 | -30.27h | No | Yes | Yes | No | No | 1.2.2.2.41.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.41.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 5/21/26 | Fri 5/22/26 | Eric Heisler | 882 |  | Matt Palastro, Dave Duda | NA | VC_Dependency Nets | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.41.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1937 | 1936 |  | -30.27h | No | Yes | Yes | No | No | 1.2.2.2.41.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.42 | Auto Scheduled | 0% | VC_Configuration Profiles | No | 0.63d | Thu 5/21/26 | Fri 5/22/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Fri 5/22/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1938 |  |  | -5.75d | Yes | Yes | Yes | No | No | 1.2.2.2.42 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.42.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Thu 5/21/26 | Thu 5/21/26 | Eric Heisler | 792 | 886 |  | NA | VC_Configuration Profiles | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.26 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.42.2 | NA | 1939 | 1846 | 1940 | -46.02h | No | Yes | Yes | No | No | 1.2.2.2.42.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.42.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 5/21/26 | Fri 5/22/26 | Eric Heisler | 885 | 894888 | Matt Palastro, Dave Duda | NA | VC_Configuration Profiles | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.42.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.45.1,1.2.2.2.43.1 | NA | 1940 | 1939 | 19481942 | -46.02h | No | Yes | Yes | No | No | 1.2.2.2.42.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.43 | Auto Scheduled | 0% | VC_Variant Tables | No | 0.63d | Fri 5/22/26 | Fri 5/22/26 |  |  |  |  | NA | Master Data Loads | Fri 5/22/26 | Fri 5/22/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1941 |  |  | -5.03d | Yes | Yes | Yes | No | No | 1.2.2.2.43 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.43.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Fri 5/22/26 | Fri 5/22/26 | Eric Heisler | 886 | 889 |  | NA | VC_Variant Tables | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.42.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.43.2 | NA | 1942 | 1940 | 1943 | -40.27h | No | Yes | Yes | No | No | 1.2.2.2.43.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.43.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 5/22/26 | Fri 5/22/26 | Eric Heisler | 888 | 891 | Matt Palastro, Dave Duda | NA | VC_Variant Tables | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.43.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.44.1 | NA | 1943 | 1942 | 1945 | -40.27h | No | Yes | Yes | No | No | 1.2.2.2.43.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.44 | Auto Scheduled | 0% | VC_Variant Tables Content | No | 0.63d | Fri 5/22/26 | Mon 5/25/26 |  |  |  |  | NA | Master Data Loads | Fri 5/22/26 | Mon 5/25/26 |  | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1944 |  |  | -5.03d | Yes | Yes | Yes | No | No | 1.2.2.2.44 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.44.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Fri 5/22/26 | Fri 5/22/26 | Eric Heisler | 889 | 892 |  | NA | VC_Variant Tables Content | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.43.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.44.2 | NA | 1945 | 1943 | 1946 | -40.27h | No | Yes | Yes | No | No | 1.2.2.2.44.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.44.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 5/22/26 | Mon 5/25/26 | Eric Heisler | 891 |  | Matt Palastro, Dave Duda | NA | VC_Variant Tables Content | Fri 5/22/26 | Mon 5/25/26 | 1.2.2.2.44.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1946 | 1945 |  | -40.27h | No | Yes | Yes | No | No | 1.2.2.2.44.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.45 | Auto Scheduled | 0% | VC_Characteristic Groups | No | 1.97d | Fri 5/22/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Fri 5/22/26 | Tue 5/26/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1947 |  |  | -5.75d | Yes | Yes | Yes | No | No | 1.2.2.2.45 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.45.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 12.75h | Fri 5/22/26 | Mon 5/25/26 | Eric Heisler | 886 | 895 |  | NA | VC_Characteristic Groups | Fri 5/22/26 | Mon 5/25/26 | 1.2.2.2.42.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.45.2 | NA | 1948 | 1940 | 1949 | -46.02h | No | Yes | Yes | No | No | 1.2.2.2.45.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.45.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 5/25/26 | Tue 5/26/26 | Eric Heisler | 894 |  | Matt Palastro, Dave Duda | NA | VC_Characteristic Groups | Mon 5/25/26 | Tue 5/26/26 | 1.2.2.2.45.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1949 | 1948 |  | -46.02h | No | Yes | Yes | No | No | 1.2.2.2.45.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.46 | Auto Scheduled | 0% | PTM_CM52_Super_BOM | No | 2d | Thu 5/21/26 | Mon 5/25/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Mon 5/25/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1950 |  |  | -8.41d | Yes | Yes | Yes | No | No | 1.2.2.2.46 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.46.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Eric Heisler | 798 | 898 |  | NA | PTM_CM52_Super_BOM | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.46.2 | NA | 1951 | 1852 | 1952 | -4036m | No | Yes | Yes | No | No | 1.2.2.2.46.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.46.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 5/21/26 | Thu 5/21/26 | Eric Heisler | 897 | 899 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.46.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.46.3 | NA | 1952 | 1951 | 1953 | -4036m | No | Yes | Yes | No | No | 1.2.2.2.46.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.46.3 | Auto Scheduled | 0% | Simulate Load | No | 8h | Thu 5/21/26 | Fri 5/22/26 | Data Migration Team | 898 | 900 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Thu 5/21/26 | Fri 5/22/26 | 1.2.2.2.46.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.46.4 | NA | 1953 | 1952 | 1954 | -67.27h | No | Yes | Yes | No | No | 1.2.2.2.46.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.46.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 5/22/26 | Fri 5/22/26 | Eric Heisler | 899 | 901 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.46.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.46.5 | NA | 1954 | 1953 | 1955 | -67.27h | No | Yes | Yes | No | No | 1.2.2.2.46.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.46.5 | Auto Scheduled | 0% | Load | No | 2h | Fri 5/22/26 | Mon 5/25/26 | Data Migration Team | 900 | 902 |  | NA | PTM_CM52_Super_BOM | Fri 5/22/26 | Mon 5/25/26 | 1.2.2.2.46.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.46.6 | NA | 1955 | 1954 | 1956 | -67.27h | No | Yes | Yes | No | No | 1.2.2.2.46.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.46.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 5/25/26 | Mon 5/25/26 | Eric Heisler | 901 | 904 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.46.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.47.1 | NA | 1956 | 1955 | 1958 | -67.27h | No | Yes | Yes | No | No | 1.2.2.2.46.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.47 | Auto Scheduled | 0% | PTM_CM53_Super_Routing | No | 2.13d | Mon 5/25/26 | Wed 5/27/26 |  |  |  |  | NA | Master Data Loads | Mon 5/25/26 | Wed 5/27/26 |  | Thu 4/16/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 1957 |  |  | -8.41d | Yes | Yes | Yes | No | No | 1.2.2.2.47 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.47.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 5/25/26 | Mon 5/25/26 | Eric Heisler | 902 | 905 |  | NA | PTM_CM53_Super_Routing | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.46.6 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.47.2 | NA | 1958 | 1956 | 1959 | -4036m | No | Yes | Yes | No | No | 1.2.2.2.47.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.47.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 5/25/26 | Mon 5/25/26 | Eric Heisler | 904 | 906 | Matt Palastro, Dave Duda | NA | PTM_CM53_Super_Routing | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.47.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.47.3 | NA | 1959 | 1958 | 1960 | -4036m | No | Yes | Yes | No | No | 1.2.2.2.47.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.47.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 5/25/26 | Tue 5/26/26 | Data Migration Team | 905 | 907 |  | NA | PTM_CM53_Super_Routing | Mon 5/25/26 | Tue 5/26/26 | 1.2.2.2.47.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.47.4 | NA | 1960 | 1959 | 1961 | -67.27h | No | Yes | Yes | No | No | 1.2.2.2.47.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.47.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 5/26/26 | Tue 5/26/26 | Eric Heisler | 906 | 908 | Matt Palastro, Dave Duda | NA | PTM_CM53_Super_Routing | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.47.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.47.5 | NA | 1961 | 1960 | 1962 | -67.27h | No | Yes | Yes | No | No | 1.2.2.2.47.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.47.5 | Auto Scheduled | 0% | Load | No | 2h | Tue 5/26/26 | Wed 5/27/26 | Data Migration Team | 907 | 909911 |  | NA | PTM_CM53_Super_Routing | Tue 5/26/26 | Wed 5/27/26 | 1.2.2.2.47.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.47.6,1.2.2.2.48.1 | NA | 1962 | 1961 | 19631965 | -67.27h | No | Yes | Yes | No | No | 1.2.2.2.47.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.47.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 5/27/26 | Wed 5/27/26 | Eric Heisler | 908 |  | Matt Palastro, Dave Duda | NA | PTM_CM53_Super_Routing | Wed 5/27/26 | Wed 5/27/26 | 1.2.2.2.47.5 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 1963 | 1962 |  | -58.27h | No | Yes | Yes | No | No | 1.2.2.2.47.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.48 | Auto Scheduled | 0% | VC_VK30 Pricing Variant | No | 0.69d | Wed 5/27/26 | Wed 5/27/26 |  |  |  |  | NA | Master Data Loads | Wed 5/27/26 | Wed 5/27/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 1964 |  |  | -8.41d | Yes | Yes | Yes | No | No | 1.2.2.2.48 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.48.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Wed 5/27/26 | Wed 5/27/26 | Eric Heisler | 908 | 912 | Matt Palastro, Dave Duda | NA | VC_VK30 Pricing Variant | Wed 5/27/26 | Wed 5/27/26 | 1.2.2.2.47.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.48.2 | NA | 1965 | 1962 | 1966 | -4036m | No | Yes | Yes | No | No | 1.2.2.2.48.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.48.2 | Auto Scheduled | 0% | Load | No | 2h | Wed 5/27/26 | Wed 5/27/26 | Eric Heisler | 911 | 913 |  | NA | VC_VK30 Pricing Variant | Wed 5/27/26 | Wed 5/27/26 | 1.2.2.2.48.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.48.3 | NA | 1966 | 1965 | 1967 | -67.27h | No | Yes | Yes | No | No | 1.2.2.2.48.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.48.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 5/27/26 | Wed 5/27/26 | Eric Heisler | 912 | 915 | Matt Palastro, Dave Duda | NA | VC_VK30 Pricing Variant | Wed 5/27/26 | Wed 5/27/26 | 1.2.2.2.48.2 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.49.1 | NA | 1967 | 1966 | 1969 | -67.27h | No | Yes | Yes | No | No | 1.2.2.2.48.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.49 | Auto Scheduled | 0% | OTC_CM22_Pricing_Condition | No | 0.69d | Wed 5/27/26 | Thu 5/28/26 |  |  |  |  | NA | Master Data Loads | Wed 5/27/26 | Thu 5/28/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 1968 |  |  | -8.41d | Yes | Yes | Yes | No | No | 1.2.2.2.49 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.49.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Wed 5/27/26 | Wed 5/27/26 | Ric Haraida | 913 | 916 | Matt Palastro, Dave Duda | NA | OTC_CM22_Pricing_Condition | Wed 5/27/26 | Wed 5/27/26 | 1.2.2.2.48.3 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.49.2 | NA | 1969 | 1967 | 1970 | -4036m | No | Yes | Yes | No | No | 1.2.2.2.49.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.49.2 | Auto Scheduled | 0% | Load | No | 2h | Wed 5/27/26 | Thu 5/28/26 | Ric Haraida | 915 | 917919 |  | NA | OTC_CM22_Pricing_Condition | Wed 5/27/26 | Thu 5/28/26 | 1.2.2.2.49.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.49.3,1.2.2.2.50.1 | NA | 1970 | 1969 | 19711973 | -67.27h | No | Yes | Yes | No | No | 1.2.2.2.49.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.49.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 5/28/26 | Thu 5/28/26 | Ric Haraida,Kim Kolesar | 916 |  | Matt Palastro, Dave Duda,kim | NA | OTC_CM22_Pricing_Condition | Thu 5/28/26 | Thu 5/28/26 | 1.2.2.2.49.2 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 1971 | 1970 |  | -66.27h | No | Yes | Yes | No | No | 1.2.2.2.49.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.50 | Auto Scheduled | 0% | OTC_CM21_CMIR | No | 0.5d | Thu 5/28/26 | Thu 5/28/26 |  |  |  |  | NA | Master Data Loads | Thu 5/28/26 | Thu 5/28/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 1972 |  |  | -8.41d | Yes | Yes | Yes | No | No | 1.2.2.2.50 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.50.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 5/28/26 | Thu 5/28/26 | Ric Haraida | 916927 | 920 |  | NA | OTC_CM21_CMIR | Thu 5/28/26 | Thu 5/28/26 | 1.2.2.2.49.2,1.2.2.2.51.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.50.2 | NA | 1973 | 19701981 | 1974 | -4036m | No | Yes | Yes | No | No | 1.2.2.2.50.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.50.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 5/28/26 | Thu 5/28/26 | Ric Haraida | 919 | 921 | Kim | NA | OTC_CM21_CMIR | Thu 5/28/26 | Thu 5/28/26 | 1.2.2.2.50.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.50.3 | NA | 1974 | 1973 | 1975 | -4036m | No | Yes | Yes | No | No | 1.2.2.2.50.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.50.3 | Auto Scheduled | 0% | Simulate Load | No | 0h | Thu 5/28/26 | Thu 5/28/26 | Data Migration Team | 920 | 922 |  | NA | OTC_CM21_CMIR | Thu 5/28/26 | Thu 5/28/26 | 1.2.2.2.50.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.2.2.50.4 | NA | 1975 | 1974 | 1976 | -67.27h | No | Yes | Yes | Yes | No | 1.2.2.2.50.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.50.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 0h | Thu 5/28/26 | Thu 5/28/26 | Ric Haraida | 921 | 923 | Kim | NA | OTC_CM21_CMIR | Thu 5/28/26 | Thu 5/28/26 | 1.2.2.2.50.3 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible | 1.2.2.2.50.5 | NA | 1976 | 1975 | 1977 | -67.27h | No | Yes | Yes | Yes | No | 1.2.2.2.50.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.50.5 | Auto Scheduled | 0% | Load | No | 0h | Thu 5/28/26 | Thu 5/28/26 | Data Migration Team | 922 | 924 |  | NA | OTC_CM21_CMIR | Thu 5/28/26 | Thu 5/28/26 | 1.2.2.2.50.4 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible | 1.2.2.2.50.6 | NA | 1977 | 1976 | 1978 | -67.27h | No | Yes | Yes | Yes | No | 1.2.2.2.50.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.50.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 5/28/26 | Thu 5/28/26 | Ric Haraida | 923 |  | Kim | NA | OTC_CM21_CMIR | Thu 5/28/26 | Thu 5/28/26 | 1.2.2.2.50.5 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 1978 | 1977 |  | -67.27h | No | Yes | Yes | No | No | 1.2.2.2.50.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.51 | Auto Scheduled | 0% | PTP_CM29_Source_List | No | 6.16d | Tue 5/19/26 | Wed 5/27/26 |  |  |  |  | NA | Master Data Loads | Tue 5/19/26 | Wed 5/27/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1979 |  |  | -7.22d | Yes | Yes | Yes | No | No | 1.2.2.2.51 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.51.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Tue 5/19/26 | Tue 5/19/26 | Nevin Varkey | 769776 |  | Sam | NA | PTP_CM29_Source_List | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.22.5,1.2.2.2.23.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 1980 | 18231830 |  | -541m | No | Yes | Yes | No | No | 1.2.2.2.51.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.51.2 | Auto Scheduled | 0% | Load | No | 2h | Tue 5/26/26 | Wed 5/27/26 | Nevin Varkey | 745 | 919928 |  | NA | PTP_CM29_Source_List | Tue 5/26/26 | Wed 5/27/26 | 1.2.2.2.18.6 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.50.1,1.2.2.2.51.3 | NA | 1981 | 1799 | 19731982 | -58.77h | No | Yes | Yes | No | No | 1.2.2.2.51.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.51.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 5/27/26 | Wed 5/27/26 | Nevin Varkey | 927 |  | Sam | NA | PTP_CM29_Source_List | Wed 5/27/26 | Wed 5/27/26 | 1.2.2.2.51.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1982 | 1981 |  | -57.77h | No | Yes | Yes | No | No | 1.2.2.2.51.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.52 | Auto Scheduled | 0% | RTR_CM11_Asset_Master | No | 3.75d | Mon 5/18/26 | Thu 5/21/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Thu 5/21/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1983 |  |  | -3.69d | Yes | Yes | Yes | No | No | 1.2.2.2.52 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.52.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes |  | 931985 |  | NA | RTR_CM11_Asset_Master | Mon 5/18/26 | Mon 5/18/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.52.2,1.2.2.2.67.1 | NA | 1984 |  | 19852039 | -1771m | No | Yes | Yes | No | No | 1.2.2.2.52.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.52.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes,Femi Oguntala | 930 | 932 | Brian Wagner | NA | RTR_CM11_Asset_Master | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.52.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.52.3 | NA | 1985 | 1984 | 1986 | -1771m | No | Yes | Yes | No | No | 1.2.2.2.52.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.52.3 | Auto Scheduled | 0% | Simulate Load | No | 8h | Mon 5/18/26 | Tue 5/19/26 | Data Migration Team | 931 | 933 |  | NA | RTR_CM11_Asset_Master | Mon 5/18/26 | Tue 5/19/26 | 1.2.2.2.52.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.52.4 | NA | 1986 | 1985 | 1987 | -29.52h | No | Yes | Yes | No | No | 1.2.2.2.52.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.52.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 16h | Tue 5/19/26 | Thu 5/21/26 | Kasey Hughes | 932 | 934 | Brian Wagner | NA | RTR_CM11_Asset_Master | Tue 5/19/26 | Thu 5/21/26 | 1.2.2.2.52.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.52.5 | NA | 1987 | 1986 | 1988 | -29.52h | No | Yes | Yes | No | No | 1.2.2.2.52.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.52.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 933 | 935 |  | NA | RTR_CM11_Asset_Master | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.52.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.52.6 | NA | 1988 | 1987 | 1989 | -29.52h | No | Yes | Yes | No | No | 1.2.2.2.52.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.52.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 5/21/26 | Thu 5/21/26 | Kasey Hughes | 934 |  | Brian Wagner | NA | RTR_CM11_Asset_Master | Thu 5/21/26 | Thu 5/21/26 | 1.2.2.2.52.5 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 1989 | 1988 |  | -29.52h | No | Yes | Yes | No | No | 1.2.2.2.52.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.53 | Auto Scheduled | 0% | PTM_CM50_Material Class | No | 2.13d | Fri 5/22/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Fri 5/22/26 | Tue 5/26/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1990 |  |  | -5.85d | Yes | Yes | Yes | No | No | 1.2.2.2.53 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.53.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Fri 5/22/26 | Fri 5/22/26 | Sam | 842 | 938941 |  | NA | PTM_CM50_Material Class | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.33.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.53.2,1.2.2.2.54.1 | NA | 1991 | 1896 | 19921995 | -2806m | No | Yes | Yes | No | No | 1.2.2.2.53.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.53.2 | Auto Scheduled | 0% | Load | No | 30m | Fri 5/22/26 | Fri 5/22/26 | Brad Meseck | 937 | 939 | Matt Palastro, Dave Duda | NA | PTM_CM50_Material Class | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.53.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.53.3 | NA | 1992 | 1991 | 1993 | -2806m | No | Yes | Yes | No | No | 1.2.2.2.53.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.53.3 | Auto Scheduled | 0% | Post Load Validation | No | 16h | Fri 5/22/26 | Tue 5/26/26 | Brad | 938 |  | brad | NA | PTM_CM50_Material Class | Fri 5/22/26 | Tue 5/26/26 | 1.2.2.2.53.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 1993 | 1992 |  | -46.77h | No | Yes | Yes | No | No | 1.2.2.2.53.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.54 | Auto Scheduled | 0% | PTM_CM55_Class assignment to materials | No | 1.13d | Fri 5/22/26 | Mon 5/25/26 |  |  |  |  | NA | Master Data Loads | Fri 5/22/26 | Mon 5/25/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 1994 |  |  | -4.91d | Yes | Yes | Yes | No | No | 1.2.2.2.54 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.54.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Fri 5/22/26 | Fri 5/22/26 | Sam | 937 | 942 |  | NA | PTM_CM55_Class assignment to materials | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.53.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.54.2 | NA | 1995 | 1991 | 1996 | -2356m | No | Yes | Yes | No | No | 1.2.2.2.54.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.54.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Fri 5/22/26 | Fri 5/22/26 | Brad Meseck | 941 | 943 | Matt Palastro, Dave Duda | NA | PTM_CM55_Class assignment to materials | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.54.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.54.3 | NA | 1996 | 1995 | 1997 | -2356m | No | Yes | Yes | No | No | 1.2.2.2.54.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.54.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 942 | 944 |  | NA | PTM_CM55_Class assignment to materials | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.54.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.54.4 | NA | 1997 | 1996 | 1998 | -39.27h | No | Yes | Yes | No | No | 1.2.2.2.54.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.54.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 5/22/26 | Fri 5/22/26 | Brad Meseck | 943 | 945 | Matt Palastro, Dave Duda | NA | PTM_CM55_Class assignment to materials | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.54.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.54.5 | NA | 1998 | 1997 | 1999 | -39.27h | No | Yes | Yes | No | No | 1.2.2.2.54.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.54.5 | Auto Scheduled | 0% | Load | No | 2h | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 944 | 946 |  | NA | PTM_CM55_Class assignment to materials | Fri 5/22/26 | Fri 5/22/26 | 1.2.2.2.54.4 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.54.6 | NA | 1999 | 1998 | 2000 | -39.27h | No | Yes | Yes | No | No | 1.2.2.2.54.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.54.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 5/22/26 | Mon 5/25/26 | Brad Meseck | 945 |  | Matt Palastro, Dave Duda | NA | PTM_CM55_Class assignment to materials | Fri 5/22/26 | Mon 5/25/26 | 1.2.2.2.54.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2000 | 1999 |  | -39.27h | No | Yes | Yes | No | No | 1.2.2.2.54.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.55 | Auto Scheduled | 0% | GTS - Material initial load from S4 (Run Interface) | No | 2.09d | Thu 5/21/26 | Mon 5/25/26 |  |  |  |  | NA | Master Data Loads | Thu 5/21/26 | Mon 5/25/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2001 |  |  | -8.78d | Yes | Yes | Yes | No | No | 1.2.2.2.55 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.55.1 | Auto Scheduled | 0% | Run material interface to GTS | No | 15.75h | Thu 5/21/26 | Mon 5/25/26 | James Van Riper | 816 | 949 |  | NA | GTS - Material initial load from S4 (Run Interface) | Thu 5/21/26 | Mon 5/25/26 | 1.2.2.2.29.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.55.2 | NA | 2002 | 1870 | 2003 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.55.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.55.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Mon 5/25/26 | Mon 5/25/26 | James Van Riper | 948 | 960 | Kim Kolesar | NA | GTS - Material initial load from S4 (Run Interface) | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.55.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.59.1 | NA | 2003 | 2002 | 2014 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.55.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.56 | Auto Scheduled | 0% | GTS - Customers initial load from S4 (Run Interface) | No | 0.25d | Mon 5/18/26 | Mon 5/18/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Mon 5/18/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 2004 |  |  | -0.19d | Yes | Yes | Yes | No | No | 1.2.2.2.56 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.56.1 | Auto Scheduled | 0% | Run material interface to GTS | No | 1h | Mon 5/18/26 | Mon 5/18/26 | James Van Riper |  | 952 |  | NA | GTS - Customers initial load from S4 (Run Interface) | Mon 5/18/26 | Mon 5/18/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.56.2 | NA | 2005 |  | 2006 | -1.52h | No | Yes | Yes | No | No | 1.2.2.2.56.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.56.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Mon 5/18/26 | Mon 5/18/26 | James Van Riper | 951 |  | Kim Kolesar | NA | GTS - Customers initial load from S4 (Run Interface) | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.56.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 2006 | 2005 |  | -1.52h | No | Yes | Yes | No | No | 1.2.2.2.56.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.57 | Auto Scheduled | 0% | GTS - Vendors initial load from S4 (Run Interface) | No | 0.25d | Tue 5/19/26 | Tue 5/19/26 |  |  |  |  | NA | Master Data Loads | Tue 5/19/26 | Tue 5/19/26 |  | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2007 |  |  | -1.44d | Yes | Yes | Yes | No | No | 1.2.2.2.57 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.57.1 | Auto Scheduled | 0% | Run material interface to GTS | No | 1h | Tue 5/19/26 | Tue 5/19/26 | James Van Riper | 759 | 955958 |  | NA | GTS - Vendors initial load from S4 (Run Interface) | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.20.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.2.2.57.2,1.2.2.2.58.2 | NA | 2008 | 1813 | 20092012 | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.57.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.57.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 5/19/26 | Tue 5/19/26 | James Van Riper | 954 |  | Kim Kolesar | NA | GTS - Vendors initial load from S4 (Run Interface) | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.57.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2009 | 2008 |  | -8.52h | No | Yes | Yes | No | No | 1.2.2.2.57.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.58 | Auto Scheduled | 0% | GTS - ECCN - Create | No | 1.13d | Mon 5/18/26 | Tue 5/19/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Tue 5/19/26 |  | Mon 4/6/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2010 |  |  | -1.06d | Yes | Yes | Yes | No | No | 1.2.2.2.58 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.58.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Mon 5/18/26 | Mon 5/18/26 | James Van Riper |  |  |  | NA | GTS - ECCN - Create | Mon 5/18/26 | Mon 5/18/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 2011 |  |  | -0.52h | No | Yes | Yes | No | No | 1.2.2.2.58.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.58.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 5/19/26 | Tue 5/19/26 | James Van Riper | 954 | 978 | Kim Kolesar | NA | GTS - ECCN - Create | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.57.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.65.1 | NA | 2012 | 2008 | 2032 | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.58.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.59 | Auto Scheduled | 0% | GTS - ECCN - Assign | No | 0.25d | Mon 5/25/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Mon 5/25/26 | Tue 5/26/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2013 |  |  | -8.78d | Yes | Yes | Yes | No | No | 1.2.2.2.59 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.59.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Mon 5/25/26 | Mon 5/25/26 | James Van Riper | 949 | 961 |  | NA | GTS - ECCN - Assign | Mon 5/25/26 | Mon 5/25/26 | 1.2.2.2.55.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.59.2 | NA | 2014 | 2003 | 2015 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.59.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.59.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Mon 5/25/26 | Tue 5/26/26 | James Van Riper | 960 | 966 | Kim Kolesar | NA | GTS - ECCN - Assign | Mon 5/25/26 | Tue 5/26/26 | 1.2.2.2.59.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.61.1 | NA | 2015 | 2014 | 2020 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.59.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.60 | Auto Scheduled | 0% | GTS - HTS - Create | No | 0.25d | Mon 5/18/26 | Mon 5/18/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Mon 5/18/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 2016 |  |  | -0.19d | Yes | Yes | Yes | No | No | 1.2.2.2.60 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.60.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Mon 5/18/26 | Mon 5/18/26 | James Van Riper |  | 964 |  | NA | GTS - HTS - Create | Mon 5/18/26 | Mon 5/18/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.2.2.60.2 | NA | 2017 |  | 2018 | -1.52h | No | Yes | Yes | No | No | 1.2.2.2.60.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.60.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Mon 5/18/26 | Mon 5/18/26 | James Van Riper | 963 |  | Kim Kolesar | NA | GTS - HTS - Create | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.60.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 2018 | 2017 |  | -1.52h | No | Yes | Yes | No | No | 1.2.2.2.60.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.61 | Auto Scheduled | 0% | GTS - HTS - Assign | No | 0.25d | Tue 5/26/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Tue 5/26/26 | Tue 5/26/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2019 |  |  | -8.78d | Yes | Yes | Yes | No | No | 1.2.2.2.61 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.61.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Tue 5/26/26 | Tue 5/26/26 | James Van Riper | 961 | 967969975 |  | NA | GTS - HTS - Assign | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.59.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.61.2,1.2.2.2.62.1,1.2.2.2.64.1 | NA | 2020 | 2015 | 202120232029 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.61.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.61.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 5/26/26 | Tue 5/26/26 | James Van Riper | 966 | 982972 | Kim Kolesar | NA | GTS - HTS - Assign | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.61.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.66.1,1.2.2.2.63.1 | NA | 2021 | 2020 | 20362026 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.61.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.62 | Auto Scheduled | 0% | GTS - License - Create | No | 0.25d | Tue 5/26/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Tue 5/26/26 | Tue 5/26/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2022 |  |  | -6.38d | Yes | Yes | Yes | No | No | 1.2.2.2.62 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.62.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Tue 5/26/26 | Tue 5/26/26 | James Van Riper | 966982 | 970 |  | NA | GTS - License - Create | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.61.1,1.2.2.2.66.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.62.2 | NA | 2023 | 20202036 | 2024 | -51.02h | No | Yes | Yes | No | No | 1.2.2.2.62.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.62.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 5/26/26 | Tue 5/26/26 | James Van Riper | 969 |  | Kim Kolesar | NA | GTS - License - Create | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.62.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2024 | 2023 |  | -51.02h | No | Yes | Yes | No | No | 1.2.2.2.62.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.63 | Auto Scheduled | 0% | Commodity Code/Tarif | No | 2.78d | Tue 5/26/26 | Fri 5/29/26 |  |  |  |  | NA | Master Data Loads | Tue 5/26/26 | Fri 5/29/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2025 |  |  | -8.78d | Yes | Yes | Yes | No | No | 1.2.2.2.63 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.63.1 | Auto Scheduled | 0% | Load | No | 21.25h | Tue 5/26/26 | Thu 5/28/26 | James Van Riper | 967 | 973 |  | NA | Commodity Code/Tarif | Tue 5/26/26 | Thu 5/28/26 | 1.2.2.2.61.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.63.2 | NA | 2026 | 2021 | 2027 | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.63.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.63.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Thu 5/28/26 | Fri 5/29/26 | James Van Riper | 972 |  | Kim Kolesar | NA | Commodity Code/Tarif | Thu 5/28/26 | Fri 5/29/26 | 1.2.2.2.63.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2027 | 2026 |  | -70.27h | No | Yes | Yes | No | No | 1.2.2.2.63.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.64 | Auto Scheduled | 0% | SPL Master File | No | 0.25d | Tue 5/26/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Tue 5/26/26 | Tue 5/26/26 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 2028 |  |  | -6.13d | Yes | Yes | Yes | No | No | 1.2.2.2.64 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.64.1 | Auto Scheduled | 0% | Load | No | 1h | Tue 5/26/26 | Tue 5/26/26 | James Van Riper | 966 | 976 |  | NA | SPL Master File | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.61.1 | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible | 1.2.2.2.64.2 | NA | 2029 | 2020 | 2030 | -49.02h | No | Yes | Yes | No | No | 1.2.2.2.64.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.64.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 5/26/26 | Tue 5/26/26 | James Van Riper | 975 |  | Kim Kolesar | NA | SPL Master File | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.64.1 | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 2030 | 2029 |  | -49.02h | No | Yes | Yes | No | No | 1.2.2.2.64.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.65 | Auto Scheduled | 0% | Initialize Embargo situation | No | 0.38d | Tue 5/19/26 | Tue 5/19/26 |  |  |  |  | NA | Master Data Loads | Tue 5/19/26 | Tue 5/19/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 2031 |  |  | -1.44d | Yes | Yes | Yes | No | No | 1.2.2.2.65 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.65.1 | Auto Scheduled | 0% | Run report /SAPSLL/EMB_CNTRY_INIT | No | 1h | Tue 5/19/26 | Tue 5/19/26 | James Van Riper | 958 | 979 |  | NA | Initialize Embargo situation | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.58.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.65.2 | NA | 2032 | 2012 | 2033 | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.65.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.65.2 | Auto Scheduled | 0% | Set Embargo situations | No | 1h | Tue 5/19/26 | Tue 5/19/26 | James Van Riper | 978 | 980 |  | NA | Initialize Embargo situation | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.65.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.2.2.65.3 | NA | 2033 | 2032 | 2034 | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.65.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.65.3 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 5/19/26 | Tue 5/19/26 | James Van Riper | 979 |  | Kim Kolesar | NA | Initialize Embargo situation | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.65.2 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 2034 | 2033 |  | -11.52h | No | Yes | Yes | No | No | 1.2.2.2.65.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.66 | Auto Scheduled | 0% | GTS - SPL (Sanctioned party list) | No | 0.25d | Tue 5/26/26 | Tue 5/26/26 |  |  |  |  | NA | Master Data Loads | Tue 5/26/26 | Tue 5/26/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2035 |  |  | -6.38d | Yes | Yes | Yes | No | No | 1.2.2.2.66 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.66.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Tue 5/26/26 | Tue 5/26/26 | James Van Riper | 967 | 969983 |  | NA | GTS - SPL (Sanctioned party list) | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.61.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.62.1,1.2.2.2.66.2 | NA | 2036 | 2021 | 20232037 | -51.02h | No | Yes | Yes | No | No | 1.2.2.2.66.1 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.66.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 5/26/26 | Tue 5/26/26 | James Van Riper | 982 |  | Kim Kolesar | NA | GTS - SPL (Sanctioned party list) | Tue 5/26/26 | Tue 5/26/26 | 1.2.2.2.66.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2037 | 2036 |  | -50.02h | No | Yes | Yes | No | No | 1.2.2.2.66.2 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.67 | Auto Scheduled | 0% | RTR_CM17_Project Definition / Builder | No | 1.13d | Mon 5/18/26 | Tue 5/19/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Tue 5/19/26 |  | Fri 4/10/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2038 |  |  | -1.19d | Yes | Yes | Yes | No | No | 1.2.2.2.67 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.67.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 930 | 986992 |  | NA | RTR_CM17_Project Definition / Builder | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.52.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.67.2,1.2.2.2.68.1 | NA | 2039 | 1984 | 20402046 | -571m | No | Yes | Yes | No | No | 1.2.2.2.67.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.67.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 985 | 987 | Brian Wagner | NA | RTR_CM17_Project Definition / Builder | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.67.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.67.3 | NA | 2040 | 2039 | 2041 | -541m | No | Yes | Yes | No | No | 1.2.2.2.67.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.67.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 986 | 988 |  | NA | RTR_CM17_Project Definition / Builder | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.67.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.67.4 | NA | 2041 | 2040 | 2042 | -9.02h | No | Yes | Yes | No | No | 1.2.2.2.67.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.67.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 987 | 989 | Brian Wagner | NA | RTR_CM17_Project Definition / Builder | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.67.3 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.67.5 | NA | 2042 | 2041 | 2043 | -9.02h | No | Yes | Yes | No | No | 1.2.2.2.67.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.67.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 5/18/26 | Tue 5/19/26 | Data Migration Team | 988 | 990 |  | NA | RTR_CM17_Project Definition / Builder | Mon 5/18/26 | Tue 5/19/26 | 1.2.2.2.67.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.67.6 | NA | 2043 | 2042 | 2044 | -9.02h | No | Yes | Yes | No | No | 1.2.2.2.67.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.67.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 989 |  | Brian Wagner | NA | RTR_CM17_Project Definition / Builder | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.67.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2044 | 2043 |  | -9.02h | No | Yes | Yes | No | No | 1.2.2.2.67.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.68 | Auto Scheduled | 0% | RTR_CM18_WBS Element | No | 1.13d | Mon 5/18/26 | Tue 5/19/26 |  |  |  |  | NA | Master Data Loads | Mon 5/18/26 | Tue 5/19/26 |  | Fri 4/10/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2045 |  |  | -1.19d | Yes | Yes | Yes | No | No | 1.2.2.2.68 | 5 | No | 500 | Future Task | No | 0d
1.2.2.2.68.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 985 | 993 |  | NA | RTR_CM18_WBS Element | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.67.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.68.2 | NA | 2046 | 2039 | 2047 | -571m | No | Yes | Yes | No | No | 1.2.2.2.68.1 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.68.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 992 | 994 | Brian Wagner | NA | RTR_CM18_WBS Element | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.68.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.2.2.68.3 | NA | 2047 | 2046 | 2048 | -571m | No | Yes | Yes | No | No | 1.2.2.2.68.2 | 6 | No | 500 | Future Task | No | 0m
1.2.2.2.68.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 993 | 995 |  | NA | RTR_CM18_WBS Element | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.68.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.2.2.68.4 | NA | 2048 | 2047 | 2049 | -9.52h | No | Yes | Yes | No | No | 1.2.2.2.68.3 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.68.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 994 | 996 | Brian Wagner | NA | RTR_CM18_WBS Element | Mon 5/18/26 | Mon 5/18/26 | 1.2.2.2.68.3 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.68.5 | NA | 2049 | 2048 | 2050 | -9.52h | No | Yes | Yes | No | No | 1.2.2.2.68.4 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.68.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 5/18/26 | Tue 5/19/26 | Data Migration Team | 995 | 997 |  | NA | RTR_CM18_WBS Element | Mon 5/18/26 | Tue 5/19/26 | 1.2.2.2.68.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.2.2.68.6 | NA | 2050 | 2049 | 2051 | -9.52h | No | Yes | Yes | No | No | 1.2.2.2.68.5 | 6 | No | 500 | Future Task | No | 0h
1.2.2.2.68.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 996 |  | Brian Wagner | NA | RTR_CM18_WBS Element | Tue 5/19/26 | Tue 5/19/26 | 1.2.2.2.68.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2051 | 2050 |  | -9.52h | No | Yes | Yes | No | No | 1.2.2.2.68.6 | 6 | No | 500 | Future Task | No | 0h
1.2.2.3 | Auto Scheduled | 0% | ITC2 Master Data Loads Complete | No | 0m | Fri 5/29/26 | Fri 5/29/26 |  | 631 | 1000SS,2176,1380SS,999,1761SS,2142SS |  | NA | ITC2 Data Load Tasks QS4 | Fri 5/29/26 | Fri 5/29/26 | 1.2.2.2 | NA | NA | As Soon As Possible | 1.2.2.4.1[SS],1.3.3.6.1,1.2.3.4.1[SS],1.2.2.4,1.2.4.4.1[SS],1.2.5.4.1[SS] | NA | 2947 | 2800 | 2945SS,2792,3330SS,2801,3351SS,4532SS | -4591m | No | Yes | Yes | Yes | No | 1.2.2.3 | 4 | No | 500 | Future Task | No | 0m
1.2.2.4 | Auto Scheduled | 0% | Mock Transactional Data | No | 2d | Thu 10/8/26 | Mon 10/12/26 |  | 99817592140 | 1008 |  | NA | ITC2 Data Load Tasks QS4 | Thu 10/8/26 | Mon 10/12/26 | 1.2.2.3,1.2.4.3,1.2.5.3 | NA | NA | As Soon As Possible | 1.2.2.5 | NA | 2801 | 294733604530 | 2052 | -90.75d | Yes | Yes | Yes | No | No | 1.2.2.4 | 4 | No | 500 | Future Task | No | 0d
1.2.2.4.1 | Auto Scheduled | 0% | Inventory | No | 4h | Thu 10/8/26 | Fri 10/9/26 |  | 998SS,1759SS,2140SS | 1.0011e+19 |  | NA | Mock Transactional Data | Thu 10/8/26 | Fri 10/9/26 | 1.2.2.3[SS],1.2.4.3[SS],1.2.5.3[SS] | NA | NA | As Soon As Possible | 1.2.2.4.2,1.2.2.4.5,1.2.2.4.6,1.2.2.4.7,1.2.2.4.8 | NA | 2945 | 2947SS,3360SS,4530SS | 2.8293e+19 | -726h | No | Yes | Yes | No | No | 1.2.2.4.1 | 5 | No | 500 | Future Task | No | 0h
1.2.2.4.2 | Auto Scheduled | 0% | Open AR | No | 4h | Fri 10/9/26 | Fri 10/9/26 |  | 1000 | 1002 |  | NA | Mock Transactional Data | Fri 10/9/26 | Fri 10/9/26 | 1.2.2.4.1 | NA | NA | As Soon As Possible | 1.2.2.4.3 | NA | 2829 | 2945 | 2824 | -726h | No | Yes | Yes | No | No | 1.2.2.4.2 | 5 | No | 500 | Future Task | No | 0h
1.2.2.4.3 | Auto Scheduled | 0% | Open AP | No | 4h | Fri 10/9/26 | Mon 10/12/26 |  | 1001 | 1003 |  | NA | Mock Transactional Data | Fri 10/9/26 | Mon 10/12/26 | 1.2.2.4.2 | NA | NA | As Soon As Possible | 1.2.2.4.4 | NA | 2824 | 2829 | 2821 | -726h | No | Yes | Yes | No | No | 1.2.2.4.3 | 5 | No | 500 | Future Task | No | 0h
1.2.2.4.4 | Auto Scheduled | 0% | Bank and Cash | No | 4h | Mon 10/12/26 | Mon 10/12/26 |  | 1002 |  |  | NA | Mock Transactional Data | Mon 10/12/26 | Mon 10/12/26 | 1.2.2.4.3 | NA | NA | As Soon As Possible |  | NA | 2821 | 2824 |  | -726h | No | Yes | Yes | No | No | 1.2.2.4.4 | 5 | No | 500 | Future Task | No | 0h
1.2.2.4.5 | Auto Scheduled | 0% | Open Purchase Orders(Manual) | No | 1d | Fri 10/9/26 | Mon 10/12/26 |  | 1000 |  |  | NA | Mock Transactional Data | Fri 10/9/26 | Mon 10/12/26 | 1.2.2.4.1 | NA | NA | As Soon As Possible |  | NA | 2944 | 2945 |  | -90.25d | No | Yes | Yes | No | No | 1.2.2.4.5 | 5 | No | 500 | Future Task | No | 0d
1.2.2.4.6 | Auto Scheduled | 0% | Open Sales Orders(Manual) | No | 1d | Fri 10/9/26 | Mon 10/12/26 |  | 1000 |  |  | NA | Mock Transactional Data | Fri 10/9/26 | Mon 10/12/26 | 1.2.2.4.1 | NA | NA | As Soon As Possible |  | NA | 2838 | 2945 |  | -90.25d | No | Yes | Yes | No | No | 1.2.2.4.6 | 5 | No | 500 | Future Task | No | 0d
1.2.2.4.7 | Auto Scheduled | 0% | Service Orders(Manual) | No | 0.5d | Fri 10/9/26 | Fri 10/9/26 |  | 1000 |  |  | NA | Mock Transactional Data | Fri 10/9/26 | Fri 10/9/26 | 1.2.2.4.1 | NA | NA | As Soon As Possible |  | NA | 2860 | 2945 |  | -89.75d | No | Yes | Yes | No | No | 1.2.2.4.7 | 5 | No | 500 | Future Task | No | 0d
1.2.2.4.8 | Auto Scheduled | 0% | Open Production Orders(Manual) | No | 1d | Fri 10/9/26 | Mon 10/12/26 |  | 1000 |  |  | NA | Mock Transactional Data | Fri 10/9/26 | Mon 10/12/26 | 1.2.2.4.1 | NA | NA | As Soon As Possible |  | NA | 2858 | 2945 |  | -90.25d | No | Yes | Yes | No | No | 1.2.2.4.8 | 5 | No | 500 | Future Task | No | 0d
1.2.2.5 | Auto Scheduled | 0% | ITC2 Mock Data Loads Complete | No | 0m | Mon 10/12/26 | Mon 10/12/26 | Mark George | 999 | 2165 |  | NA | ITC2 Data Load Tasks QS4 | Mon 10/12/26 | Mon 10/12/26 | 1.2.2.4 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible | 1.3.3.2 | NA | 2052 | 2801 | 2799 | -43560m | No | Yes | Yes | Yes | No | 1.2.2.5 | 4 | No | 500 | Future Task | No | 0m
1.2.3 | Auto Scheduled | 0% | ITC3 Data Load Tasks QS5 | No | 11.88d | Mon 6/8/26 | Tue 6/23/26 |  |  | 1389 |  | NA | Data Readiness | Mon 6/8/26 | Tue 6/23/26 |  | Thu 3/13/25 | Tue 4/21/26 | As Soon As Possible | 1.2.4 | NA | 2053 |  | 2422 | -24.31d | Yes | Yes | Yes | No | No | 1.2.3 | 3 | No | 500 | Future Task | No | 0d
1.2.3.1 | Auto Scheduled | 0% | PMO Authorization to Start Data Loads | No | 2h | Mon 6/8/26 | Mon 6/8/26 | Mark George | 72 | 1011 |  | NA | ITC3 Data Load Tasks QS5 | Mon 6/8/26 | Mon 6/8/26 | 1.1.1.6 | Mon 4/6/26 | Mon 4/6/26 | Must Start On | 1.2.3.2 | Mon 6/8/26 | 2054 | 1284 | 2959 | 0h | No | Yes | Yes | No | No | 1.2.3.1 | 4 | No | 500 | Future Task | No | 0h
1.2.3.2 | Auto Scheduled | 0% | Master Data Loads | No | 9.63d | Mon 6/8/26 | Fri 6/19/26 |  | 1010 | 1378 |  | NA | ITC3 Data Load Tasks QS5 | Mon 6/8/26 | Fri 6/19/26 | 1.2.3.1 | NA | NA | As Soon As Possible | 1.2.3.3 | NA | 2959 | 2054 | 2958 | -24.56d | Yes | Yes | Yes | No | No | 1.2.3.2 | 4 | No | 500 | Future Task | No | 0d
1.2.3.2.1 | Auto Scheduled | 0% | RTR_CM02_Profit Center Hierarchy | No | 0.75d | Mon 6/8/26 | Mon 6/8/26 |  |  | 10451047 |  | NA | Master Data Loads | Mon 6/8/26 | Mon 6/8/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.3.2.6.2,1.2.3.2.6.4 | NA | 2960 |  | 29932995 | -24.56d | Yes | Yes | Yes | No | No | 1.2.3.2.1 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.1.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 1h | Mon 6/8/26 | Mon 6/8/26 | Kasey Hughes |  | 1014 |  | NA | RTR_CM02_Profit Center Hierarchy | Mon 6/8/26 | Mon 6/8/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.3.2.1.2 | NA | 2961 |  | 2962 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.1.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.1.2 | Auto Scheduled | 0% | Load | No | 2h | Mon 6/8/26 | Mon 6/8/26 | Kasey Hughes | 1013 | 1015 |  | NA | RTR_CM02_Profit Center Hierarchy | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.1.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.3.2.1.3 | NA | 2962 | 2961 | 2963 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.1.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.1.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 6/8/26 | Mon 6/8/26 | Kasey Hughes | 1014 | 10171030 | Brian Wagner | NA | RTR_CM02_Profit Center Hierarchy | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.1.2 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.3.2.2.1,1.2.3.2.4.1 | NA | 2963 | 2962 | 29652978 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.1.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.2 | Auto Scheduled | 0% | RTR_CM03_Cost Center Hierarchy | No | 0.75d | Tue 6/9/26 | Tue 6/9/26 |  |  | 10451047 |  | NA | Master Data Loads | Tue 6/9/26 | Tue 6/9/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.6.2,1.2.3.2.6.4 | NA | 2964 |  | 29932995 | -24.56d | Yes | Yes | Yes | No | No | 1.2.3.2.2 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.2.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 1h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1015 | 1018 |  | NA | RTR_CM03_Cost Center Hierarchy | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.1.3 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.3.2.2.2 | NA | 2965 | 2963 | 2966 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.2.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.2.2 | Auto Scheduled | 0% | Load | No | 2h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1017 | 1019 |  | NA | RTR_CM03_Cost Center Hierarchy | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.2.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.2.3 | NA | 2966 | 2965 | 2967 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.2.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.2.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1018 | 10211056 | Brian Wagner | NA | RTR_CM03_Cost Center Hierarchy | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.2.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.3.1,1.2.3.2.8.1 | NA | 2967 | 2966 | 29693004 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.2.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.3 | Auto Scheduled | 0% | RTR_CM01_GL_Account_Master to CC 1000 | No | 2.44d | Tue 6/9/26 | Fri 6/12/26 |  |  | 1045 |  | NA | Master Data Loads | Tue 6/9/26 | Fri 6/12/26 |  | Tue 4/7/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.6.2 | NA | 2968 |  | 2993 | -24.56d | Yes | Yes | Yes | No | No | 1.2.3.2.3 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.3.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1019 | 1022 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.2.3 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.3.2 | NA | 2969 | 2967 | 2970 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.3.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.3.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 6/9/26 | Wed 6/10/26 | Kasey Hughes | 1021 | 1023 | Brian Wagner | NA | RTR_CM01_GL_Account_Master to CC 1000 | Tue 6/9/26 | Wed 6/10/26 | 1.2.3.2.3.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.3.3 | NA | 2970 | 2969 | 2971 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.3.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.3.3 | Auto Scheduled | 0% | Simulate Load | No | 6h | Wed 6/10/26 | Wed 6/10/26 | Data Migration Team | 1022 | 1024 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.3.2 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.3.4 | NA | 2971 | 2970 | 2972 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.3.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.3.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 6/10/26 | Thu 6/11/26 | Kasey Hughes | 1023 | 1025 | Brian Wagner | NA | RTR_CM01_GL_Account_Master to CC 1000 | Wed 6/10/26 | Thu 6/11/26 | 1.2.3.2.3.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.3.5 | NA | 2972 | 2971 | 2973 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.3.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.3.5 | Auto Scheduled | 0% | Load | No | 1h | Thu 6/11/26 | Thu 6/11/26 | Data Migration Team | 1024 | 1026 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.3.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.3.6 | NA | 2973 | 2972 | 2974 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.3.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.3.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Thu 6/11/26 | Thu 6/11/26 | Kasey Hughes | 1025 | 1.0491e+19 | Brian Wagner | NA | RTR_CM01_GL_Account_Master to CC 1000 | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.3.5 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.7.1,1.2.3.2.9.1,1.2.3.2.11.1,1.2.3.2.13.1,1.2.3.2.3.7 | NA | 2974 | 2973 | 2.9973e+19 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.3.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.3.7 | Auto Scheduled | 0% | Extend GL to all Company Codes | No | 2h | Thu 6/11/26 | Thu 6/11/26 | Kasey Hughes | 1026 | 1028 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.3.6 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.3.8 | NA | 2975 | 2974 | 2976 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.3.7 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.3.8 | Auto Scheduled | 0% | Post GL Extention Validation | No | 2h | Thu 6/11/26 | Fri 6/12/26 |  | 1027 | 10941047 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.3.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.14.3,1.2.3.2.6.4 | NA | 2976 | 2975 | 30422995 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.3.8 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.4 | Auto Scheduled | 0% | RTR_CM05_Profit_Center | No | 1.13d | Tue 6/9/26 | Wed 6/10/26 |  |  |  |  | NA | Master Data Loads | Tue 6/9/26 | Wed 6/10/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 2977 |  |  | -22.94d | Yes | Yes | Yes | No | No | 1.2.3.2.4 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.4.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1015 | 1031 |  | NA | RTR_CM05_Profit_Center | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.1.3 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.3.2.4.2 | NA | 2978 | 2963 | 2979 | -183.52h | No | Yes | Yes | No | No | 1.2.3.2.4.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.4.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1030 | 1032 | Brian Wagner | NA | RTR_CM05_Profit_Center | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.4.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.4.3 | NA | 2979 | 2978 | 2980 | -183.52h | No | Yes | Yes | No | No | 1.2.3.2.4.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.4.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 6/9/26 | Tue 6/9/26 | Data Migration Team | 1031 | 1033 |  | NA | RTR_CM05_Profit_Center | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.4.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.4.4 | NA | 2980 | 2979 | 2981 | -183.52h | No | Yes | Yes | No | No | 1.2.3.2.4.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.4.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1032 | 1034 | Brian Wagner | NA | RTR_CM05_Profit_Center | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.4.3 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.4.5 | NA | 2981 | 2980 | 2982 | -183.52h | No | Yes | Yes | No | No | 1.2.3.2.4.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.4.5 | Auto Scheduled | 0% | Load | No | 1h | Tue 6/9/26 | Tue 6/9/26 | Data Migration Team | 1033 | 1035 |  | NA | RTR_CM05_Profit_Center | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.4.4 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.4.6 | NA | 2982 | 2981 | 2983 | -183.52h | No | Yes | Yes | No | No | 1.2.3.2.4.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.4.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Tue 6/9/26 | Wed 6/10/26 | Kasey Hughes | 1034 | 103711661173 | Brian Wagner | NA | RTR_CM05_Profit_Center | Tue 6/9/26 | Wed 6/10/26 | 1.2.3.2.4.5 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.5.1,1.2.3.2.25.1,1.2.3.2.26.1 | NA | 2983 | 2982 | 298531143121 | -183.52h | No | Yes | Yes | No | No | 1.2.3.2.4.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.5 | Auto Scheduled | 0% | RTR_CM04_Cost_Center | No | 1.13d | Wed 6/10/26 | Thu 6/11/26 |  |  | 1043 |  | NA | Master Data Loads | Wed 6/10/26 | Thu 6/11/26 |  | Tue 4/7/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.6 | NA | 2984 |  | 2991 | -22.94d | Yes | Yes | Yes | No | No | 1.2.3.2.5 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.5.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Wed 6/10/26 | Wed 6/10/26 | Kasey Hughes | 1035 | 1038 |  | NA | RTR_CM04_Cost_Center | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.4.6 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.5.2 | NA | 2985 | 2983 | 2986 | -183.52h | No | Yes | Yes | No | No | 1.2.3.2.5.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.5.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Wed 6/10/26 | Wed 6/10/26 | Kasey Hughes | 1037 | 1039 | Brian Wagner | NA | RTR_CM04_Cost_Center | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.5.1 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.5.3 | NA | 2986 | 2985 | 2987 | -183.52h | No | Yes | Yes | No | No | 1.2.3.2.5.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.5.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 6/10/26 | Wed 6/10/26 | Data Migration Team | 1038 | 1040 |  | NA | RTR_CM04_Cost_Center | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.5.2 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.5.4 | NA | 2987 | 2986 | 2988 | -183.52h | No | Yes | Yes | No | No | 1.2.3.2.5.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.5.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 6/10/26 | Wed 6/10/26 | Kasey Hughes | 1039 | 1041 | Brian Wagner | NA | RTR_CM04_Cost_Center | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.5.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.5.5 | NA | 2988 | 2987 | 2989 | -183.52h | No | Yes | Yes | No | No | 1.2.3.2.5.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.5.5 | Auto Scheduled | 0% | Load | No | 1h | Wed 6/10/26 | Wed 6/10/26 | Data Migration Team | 1040 | 1042 |  | NA | RTR_CM04_Cost_Center | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.5.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.5.6 | NA | 2989 | 2988 | 2990 | -183.52h | No | Yes | Yes | No | No | 1.2.3.2.5.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.5.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Thu 6/11/26 | Thu 6/11/26 | Kasey Hughes | 1041 |  | Brian Wagner | NA | RTR_CM04_Cost_Center | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.5.5 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 2990 | 2989 |  | -183.52h | No | Yes | Yes | No | No | 1.2.3.2.5.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.6 | Auto Scheduled | 0% | Manual Configuration Activities in QS5 | No | 5.94d | Thu 6/11/26 | Fri 6/19/26 |  | 1036 |  |  | NA | Master Data Loads | Thu 6/11/26 | Fri 6/19/26 | 1.2.3.2.5 | Mon 4/6/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2991 | 2984 |  | -23.88d | Yes | Yes | Yes | No | No | 1.2.3.2.6 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.6.1 | Auto Scheduled | 0% | Open Client | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Basis |  |  |  | NA | Manual Configuration Activities in QS5 | Thu 6/11/26 | Thu 6/11/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 2992 |  |  | -8641m | No | Yes | Yes | No | No | 1.2.3.2.6.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.6.2 | Auto Scheduled | 0% | Service Enterprise Setup | No | 5d | Fri 6/12/26 | Fri 6/19/26 | Keith Riley | 101210161020 |  |  | NA | Manual Configuration Activities in QS5 | Fri 6/12/26 | Fri 6/19/26 | 1.2.3.2.1,1.2.3.2.2,1.2.3.2.3 | Wed 4/8/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2993 | 296029642968 |  | -23.88d | No | Yes | Yes | No | No | 1.2.3.2.6.2 | 6 | No | 500 | Future Task | No | 0d
1.2.3.2.6.3 | Auto Scheduled | 0% | Close Client | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Basis |  |  |  | NA | Manual Configuration Activities in QS5 | Thu 6/11/26 | Thu 6/11/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 2994 |  |  | -8641m | No | Yes | Yes | No | No | 1.2.3.2.6.3 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.6.4 | Auto Scheduled | 0% | Intercompany Business Partner Setup | No | 2h | Fri 6/12/26 | Fri 6/12/26 | Functional Leads | 101210161028 |  |  | NA | Manual Configuration Activities in QS5 | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.1,1.2.3.2.2,1.2.3.2.3.8 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 2995 | 296029642976 |  | -153.02h | No | Yes | Yes | No | No | 1.2.3.2.6.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.7 | Auto Scheduled | 0% | RTR_CM09_Activity_Type | No | 1.38d | Thu 6/11/26 | Mon 6/15/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Mon 6/15/26 |  | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 2996 |  |  | -19.75d | Yes | Yes | Yes | No | No | 1.2.3.2.7 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.7.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Thu 6/11/26 | Thu 6/11/26 | Kasey Hughes | 1026 | 1050 |  | NA | RTR_CM09_Activity_Type | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.3.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.7.2 | NA | 2997 | 2974 | 2998 | -158.02h | No | Yes | Yes | No | No | 1.2.3.2.7.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.7.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 6/11/26 | Fri 6/12/26 | Kasey Hughes | 1049 | 1051 | Brian Wagner | NA | RTR_CM09_Activity_Type | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.7.1 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.7.3 | NA | 2998 | 2997 | 2999 | -158.02h | No | Yes | Yes | No | No | 1.2.3.2.7.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.7.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 6/12/26 | Fri 6/12/26 | Data Migration Team | 1050 | 1052 |  | NA | RTR_CM09_Activity_Type | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.7.2 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.7.4 | NA | 2999 | 2998 | 3000 | -158.02h | No | Yes | Yes | No | No | 1.2.3.2.7.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.7.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 6/12/26 | Fri 6/12/26 | Kasey Hughes | 1051 | 1053 | Brian Wagner | NA | RTR_CM09_Activity_Type | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.7.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.7.5 | NA | 3000 | 2999 | 3001 | -158.02h | No | Yes | Yes | No | No | 1.2.3.2.7.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.7.5 | Auto Scheduled | 0% | Load | No | 1h | Fri 6/12/26 | Fri 6/12/26 | Data Migration Team | 1052 | 1054 |  | NA | RTR_CM09_Activity_Type | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.7.4 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.7.6 | NA | 3001 | 3000 | 3002 | -158.02h | No | Yes | Yes | No | No | 1.2.3.2.7.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.7.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Fri 6/12/26 | Mon 6/15/26 | Kasey Hughes | 1053 |  | Brian Wagner | NA | RTR_CM09_Activity_Type | Fri 6/12/26 | Mon 6/15/26 | 1.2.3.2.7.5 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 3002 | 3001 |  | -158.02h | No | Yes | Yes | No | No | 1.2.3.2.7.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.8 | Auto Scheduled | 0% | RTR_CM12_Activity Rates | No | 1.13d | Tue 6/9/26 | Wed 6/10/26 |  |  |  |  | NA | Master Data Loads | Tue 6/9/26 | Wed 6/10/26 |  | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible |  | NA | 3003 |  |  | -17.56d | Yes | Yes | Yes | No | No | 1.2.3.2.8 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.8.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1019 | 1057 |  | NA | RTR_CM12_Activity Rates | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.2.3 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.8.2 | NA | 3004 | 2967 | 3005 | -140.52h | No | Yes | Yes | No | No | 1.2.3.2.8.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.8.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 6/9/26 | Wed 6/10/26 | Kasey Hughes | 1056 | 1058 | Brian Wagner | NA | RTR_CM12_Activity Rates | Tue 6/9/26 | Wed 6/10/26 | 1.2.3.2.8.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.8.3 | NA | 3005 | 3004 | 3006 | -140.52h | No | Yes | Yes | No | No | 1.2.3.2.8.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.8.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 6/10/26 | Wed 6/10/26 | Data Migration Team | 1057 | 1059 |  | NA | RTR_CM12_Activity Rates | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.8.2 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.8.4 | NA | 3006 | 3005 | 3007 | -140.52h | No | Yes | Yes | No | No | 1.2.3.2.8.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.8.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 6/10/26 | Wed 6/10/26 | Kasey Hughes | 1058 | 1060 | Brian Wagner | NA | RTR_CM12_Activity Rates | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.8.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.8.5 | NA | 3007 | 3006 | 3008 | -140.52h | No | Yes | Yes | No | No | 1.2.3.2.8.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.8.5 | Auto Scheduled | 0% | Load | No | 1h | Wed 6/10/26 | Wed 6/10/26 | Data Migration Team | 1059 | 1061 |  | NA | RTR_CM12_Activity Rates | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.8.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.8.6 | NA | 3008 | 3007 | 3009 | -140.52h | No | Yes | Yes | No | No | 1.2.3.2.8.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.8.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Wed 6/10/26 | Wed 6/10/26 | Kasey Hughes | 1060 |  | Brian Wagner | NA | RTR_CM12_Activity Rates | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.8.5 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible |  | NA | 3009 | 3008 |  | -140.52h | No | Yes | Yes | No | No | 1.2.3.2.8.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.9 | Auto Scheduled | 0% | RTR_CM06_Bank_master | No | 3.81d | Mon 6/8/26 | Fri 6/12/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Fri 6/12/26 |  | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 3010 |  |  | -21.06d | Yes | Yes | Yes | No | No | 1.2.3.2.9 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.9.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Thu 6/11/26 | Thu 6/11/26 | Data Migration Team | 1026 | 1064 |  | NA | RTR_CM06_Bank_master | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.3.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.9.2 | NA | 3011 | 2974 | 3012 | -150.02h | No | Yes | Yes | No | No | 1.2.3.2.9.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.9.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 6/11/26 | Fri 6/12/26 | Kasey Hughes | 1063 |  | Brian Wagner | NA | RTR_CM06_Bank_master | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.9.1 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 3012 | 3011 |  | -150.02h | No | Yes | Yes | No | No | 1.2.3.2.9.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.9.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 6/8/26 | Mon 6/8/26 | Data Migration Team |  | 1066 |  | NA | RTR_CM06_Bank_master | Mon 6/8/26 | Mon 6/8/26 |  | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.9.4 | NA | 3013 |  | 3014 | -168.52h | No | Yes | Yes | No | No | 1.2.3.2.9.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.9.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 6/8/26 | Mon 6/8/26 | Kasey Hughes | 1065 | 1067 | Brian Wagner | NA | RTR_CM06_Bank_master | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.9.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.9.5 | NA | 3014 | 3013 | 3015 | -168.52h | No | Yes | Yes | No | No | 1.2.3.2.9.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.9.5 | Auto Scheduled | 0% | Load | No | 5h | Mon 6/8/26 | Tue 6/9/26 | Data Migration Team | 1066 | 10681070 |  | NA | RTR_CM06_Bank_master | Mon 6/8/26 | Tue 6/9/26 | 1.2.3.2.9.4 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.9.6,1.2.3.2.10.1 | NA | 3015 | 3014 | 30163018 | -168.52h | No | Yes | Yes | No | No | 1.2.3.2.9.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.9.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1067 | 11041115 | Brian Wagner | NA | RTR_CM06_Bank_master | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.9.5 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.15.3,1.2.3.2.17.3 | NA | 3016 | 3015 | 30523063 | -168.52h | No | Yes | Yes | No | No | 1.2.3.2.9.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.10 | Auto Scheduled | 0% | RTR_CM08_Exchange_Rates | No | 1.13d | Tue 6/9/26 | Wed 6/10/26 |  |  |  |  | NA | Master Data Loads | Tue 6/9/26 | Wed 6/10/26 |  | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 3017 |  |  | -17.06d | Yes | Yes | Yes | No | No | 1.2.3.2.10 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.10.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1067 | 1071 |  | NA | RTR_CM08_Exchange_Rates | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.9.5 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.10.2 | NA | 3018 | 3015 | 3019 | -136.52h | No | Yes | Yes | No | No | 1.2.3.2.10.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.10.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1070 | 1072 | Brian Wagner | NA | RTR_CM08_Exchange_Rates | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.10.1 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.10.3 | NA | 3019 | 3018 | 3020 | -136.52h | No | Yes | Yes | No | No | 1.2.3.2.10.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.10.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 6/9/26 | Tue 6/9/26 | Data Migration Team | 1071 | 1073 |  | NA | RTR_CM08_Exchange_Rates | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.10.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.10.4 | NA | 3020 | 3019 | 3021 | -136.52h | No | Yes | Yes | No | No | 1.2.3.2.10.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.10.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1072 | 1074 | Brian Wagner | NA | RTR_CM08_Exchange_Rates | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.10.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.10.5 | NA | 3021 | 3020 | 3022 | -136.52h | No | Yes | Yes | No | No | 1.2.3.2.10.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.10.5 | Auto Scheduled | 0% | Load | No | 1h | Wed 6/10/26 | Wed 6/10/26 | Data Migration Team | 1073 | 1075 |  | NA | RTR_CM08_Exchange_Rates | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.10.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.10.6 | NA | 3022 | 3021 | 3023 | -136.52h | No | Yes | Yes | No | No | 1.2.3.2.10.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.10.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Wed 6/10/26 | Wed 6/10/26 | Kasey Hughes | 1074 |  | Brian Wagner | NA | RTR_CM08_Exchange_Rates | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.10.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 3023 | 3022 |  | -136.52h | No | Yes | Yes | No | No | 1.2.3.2.10.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.11 | Auto Scheduled | 0% | RTR_CM14_Cost Element_Group | No | 1.44d | Thu 6/11/26 | Mon 6/15/26 | Kasey Hughes |  |  | Brian Wagner | NA | Master Data Loads | Thu 6/11/26 | Mon 6/15/26 |  | Wed 4/8/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 3024 |  |  | -19.81d | Yes | Yes | Yes | No | No | 1.2.3.2.11 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.11.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Kasey Hughes | 1026 | 1078 |  | NA | RTR_CM14_Cost Element_Group | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.3.6 | Wed 4/8/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.11.2 | NA | 3025 | 2974 | 3026 | -9511m | No | Yes | Yes | No | No | 1.2.3.2.11.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.11.2 | Auto Scheduled | 0% | Load | No | 8h | Thu 6/11/26 | Fri 6/12/26 | Kasey Hughes | 1077 | 1079 |  | NA | RTR_CM14_Cost Element_Group | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.11.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.11.3 | NA | 3026 | 3025 | 3027 | -158.52h | No | Yes | Yes | No | No | 1.2.3.2.11.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.11.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 6/12/26 | Mon 6/15/26 | Kasey Hughes | 1078 |  | Brian Wagner | NA | RTR_CM14_Cost Element_Group | Fri 6/12/26 | Mon 6/15/26 | 1.2.3.2.11.2 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 3027 | 3026 |  | -158.52h | No | Yes | Yes | No | No | 1.2.3.2.11.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.12 | Auto Scheduled | 0% | OTC_CM19_Customer_Master - Bill-To | No | 2h | Mon 6/8/26 | Mon 6/8/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Mon 6/8/26 |  | Wed 4/16/25 | Wed 4/16/25 | As Soon As Possible |  | NA | 3028 |  |  | -121.52h | No | Yes | Yes | No | No | 1.2.3.2.12 | 5 | No | 500 | Future Task | No | 0h
1.2.3.2.13 | Auto Scheduled | 0% | OTC_CM19_Customer_Master - Ship-To | No | 1.5d | Thu 6/11/26 | Mon 6/15/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Mon 6/15/26 |  | Wed 4/8/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3029 |  |  | -24.31d | Yes | Yes | Yes | No | No | 1.2.3.2.13 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.13.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Ric Haraida | 1026 | 1083 |  | NA | OTC_CM19_Customer_Master - Ship-To | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.3.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.13.2 | NA | 3030 | 2974 | 3031 | -11671m | No | Yes | Yes | No | No | 1.2.3.2.13.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.13.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Ric Haraida | 1082 | 108710921084 | Kim Kolesar | NA | OTC_CM19_Customer_Master - Ship-To | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.13.1 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.3.2.13.6,1.2.3.2.14.1,1.2.3.2.13.3 | NA | 3031 | 3030 | 303530403032 | -11671m | No | Yes | Yes | No | No | 1.2.3.2.13.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.13.3 | Auto Scheduled | 0% | Open client for BP number range update | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Basis | 1083 | 1085 |  | NA | OTC_CM19_Customer_Master - Ship-To | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.13.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.13.4 | NA | 3032 | 3031 | 3033 | -8956m | No | Yes | Yes | No | No | 1.2.3.2.13.3 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.13.4 | Auto Scheduled | 0% | Update number range BP02 from Internal to External | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Ric Haraida | 1084 | 1086 |  | NA | OTC_CM19_Customer_Master - Ship-To | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.13.3 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.13.5 | NA | 3033 | 3032 | 3034 | -8956m | No | Yes | Yes | No | No | 1.2.3.2.13.4 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.13.5 | Auto Scheduled | 0% | Close Client | No | 15m | Thu 6/11/26 | Thu 6/11/26 | Basis | 1085 |  |  | NA | OTC_CM19_Customer_Master - Ship-To | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.13.4 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3034 | 3033 |  | -8956m | No | Yes | Yes | No | No | 1.2.3.2.13.5 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.13.6 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 6/11/26 | Thu 6/11/26 | Data Migration Team | 1083 | 108810941098 |  | NA | OTC_CM19_Customer_Master - Ship-To | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.13.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.13.7,1.2.3.2.14.3,1.2.3.2.14.7 | NA | 3035 | 3031 | 303630423046 | -194.52h | No | Yes | Yes | No | No | 1.2.3.2.13.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.13.7 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 4h | Thu 6/11/26 | Fri 6/12/26 | Ric Haraida | 1087 | 1089 | Kim Kolesar | NA | OTC_CM19_Customer_Master - Ship-To | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.13.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.13.8 | NA | 3036 | 3035 | 3037 | -159.02h | No | Yes | Yes | No | No | 1.2.3.2.13.7 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.13.8 | Auto Scheduled | 0% | Load | No | 3h | Fri 6/12/26 | Fri 6/12/26 | Data Migration Team | 1088 | 1090 |  | NA | OTC_CM19_Customer_Master - Ship-To | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.13.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.13.9 | NA | 3037 | 3036 | 3038 | -159.02h | No | Yes | Yes | No | No | 1.2.3.2.13.8 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.13.9 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 6/12/26 | Mon 6/15/26 | Ric Haraida | 1089 |  | Kim Kolesar | NA | OTC_CM19_Customer_Master - Ship-To | Fri 6/12/26 | Mon 6/15/26 | 1.2.3.2.13.8 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 3038 | 3037 |  | -159.02h | No | Yes | Yes | No | No | 1.2.3.2.13.9 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.14 | Auto Scheduled | 0% | OTC_CM19_Customer_Master - Sold-To | No | 1.63d | Thu 6/11/26 | Mon 6/15/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Mon 6/15/26 |  | Wed 4/8/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 3039 |  |  | -24.19d | Yes | Yes | Yes | No | No | 1.2.3.2.14 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.14.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Ric Haraida | 1083 | 1093 |  | NA | OTC_CM19_Customer_Master - Sold-To | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.13.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.14.2 | NA | 3040 | 3031 | 3041 | -8941m | No | Yes | Yes | No | No | 1.2.3.2.14.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.14.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Ric Haraida | 1092 |  | Kim Kolesar | NA | OTC_CM19_Customer_Master - Sold-To | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.14.1 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 3041 | 3040 |  | -8941m | No | Yes | Yes | No | No | 1.2.3.2.14.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.14.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 6/12/26 | Fri 6/12/26 | Data Migration Team | 10281087 | 1095 |  | NA | OTC_CM19_Customer_Master - Sold-To | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.3.8,1.2.3.2.13.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.14.4 | NA | 3042 | 29763035 | 3043 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.14.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.14.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 3h | Fri 6/12/26 | Fri 6/12/26 | Ric Haraida | 1094 | 1096 | Kim Kolesar | NA | OTC_CM19_Customer_Master - Sold-To | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.14.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.14.5 | NA | 3043 | 3042 | 3044 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.14.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.14.5 | Auto Scheduled | 0% | Load | No | 3h | Fri 6/12/26 | Mon 6/15/26 | Data Migration Team | 1095 | 1.0971e+19 |  | NA | OTC_CM19_Customer_Master - Sold-To | Fri 6/12/26 | Mon 6/15/26 | 1.2.3.2.14.4 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.14.6,1.2.3.2.15.1,1.2.3.2.16.1,1.2.3.2.17.1,1.2.3.2.18.1 | NA | 3044 | 3043 | 3.0453e+19 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.14.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.14.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 6/15/26 | Mon 6/15/26 | Ric Haraida | 1096 |  | Kim Kolesar | NA | OTC_CM19_Customer_Master - Sold-To | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 3045 | 3044 |  | -161.02h | No | Yes | Yes | No | No | 1.2.3.2.14.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.14.7 | Auto Scheduled | 0% | Open client for BP number range update | No | 15m | Thu 6/11/26 | Thu 6/11/26 | Basis | 1087 | 1099 |  | NA | OTC_CM19_Customer_Master - Sold-To | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.13.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.14.8 | NA | 3046 | 3035 | 3047 | -8986m | No | Yes | Yes | No | No | 1.2.3.2.14.7 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.14.8 | Auto Scheduled | 0% | Update number range BP02 from Internal to External | No | 15m | Thu 6/11/26 | Thu 6/11/26 | Ric Haraida | 1098 | 1100 |  | NA | OTC_CM19_Customer_Master - Sold-To | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.14.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.3.2.14.9 | NA | 3047 | 3046 | 3048 | -8986m | No | Yes | Yes | No | No | 1.2.3.2.14.8 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.14.9 | Auto Scheduled | 0% | Close Client | No | 15m | Fri 6/12/26 | Fri 6/12/26 | Basis | 1099 |  |  | NA | OTC_CM19_Customer_Master - Sold-To | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.14.8 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 3048 | 3047 |  | -8986m | No | Yes | Yes | No | No | 1.2.3.2.14.9 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.15 | Auto Scheduled | 0% | PTP_CM27_Vendor Master as Customer - FLCU01 | No | 4.81d | Mon 6/15/26 | Fri 6/19/26 |  |  |  |  | NA | Master Data Loads | Mon 6/15/26 | Fri 6/19/26 |  | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 3049 |  |  | -24.56d | Yes | Yes | Yes | No | No | 1.2.3.2.15 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.15.1 | Auto Scheduled | 0% | Extract File | No | 1h | Mon 6/15/26 | Mon 6/15/26 | Data Migration Team | 1096 | 1103 |  | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.15.2 | NA | 3050 | 3044 | 3051 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.15.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.15.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Mon 6/15/26 | Mon 6/15/26 | Nevin Varkey | 1102 | 1104 | Sam Houff | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.15.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.15.3 | NA | 3051 | 3050 | 3052 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.15.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.15.3 | Auto Scheduled | 0% | Simulate Load | No | 11.25h | Mon 6/15/26 | Tue 6/16/26 | Data Migration Team | 10681103 | 1105 |  | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Mon 6/15/26 | Tue 6/16/26 | 1.2.3.2.9.6,1.2.3.2.15.2 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.15.4 | NA | 3052 | 30163051 | 3053 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.15.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.15.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 6/16/26 | Thu 6/18/26 | Nevin Varkey | 1104 | 1106 | Sam Houff | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Tue 6/16/26 | Thu 6/18/26 | 1.2.3.2.15.3 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.15.5 | NA | 3053 | 3052 | 3054 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.15.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.15.5 | Auto Scheduled | 0% | Load | No | 1h | Thu 6/18/26 | Fri 6/19/26 | Data Migration Team | 1105 | 1107 |  | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Thu 6/18/26 | Fri 6/19/26 | 1.2.3.2.15.4 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.15.6 | NA | 3054 | 3053 | 3055 | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.15.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.15.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Fri 6/19/26 | Fri 6/19/26 | Nevin Varkey | 1106 |  | Sam Houff | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Fri 6/19/26 | Fri 6/19/26 | 1.2.3.2.15.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 3055 | 3054 |  | -196.52h | No | Yes | Yes | No | No | 1.2.3.2.15.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.16 | Auto Scheduled | 0% | OTC_CM23_Customer_Hierarchy | No | 0.69d | Mon 6/15/26 | Mon 6/15/26 |  |  |  |  | NA | Master Data Loads | Mon 6/15/26 | Mon 6/15/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 3056 |  |  | -20.44d | Yes | Yes | Yes | No | No | 1.2.3.2.16 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.16.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Mon 6/15/26 | Mon 6/15/26 | Ric Haraida | 1096 | 1110 | Kim Kolesar | NA | OTC_CM23_Customer_Hierarchy | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.16.2 | NA | 3057 | 3044 | 3058 | -9811m | No | Yes | Yes | No | No | 1.2.3.2.16.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.16.2 | Auto Scheduled | 0% | Load | No | 2h | Mon 6/15/26 | Mon 6/15/26 | Ric Haraida | 1109 | 1111 |  | NA | OTC_CM23_Customer_Hierarchy | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.16.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.16.3 | NA | 3058 | 3057 | 3059 | -163.52h | No | Yes | Yes | No | No | 1.2.3.2.16.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.16.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 6/15/26 | Mon 6/15/26 | Ric Haraida | 1110 |  | Kim Kolesar | NA | OTC_CM23_Customer_Hierarchy | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.16.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 3059 | 3058 |  | -163.52h | No | Yes | Yes | No | No | 1.2.3.2.16.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.17 | Auto Scheduled | 0% | PTP_CM27_Vendor Master - Z001 - External Sales Rep | No | 3.38d | Mon 6/15/26 | Thu 6/18/26 |  |  |  |  | NA | Master Data Loads | Mon 6/15/26 | Thu 6/18/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3060 |  |  | -23.13d | Yes | Yes | Yes | No | No | 1.2.3.2.17 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.17.1 | Auto Scheduled | 0% | Extract File | No | 1h | Mon 6/15/26 | Mon 6/15/26 | Data Migration Team | 1096 | 11141127 |  | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.17.2,1.2.3.2.19.1 | NA | 3061 | 3044 | 30623075 | -185.02h | No | Yes | Yes | No | No | 1.2.3.2.17.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.17.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Mon 6/15/26 | Mon 6/15/26 | Nevin Varkey | 1113 | 1115 | Sam Houff | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.17.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.17.3 | NA | 3062 | 3061 | 3063 | -185.02h | No | Yes | Yes | No | No | 1.2.3.2.17.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.17.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 6/15/26 | Mon 6/15/26 | Data Migration Team | 10681114 | 1116 |  | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.9.6,1.2.3.2.17.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.17.4 | NA | 3063 | 30163062 | 3064 | -185.02h | No | Yes | Yes | No | No | 1.2.3.2.17.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.17.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 6/15/26 | Mon 6/15/26 | Nevin Varkey | 1115 | 1117 | Sam Houff | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.17.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.17.5 | NA | 3064 | 3063 | 3065 | -185.02h | No | Yes | Yes | No | No | 1.2.3.2.17.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.17.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 6/15/26 | Thu 6/18/26 | Data Migration Team | 1116 | 1118 |  | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Mon 6/15/26 | Thu 6/18/26 | 1.2.3.2.17.4 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.17.6 | NA | 3065 | 3064 | 3066 | -185.02h | No | Yes | Yes | No | No | 1.2.3.2.17.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.17.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Thu 6/18/26 | Thu 6/18/26 | Nevin Varkey | 1117 |  | Sam Houff | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Thu 6/18/26 | Thu 6/18/26 | 1.2.3.2.17.5 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3066 | 3065 |  | -185.02h | No | Yes | Yes | No | No | 1.2.3.2.17.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.18 | Auto Scheduled | 0% | RTR_CM10_Credit_Management_Role | No | 1.84d | Mon 6/15/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Mon 6/15/26 | Tue 6/16/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3067 |  |  | -22.35d | Yes | Yes | Yes | No | No | 1.2.3.2.18 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.18.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 6/15/26 | Mon 6/15/26 | Kasey Hughes | 1096 | 1121 |  | NA | RTR_CM10_Credit_Management_Role | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.18.2 | NA | 3068 | 3044 | 3069 | -10726m | No | Yes | Yes | No | No | 1.2.3.2.18.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.18.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 6/15/26 | Mon 6/15/26 | Kasey Hughes | 1120 | 1122 | Brian Wagner | NA | RTR_CM10_Credit_Management_Role | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.18.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.18.3 | NA | 3069 | 3068 | 3070 | -10726m | No | Yes | Yes | No | No | 1.2.3.2.18.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.18.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 6/15/26 | Mon 6/15/26 | Data Migration Team | 1121 | 1123 |  | NA | RTR_CM10_Credit_Management_Role | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.18.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.18.4 | NA | 3070 | 3069 | 3071 | -178.77h | No | Yes | Yes | No | No | 1.2.3.2.18.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.18.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 6/15/26 | Mon 6/15/26 | Kasey Hughes | 1122 | 11241141 | Brian Wagner | NA | RTR_CM10_Credit_Management_Role | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.18.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.18.5,1.2.3.2.21.1 | NA | 3071 | 3070 | 30723089 | -178.77h | No | Yes | Yes | No | No | 1.2.3.2.18.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.18.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 6/15/26 | Tue 6/16/26 | Data Migration Team | 1123 | 1125 |  | NA | RTR_CM10_Credit_Management_Role | Mon 6/15/26 | Tue 6/16/26 | 1.2.3.2.18.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.18.6 | NA | 3072 | 3071 | 3073 | -178.77h | No | Yes | Yes | No | No | 1.2.3.2.18.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.18.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 6/16/26 | Tue 6/16/26 | Kasey Hughes | 1124 | 11421307 | Brian Wagner | NA | RTR_CM10_Credit_Management_Role | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.18.5 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.21.2,1.2.3.2.51.2 | NA | 3073 | 3072 | 30903255 | -178.77h | No | Yes | Yes | No | No | 1.2.3.2.18.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.19 | Auto Scheduled | 0% | PTP_CM27_Vendor Master | No | 6.28d | Mon 6/8/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Tue 6/16/26 |  | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 3074 |  |  | -23.78d | Yes | Yes | Yes | No | No | 1.2.3.2.19 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.19.1 | Auto Scheduled | 0% | Extract File | No | 1h | Mon 6/15/26 | Mon 6/15/26 | Data Migration Team | 1113 | 1128 |  | NA | PTP_CM27_Vendor Master | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.17.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.19.2 | NA | 3075 | 3061 | 3076 | -169.77h | No | Yes | Yes | No | No | 1.2.3.2.19.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.19.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Mon 6/15/26 | Mon 6/15/26 | Nevin Varkey | 1127 | 1129 | Sam Houff | NA | PTP_CM27_Vendor Master | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.19.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.19.3 | NA | 3076 | 3075 | 3077 | -169.77h | No | Yes | Yes | No | No | 1.2.3.2.19.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.19.3 | Auto Scheduled | 0% | Simulate Load | No | 2.25h | Mon 6/15/26 | Mon 6/15/26 | Data Migration Team | 1128 | 1130 |  | NA | PTP_CM27_Vendor Master | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.19.2 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.19.4 | NA | 3077 | 3076 | 3078 | -169.77h | No | Yes | Yes | No | No | 1.2.3.2.19.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.19.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 6/15/26 | Tue 6/16/26 | Nevin Varkey | 1129 |  | Sam Houff | NA | PTP_CM27_Vendor Master | Mon 6/15/26 | Tue 6/16/26 | 1.2.3.2.19.3 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 3078 | 3077 |  | -169.77h | No | Yes | Yes | No | No | 1.2.3.2.19.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.19.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 6/8/26 | Mon 6/8/26 | Data Migration Team |  | 1132 |  | NA | PTP_CM27_Vendor Master | Mon 6/8/26 | Mon 6/8/26 |  | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.19.6 | NA | 3079 |  | 3080 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.19.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.19.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 6/8/26 | Mon 6/8/26 | Nevin Varkey | 1131 | 114511601184 | Sam Houff | NA | PTP_CM27_Vendor Master | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.19.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.22.1,1.2.3.2.24.2,1.2.3.2.27.5 | NA | 3080 | 3079 | 309331083132 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.19.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.20 | Auto Scheduled | 0% | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | No | 0.88d | Mon 6/8/26 | Tue 6/9/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Tue 6/9/26 |  | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 3081 |  |  | -16.44d | Yes | Yes | Yes | No | No | 1.2.3.2.20 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.20.1 | Auto Scheduled | 0% | Extract File(Will Extract from LFA1) | No | 1h | Mon 6/8/26 | Mon 6/8/26 | Nevin Varkey |  | 11351159 |  | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Mon 6/8/26 | Mon 6/8/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.20.2,1.2.3.2.24.1 | NA | 3082 |  | 30833107 | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.20.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.20.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Mon 6/8/26 | Mon 6/8/26 | Nevin Varkey | 1134 | 1136 | Sam Houff | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.20.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.20.3 | NA | 3083 | 3082 | 3084 | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.20.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.20.3 | Auto Scheduled | 0% | Simulate Load/ Not Needed | No | 1h | Mon 6/8/26 | Mon 6/8/26 | Nevin Varkey | 1135 | 11371138 |  | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.20.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.20.4,1.2.3.2.20.5 | NA | 3084 | 3083 | 30853086 | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.20.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.20.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 6/8/26 | Mon 6/8/26 | Nevin Varkey | 1136 |  | Sam Houff | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.20.3 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3085 | 3084 |  | -125.52h | No | Yes | Yes | No | No | 1.2.3.2.20.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.20.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 6/8/26 | Mon 6/8/26 | Nevin Varkkey | 1136 | 1139 |  | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.20.3 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.20.6 | NA | 3086 | 3084 | 3087 | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.20.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.20.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 6/8/26 | Tue 6/9/26 | Nevin Varkey | 1138 | 1334 | Sam Houff | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Mon 6/8/26 | Tue 6/9/26 | 1.2.3.2.20.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.57.1 | NA | 3087 | 3086 | 3282 | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.20.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.21 | Auto Scheduled | 0% | RTR_****_Credit Hierarchy | No | 1.91d | Mon 6/15/26 | Wed 6/17/26 |  |  |  |  | NA | Master Data Loads | Mon 6/15/26 | Wed 6/17/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3088 |  |  | -22.22d | Yes | Yes | Yes | No | No | 1.2.3.2.21 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.21.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Mon 6/15/26 | Mon 6/15/26 | Kasey Hughes | 1123 |  | Brian Wagner | NA | RTR_****_Credit Hierarchy | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.18.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 3089 | 3071 |  | -9781m | No | Yes | Yes | No | No | 1.2.3.2.21.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.21.2 | Auto Scheduled | 0% | Load | No | 2h | Tue 6/16/26 | Wed 6/17/26 | Kasey Hughes | 1125 | 1143 |  | NA | RTR_****_Credit Hierarchy | Tue 6/16/26 | Wed 6/17/26 | 1.2.3.2.18.6 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.21.3 | NA | 3090 | 3073 | 3091 | -177.77h | No | Yes | Yes | No | No | 1.2.3.2.21.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.21.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 6/17/26 | Wed 6/17/26 | Kasey Hughes | 1142 |  | Brian Wagner | NA | RTR_****_Credit Hierarchy | Wed 6/17/26 | Wed 6/17/26 | 1.2.3.2.21.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3091 | 3090 |  | -177.77h | No | Yes | Yes | No | No | 1.2.3.2.21.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.22 | Auto Scheduled | 0% | PTP_CM27_BP_Intercompany Supplier | No | 1.13d | Mon 6/8/26 | Tue 6/9/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Tue 6/9/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 3092 |  |  | -16.44d | Yes | Yes | Yes | No | No | 1.2.3.2.22 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.22.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 6/8/26 | Mon 6/8/26 | Nevin Varkey,Ric Haraida | 1132 | 1146 |  | NA | PTP_CM27_BP_Intercompany Supplier | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.19.6 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.22.2 | NA | 3093 | 3080 | 3094 | -7891m | No | Yes | Yes | No | No | 1.2.3.2.22.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.22.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 6/8/26 | Mon 6/8/26 | Nevin Varkey,Ric Haraida | 1145 | 1147 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Supplier | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.22.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.22.3 | NA | 3094 | 3093 | 3095 | -7891m | No | Yes | Yes | No | No | 1.2.3.2.22.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.22.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 6/8/26 | Mon 6/8/26 | Data Migration Team | 1146 | 1148 |  | NA | PTP_CM27_BP_Intercompany Supplier | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.22.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.22.4 | NA | 3095 | 3094 | 3096 | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.22.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.22.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 6/8/26 | Tue 6/9/26 | Nevin Varkey,Ric Haraida | 1147 | 1149 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Supplier | Mon 6/8/26 | Tue 6/9/26 | 1.2.3.2.22.3 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.22.5 | NA | 3096 | 3095 | 3097 | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.22.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.22.5 | Auto Scheduled | 0% | Load | No | 2h | Tue 6/9/26 | Tue 6/9/26 | Data Migration Team | 1148 | 11501306 |  | NA | PTP_CM27_BP_Intercompany Supplier | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.22.4 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.22.6,1.2.3.2.51.1 | NA | 3097 | 3096 | 30983254 | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.22.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.22.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 6/9/26 | Tue 6/9/26 | Nevin Varkey,Ric Haraida | 1149 |  | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Supplier | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.22.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 3098 | 3097 |  | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.22.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.23 | Auto Scheduled | 0% | PTP_CM27_BP_Intercompany Customer | No | 1.06d | Mon 6/8/26 | Tue 6/9/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Tue 6/9/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 3099 |  |  | -16d | Yes | Yes | Yes | No | No | 1.2.3.2.23 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.23.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 6/8/26 | Mon 6/8/26 | Nevin Varkey,Ric Haraida |  |  |  | NA | PTP_CM27_BP_Intercompany Customer | Mon 6/8/26 | Mon 6/8/26 |  | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3100 |  |  | -7201m | No | Yes | Yes | No | No | 1.2.3.2.23.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.23.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 6/8/26 | Mon 6/8/26 | Nevin Varkey,Ric Haraida |  | 1154 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Customer | Mon 6/8/26 | Mon 6/8/26 |  | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.23.3 | NA | 3101 |  | 3102 | -7681m | No | Yes | Yes | No | No | 1.2.3.2.23.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.23.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 6/8/26 | Mon 6/8/26 | Data Migration Team | 1153 | 1155 |  | NA | PTP_CM27_BP_Intercompany Customer | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.23.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.23.4 | NA | 3102 | 3101 | 3103 | -128.02h | No | Yes | Yes | No | No | 1.2.3.2.23.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.23.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 6/8/26 | Mon 6/8/26 | Nevin Varkey,Ric Haraida | 1154 | 1156 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Customer | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.23.3 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.23.5 | NA | 3103 | 3102 | 3104 | -128.02h | No | Yes | Yes | No | No | 1.2.3.2.23.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.23.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 6/8/26 | Mon 6/8/26 | Data Migration Team | 1155 | 11571306 |  | NA | PTP_CM27_BP_Intercompany Customer | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.23.4 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.23.6,1.2.3.2.51.1 | NA | 3104 | 3103 | 31053254 | -128.02h | No | Yes | Yes | No | No | 1.2.3.2.23.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.23.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 6/8/26 | Tue 6/9/26 | Nevin Varkey,Ric Haraida | 1156 |  | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Customer | Mon 6/8/26 | Tue 6/9/26 | 1.2.3.2.23.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 3105 | 3104 |  | -128.02h | No | Yes | Yes | No | No | 1.2.3.2.23.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.24 | Auto Scheduled | 0% | PTP_CM26_Material_Master - All Types | No | 2.28d | Mon 6/8/26 | Wed 6/10/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Wed 6/10/26 |  | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 3106 |  |  | -23.53d | Yes | Yes | Yes | No | No | 1.2.3.2.24 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.24.1 | Auto Scheduled | 0% | Extract File | No | 5h | Mon 6/8/26 | Tue 6/9/26 | Data Migration Team | 1134 |  |  | NA | PTP_CM26_Material_Master - All Types | Mon 6/8/26 | Tue 6/9/26 | 1.2.3.2.20.1 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3107 | 3082 |  | -127.27h | No | Yes | Yes | No | No | 1.2.3.2.24.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.24.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Mon 6/8/26 | Tue 6/9/26 | Nevin Varkey,Ric Haraida | 1132 | 1161 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - All Types | Mon 6/8/26 | Tue 6/9/26 | 1.2.3.2.19.6 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.24.3 | NA | 3108 | 3080 | 3109 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.24.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.24.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 6/9/26 | Tue 6/9/26 | Data Migration Team | 1160 | 1162 |  | NA | PTP_CM26_Material_Master - All Types | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.24.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.24.4 | NA | 3109 | 3108 | 3110 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.24.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.24.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 4h | Tue 6/9/26 | Wed 6/10/26 | Nevin Varkey | 1161 | 1163 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - All Types | Tue 6/9/26 | Wed 6/10/26 | 1.2.3.2.24.3 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.24.5 | NA | 3110 | 3109 | 3111 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.24.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.24.5 | Auto Scheduled | 0% | Load | No | 3h | Wed 6/10/26 | Wed 6/10/26 | Data Migration Team | 1162 | 116411671174 |  | NA | PTP_CM26_Material_Master - All Types | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.24.4 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.24.6,1.2.3.2.25.2,1.2.3.2.26.2 | NA | 3111 | 3110 | 311231153122 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.24.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.24.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Wed 6/10/26 | Wed 6/10/26 | Nevin Varkey | 1163 | 118011871194 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - All Types | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.24.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.27.1,1.2.3.2.28.1,1.2.3.2.29.1 | NA | 3112 | 3111 | 312831353142 | -183.77h | No | Yes | Yes | No | No | 1.2.3.2.24.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.25 | Auto Scheduled | 0% | PTP_CM26_Material_Master - SERV - Service Materials | No | 1.34d | Wed 6/10/26 | Thu 6/11/26 |  |  |  |  | NA | Master Data Loads | Wed 6/10/26 | Thu 6/11/26 |  | Tue 4/7/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 3113 |  |  | -18.16d | Yes | Yes | Yes | No | No | 1.2.3.2.25 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.25.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Wed 6/10/26 | Wed 6/10/26 | Nevin Varkey,Ric Haraida | 1035 |  |  | NA | PTP_CM26_Material_Master - SERV - Service Materials | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.4.6 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 3114 | 2983 |  | -8101m | No | Yes | Yes | No | No | 1.2.3.2.25.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.25.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Wed 6/10/26 | Wed 6/10/26 | Nevin Varkey,Ric Haraida | 1163 | 1168 | Sam Houff,Kim Kolesar | NA | PTP_CM26_Material_Master - SERV - Service Materials | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.24.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.25.3 | NA | 3115 | 3111 | 3116 | -8716m | No | Yes | Yes | No | No | 1.2.3.2.25.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.25.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 6/10/26 | Wed 6/10/26 | Data Migration Team | 1167 | 1169 |  | NA | PTP_CM26_Material_Master - SERV - Service Materials | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.25.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.25.4 | NA | 3116 | 3115 | 3117 | -145.27h | No | Yes | Yes | No | No | 1.2.3.2.25.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.25.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 6/10/26 | Wed 6/10/26 | Nevin Varkey,Ric Haraida | 1168 | 1170 | Sam Houff,Kim Kolesar | NA | PTP_CM26_Material_Master - SERV - Service Materials | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.25.3 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.25.5 | NA | 3117 | 3116 | 3118 | -145.27h | No | Yes | Yes | No | No | 1.2.3.2.25.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.25.5 | Auto Scheduled | 0% | Load | No | 2h | Wed 6/10/26 | Thu 6/11/26 | Data Migration Team | 1169 | 1171 |  | NA | PTP_CM26_Material_Master - SERV - Service Materials | Wed 6/10/26 | Thu 6/11/26 | 1.2.3.2.25.4 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.25.6 | NA | 3118 | 3117 | 3119 | -145.27h | No | Yes | Yes | No | No | 1.2.3.2.25.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.25.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 6/11/26 | Thu 6/11/26 | Nevin Varkey,Ric Haraida | 1170 |  | Sam Houff,Kim Kolesar | NA | PTP_CM26_Material_Master - SERV - Service Materials | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.25.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 3119 | 3118 |  | -145.27h | No | Yes | Yes | No | No | 1.2.3.2.25.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.26 | Auto Scheduled | 0% | PTP_CM26_Material_Master - KMAT - Configurable Materials | No | 1.34d | Wed 6/10/26 | Thu 6/11/26 |  |  | 12651262 |  | NA | Master Data Loads | Wed 6/10/26 | Thu 6/11/26 |  | Tue 4/7/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.42.1,1.2.3.2.41.1 | NA | 3120 |  | 32133210 | -23.5d | Yes | Yes | Yes | No | No | 1.2.3.2.26 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.26.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Wed 6/10/26 | Wed 6/10/26 | Eric Heisler | 1035 |  |  | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.4.6 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 3121 | 2983 |  | -9346m | No | Yes | Yes | No | No | 1.2.3.2.26.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.26.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Wed 6/10/26 | Wed 6/10/26 | Eric Heisler | 1163 | 1175 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.24.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.26.3 | NA | 3122 | 3111 | 3123 | -11416m | No | Yes | Yes | No | No | 1.2.3.2.26.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.26.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 6/10/26 | Wed 6/10/26 | Data Migration Team | 1174 | 1176 |  | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.26.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.3.2.26.4 | NA | 3123 | 3122 | 3124 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.26.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.26.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 6/10/26 | Wed 6/10/26 | Eric Heisler | 1175 | 1177 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Wed 6/10/26 | Wed 6/10/26 | 1.2.3.2.26.3 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.26.5 | NA | 3124 | 3123 | 3125 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.26.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.26.5 | Auto Scheduled | 0% | Load | No | 2h | Wed 6/10/26 | Thu 6/11/26 | Data Migration Team | 1176 | 1178 |  | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Wed 6/10/26 | Thu 6/11/26 | 1.2.3.2.26.4 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.26.6 | NA | 3125 | 3124 | 3126 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.26.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.26.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 6/11/26 | Thu 6/11/26 | Eric Heisler | 1177 | 1.1801e+19 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.26.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.27.1,1.2.3.2.28.1,1.2.3.2.29.1,1.2.3.2.40.1,1.2.3.2.46.1 | NA | 3126 | 3125 | 3.1283e+19 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.26.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.27 | Auto Scheduled | 0% | PTP_CM28_Purchase_Info_Records | No | 3.59d | Mon 6/8/26 | Fri 6/12/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Fri 6/12/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3127 |  |  | -19.96d | Yes | Yes | Yes | No | No | 1.2.3.2.27 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.27.1 | Auto Scheduled | 0% | Extract File | No | 1h | Thu 6/11/26 | Thu 6/11/26 | Data Migration Team | 11641178 | 11811201 |  | NA | PTP_CM28_Purchase_Info_Records | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.24.6,1.2.3.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.27.2,1.2.3.2.30.1 | NA | 3128 | 31123126 | 31293149 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.27.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.27.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 6/11/26 | Thu 6/11/26 | Nevin Varkey | 1180 | 1182 | Sam Houff | NA | PTP_CM28_Purchase_Info_Records | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.27.1 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.27.3 | NA | 3129 | 3128 | 3130 | -151.27h | No | Yes | Yes | No | No | 1.2.3.2.27.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.27.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 6/11/26 | Thu 6/11/26 | Data Migration Team | 1181 | 1183 |  | NA | PTP_CM28_Purchase_Info_Records | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.27.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.27.4 | NA | 3130 | 3129 | 3131 | -151.27h | No | Yes | Yes | No | No | 1.2.3.2.27.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.27.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 6/11/26 | Fri 6/12/26 | Nevin Varkey | 1182 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Records | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.27.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3131 | 3130 |  | -151.27h | No | Yes | Yes | No | No | 1.2.3.2.27.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.27.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 6/8/26 | Mon 6/8/26 | Data Migration Team | 1132 | 1185 |  | NA | PTP_CM28_Purchase_Info_Records | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.19.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.27.6 | NA | 3132 | 3080 | 3133 | -125.52h | No | Yes | Yes | No | No | 1.2.3.2.27.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.27.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 6/8/26 | Mon 6/8/26 | Nevin Varkey | 1184 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Records | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.27.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 3133 | 3132 |  | -125.52h | No | Yes | Yes | No | No | 1.2.3.2.27.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.28 | Auto Scheduled | 0% | PTP_CM28_Purchase_Info_Record External Processing | No | 1.13d | Thu 6/11/26 | Fri 6/12/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Fri 6/12/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3134 |  |  | -19.28d | Yes | Yes | Yes | No | No | 1.2.3.2.28 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.28.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Nevin Varkey | 11641178 | 1188 |  | NA | PTP_CM28_Purchase_Info_Record External Processing | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.24.6,1.2.3.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.28.2 | NA | 3135 | 31123126 | 3136 | -9256m | No | Yes | Yes | No | No | 1.2.3.2.28.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.28.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Nevin Varkey | 1187 | 1189 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record External Processing | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.28.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.28.3 | NA | 3136 | 3135 | 3137 | -9256m | No | Yes | Yes | No | No | 1.2.3.2.28.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.28.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 6/11/26 | Thu 6/11/26 | Data Migration Team | 1188 | 1190 |  | NA | PTP_CM28_Purchase_Info_Record External Processing | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.28.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.28.4 | NA | 3137 | 3136 | 3138 | -154.27h | No | Yes | Yes | No | No | 1.2.3.2.28.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.28.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 6/11/26 | Thu 6/11/26 | Nevin Varkey | 1189 | 1191 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record External Processing | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.28.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.28.5 | NA | 3138 | 3137 | 3139 | -154.27h | No | Yes | Yes | No | No | 1.2.3.2.28.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.28.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 6/11/26 | Fri 6/12/26 | Data Migration Team | 1190 | 1192 |  | NA | PTP_CM28_Purchase_Info_Record External Processing | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.28.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.28.6 | NA | 3139 | 3138 | 3140 | -154.27h | No | Yes | Yes | No | No | 1.2.3.2.28.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.28.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 6/12/26 | Fri 6/12/26 | Nevin Varkey | 1191 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Record External Processing | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.28.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3140 | 3139 |  | -154.27h | No | Yes | Yes | No | No | 1.2.3.2.28.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.29 | Auto Scheduled | 0% | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | No | 1.13d | Thu 6/11/26 | Fri 6/12/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Fri 6/12/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3141 |  |  | -23.78d | Yes | Yes | Yes | No | No | 1.2.3.2.29 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.29.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Nevin Varkey | 11641178 | 1195 |  | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.24.6,1.2.3.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.29.2 | NA | 3142 | 31123126 | 3143 | -11416m | No | Yes | Yes | No | No | 1.2.3.2.29.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.29.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Nevin Varkey | 1194 | 1196 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.29.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.29.3 | NA | 3143 | 3142 | 3144 | -11416m | No | Yes | Yes | No | No | 1.2.3.2.29.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.29.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 6/11/26 | Thu 6/11/26 | Data Migration Team | 1195 | 11971328 |  | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.29.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.29.4,1.2.3.2.55.1 | NA | 3144 | 3143 | 31453276 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.29.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.29.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 6/11/26 | Thu 6/11/26 | Nevin Varkey | 1196 | 1198 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.29.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.29.5 | NA | 3145 | 3144 | 3146 | -154.27h | No | Yes | Yes | No | No | 1.2.3.2.29.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.29.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 6/11/26 | Fri 6/12/26 | Data Migration Team | 1197 | 1199 |  | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.29.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.29.6 | NA | 3146 | 3145 | 3147 | -154.27h | No | Yes | Yes | No | No | 1.2.3.2.29.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.29.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 6/12/26 | Fri 6/12/26 | Nevin Varkey | 1198 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.29.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3147 | 3146 |  | -154.27h | No | Yes | Yes | No | No | 1.2.3.2.29.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.30 | Auto Scheduled | 0% | PTM_CM31_BOM Conversion | No | 2.48d | Thu 6/11/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Tue 6/16/26 |  | Wed 4/15/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3148 |  |  | -22.8d | Yes | Yes | Yes | No | No | 1.2.3.2.30 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.30.1 | Auto Scheduled | 0% | Extract File | No | 1h | Thu 6/11/26 | Thu 6/11/26 | Data Migration Team | 1180 | 12021208 |  | NA | PTM_CM31_BOM Conversion | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.27.1 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.30.2,1.2.3.2.31.1 | NA | 3149 | 3128 | 31503156 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.30.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.30.2 | Auto Scheduled | 0% | Pre Load Validation | No | 0.5h | Thu 6/11/26 | Thu 6/11/26 | Brad Meseck | 1201 | 1203 | Matt Palastro, Dave Duda | NA | PTM_CM31_BOM Conversion | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.30.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.30.3 | NA | 3150 | 3149 | 3151 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.30.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.30.3 | Auto Scheduled | 0% | Simulate Load | No | 15.5h | Thu 6/11/26 | Mon 6/15/26 | Data Migration Team | 1202 | 1204 |  | NA | PTM_CM31_BOM Conversion | Thu 6/11/26 | Mon 6/15/26 | 1.2.3.2.30.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.30.4 | NA | 3151 | 3150 | 3152 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.30.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.30.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 0.5h | Mon 6/15/26 | Mon 6/15/26 | Brad Meseck | 1203 | 1205 | Matt Palastro, Dave Duda | NA | PTM_CM31_BOM Conversion | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.30.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 2026-04-01 | NA | 3152 | 3151 | 3153 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.30.4 | 6 | No | 500 | Future Task | No | 0h
2026-04-01 | Auto Scheduled | 0% | Load | No | 1h | Mon 6/15/26 | Mon 6/15/26 | Data Migration Team | 1204 | 1206 |  | NA | PTM_CM31_BOM Conversion | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.30.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.30.6 | NA | 3153 | 3152 | 3154 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.30.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.30.6 | Auto Scheduled | 0% | Post Load Validation | No | 0.5h | Tue 6/16/26 | Tue 6/16/26 | Brad Meseck | 1205 | 1209 | Matt Palastro, Dave Duda | NA | PTM_CM31_BOM Conversion | Tue 6/16/26 | Tue 6/16/26 | 2026-04-01 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.31.2 | NA | 3154 | 3153 | 3157 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.30.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.31 | Auto Scheduled | 0% | PTM_CM40_Work Center Conversion | No | 3.08d | Thu 6/11/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Tue 6/16/26 |  | Thu 4/16/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 3155 |  |  | -22.8d | Yes | Yes | Yes | No | No | 1.2.3.2.31 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.31.1 | Auto Scheduled | 0% | Extract File | No | 1h | Thu 6/11/26 | Thu 6/11/26 | Data Migration Team | 1201 | 1215 |  | NA | PTM_CM40_Work Center Conversion | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.30.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.32.1 | NA | 3156 | 3149 | 3163 | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.31.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.31.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 6/16/26 | Tue 6/16/26 | Brad Meseck | 1206 | 1210 | Matt Palastro, Dave Duda | NA | PTM_CM40_Work Center Conversion | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.30.6 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.31.3 | NA | 3157 | 3154 | 3158 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.31.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.31.3 | Auto Scheduled | 0% | Simulate Load | No | 0.25h | Tue 6/16/26 | Tue 6/16/26 | Data Migration Team | 1209 | 1211 |  | NA | PTM_CM40_Work Center Conversion | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.31.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.31.4 | NA | 3158 | 3157 | 3159 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.31.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.31.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 0.5h | Tue 6/16/26 | Tue 6/16/26 | Brad Meseck | 1210 | 1212 | Matt Palastro, Dave Duda | NA | PTM_CM40_Work Center Conversion | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.31.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.31.5 | NA | 3159 | 3158 | 3160 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.31.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.31.5 | Auto Scheduled | 0% | Load | No | 1h | Tue 6/16/26 | Tue 6/16/26 | Data Migration Team | 1211 | 1213 |  | NA | PTM_CM40_Work Center Conversion | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.31.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.31.6 | NA | 3160 | 3159 | 3161 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.31.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.31.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Tue 6/16/26 | Tue 6/16/26 | Brad Meseck | 1212 | 1216 | Matt Palastro, Dave Duda | NA | PTM_CM40_Work Center Conversion | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.31.5 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.32.2 | NA | 3161 | 3160 | 3164 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.31.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.32 | Auto Scheduled | 0% | PTM_CM38_Routing Conversion | No | 4.27d | Thu 6/11/26 | Thu 6/18/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Thu 6/18/26 |  | Thu 4/16/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 3162 |  |  | -22.8d | Yes | Yes | Yes | No | No | 1.2.3.2.32 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.32.1 | Auto Scheduled | 0% | Extract File | No | 1h | Thu 6/11/26 | Thu 6/11/26 | Data Migration Team | 1208 | 1222 |  | NA | PTM_CM38_Routing Conversion | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.31.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.33.1 | NA | 3163 | 3156 | 3170 | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.32.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.32.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 6/16/26 | Wed 6/17/26 | Brad Meseck | 1213 | 1217 | Matt Palastro, Dave Duda | NA | PTM_CM38_Routing Conversion | Tue 6/16/26 | Wed 6/17/26 | 1.2.3.2.31.6 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.32.3 | NA | 3164 | 3161 | 3165 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.32.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.32.3 | Auto Scheduled | 0% | Simulate Load | No | 2h | Wed 6/17/26 | Wed 6/17/26 | Data Migration Team | 1216 | 1218SS |  | NA | PTM_CM38_Routing Conversion | Wed 6/17/26 | Wed 6/17/26 | 1.2.3.2.32.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.32.4[SS] | NA | 3165 | 3164 | 3166SS | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.32.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.32.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 3h | Wed 6/17/26 | Wed 6/17/26 | Brad Meseck | 1217SS | 1219 | Matt Palastro, Dave Duda | NA | PTM_CM38_Routing Conversion | Wed 6/17/26 | Wed 6/17/26 | 1.2.3.2.32.3[SS] | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.32.5 | NA | 3166 | 3165SS | 3167 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.32.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.32.5 | Auto Scheduled | 0% | Load | No | 1h | Wed 6/17/26 | Wed 6/17/26 | Data Migration Team | 1218 | 1220 |  | NA | PTM_CM38_Routing Conversion | Wed 6/17/26 | Wed 6/17/26 | 1.2.3.2.32.4 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.32.6 | NA | 3167 | 3166 | 3168 | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.32.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.32.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Wed 6/17/26 | Thu 6/18/26 | Brad Meseck | 1219 |  | Matt Palastro, Dave Duda | NA | PTM_CM38_Routing Conversion | Wed 6/17/26 | Thu 6/18/26 | 1.2.3.2.32.5 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 3168 | 3167 |  | -182.39h | No | Yes | Yes | No | No | 1.2.3.2.32.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.33 | Auto Scheduled | 0% | PTM_CM36_Production Version Conversion | No | 1.13d | Thu 6/11/26 | Mon 6/15/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Mon 6/15/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3169 |  |  | -21.72d | Yes | Yes | Yes | No | No | 1.2.3.2.33 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.33.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 6/11/26 | Fri 6/12/26 | Brad Meseck | 1215 | 12231317 |  | NA | PTM_CM36_Production Version Conversion | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.32.1 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than | 1.2.3.2.33.2,1.2.3.2.53.1 | Mon 4/20/26 | 3170 | 3163 | 31713265 | -10426m | No | Yes | Yes | No | No | 1.2.3.2.33.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.33.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Fri 6/12/26 | Fri 6/12/26 | Brad Meseck | 1222 | 1224 | Matt Palastro, Dave Duda | NA | PTM_CM36_Production Version Conversion | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.33.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.33.3 | NA | 3171 | 3170 | 3172 | -10426m | No | Yes | Yes | No | No | 1.2.3.2.33.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.33.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 6/12/26 | Fri 6/12/26 | Data Migration Team | 1223 | 1225 |  | NA | PTM_CM36_Production Version Conversion | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.33.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.33.4 | NA | 3172 | 3171 | 3173 | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.33.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.33.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 6/12/26 | Fri 6/12/26 | Brad Meseck | 1224 | 1226 | Matt Palastro, Dave Duda | NA | PTM_CM36_Production Version Conversion | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.33.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.33.5 | NA | 3173 | 3172 | 3174 | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.33.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.33.5 | Auto Scheduled | 0% | Load | No | 2h | Fri 6/12/26 | Fri 6/12/26 | Data Migration Team | 1225 | 1227 |  | NA | PTM_CM36_Production Version Conversion | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.33.4 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.33.6 | NA | 3174 | 3173 | 3175 | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.33.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.33.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 6/12/26 | Mon 6/15/26 | Brad Meseck | 1226 | 1229 | Matt Palastro, Dave Duda | NA | PTM_CM36_Production Version Conversion | Fri 6/12/26 | Mon 6/15/26 | 1.2.3.2.33.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.34.1 | NA | 3175 | 3174 | 3177 | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.33.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.34 | Auto Scheduled | 0% | PTM_CM35_Inspection Plan | No | 1.13d | Mon 6/15/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Mon 6/15/26 | Tue 6/16/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 3176 |  |  | -21.72d | Yes | Yes | Yes | No | No | 1.2.3.2.34 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.34.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 6/15/26 | Mon 6/15/26 | Brad Meseck | 1227 | 12301236 |  | NA | PTM_CM35_Inspection Plan | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.33.6 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.34.2,1.2.3.2.35.1 | NA | 3177 | 3175 | 31783184 | -10426m | No | Yes | Yes | No | No | 1.2.3.2.34.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.34.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 6/15/26 | Mon 6/15/26 | Brad Meseck | 1229 | 1231 | Matt Palastro, Dave Duda | NA | PTM_CM35_Inspection Plan | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.34.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.34.3 | NA | 3178 | 3177 | 3179 | -10036m | No | Yes | Yes | No | No | 1.2.3.2.34.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.34.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 6/15/26 | Mon 6/15/26 | Data Migration Team | 1230 | 1232 |  | NA | PTM_CM35_Inspection Plan | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.34.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.34.4 | NA | 3179 | 3178 | 3180 | -167.27h | No | Yes | Yes | No | No | 1.2.3.2.34.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.34.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 6/15/26 | Mon 6/15/26 | Brad Meseck | 1231 | 1233 | Matt Palastro, Dave Duda | NA | PTM_CM35_Inspection Plan | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.34.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.34.5 | NA | 3180 | 3179 | 3181 | -167.27h | No | Yes | Yes | No | No | 1.2.3.2.34.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.34.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 6/15/26 | Mon 6/15/26 | Data Migration Team | 1232 | 1234 |  | NA | PTM_CM35_Inspection Plan | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.34.4 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.34.6 | NA | 3181 | 3180 | 3182 | -167.27h | No | Yes | Yes | No | No | 1.2.3.2.34.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.34.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 6/15/26 | Tue 6/16/26 | Brad Meseck | 1233 |  | Matt Palastro, Dave Duda | NA | PTM_CM35_Inspection Plan | Mon 6/15/26 | Tue 6/16/26 | 1.2.3.2.34.5 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 3182 | 3181 |  | -167.27h | No | Yes | Yes | No | No | 1.2.3.2.34.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.35 | Auto Scheduled | 0% | PTM_CM48_Equipment_Master_Serial Numbers | No | 1.13d | Mon 6/15/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Mon 6/15/26 | Tue 6/16/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 3183 |  |  | -21.72d | Yes | Yes | Yes | No | No | 1.2.3.2.35 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.35.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 6/15/26 | Mon 6/15/26 | Brad Meseck | 1229 | 1237 |  | NA | PTM_CM48_Equipment_Master_Serial Numbers | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.34.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.35.2 | NA | 3184 | 3177 | 3185 | -10426m | No | Yes | Yes | No | No | 1.2.3.2.35.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.35.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 6/15/26 | Mon 6/15/26 | Brad Meseck | 1236 | 1238 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Serial Numbers | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.35.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.35.3 | NA | 3185 | 3184 | 3186 | -10426m | No | Yes | Yes | No | No | 1.2.3.2.35.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.35.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 6/15/26 | Mon 6/15/26 | Data Migration Team | 1237 | 1239 |  | NA | PTM_CM48_Equipment_Master_Serial Numbers | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.35.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.35.4 | NA | 3186 | 3185 | 3187 | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.35.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.35.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 6/15/26 | Mon 6/15/26 | Brad Meseck | 1238 | 1240 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Serial Numbers | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.35.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.35.5 | NA | 3187 | 3186 | 3188 | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.35.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.35.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 6/15/26 | Mon 6/15/26 | Data Migration Team | 1239 | 1241 |  | NA | PTM_CM48_Equipment_Master_Serial Numbers | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.35.4 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.35.6 | NA | 3188 | 3187 | 3189 | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.35.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.35.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 6/15/26 | Tue 6/16/26 | Brad Meseck | 1240 | 1243 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Serial Numbers | Mon 6/15/26 | Tue 6/16/26 | 1.2.3.2.35.5 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.36.1 | NA | 3189 | 3188 | 3191 | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.35.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.36 | Auto Scheduled | 0% | PTM_CM48_Equipment_Master_Service | No | 6.78d | Mon 6/8/26 | Wed 6/17/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Wed 6/17/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 3190 |  |  | -21.72d | Yes | Yes | Yes | No | No | 1.2.3.2.36 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.36.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 6/16/26 | Tue 6/16/26 | Brad Meseck | 1241 | 1244 |  | NA | PTM_CM48_Equipment_Master_Service | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.35.6 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.36.2 | NA | 3191 | 3189 | 3192 | -10426m | No | Yes | Yes | No | No | 1.2.3.2.36.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.36.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 6/16/26 | Tue 6/16/26 | Brad Meseck | 1243 | 1245 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Service | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.36.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.36.3 | NA | 3192 | 3191 | 3193 | -10426m | No | Yes | Yes | No | No | 1.2.3.2.36.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.36.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 6/16/26 | Tue 6/16/26 | Data Migration Team | 1244 | 1246 |  | NA | PTM_CM48_Equipment_Master_Service | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.36.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.36.4 | NA | 3193 | 3192 | 3194 | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.36.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.36.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 6/16/26 | Tue 6/16/26 | Brad Meseck | 1245 | 1247 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Service | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.36.3 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible | 1.2.3.2.36.5 | NA | 3194 | 3193 | 3195 | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.36.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.36.5 | Auto Scheduled | 0% | Load | No | 2h | Tue 6/16/26 | Wed 6/17/26 | Data Migration Team | 1246 |  |  | NA | PTM_CM48_Equipment_Master_Service | Tue 6/16/26 | Wed 6/17/26 | 1.2.3.2.36.4 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 3195 | 3194 |  | -173.77h | No | Yes | Yes | No | No | 1.2.3.2.36.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.36.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 6/8/26 | Mon 6/8/26 | Brad Meseck |  |  | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Service | Mon 6/8/26 | Mon 6/8/26 |  | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 3196 |  |  | -122.52h | No | Yes | Yes | No | No | 1.2.3.2.36.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.37 | Auto Scheduled | 0% | VC_Object Dependencies | No | 0.63d | Mon 6/8/26 | Mon 6/8/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Mon 6/8/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 3197 |  |  | -17.44d | Yes | Yes | Yes | No | No | 1.2.3.2.37 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.37.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Mon 6/8/26 | Mon 6/8/26 | Eric Heisler |  | 1251 |  | NA | VC_Object Dependencies | Mon 6/8/26 | Mon 6/8/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.3.2.37.2 | NA | 3198 |  | 3199 | -139.52h | No | Yes | Yes | No | No | 1.2.3.2.37.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.37.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 6/8/26 | Mon 6/8/26 | Eric Heisler | 1250 | 1253 | Matt Palastro, Dave Duda | NA | VC_Object Dependencies | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.37.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.3.2.38.1 | NA | 3199 | 3198 | 3201 | -139.52h | No | Yes | Yes | No | No | 1.2.3.2.37.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.38 | Auto Scheduled | 0% | VC_Characteristics | No | 0.63d | Mon 6/8/26 | Tue 6/9/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Tue 6/9/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 3200 |  |  | -17.44d | Yes | Yes | Yes | No | No | 1.2.3.2.38 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.38.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Mon 6/8/26 | Tue 6/9/26 | Eric Heisler | 1251 | 1254 |  | NA | VC_Characteristics | Mon 6/8/26 | Tue 6/9/26 | 1.2.3.2.37.2 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.3.2.38.2 | NA | 3201 | 3199 | 3202 | -139.52h | No | Yes | Yes | No | No | 1.2.3.2.38.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.38.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 6/9/26 | Tue 6/9/26 | Eric Heisler | 1253 | 1256 | Matt Palastro, Dave Duda | NA | VC_Characteristics | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.38.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.39.1 | NA | 3202 | 3201 | 3204 | -139.52h | No | Yes | Yes | No | No | 1.2.3.2.38.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.39 | Auto Scheduled | 0% | VC_Classes | No | 0.63d | Tue 6/9/26 | Wed 6/10/26 |  |  |  |  | NA | Master Data Loads | Tue 6/9/26 | Wed 6/10/26 |  | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 3203 |  |  | -17.44d | Yes | Yes | Yes | No | No | 1.2.3.2.39 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.39.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Tue 6/9/26 | Tue 6/9/26 | Eric Heisler | 1254 | 1257 |  | NA | VC_Classes | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.38.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.39.2 | NA | 3204 | 3202 | 3205 | -139.52h | No | Yes | Yes | No | No | 1.2.3.2.39.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.39.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 6/9/26 | Wed 6/10/26 | Eric Heisler | 1256 | 1262 | Matt Palastro, Dave Duda | NA | VC_Classes | Tue 6/9/26 | Wed 6/10/26 | 1.2.3.2.39.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.3.2.41.1 | NA | 3205 | 3204 | 3210 | -139.52h | No | Yes | Yes | No | No | 1.2.3.2.39.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.40 | Auto Scheduled | 0% | VC_Classification (Class Type 200) | No | 0.63d | Thu 6/11/26 | Fri 6/12/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Fri 6/12/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3206 |  |  | -18.78d | Yes | Yes | Yes | No | No | 1.2.3.2.40 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.40.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Thu 6/11/26 | Thu 6/11/26 | Eric Heisler | 1178 | 1260 |  | NA | VC_Classification (Class Type 200) | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.26.6 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.40.2 | NA | 3207 | 3126 | 3208 | -150.27h | No | Yes | Yes | No | No | 1.2.3.2.40.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.40.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 6/11/26 | Fri 6/12/26 | Eric Heisler | 1259 |  | Matt Palastro, Dave Duda | NA | VC_Classification (Class Type 200) | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.40.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3208 | 3207 |  | -150.27h | No | Yes | Yes | No | No | 1.2.3.2.40.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.41 | Auto Scheduled | 0% | VC_Dependency Nets | No | 0.63d | Thu 6/11/26 | Fri 6/12/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Fri 6/12/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3209 |  |  | -18.78d | Yes | Yes | Yes | No | No | 1.2.3.2.41 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.41.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Thu 6/11/26 | Thu 6/11/26 | Eric Heisler | 11721257 | 1263 |  | NA | VC_Dependency Nets | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.26,1.2.3.2.39.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.41.2 | NA | 3210 | 31203205 | 3211 | -150.27h | No | Yes | Yes | No | No | 1.2.3.2.41.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.41.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 6/11/26 | Fri 6/12/26 | Eric Heisler | 1262 |  | Matt Palastro, Dave Duda | NA | VC_Dependency Nets | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.41.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3211 | 3210 |  | -150.27h | No | Yes | Yes | No | No | 1.2.3.2.41.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.42 | Auto Scheduled | 0% | VC_Configuration Profiles | No | 0.63d | Thu 6/11/26 | Fri 6/12/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Fri 6/12/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3212 |  |  | -20.75d | Yes | Yes | Yes | No | No | 1.2.3.2.42 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.42.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Thu 6/11/26 | Thu 6/11/26 | Eric Heisler | 1172 | 1266 |  | NA | VC_Configuration Profiles | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.26 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.42.2 | NA | 3213 | 3120 | 3214 | -166.02h | No | Yes | Yes | No | No | 1.2.3.2.42.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.42.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 6/11/26 | Fri 6/12/26 | Eric Heisler | 1265 | 12741268 | Matt Palastro, Dave Duda | NA | VC_Configuration Profiles | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.42.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.45.1,1.2.3.2.43.1 | NA | 3214 | 3213 | 32223216 | -166.02h | No | Yes | Yes | No | No | 1.2.3.2.42.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.43 | Auto Scheduled | 0% | VC_Variant Tables | No | 0.63d | Fri 6/12/26 | Fri 6/12/26 |  |  |  |  | NA | Master Data Loads | Fri 6/12/26 | Fri 6/12/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3215 |  |  | -20.03d | Yes | Yes | Yes | No | No | 1.2.3.2.43 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.43.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Fri 6/12/26 | Fri 6/12/26 | Eric Heisler | 1266 | 1269 |  | NA | VC_Variant Tables | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.42.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.43.2 | NA | 3216 | 3214 | 3217 | -160.27h | No | Yes | Yes | No | No | 1.2.3.2.43.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.43.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 6/12/26 | Fri 6/12/26 | Eric Heisler | 1268 | 1271 | Matt Palastro, Dave Duda | NA | VC_Variant Tables | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.43.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.44.1 | NA | 3217 | 3216 | 3219 | -160.27h | No | Yes | Yes | No | No | 1.2.3.2.43.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.44 | Auto Scheduled | 0% | VC_Variant Tables Content | No | 0.63d | Fri 6/12/26 | Mon 6/15/26 |  |  |  |  | NA | Master Data Loads | Fri 6/12/26 | Mon 6/15/26 |  | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3218 |  |  | -20.03d | Yes | Yes | Yes | No | No | 1.2.3.2.44 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.44.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Fri 6/12/26 | Fri 6/12/26 | Eric Heisler | 1269 | 1272 |  | NA | VC_Variant Tables Content | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.43.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.44.2 | NA | 3219 | 3217 | 3220 | -160.27h | No | Yes | Yes | No | No | 1.2.3.2.44.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.44.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 6/12/26 | Mon 6/15/26 | Eric Heisler | 1271 |  | Matt Palastro, Dave Duda | NA | VC_Variant Tables Content | Fri 6/12/26 | Mon 6/15/26 | 1.2.3.2.44.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3220 | 3219 |  | -160.27h | No | Yes | Yes | No | No | 1.2.3.2.44.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.45 | Auto Scheduled | 0% | VC_Characteristic Groups | No | 1.97d | Fri 6/12/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Fri 6/12/26 | Tue 6/16/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3221 |  |  | -20.75d | Yes | Yes | Yes | No | No | 1.2.3.2.45 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.45.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 12.75h | Fri 6/12/26 | Mon 6/15/26 | Eric Heisler | 1266 | 1275 |  | NA | VC_Characteristic Groups | Fri 6/12/26 | Mon 6/15/26 | 1.2.3.2.42.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.45.2 | NA | 3222 | 3214 | 3223 | -166.02h | No | Yes | Yes | No | No | 1.2.3.2.45.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.45.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 6/15/26 | Tue 6/16/26 | Eric Heisler | 1274 |  | Matt Palastro, Dave Duda | NA | VC_Characteristic Groups | Mon 6/15/26 | Tue 6/16/26 | 1.2.3.2.45.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3223 | 3222 |  | -166.02h | No | Yes | Yes | No | No | 1.2.3.2.45.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.46 | Auto Scheduled | 0% | PTM_CM52_Super_BOM | No | 2d | Thu 6/11/26 | Mon 6/15/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Mon 6/15/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3224 |  |  | -23.41d | Yes | Yes | Yes | No | No | 1.2.3.2.46 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.46.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Eric Heisler | 1178 | 1278 |  | NA | PTM_CM52_Super_BOM | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.46.2 | NA | 3225 | 3126 | 3226 | -11236m | No | Yes | Yes | No | No | 1.2.3.2.46.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.46.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 6/11/26 | Thu 6/11/26 | Eric Heisler | 1277 | 1279 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.46.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.46.3 | NA | 3226 | 3225 | 3227 | -11236m | No | Yes | Yes | No | No | 1.2.3.2.46.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.46.3 | Auto Scheduled | 0% | Simulate Load | No | 8h | Thu 6/11/26 | Fri 6/12/26 | Data Migration Team | 1278 | 1280 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Thu 6/11/26 | Fri 6/12/26 | 1.2.3.2.46.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.46.4 | NA | 3227 | 3226 | 3228 | -187.27h | No | Yes | Yes | No | No | 1.2.3.2.46.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.46.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 6/12/26 | Fri 6/12/26 | Eric Heisler | 1279 | 1281 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.46.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.46.5 | NA | 3228 | 3227 | 3229 | -187.27h | No | Yes | Yes | No | No | 1.2.3.2.46.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.46.5 | Auto Scheduled | 0% | Load | No | 2h | Fri 6/12/26 | Mon 6/15/26 | Data Migration Team | 1280 | 1282 |  | NA | PTM_CM52_Super_BOM | Fri 6/12/26 | Mon 6/15/26 | 1.2.3.2.46.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.46.6 | NA | 3229 | 3228 | 3230 | -187.27h | No | Yes | Yes | No | No | 1.2.3.2.46.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.46.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 6/15/26 | Mon 6/15/26 | Eric Heisler | 1281 | 1284 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.46.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.47.1 | NA | 3230 | 3229 | 3232 | -187.27h | No | Yes | Yes | No | No | 1.2.3.2.46.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.47 | Auto Scheduled | 0% | PTM_CM53_Super_Routing | No | 2.13d | Mon 6/15/26 | Wed 6/17/26 |  |  |  |  | NA | Master Data Loads | Mon 6/15/26 | Wed 6/17/26 |  | Thu 4/16/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 3231 |  |  | -23.41d | Yes | Yes | Yes | No | No | 1.2.3.2.47 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.47.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 6/15/26 | Mon 6/15/26 | Eric Heisler | 1282 | 1285 |  | NA | PTM_CM53_Super_Routing | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.46.6 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.47.2 | NA | 3232 | 3230 | 3233 | -11236m | No | Yes | Yes | No | No | 1.2.3.2.47.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.47.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 6/15/26 | Mon 6/15/26 | Eric Heisler | 1284 | 1286 | Matt Palastro, Dave Duda | NA | PTM_CM53_Super_Routing | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.47.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.47.3 | NA | 3233 | 3232 | 3234 | -11236m | No | Yes | Yes | No | No | 1.2.3.2.47.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.47.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 6/15/26 | Tue 6/16/26 | Data Migration Team | 1285 | 1287 |  | NA | PTM_CM53_Super_Routing | Mon 6/15/26 | Tue 6/16/26 | 1.2.3.2.47.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.47.4 | NA | 3234 | 3233 | 3235 | -187.27h | No | Yes | Yes | No | No | 1.2.3.2.47.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.47.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 6/16/26 | Tue 6/16/26 | Eric Heisler | 1286 | 1288 | Matt Palastro, Dave Duda | NA | PTM_CM53_Super_Routing | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.47.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.47.5 | NA | 3235 | 3234 | 3236 | -187.27h | No | Yes | Yes | No | No | 1.2.3.2.47.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.47.5 | Auto Scheduled | 0% | Load | No | 2h | Tue 6/16/26 | Wed 6/17/26 | Data Migration Team | 1287 | 12891291 |  | NA | PTM_CM53_Super_Routing | Tue 6/16/26 | Wed 6/17/26 | 1.2.3.2.47.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.47.6,1.2.3.2.48.1 | NA | 3236 | 3235 | 32373239 | -187.27h | No | Yes | Yes | No | No | 1.2.3.2.47.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.47.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 6/17/26 | Wed 6/17/26 | Eric Heisler | 1288 |  | Matt Palastro, Dave Duda | NA | PTM_CM53_Super_Routing | Wed 6/17/26 | Wed 6/17/26 | 1.2.3.2.47.5 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 3237 | 3236 |  | -178.27h | No | Yes | Yes | No | No | 1.2.3.2.47.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.48 | Auto Scheduled | 0% | VC_VK30 Pricing Variant | No | 0.69d | Wed 6/17/26 | Wed 6/17/26 |  |  |  |  | NA | Master Data Loads | Wed 6/17/26 | Wed 6/17/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 3238 |  |  | -23.41d | Yes | Yes | Yes | No | No | 1.2.3.2.48 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.48.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Wed 6/17/26 | Wed 6/17/26 | Eric Heisler | 1288 | 1292 | Matt Palastro, Dave Duda | NA | VC_VK30 Pricing Variant | Wed 6/17/26 | Wed 6/17/26 | 1.2.3.2.47.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.48.2 | NA | 3239 | 3236 | 3240 | -11236m | No | Yes | Yes | No | No | 1.2.3.2.48.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.48.2 | Auto Scheduled | 0% | Load | No | 2h | Wed 6/17/26 | Wed 6/17/26 | Eric Heisler | 1291 | 1293 |  | NA | VC_VK30 Pricing Variant | Wed 6/17/26 | Wed 6/17/26 | 1.2.3.2.48.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.48.3 | NA | 3240 | 3239 | 3241 | -187.27h | No | Yes | Yes | No | No | 1.2.3.2.48.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.48.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 6/17/26 | Wed 6/17/26 | Eric Heisler | 1292 | 1295 | Matt Palastro, Dave Duda | NA | VC_VK30 Pricing Variant | Wed 6/17/26 | Wed 6/17/26 | 1.2.3.2.48.2 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.49.1 | NA | 3241 | 3240 | 3243 | -187.27h | No | Yes | Yes | No | No | 1.2.3.2.48.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.49 | Auto Scheduled | 0% | OTC_CM22_Pricing_Condition | No | 0.69d | Wed 6/17/26 | Thu 6/18/26 |  |  |  |  | NA | Master Data Loads | Wed 6/17/26 | Thu 6/18/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 3242 |  |  | -23.41d | Yes | Yes | Yes | No | No | 1.2.3.2.49 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.49.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Wed 6/17/26 | Wed 6/17/26 | Ric Haraida | 1293 | 1296 | Matt Palastro, Dave Duda | NA | OTC_CM22_Pricing_Condition | Wed 6/17/26 | Wed 6/17/26 | 1.2.3.2.48.3 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.49.2 | NA | 3243 | 3241 | 3244 | -11236m | No | Yes | Yes | No | No | 1.2.3.2.49.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.49.2 | Auto Scheduled | 0% | Load | No | 2h | Wed 6/17/26 | Thu 6/18/26 | Ric Haraida | 1295 | 12971299 |  | NA | OTC_CM22_Pricing_Condition | Wed 6/17/26 | Thu 6/18/26 | 1.2.3.2.49.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.49.3,1.2.3.2.50.1 | NA | 3244 | 3243 | 32453247 | -187.27h | No | Yes | Yes | No | No | 1.2.3.2.49.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.49.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 6/18/26 | Thu 6/18/26 | Ric Haraida,Kim Kolesar | 1296 |  | Matt Palastro, Dave Duda,kim | NA | OTC_CM22_Pricing_Condition | Thu 6/18/26 | Thu 6/18/26 | 1.2.3.2.49.2 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 3245 | 3244 |  | -186.27h | No | Yes | Yes | No | No | 1.2.3.2.49.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.50 | Auto Scheduled | 0% | OTC_CM21_CMIR | No | 0.5d | Thu 6/18/26 | Thu 6/18/26 |  |  |  |  | NA | Master Data Loads | Thu 6/18/26 | Thu 6/18/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 3246 |  |  | -23.41d | Yes | Yes | Yes | No | No | 1.2.3.2.50 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.50.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 6/18/26 | Thu 6/18/26 | Ric Haraida | 12961307 | 1300 |  | NA | OTC_CM21_CMIR | Thu 6/18/26 | Thu 6/18/26 | 1.2.3.2.49.2,1.2.3.2.51.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.50.2 | NA | 3247 | 32443255 | 3248 | -11236m | No | Yes | Yes | No | No | 1.2.3.2.50.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.50.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 6/18/26 | Thu 6/18/26 | Ric Haraida | 1299 | 1301 | Kim | NA | OTC_CM21_CMIR | Thu 6/18/26 | Thu 6/18/26 | 1.2.3.2.50.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.50.3 | NA | 3248 | 3247 | 3249 | -11236m | No | Yes | Yes | No | No | 1.2.3.2.50.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.50.3 | Auto Scheduled | 0% | Simulate Load | No | 0h | Thu 6/18/26 | Thu 6/18/26 | Data Migration Team | 1300 | 1302 |  | NA | OTC_CM21_CMIR | Thu 6/18/26 | Thu 6/18/26 | 1.2.3.2.50.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.3.2.50.4 | NA | 3249 | 3248 | 3250 | -187.27h | No | Yes | Yes | Yes | No | 1.2.3.2.50.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.50.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 0h | Thu 6/18/26 | Thu 6/18/26 | Ric Haraida | 1301 | 1303 | Kim | NA | OTC_CM21_CMIR | Thu 6/18/26 | Thu 6/18/26 | 1.2.3.2.50.3 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible | 1.2.3.2.50.5 | NA | 3250 | 3249 | 3251 | -187.27h | No | Yes | Yes | Yes | No | 1.2.3.2.50.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.50.5 | Auto Scheduled | 0% | Load | No | 0h | Thu 6/18/26 | Thu 6/18/26 | Data Migration Team | 1302 | 1304 |  | NA | OTC_CM21_CMIR | Thu 6/18/26 | Thu 6/18/26 | 1.2.3.2.50.4 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible | 1.2.3.2.50.6 | NA | 3251 | 3250 | 3252 | -187.27h | No | Yes | Yes | Yes | No | 1.2.3.2.50.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.50.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 6/18/26 | Thu 6/18/26 | Ric Haraida | 1303 |  | Kim | NA | OTC_CM21_CMIR | Thu 6/18/26 | Thu 6/18/26 | 1.2.3.2.50.5 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 3252 | 3251 |  | -187.27h | No | Yes | Yes | No | No | 1.2.3.2.50.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.51 | Auto Scheduled | 0% | PTP_CM29_Source_List | No | 6.16d | Tue 6/9/26 | Wed 6/17/26 |  |  |  |  | NA | Master Data Loads | Tue 6/9/26 | Wed 6/17/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 3253 |  |  | -22.22d | Yes | Yes | Yes | No | No | 1.2.3.2.51 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.51.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Tue 6/9/26 | Tue 6/9/26 | Nevin Varkey | 11491156 |  | Sam | NA | PTP_CM29_Source_List | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.22.5,1.2.3.2.23.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 3254 | 30973104 |  | -7741m | No | Yes | Yes | No | No | 1.2.3.2.51.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.51.2 | Auto Scheduled | 0% | Load | No | 2h | Tue 6/16/26 | Wed 6/17/26 | Nevin Varkey | 1125 | 12991308 |  | NA | PTP_CM29_Source_List | Tue 6/16/26 | Wed 6/17/26 | 1.2.3.2.18.6 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.50.1,1.2.3.2.51.3 | NA | 3255 | 3073 | 32473256 | -178.77h | No | Yes | Yes | No | No | 1.2.3.2.51.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.51.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 6/17/26 | Wed 6/17/26 | Nevin Varkey | 1307 |  | Sam | NA | PTP_CM29_Source_List | Wed 6/17/26 | Wed 6/17/26 | 1.2.3.2.51.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3256 | 3255 |  | -177.77h | No | Yes | Yes | No | No | 1.2.3.2.51.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.52 | Auto Scheduled | 0% | RTR_CM11_Asset_Master | No | 3.75d | Mon 6/8/26 | Thu 6/11/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Thu 6/11/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3257 |  |  | -18.69d | Yes | Yes | Yes | No | No | 1.2.3.2.52 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.52.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 6/8/26 | Mon 6/8/26 | Kasey Hughes |  | 13111365 |  | NA | RTR_CM11_Asset_Master | Mon 6/8/26 | Mon 6/8/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.52.2,1.2.3.2.67.1 | NA | 3258 |  | 32593313 | -8971m | No | Yes | Yes | No | No | 1.2.3.2.52.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.52.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 6/8/26 | Mon 6/8/26 | Kasey Hughes,Femi Oguntala | 1310 | 1312 | Brian Wagner | NA | RTR_CM11_Asset_Master | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.52.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.52.3 | NA | 3259 | 3258 | 3260 | -8971m | No | Yes | Yes | No | No | 1.2.3.2.52.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.52.3 | Auto Scheduled | 0% | Simulate Load | No | 8h | Mon 6/8/26 | Tue 6/9/26 | Data Migration Team | 1311 | 1313 |  | NA | RTR_CM11_Asset_Master | Mon 6/8/26 | Tue 6/9/26 | 1.2.3.2.52.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.52.4 | NA | 3260 | 3259 | 3261 | -149.52h | No | Yes | Yes | No | No | 1.2.3.2.52.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.52.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 16h | Tue 6/9/26 | Thu 6/11/26 | Kasey Hughes | 1312 | 1314 | Brian Wagner | NA | RTR_CM11_Asset_Master | Tue 6/9/26 | Thu 6/11/26 | 1.2.3.2.52.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.52.5 | NA | 3261 | 3260 | 3262 | -149.52h | No | Yes | Yes | No | No | 1.2.3.2.52.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.52.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 6/11/26 | Thu 6/11/26 | Data Migration Team | 1313 | 1315 |  | NA | RTR_CM11_Asset_Master | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.52.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.52.6 | NA | 3262 | 3261 | 3263 | -149.52h | No | Yes | Yes | No | No | 1.2.3.2.52.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.52.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 6/11/26 | Thu 6/11/26 | Kasey Hughes | 1314 |  | Brian Wagner | NA | RTR_CM11_Asset_Master | Thu 6/11/26 | Thu 6/11/26 | 1.2.3.2.52.5 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3263 | 3262 |  | -149.52h | No | Yes | Yes | No | No | 1.2.3.2.52.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.53 | Auto Scheduled | 0% | PTM_CM50_Material Class | No | 2.13d | Fri 6/12/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Fri 6/12/26 | Tue 6/16/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3264 |  |  | -20.85d | Yes | Yes | Yes | No | No | 1.2.3.2.53 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.53.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Fri 6/12/26 | Fri 6/12/26 | Sam | 1222 | 13181321 |  | NA | PTM_CM50_Material Class | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.33.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.53.2,1.2.3.2.54.1 | NA | 3265 | 3170 | 32663269 | -10006m | No | Yes | Yes | No | No | 1.2.3.2.53.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.53.2 | Auto Scheduled | 0% | Load | No | 30m | Fri 6/12/26 | Fri 6/12/26 | Brad Meseck | 1317 | 1319 | Matt Palastro, Dave Duda | NA | PTM_CM50_Material Class | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.53.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.53.3 | NA | 3266 | 3265 | 3267 | -10006m | No | Yes | Yes | No | No | 1.2.3.2.53.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.53.3 | Auto Scheduled | 0% | Post Load Validation | No | 16h | Fri 6/12/26 | Tue 6/16/26 | Brad | 1318 |  | brad | NA | PTM_CM50_Material Class | Fri 6/12/26 | Tue 6/16/26 | 1.2.3.2.53.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3267 | 3266 |  | -166.77h | No | Yes | Yes | No | No | 1.2.3.2.53.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.54 | Auto Scheduled | 0% | PTM_CM55_Class assignment to materials | No | 1.13d | Fri 6/12/26 | Mon 6/15/26 |  |  |  |  | NA | Master Data Loads | Fri 6/12/26 | Mon 6/15/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3268 |  |  | -19.91d | Yes | Yes | Yes | No | No | 1.2.3.2.54 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.54.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Fri 6/12/26 | Fri 6/12/26 | Sam | 1317 | 1322 |  | NA | PTM_CM55_Class assignment to materials | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.53.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.54.2 | NA | 3269 | 3265 | 3270 | -9556m | No | Yes | Yes | No | No | 1.2.3.2.54.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.54.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Fri 6/12/26 | Fri 6/12/26 | Brad Meseck | 1321 | 1323 | Matt Palastro, Dave Duda | NA | PTM_CM55_Class assignment to materials | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.54.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.54.3 | NA | 3270 | 3269 | 3271 | -9556m | No | Yes | Yes | No | No | 1.2.3.2.54.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.54.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 6/12/26 | Fri 6/12/26 | Data Migration Team | 1322 | 1324 |  | NA | PTM_CM55_Class assignment to materials | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.54.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.54.4 | NA | 3271 | 3270 | 3272 | -159.27h | No | Yes | Yes | No | No | 1.2.3.2.54.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.54.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 6/12/26 | Fri 6/12/26 | Brad Meseck | 1323 | 1325 | Matt Palastro, Dave Duda | NA | PTM_CM55_Class assignment to materials | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.54.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.54.5 | NA | 3272 | 3271 | 3273 | -159.27h | No | Yes | Yes | No | No | 1.2.3.2.54.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.54.5 | Auto Scheduled | 0% | Load | No | 2h | Fri 6/12/26 | Fri 6/12/26 | Data Migration Team | 1324 | 1326 |  | NA | PTM_CM55_Class assignment to materials | Fri 6/12/26 | Fri 6/12/26 | 1.2.3.2.54.4 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.54.6 | NA | 3273 | 3272 | 3274 | -159.27h | No | Yes | Yes | No | No | 1.2.3.2.54.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.54.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 6/12/26 | Mon 6/15/26 | Brad Meseck | 1325 |  | Matt Palastro, Dave Duda | NA | PTM_CM55_Class assignment to materials | Fri 6/12/26 | Mon 6/15/26 | 1.2.3.2.54.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3274 | 3273 |  | -159.27h | No | Yes | Yes | No | No | 1.2.3.2.54.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.55 | Auto Scheduled | 0% | GTS - Material initial load from S4 (Run Interface) | No | 2.09d | Thu 6/11/26 | Mon 6/15/26 |  |  |  |  | NA | Master Data Loads | Thu 6/11/26 | Mon 6/15/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3275 |  |  | -23.78d | Yes | Yes | Yes | No | No | 1.2.3.2.55 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.55.1 | Auto Scheduled | 0% | Run material interface to GTS | No | 15.75h | Thu 6/11/26 | Mon 6/15/26 | James Van Riper | 1196 | 1329 |  | NA | GTS - Material initial load from S4 (Run Interface) | Thu 6/11/26 | Mon 6/15/26 | 1.2.3.2.29.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.55.2 | NA | 3276 | 3144 | 3277 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.55.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.55.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Mon 6/15/26 | Mon 6/15/26 | James Van Riper | 1328 | 1340 | Kim Kolesar | NA | GTS - Material initial load from S4 (Run Interface) | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.55.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.59.1 | NA | 3277 | 3276 | 3288 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.55.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.56 | Auto Scheduled | 0% | GTS - Customers initial load from S4 (Run Interface) | No | 0.25d | Mon 6/8/26 | Mon 6/8/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Mon 6/8/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 3278 |  |  | -15.19d | Yes | Yes | Yes | No | No | 1.2.3.2.56 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.56.1 | Auto Scheduled | 0% | Run material interface to GTS | No | 1h | Mon 6/8/26 | Mon 6/8/26 | James Van Riper |  | 1332 |  | NA | GTS - Customers initial load from S4 (Run Interface) | Mon 6/8/26 | Mon 6/8/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.56.2 | NA | 3279 |  | 3280 | -121.52h | No | Yes | Yes | No | No | 1.2.3.2.56.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.56.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Mon 6/8/26 | Mon 6/8/26 | James Van Riper | 1331 |  | Kim Kolesar | NA | GTS - Customers initial load from S4 (Run Interface) | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.56.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 3280 | 3279 |  | -121.52h | No | Yes | Yes | No | No | 1.2.3.2.56.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.57 | Auto Scheduled | 0% | GTS - Vendors initial load from S4 (Run Interface) | No | 0.25d | Tue 6/9/26 | Tue 6/9/26 |  |  |  |  | NA | Master Data Loads | Tue 6/9/26 | Tue 6/9/26 |  | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 3281 |  |  | -16.44d | Yes | Yes | Yes | No | No | 1.2.3.2.57 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.57.1 | Auto Scheduled | 0% | Run material interface to GTS | No | 1h | Tue 6/9/26 | Tue 6/9/26 | James Van Riper | 1139 | 13351338 |  | NA | GTS - Vendors initial load from S4 (Run Interface) | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.20.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.3.2.57.2,1.2.3.2.58.2 | NA | 3282 | 3087 | 32833286 | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.57.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.57.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 6/9/26 | Tue 6/9/26 | James Van Riper | 1334 |  | Kim Kolesar | NA | GTS - Vendors initial load from S4 (Run Interface) | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.57.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 3283 | 3282 |  | -128.52h | No | Yes | Yes | No | No | 1.2.3.2.57.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.58 | Auto Scheduled | 0% | GTS - ECCN - Create | No | 1.13d | Mon 6/8/26 | Tue 6/9/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Tue 6/9/26 |  | Mon 4/6/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 3284 |  |  | -16.06d | Yes | Yes | Yes | No | No | 1.2.3.2.58 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.58.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Mon 6/8/26 | Mon 6/8/26 | James Van Riper |  |  |  | NA | GTS - ECCN - Create | Mon 6/8/26 | Mon 6/8/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 3285 |  |  | -120.52h | No | Yes | Yes | No | No | 1.2.3.2.58.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.58.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 6/9/26 | Tue 6/9/26 | James Van Riper | 1334 | 1358 | Kim Kolesar | NA | GTS - ECCN - Create | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.57.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.65.1 | NA | 3286 | 3282 | 3306 | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.58.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.59 | Auto Scheduled | 0% | GTS - ECCN - Assign | No | 0.25d | Mon 6/15/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Mon 6/15/26 | Tue 6/16/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3287 |  |  | -23.78d | Yes | Yes | Yes | No | No | 1.2.3.2.59 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.59.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Mon 6/15/26 | Mon 6/15/26 | James Van Riper | 1329 | 1341 |  | NA | GTS - ECCN - Assign | Mon 6/15/26 | Mon 6/15/26 | 1.2.3.2.55.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.59.2 | NA | 3288 | 3277 | 3289 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.59.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.59.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Mon 6/15/26 | Tue 6/16/26 | James Van Riper | 1340 | 1346 | Kim Kolesar | NA | GTS - ECCN - Assign | Mon 6/15/26 | Tue 6/16/26 | 1.2.3.2.59.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.61.1 | NA | 3289 | 3288 | 3294 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.59.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.60 | Auto Scheduled | 0% | GTS - HTS - Create | No | 0.25d | Mon 6/8/26 | Mon 6/8/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Mon 6/8/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 3290 |  |  | -15.19d | Yes | Yes | Yes | No | No | 1.2.3.2.60 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.60.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Mon 6/8/26 | Mon 6/8/26 | James Van Riper |  | 1344 |  | NA | GTS - HTS - Create | Mon 6/8/26 | Mon 6/8/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.3.2.60.2 | NA | 3291 |  | 3292 | -121.52h | No | Yes | Yes | No | No | 1.2.3.2.60.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.60.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Mon 6/8/26 | Mon 6/8/26 | James Van Riper | 1343 |  | Kim Kolesar | NA | GTS - HTS - Create | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.60.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 3292 | 3291 |  | -121.52h | No | Yes | Yes | No | No | 1.2.3.2.60.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.61 | Auto Scheduled | 0% | GTS - HTS - Assign | No | 0.25d | Tue 6/16/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Tue 6/16/26 | Tue 6/16/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3293 |  |  | -23.78d | Yes | Yes | Yes | No | No | 1.2.3.2.61 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.61.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Tue 6/16/26 | Tue 6/16/26 | James Van Riper | 1341 | 134713491355 |  | NA | GTS - HTS - Assign | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.59.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.61.2,1.2.3.2.62.1,1.2.3.2.64.1 | NA | 3294 | 3289 | 329532973303 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.61.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.61.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 6/16/26 | Tue 6/16/26 | James Van Riper | 1346 | 13621352 | Kim Kolesar | NA | GTS - HTS - Assign | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.61.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.66.1,1.2.3.2.63.1 | NA | 3295 | 3294 | 33103300 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.61.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.62 | Auto Scheduled | 0% | GTS - License - Create | No | 0.25d | Tue 6/16/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Tue 6/16/26 | Tue 6/16/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3296 |  |  | -21.38d | Yes | Yes | Yes | No | No | 1.2.3.2.62 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.62.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Tue 6/16/26 | Tue 6/16/26 | James Van Riper | 13461362 | 1350 |  | NA | GTS - License - Create | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.61.1,1.2.3.2.66.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.62.2 | NA | 3297 | 32943310 | 3298 | -171.02h | No | Yes | Yes | No | No | 1.2.3.2.62.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.62.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 6/16/26 | Tue 6/16/26 | James Van Riper | 1349 |  | Kim Kolesar | NA | GTS - License - Create | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.62.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3298 | 3297 |  | -171.02h | No | Yes | Yes | No | No | 1.2.3.2.62.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.63 | Auto Scheduled | 0% | Commodity Code/Tarif | No | 2.78d | Tue 6/16/26 | Fri 6/19/26 |  |  |  |  | NA | Master Data Loads | Tue 6/16/26 | Fri 6/19/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3299 |  |  | -23.78d | Yes | Yes | Yes | No | No | 1.2.3.2.63 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.63.1 | Auto Scheduled | 0% | Load | No | 21.25h | Tue 6/16/26 | Thu 6/18/26 | James Van Riper | 1347 | 1353 |  | NA | Commodity Code/Tarif | Tue 6/16/26 | Thu 6/18/26 | 1.2.3.2.61.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.63.2 | NA | 3300 | 3295 | 3301 | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.63.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.63.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Thu 6/18/26 | Fri 6/19/26 | James Van Riper | 1352 |  | Kim Kolesar | NA | Commodity Code/Tarif | Thu 6/18/26 | Fri 6/19/26 | 1.2.3.2.63.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3301 | 3300 |  | -190.27h | No | Yes | Yes | No | No | 1.2.3.2.63.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.64 | Auto Scheduled | 0% | SPL Master File | No | 0.25d | Tue 6/16/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Tue 6/16/26 | Tue 6/16/26 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 3302 |  |  | -21.13d | Yes | Yes | Yes | No | No | 1.2.3.2.64 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.64.1 | Auto Scheduled | 0% | Load | No | 1h | Tue 6/16/26 | Tue 6/16/26 | James Van Riper | 1346 | 1356 |  | NA | SPL Master File | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.61.1 | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible | 1.2.3.2.64.2 | NA | 3303 | 3294 | 3304 | -169.02h | No | Yes | Yes | No | No | 1.2.3.2.64.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.64.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 6/16/26 | Tue 6/16/26 | James Van Riper | 1355 |  | Kim Kolesar | NA | SPL Master File | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.64.1 | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 3304 | 3303 |  | -169.02h | No | Yes | Yes | No | No | 1.2.3.2.64.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.65 | Auto Scheduled | 0% | Initialize Embargo situation | No | 0.38d | Tue 6/9/26 | Tue 6/9/26 |  |  |  |  | NA | Master Data Loads | Tue 6/9/26 | Tue 6/9/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 3305 |  |  | -16.44d | Yes | Yes | Yes | No | No | 1.2.3.2.65 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.65.1 | Auto Scheduled | 0% | Run report /SAPSLL/EMB_CNTRY_INIT | No | 1h | Tue 6/9/26 | Tue 6/9/26 | James Van Riper | 1338 | 1359 |  | NA | Initialize Embargo situation | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.58.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.65.2 | NA | 3306 | 3286 | 3307 | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.65.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.65.2 | Auto Scheduled | 0% | Set Embargo situations | No | 1h | Tue 6/9/26 | Tue 6/9/26 | James Van Riper | 1358 | 1360 |  | NA | Initialize Embargo situation | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.65.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.3.2.65.3 | NA | 3307 | 3306 | 3308 | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.65.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.65.3 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 6/9/26 | Tue 6/9/26 | James Van Riper | 1359 |  | Kim Kolesar | NA | Initialize Embargo situation | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.65.2 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 3308 | 3307 |  | -131.52h | No | Yes | Yes | No | No | 1.2.3.2.65.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.66 | Auto Scheduled | 0% | GTS - SPL (Sanctioned party list) | No | 0.25d | Tue 6/16/26 | Tue 6/16/26 |  |  |  |  | NA | Master Data Loads | Tue 6/16/26 | Tue 6/16/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3309 |  |  | -21.38d | Yes | Yes | Yes | No | No | 1.2.3.2.66 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.66.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Tue 6/16/26 | Tue 6/16/26 | James Van Riper | 1347 | 13491363 |  | NA | GTS - SPL (Sanctioned party list) | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.61.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.62.1,1.2.3.2.66.2 | NA | 3310 | 3295 | 32973311 | -171.02h | No | Yes | Yes | No | No | 1.2.3.2.66.1 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.66.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 6/16/26 | Tue 6/16/26 | James Van Riper | 1362 |  | Kim Kolesar | NA | GTS - SPL (Sanctioned party list) | Tue 6/16/26 | Tue 6/16/26 | 1.2.3.2.66.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 3311 | 3310 |  | -170.02h | No | Yes | Yes | No | No | 1.2.3.2.66.2 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.67 | Auto Scheduled | 0% | RTR_CM17_Project Definition / Builder | No | 1.13d | Mon 6/8/26 | Tue 6/9/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Tue 6/9/26 |  | Fri 4/10/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3312 |  |  | -16.19d | Yes | Yes | Yes | No | No | 1.2.3.2.67 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.67.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 6/8/26 | Mon 6/8/26 | Kasey Hughes | 1310 | 13661372 |  | NA | RTR_CM17_Project Definition / Builder | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.52.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.67.2,1.2.3.2.68.1 | NA | 3313 | 3258 | 33143320 | -7771m | No | Yes | Yes | No | No | 1.2.3.2.67.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.67.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 6/8/26 | Mon 6/8/26 | Kasey Hughes | 1365 | 1367 | Brian Wagner | NA | RTR_CM17_Project Definition / Builder | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.67.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.67.3 | NA | 3314 | 3313 | 3315 | -7741m | No | Yes | Yes | No | No | 1.2.3.2.67.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.67.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 6/8/26 | Mon 6/8/26 | Data Migration Team | 1366 | 1368 |  | NA | RTR_CM17_Project Definition / Builder | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.67.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.67.4 | NA | 3315 | 3314 | 3316 | -129.02h | No | Yes | Yes | No | No | 1.2.3.2.67.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.67.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 6/8/26 | Mon 6/8/26 | Kasey Hughes | 1367 | 1369 | Brian Wagner | NA | RTR_CM17_Project Definition / Builder | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.67.3 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.67.5 | NA | 3316 | 3315 | 3317 | -129.02h | No | Yes | Yes | No | No | 1.2.3.2.67.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.67.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 6/8/26 | Tue 6/9/26 | Data Migration Team | 1368 | 1370 |  | NA | RTR_CM17_Project Definition / Builder | Mon 6/8/26 | Tue 6/9/26 | 1.2.3.2.67.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.67.6 | NA | 3317 | 3316 | 3318 | -129.02h | No | Yes | Yes | No | No | 1.2.3.2.67.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.67.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1369 |  | Brian Wagner | NA | RTR_CM17_Project Definition / Builder | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.67.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3318 | 3317 |  | -129.02h | No | Yes | Yes | No | No | 1.2.3.2.67.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.68 | Auto Scheduled | 0% | RTR_CM18_WBS Element | No | 1.13d | Mon 6/8/26 | Tue 6/9/26 |  |  |  |  | NA | Master Data Loads | Mon 6/8/26 | Tue 6/9/26 |  | Fri 4/10/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3319 |  |  | -16.19d | Yes | Yes | Yes | No | No | 1.2.3.2.68 | 5 | No | 500 | Future Task | No | 0d
1.2.3.2.68.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 6/8/26 | Mon 6/8/26 | Kasey Hughes | 1365 | 1373 |  | NA | RTR_CM18_WBS Element | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.67.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.68.2 | NA | 3320 | 3313 | 3321 | -7771m | No | Yes | Yes | No | No | 1.2.3.2.68.1 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.68.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 6/8/26 | Mon 6/8/26 | Kasey Hughes | 1372 | 1374 | Brian Wagner | NA | RTR_CM18_WBS Element | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.68.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.3.2.68.3 | NA | 3321 | 3320 | 3322 | -7771m | No | Yes | Yes | No | No | 1.2.3.2.68.2 | 6 | No | 500 | Future Task | No | 0m
1.2.3.2.68.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 6/8/26 | Mon 6/8/26 | Data Migration Team | 1373 | 1375 |  | NA | RTR_CM18_WBS Element | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.68.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.3.2.68.4 | NA | 3322 | 3321 | 3323 | -129.52h | No | Yes | Yes | No | No | 1.2.3.2.68.3 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.68.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 6/8/26 | Mon 6/8/26 | Kasey Hughes | 1374 | 1376 | Brian Wagner | NA | RTR_CM18_WBS Element | Mon 6/8/26 | Mon 6/8/26 | 1.2.3.2.68.3 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.68.5 | NA | 3323 | 3322 | 3324 | -129.52h | No | Yes | Yes | No | No | 1.2.3.2.68.4 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.68.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 6/8/26 | Tue 6/9/26 | Data Migration Team | 1375 | 1377 |  | NA | RTR_CM18_WBS Element | Mon 6/8/26 | Tue 6/9/26 | 1.2.3.2.68.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.3.2.68.6 | NA | 3324 | 3323 | 3325 | -129.52h | No | Yes | Yes | No | No | 1.2.3.2.68.5 | 6 | No | 500 | Future Task | No | 0h
1.2.3.2.68.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 6/9/26 | Tue 6/9/26 | Kasey Hughes | 1376 |  | Brian Wagner | NA | RTR_CM18_WBS Element | Tue 6/9/26 | Tue 6/9/26 | 1.2.3.2.68.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 3325 | 3324 |  | -129.52h | No | Yes | Yes | No | No | 1.2.3.2.68.6 | 6 | No | 500 | Future Task | No | 0h
1.2.3.3 | Auto Scheduled | 0% | ITC3 Master Data Loads Complete | No | 0m | Fri 6/19/26 | Fri 6/19/26 |  | 1011 | 21861379 |  | NA | ITC3 Data Load Tasks QS5 | Fri 6/19/26 | Fri 6/19/26 | 1.2.3.2 | NA | NA | As Soon As Possible | 1.3.3.7.1,1.2.3.4 | NA | 2958 | 2959 | 9223326 | -11791m | No | Yes | Yes | Yes | No | 1.2.3.3 | 4 | No | 500 | Future Task | No | 0m
1.2.3.4 | Auto Scheduled | 0% | Mock Transactional Data | No | 2d | Fri 6/19/26 | Tue 6/23/26 |  | 1378 | 1388 |  | NA | ITC3 Data Load Tasks QS5 | Fri 6/19/26 | Tue 6/23/26 | 1.2.3.3 | NA | NA | As Soon As Possible | 1.2.3.5 | NA | 3326 | 2958 | 2421 | -24.56d | Yes | Yes | Yes | No | No | 1.2.3.4 | 4 | No | 500 | Future Task | No | 0d
1.2.3.4.1 | Auto Scheduled | 0% | Inventory | No | 4h | Fri 6/19/26 | Mon 6/22/26 |  | 998SS | 1.3811e+19 |  | NA | Mock Transactional Data | Fri 6/19/26 | Mon 6/22/26 | 1.2.2.3[SS] | NA | NA | As Soon As Possible | 1.2.3.4.2,1.2.3.4.5,1.2.3.4.6,1.2.3.4.7,1.2.3.4.8 | NA | 3330 | 2947SS | 3.3313e+19 | -196.52h | No | Yes | Yes | No | No | 1.2.3.4.1 | 5 | No | 500 | Future Task | No | 0h
1.2.3.4.2 | Auto Scheduled | 0% | Open AR | No | 4h | Mon 6/22/26 | Mon 6/22/26 |  | 1380 | 1382 |  | NA | Mock Transactional Data | Mon 6/22/26 | Mon 6/22/26 | 1.2.3.4.1 | NA | NA | As Soon As Possible | 1.2.3.4.3 | NA | 3331 | 3330 | 3332 | -196.52h | No | Yes | Yes | No | No | 1.2.3.4.2 | 5 | No | 500 | Future Task | No | 0h
1.2.3.4.3 | Auto Scheduled | 0% | Open AP | No | 4h | Mon 6/22/26 | Tue 6/23/26 |  | 1381 | 1383 |  | NA | Mock Transactional Data | Mon 6/22/26 | Tue 6/23/26 | 1.2.3.4.2 | NA | NA | As Soon As Possible | 1.2.3.4.4 | NA | 3332 | 3331 | 3333 | -196.52h | No | Yes | Yes | No | No | 1.2.3.4.3 | 5 | No | 500 | Future Task | No | 0h
1.2.3.4.4 | Auto Scheduled | 0% | Bank and Cash | No | 4h | Tue 6/23/26 | Tue 6/23/26 |  | 1382 |  |  | NA | Mock Transactional Data | Tue 6/23/26 | Tue 6/23/26 | 1.2.3.4.3 | NA | NA | As Soon As Possible |  | NA | 3333 | 3332 |  | -196.52h | No | Yes | Yes | No | No | 1.2.3.4.4 | 5 | No | 500 | Future Task | No | 0h
1.2.3.4.5 | Auto Scheduled | 0% | Open Purchase Orders(Manual) | No | 1d | Mon 6/22/26 | Tue 6/23/26 |  | 1380 |  |  | NA | Mock Transactional Data | Mon 6/22/26 | Tue 6/23/26 | 1.2.3.4.1 | NA | NA | As Soon As Possible |  | NA | 3334 | 3330 |  | -24.06d | No | Yes | Yes | No | No | 1.2.3.4.5 | 5 | No | 500 | Future Task | No | 0d
1.2.3.4.6 | Auto Scheduled | 0% | Open Sales Orders(Manual) | No | 1d | Mon 6/22/26 | Tue 6/23/26 |  | 1380 |  |  | NA | Mock Transactional Data | Mon 6/22/26 | Tue 6/23/26 | 1.2.3.4.1 | NA | NA | As Soon As Possible |  | NA | 3335 | 3330 |  | -24.06d | No | Yes | Yes | No | No | 1.2.3.4.6 | 5 | No | 500 | Future Task | No | 0d
1.2.3.4.7 | Auto Scheduled | 0% | Service Orders(Manual) | No | 0.5d | Mon 6/22/26 | Mon 6/22/26 |  | 1380 |  |  | NA | Mock Transactional Data | Mon 6/22/26 | Mon 6/22/26 | 1.2.3.4.1 | NA | NA | As Soon As Possible |  | NA | 3336 | 3330 |  | -23.56d | No | Yes | Yes | No | No | 1.2.3.4.7 | 5 | No | 500 | Future Task | No | 0d
1.2.3.4.8 | Auto Scheduled | 0% | Open Production Orders(Manual) | No | 1d | Mon 6/22/26 | Tue 6/23/26 |  | 1380 |  |  | NA | Mock Transactional Data | Mon 6/22/26 | Tue 6/23/26 | 1.2.3.4.1 | NA | NA | As Soon As Possible |  | NA | 3337 | 3330 |  | -24.06d | No | Yes | Yes | No | No | 1.2.3.4.8 | 5 | No | 500 | Future Task | No | 0d
1.2.3.5 | Auto Scheduled | 0% | ITC3 Mock Data Loads Complete | No | 0m | Tue 6/23/26 | Tue 6/23/26 | Mark George | 1379 | 2166 |  | NA | ITC3 Data Load Tasks QS5 | Tue 6/23/26 | Tue 6/23/26 | 1.2.3.4 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible | 1.3.3.3 | NA | 2421 | 3326 | 931 | -11791m | No | Yes | Yes | Yes | No | 1.2.3.5 | 4 | No | 500 | Future Task | No | 0m
1.2.4 | Auto Scheduled | 0% | UAT Data Load Tasks QS4 | No | 80.66d | Mon 6/22/26 | Mon 10/12/26 |  | 1009103134 |  |  | NA | Data Readiness | Mon 6/22/26 | Mon 10/12/26 | 1.2.3,1.1.1.7,1.1.1.8 | Thu 3/13/25 | Tue 4/21/26 | As Soon As Possible |  | NA | 2422 | 20538843367 |  | -40.66d | Yes | Yes | Yes | No | No | 1.2.4 | 3 | No | 500 | Future Task | No | 0d
1.2.4.1 | Auto Scheduled | 0% | PMO Authorization to Start Data Loads | No | 1m | Mon 6/22/26 | Mon 6/22/26 | Mark George | 103134 | 1.3932e+19 |  | NA | UAT Data Load Tasks QS4 | Mon 6/22/26 | Mon 6/22/26 | 1.1.1.7,1.1.1.8 | Mon 4/6/26 | Mon 4/6/26 | Start No Later Than | 1.2.4.2.1.1,1.2.4.2.37.1,1.2.4.2.58.1,1.2.4.2.60.1,1.2.4.2 | Mon 6/22/26 | 2423 | 8843367 | 2.4253e+19 | -32670m | No | Yes | Yes | No | No | 1.2.4.1 | 4 | No | 500 | Future Task | No | 0m
1.2.4.2 | Auto Scheduled | 0% | Master Data Loads | No | 10.56d | Thu 9/24/26 | Thu 10/8/26 |  | 1390 | 1759 |  | NA | UAT Data Load Tasks QS4 | Thu 9/24/26 | Thu 10/8/26 | 1.2.4.1 | NA | NA | As Soon As Possible | 1.2.4.3 | NA | 2898 | 2423 | 3360 | -90.75d | Yes | Yes | Yes | No | No | 1.2.4.2 | 4 | No | 500 | Future Task | No | 0d
1.2.4.2.1 | Auto Scheduled | 0% | RTR_CM02_Profit Center Hierarchy | No | 0.75d | Thu 9/24/26 | Thu 9/24/26 |  |  | 14251427 |  | NA | Master Data Loads | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.4.2.6.2,1.2.4.2.6.4 | NA | 2424 |  | 24572459 | -89.81d | Yes | Yes | Yes | No | No | 1.2.4.2.1 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.1.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1390 | 1394 |  | NA | RTR_CM02_Profit Center Hierarchy | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.1 | Mon 4/6/26 | Mon 4/6/26 | Start No Earlier Than | 1.2.4.2.1.2 | Mon 4/6/26 | 2425 | 2423 | 2426 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.1.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.1.2 | Auto Scheduled | 0% | Load | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1393 | 1395 |  | NA | RTR_CM02_Profit Center Hierarchy | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.1.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.4.2.1.3 | NA | 2426 | 2425 | 2427 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.1.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.1.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1394 | 13971410 | Brian Wagner | NA | RTR_CM02_Profit Center Hierarchy | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.1.2 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.4.2.2.1,1.2.4.2.4.1 | NA | 2427 | 2426 | 24292442 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.1.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.2 | Auto Scheduled | 0% | RTR_CM03_Cost Center Hierarchy | No | 0.75d | Thu 9/24/26 | Fri 9/25/26 |  |  | 14251427 |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.6.2,1.2.4.2.6.4 | NA | 2428 |  | 24572459 | -89.81d | Yes | Yes | Yes | No | No | 1.2.4.2.2 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.2.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1395 | 1398 |  | NA | RTR_CM03_Cost Center Hierarchy | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.1.3 | Mon 4/6/26 | Mon 4/6/26 | Start No Earlier Than | 1.2.4.2.2.2 | Mon 4/6/26 | 2429 | 2427 | 2430 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.2.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.2.2 | Auto Scheduled | 0% | Load | No | 2h | Thu 9/24/26 | Fri 9/25/26 | Kasey Hughes | 1397 | 1399 |  | NA | RTR_CM03_Cost Center Hierarchy | Thu 9/24/26 | Fri 9/25/26 | 1.2.4.2.2.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.2.3 | NA | 2430 | 2429 | 2431 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.2.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.2.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1398 | 14011436 | Brian Wagner | NA | RTR_CM03_Cost Center Hierarchy | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.2.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.3.1,1.2.4.2.8.1 | NA | 2431 | 2430 | 24332468 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.2.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.3 | Auto Scheduled | 0% | RTR_CM01_GL_Account_Master to CC 1000 | No | 2.44d | Fri 9/25/26 | Tue 9/29/26 |  |  | 1425 |  | NA | Master Data Loads | Fri 9/25/26 | Tue 9/29/26 |  | Tue 4/7/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.6.2 | NA | 2432 |  | 2457 | -89.81d | Yes | Yes | Yes | No | No | 1.2.4.2.3 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.3.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1399 | 1402 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.2.3 | Tue 4/7/26 | Tue 4/7/26 | Start No Earlier Than | 1.2.4.2.3.2 | Mon 4/6/26 | 2433 | 2431 | 2434 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.3.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.3.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1401 | 1403 | Brian Wagner | NA | RTR_CM01_GL_Account_Master to CC 1000 | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.3.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.3.3 | NA | 2434 | 2433 | 2435 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.3.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.3.3 | Auto Scheduled | 0% | Simulate Load | No | 6h | Fri 9/25/26 | Mon 9/28/26 | Data Migration Team | 1402 | 1404 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Fri 9/25/26 | Mon 9/28/26 | 1.2.4.2.3.2 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.3.4 | NA | 2435 | 2434 | 2436 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.3.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.3.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 9/28/26 | Tue 9/29/26 | Kasey Hughes | 1403 | 1405 | Brian Wagner | NA | RTR_CM01_GL_Account_Master to CC 1000 | Mon 9/28/26 | Tue 9/29/26 | 1.2.4.2.3.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.3.5 | NA | 2436 | 2435 | 2437 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.3.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.3.5 | Auto Scheduled | 0% | Load | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1404 | 1406 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.3.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.3.6 | NA | 2437 | 2436 | 2438 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.3.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.3.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Kasey Hughes | 1405 | 1.4291e+19 | Brian Wagner | NA | RTR_CM01_GL_Account_Master to CC 1000 | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.3.5 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.7.1,1.2.4.2.9.1,1.2.4.2.11.1,1.2.4.2.13.1,1.2.4.2.3.7 | NA | 2438 | 2437 | 2.4612e+19 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.3.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.3.7 | Auto Scheduled | 0% | Extend GL to all Company Codes | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Kasey Hughes | 1406 | 1408 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.3.6 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.3.8 | NA | 2439 | 2438 | 2440 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.3.7 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.3.8 | Auto Scheduled | 0% | Post GL Extention Validation | No | 2h | Tue 9/29/26 | Tue 9/29/26 |  | 1407 | 14741427 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.3.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.14.3,1.2.4.2.6.4 | NA | 2440 | 2439 | 25062459 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.3.8 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.4 | Auto Scheduled | 0% | RTR_CM05_Profit_Center | No | 1.13d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 2441 |  |  | -84.72d | Yes | Yes | Yes | No | No | 1.2.4.2.4 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.4.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1395 | 1411 |  | NA | RTR_CM05_Profit_Center | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.1.3 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.4.2.4.2 | NA | 2442 | 2427 | 2443 | -677.75h | No | Yes | Yes | No | No | 1.2.4.2.4.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.4.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 9/24/26 | Fri 9/25/26 | Kasey Hughes | 1410 | 1412 | Brian Wagner | NA | RTR_CM05_Profit_Center | Thu 9/24/26 | Fri 9/25/26 | 1.2.4.2.4.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.4.3 | NA | 2443 | 2442 | 2444 | -677.75h | No | Yes | Yes | No | No | 1.2.4.2.4.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.4.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Data Migration Team | 1411 | 1413 |  | NA | RTR_CM05_Profit_Center | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.4.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.4.4 | NA | 2444 | 2443 | 2445 | -677.75h | No | Yes | Yes | No | No | 1.2.4.2.4.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.4.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1412 | 1414 | Brian Wagner | NA | RTR_CM05_Profit_Center | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.4.3 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.4.5 | NA | 2445 | 2444 | 2446 | -677.75h | No | Yes | Yes | No | No | 1.2.4.2.4.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.4.5 | Auto Scheduled | 0% | Load | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Data Migration Team | 1413 | 1415 |  | NA | RTR_CM05_Profit_Center | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.4.4 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.4.6 | NA | 2446 | 2445 | 2447 | -677.75h | No | Yes | Yes | No | No | 1.2.4.2.4.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.4.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1414 | 141715461553 | Brian Wagner | NA | RTR_CM05_Profit_Center | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.4.5 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.5.1,1.2.4.2.25.1,1.2.4.2.26.1 | NA | 2447 | 2446 | 244925782585 | -677.75h | No | Yes | Yes | No | No | 1.2.4.2.4.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.5 | Auto Scheduled | 0% | RTR_CM04_Cost_Center | No | 1.13d | Fri 9/25/26 | Tue 9/29/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Tue 9/29/26 |  | Tue 4/7/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 2448 |  |  | -83.19d | Yes | Yes | Yes | No | No | 1.2.4.2.5 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.5.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Fri 9/25/26 | Mon 9/28/26 | Kasey Hughes | 1415 | 1418 |  | NA | RTR_CM04_Cost_Center | Fri 9/25/26 | Mon 9/28/26 | 1.2.4.2.4.6 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.5.2 | NA | 2449 | 2447 | 2450 | -665.5h | No | Yes | Yes | No | No | 1.2.4.2.5.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.5.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Kasey Hughes | 1417 | 1419 | Brian Wagner | NA | RTR_CM04_Cost_Center | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.5.1 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.5.3 | NA | 2450 | 2449 | 2451 | -665.5h | No | Yes | Yes | No | No | 1.2.4.2.5.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.5.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1418 | 1420 |  | NA | RTR_CM04_Cost_Center | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.5.2 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.5.4 | NA | 2451 | 2450 | 2452 | -665.5h | No | Yes | Yes | No | No | 1.2.4.2.5.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.5.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Kasey Hughes | 1419 | 1421 | Brian Wagner | NA | RTR_CM04_Cost_Center | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.5.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.5.5 | NA | 2452 | 2451 | 2453 | -665.5h | No | Yes | Yes | No | No | 1.2.4.2.5.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.5.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1420 | 1422 |  | NA | RTR_CM04_Cost_Center | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.5.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.5.6 | NA | 2453 | 2452 | 2454 | -665.5h | No | Yes | Yes | No | No | 1.2.4.2.5.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.5.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 9/28/26 | Tue 9/29/26 | Kasey Hughes | 1421 |  | Brian Wagner | NA | RTR_CM04_Cost_Center | Mon 9/28/26 | Tue 9/29/26 | 1.2.4.2.5.5 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 2454 | 2453 |  | -665.5h | No | Yes | Yes | No | No | 1.2.4.2.5.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.6 | Auto Scheduled | 0% | Manual Configuration Activities in QS5 | No | 8.94d | Thu 9/24/26 | Tue 10/6/26 |  | 40 |  |  | NA | Master Data Loads | Thu 9/24/26 | Tue 10/6/26 | 1.1.1.4.22 | Mon 4/6/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2455 | 652 |  | -89.13d | Yes | Yes | Yes | No | No | 1.2.4.2.6 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.6.1 | Auto Scheduled | 0% | Open Client | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Basis |  |  |  | NA | Manual Configuration Activities in QS5 | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 2456 |  |  | -38520m | No | Yes | Yes | No | No | 1.2.4.2.6.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.6.2 | Auto Scheduled | 0% | Service Enterprise Setup | No | 5d | Wed 9/30/26 | Tue 10/6/26 | Keith Riley | 139213961400 |  |  | NA | Manual Configuration Activities in QS5 | Wed 9/30/26 | Tue 10/6/26 | 1.2.4.2.1,1.2.4.2.2,1.2.4.2.3 | Wed 4/8/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2457 | 242424282432 |  | -89.13d | No | Yes | Yes | No | No | 1.2.4.2.6.2 | 6 | No | 500 | Future Task | No | 0d
1.2.4.2.6.3 | Auto Scheduled | 0% | Close Client | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Basis |  |  |  | NA | Manual Configuration Activities in QS5 | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 2458 |  |  | -38520m | No | Yes | Yes | No | No | 1.2.4.2.6.3 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.6.4 | Auto Scheduled | 0% | Intercompany Business Partner Setup | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Functional Leads | 139213961408 |  |  | NA | Manual Configuration Activities in QS5 | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.1,1.2.4.2.2,1.2.4.2.3.8 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 2459 | 242424282440 |  | -675h | No | Yes | Yes | No | No | 1.2.4.2.6.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.7 | Auto Scheduled | 0% | RTR_CM09_Activity_Type | No | 1.38d | Tue 9/29/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Wed 9/30/26 |  | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 2460 |  |  | -85d | Yes | Yes | Yes | No | No | 1.2.4.2.7 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.7.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Kasey Hughes | 1406 | 1430 |  | NA | RTR_CM09_Activity_Type | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.3.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.7.2 | NA | 2461 | 2438 | 2462 | -680h | No | Yes | Yes | No | No | 1.2.4.2.7.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.7.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 9/29/26 | Wed 9/30/26 | Kasey Hughes | 1429 | 1431 | Brian Wagner | NA | RTR_CM09_Activity_Type | Tue 9/29/26 | Wed 9/30/26 | 1.2.4.2.7.1 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.7.3 | NA | 2462 | 2461 | 2463 | -680h | No | Yes | Yes | No | No | 1.2.4.2.7.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.7.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1430 | 1432 |  | NA | RTR_CM09_Activity_Type | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.7.2 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.7.4 | NA | 2463 | 2462 | 2464 | -680h | No | Yes | Yes | No | No | 1.2.4.2.7.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.7.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Kasey Hughes | 1431 | 1433 | Brian Wagner | NA | RTR_CM09_Activity_Type | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.7.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.7.5 | NA | 2464 | 2463 | 2465 | -680h | No | Yes | Yes | No | No | 1.2.4.2.7.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.7.5 | Auto Scheduled | 0% | Load | No | 1h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1432 | 1434 |  | NA | RTR_CM09_Activity_Type | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.7.4 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.7.6 | NA | 2465 | 2464 | 2466 | -680h | No | Yes | Yes | No | No | 1.2.4.2.7.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.7.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Kasey Hughes | 1433 |  | Brian Wagner | NA | RTR_CM09_Activity_Type | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.7.5 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 2466 | 2465 |  | -680h | No | Yes | Yes | No | No | 1.2.4.2.7.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.8 | Auto Scheduled | 0% | RTR_CM12_Activity Rates | No | 1.13d | Fri 9/25/26 | Mon 9/28/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Mon 9/28/26 |  | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible |  | NA | 2467 |  |  | -82.81d | Yes | Yes | Yes | No | No | 1.2.4.2.8 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.8.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1399 | 1437 |  | NA | RTR_CM12_Activity Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.2.3 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.8.2 | NA | 2468 | 2431 | 2469 | -662.5h | No | Yes | Yes | No | No | 1.2.4.2.8.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.8.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1436 | 1438 | Brian Wagner | NA | RTR_CM12_Activity Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.8.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.8.3 | NA | 2469 | 2468 | 2470 | -662.5h | No | Yes | Yes | No | No | 1.2.4.2.8.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.8.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 9/25/26 | Mon 9/28/26 | Data Migration Team | 1437 | 1439 |  | NA | RTR_CM12_Activity Rates | Fri 9/25/26 | Mon 9/28/26 | 1.2.4.2.8.2 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.8.4 | NA | 2470 | 2469 | 2471 | -662.5h | No | Yes | Yes | No | No | 1.2.4.2.8.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.8.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Kasey Hughes | 1438 | 1440 | Brian Wagner | NA | RTR_CM12_Activity Rates | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.8.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.8.5 | NA | 2471 | 2470 | 2472 | -662.5h | No | Yes | Yes | No | No | 1.2.4.2.8.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.8.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1439 | 1441 |  | NA | RTR_CM12_Activity Rates | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.8.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.8.6 | NA | 2472 | 2471 | 2473 | -662.5h | No | Yes | Yes | No | No | 1.2.4.2.8.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.8.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Kasey Hughes | 1440 |  | Brian Wagner | NA | RTR_CM12_Activity Rates | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.8.5 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible |  | NA | 2473 | 2472 |  | -662.5h | No | Yes | Yes | No | No | 1.2.4.2.8.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.9 | Auto Scheduled | 0% | RTR_CM06_Bank_master | No | 3.81d | Thu 9/24/26 | Tue 9/29/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Tue 9/29/26 |  | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 2474 |  |  | -86.31d | Yes | Yes | Yes | No | No | 1.2.4.2.9 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.9.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1406 | 1444 |  | NA | RTR_CM06_Bank_master | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.3.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.9.2 | NA | 2475 | 2438 | 2476 | -672h | No | Yes | Yes | No | No | 1.2.4.2.9.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.9.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Kasey Hughes | 1443 |  | Brian Wagner | NA | RTR_CM06_Bank_master | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.9.1 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 2476 | 2475 |  | -672h | No | Yes | Yes | No | No | 1.2.4.2.9.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.9.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team |  | 1446 |  | NA | RTR_CM06_Bank_master | Thu 9/24/26 | Thu 9/24/26 |  | Thu 4/9/26 | Thu 4/9/26 | Start No Earlier Than | 1.2.4.2.9.4 | Wed 4/15/26 | 2477 |  | 2478 | -690.5h | No | Yes | Yes | No | No | 1.2.4.2.9.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.9.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1445 | 1447 | Brian Wagner | NA | RTR_CM06_Bank_master | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.9.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.9.5 | NA | 2478 | 2477 | 2479 | -690.5h | No | Yes | Yes | No | No | 1.2.4.2.9.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.9.5 | Auto Scheduled | 0% | Load | No | 5h | Thu 9/24/26 | Fri 9/25/26 | Data Migration Team | 1446 | 14481450 |  | NA | RTR_CM06_Bank_master | Thu 9/24/26 | Fri 9/25/26 | 1.2.4.2.9.4 | Thu 4/9/26 | Thu 4/9/26 | Finish No Earlier Than | 1.2.4.2.9.6,1.2.4.2.10.1 | Wed 4/15/26 | 2479 | 2478 | 24802482 | -690.5h | No | Yes | Yes | No | No | 1.2.4.2.9.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.9.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1447 | 14841495 | Brian Wagner | NA | RTR_CM06_Bank_master | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.9.5 | Thu 4/9/26 | Thu 4/9/26 | Finish No Earlier Than | 1.2.4.2.15.3,1.2.4.2.17.3 | Tue 4/14/26 | 2480 | 2479 | 25162527 | -690.5h | No | Yes | Yes | No | No | 1.2.4.2.9.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.10 | Auto Scheduled | 0% | RTR_CM08_Exchange_Rates | No | 1.13d | Fri 9/25/26 | Mon 9/28/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Mon 9/28/26 |  | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 2481 |  |  | -82.31d | Yes | Yes | Yes | No | No | 1.2.4.2.10 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.10.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1447 | 1451 |  | NA | RTR_CM08_Exchange_Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.9.5 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.10.2 | NA | 2482 | 2479 | 2483 | -658.5h | No | Yes | Yes | No | No | 1.2.4.2.10.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.10.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1450 | 1452 | Brian Wagner | NA | RTR_CM08_Exchange_Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.10.1 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.10.3 | NA | 2483 | 2482 | 2484 | -658.5h | No | Yes | Yes | No | No | 1.2.4.2.10.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.10.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Data Migration Team | 1451 | 1453 |  | NA | RTR_CM08_Exchange_Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.10.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.10.4 | NA | 2484 | 2483 | 2485 | -658.5h | No | Yes | Yes | No | No | 1.2.4.2.10.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.10.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1452 | 1454 | Brian Wagner | NA | RTR_CM08_Exchange_Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.10.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.10.5 | NA | 2485 | 2484 | 2486 | -658.5h | No | Yes | Yes | No | No | 1.2.4.2.10.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.10.5 | Auto Scheduled | 0% | Load | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Data Migration Team | 1453 | 1455 |  | NA | RTR_CM08_Exchange_Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.10.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.10.6 | NA | 2486 | 2485 | 2487 | -658.5h | No | Yes | Yes | No | No | 1.2.4.2.10.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.10.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Fri 9/25/26 | Mon 9/28/26 | Kasey Hughes | 1454 |  | Brian Wagner | NA | RTR_CM08_Exchange_Rates | Fri 9/25/26 | Mon 9/28/26 | 1.2.4.2.10.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 2487 | 2486 |  | -658.5h | No | Yes | Yes | No | No | 1.2.4.2.10.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.11 | Auto Scheduled | 0% | RTR_CM14_Cost Element_Group | No | 4.44d | Tue 9/29/26 | Mon 10/5/26 | Kasey Hughes |  |  | Brian Wagner | NA | Master Data Loads | Tue 9/29/26 | Mon 10/5/26 |  | Wed 4/8/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2488 |  |  | -88.06d | Yes | Yes | Yes | No | No | 1.2.4.2.11 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.11.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Kasey Hughes | 1406 | 1458 |  | NA | RTR_CM14_Cost Element_Group | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.3.6 | Wed 4/8/26 | Tue 4/14/26 | Finish No Earlier Than | 1.2.4.2.11.2 | Tue 4/14/26 | 2489 | 2438 | 2490 | -42270m | No | Yes | Yes | No | No | 1.2.4.2.11.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.11.2 | Auto Scheduled | 0% | Load | No | 32h | Tue 9/29/26 | Mon 10/5/26 | Kasey Hughes | 1457 | 1459 |  | NA | RTR_CM14_Cost Element_Group | Tue 9/29/26 | Mon 10/5/26 | 1.2.4.2.11.1 | Wed 4/15/26 | Wed 4/15/26 | Finish No Earlier Than | 1.2.4.2.11.3 | Tue 4/21/26 | 2490 | 2489 | 2491 | -704.5h | No | Yes | Yes | No | No | 1.2.4.2.11.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.11.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 10/5/26 | Mon 10/5/26 | Kasey Hughes | 1458 |  | Brian Wagner | NA | RTR_CM14_Cost Element_Group | Mon 10/5/26 | Mon 10/5/26 | 1.2.4.2.11.2 | Wed 4/15/26 | Wed 4/15/26 | Start No Earlier Than |  | Fri 4/17/26 | 2491 | 2490 |  | -704.5h | No | Yes | Yes | No | No | 1.2.4.2.11.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.12 | Auto Scheduled | 0% | OTC_CM19_Customer_Master - Bill-To | No | 2h | Thu 9/24/26 | Thu 9/24/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Thu 9/24/26 |  | Wed 4/16/25 | Wed 4/16/25 | As Soon As Possible |  | NA | 2492 |  |  | -643.5h | No | Yes | Yes | No | No | 1.2.4.2.12 | 5 | No | 500 | Future Task | No | 0h
1.2.4.2.13 | Auto Scheduled | 0% | OTC_CM19_Customer_Master - Ship-To | No | 1.5d | Tue 9/29/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Wed 9/30/26 |  | Wed 4/8/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2493 |  |  | -89.56d | Yes | Yes | Yes | No | No | 1.2.4.2.13 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.13.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Ric Haraida | 1406 | 1463 |  | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.3.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.13.2 | NA | 2494 | 2438 | 2495 | -42990m | No | Yes | Yes | No | No | 1.2.4.2.13.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.13.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Ric Haraida | 1462 | 146714721464 | Kim Kolesar | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.13.1 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.4.2.13.6,1.2.4.2.14.1,1.2.4.2.13.3 | NA | 2495 | 2494 | 249925042496 | -42990m | No | Yes | Yes | No | No | 1.2.4.2.13.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.13.3 | Auto Scheduled | 0% | Open client for BP number range update | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Basis | 1463 | 1465 |  | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.13.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.13.4 | NA | 2496 | 2495 | 2497 | -40275m | No | Yes | Yes | No | No | 1.2.4.2.13.3 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.13.4 | Auto Scheduled | 0% | Update number range BP02 from Internal to External | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Ric Haraida | 1464 | 1466 |  | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.13.3 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.13.5 | NA | 2497 | 2496 | 2498 | -40275m | No | Yes | Yes | No | No | 1.2.4.2.13.4 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.13.5 | Auto Scheduled | 0% | Close Client | No | 15m | Tue 9/29/26 | Tue 9/29/26 | Basis | 1465 |  |  | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.13.4 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2498 | 2497 |  | -40275m | No | Yes | Yes | No | No | 1.2.4.2.13.5 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.13.6 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1463 | 146814741478 |  | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.13.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.13.7,1.2.4.2.14.3,1.2.4.2.14.7 | NA | 2499 | 2495 | 250025062510 | -716.5h | No | Yes | Yes | No | No | 1.2.4.2.13.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.13.7 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 4h | Tue 9/29/26 | Wed 9/30/26 | Ric Haraida | 1467 | 1469 | Kim Kolesar | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Wed 9/30/26 | 1.2.4.2.13.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.13.8 | NA | 2500 | 2499 | 2501 | -681h | No | Yes | Yes | No | No | 1.2.4.2.13.7 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.13.8 | Auto Scheduled | 0% | Load | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1468 | 1470 |  | NA | OTC_CM19_Customer_Master - Ship-To | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.13.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.13.9 | NA | 2501 | 2500 | 2502 | -681h | No | Yes | Yes | No | No | 1.2.4.2.13.8 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.13.9 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Ric Haraida | 1469 |  | Kim Kolesar | NA | OTC_CM19_Customer_Master - Ship-To | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.13.8 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 2502 | 2501 |  | -681h | No | Yes | Yes | No | No | 1.2.4.2.13.9 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.14 | Auto Scheduled | 0% | OTC_CM19_Customer_Master - Sold-To | No | 1.63d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Wed 4/8/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 2503 |  |  | -89.44d | Yes | Yes | Yes | No | No | 1.2.4.2.14 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.14.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Ric Haraida | 1463 | 1473 |  | NA | OTC_CM19_Customer_Master - Sold-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.13.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.14.2 | NA | 2504 | 2495 | 2505 | -40260m | No | Yes | Yes | No | No | 1.2.4.2.14.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.14.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Ric Haraida | 1472 |  | Kim Kolesar | NA | OTC_CM19_Customer_Master - Sold-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.14.1 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 2505 | 2504 |  | -40260m | No | Yes | Yes | No | No | 1.2.4.2.14.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.14.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 14081467 | 1475 |  | NA | OTC_CM19_Customer_Master - Sold-To | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.3.8,1.2.4.2.13.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.14.4 | NA | 2506 | 24402499 | 2507 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.14.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.14.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Ric Haraida | 1474 | 1476 | Kim Kolesar | NA | OTC_CM19_Customer_Master - Sold-To | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.14.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.14.5 | NA | 2507 | 2506 | 2508 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.14.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.14.5 | Auto Scheduled | 0% | Load | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1475 | 1.4771e+19 |  | NA | OTC_CM19_Customer_Master - Sold-To | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.14.4 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.14.6,1.2.4.2.15.1,1.2.4.2.16.1,1.2.4.2.17.1,1.2.4.2.18.1 | NA | 2508 | 2507 | 2.5093e+19 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.14.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.14.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Thu 10/1/26 | Ric Haraida | 1476 |  | Kim Kolesar | NA | OTC_CM19_Customer_Master - Sold-To | Wed 9/30/26 | Thu 10/1/26 | 1.2.4.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 2509 | 2508 |  | -683h | No | Yes | Yes | No | No | 1.2.4.2.14.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.14.7 | Auto Scheduled | 0% | Open client for BP number range update | No | 15m | Tue 9/29/26 | Tue 9/29/26 | Basis | 1467 | 1479 |  | NA | OTC_CM19_Customer_Master - Sold-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.13.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.14.8 | NA | 2510 | 2499 | 2511 | -40305m | No | Yes | Yes | No | No | 1.2.4.2.14.7 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.14.8 | Auto Scheduled | 0% | Update number range BP02 from Internal to External | No | 15m | Tue 9/29/26 | Tue 9/29/26 | Ric Haraida | 1478 | 1480 |  | NA | OTC_CM19_Customer_Master - Sold-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.14.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.4.2.14.9 | NA | 2511 | 2510 | 2512 | -40305m | No | Yes | Yes | No | No | 1.2.4.2.14.8 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.14.9 | Auto Scheduled | 0% | Close Client | No | 15m | Tue 9/29/26 | Tue 9/29/26 | Basis | 1479 |  |  | NA | OTC_CM19_Customer_Master - Sold-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.14.8 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 2512 | 2511 |  | -40305m | No | Yes | Yes | No | No | 1.2.4.2.14.9 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.15 | Auto Scheduled | 0% | PTP_CM27_Vendor Master as Customer - FLCU01 | No | 4.81d | Wed 9/30/26 | Wed 10/7/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Wed 10/7/26 |  | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 2513 |  |  | -89.81d | Yes | Yes | Yes | No | No | 1.2.4.2.15 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.15.1 | Auto Scheduled | 0% | Extract File | No | 1h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1476 | 1483 |  | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.15.2 | NA | 2514 | 2508 | 2515 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.15.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.15.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Nevin Varkey | 1482 | 1484 | Sam Houff | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.15.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.15.3 | NA | 2515 | 2514 | 2516 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.15.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.15.3 | Auto Scheduled | 0% | Simulate Load | No | 11.25h | Thu 10/1/26 | Fri 10/2/26 | Data Migration Team | 14481483 | 1485 |  | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Thu 10/1/26 | Fri 10/2/26 | 1.2.4.2.9.6,1.2.4.2.15.2 | Fri 4/10/26 | Mon 4/13/26 | Finish No Earlier Than | 1.2.4.2.15.4 | Mon 4/13/26 | 2516 | 24802515 | 2517 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.15.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.15.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 10/2/26 | Tue 10/6/26 | Nevin Varkey | 1484 | 1486 | Sam Houff | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Fri 10/2/26 | Tue 10/6/26 | 1.2.4.2.15.3 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.4.2.15.5 | NA | 2517 | 2516 | 2518 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.15.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.15.5 | Auto Scheduled | 0% | Load | No | 1h | Tue 10/6/26 | Wed 10/7/26 | Data Migration Team | 1485 | 1487 |  | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Tue 10/6/26 | Wed 10/7/26 | 1.2.4.2.15.4 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.4.2.15.6 | NA | 2518 | 2517 | 2519 | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.15.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.15.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Wed 10/7/26 | Wed 10/7/26 | Nevin Varkey | 1486 |  | Sam Houff | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Wed 10/7/26 | Wed 10/7/26 | 1.2.4.2.15.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 2519 | 2518 |  | -718.5h | No | Yes | Yes | No | No | 1.2.4.2.15.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.16 | Auto Scheduled | 0% | OTC_CM23_Customer_Hierarchy | No | 0.69d | Wed 9/30/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Thu 10/1/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 2520 |  |  | -85.69d | Yes | Yes | Yes | No | No | 1.2.4.2.16 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.16.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Wed 9/30/26 | Wed 9/30/26 | Ric Haraida | 1476 | 1490 | Kim Kolesar | NA | OTC_CM23_Customer_Hierarchy | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.4.2.16.2 | Mon 4/6/26 | 2521 | 2508 | 2522 | -41130m | No | Yes | Yes | No | No | 1.2.4.2.16.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.16.2 | Auto Scheduled | 0% | Load | No | 2h | Wed 9/30/26 | Thu 10/1/26 | Ric Haraida | 1489 | 1491 |  | NA | OTC_CM23_Customer_Hierarchy | Wed 9/30/26 | Thu 10/1/26 | 1.2.4.2.16.1 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.4.2.16.3 | Wed 4/15/26 | 2522 | 2521 | 2523 | -685.5h | No | Yes | Yes | No | No | 1.2.4.2.16.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.16.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/1/26 | Thu 10/1/26 | Ric Haraida | 1490 |  | Kim Kolesar | NA | OTC_CM23_Customer_Hierarchy | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.16.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 2523 | 2522 |  | -685.5h | No | Yes | Yes | No | No | 1.2.4.2.16.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.17 | Auto Scheduled | 0% | PTP_CM27_Vendor Master - Z001 - External Sales Rep | No | 3.38d | Wed 9/30/26 | Tue 10/6/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Tue 10/6/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2524 |  |  | -88.38d | Yes | Yes | Yes | No | No | 1.2.4.2.17 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.17.1 | Auto Scheduled | 0% | Extract File | No | 1h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1476 | 14941507 |  | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.17.2,1.2.4.2.19.1 | NA | 2525 | 2508 | 25262539 | -707h | No | Yes | Yes | No | No | 1.2.4.2.17.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.17.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Nevin Varkey | 1493 | 1495 | Sam Houff | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.17.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.17.3 | NA | 2526 | 2525 | 2527 | -707h | No | Yes | Yes | No | No | 1.2.4.2.17.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.17.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 14481494 | 1496 |  | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.9.6,1.2.4.2.17.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.17.4 | NA | 2527 | 24802526 | 2528 | -707h | No | Yes | Yes | No | No | 1.2.4.2.17.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.17.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Nevin Varkey | 1495 | 1497 | Sam Houff | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.17.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.17.5 | NA | 2528 | 2527 | 2529 | -707h | No | Yes | Yes | No | No | 1.2.4.2.17.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.17.5 | Auto Scheduled | 0% | Load | No | 1h | Thu 10/1/26 | Mon 10/5/26 | Data Migration Team | 1496 | 1498 |  | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Thu 10/1/26 | Mon 10/5/26 | 1.2.4.2.17.4 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.17.6 | NA | 2529 | 2528 | 2530 | -707h | No | Yes | Yes | No | No | 1.2.4.2.17.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.17.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Tue 10/6/26 | Tue 10/6/26 | Nevin Varkey | 1497 |  | Sam Houff | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Tue 10/6/26 | Tue 10/6/26 | 1.2.4.2.17.5 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2530 | 2529 |  | -707h | No | Yes | Yes | No | No | 1.2.4.2.17.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.18 | Auto Scheduled | 0% | RTR_CM10_Credit_Management_Role | No | 1.84d | Wed 9/30/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Fri 10/2/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2531 |  |  | -87.59d | Yes | Yes | Yes | No | No | 1.2.4.2.18 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.18.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Wed 9/30/26 | Wed 9/30/26 | Kasey Hughes | 1476 | 1501 |  | NA | RTR_CM10_Credit_Management_Role | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.18.2 | NA | 2532 | 2508 | 2533 | -42045m | No | Yes | Yes | No | No | 1.2.4.2.18.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.18.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Wed 9/30/26 | Wed 9/30/26 | Kasey Hughes | 1500 | 1502 | Brian Wagner | NA | RTR_CM10_Credit_Management_Role | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.18.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.18.3 | NA | 2533 | 2532 | 2534 | -42045m | No | Yes | Yes | No | No | 1.2.4.2.18.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.18.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1501 | 1503 |  | NA | RTR_CM10_Credit_Management_Role | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.18.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.18.4 | NA | 2534 | 2533 | 2535 | -700.75h | No | Yes | Yes | No | No | 1.2.4.2.18.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.18.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Kasey Hughes | 1502 | 15041521 | Brian Wagner | NA | RTR_CM10_Credit_Management_Role | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.18.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.18.5,1.2.4.2.21.1 | NA | 2535 | 2534 | 25362553 | -700.75h | No | Yes | Yes | No | No | 1.2.4.2.18.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.18.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1503 | 1505 |  | NA | RTR_CM10_Credit_Management_Role | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.18.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.18.6 | NA | 2536 | 2535 | 2537 | -700.75h | No | Yes | Yes | No | No | 1.2.4.2.18.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.18.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/1/26 | Fri 10/2/26 | Kasey Hughes | 1504 | 15221687 | Brian Wagner | NA | RTR_CM10_Credit_Management_Role | Thu 10/1/26 | Fri 10/2/26 | 1.2.4.2.18.5 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.21.2,1.2.4.2.51.2 | NA | 2537 | 2536 | 25542719 | -700.75h | No | Yes | Yes | No | No | 1.2.4.2.18.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.19 | Auto Scheduled | 0% | PTP_CM27_Vendor Master | No | 6.28d | Thu 9/24/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 10/2/26 |  | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2538 |  |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.4.2.19 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.19.1 | Auto Scheduled | 0% | Extract File | No | 1h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1493 | 1508 |  | NA | PTP_CM27_Vendor Master | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.17.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.19.2 | NA | 2539 | 2525 | 2540 | -691.75h | No | Yes | Yes | No | No | 1.2.4.2.19.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.19.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Nevin Varkey | 1507 | 1509 | Sam Houff | NA | PTP_CM27_Vendor Master | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.19.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.19.3 | NA | 2540 | 2539 | 2541 | -691.75h | No | Yes | Yes | No | No | 1.2.4.2.19.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.19.3 | Auto Scheduled | 0% | Simulate Load | No | 2.25h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1508 | 1510 |  | NA | PTP_CM27_Vendor Master | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.19.2 | Fri 4/10/26 | Tue 4/14/26 | Finish No Earlier Than | 1.2.4.2.19.4 | Fri 4/10/26 | 2541 | 2540 | 2542 | -691.75h | No | Yes | Yes | No | No | 1.2.4.2.19.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.19.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 10/1/26 | Fri 10/2/26 | Nevin Varkey | 1509 |  | Sam Houff | NA | PTP_CM27_Vendor Master | Thu 10/1/26 | Fri 10/2/26 | 1.2.4.2.19.3 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 2542 | 2541 |  | -691.75h | No | Yes | Yes | No | No | 1.2.4.2.19.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.19.5 | Auto Scheduled | 0% | Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team |  | 1512 |  | NA | PTP_CM27_Vendor Master | Thu 9/24/26 | Thu 9/24/26 |  | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.4.2.19.6 | NA | 2543 |  | 2544 | -726h | No | Yes | Yes | No | No | 1.2.4.2.19.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.19.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey | 1511 | 152515401564 | Sam Houff | NA | PTP_CM27_Vendor Master | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.19.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.22.1,1.2.4.2.24.2,1.2.4.2.27.5 | NA | 2544 | 2543 | 255725722596 | -726h | No | Yes | Yes | No | No | 1.2.4.2.19.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.20 | Auto Scheduled | 0% | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | No | 0.88d | Thu 9/24/26 | Thu 9/24/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Thu 9/24/26 |  | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2545 |  |  | -81.69d | Yes | Yes | Yes | No | No | 1.2.4.2.20 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.20.1 | Auto Scheduled | 0% | Extract File(Will Extract from LFA1) | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey |  | 15151539 |  | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 9/24/26 | Thu 9/24/26 |  | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.4.2.20.2,1.2.4.2.24.1 | Thu 4/16/26 | 2546 |  | 25472571 | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.20.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.20.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey | 1514 | 1516 | Sam Houff | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.20.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.20.3 | NA | 2547 | 2546 | 2548 | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.20.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.20.3 | Auto Scheduled | 0% | Simulate Load/ Not Needed | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey | 1515 | 15171518 |  | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.20.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.20.4,1.2.4.2.20.5 | NA | 2548 | 2547 | 25492550 | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.20.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.20.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey | 1516 |  | Sam Houff | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.20.3 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2549 | 2548 |  | -647.5h | No | Yes | Yes | No | No | 1.2.4.2.20.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.20.5 | Auto Scheduled | 0% | Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkkey | 1516 | 1519 |  | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.20.3 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.20.6 | NA | 2550 | 2548 | 2551 | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.20.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.20.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey | 1518 | 1714 | Sam Houff | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.20.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.57.1 | NA | 2551 | 2550 | 2746 | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.20.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.21 | Auto Scheduled | 0% | RTR_****_Credit Hierarchy | No | 1.91d | Thu 10/1/26 | Mon 10/5/26 |  |  |  |  | NA | Master Data Loads | Thu 10/1/26 | Mon 10/5/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2552 |  |  | -87.47d | Yes | Yes | Yes | No | No | 1.2.4.2.21 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.21.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Thu 10/1/26 | Thu 10/1/26 | Kasey Hughes | 1503 |  | Brian Wagner | NA | RTR_****_Credit Hierarchy | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.18.4 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than |  | Wed 4/15/26 | 2553 | 2535 |  | -41100m | No | Yes | Yes | No | No | 1.2.4.2.21.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.21.2 | Auto Scheduled | 0% | Load | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Kasey Hughes | 1505 | 1523 |  | NA | RTR_****_Credit Hierarchy | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.18.6 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.21.3 | NA | 2554 | 2537 | 2555 | -699.75h | No | Yes | Yes | No | No | 1.2.4.2.21.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.21.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 10/2/26 | Mon 10/5/26 | Kasey Hughes | 1522 |  | Brian Wagner | NA | RTR_****_Credit Hierarchy | Fri 10/2/26 | Mon 10/5/26 | 1.2.4.2.21.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2555 | 2554 |  | -699.75h | No | Yes | Yes | No | No | 1.2.4.2.21.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.22 | Auto Scheduled | 0% | PTP_CM27_BP_Intercompany Supplier | No | 1.13d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 2556 |  |  | -81.69d | Yes | Yes | Yes | No | No | 1.2.4.2.22 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.22.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey,Ric Haraida | 1512 | 1526 |  | NA | PTP_CM27_BP_Intercompany Supplier | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.19.6 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.22.2 | NA | 2557 | 2544 | 2558 | -39210m | No | Yes | Yes | No | No | 1.2.4.2.22.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.22.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey,Ric Haraida | 1525 | 1527 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Supplier | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.22.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.22.3 | NA | 2558 | 2557 | 2559 | -39210m | No | Yes | Yes | No | No | 1.2.4.2.22.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.22.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 1526 | 1528 |  | NA | PTP_CM27_BP_Intercompany Supplier | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.22.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.22.4 | NA | 2559 | 2558 | 2560 | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.22.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.22.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey,Ric Haraida | 1527 | 1529 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Supplier | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.22.3 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.22.5 | NA | 2560 | 2559 | 2561 | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.22.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.22.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 9/24/26 | Fri 9/25/26 | Data Migration Team | 1528 | 15301686 |  | NA | PTP_CM27_BP_Intercompany Supplier | Thu 9/24/26 | Fri 9/25/26 | 1.2.4.2.22.4 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.4.2.22.6,1.2.4.2.51.1 | NA | 2561 | 2560 | 25622718 | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.22.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.22.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 9/25/26 | Fri 9/25/26 | Nevin Varkey,Ric Haraida | 1529 |  | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Supplier | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.22.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 2562 | 2561 |  | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.22.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.23 | Auto Scheduled | 0% | PTP_CM27_BP_Intercompany Customer | No | 1.06d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 2563 |  |  | -81.25d | Yes | Yes | Yes | No | No | 1.2.4.2.23 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.23.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey,Ric Haraida |  |  |  | NA | PTP_CM27_BP_Intercompany Customer | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2564 |  |  | -38520m | No | Yes | Yes | No | No | 1.2.4.2.23.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.23.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey,Ric Haraida |  | 1534 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Customer | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.23.3 | NA | 2565 |  | 2566 | -39000m | No | Yes | Yes | No | No | 1.2.4.2.23.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.23.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 1533 | 1535 |  | NA | PTP_CM27_BP_Intercompany Customer | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.23.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.23.4 | NA | 2566 | 2565 | 2567 | -650h | No | Yes | Yes | No | No | 1.2.4.2.23.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.23.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey,Ric Haraida | 1534 | 1536 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Customer | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.23.3 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.23.5 | NA | 2567 | 2566 | 2568 | -650h | No | Yes | Yes | No | No | 1.2.4.2.23.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.23.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 1535 | 15371686 |  | NA | PTP_CM27_BP_Intercompany Customer | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.23.4 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.4.2.23.6,1.2.4.2.51.1 | NA | 2568 | 2567 | 25692718 | -650h | No | Yes | Yes | No | No | 1.2.4.2.23.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.23.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Fri 9/25/26 | Nevin Varkey,Ric Haraida | 1536 |  | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Customer | Thu 9/24/26 | Fri 9/25/26 | 1.2.4.2.23.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 2569 | 2568 |  | -650h | No | Yes | Yes | No | No | 1.2.4.2.23.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.24 | Auto Scheduled | 0% | PTP_CM26_Material_Master - All Types | No | 2.28d | Thu 9/24/26 | Mon 9/28/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Mon 9/28/26 |  | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2570 |  |  | -90.5d | Yes | Yes | Yes | No | No | 1.2.4.2.24 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.24.1 | Auto Scheduled | 0% | Extract File | No | 5h | Thu 9/24/26 | Fri 9/25/26 | Data Migration Team | 1514 |  |  | NA | PTP_CM26_Material_Master - All Types | Thu 9/24/26 | Fri 9/25/26 | 1.2.4.2.20.1 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2571 | 2546 |  | -649.25h | No | Yes | Yes | No | No | 1.2.4.2.24.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.24.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 9/24/26 | Fri 9/25/26 | Nevin Varkey,Ric Haraida | 1512 | 1541 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - All Types | Thu 9/24/26 | Fri 9/25/26 | 1.2.4.2.19.6 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.4.2.24.3 | NA | 2572 | 2544 | 2573 | -726h | No | Yes | Yes | No | No | 1.2.4.2.24.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.24.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Data Migration Team | 1540 | 1542 |  | NA | PTP_CM26_Material_Master - All Types | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.24.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.4.2.24.4 | NA | 2573 | 2572 | 2574 | -726h | No | Yes | Yes | No | No | 1.2.4.2.24.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.24.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 4h | Fri 9/25/26 | Fri 9/25/26 | Nevin Varkey | 1541 | 1543 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - All Types | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.24.3 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.4.2.24.5 | NA | 2574 | 2573 | 2575 | -726h | No | Yes | Yes | No | No | 1.2.4.2.24.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.24.5 | Auto Scheduled | 0% | Load | No | 3h | Fri 9/25/26 | Mon 9/28/26 | Data Migration Team | 1542 | 154415471554 |  | NA | PTP_CM26_Material_Master - All Types | Fri 9/25/26 | Mon 9/28/26 | 1.2.4.2.24.4 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.24.6,1.2.4.2.25.2,1.2.4.2.26.2 | NA | 2575 | 2574 | 257625792586 | -726h | No | Yes | Yes | No | No | 1.2.4.2.24.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.24.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Nevin Varkey | 1543 | 156015671574 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - All Types | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.24.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.27.1,1.2.4.2.28.1,1.2.4.2.29.1 | NA | 2576 | 2575 | 259225992606 | -705.75h | No | Yes | Yes | No | No | 1.2.4.2.24.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.25 | Auto Scheduled | 0% | PTP_CM26_Material_Master - SERV - Service Materials | No | 1.34d | Fri 9/25/26 | Tue 9/29/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Tue 9/29/26 |  | Tue 4/7/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2577 |  |  | -83.41d | Yes | Yes | Yes | No | No | 1.2.4.2.25 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.25.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Fri 9/25/26 | Fri 9/25/26 | Nevin Varkey,Ric Haraida | 1415 |  |  | NA | PTP_CM26_Material_Master - SERV - Service Materials | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.4.6 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 2578 | 2447 |  | -39420m | No | Yes | Yes | No | No | 1.2.4.2.25.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.25.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 9/28/26 | Mon 9/28/26 | Nevin Varkey,Ric Haraida | 1543 | 1548 | Sam Houff,Kim Kolesar | NA | PTP_CM26_Material_Master - SERV - Service Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.24.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.4.2.25.3 | NA | 2579 | 2575 | 2580 | -40035m | No | Yes | Yes | No | No | 1.2.4.2.25.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.25.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1547 | 1549 |  | NA | PTP_CM26_Material_Master - SERV - Service Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.25.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.4.2.25.4 | NA | 2580 | 2579 | 2581 | -667.25h | No | Yes | Yes | No | No | 1.2.4.2.25.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.25.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Nevin Varkey,Ric Haraida | 1548 | 1550 | Sam Houff,Kim Kolesar | NA | PTP_CM26_Material_Master - SERV - Service Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.25.3 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.25.5 | NA | 2581 | 2580 | 2582 | -667.25h | No | Yes | Yes | No | No | 1.2.4.2.25.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.25.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1549 | 1551 |  | NA | PTP_CM26_Material_Master - SERV - Service Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.25.4 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.25.6 | NA | 2582 | 2581 | 2583 | -667.25h | No | Yes | Yes | No | No | 1.2.4.2.25.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.25.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 9/28/26 | Tue 9/29/26 | Nevin Varkey,Ric Haraida | 1550 |  | Sam Houff,Kim Kolesar | NA | PTP_CM26_Material_Master - SERV - Service Materials | Mon 9/28/26 | Tue 9/29/26 | 1.2.4.2.25.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2583 | 2582 |  | -667.25h | No | Yes | Yes | No | No | 1.2.4.2.25.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.26 | Auto Scheduled | 0% | PTP_CM26_Material_Master - KMAT - Configurable Materials | No | 1.34d | Fri 9/25/26 | Tue 9/29/26 |  |  | 16451642 |  | NA | Master Data Loads | Fri 9/25/26 | Tue 9/29/26 |  | Tue 4/7/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.42.1,1.2.4.2.41.1 | NA | 2584 |  | 26772674 | -90.47d | Yes | Yes | Yes | No | No | 1.2.4.2.26 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.26.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Fri 9/25/26 | Fri 9/25/26 | Eric Heisler | 1415 |  |  | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.4.6 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 2585 | 2447 |  | -40665m | No | Yes | Yes | No | No | 1.2.4.2.26.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.26.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 9/28/26 | Mon 9/28/26 | Eric Heisler | 1543 | 1555 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.24.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.4.2.26.3 | NA | 2586 | 2575 | 2587 | -43560m | No | Yes | Yes | No | No | 1.2.4.2.26.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.26.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1554 | 1556 |  | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.26.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.4.2.26.4 | NA | 2587 | 2586 | 2588 | -726h | No | Yes | Yes | No | No | 1.2.4.2.26.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.26.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Eric Heisler | 1555 | 1557 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.26.3 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.26.5 | NA | 2588 | 2587 | 2589 | -726h | No | Yes | Yes | No | No | 1.2.4.2.26.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.26.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1556 | 1558 |  | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.4.2.26.4 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.26.6 | NA | 2589 | 2588 | 2590 | -726h | No | Yes | Yes | No | No | 1.2.4.2.26.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.26.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 9/28/26 | Tue 9/29/26 | Eric Heisler | 1557 | 1.5602e+19 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Mon 9/28/26 | Tue 9/29/26 | 1.2.4.2.26.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.27.1,1.2.4.2.28.1,1.2.4.2.29.1,1.2.4.2.40.1,1.2.4.2.46.1 | NA | 2590 | 2589 | 2.5923e+19 | -726h | No | Yes | Yes | No | No | 1.2.4.2.26.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.27 | Auto Scheduled | 0% | PTP_CM28_Purchase_Info_Records | No | 3.59d | Thu 9/24/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Wed 9/30/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2591 |  |  | -84.7d | Yes | Yes | Yes | No | No | 1.2.4.2.27 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.27.1 | Auto Scheduled | 0% | Extract File | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 15441558 | 15611581 |  | NA | PTP_CM28_Purchase_Info_Records | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.24.6,1.2.4.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.27.2,1.2.4.2.30.1 | NA | 2592 | 25762590 | 25932613 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.27.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.27.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 1560 | 1562 | Sam Houff | NA | PTP_CM28_Purchase_Info_Records | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.27.1 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.27.3 | NA | 2593 | 2592 | 2594 | -673.25h | No | Yes | Yes | No | No | 1.2.4.2.27.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.27.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1561 | 1563 |  | NA | PTP_CM28_Purchase_Info_Records | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.27.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.27.4 | NA | 2594 | 2593 | 2595 | -673.25h | No | Yes | Yes | No | No | 1.2.4.2.27.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.27.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 9/29/26 | Wed 9/30/26 | Nevin Varkey | 1562 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Records | Tue 9/29/26 | Wed 9/30/26 | 1.2.4.2.27.3 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than |  | Fri 4/17/26 | 2595 | 2594 |  | -673.25h | No | Yes | Yes | No | No | 1.2.4.2.27.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.27.5 | Auto Scheduled | 0% | Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 1512 | 1565 |  | NA | PTP_CM28_Purchase_Info_Records | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.19.6 | Wed 4/15/26 | Wed 4/15/26 | Start No Earlier Than | 1.2.4.2.27.6 | Fri 4/17/26 | 2596 | 2544 | 2597 | -647.5h | No | Yes | Yes | No | No | 1.2.4.2.27.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.27.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey | 1564 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Records | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.27.5 | Wed 4/15/26 | Wed 4/15/26 | Start No Earlier Than |  | Fri 4/17/26 | 2597 | 2596 |  | -647.5h | No | Yes | Yes | No | No | 1.2.4.2.27.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.28 | Auto Scheduled | 0% | PTP_CM28_Purchase_Info_Record External Processing | No | 1.13d | Tue 9/29/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Wed 9/30/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2598 |  |  | -84.53d | Yes | Yes | Yes | No | No | 1.2.4.2.28 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.28.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 15441558 | 1568 |  | NA | PTP_CM28_Purchase_Info_Record External Processing | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.24.6,1.2.4.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.28.2 | NA | 2599 | 25762590 | 2600 | -40575m | No | Yes | Yes | No | No | 1.2.4.2.28.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.28.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 1567 | 1569 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record External Processing | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.28.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.28.3 | NA | 2600 | 2599 | 2601 | -40575m | No | Yes | Yes | No | No | 1.2.4.2.28.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.28.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1568 | 1570 |  | NA | PTP_CM28_Purchase_Info_Record External Processing | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.28.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.28.4 | NA | 2601 | 2600 | 2602 | -676.25h | No | Yes | Yes | No | No | 1.2.4.2.28.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.28.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 1569 | 1571 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record External Processing | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.28.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.28.5 | NA | 2602 | 2601 | 2603 | -676.25h | No | Yes | Yes | No | No | 1.2.4.2.28.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.28.5 | Auto Scheduled | 0% | Load | No | 2h | Tue 9/29/26 | Wed 9/30/26 | Data Migration Team | 1570 | 1572 |  | NA | PTP_CM28_Purchase_Info_Record External Processing | Tue 9/29/26 | Wed 9/30/26 | 1.2.4.2.28.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.28.6 | NA | 2603 | 2602 | 2604 | -676.25h | No | Yes | Yes | No | No | 1.2.4.2.28.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.28.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Nevin Varkey | 1571 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Record External Processing | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.28.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2604 | 2603 |  | -676.25h | No | Yes | Yes | No | No | 1.2.4.2.28.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.29 | Auto Scheduled | 0% | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | No | 1.13d | Tue 9/29/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Wed 9/30/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2605 |  |  | -89.03d | Yes | Yes | Yes | No | No | 1.2.4.2.29 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.29.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 15441558 | 1575 |  | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.24.6,1.2.4.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.29.2 | NA | 2606 | 25762590 | 2607 | -42735m | No | Yes | Yes | No | No | 1.2.4.2.29.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.29.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 1574 | 1576 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.29.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.29.3 | NA | 2607 | 2606 | 2608 | -42735m | No | Yes | Yes | No | No | 1.2.4.2.29.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.29.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1575 | 15771708 |  | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.29.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.29.4,1.2.4.2.55.1 | NA | 2608 | 2607 | 26092740 | -712.25h | No | Yes | Yes | No | No | 1.2.4.2.29.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.29.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 1576 | 1578 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.29.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.29.5 | NA | 2609 | 2608 | 2610 | -676.25h | No | Yes | Yes | No | No | 1.2.4.2.29.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.29.5 | Auto Scheduled | 0% | Load | No | 2h | Tue 9/29/26 | Wed 9/30/26 | Data Migration Team | 1577 | 1579 |  | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Tue 9/29/26 | Wed 9/30/26 | 1.2.4.2.29.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.29.6 | NA | 2610 | 2609 | 2611 | -676.25h | No | Yes | Yes | No | No | 1.2.4.2.29.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.29.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Nevin Varkey | 1578 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.29.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2611 | 2610 |  | -676.25h | No | Yes | Yes | No | No | 1.2.4.2.29.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.30 | Auto Scheduled | 0% | PTM_CM31_BOM Conversion | No | 2.48d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Wed 4/15/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2612 |  |  | -87.55d | Yes | Yes | Yes | No | No | 1.2.4.2.30 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.30.1 | Auto Scheduled | 0% | Extract File | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1560 | 15821588 |  | NA | PTM_CM31_BOM Conversion | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.27.1 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.30.2,1.2.4.2.31.1 | NA | 2613 | 2592 | 26142620 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.30.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.30.2 | Auto Scheduled | 0% | Pre Load Validation | No | 0.5h | Tue 9/29/26 | Tue 9/29/26 | Brad Meseck | 1581 | 1583 | Matt Palastro, Dave Duda | NA | PTM_CM31_BOM Conversion | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.30.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.30.3 | NA | 2614 | 2613 | 2615 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.30.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.30.3 | Auto Scheduled | 0% | Simulate Load | No | 15.5h | Tue 9/29/26 | Thu 10/1/26 | Data Migration Team | 1582 | 1584 |  | NA | PTM_CM31_BOM Conversion | Tue 9/29/26 | Thu 10/1/26 | 1.2.4.2.30.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.4.2.30.4 | Fri 4/17/26 | 2615 | 2614 | 2616 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.30.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.30.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 0.5h | Thu 10/1/26 | Thu 10/1/26 | Brad Meseck | 1583 | 1585 | Matt Palastro, Dave Duda | NA | PTM_CM31_BOM Conversion | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.30.3 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 2026-04-01 | Fri 4/17/26 | 2616 | 2615 | 2617 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.30.4 | 6 | No | 500 | Future Task | No | 0h
2026-04-01 | Auto Scheduled | 0% | Load | No | 1h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1584 | 1586 |  | NA | PTM_CM31_BOM Conversion | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.30.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.30.6 | NA | 2617 | 2616 | 2618 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.30.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.30.6 | Auto Scheduled | 0% | Post Load Validation | No | 0.5h | Thu 10/1/26 | Thu 10/1/26 | Brad Meseck | 1585 | 1589 | Matt Palastro, Dave Duda | NA | PTM_CM31_BOM Conversion | Thu 10/1/26 | Thu 10/1/26 | 2026-04-01 | Thu 4/16/26 | Fri 4/17/26 | Finish No Earlier Than | 1.2.4.2.31.2 | Thu 4/16/26 | 2618 | 2617 | 2621 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.30.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.31 | Auto Scheduled | 0% | PTM_CM40_Work Center Conversion | No | 3.08d | Tue 9/29/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Fri 10/2/26 |  | Thu 4/16/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 2619 |  |  | -87.55d | Yes | Yes | Yes | No | No | 1.2.4.2.31 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.31.1 | Auto Scheduled | 0% | Extract File | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1581 | 1595 |  | NA | PTM_CM40_Work Center Conversion | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.30.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.32.1 | NA | 2620 | 2613 | 2627 | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.31.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.31.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 10/1/26 | Fri 10/2/26 | Brad Meseck | 1586 | 1590 | Matt Palastro, Dave Duda | NA | PTM_CM40_Work Center Conversion | Thu 10/1/26 | Fri 10/2/26 | 1.2.4.2.30.6 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.31.3 | NA | 2621 | 2618 | 2622 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.31.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.31.3 | Auto Scheduled | 0% | Simulate Load | No | 0.25h | Fri 10/2/26 | Fri 10/2/26 | Data Migration Team | 1589 | 1591 |  | NA | PTM_CM40_Work Center Conversion | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.31.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.31.4 | NA | 2622 | 2621 | 2623 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.31.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.31.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 0.5h | Fri 10/2/26 | Fri 10/2/26 | Brad Meseck | 1590 | 1592 | Matt Palastro, Dave Duda | NA | PTM_CM40_Work Center Conversion | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.31.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.31.5 | NA | 2623 | 2622 | 2624 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.31.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.31.5 | Auto Scheduled | 0% | Load | No | 1h | Fri 10/2/26 | Fri 10/2/26 | Data Migration Team | 1591 | 1593 |  | NA | PTM_CM40_Work Center Conversion | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.31.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.31.6 | NA | 2624 | 2623 | 2625 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.31.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.31.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Brad Meseck | 1592 | 1596 | Matt Palastro, Dave Duda | NA | PTM_CM40_Work Center Conversion | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.31.5 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.4.2.32.2 | NA | 2625 | 2624 | 2628 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.31.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.32 | Auto Scheduled | 0% | PTM_CM38_Routing Conversion | No | 4.27d | Tue 9/29/26 | Mon 10/5/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Mon 10/5/26 |  | Thu 4/16/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 2626 |  |  | -88.05d | Yes | Yes | Yes | No | No | 1.2.4.2.32 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.32.1 | Auto Scheduled | 0% | Extract File | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1588 | 1602 |  | NA | PTM_CM38_Routing Conversion | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.31.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.33.1 | NA | 2627 | 2620 | 2634 | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.32.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.32.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Fri 10/2/26 | Mon 10/5/26 | Brad Meseck | 1593 | 1597 | Matt Palastro, Dave Duda | NA | PTM_CM38_Routing Conversion | Fri 10/2/26 | Mon 10/5/26 | 1.2.4.2.31.6 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.4.2.32.3 | NA | 2628 | 2625 | 2629 | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.32.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.32.3 | Auto Scheduled | 0% | Simulate Load | No | 2h | Mon 10/5/26 | Mon 10/5/26 | Data Migration Team | 1596 | 1598SS |  | NA | PTM_CM38_Routing Conversion | Mon 10/5/26 | Mon 10/5/26 | 1.2.4.2.32.2 | Mon 4/20/26 | Mon 4/20/26 | Finish No Earlier Than | 1.2.4.2.32.4[SS] | Fri 4/17/26 | 2629 | 2628 | 2630SS | -700.38h | No | Yes | Yes | No | No | 1.2.4.2.32.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.32.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 3h | Mon 10/5/26 | Mon 10/5/26 | Brad Meseck | 1597SS | 1599 | Matt Palastro, Dave Duda | NA | PTM_CM38_Routing Conversion | Mon 10/5/26 | Mon 10/5/26 | 1.2.4.2.32.3[SS] | Mon 4/20/26 | Mon 4/20/26 | Start No Earlier Than | 1.2.4.2.32.5 | Fri 4/17/26 | 2630 | 2629SS | 2631 | -704.38h | No | Yes | Yes | No | No | 1.2.4.2.32.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.32.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 10/5/26 | Mon 10/5/26 | Data Migration Team | 1598 | 1600 |  | NA | PTM_CM38_Routing Conversion | Mon 10/5/26 | Mon 10/5/26 | 1.2.4.2.32.4 | Mon 4/20/26 | Mon 4/20/26 | Start No Earlier Than | 1.2.4.2.32.6 | Mon 4/20/26 | 2631 | 2630 | 2632 | -704.38h | No | Yes | Yes | No | No | 1.2.4.2.32.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.32.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 10/5/26 | Mon 10/5/26 | Brad Meseck | 1599 |  | Matt Palastro, Dave Duda | NA | PTM_CM38_Routing Conversion | Mon 10/5/26 | Mon 10/5/26 | 1.2.4.2.32.5 | Mon 4/20/26 | Tue 4/21/26 | Start No Earlier Than |  | Mon 4/20/26 | 2632 | 2631 |  | -704.38h | No | Yes | Yes | No | No | 1.2.4.2.32.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.33 | Auto Scheduled | 0% | PTM_CM36_Production Version Conversion | No | 1.13d | Tue 9/29/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Wed 9/30/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2633 |  |  | -86.97d | Yes | Yes | Yes | No | No | 1.2.4.2.33 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.33.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Brad Meseck | 1595 | 16031697 |  | NA | PTM_CM36_Production Version Conversion | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.32.1 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than | 1.2.4.2.33.2,1.2.4.2.53.1 | Mon 4/20/26 | 2634 | 2627 | 26352729 | -41745m | No | Yes | Yes | No | No | 1.2.4.2.33.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.33.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Brad Meseck | 1602 | 1604 | Matt Palastro, Dave Duda | NA | PTM_CM36_Production Version Conversion | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.33.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.33.3 | NA | 2635 | 2634 | 2636 | -41745m | No | Yes | Yes | No | No | 1.2.4.2.33.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.33.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 9/29/26 | Wed 9/30/26 | Data Migration Team | 1603 | 1605 |  | NA | PTM_CM36_Production Version Conversion | Tue 9/29/26 | Wed 9/30/26 | 1.2.4.2.33.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.33.4 | NA | 2636 | 2635 | 2637 | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.33.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.33.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Brad Meseck | 1604 | 1606 | Matt Palastro, Dave Duda | NA | PTM_CM36_Production Version Conversion | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.33.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.33.5 | NA | 2637 | 2636 | 2638 | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.33.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.33.5 | Auto Scheduled | 0% | Load | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1605 | 1607 |  | NA | PTM_CM36_Production Version Conversion | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.33.4 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.33.6 | NA | 2638 | 2637 | 2639 | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.33.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.33.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Brad Meseck | 1606 | 1609 | Matt Palastro, Dave Duda | NA | PTM_CM36_Production Version Conversion | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.33.5 | Fri 4/17/26 | Fri 4/17/26 | Finish No Earlier Than | 1.2.4.2.34.1 | Fri 4/17/26 | 2639 | 2638 | 2641 | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.33.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.34 | Auto Scheduled | 0% | PTM_CM35_Inspection Plan | No | 1.13d | Wed 9/30/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Fri 10/2/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 2640 |  |  | -86.97d | Yes | Yes | Yes | No | No | 1.2.4.2.34 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.34.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Wed 9/30/26 | Wed 9/30/26 | Brad Meseck | 1607 | 16101616 |  | NA | PTM_CM35_Inspection Plan | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.33.6 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.34.2,1.2.4.2.35.1 | NA | 2641 | 2639 | 26422648 | -41745m | No | Yes | Yes | No | No | 1.2.4.2.34.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.34.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Wed 9/30/26 | Thu 10/1/26 | Brad Meseck | 1609 | 1611 | Matt Palastro, Dave Duda | NA | PTM_CM35_Inspection Plan | Wed 9/30/26 | Thu 10/1/26 | 1.2.4.2.34.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.34.3 | NA | 2642 | 2641 | 2643 | -41355m | No | Yes | Yes | No | No | 1.2.4.2.34.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.34.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1610 | 1612 |  | NA | PTM_CM35_Inspection Plan | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.34.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.34.4 | NA | 2643 | 2642 | 2644 | -689.25h | No | Yes | Yes | No | No | 1.2.4.2.34.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.34.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Brad Meseck | 1611 | 1613 | Matt Palastro, Dave Duda | NA | PTM_CM35_Inspection Plan | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.34.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.34.5 | NA | 2644 | 2643 | 2645 | -689.25h | No | Yes | Yes | No | No | 1.2.4.2.34.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.34.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1612 | 1614 |  | NA | PTM_CM35_Inspection Plan | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.34.4 | Fri 4/17/26 | Mon 4/20/26 | Finish No Earlier Than | 1.2.4.2.34.6 | Fri 4/17/26 | 2645 | 2644 | 2646 | -689.25h | No | Yes | Yes | No | No | 1.2.4.2.34.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.34.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/1/26 | Fri 10/2/26 | Brad Meseck | 1613 |  | Matt Palastro, Dave Duda | NA | PTM_CM35_Inspection Plan | Thu 10/1/26 | Fri 10/2/26 | 1.2.4.2.34.5 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 2646 | 2645 |  | -689.25h | No | Yes | Yes | No | No | 1.2.4.2.34.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.35 | Auto Scheduled | 0% | PTM_CM48_Equipment_Master_Serial Numbers | No | 1.13d | Wed 9/30/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Fri 10/2/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 2647 |  |  | -86.97d | Yes | Yes | Yes | No | No | 1.2.4.2.35 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.35.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Wed 9/30/26 | Thu 10/1/26 | Brad Meseck | 1609 | 1617 |  | NA | PTM_CM48_Equipment_Master_Serial Numbers | Wed 9/30/26 | Thu 10/1/26 | 1.2.4.2.34.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.35.2 | NA | 2648 | 2641 | 2649 | -41745m | No | Yes | Yes | No | No | 1.2.4.2.35.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.35.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 10/1/26 | Thu 10/1/26 | Brad Meseck | 1616 | 1618 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Serial Numbers | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.35.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.35.3 | NA | 2649 | 2648 | 2650 | -41745m | No | Yes | Yes | No | No | 1.2.4.2.35.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.35.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1617 | 1619 |  | NA | PTM_CM48_Equipment_Master_Serial Numbers | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.35.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.35.4 | NA | 2650 | 2649 | 2651 | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.35.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.35.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Brad Meseck | 1618 | 1620 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Serial Numbers | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.35.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.35.5 | NA | 2651 | 2650 | 2652 | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.35.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.35.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1619 | 1621 |  | NA | PTM_CM48_Equipment_Master_Serial Numbers | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.35.4 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.4.2.35.6 | NA | 2652 | 2651 | 2653 | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.35.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.35.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/1/26 | Fri 10/2/26 | Brad Meseck | 1620 | 1623 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Serial Numbers | Thu 10/1/26 | Fri 10/2/26 | 1.2.4.2.35.5 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.4.2.36.1 | NA | 2653 | 2652 | 2655 | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.35.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.36 | Auto Scheduled | 0% | PTM_CM48_Equipment_Master_Service | No | 6.78d | Thu 9/24/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 10/2/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 2654 |  |  | -86.97d | Yes | Yes | Yes | No | No | 1.2.4.2.36 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.36.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Fri 10/2/26 | Fri 10/2/26 | Brad Meseck | 1621 | 1624 |  | NA | PTM_CM48_Equipment_Master_Service | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.35.6 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.4.2.36.2 | NA | 2655 | 2653 | 2656 | -41745m | No | Yes | Yes | No | No | 1.2.4.2.36.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.36.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Fri 10/2/26 | Fri 10/2/26 | Brad Meseck | 1623 | 1625 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Service | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.36.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.4.2.36.3 | NA | 2656 | 2655 | 2657 | -41745m | No | Yes | Yes | No | No | 1.2.4.2.36.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.36.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 10/2/26 | Fri 10/2/26 | Data Migration Team | 1624 | 1626 |  | NA | PTM_CM48_Equipment_Master_Service | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.36.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.4.2.36.4 | NA | 2657 | 2656 | 2658 | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.36.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.36.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Brad Meseck | 1625 | 1627 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Service | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.36.3 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible | 1.2.4.2.36.5 | NA | 2658 | 2657 | 2659 | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.36.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.36.5 | Auto Scheduled | 0% | Load | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Data Migration Team | 1626 |  |  | NA | PTM_CM48_Equipment_Master_Service | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.36.4 | Tue 4/21/26 | Tue 4/21/26 | Finish No Earlier Than |  | Tue 4/21/26 | 2659 | 2658 |  | -695.75h | No | Yes | Yes | No | No | 1.2.4.2.36.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.36.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Thu 9/24/26 | Brad Meseck |  |  | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Service | Thu 9/24/26 | Thu 9/24/26 |  | Tue 4/21/26 | Tue 4/21/26 | Start No Earlier Than |  | Tue 4/21/26 | 2660 |  |  | -644.5h | No | Yes | Yes | No | No | 1.2.4.2.36.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.37 | Auto Scheduled | 0% | VC_Object Dependencies | No | 0.63d | Thu 9/24/26 | Thu 9/24/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 2661 |  |  | -82.69d | Yes | Yes | Yes | No | No | 1.2.4.2.37 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.37.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Eric Heisler | 1390 | 1631 |  | NA | VC_Object Dependencies | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.4.2.37.2 | NA | 2662 | 2423 | 2663 | -661.5h | No | Yes | Yes | No | No | 1.2.4.2.37.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.37.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Thu 9/24/26 | Eric Heisler | 1630 | 1633 | Matt Palastro, Dave Duda | NA | VC_Object Dependencies | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.37.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.4.2.38.1 | NA | 2663 | 2662 | 2665 | -661.5h | No | Yes | Yes | No | No | 1.2.4.2.37.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.38 | Auto Scheduled | 0% | VC_Characteristics | No | 0.63d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 2664 |  |  | -82.69d | Yes | Yes | Yes | No | No | 1.2.4.2.38 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.38.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Eric Heisler | 1631 | 1634 |  | NA | VC_Characteristics | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.37.2 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.4.2.38.2 | NA | 2665 | 2663 | 2666 | -661.5h | No | Yes | Yes | No | No | 1.2.4.2.38.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.38.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Fri 9/25/26 | Eric Heisler | 1633 | 1636 | Matt Palastro, Dave Duda | NA | VC_Characteristics | Thu 9/24/26 | Fri 9/25/26 | 1.2.4.2.38.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.39.1 | NA | 2666 | 2665 | 2668 | -661.5h | No | Yes | Yes | No | No | 1.2.4.2.38.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.39 | Auto Scheduled | 0% | VC_Classes | No | 0.63d | Fri 9/25/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Fri 9/25/26 |  | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 2667 |  |  | -82.69d | Yes | Yes | Yes | No | No | 1.2.4.2.39 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.39.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Eric Heisler | 1634 | 1637 |  | NA | VC_Classes | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.38.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.39.2 | NA | 2668 | 2666 | 2669 | -661.5h | No | Yes | Yes | No | No | 1.2.4.2.39.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.39.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 9/25/26 | Fri 9/25/26 | Eric Heisler | 1636 | 1642 | Matt Palastro, Dave Duda | NA | VC_Classes | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.39.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.4.2.41.1 | NA | 2669 | 2668 | 2674 | -661.5h | No | Yes | Yes | No | No | 1.2.4.2.39.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.40 | Auto Scheduled | 0% | VC_Classification (Class Type 200) | No | 0.63d | Tue 9/29/26 | Tue 9/29/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Tue 9/29/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2670 |  |  | -84.03d | Yes | Yes | Yes | No | No | 1.2.4.2.40 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.40.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 1558 | 1640 |  | NA | VC_Classification (Class Type 200) | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.26.6 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.40.2 | NA | 2671 | 2590 | 2672 | -672.25h | No | Yes | Yes | No | No | 1.2.4.2.40.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.40.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 1639 |  | Matt Palastro, Dave Duda | NA | VC_Classification (Class Type 200) | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.40.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2672 | 2671 |  | -672.25h | No | Yes | Yes | No | No | 1.2.4.2.40.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.41 | Auto Scheduled | 0% | VC_Dependency Nets | No | 0.63d | Tue 9/29/26 | Tue 9/29/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Tue 9/29/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2673 |  |  | -84.03d | Yes | Yes | Yes | No | No | 1.2.4.2.41 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.41.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 15521637 | 1643 |  | NA | VC_Dependency Nets | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.26,1.2.4.2.39.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.41.2 | NA | 2674 | 25842669 | 2675 | -672.25h | No | Yes | Yes | No | No | 1.2.4.2.41.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.41.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 1642 |  | Matt Palastro, Dave Duda | NA | VC_Dependency Nets | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.41.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2675 | 2674 |  | -672.25h | No | Yes | Yes | No | No | 1.2.4.2.41.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.42 | Auto Scheduled | 0% | VC_Configuration Profiles | No | 0.63d | Tue 9/29/26 | Tue 9/29/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Tue 9/29/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2676 |  |  | -86d | Yes | Yes | Yes | No | No | 1.2.4.2.42 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.42.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 1552 | 1646 |  | NA | VC_Configuration Profiles | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.26 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.42.2 | NA | 2677 | 2584 | 2678 | -688h | No | Yes | Yes | No | No | 1.2.4.2.42.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.42.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 1645 | 16541648 | Matt Palastro, Dave Duda | NA | VC_Configuration Profiles | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.42.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.45.1,1.2.4.2.43.1 | NA | 2678 | 2677 | 26862680 | -688h | No | Yes | Yes | No | No | 1.2.4.2.42.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.43 | Auto Scheduled | 0% | VC_Variant Tables | No | 0.63d | Tue 9/29/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Wed 9/30/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2679 |  |  | -85.28d | Yes | Yes | Yes | No | No | 1.2.4.2.43 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.43.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Tue 9/29/26 | Wed 9/30/26 | Eric Heisler | 1646 | 1649 |  | NA | VC_Variant Tables | Tue 9/29/26 | Wed 9/30/26 | 1.2.4.2.42.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.43.2 | NA | 2680 | 2678 | 2681 | -682.25h | No | Yes | Yes | No | No | 1.2.4.2.43.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.43.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Eric Heisler | 1648 | 1651 | Matt Palastro, Dave Duda | NA | VC_Variant Tables | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.43.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.44.1 | NA | 2681 | 2680 | 2683 | -682.25h | No | Yes | Yes | No | No | 1.2.4.2.43.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.44 | Auto Scheduled | 0% | VC_Variant Tables Content | No | 0.63d | Wed 9/30/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Thu 10/1/26 |  | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2682 |  |  | -85.28d | Yes | Yes | Yes | No | No | 1.2.4.2.44 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.44.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Eric Heisler | 1649 | 1652 |  | NA | VC_Variant Tables Content | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.43.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.44.2 | NA | 2683 | 2681 | 2684 | -682.25h | No | Yes | Yes | No | No | 1.2.4.2.44.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.44.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Thu 10/1/26 | Eric Heisler | 1651 |  | Matt Palastro, Dave Duda | NA | VC_Variant Tables Content | Wed 9/30/26 | Thu 10/1/26 | 1.2.4.2.44.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2684 | 2683 |  | -682.25h | No | Yes | Yes | No | No | 1.2.4.2.44.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.45 | Auto Scheduled | 0% | VC_Characteristic Groups | No | 1.97d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2685 |  |  | -86d | Yes | Yes | Yes | No | No | 1.2.4.2.45 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.45.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 12.75h | Tue 9/29/26 | Thu 10/1/26 | Eric Heisler | 1646 | 1655 |  | NA | VC_Characteristic Groups | Tue 9/29/26 | Thu 10/1/26 | 1.2.4.2.42.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.4.2.45.2 | Fri 4/17/26 | 2686 | 2678 | 2687 | -688h | No | Yes | Yes | No | No | 1.2.4.2.45.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.45.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/1/26 | Thu 10/1/26 | Eric Heisler | 1654 |  | Matt Palastro, Dave Duda | NA | VC_Characteristic Groups | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.45.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2687 | 2686 |  | -688h | No | Yes | Yes | No | No | 1.2.4.2.45.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.46 | Auto Scheduled | 0% | PTM_CM52_Super_BOM | No | 4.09d | Tue 9/29/26 | Mon 10/5/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Mon 10/5/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2688 |  |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.4.2.46 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.46.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 1558 | 1658 |  | NA | PTM_CM52_Super_BOM | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.46.2 | NA | 2689 | 2590 | 2690 | -43560m | No | Yes | Yes | No | No | 1.2.4.2.46.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.46.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 1657 | 1659 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.46.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.46.3 | NA | 2690 | 2689 | 2691 | -43560m | No | Yes | Yes | No | No | 1.2.4.2.46.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.46.3 | Auto Scheduled | 0% | Simulate Load | No | 24.75h | Tue 9/29/26 | Fri 10/2/26 | Data Migration Team | 1658 | 1660 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Tue 9/29/26 | Fri 10/2/26 | 1.2.4.2.46.2 | Wed 4/15/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.4.2.46.4 | Mon 4/20/26 | 2691 | 2690 | 2692 | -726h | No | Yes | Yes | No | No | 1.2.4.2.46.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.46.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Eric Heisler | 1659 | 1661 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.46.3 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.4.2.46.5 | Fri 4/17/26 | 2692 | 2691 | 2693 | -726h | No | Yes | Yes | No | No | 1.2.4.2.46.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.46.5 | Auto Scheduled | 0% | Load | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Data Migration Team | 1660 | 1662 |  | NA | PTM_CM52_Super_BOM | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.46.4 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than | 1.2.4.2.46.6 | Fri 4/17/26 | 2693 | 2692 | 2694 | -726h | No | Yes | Yes | No | No | 1.2.4.2.46.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.46.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 10/5/26 | Mon 10/5/26 | Eric Heisler | 1661 | 1664 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Mon 10/5/26 | Mon 10/5/26 | 1.2.4.2.46.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.47.1 | NA | 2694 | 2693 | 2696 | -726h | No | Yes | Yes | No | No | 1.2.4.2.46.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.47 | Auto Scheduled | 0% | PTM_CM53_Super_Routing | No | 2.13d | Mon 10/5/26 | Wed 10/7/26 |  |  |  |  | NA | Master Data Loads | Mon 10/5/26 | Wed 10/7/26 |  | Thu 4/16/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 2695 |  |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.4.2.47 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.47.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 10/5/26 | Mon 10/5/26 | Eric Heisler | 1662 | 1665 |  | NA | PTM_CM53_Super_Routing | Mon 10/5/26 | Mon 10/5/26 | 1.2.4.2.46.6 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.47.2 | NA | 2696 | 2694 | 2697 | -43560m | No | Yes | Yes | No | No | 1.2.4.2.47.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.47.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 10/5/26 | Mon 10/5/26 | Eric Heisler | 1664 | 1666 | Matt Palastro, Dave Duda | NA | PTM_CM53_Super_Routing | Mon 10/5/26 | Mon 10/5/26 | 1.2.4.2.47.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.47.3 | NA | 2697 | 2696 | 2698 | -43560m | No | Yes | Yes | No | No | 1.2.4.2.47.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.47.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 10/5/26 | Tue 10/6/26 | Data Migration Team | 1665 | 1667 |  | NA | PTM_CM53_Super_Routing | Mon 10/5/26 | Tue 10/6/26 | 1.2.4.2.47.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.47.4 | NA | 2698 | 2697 | 2699 | -726h | No | Yes | Yes | No | No | 1.2.4.2.47.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.47.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 10/6/26 | Tue 10/6/26 | Eric Heisler | 1666 | 1668 | Matt Palastro, Dave Duda | NA | PTM_CM53_Super_Routing | Tue 10/6/26 | Tue 10/6/26 | 1.2.4.2.47.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.47.5 | NA | 2699 | 2698 | 2700 | -726h | No | Yes | Yes | No | No | 1.2.4.2.47.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.47.5 | Auto Scheduled | 0% | Load | No | 2h | Tue 10/6/26 | Wed 10/7/26 | Data Migration Team | 1667 | 16691671 |  | NA | PTM_CM53_Super_Routing | Tue 10/6/26 | Wed 10/7/26 | 1.2.4.2.47.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.47.6,1.2.4.2.48.1 | NA | 2700 | 2699 | 27012703 | -726h | No | Yes | Yes | No | No | 1.2.4.2.47.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.47.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 10/7/26 | Wed 10/7/26 | Eric Heisler | 1668 |  | Matt Palastro, Dave Duda | NA | PTM_CM53_Super_Routing | Wed 10/7/26 | Wed 10/7/26 | 1.2.4.2.47.5 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 2701 | 2700 |  | -717h | No | Yes | Yes | No | No | 1.2.4.2.47.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.48 | Auto Scheduled | 0% | VC_VK30 Pricing Variant | No | 0.69d | Wed 10/7/26 | Wed 10/7/26 |  |  |  |  | NA | Master Data Loads | Wed 10/7/26 | Wed 10/7/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 2702 |  |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.4.2.48 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.48.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Wed 10/7/26 | Wed 10/7/26 | Eric Heisler | 1668 | 1672 | Matt Palastro, Dave Duda | NA | VC_VK30 Pricing Variant | Wed 10/7/26 | Wed 10/7/26 | 1.2.4.2.47.5 | Fri 4/17/26 | Fri 4/17/26 | Start No Earlier Than | 1.2.4.2.48.2 | Mon 4/6/26 | 2703 | 2700 | 2704 | -43560m | No | Yes | Yes | No | No | 1.2.4.2.48.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.48.2 | Auto Scheduled | 0% | Load | No | 2h | Wed 10/7/26 | Wed 10/7/26 | Eric Heisler | 1671 | 1673 |  | NA | VC_VK30 Pricing Variant | Wed 10/7/26 | Wed 10/7/26 | 1.2.4.2.48.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.48.3 | NA | 2704 | 2703 | 2705 | -726h | No | Yes | Yes | No | No | 1.2.4.2.48.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.48.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 10/7/26 | Wed 10/7/26 | Eric Heisler | 1672 | 1675 | Matt Palastro, Dave Duda | NA | VC_VK30 Pricing Variant | Wed 10/7/26 | Wed 10/7/26 | 1.2.4.2.48.2 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.4.2.49.1 | NA | 2705 | 2704 | 2707 | -726h | No | Yes | Yes | No | No | 1.2.4.2.48.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.49 | Auto Scheduled | 0% | OTC_CM22_Pricing_Condition | No | 0.69d | Wed 10/7/26 | Thu 10/8/26 |  |  |  |  | NA | Master Data Loads | Wed 10/7/26 | Thu 10/8/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 2706 |  |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.4.2.49 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.49.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Wed 10/7/26 | Wed 10/7/26 | Ric Haraida | 1673 | 1676 | Matt Palastro, Dave Duda | NA | OTC_CM22_Pricing_Condition | Wed 10/7/26 | Wed 10/7/26 | 1.2.4.2.48.3 | Mon 4/20/26 | Mon 4/20/26 | Start No Earlier Than | 1.2.4.2.49.2 | Mon 4/6/26 | 2707 | 2705 | 2708 | -43560m | No | Yes | Yes | No | No | 1.2.4.2.49.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.49.2 | Auto Scheduled | 0% | Load | No | 2h | Wed 10/7/26 | Thu 10/8/26 | Ric Haraida | 1675 | 16771679 |  | NA | OTC_CM22_Pricing_Condition | Wed 10/7/26 | Thu 10/8/26 | 1.2.4.2.49.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.4.2.49.3,1.2.4.2.50.1 | NA | 2708 | 2707 | 27092711 | -726h | No | Yes | Yes | No | No | 1.2.4.2.49.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.49.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/8/26 | Thu 10/8/26 | Ric Haraida,Kim Kolesar | 1676 |  | Matt Palastro, Dave Duda,kim | NA | OTC_CM22_Pricing_Condition | Thu 10/8/26 | Thu 10/8/26 | 1.2.4.2.49.2 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 2709 | 2708 |  | -725h | No | Yes | Yes | No | No | 1.2.4.2.49.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.50 | Auto Scheduled | 0% | OTC_CM21_CMIR | No | 0.5d | Thu 10/8/26 | Thu 10/8/26 |  |  |  |  | NA | Master Data Loads | Thu 10/8/26 | Thu 10/8/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 2710 |  |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.4.2.50 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.50.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 10/8/26 | Thu 10/8/26 | Ric Haraida | 16761687 | 1680 |  | NA | OTC_CM21_CMIR | Thu 10/8/26 | Thu 10/8/26 | 1.2.4.2.49.2,1.2.4.2.51.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.4.2.50.2 | NA | 2711 | 27082719 | 2712 | -43560m | No | Yes | Yes | No | No | 1.2.4.2.50.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.50.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 10/8/26 | Thu 10/8/26 | Ric Haraida | 1679 | 1681 | Kim | NA | OTC_CM21_CMIR | Thu 10/8/26 | Thu 10/8/26 | 1.2.4.2.50.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.4.2.50.3 | NA | 2712 | 2711 | 2713 | -43560m | No | Yes | Yes | No | No | 1.2.4.2.50.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.50.3 | Auto Scheduled | 0% | Simulate Load | No | 0h | Thu 10/8/26 | Thu 10/8/26 | Data Migration Team | 1680 | 1682 |  | NA | OTC_CM21_CMIR | Thu 10/8/26 | Thu 10/8/26 | 1.2.4.2.50.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.4.2.50.4 | NA | 2713 | 2712 | 2714 | -726h | No | Yes | Yes | Yes | No | 1.2.4.2.50.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.50.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 0h | Thu 10/8/26 | Thu 10/8/26 | Ric Haraida | 1681 | 1683 | Kim | NA | OTC_CM21_CMIR | Thu 10/8/26 | Thu 10/8/26 | 1.2.4.2.50.3 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible | 1.2.4.2.50.5 | NA | 2714 | 2713 | 2715 | -726h | No | Yes | Yes | Yes | No | 1.2.4.2.50.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.50.5 | Auto Scheduled | 0% | Load | No | 0h | Thu 10/8/26 | Thu 10/8/26 | Data Migration Team | 1682 | 1684 |  | NA | OTC_CM21_CMIR | Thu 10/8/26 | Thu 10/8/26 | 1.2.4.2.50.4 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible | 1.2.4.2.50.6 | NA | 2715 | 2714 | 2716 | -726h | No | Yes | Yes | Yes | No | 1.2.4.2.50.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.50.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/8/26 | Thu 10/8/26 | Ric Haraida | 1683 |  | Kim | NA | OTC_CM21_CMIR | Thu 10/8/26 | Thu 10/8/26 | 1.2.4.2.50.5 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 2716 | 2715 |  | -726h | No | Yes | Yes | No | No | 1.2.4.2.50.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.51 | Auto Scheduled | 0% | PTP_CM29_Source_List | No | 6.16d | Fri 9/25/26 | Mon 10/5/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Mon 10/5/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 2717 |  |  | -87.47d | Yes | Yes | Yes | No | No | 1.2.4.2.51 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.51.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Fri 9/25/26 | Fri 9/25/26 | Nevin Varkey | 15291536 |  | Sam | NA | PTP_CM29_Source_List | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.22.5,1.2.4.2.23.5 | Tue 4/14/26 | Tue 4/14/26 | Start No Earlier Than |  | Fri 4/17/26 | 2718 | 25612568 |  | -39060m | No | Yes | Yes | No | No | 1.2.4.2.51.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.51.2 | Auto Scheduled | 0% | Load | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Nevin Varkey | 1505 | 16791688 |  | NA | PTP_CM29_Source_List | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.18.6 | Mon 4/13/26 | Mon 4/13/26 | Finish No Earlier Than | 1.2.4.2.50.1,1.2.4.2.51.3 | Fri 4/17/26 | 2719 | 2537 | 27112720 | -700.75h | No | Yes | Yes | No | No | 1.2.4.2.51.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.51.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 10/2/26 | Mon 10/5/26 | Nevin Varkey | 1687 |  | Sam | NA | PTP_CM29_Source_List | Fri 10/2/26 | Mon 10/5/26 | 1.2.4.2.51.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2720 | 2719 |  | -699.75h | No | Yes | Yes | No | No | 1.2.4.2.51.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.52 | Auto Scheduled | 0% | RTR_CM11_Asset_Master | No | 6.63d | Thu 9/24/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 10/2/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2721 |  |  | -86.81d | Yes | Yes | Yes | No | No | 1.2.4.2.52 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.52.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes |  | 16911745 |  | NA | RTR_CM11_Asset_Master | Thu 9/24/26 | Thu 9/24/26 |  | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.4.2.52.2,1.2.4.2.67.1 | Wed 4/15/26 | 2722 |  | 27232777 | -41670m | No | Yes | Yes | No | No | 1.2.4.2.52.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.52.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes,Femi Oguntala | 1690 | 1692 | Brian Wagner | NA | RTR_CM11_Asset_Master | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.52.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.52.3 | NA | 2723 | 2722 | 2724 | -41670m | No | Yes | Yes | No | No | 1.2.4.2.52.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.52.3 | Auto Scheduled | 0% | Simulate Load | No | 31h | Thu 9/24/26 | Wed 9/30/26 | Data Migration Team | 1691 | 1693 |  | NA | RTR_CM11_Asset_Master | Thu 9/24/26 | Wed 9/30/26 | 1.2.4.2.52.2 | Fri 4/10/26 | Fri 4/10/26 | Finish No Earlier Than | 1.2.4.2.52.4 | Mon 4/20/26 | 2724 | 2723 | 2725 | -694.5h | No | Yes | Yes | No | No | 1.2.4.2.52.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.52.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 16h | Wed 9/30/26 | Fri 10/2/26 | Kasey Hughes | 1692 | 1694 | Brian Wagner | NA | RTR_CM11_Asset_Master | Wed 9/30/26 | Fri 10/2/26 | 1.2.4.2.52.3 | Fri 4/10/26 | Fri 4/10/26 | Finish No Earlier Than | 1.2.4.2.52.5 | Fri 4/17/26 | 2725 | 2724 | 2726 | -694.5h | No | Yes | Yes | No | No | 1.2.4.2.52.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.52.5 | Auto Scheduled | 0% | Load | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Data Migration Team | 1693 | 1695 |  | NA | RTR_CM11_Asset_Master | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.52.4 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.4.2.52.6 | Fri 4/17/26 | 2726 | 2725 | 2727 | -694.5h | No | Yes | Yes | No | No | 1.2.4.2.52.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.52.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 10/2/26 | Fri 10/2/26 | Kasey Hughes | 1694 |  | Brian Wagner | NA | RTR_CM11_Asset_Master | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.52.5 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2727 | 2726 |  | -694.5h | No | Yes | Yes | No | No | 1.2.4.2.52.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.53 | Auto Scheduled | 0% | PTM_CM50_Material Class | No | 2.13d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2728 |  |  | -86.09d | Yes | Yes | Yes | No | No | 1.2.4.2.53 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.53.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Sam | 1602 | 16981701 |  | NA | PTM_CM50_Material Class | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.33.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.53.2,1.2.4.2.54.1 | NA | 2729 | 2634 | 27302733 | -41325m | No | Yes | Yes | No | No | 1.2.4.2.53.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.53.2 | Auto Scheduled | 0% | Load | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Brad Meseck | 1697 | 1699 | Matt Palastro, Dave Duda | NA | PTM_CM50_Material Class | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.53.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.53.3 | NA | 2730 | 2729 | 2731 | -41325m | No | Yes | Yes | No | No | 1.2.4.2.53.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.53.3 | Auto Scheduled | 0% | Post Load Validation | No | 16h | Tue 9/29/26 | Thu 10/1/26 | Brad | 1698 |  | brad | NA | PTM_CM50_Material Class | Tue 9/29/26 | Thu 10/1/26 | 1.2.4.2.53.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than |  | Mon 4/20/26 | 2731 | 2730 |  | -688.75h | No | Yes | Yes | No | No | 1.2.4.2.53.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.54 | Auto Scheduled | 0% | PTM_CM55_Class assignment to materials | No | 1.13d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2732 |  |  | -85.16d | Yes | Yes | Yes | No | No | 1.2.4.2.54 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.54.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Sam | 1697 | 1702 |  | NA | PTM_CM55_Class assignment to materials | Tue 9/29/26 | Tue 9/29/26 | 1.2.4.2.53.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.54.2 | NA | 2733 | 2729 | 2734 | -40875m | No | Yes | Yes | No | No | 1.2.4.2.54.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.54.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Wed 9/30/26 | Brad Meseck | 1701 | 1703 | Matt Palastro, Dave Duda | NA | PTM_CM55_Class assignment to materials | Tue 9/29/26 | Wed 9/30/26 | 1.2.4.2.54.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.54.3 | NA | 2734 | 2733 | 2735 | -40875m | No | Yes | Yes | No | No | 1.2.4.2.54.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.54.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1702 | 1704 |  | NA | PTM_CM55_Class assignment to materials | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.54.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.54.4 | NA | 2735 | 2734 | 2736 | -681.25h | No | Yes | Yes | No | No | 1.2.4.2.54.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.54.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Brad Meseck | 1703 | 1705 | Matt Palastro, Dave Duda | NA | PTM_CM55_Class assignment to materials | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.54.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.54.5 | NA | 2736 | 2735 | 2737 | -681.25h | No | Yes | Yes | No | No | 1.2.4.2.54.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.54.5 | Auto Scheduled | 0% | Load | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1704 | 1706 |  | NA | PTM_CM55_Class assignment to materials | Wed 9/30/26 | Wed 9/30/26 | 1.2.4.2.54.4 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.54.6 | NA | 2737 | 2736 | 2738 | -681.25h | No | Yes | Yes | No | No | 1.2.4.2.54.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.54.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Thu 10/1/26 | Brad Meseck | 1705 |  | Matt Palastro, Dave Duda | NA | PTM_CM55_Class assignment to materials | Wed 9/30/26 | Thu 10/1/26 | 1.2.4.2.54.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2738 | 2737 |  | -681.25h | No | Yes | Yes | No | No | 1.2.4.2.54.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.55 | Auto Scheduled | 0% | GTS - Material initial load from S4 (Run Interface) | No | 2.09d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2739 |  |  | -89.03d | Yes | Yes | Yes | No | No | 1.2.4.2.55 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.55.1 | Auto Scheduled | 0% | Run material interface to GTS | No | 15.75h | Tue 9/29/26 | Thu 10/1/26 | James Van Riper | 1576 | 1709 |  | NA | GTS - Material initial load from S4 (Run Interface) | Tue 9/29/26 | Thu 10/1/26 | 1.2.4.2.29.3 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.4.2.55.2 | Fri 4/17/26 | 2740 | 2608 | 2741 | -712.25h | No | Yes | Yes | No | No | 1.2.4.2.55.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.55.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Thu 10/1/26 | Thu 10/1/26 | James Van Riper | 1708 | 1720 | Kim Kolesar | NA | GTS - Material initial load from S4 (Run Interface) | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.55.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.59.1 | NA | 2741 | 2740 | 2752 | -712.25h | No | Yes | Yes | No | No | 1.2.4.2.55.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.56 | Auto Scheduled | 0% | GTS - Customers initial load from S4 (Run Interface) | No | 0.25d | Thu 9/24/26 | Thu 9/24/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Thu 9/24/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 2742 |  |  | -80.44d | Yes | Yes | Yes | No | No | 1.2.4.2.56 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.56.1 | Auto Scheduled | 0% | Run material interface to GTS | No | 1h | Thu 9/24/26 | Thu 9/24/26 | James Van Riper |  | 1712 |  | NA | GTS - Customers initial load from S4 (Run Interface) | Thu 9/24/26 | Thu 9/24/26 |  | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.4.2.56.2 | Wed 4/15/26 | 2743 |  | 2744 | -643.5h | No | Yes | Yes | No | No | 1.2.4.2.56.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.56.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Thu 9/24/26 | Thu 9/24/26 | James Van Riper | 1711 |  | Kim Kolesar | NA | GTS - Customers initial load from S4 (Run Interface) | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.56.1 | Fri 4/10/26 | Fri 4/10/26 | Finish No Earlier Than |  | Mon 4/20/26 | 2744 | 2743 |  | -643.5h | No | Yes | Yes | No | No | 1.2.4.2.56.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.57 | Auto Scheduled | 0% | GTS - Vendors initial load from S4 (Run Interface) | No | 0.25d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2745 |  |  | -81.69d | Yes | Yes | Yes | No | No | 1.2.4.2.57 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.57.1 | Auto Scheduled | 0% | Run material interface to GTS | No | 1h | Thu 9/24/26 | Fri 9/25/26 | James Van Riper | 1519 | 17151718 |  | NA | GTS - Vendors initial load from S4 (Run Interface) | Thu 9/24/26 | Fri 9/25/26 | 1.2.4.2.20.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.4.2.57.2,1.2.4.2.58.2 | NA | 2746 | 2551 | 27472750 | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.57.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.57.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 9/25/26 | Fri 9/25/26 | James Van Riper | 1714 |  | Kim Kolesar | NA | GTS - Vendors initial load from S4 (Run Interface) | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.57.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 2747 | 2746 |  | -650.5h | No | Yes | Yes | No | No | 1.2.4.2.57.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.58 | Auto Scheduled | 0% | GTS - ECCN - Create | No | 1.13d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Mon 4/6/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 2748 |  |  | -81.31d | Yes | Yes | Yes | No | No | 1.2.4.2.58 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.58.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Thu 9/24/26 | Thu 9/24/26 | James Van Riper | 1390 |  |  | NA | GTS - ECCN - Create | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 2749 | 2423 |  | -642.5h | No | Yes | Yes | No | No | 1.2.4.2.58.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.58.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 9/25/26 | Fri 9/25/26 | James Van Riper | 1714 | 1738 | Kim Kolesar | NA | GTS - ECCN - Create | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.57.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.65.1 | NA | 2750 | 2746 | 2770 | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.58.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.59 | Auto Scheduled | 0% | GTS - ECCN - Assign | No | 0.25d | Thu 10/1/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Thu 10/1/26 | Thu 10/1/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2751 |  |  | -89.03d | Yes | Yes | Yes | No | No | 1.2.4.2.59 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.59.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Thu 10/1/26 | Thu 10/1/26 | James Van Riper | 1709 | 1721 |  | NA | GTS - ECCN - Assign | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.55.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.4.2.59.2 | Fri 4/17/26 | 2752 | 2741 | 2753 | -712.25h | No | Yes | Yes | No | No | 1.2.4.2.59.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.59.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Thu 10/1/26 | Thu 10/1/26 | James Van Riper | 1720 | 1726 | Kim Kolesar | NA | GTS - ECCN - Assign | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.59.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.61.1 | NA | 2753 | 2752 | 2758 | -712.25h | No | Yes | Yes | No | No | 1.2.4.2.59.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.60 | Auto Scheduled | 0% | GTS - HTS - Create | No | 0.25d | Thu 9/24/26 | Thu 9/24/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 2754 |  |  | -80.44d | Yes | Yes | Yes | No | No | 1.2.4.2.60 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.60.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Thu 9/24/26 | Thu 9/24/26 | James Van Riper | 1390 | 1724 |  | NA | GTS - HTS - Create | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.4.2.60.2 | NA | 2755 | 2423 | 2756 | -643.5h | No | Yes | Yes | No | No | 1.2.4.2.60.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.60.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Thu 9/24/26 | Thu 9/24/26 | James Van Riper | 1723 |  | Kim Kolesar | NA | GTS - HTS - Create | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.60.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 2756 | 2755 |  | -643.5h | No | Yes | Yes | No | No | 1.2.4.2.60.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.61 | Auto Scheduled | 0% | GTS - HTS - Assign | No | 0.25d | Thu 10/1/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Thu 10/1/26 | Fri 10/2/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2757 |  |  | -89.03d | Yes | Yes | Yes | No | No | 1.2.4.2.61 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.61.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Thu 10/1/26 | Thu 10/1/26 | James Van Riper | 1721 | 172717291735 |  | NA | GTS - HTS - Assign | Thu 10/1/26 | Thu 10/1/26 | 1.2.4.2.59.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.61.2,1.2.4.2.62.1,1.2.4.2.64.1 | NA | 2758 | 2753 | 275927612767 | -712.25h | No | Yes | Yes | No | No | 1.2.4.2.61.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.61.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 1726 | 17421732 | Kim Kolesar | NA | GTS - HTS - Assign | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.61.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.66.1,1.2.4.2.63.1 | NA | 2759 | 2758 | 27742764 | -712.25h | No | Yes | Yes | No | No | 1.2.4.2.61.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.62 | Auto Scheduled | 0% | GTS - License - Create | No | 0.25d | Fri 10/2/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Fri 10/2/26 | Fri 10/2/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2760 |  |  | -86.63d | Yes | Yes | Yes | No | No | 1.2.4.2.62 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.62.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 17261742 | 1730 |  | NA | GTS - License - Create | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.61.1,1.2.4.2.66.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.62.2 | NA | 2761 | 27582774 | 2762 | -693h | No | Yes | Yes | No | No | 1.2.4.2.62.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.62.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 1729 |  | Kim Kolesar | NA | GTS - License - Create | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.62.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2762 | 2761 |  | -693h | No | Yes | Yes | No | No | 1.2.4.2.62.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.63 | Auto Scheduled | 0% | Commodity Code/Tarif | No | 2.78d | Fri 10/2/26 | Tue 10/6/26 |  |  |  |  | NA | Master Data Loads | Fri 10/2/26 | Tue 10/6/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2763 |  |  | -89.03d | Yes | Yes | Yes | No | No | 1.2.4.2.63 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.63.1 | Auto Scheduled | 0% | Load | No | 21.25h | Fri 10/2/26 | Tue 10/6/26 | James Van Riper | 1727 | 1733 |  | NA | Commodity Code/Tarif | Fri 10/2/26 | Tue 10/6/26 | 1.2.4.2.61.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.4.2.63.2 | Mon 4/20/26 | 2764 | 2759 | 2765 | -712.25h | No | Yes | Yes | No | No | 1.2.4.2.63.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.63.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 10/6/26 | Tue 10/6/26 | James Van Riper | 1732 |  | Kim Kolesar | NA | Commodity Code/Tarif | Tue 10/6/26 | Tue 10/6/26 | 1.2.4.2.63.1 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than |  | Fri 4/17/26 | 2765 | 2764 |  | -712.25h | No | Yes | Yes | No | No | 1.2.4.2.63.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.64 | Auto Scheduled | 0% | SPL Master File | No | 0.25d | Fri 10/2/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Fri 10/2/26 | Fri 10/2/26 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 2766 |  |  | -86.38d | Yes | Yes | Yes | No | No | 1.2.4.2.64 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.64.1 | Auto Scheduled | 0% | Load | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 1726 | 1736 |  | NA | SPL Master File | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.61.1 | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible | 1.2.4.2.64.2 | NA | 2767 | 2758 | 2768 | -691h | No | Yes | Yes | No | No | 1.2.4.2.64.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.64.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 1735 |  | Kim Kolesar | NA | SPL Master File | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.64.1 | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 2768 | 2767 |  | -691h | No | Yes | Yes | No | No | 1.2.4.2.64.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.65 | Auto Scheduled | 0% | Initialize Embargo situation | No | 0.38d | Fri 9/25/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Fri 9/25/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 2769 |  |  | -81.69d | Yes | Yes | Yes | No | No | 1.2.4.2.65 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.65.1 | Auto Scheduled | 0% | Run report /SAPSLL/EMB_CNTRY_INIT | No | 1h | Fri 9/25/26 | Fri 9/25/26 | James Van Riper | 1718 | 1739 |  | NA | Initialize Embargo situation | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.58.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.65.2 | NA | 2770 | 2750 | 2771 | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.65.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.65.2 | Auto Scheduled | 0% | Set Embargo situations | No | 1h | Fri 9/25/26 | Fri 9/25/26 | James Van Riper | 1738 | 1740 |  | NA | Initialize Embargo situation | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.65.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.4.2.65.3 | NA | 2771 | 2770 | 2772 | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.65.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.65.3 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 9/25/26 | Fri 9/25/26 | James Van Riper | 1739 |  | Kim Kolesar | NA | Initialize Embargo situation | Fri 9/25/26 | Fri 9/25/26 | 1.2.4.2.65.2 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 2772 | 2771 |  | -653.5h | No | Yes | Yes | No | No | 1.2.4.2.65.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.66 | Auto Scheduled | 0% | GTS - SPL (Sanctioned party list) | No | 0.25d | Fri 10/2/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Fri 10/2/26 | Fri 10/2/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2773 |  |  | -86.63d | Yes | Yes | Yes | No | No | 1.2.4.2.66 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.66.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 1727 | 17291743 |  | NA | GTS - SPL (Sanctioned party list) | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.61.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.62.1,1.2.4.2.66.2 | NA | 2774 | 2759 | 27612775 | -693h | No | Yes | Yes | No | No | 1.2.4.2.66.1 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.66.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 1742 |  | Kim Kolesar | NA | GTS - SPL (Sanctioned party list) | Fri 10/2/26 | Fri 10/2/26 | 1.2.4.2.66.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 2775 | 2774 |  | -692h | No | Yes | Yes | No | No | 1.2.4.2.66.2 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.67 | Auto Scheduled | 0% | RTR_CM17_Project Definition / Builder | No | 1.13d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Fri 4/10/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2776 |  |  | -81.44d | Yes | Yes | Yes | No | No | 1.2.4.2.67 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.67.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1690 | 17461752 |  | NA | RTR_CM17_Project Definition / Builder | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.52.1 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.4.2.67.2,1.2.4.2.68.1 | Mon 4/20/26 | 2777 | 2722 | 27782784 | -39090m | No | Yes | Yes | No | No | 1.2.4.2.67.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.67.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1745 | 1747 | Brian Wagner | NA | RTR_CM17_Project Definition / Builder | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.67.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.67.3 | NA | 2778 | 2777 | 2779 | -39060m | No | Yes | Yes | No | No | 1.2.4.2.67.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.67.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 1746 | 1748 |  | NA | RTR_CM17_Project Definition / Builder | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.67.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.67.4 | NA | 2779 | 2778 | 2780 | -651h | No | Yes | Yes | No | No | 1.2.4.2.67.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.67.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1747 | 1749 | Brian Wagner | NA | RTR_CM17_Project Definition / Builder | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.67.3 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.67.5 | NA | 2780 | 2779 | 2781 | -651h | No | Yes | Yes | No | No | 1.2.4.2.67.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.67.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 1748 | 1750 |  | NA | RTR_CM17_Project Definition / Builder | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.67.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.67.6 | NA | 2781 | 2780 | 2782 | -651h | No | Yes | Yes | No | No | 1.2.4.2.67.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.67.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Fri 9/25/26 | Kasey Hughes | 1749 |  | Brian Wagner | NA | RTR_CM17_Project Definition / Builder | Thu 9/24/26 | Fri 9/25/26 | 1.2.4.2.67.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2782 | 2781 |  | -651h | No | Yes | Yes | No | No | 1.2.4.2.67.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.68 | Auto Scheduled | 0% | RTR_CM18_WBS Element | No | 1.25d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Fri 4/10/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2783 |  |  | -81.44d | Yes | Yes | Yes | No | No | 1.2.4.2.68 | 5 | No | 500 | Future Task | No | 0d
1.2.4.2.68.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1745 | 1753 |  | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.67.1 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.4.2.68.2 | Fri 4/17/26 | 2784 | 2777 | 2785 | -39090m | No | Yes | Yes | No | No | 1.2.4.2.68.1 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.68.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1752 | 1754 | Brian Wagner | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.68.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.4.2.68.3 | NA | 2785 | 2784 | 2786 | -39090m | No | Yes | Yes | No | No | 1.2.4.2.68.2 | 6 | No | 500 | Future Task | No | 0m
1.2.4.2.68.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 1753 | 1755 |  | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.68.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.4.2.68.4 | NA | 2786 | 2785 | 2787 | -651.5h | No | Yes | Yes | No | No | 1.2.4.2.68.3 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.68.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1754 | 1756 | Brian Wagner | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.68.3 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.68.5 | NA | 2787 | 2786 | 2788 | -651.5h | No | Yes | Yes | No | No | 1.2.4.2.68.4 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.68.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 1755 | 1757 |  | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Thu 9/24/26 | 1.2.4.2.68.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.4.2.68.6 | NA | 2788 | 2787 | 2789 | -651.5h | No | Yes | Yes | No | No | 1.2.4.2.68.5 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.68.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Fri 9/25/26 | Kasey Hughes | 1756 |  | Brian Wagner | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Fri 9/25/26 | 1.2.4.2.68.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 2789 | 2788 |  | -651.5h | No | Yes | Yes | No | No | 1.2.4.2.68.6 | 6 | No | 500 | Future Task | No | 0h
1.2.4.2.68.7 | Auto Scheduled | 0% | UAT Mock Data Loads Complete | No | 15m | Thu 9/24/26 | Thu 9/24/26 | Mark George |  |  |  | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Thu 9/24/26 |  | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 2790 |  |  | -38505m | No | Yes | Yes | Yes | No | 1.2.4.2.68.7 | 6 | No | 500 | Future Task | No | 0m
1.2.4.3 | Auto Scheduled | 0% | UAT Master Data Loads Complete | No | 0m | Thu 10/8/26 | Thu 10/8/26 |  | 1391 | 1000SS,999,1761SS,1760,2196 |  | NA | UAT Data Load Tasks QS4 | Thu 10/8/26 | Thu 10/8/26 | 1.2.4.2 | NA | NA | As Soon As Possible | 1.2.2.4.1[SS],1.2.2.4,1.2.4.4.1[SS],1.2.4.4,1.3.3.8.1 | NA | 3360 | 2898 | 2945SS,2801,3351SS,3350,924 | -43560m | No | Yes | Yes | Yes | No | 1.2.4.3 | 4 | No | 500 | Future Task | No | 0m
1.2.4.4 | Auto Scheduled | 0% | Mock Transactional Data | No | 2d | Thu 10/8/26 | Mon 10/12/26 |  | 1759 | 1769 |  | NA | UAT Data Load Tasks QS4 | Thu 10/8/26 | Mon 10/12/26 | 1.2.4.3 | NA | NA | As Soon As Possible | 1.2.4.5 | NA | 3350 | 3360 | 2938 | -40.66d | Yes | Yes | Yes | No | No | 1.2.4.4 | 4 | No | 500 | Future Task | No | 0d
1.2.4.4.1 | Auto Scheduled | 0% | Inventory | No | 4h | Thu 10/8/26 | Fri 10/9/26 |  | 998SS,1759SS | 1.7622e+19 |  | NA | Mock Transactional Data | Thu 10/8/26 | Fri 10/9/26 | 1.2.2.3[SS],1.2.4.3[SS] | NA | NA | As Soon As Possible | 1.2.4.4.2,1.2.4.4.5,1.2.4.4.6,1.2.4.4.7,1.2.4.4.8 | NA | 3351 | 2947SS,3360SS | 3.3523e+19 | -325.25h | No | Yes | Yes | No | No | 1.2.4.4.1 | 5 | No | 500 | Future Task | No | 0h
1.2.4.4.2 | Auto Scheduled | 0% | Open AR | No | 4h | Fri 10/9/26 | Fri 10/9/26 |  | 1761 | 1763 |  | NA | Mock Transactional Data | Fri 10/9/26 | Fri 10/9/26 | 1.2.4.4.1 | NA | NA | As Soon As Possible | 1.2.4.4.3 | NA | 3352 | 3351 | 3353 | -325.25h | No | Yes | Yes | No | No | 1.2.4.4.2 | 5 | No | 500 | Future Task | No | 0h
1.2.4.4.3 | Auto Scheduled | 0% | Open AP | No | 4h | Fri 10/9/26 | Mon 10/12/26 |  | 1762 | 1764 |  | NA | Mock Transactional Data | Fri 10/9/26 | Mon 10/12/26 | 1.2.4.4.2 | NA | NA | As Soon As Possible | 1.2.4.4.4 | NA | 3353 | 3352 | 3354 | -325.25h | No | Yes | Yes | No | No | 1.2.4.4.3 | 5 | No | 500 | Future Task | No | 0h
1.2.4.4.4 | Auto Scheduled | 0% | Bank and Cash | No | 4h | Mon 10/12/26 | Mon 10/12/26 |  | 1763 |  |  | NA | Mock Transactional Data | Mon 10/12/26 | Mon 10/12/26 | 1.2.4.4.3 | NA | NA | As Soon As Possible |  | NA | 3354 | 3353 |  | -325.25h | No | Yes | Yes | No | No | 1.2.4.4.4 | 5 | No | 500 | Future Task | No | 0h
1.2.4.4.5 | Auto Scheduled | 0% | Open Purchase Orders(Manual) | No | 1d | Fri 10/9/26 | Mon 10/12/26 |  | 1761 |  |  | NA | Mock Transactional Data | Fri 10/9/26 | Mon 10/12/26 | 1.2.4.4.1 | NA | NA | As Soon As Possible |  | NA | 3355 | 3351 |  | -40.16d | No | Yes | Yes | No | No | 1.2.4.4.5 | 5 | No | 500 | Future Task | No | 0d
1.2.4.4.6 | Auto Scheduled | 0% | Open Sales Orders(Manual) | No | 1d | Fri 10/9/26 | Mon 10/12/26 |  | 1761 |  |  | NA | Mock Transactional Data | Fri 10/9/26 | Mon 10/12/26 | 1.2.4.4.1 | NA | NA | As Soon As Possible |  | NA | 3356 | 3351 |  | -40.16d | No | Yes | Yes | No | No | 1.2.4.4.6 | 5 | No | 500 | Future Task | No | 0d
1.2.4.4.7 | Auto Scheduled | 0% | Service Orders(Manual) | No | 0.5d | Fri 10/9/26 | Fri 10/9/26 |  | 1761 |  |  | NA | Mock Transactional Data | Fri 10/9/26 | Fri 10/9/26 | 1.2.4.4.1 | NA | NA | As Soon As Possible |  | NA | 3357 | 3351 |  | -39.66d | No | Yes | Yes | No | No | 1.2.4.4.7 | 5 | No | 500 | Future Task | No | 0d
1.2.4.4.8 | Auto Scheduled | 0% | Open Production Orders(Manual) | No | 1d | Fri 10/9/26 | Mon 10/12/26 |  | 1761 |  |  | NA | Mock Transactional Data | Fri 10/9/26 | Mon 10/12/26 | 1.2.4.4.1 | NA | NA | As Soon As Possible |  | NA | 3358 | 3351 |  | -40.16d | No | Yes | Yes | No | No | 1.2.4.4.8 | 5 | No | 500 | Future Task | No | 0d
1.2.4.5 | Auto Scheduled | 0% | UAT Mock Data Loads Complete | No | 15m | Mon 10/12/26 | Mon 10/12/26 | Mark George | 1760 | 2167 |  | NA | UAT Data Load Tasks QS4 | Mon 10/12/26 | Mon 10/12/26 | 1.2.4.4 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible | 1.3.3.4 | NA | 2938 | 3350 | 690 | -19515m | No | Yes | Yes | Yes | No | 1.2.4.5 | 4 | No | 500 | Future Task | No | 0m
1.2.5 | Auto Scheduled | 0% | PROD Data Load Tasks P? | No | 10.56d | Thu 9/24/26 | Thu 10/8/26 |  | 134 |  |  | NA | Data Readiness | Thu 9/24/26 | Thu 10/8/26 | 1.1.1.8 | Thu 3/13/25 | Tue 4/21/26 | As Soon As Possible |  | NA | 4160 | 3367 |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.5 | 3 | No | 500 | Future Task | No | 0d
1.2.5.1 | Auto Scheduled | 0% | PMO Authorization to Start Data Loads | No | 1m | Thu 9/24/26 | Thu 9/24/26 | Mark George | 134 | 1.7742e+19 |  | NA | PROD Data Load Tasks P? | Thu 9/24/26 | Thu 9/24/26 | 1.1.1.8 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.5.2.1.1,1.2.5.2.37.1,1.2.5.2.58.1,1.2.5.2.60.1,1.2.5.2 | NA | 4161 | 3367 | 4.1644e+19 | -43561m | No | Yes | Yes | No | No | 1.2.5.1 | 4 | No | 500 | Future Task | No | 0m
1.2.5.2 | Manually Scheduled | 0% | Master Data Loads | No | 5d | Thu 9/24/26 | Thu 10/1/26 |  | 1771 | 2140 |  | NA | PROD Data Load Tasks P? | Thu 9/24/26 | Thu 10/1/26 | 1.2.5.1 | NA | NA | As Soon As Possible | 1.2.5.3 | NA | 4162 | 4161 | 4530 | 0d | Yes | Yes | Yes | No | No | 1.2.5.2 | 4 | No | 500 | Future Task | Yes | 0d
1.2.5.2.1 | Auto Scheduled | 0% | RTR_CM02_Profit Center Hierarchy | No | 0.75d | Thu 9/24/26 | Thu 9/24/26 |  |  | 18061808 |  | NA | Master Data Loads | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.5.2.6.2,1.2.5.2.6.4 | NA | 4163 |  | 41964198 | -89.81d | Yes | Yes | Yes | No | No | 1.2.5.2.1 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.1.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1771 | 1775 |  | NA | RTR_CM02_Profit Center Hierarchy | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.1 | Mon 4/6/26 | Mon 4/6/26 | Start No Earlier Than | 1.2.5.2.1.2 | Mon 4/6/26 | 4164 | 4161 | 4165 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.1.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.1.2 | Auto Scheduled | 0% | Load | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1774 | 1776 |  | NA | RTR_CM02_Profit Center Hierarchy | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.1.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.5.2.1.3 | NA | 4165 | 4164 | 4166 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.1.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.1.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1775 | 17781791 | Brian Wagner | NA | RTR_CM02_Profit Center Hierarchy | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.1.2 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.5.2.2.1,1.2.5.2.4.1 | NA | 4166 | 4165 | 41684181 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.1.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.2 | Auto Scheduled | 0% | RTR_CM03_Cost Center Hierarchy | No | 0.75d | Thu 9/24/26 | Fri 9/25/26 |  |  | 18061808 |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.6.2,1.2.5.2.6.4 | NA | 4167 |  | 41964198 | -89.81d | Yes | Yes | Yes | No | No | 1.2.5.2.2 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.2.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1776 | 1779 |  | NA | RTR_CM03_Cost Center Hierarchy | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.1.3 | Mon 4/6/26 | Mon 4/6/26 | Start No Earlier Than | 1.2.5.2.2.2 | Mon 4/6/26 | 4168 | 4166 | 4169 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.2.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.2.2 | Auto Scheduled | 0% | Load | No | 2h | Thu 9/24/26 | Fri 9/25/26 | Kasey Hughes | 1778 | 1780 |  | NA | RTR_CM03_Cost Center Hierarchy | Thu 9/24/26 | Fri 9/25/26 | 1.2.5.2.2.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.2.3 | NA | 4169 | 4168 | 4170 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.2.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.2.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1779 | 17821817 | Brian Wagner | NA | RTR_CM03_Cost Center Hierarchy | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.2.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.3.1,1.2.5.2.8.1 | NA | 4170 | 4169 | 41724207 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.2.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.3 | Auto Scheduled | 0% | RTR_CM01_GL_Account_Master to CC 1000 | No | 2.44d | Fri 9/25/26 | Wed 9/30/26 |  |  | 1806 |  | NA | Master Data Loads | Fri 9/25/26 | Wed 9/30/26 |  | Tue 4/7/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.6.2 | NA | 4171 |  | 4196 | -89.81d | Yes | Yes | Yes | No | No | 1.2.5.2.3 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.3.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1780 | 1783 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.2.3 | Tue 4/7/26 | Tue 4/7/26 | Start No Earlier Than | 1.2.5.2.3.2 | Mon 4/6/26 | 4172 | 4170 | 4173 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.3.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.3.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1782 | 1784 | Brian Wagner | NA | RTR_CM01_GL_Account_Master to CC 1000 | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.3.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.3.3 | NA | 4173 | 4172 | 4174 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.3.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.3.3 | Auto Scheduled | 0% | Simulate Load | No | 6h | Fri 9/25/26 | Mon 9/28/26 | Data Migration Team | 1783 | 1785 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Fri 9/25/26 | Mon 9/28/26 | 1.2.5.2.3.2 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.3.4 | NA | 4174 | 4173 | 4175 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.3.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.3.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 9/28/26 | Tue 9/29/26 | Kasey Hughes | 1784 | 1786 | Brian Wagner | NA | RTR_CM01_GL_Account_Master to CC 1000 | Mon 9/28/26 | Tue 9/29/26 | 1.2.5.2.3.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.3.5 | NA | 4175 | 4174 | 4176 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.3.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.3.5 | Auto Scheduled | 0% | Load | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1785 | 1787 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.3.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.3.6 | NA | 4176 | 4175 | 4177 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.3.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.3.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Kasey Hughes | 1786 | 1.8102e+19 | Brian Wagner | NA | RTR_CM01_GL_Account_Master to CC 1000 | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.3.5 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.7.1,1.2.5.2.9.1,1.2.5.2.11.1,1.2.5.2.13.1,1.2.5.2.3.7 | NA | 4177 | 4176 | 4.2004e+19 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.3.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.3.7 | Auto Scheduled | 0% | Extend GL to all Company Codes | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Kasey Hughes | 1787 | 1789 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.3.6 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.3.8 | NA | 4178 | 4177 | 4179 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.3.7 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.3.8 | Auto Scheduled | 0% | Post GL Extention Validation | No | 2h | Tue 9/29/26 | Wed 9/30/26 |  | 1788 | 18551808 |  | NA | RTR_CM01_GL_Account_Master to CC 1000 | Tue 9/29/26 | Wed 9/30/26 | 1.2.5.2.3.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.14.3,1.2.5.2.6.4 | NA | 4179 | 4178 | 42454198 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.3.8 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.4 | Auto Scheduled | 0% | RTR_CM05_Profit_Center | No | 1.13d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 4180 |  |  | -84.72d | Yes | Yes | Yes | No | No | 1.2.5.2.4 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.4.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1776 | 1792 |  | NA | RTR_CM05_Profit_Center | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.1.3 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.5.2.4.2 | NA | 4181 | 4166 | 4182 | -677.77h | No | Yes | Yes | No | No | 1.2.5.2.4.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.4.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 9/24/26 | Fri 9/25/26 | Kasey Hughes | 1791 | 1793 | Brian Wagner | NA | RTR_CM05_Profit_Center | Thu 9/24/26 | Fri 9/25/26 | 1.2.5.2.4.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.4.3 | NA | 4182 | 4181 | 4183 | -677.77h | No | Yes | Yes | No | No | 1.2.5.2.4.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.4.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Data Migration Team | 1792 | 1794 |  | NA | RTR_CM05_Profit_Center | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.4.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.4.4 | NA | 4183 | 4182 | 4184 | -677.77h | No | Yes | Yes | No | No | 1.2.5.2.4.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.4.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1793 | 1795 | Brian Wagner | NA | RTR_CM05_Profit_Center | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.4.3 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.4.5 | NA | 4184 | 4183 | 4185 | -677.77h | No | Yes | Yes | No | No | 1.2.5.2.4.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.4.5 | Auto Scheduled | 0% | Load | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Data Migration Team | 1794 | 1796 |  | NA | RTR_CM05_Profit_Center | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.4.4 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.4.6 | NA | 4185 | 4184 | 4186 | -677.77h | No | Yes | Yes | No | No | 1.2.5.2.4.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.4.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1795 | 179819271934 | Brian Wagner | NA | RTR_CM05_Profit_Center | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.4.5 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.5.1,1.2.5.2.25.1,1.2.5.2.26.1 | NA | 4186 | 4185 | 418843174324 | -677.77h | No | Yes | Yes | No | No | 1.2.5.2.4.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.5 | Auto Scheduled | 0% | RTR_CM04_Cost_Center | No | 1.13d | Fri 9/25/26 | Tue 9/29/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Tue 9/29/26 |  | Tue 4/7/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 4187 |  |  | -83.19d | Yes | Yes | Yes | No | No | 1.2.5.2.5 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.5.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Fri 9/25/26 | Mon 9/28/26 | Kasey Hughes | 1796 | 1799 |  | NA | RTR_CM04_Cost_Center | Fri 9/25/26 | Mon 9/28/26 | 1.2.5.2.4.6 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.5.2 | NA | 4188 | 4186 | 4189 | -665.52h | No | Yes | Yes | No | No | 1.2.5.2.5.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.5.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Kasey Hughes | 1798 | 1800 | Brian Wagner | NA | RTR_CM04_Cost_Center | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.5.1 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.5.3 | NA | 4189 | 4188 | 4190 | -665.52h | No | Yes | Yes | No | No | 1.2.5.2.5.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.5.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1799 | 1801 |  | NA | RTR_CM04_Cost_Center | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.5.2 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.5.4 | NA | 4190 | 4189 | 4191 | -665.52h | No | Yes | Yes | No | No | 1.2.5.2.5.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.5.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Kasey Hughes | 1800 | 1802 | Brian Wagner | NA | RTR_CM04_Cost_Center | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.5.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.5.5 | NA | 4191 | 4190 | 4192 | -665.52h | No | Yes | Yes | No | No | 1.2.5.2.5.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.5.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1801 | 1803 |  | NA | RTR_CM04_Cost_Center | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.5.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.5.6 | NA | 4192 | 4191 | 4193 | -665.52h | No | Yes | Yes | No | No | 1.2.5.2.5.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.5.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 9/28/26 | Tue 9/29/26 | Kasey Hughes | 1802 |  | Brian Wagner | NA | RTR_CM04_Cost_Center | Mon 9/28/26 | Tue 9/29/26 | 1.2.5.2.5.5 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 4193 | 4192 |  | -665.52h | No | Yes | Yes | No | No | 1.2.5.2.5.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.6 | Auto Scheduled | 0% | Manual Configuration Activities in QS5 | No | 8.94d | Thu 9/24/26 | Wed 10/7/26 |  | 40 |  |  | NA | Master Data Loads | Thu 9/24/26 | Wed 10/7/26 | 1.1.1.4.22 | Mon 4/6/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 4194 | 652 |  | -89.13d | Yes | Yes | Yes | No | No | 1.2.5.2.6 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.6.1 | Auto Scheduled | 0% | Open Client | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Basis |  |  |  | NA | Manual Configuration Activities in QS5 | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 4195 |  |  | -38521m | No | Yes | Yes | No | No | 1.2.5.2.6.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.6.2 | Auto Scheduled | 0% | Service Enterprise Setup | No | 5d | Wed 9/30/26 | Wed 10/7/26 | Keith Riley | 177317771781 |  |  | NA | Manual Configuration Activities in QS5 | Wed 9/30/26 | Wed 10/7/26 | 1.2.5.2.1,1.2.5.2.2,1.2.5.2.3 | Wed 4/8/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 4196 | 416341674171 |  | -89.13d | No | Yes | Yes | No | No | 1.2.5.2.6.2 | 6 | No | 500 | Future Task | No | 0d
1.2.5.2.6.3 | Auto Scheduled | 0% | Close Client | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Basis |  |  |  | NA | Manual Configuration Activities in QS5 | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 4197 |  |  | -38521m | No | Yes | Yes | No | No | 1.2.5.2.6.3 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.6.4 | Auto Scheduled | 0% | Intercompany Business Partner Setup | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Functional Leads | 177317771789 |  |  | NA | Manual Configuration Activities in QS5 | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.1,1.2.5.2.2,1.2.5.2.3.8 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 4198 | 416341674179 |  | -675.02h | No | Yes | Yes | No | No | 1.2.5.2.6.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.7 | Auto Scheduled | 0% | RTR_CM09_Activity_Type | No | 1.38d | Tue 9/29/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Wed 9/30/26 |  | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 4199 |  |  | -85d | Yes | Yes | Yes | No | No | 1.2.5.2.7 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.7.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Kasey Hughes | 1787 | 1811 |  | NA | RTR_CM09_Activity_Type | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.3.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.7.2 | NA | 4200 | 4177 | 4201 | -680.02h | No | Yes | Yes | No | No | 1.2.5.2.7.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.7.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 9/29/26 | Wed 9/30/26 | Kasey Hughes | 1810 | 1812 | Brian Wagner | NA | RTR_CM09_Activity_Type | Tue 9/29/26 | Wed 9/30/26 | 1.2.5.2.7.1 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.7.3 | NA | 4201 | 4200 | 4202 | -680.02h | No | Yes | Yes | No | No | 1.2.5.2.7.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.7.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1811 | 1813 |  | NA | RTR_CM09_Activity_Type | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.7.2 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.7.4 | NA | 4202 | 4201 | 4203 | -680.02h | No | Yes | Yes | No | No | 1.2.5.2.7.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.7.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Kasey Hughes | 1812 | 1814 | Brian Wagner | NA | RTR_CM09_Activity_Type | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.7.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.7.5 | NA | 4203 | 4202 | 4204 | -680.02h | No | Yes | Yes | No | No | 1.2.5.2.7.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.7.5 | Auto Scheduled | 0% | Load | No | 1h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1813 | 1815 |  | NA | RTR_CM09_Activity_Type | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.7.4 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.7.6 | NA | 4204 | 4203 | 4205 | -680.02h | No | Yes | Yes | No | No | 1.2.5.2.7.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.7.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Kasey Hughes | 1814 |  | Brian Wagner | NA | RTR_CM09_Activity_Type | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.7.5 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 4205 | 4204 |  | -680.02h | No | Yes | Yes | No | No | 1.2.5.2.7.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.8 | Auto Scheduled | 0% | RTR_CM12_Activity Rates | No | 1.13d | Fri 9/25/26 | Mon 9/28/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Mon 9/28/26 |  | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible |  | NA | 4206 |  |  | -82.81d | Yes | Yes | Yes | No | No | 1.2.5.2.8 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.8.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1780 | 1818 |  | NA | RTR_CM12_Activity Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.2.3 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.8.2 | NA | 4207 | 4170 | 4208 | -662.52h | No | Yes | Yes | No | No | 1.2.5.2.8.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.8.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1817 | 1819 | Brian Wagner | NA | RTR_CM12_Activity Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.8.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.8.3 | NA | 4208 | 4207 | 4209 | -662.52h | No | Yes | Yes | No | No | 1.2.5.2.8.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.8.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 9/25/26 | Mon 9/28/26 | Data Migration Team | 1818 | 1820 |  | NA | RTR_CM12_Activity Rates | Fri 9/25/26 | Mon 9/28/26 | 1.2.5.2.8.2 | Tue 4/7/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.8.4 | NA | 4209 | 4208 | 4210 | -662.52h | No | Yes | Yes | No | No | 1.2.5.2.8.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.8.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Kasey Hughes | 1819 | 1821 | Brian Wagner | NA | RTR_CM12_Activity Rates | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.8.3 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.8.5 | NA | 4210 | 4209 | 4211 | -662.52h | No | Yes | Yes | No | No | 1.2.5.2.8.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.8.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1820 | 1822 |  | NA | RTR_CM12_Activity Rates | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.8.4 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.8.6 | NA | 4211 | 4210 | 4212 | -662.52h | No | Yes | Yes | No | No | 1.2.5.2.8.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.8.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Kasey Hughes | 1821 |  | Brian Wagner | NA | RTR_CM12_Activity Rates | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.8.5 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible |  | NA | 4212 | 4211 |  | -662.52h | No | Yes | Yes | No | No | 1.2.5.2.8.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.9 | Auto Scheduled | 0% | RTR_CM06_Bank_master | No | 3.81d | Thu 9/24/26 | Tue 9/29/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Tue 9/29/26 |  | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 4213 |  |  | -86.31d | Yes | Yes | Yes | No | No | 1.2.5.2.9 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.9.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1787 | 1825 |  | NA | RTR_CM06_Bank_master | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.3.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.9.2 | NA | 4214 | 4177 | 4215 | -672.02h | No | Yes | Yes | No | No | 1.2.5.2.9.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.9.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Kasey Hughes | 1824 |  | Brian Wagner | NA | RTR_CM06_Bank_master | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.9.1 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 4215 | 4214 |  | -672.02h | No | Yes | Yes | No | No | 1.2.5.2.9.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.9.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team |  | 1827 |  | NA | RTR_CM06_Bank_master | Thu 9/24/26 | Thu 9/24/26 |  | Thu 4/9/26 | Thu 4/9/26 | Start No Earlier Than | 1.2.5.2.9.4 | Wed 4/15/26 | 4216 |  | 4217 | -690.52h | No | Yes | Yes | No | No | 1.2.5.2.9.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.9.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 1826 | 1828 | Brian Wagner | NA | RTR_CM06_Bank_master | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.9.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.9.5 | NA | 4217 | 4216 | 4218 | -690.52h | No | Yes | Yes | No | No | 1.2.5.2.9.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.9.5 | Auto Scheduled | 0% | Load | No | 5h | Thu 9/24/26 | Fri 9/25/26 | Data Migration Team | 1827 | 18291831 |  | NA | RTR_CM06_Bank_master | Thu 9/24/26 | Fri 9/25/26 | 1.2.5.2.9.4 | Thu 4/9/26 | Thu 4/9/26 | Finish No Earlier Than | 1.2.5.2.9.6,1.2.5.2.10.1 | Wed 4/15/26 | 4218 | 4217 | 42194221 | -690.52h | No | Yes | Yes | No | No | 1.2.5.2.9.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.9.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1828 | 18651876 | Brian Wagner | NA | RTR_CM06_Bank_master | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.9.5 | Thu 4/9/26 | Thu 4/9/26 | Finish No Earlier Than | 1.2.5.2.15.3,1.2.5.2.17.3 | Tue 4/14/26 | 4219 | 4218 | 42554266 | -690.52h | No | Yes | Yes | No | No | 1.2.5.2.9.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.10 | Auto Scheduled | 0% | RTR_CM08_Exchange_Rates | No | 1.13d | Fri 9/25/26 | Mon 9/28/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Mon 9/28/26 |  | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 4220 |  |  | -82.31d | Yes | Yes | Yes | No | No | 1.2.5.2.10 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.10.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1828 | 1832 |  | NA | RTR_CM08_Exchange_Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.9.5 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.10.2 | NA | 4221 | 4218 | 4222 | -658.52h | No | Yes | Yes | No | No | 1.2.5.2.10.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.10.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1831 | 1833 | Brian Wagner | NA | RTR_CM08_Exchange_Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.10.1 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.10.3 | NA | 4222 | 4221 | 4223 | -658.52h | No | Yes | Yes | No | No | 1.2.5.2.10.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.10.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Data Migration Team | 1832 | 1834 |  | NA | RTR_CM08_Exchange_Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.10.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.10.4 | NA | 4223 | 4222 | 4224 | -658.52h | No | Yes | Yes | No | No | 1.2.5.2.10.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.10.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Kasey Hughes | 1833 | 1835 | Brian Wagner | NA | RTR_CM08_Exchange_Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.10.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.10.5 | NA | 4224 | 4223 | 4225 | -658.52h | No | Yes | Yes | No | No | 1.2.5.2.10.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.10.5 | Auto Scheduled | 0% | Load | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Data Migration Team | 1834 | 1836 |  | NA | RTR_CM08_Exchange_Rates | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.10.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.10.6 | NA | 4225 | 4224 | 4226 | -658.52h | No | Yes | Yes | No | No | 1.2.5.2.10.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.10.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Fri 9/25/26 | Mon 9/28/26 | Kasey Hughes | 1835 |  | Brian Wagner | NA | RTR_CM08_Exchange_Rates | Fri 9/25/26 | Mon 9/28/26 | 1.2.5.2.10.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 4226 | 4225 |  | -658.52h | No | Yes | Yes | No | No | 1.2.5.2.10.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.11 | Auto Scheduled | 0% | RTR_CM14_Cost Element_Group | No | 4.44d | Tue 9/29/26 | Mon 10/5/26 | Kasey Hughes |  |  | Brian Wagner | NA | Master Data Loads | Tue 9/29/26 | Mon 10/5/26 |  | Wed 4/8/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 4227 |  |  | -88.06d | Yes | Yes | Yes | No | No | 1.2.5.2.11 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.11.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Kasey Hughes | 1787 | 1839 |  | NA | RTR_CM14_Cost Element_Group | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.3.6 | Wed 4/8/26 | Tue 4/14/26 | Finish No Earlier Than | 1.2.5.2.11.2 | Tue 4/14/26 | 4228 | 4177 | 4229 | -42271m | No | Yes | Yes | No | No | 1.2.5.2.11.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.11.2 | Auto Scheduled | 0% | Load | No | 32h | Tue 9/29/26 | Mon 10/5/26 | Kasey Hughes | 1838 | 1840 |  | NA | RTR_CM14_Cost Element_Group | Tue 9/29/26 | Mon 10/5/26 | 1.2.5.2.11.1 | Wed 4/15/26 | Wed 4/15/26 | Finish No Earlier Than | 1.2.5.2.11.3 | Tue 4/21/26 | 4229 | 4228 | 4230 | -704.52h | No | Yes | Yes | No | No | 1.2.5.2.11.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.11.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 10/5/26 | Mon 10/5/26 | Kasey Hughes | 1839 |  | Brian Wagner | NA | RTR_CM14_Cost Element_Group | Mon 10/5/26 | Mon 10/5/26 | 1.2.5.2.11.2 | Wed 4/15/26 | Wed 4/15/26 | Start No Earlier Than |  | Fri 4/17/26 | 4230 | 4229 |  | -704.52h | No | Yes | Yes | No | No | 1.2.5.2.11.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.12 | Auto Scheduled | 0% | OTC_CM19_Customer_Master - Bill-To | No | 2h | Thu 9/24/26 | Thu 9/24/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Thu 9/24/26 |  | Wed 4/16/25 | Wed 4/16/25 | As Soon As Possible |  | NA | 4231 |  |  | -643.52h | No | Yes | Yes | No | No | 1.2.5.2.12 | 5 | No | 500 | Future Task | No | 0h
1.2.5.2.13 | Auto Scheduled | 0% | OTC_CM19_Customer_Master - Ship-To | No | 1.5d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Wed 4/8/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4232 |  |  | -89.56d | Yes | Yes | Yes | No | No | 1.2.5.2.13 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.13.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Ric Haraida | 1787 | 1844 |  | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.3.6 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.13.2 | NA | 4233 | 4177 | 4234 | -42991m | No | Yes | Yes | No | No | 1.2.5.2.13.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.13.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Ric Haraida | 1843 | 184818531845 | Kim Kolesar | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.13.1 | Wed 4/8/26 | Wed 4/8/26 | As Soon As Possible | 1.2.5.2.13.6,1.2.5.2.14.1,1.2.5.2.13.3 | NA | 4234 | 4233 | 423842434235 | -42991m | No | Yes | Yes | No | No | 1.2.5.2.13.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.13.3 | Auto Scheduled | 0% | Open client for BP number range update | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Basis | 1844 | 1846 |  | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.13.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.13.4 | NA | 4235 | 4234 | 4236 | -40276m | No | Yes | Yes | No | No | 1.2.5.2.13.3 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.13.4 | Auto Scheduled | 0% | Update number range BP02 from Internal to External | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Ric Haraida | 1845 | 1847 |  | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.13.3 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.13.5 | NA | 4236 | 4235 | 4237 | -40276m | No | Yes | Yes | No | No | 1.2.5.2.13.4 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.13.5 | Auto Scheduled | 0% | Close Client | No | 15m | Tue 9/29/26 | Tue 9/29/26 | Basis | 1846 |  |  | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.13.4 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4237 | 4236 |  | -40276m | No | Yes | Yes | No | No | 1.2.5.2.13.5 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.13.6 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1844 | 184918551859 |  | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.13.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.13.7,1.2.5.2.14.3,1.2.5.2.14.7 | NA | 4238 | 4234 | 423942454249 | -716.52h | No | Yes | Yes | No | No | 1.2.5.2.13.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.13.7 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 4h | Tue 9/29/26 | Wed 9/30/26 | Ric Haraida | 1848 | 1850 | Kim Kolesar | NA | OTC_CM19_Customer_Master - Ship-To | Tue 9/29/26 | Wed 9/30/26 | 1.2.5.2.13.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.13.8 | NA | 4239 | 4238 | 4240 | -681.02h | No | Yes | Yes | No | No | 1.2.5.2.13.7 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.13.8 | Auto Scheduled | 0% | Load | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1849 | 1851 |  | NA | OTC_CM19_Customer_Master - Ship-To | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.13.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.13.9 | NA | 4240 | 4239 | 4241 | -681.02h | No | Yes | Yes | No | No | 1.2.5.2.13.8 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.13.9 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Thu 10/1/26 | Ric Haraida | 1850 |  | Kim Kolesar | NA | OTC_CM19_Customer_Master - Ship-To | Wed 9/30/26 | Thu 10/1/26 | 1.2.5.2.13.8 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 4241 | 4240 |  | -681.02h | No | Yes | Yes | No | No | 1.2.5.2.13.9 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.14 | Auto Scheduled | 0% | OTC_CM19_Customer_Master - Sold-To | No | 1.63d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Wed 4/8/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 4242 |  |  | -89.44d | Yes | Yes | Yes | No | No | 1.2.5.2.14 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.14.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Ric Haraida | 1844 | 1854 |  | NA | OTC_CM19_Customer_Master - Sold-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.13.2 | Wed 4/8/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.14.2 | NA | 4243 | 4234 | 4244 | -40261m | No | Yes | Yes | No | No | 1.2.5.2.14.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.14.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Ric Haraida | 1853 |  | Kim Kolesar | NA | OTC_CM19_Customer_Master - Sold-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.14.1 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 4244 | 4243 |  | -40261m | No | Yes | Yes | No | No | 1.2.5.2.14.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.14.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 17891848 | 1856 |  | NA | OTC_CM19_Customer_Master - Sold-To | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.3.8,1.2.5.2.13.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.14.4 | NA | 4245 | 41794238 | 4246 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.14.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.14.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Ric Haraida | 1855 | 1857 | Kim Kolesar | NA | OTC_CM19_Customer_Master - Sold-To | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.14.3 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.14.5 | NA | 4246 | 4245 | 4247 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.14.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.14.5 | Auto Scheduled | 0% | Load | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1856 | 1.8582e+19 |  | NA | OTC_CM19_Customer_Master - Sold-To | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.14.4 | Thu 4/9/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.14.6,1.2.5.2.15.1,1.2.5.2.16.1,1.2.5.2.17.1,1.2.5.2.18.1 | NA | 4247 | 4246 | 4.2484e+19 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.14.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.14.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Thu 10/1/26 | Ric Haraida | 1857 |  | Kim Kolesar | NA | OTC_CM19_Customer_Master - Sold-To | Wed 9/30/26 | Thu 10/1/26 | 1.2.5.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 4248 | 4247 |  | -683.02h | No | Yes | Yes | No | No | 1.2.5.2.14.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.14.7 | Auto Scheduled | 0% | Open client for BP number range update | No | 15m | Tue 9/29/26 | Tue 9/29/26 | Basis | 1848 | 1860 |  | NA | OTC_CM19_Customer_Master - Sold-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.13.6 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.14.8 | NA | 4249 | 4238 | 4250 | -40306m | No | Yes | Yes | No | No | 1.2.5.2.14.7 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.14.8 | Auto Scheduled | 0% | Update number range BP02 from Internal to External | No | 15m | Tue 9/29/26 | Tue 9/29/26 | Ric Haraida | 1859 | 1861 |  | NA | OTC_CM19_Customer_Master - Sold-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.14.7 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible | 1.2.5.2.14.9 | NA | 4250 | 4249 | 4251 | -40306m | No | Yes | Yes | No | No | 1.2.5.2.14.8 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.14.9 | Auto Scheduled | 0% | Close Client | No | 15m | Tue 9/29/26 | Tue 9/29/26 | Basis | 1860 |  |  | NA | OTC_CM19_Customer_Master - Sold-To | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.14.8 | Thu 4/9/26 | Thu 4/9/26 | As Soon As Possible |  | NA | 4251 | 4250 |  | -40306m | No | Yes | Yes | No | No | 1.2.5.2.14.9 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.15 | Auto Scheduled | 0% | PTP_CM27_Vendor Master as Customer - FLCU01 | No | 4.81d | Wed 9/30/26 | Wed 10/7/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Wed 10/7/26 |  | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 4252 |  |  | -89.81d | Yes | Yes | Yes | No | No | 1.2.5.2.15 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.15.1 | Auto Scheduled | 0% | Extract File | No | 1h | Wed 9/30/26 | Thu 10/1/26 | Data Migration Team | 1857 | 1864 |  | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Wed 9/30/26 | Thu 10/1/26 | 1.2.5.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.15.2 | NA | 4253 | 4247 | 4254 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.15.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.15.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Nevin Varkey | 1863 | 1865 | Sam Houff | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.15.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.15.3 | NA | 4254 | 4253 | 4255 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.15.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.15.3 | Auto Scheduled | 0% | Simulate Load | No | 11.25h | Thu 10/1/26 | Fri 10/2/26 | Data Migration Team | 18291864 | 1866 |  | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Thu 10/1/26 | Fri 10/2/26 | 1.2.5.2.9.6,1.2.5.2.15.2 | Fri 4/10/26 | Mon 4/13/26 | Finish No Earlier Than | 1.2.5.2.15.4 | Mon 4/13/26 | 4255 | 42194254 | 4256 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.15.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.15.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 10/2/26 | Tue 10/6/26 | Nevin Varkey | 1865 | 1867 | Sam Houff | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Fri 10/2/26 | Tue 10/6/26 | 1.2.5.2.15.3 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.5.2.15.5 | NA | 4256 | 4255 | 4257 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.15.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.15.5 | Auto Scheduled | 0% | Load | No | 1h | Tue 10/6/26 | Wed 10/7/26 | Data Migration Team | 1866 | 1868 |  | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Tue 10/6/26 | Wed 10/7/26 | 1.2.5.2.15.4 | Fri 4/10/26 | Tue 4/14/26 | As Soon As Possible | 1.2.5.2.15.6 | NA | 4257 | 4256 | 4258 | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.15.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.15.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Wed 10/7/26 | Wed 10/7/26 | Nevin Varkey | 1867 |  | Sam Houff | NA | PTP_CM27_Vendor Master as Customer - FLCU01 | Wed 10/7/26 | Wed 10/7/26 | 1.2.5.2.15.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 4258 | 4257 |  | -718.52h | No | Yes | Yes | No | No | 1.2.5.2.15.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.16 | Auto Scheduled | 0% | OTC_CM23_Customer_Hierarchy | No | 0.69d | Wed 9/30/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Thu 10/1/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 4259 |  |  | -85.69d | Yes | Yes | Yes | No | No | 1.2.5.2.16 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.16.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Wed 9/30/26 | Wed 9/30/26 | Ric Haraida | 1857 | 1871 | Kim Kolesar | NA | OTC_CM23_Customer_Hierarchy | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.5.2.16.2 | Mon 4/6/26 | 4260 | 4247 | 4261 | -41131m | No | Yes | Yes | No | No | 1.2.5.2.16.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.16.2 | Auto Scheduled | 0% | Load | No | 2h | Wed 9/30/26 | Thu 10/1/26 | Ric Haraida | 1870 | 1872 |  | NA | OTC_CM23_Customer_Hierarchy | Wed 9/30/26 | Thu 10/1/26 | 1.2.5.2.16.1 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.5.2.16.3 | Wed 4/15/26 | 4261 | 4260 | 4262 | -685.52h | No | Yes | Yes | No | No | 1.2.5.2.16.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.16.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/1/26 | Thu 10/1/26 | Ric Haraida | 1871 |  | Kim Kolesar | NA | OTC_CM23_Customer_Hierarchy | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.16.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 4262 | 4261 |  | -685.52h | No | Yes | Yes | No | No | 1.2.5.2.16.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.17 | Auto Scheduled | 0% | PTP_CM27_Vendor Master - Z001 - External Sales Rep | No | 3.38d | Wed 9/30/26 | Tue 10/6/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Tue 10/6/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4263 |  |  | -88.38d | Yes | Yes | Yes | No | No | 1.2.5.2.17 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.17.1 | Auto Scheduled | 0% | Extract File | No | 1h | Wed 9/30/26 | Thu 10/1/26 | Data Migration Team | 1857 | 18751888 |  | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Wed 9/30/26 | Thu 10/1/26 | 1.2.5.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.17.2,1.2.5.2.19.1 | NA | 4264 | 4247 | 42654278 | -707.02h | No | Yes | Yes | No | No | 1.2.5.2.17.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.17.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Nevin Varkey | 1874 | 1876 | Sam Houff | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.17.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.17.3 | NA | 4265 | 4264 | 4266 | -707.02h | No | Yes | Yes | No | No | 1.2.5.2.17.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.17.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 18291875 | 1877 |  | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.9.6,1.2.5.2.17.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.17.4 | NA | 4266 | 42194265 | 4267 | -707.02h | No | Yes | Yes | No | No | 1.2.5.2.17.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.17.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Nevin Varkey | 1876 | 1878 | Sam Houff | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.17.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.17.5 | NA | 4267 | 4266 | 4268 | -707.02h | No | Yes | Yes | No | No | 1.2.5.2.17.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.17.5 | Auto Scheduled | 0% | Load | No | 1h | Thu 10/1/26 | Tue 10/6/26 | Data Migration Team | 1877 | 1879 |  | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Thu 10/1/26 | Tue 10/6/26 | 1.2.5.2.17.4 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.17.6 | NA | 4268 | 4267 | 4269 | -707.02h | No | Yes | Yes | No | No | 1.2.5.2.17.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.17.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Tue 10/6/26 | Tue 10/6/26 | Nevin Varkey | 1878 |  | Sam Houff | NA | PTP_CM27_Vendor Master - Z001 - External Sales Rep | Tue 10/6/26 | Tue 10/6/26 | 1.2.5.2.17.5 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4269 | 4268 |  | -707.02h | No | Yes | Yes | No | No | 1.2.5.2.17.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.18 | Auto Scheduled | 0% | RTR_CM10_Credit_Management_Role | No | 1.84d | Wed 9/30/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Fri 10/2/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4270 |  |  | -87.6d | Yes | Yes | Yes | No | No | 1.2.5.2.18 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.18.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Wed 9/30/26 | Wed 9/30/26 | Kasey Hughes | 1857 | 1882 |  | NA | RTR_CM10_Credit_Management_Role | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.14.5 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.18.2 | NA | 4271 | 4247 | 4272 | -42046m | No | Yes | Yes | No | No | 1.2.5.2.18.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.18.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Wed 9/30/26 | Thu 10/1/26 | Kasey Hughes | 1881 | 1883 | Brian Wagner | NA | RTR_CM10_Credit_Management_Role | Wed 9/30/26 | Thu 10/1/26 | 1.2.5.2.18.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.18.3 | NA | 4272 | 4271 | 4273 | -42046m | No | Yes | Yes | No | No | 1.2.5.2.18.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.18.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1882 | 1884 |  | NA | RTR_CM10_Credit_Management_Role | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.18.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.18.4 | NA | 4273 | 4272 | 4274 | -700.77h | No | Yes | Yes | No | No | 1.2.5.2.18.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.18.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Kasey Hughes | 1883 | 18851902 | Brian Wagner | NA | RTR_CM10_Credit_Management_Role | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.18.3 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.18.5,1.2.5.2.21.1 | NA | 4274 | 4273 | 42754292 | -700.77h | No | Yes | Yes | No | No | 1.2.5.2.18.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.18.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1884 | 1886 |  | NA | RTR_CM10_Credit_Management_Role | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.18.4 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.18.6 | NA | 4275 | 4274 | 4276 | -700.77h | No | Yes | Yes | No | No | 1.2.5.2.18.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.18.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/1/26 | Fri 10/2/26 | Kasey Hughes | 1885 | 19032068 | Brian Wagner | NA | RTR_CM10_Credit_Management_Role | Thu 10/1/26 | Fri 10/2/26 | 1.2.5.2.18.5 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.21.2,1.2.5.2.51.2 | NA | 4276 | 4275 | 42934458 | -700.77h | No | Yes | Yes | No | No | 1.2.5.2.18.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.19 | Auto Scheduled | 0% | PTP_CM27_Vendor Master | No | 6.28d | Thu 9/24/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 10/2/26 |  | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 4277 |  |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.5.2.19 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.19.1 | Auto Scheduled | 0% | Extract File | No | 1h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1874 | 1889 |  | NA | PTP_CM27_Vendor Master | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.17.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.19.2 | NA | 4278 | 4264 | 4279 | -691.77h | No | Yes | Yes | No | No | 1.2.5.2.19.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.19.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Nevin Varkey | 1888 | 1890 | Sam Houff | NA | PTP_CM27_Vendor Master | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.19.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.19.3 | NA | 4279 | 4278 | 4280 | -691.77h | No | Yes | Yes | No | No | 1.2.5.2.19.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.19.3 | Auto Scheduled | 0% | Simulate Load | No | 2.25h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1889 | 1891 |  | NA | PTP_CM27_Vendor Master | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.19.2 | Fri 4/10/26 | Tue 4/14/26 | Finish No Earlier Than | 1.2.5.2.19.4 | Fri 4/10/26 | 4280 | 4279 | 4281 | -691.77h | No | Yes | Yes | No | No | 1.2.5.2.19.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.19.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 10/1/26 | Fri 10/2/26 | Nevin Varkey | 1890 |  | Sam Houff | NA | PTP_CM27_Vendor Master | Thu 10/1/26 | Fri 10/2/26 | 1.2.5.2.19.3 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 4281 | 4280 |  | -691.77h | No | Yes | Yes | No | No | 1.2.5.2.19.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.19.5 | Auto Scheduled | 0% | Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team |  | 1893 |  | NA | PTP_CM27_Vendor Master | Thu 9/24/26 | Thu 9/24/26 |  | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.5.2.19.6 | NA | 4282 |  | 4283 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.19.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.19.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey | 1892 | 190619211945 | Sam Houff | NA | PTP_CM27_Vendor Master | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.19.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.22.1,1.2.5.2.24.2,1.2.5.2.27.5 | NA | 4283 | 4282 | 429643114335 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.19.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.20 | Auto Scheduled | 0% | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | No | 0.88d | Thu 9/24/26 | Thu 9/24/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Thu 9/24/26 |  | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 4284 |  |  | -81.69d | Yes | Yes | Yes | No | No | 1.2.5.2.20 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.20.1 | Auto Scheduled | 0% | Extract File(Will Extract from LFA1) | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey |  | 18961920 |  | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 9/24/26 | Thu 9/24/26 |  | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.5.2.20.2,1.2.5.2.24.1 | Thu 4/16/26 | 4285 |  | 42864310 | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.20.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.20.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey | 1895 | 1897 | Sam Houff | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.20.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.20.3 | NA | 4286 | 4285 | 4287 | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.20.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.20.3 | Auto Scheduled | 0% | Simulate Load/ Not Needed | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey | 1896 | 18981899 |  | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.20.2 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.20.4,1.2.5.2.20.5 | NA | 4287 | 4286 | 42884289 | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.20.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.20.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey | 1897 |  | Sam Houff | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.20.3 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4288 | 4287 |  | -647.52h | No | Yes | Yes | No | No | 1.2.5.2.20.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.20.5 | Auto Scheduled | 0% | Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkkey | 1897 | 1900 |  | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.20.3 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.20.6 | NA | 4289 | 4287 | 4290 | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.20.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.20.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey | 1899 | 2095 | Sam Houff | NA | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.20.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.57.1 | NA | 4290 | 4289 | 4485 | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.20.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.21 | Auto Scheduled | 0% | RTR_****_Credit Hierarchy | No | 1.91d | Thu 10/1/26 | Mon 10/5/26 |  |  |  |  | NA | Master Data Loads | Thu 10/1/26 | Mon 10/5/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4291 |  |  | -87.47d | Yes | Yes | Yes | No | No | 1.2.5.2.21 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.21.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Thu 10/1/26 | Thu 10/1/26 | Kasey Hughes | 1884 |  | Brian Wagner | NA | RTR_****_Credit Hierarchy | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.18.4 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than |  | Wed 4/15/26 | 4292 | 4274 |  | -41101m | No | Yes | Yes | No | No | 1.2.5.2.21.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.21.2 | Auto Scheduled | 0% | Load | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Kasey Hughes | 1886 | 1904 |  | NA | RTR_****_Credit Hierarchy | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.18.6 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.21.3 | NA | 4293 | 4276 | 4294 | -699.77h | No | Yes | Yes | No | No | 1.2.5.2.21.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.21.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 10/2/26 | Mon 10/5/26 | Kasey Hughes | 1903 |  | Brian Wagner | NA | RTR_****_Credit Hierarchy | Fri 10/2/26 | Mon 10/5/26 | 1.2.5.2.21.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4294 | 4293 |  | -699.77h | No | Yes | Yes | No | No | 1.2.5.2.21.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.22 | Auto Scheduled | 0% | PTP_CM27_BP_Intercompany Supplier | No | 1.13d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 4295 |  |  | -81.69d | Yes | Yes | Yes | No | No | 1.2.5.2.22 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.22.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey,Ric Haraida | 1893 | 1907 |  | NA | PTP_CM27_BP_Intercompany Supplier | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.19.6 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.22.2 | NA | 4296 | 4283 | 4297 | -39211m | No | Yes | Yes | No | No | 1.2.5.2.22.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.22.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey,Ric Haraida | 1906 | 1908 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Supplier | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.22.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.22.3 | NA | 4297 | 4296 | 4298 | -39211m | No | Yes | Yes | No | No | 1.2.5.2.22.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.22.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 1907 | 1909 |  | NA | PTP_CM27_BP_Intercompany Supplier | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.22.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.22.4 | NA | 4298 | 4297 | 4299 | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.22.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.22.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey,Ric Haraida | 1908 | 1910 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Supplier | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.22.3 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.22.5 | NA | 4299 | 4298 | 4300 | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.22.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.22.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 9/24/26 | Fri 9/25/26 | Data Migration Team | 1909 | 19112067 |  | NA | PTP_CM27_BP_Intercompany Supplier | Thu 9/24/26 | Fri 9/25/26 | 1.2.5.2.22.4 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.5.2.22.6,1.2.5.2.51.1 | NA | 4300 | 4299 | 43014457 | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.22.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.22.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 9/25/26 | Fri 9/25/26 | Nevin Varkey,Ric Haraida | 1910 |  | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Supplier | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.22.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 4301 | 4300 |  | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.22.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.23 | Auto Scheduled | 0% | PTP_CM27_BP_Intercompany Customer | No | 1.06d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 4302 |  |  | -81.25d | Yes | Yes | Yes | No | No | 1.2.5.2.23 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.23.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey,Ric Haraida |  |  |  | NA | PTP_CM27_BP_Intercompany Customer | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4303 |  |  | -38521m | No | Yes | Yes | No | No | 1.2.5.2.23.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.23.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey,Ric Haraida |  | 1915 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Customer | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.23.3 | NA | 4304 |  | 4305 | -39001m | No | Yes | Yes | No | No | 1.2.5.2.23.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.23.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 1914 | 1916 |  | NA | PTP_CM27_BP_Intercompany Customer | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.23.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.23.4 | NA | 4305 | 4304 | 4306 | -650.02h | No | Yes | Yes | No | No | 1.2.5.2.23.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.23.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey,Ric Haraida | 1915 | 1917 | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Customer | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.23.3 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.23.5 | NA | 4306 | 4305 | 4307 | -650.02h | No | Yes | Yes | No | No | 1.2.5.2.23.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.23.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 1916 | 19182067 |  | NA | PTP_CM27_BP_Intercompany Customer | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.23.4 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.5.2.23.6,1.2.5.2.51.1 | NA | 4307 | 4306 | 43084457 | -650.02h | No | Yes | Yes | No | No | 1.2.5.2.23.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.23.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Fri 9/25/26 | Nevin Varkey,Ric Haraida | 1917 |  | Sam Houff,Kim Kolesar | NA | PTP_CM27_BP_Intercompany Customer | Thu 9/24/26 | Fri 9/25/26 | 1.2.5.2.23.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 4308 | 4307 |  | -650.02h | No | Yes | Yes | No | No | 1.2.5.2.23.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.24 | Auto Scheduled | 0% | PTP_CM26_Material_Master - All Types | No | 2.28d | Thu 9/24/26 | Mon 9/28/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Mon 9/28/26 |  | Fri 4/10/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 4309 |  |  | -90.5d | Yes | Yes | Yes | No | No | 1.2.5.2.24 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.24.1 | Auto Scheduled | 0% | Extract File | No | 5h | Thu 9/24/26 | Fri 9/25/26 | Data Migration Team | 1895 |  |  | NA | PTP_CM26_Material_Master - All Types | Thu 9/24/26 | Fri 9/25/26 | 1.2.5.2.20.1 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4310 | 4285 |  | -649.27h | No | Yes | Yes | No | No | 1.2.5.2.24.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.24.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 9/24/26 | Fri 9/25/26 | Nevin Varkey,Ric Haraida | 1893 | 1922 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - All Types | Thu 9/24/26 | Fri 9/25/26 | 1.2.5.2.19.6 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible | 1.2.5.2.24.3 | NA | 4311 | 4283 | 4312 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.24.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.24.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 9/25/26 | Fri 9/25/26 | Data Migration Team | 1921 | 1923 |  | NA | PTP_CM26_Material_Master - All Types | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.24.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.5.2.24.4 | NA | 4312 | 4311 | 4313 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.24.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.24.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 4h | Fri 9/25/26 | Fri 9/25/26 | Nevin Varkey | 1922 | 1924 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - All Types | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.24.3 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.5.2.24.5 | NA | 4313 | 4312 | 4314 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.24.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.24.5 | Auto Scheduled | 0% | Load | No | 3h | Fri 9/25/26 | Mon 9/28/26 | Data Migration Team | 1923 | 192519281935 |  | NA | PTP_CM26_Material_Master - All Types | Fri 9/25/26 | Mon 9/28/26 | 1.2.5.2.24.4 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.24.6,1.2.5.2.25.2,1.2.5.2.26.2 | NA | 4314 | 4313 | 431543184325 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.24.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.24.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Nevin Varkey | 1924 | 194119481955 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - All Types | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.24.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.27.1,1.2.5.2.28.1,1.2.5.2.29.1 | NA | 4315 | 4314 | 433143384345 | -705.77h | No | Yes | Yes | No | No | 1.2.5.2.24.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.25 | Auto Scheduled | 0% | PTP_CM26_Material_Master - SERV - Service Materials | No | 1.34d | Fri 9/25/26 | Tue 9/29/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Tue 9/29/26 |  | Tue 4/7/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 4316 |  |  | -83.41d | Yes | Yes | Yes | No | No | 1.2.5.2.25 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.25.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Fri 9/25/26 | Mon 9/28/26 | Nevin Varkey,Ric Haraida | 1796 |  |  | NA | PTP_CM26_Material_Master - SERV - Service Materials | Fri 9/25/26 | Mon 9/28/26 | 1.2.5.2.4.6 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 4317 | 4186 |  | -39421m | No | Yes | Yes | No | No | 1.2.5.2.25.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.25.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 9/28/26 | Mon 9/28/26 | Nevin Varkey,Ric Haraida | 1924 | 1929 | Sam Houff,Kim Kolesar | NA | PTP_CM26_Material_Master - SERV - Service Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.24.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.5.2.25.3 | NA | 4318 | 4314 | 4319 | -40036m | No | Yes | Yes | No | No | 1.2.5.2.25.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.25.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1928 | 1930 |  | NA | PTP_CM26_Material_Master - SERV - Service Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.25.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.5.2.25.4 | NA | 4319 | 4318 | 4320 | -667.27h | No | Yes | Yes | No | No | 1.2.5.2.25.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.25.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Nevin Varkey,Ric Haraida | 1929 | 1931 | Sam Houff,Kim Kolesar | NA | PTP_CM26_Material_Master - SERV - Service Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.25.3 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.25.5 | NA | 4320 | 4319 | 4321 | -667.27h | No | Yes | Yes | No | No | 1.2.5.2.25.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.25.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1930 | 1932 |  | NA | PTP_CM26_Material_Master - SERV - Service Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.25.4 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.25.6 | NA | 4321 | 4320 | 4322 | -667.27h | No | Yes | Yes | No | No | 1.2.5.2.25.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.25.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 9/28/26 | Tue 9/29/26 | Nevin Varkey,Ric Haraida | 1931 |  | Sam Houff,Kim Kolesar | NA | PTP_CM26_Material_Master - SERV - Service Materials | Mon 9/28/26 | Tue 9/29/26 | 1.2.5.2.25.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 4322 | 4321 |  | -667.27h | No | Yes | Yes | No | No | 1.2.5.2.25.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.26 | Auto Scheduled | 0% | PTP_CM26_Material_Master - KMAT - Configurable Materials | No | 1.34d | Fri 9/25/26 | Tue 9/29/26 |  |  | 20262023 |  | NA | Master Data Loads | Fri 9/25/26 | Tue 9/29/26 |  | Tue 4/7/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.42.1,1.2.5.2.41.1 | NA | 4323 |  | 44164413 | -90.47d | Yes | Yes | Yes | No | No | 1.2.5.2.26 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.26.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Fri 9/25/26 | Mon 9/28/26 | Eric Heisler | 1796 |  |  | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Fri 9/25/26 | Mon 9/28/26 | 1.2.5.2.4.6 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 4324 | 4186 |  | -40666m | No | Yes | Yes | No | No | 1.2.5.2.26.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.26.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 9/28/26 | Mon 9/28/26 | Eric Heisler | 1924 | 1936 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.24.5 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.5.2.26.3 | NA | 4325 | 4314 | 4326 | -43561m | No | Yes | Yes | No | No | 1.2.5.2.26.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.26.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1935 | 1937 |  | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.26.2 | Tue 4/14/26 | Tue 4/14/26 | As Soon As Possible | 1.2.5.2.26.4 | NA | 4326 | 4325 | 4327 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.26.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.26.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Eric Heisler | 1936 | 1938 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.26.3 | Tue 4/14/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.26.5 | NA | 4327 | 4326 | 4328 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.26.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.26.5 | Auto Scheduled | 0% | Load | No | 2h | Mon 9/28/26 | Mon 9/28/26 | Data Migration Team | 1937 | 1939 |  | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Mon 9/28/26 | Mon 9/28/26 | 1.2.5.2.26.4 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.26.6 | NA | 4328 | 4327 | 4329 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.26.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.26.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 9/28/26 | Tue 9/29/26 | Eric Heisler | 1938 | 1.9412e+19 | Sam Houff,Kim Kolesar,Matt | NA | PTP_CM26_Material_Master - KMAT - Configurable Materials | Mon 9/28/26 | Tue 9/29/26 | 1.2.5.2.26.5 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.27.1,1.2.5.2.28.1,1.2.5.2.29.1,1.2.5.2.40.1,1.2.5.2.46.1 | NA | 4329 | 4328 | 4.3314e+19 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.26.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.27 | Auto Scheduled | 0% | PTP_CM28_Purchase_Info_Records | No | 3.59d | Thu 9/24/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Wed 9/30/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4330 |  |  | -84.71d | Yes | Yes | Yes | No | No | 1.2.5.2.27 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.27.1 | Auto Scheduled | 0% | Extract File | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 19251939 | 19421962 |  | NA | PTP_CM28_Purchase_Info_Records | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.24.6,1.2.5.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.27.2,1.2.5.2.30.1 | NA | 4331 | 43154329 | 43324352 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.27.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.27.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 1941 | 1943 | Sam Houff | NA | PTP_CM28_Purchase_Info_Records | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.27.1 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.27.3 | NA | 4332 | 4331 | 4333 | -673.27h | No | Yes | Yes | No | No | 1.2.5.2.27.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.27.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1942 | 1944 |  | NA | PTP_CM28_Purchase_Info_Records | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.27.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.27.4 | NA | 4333 | 4332 | 4334 | -673.27h | No | Yes | Yes | No | No | 1.2.5.2.27.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.27.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 9/29/26 | Wed 9/30/26 | Nevin Varkey | 1943 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Records | Tue 9/29/26 | Wed 9/30/26 | 1.2.5.2.27.3 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than |  | Fri 4/17/26 | 4334 | 4333 |  | -673.27h | No | Yes | Yes | No | No | 1.2.5.2.27.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.27.5 | Auto Scheduled | 0% | Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 1893 | 1946 |  | NA | PTP_CM28_Purchase_Info_Records | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.19.6 | Wed 4/15/26 | Wed 4/15/26 | Start No Earlier Than | 1.2.5.2.27.6 | Fri 4/17/26 | 4335 | 4283 | 4336 | -647.52h | No | Yes | Yes | No | No | 1.2.5.2.27.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.27.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Nevin Varkey | 1945 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Records | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.27.5 | Wed 4/15/26 | Wed 4/15/26 | Start No Earlier Than |  | Fri 4/17/26 | 4336 | 4335 |  | -647.52h | No | Yes | Yes | No | No | 1.2.5.2.27.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.28 | Auto Scheduled | 0% | PTP_CM28_Purchase_Info_Record External Processing | No | 1.13d | Tue 9/29/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Wed 9/30/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4337 |  |  | -84.53d | Yes | Yes | Yes | No | No | 1.2.5.2.28 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.28.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 19251939 | 1949 |  | NA | PTP_CM28_Purchase_Info_Record External Processing | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.24.6,1.2.5.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.28.2 | NA | 4338 | 43154329 | 4339 | -40576m | No | Yes | Yes | No | No | 1.2.5.2.28.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.28.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 1948 | 1950 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record External Processing | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.28.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.28.3 | NA | 4339 | 4338 | 4340 | -40576m | No | Yes | Yes | No | No | 1.2.5.2.28.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.28.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1949 | 1951 |  | NA | PTP_CM28_Purchase_Info_Record External Processing | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.28.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.28.4 | NA | 4340 | 4339 | 4341 | -676.27h | No | Yes | Yes | No | No | 1.2.5.2.28.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.28.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 1950 | 1952 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record External Processing | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.28.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.28.5 | NA | 4341 | 4340 | 4342 | -676.27h | No | Yes | Yes | No | No | 1.2.5.2.28.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.28.5 | Auto Scheduled | 0% | Load | No | 2h | Tue 9/29/26 | Wed 9/30/26 | Data Migration Team | 1951 | 1953 |  | NA | PTP_CM28_Purchase_Info_Record External Processing | Tue 9/29/26 | Wed 9/30/26 | 1.2.5.2.28.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.28.6 | NA | 4342 | 4341 | 4343 | -676.27h | No | Yes | Yes | No | No | 1.2.5.2.28.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.28.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Nevin Varkey | 1952 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Record External Processing | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.28.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4343 | 4342 |  | -676.27h | No | Yes | Yes | No | No | 1.2.5.2.28.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.29 | Auto Scheduled | 0% | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | No | 1.13d | Tue 9/29/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Wed 9/30/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4344 |  |  | -89.03d | Yes | Yes | Yes | No | No | 1.2.5.2.29 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.29.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 19251939 | 1956 |  | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.24.6,1.2.5.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.29.2 | NA | 4345 | 43154329 | 4346 | -42736m | No | Yes | Yes | No | No | 1.2.5.2.29.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.29.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 1955 | 1957 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.29.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.29.3 | NA | 4346 | 4345 | 4347 | -42736m | No | Yes | Yes | No | No | 1.2.5.2.29.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.29.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1956 | 19582089 |  | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.29.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.29.4,1.2.5.2.55.1 | NA | 4347 | 4346 | 43484479 | -712.27h | No | Yes | Yes | No | No | 1.2.5.2.29.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.29.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Nevin Varkey | 1957 | 1959 | Sam Houff | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.29.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.29.5 | NA | 4348 | 4347 | 4349 | -676.27h | No | Yes | Yes | No | No | 1.2.5.2.29.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.29.5 | Auto Scheduled | 0% | Load | No | 2h | Tue 9/29/26 | Wed 9/30/26 | Data Migration Team | 1958 | 1960 |  | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Tue 9/29/26 | Wed 9/30/26 | 1.2.5.2.29.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.29.6 | NA | 4349 | 4348 | 4350 | -676.27h | No | Yes | Yes | No | No | 1.2.5.2.29.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.29.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Nevin Varkey | 1959 |  | Sam Houff | NA | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.29.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4350 | 4349 |  | -676.27h | No | Yes | Yes | No | No | 1.2.5.2.29.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.30 | Auto Scheduled | 0% | PTM_CM31_BOM Conversion | No | 2.48d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Wed 4/15/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4351 |  |  | -87.55d | Yes | Yes | Yes | No | No | 1.2.5.2.30 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.30.1 | Auto Scheduled | 0% | Extract File | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1941 | 19631969 |  | NA | PTM_CM31_BOM Conversion | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.27.1 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.30.2,1.2.5.2.31.1 | NA | 4352 | 4331 | 43534359 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.30.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.30.2 | Auto Scheduled | 0% | Pre Load Validation | No | 0.5h | Tue 9/29/26 | Tue 9/29/26 | Brad Meseck | 1962 | 1964 | Matt Palastro, Dave Duda | NA | PTM_CM31_BOM Conversion | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.30.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.30.3 | NA | 4353 | 4352 | 4354 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.30.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.30.3 | Auto Scheduled | 0% | Simulate Load | No | 15.5h | Tue 9/29/26 | Thu 10/1/26 | Data Migration Team | 1963 | 1965 |  | NA | PTM_CM31_BOM Conversion | Tue 9/29/26 | Thu 10/1/26 | 1.2.5.2.30.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.5.2.30.4 | Fri 4/17/26 | 4354 | 4353 | 4355 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.30.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.30.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 0.5h | Thu 10/1/26 | Thu 10/1/26 | Brad Meseck | 1964 | 1966 | Matt Palastro, Dave Duda | NA | PTM_CM31_BOM Conversion | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.30.3 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 2026-04-01 | Fri 4/17/26 | 4355 | 4354 | 4356 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.30.4 | 6 | No | 500 | Future Task | No | 0h
2026-04-01 | Auto Scheduled | 0% | Load | No | 1h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1965 | 1967 |  | NA | PTM_CM31_BOM Conversion | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.30.4 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.30.6 | NA | 4356 | 4355 | 4357 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.30.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.30.6 | Auto Scheduled | 0% | Post Load Validation | No | 0.5h | Thu 10/1/26 | Thu 10/1/26 | Brad Meseck | 1966 | 1970 | Matt Palastro, Dave Duda | NA | PTM_CM31_BOM Conversion | Thu 10/1/26 | Thu 10/1/26 | 2026-04-01 | Thu 4/16/26 | Fri 4/17/26 | Finish No Earlier Than | 1.2.5.2.31.2 | Thu 4/16/26 | 4357 | 4356 | 4360 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.30.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.31 | Auto Scheduled | 0% | PTM_CM40_Work Center Conversion | No | 3.08d | Tue 9/29/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Fri 10/2/26 |  | Thu 4/16/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 4358 |  |  | -87.55d | Yes | Yes | Yes | No | No | 1.2.5.2.31 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.31.1 | Auto Scheduled | 0% | Extract File | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1962 | 1976 |  | NA | PTM_CM40_Work Center Conversion | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.30.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.32.1 | NA | 4359 | 4352 | 4366 | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.31.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.31.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Thu 10/1/26 | Fri 10/2/26 | Brad Meseck | 1967 | 1971 | Matt Palastro, Dave Duda | NA | PTM_CM40_Work Center Conversion | Thu 10/1/26 | Fri 10/2/26 | 1.2.5.2.30.6 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.31.3 | NA | 4360 | 4357 | 4361 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.31.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.31.3 | Auto Scheduled | 0% | Simulate Load | No | 0.25h | Fri 10/2/26 | Fri 10/2/26 | Data Migration Team | 1970 | 1972 |  | NA | PTM_CM40_Work Center Conversion | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.31.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.31.4 | NA | 4361 | 4360 | 4362 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.31.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.31.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 0.5h | Fri 10/2/26 | Fri 10/2/26 | Brad Meseck | 1971 | 1973 | Matt Palastro, Dave Duda | NA | PTM_CM40_Work Center Conversion | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.31.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.31.5 | NA | 4362 | 4361 | 4363 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.31.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.31.5 | Auto Scheduled | 0% | Load | No | 1h | Fri 10/2/26 | Fri 10/2/26 | Data Migration Team | 1972 | 1974 |  | NA | PTM_CM40_Work Center Conversion | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.31.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.31.6 | NA | 4363 | 4362 | 4364 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.31.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.31.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Brad Meseck | 1973 | 1977 | Matt Palastro, Dave Duda | NA | PTM_CM40_Work Center Conversion | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.31.5 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.5.2.32.2 | NA | 4364 | 4363 | 4367 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.31.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.32 | Auto Scheduled | 0% | PTM_CM38_Routing Conversion | No | 4.27d | Tue 9/29/26 | Mon 10/5/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Mon 10/5/26 |  | Thu 4/16/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 4365 |  |  | -88.05d | Yes | Yes | Yes | No | No | 1.2.5.2.32 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.32.1 | Auto Scheduled | 0% | Extract File | No | 1h | Tue 9/29/26 | Tue 9/29/26 | Data Migration Team | 1969 | 1983 |  | NA | PTM_CM38_Routing Conversion | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.31.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.33.1 | NA | 4366 | 4359 | 4373 | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.32.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.32.2 | Auto Scheduled | 0% | Pre Load Validation | No | 2h | Fri 10/2/26 | Mon 10/5/26 | Brad Meseck | 1974 | 1978 | Matt Palastro, Dave Duda | NA | PTM_CM38_Routing Conversion | Fri 10/2/26 | Mon 10/5/26 | 1.2.5.2.31.6 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.5.2.32.3 | NA | 4367 | 4364 | 4368 | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.32.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.32.3 | Auto Scheduled | 0% | Simulate Load | No | 2h | Mon 10/5/26 | Mon 10/5/26 | Data Migration Team | 1977 | 1979SS |  | NA | PTM_CM38_Routing Conversion | Mon 10/5/26 | Mon 10/5/26 | 1.2.5.2.32.2 | Mon 4/20/26 | Mon 4/20/26 | Finish No Earlier Than | 1.2.5.2.32.4[SS] | Fri 4/17/26 | 4368 | 4367 | 4369SS | -700.39h | No | Yes | Yes | No | No | 1.2.5.2.32.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.32.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 3h | Mon 10/5/26 | Mon 10/5/26 | Brad Meseck | 1978SS | 1980 | Matt Palastro, Dave Duda | NA | PTM_CM38_Routing Conversion | Mon 10/5/26 | Mon 10/5/26 | 1.2.5.2.32.3[SS] | Mon 4/20/26 | Mon 4/20/26 | Start No Earlier Than | 1.2.5.2.32.5 | Fri 4/17/26 | 4369 | 4368SS | 4370 | -704.39h | No | Yes | Yes | No | No | 1.2.5.2.32.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.32.5 | Auto Scheduled | 0% | Load | No | 1h | Mon 10/5/26 | Mon 10/5/26 | Data Migration Team | 1979 | 1981 |  | NA | PTM_CM38_Routing Conversion | Mon 10/5/26 | Mon 10/5/26 | 1.2.5.2.32.4 | Mon 4/20/26 | Mon 4/20/26 | Start No Earlier Than | 1.2.5.2.32.6 | Mon 4/20/26 | 4370 | 4369 | 4371 | -704.39h | No | Yes | Yes | No | No | 1.2.5.2.32.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.32.6 | Auto Scheduled | 0% | Post Load Validation | No | 2h | Mon 10/5/26 | Mon 10/5/26 | Brad Meseck | 1980 |  | Matt Palastro, Dave Duda | NA | PTM_CM38_Routing Conversion | Mon 10/5/26 | Mon 10/5/26 | 1.2.5.2.32.5 | Mon 4/20/26 | Tue 4/21/26 | Start No Earlier Than |  | Mon 4/20/26 | 4371 | 4370 |  | -704.39h | No | Yes | Yes | No | No | 1.2.5.2.32.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.33 | Auto Scheduled | 0% | PTM_CM36_Production Version Conversion | No | 1.13d | Tue 9/29/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Wed 9/30/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4372 |  |  | -86.97d | Yes | Yes | Yes | No | No | 1.2.5.2.33 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.33.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Brad Meseck | 1976 | 19842078 |  | NA | PTM_CM36_Production Version Conversion | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.32.1 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than | 1.2.5.2.33.2,1.2.5.2.53.1 | Mon 4/20/26 | 4373 | 4366 | 43744468 | -41746m | No | Yes | Yes | No | No | 1.2.5.2.33.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.33.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Brad Meseck | 1983 | 1985 | Matt Palastro, Dave Duda | NA | PTM_CM36_Production Version Conversion | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.33.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.33.3 | NA | 4374 | 4373 | 4375 | -41746m | No | Yes | Yes | No | No | 1.2.5.2.33.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.33.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Tue 9/29/26 | Wed 9/30/26 | Data Migration Team | 1984 | 1986 |  | NA | PTM_CM36_Production Version Conversion | Tue 9/29/26 | Wed 9/30/26 | 1.2.5.2.33.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.33.4 | NA | 4375 | 4374 | 4376 | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.33.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.33.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Brad Meseck | 1985 | 1987 | Matt Palastro, Dave Duda | NA | PTM_CM36_Production Version Conversion | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.33.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.33.5 | NA | 4376 | 4375 | 4377 | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.33.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.33.5 | Auto Scheduled | 0% | Load | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 1986 | 1988 |  | NA | PTM_CM36_Production Version Conversion | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.33.4 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.33.6 | NA | 4377 | 4376 | 4378 | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.33.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.33.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Brad Meseck | 1987 | 1990 | Matt Palastro, Dave Duda | NA | PTM_CM36_Production Version Conversion | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.33.5 | Fri 4/17/26 | Fri 4/17/26 | Finish No Earlier Than | 1.2.5.2.34.1 | Fri 4/17/26 | 4378 | 4377 | 4380 | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.33.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.34 | Auto Scheduled | 0% | PTM_CM35_Inspection Plan | No | 1.13d | Wed 9/30/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Fri 10/2/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 4379 |  |  | -86.97d | Yes | Yes | Yes | No | No | 1.2.5.2.34 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.34.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Wed 9/30/26 | Wed 9/30/26 | Brad Meseck | 1988 | 19911997 |  | NA | PTM_CM35_Inspection Plan | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.33.6 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.34.2,1.2.5.2.35.1 | NA | 4380 | 4378 | 43814387 | -41746m | No | Yes | Yes | No | No | 1.2.5.2.34.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.34.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Wed 9/30/26 | Thu 10/1/26 | Brad Meseck | 1990 | 1992 | Matt Palastro, Dave Duda | NA | PTM_CM35_Inspection Plan | Wed 9/30/26 | Thu 10/1/26 | 1.2.5.2.34.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.34.3 | NA | 4381 | 4380 | 4382 | -41356m | No | Yes | Yes | No | No | 1.2.5.2.34.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.34.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1991 | 1993 |  | NA | PTM_CM35_Inspection Plan | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.34.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.34.4 | NA | 4382 | 4381 | 4383 | -689.27h | No | Yes | Yes | No | No | 1.2.5.2.34.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.34.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Brad Meseck | 1992 | 1994 | Matt Palastro, Dave Duda | NA | PTM_CM35_Inspection Plan | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.34.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.34.5 | NA | 4383 | 4382 | 4384 | -689.27h | No | Yes | Yes | No | No | 1.2.5.2.34.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.34.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1993 | 1995 |  | NA | PTM_CM35_Inspection Plan | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.34.4 | Fri 4/17/26 | Mon 4/20/26 | Finish No Earlier Than | 1.2.5.2.34.6 | Fri 4/17/26 | 4384 | 4383 | 4385 | -689.27h | No | Yes | Yes | No | No | 1.2.5.2.34.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.34.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/1/26 | Fri 10/2/26 | Brad Meseck | 1994 |  | Matt Palastro, Dave Duda | NA | PTM_CM35_Inspection Plan | Thu 10/1/26 | Fri 10/2/26 | 1.2.5.2.34.5 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 4385 | 4384 |  | -689.27h | No | Yes | Yes | No | No | 1.2.5.2.34.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.35 | Auto Scheduled | 0% | PTM_CM48_Equipment_Master_Serial Numbers | No | 1.13d | Wed 9/30/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Fri 10/2/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 4386 |  |  | -86.97d | Yes | Yes | Yes | No | No | 1.2.5.2.35 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.35.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Wed 9/30/26 | Thu 10/1/26 | Brad Meseck | 1990 | 1998 |  | NA | PTM_CM48_Equipment_Master_Serial Numbers | Wed 9/30/26 | Thu 10/1/26 | 1.2.5.2.34.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.35.2 | NA | 4387 | 4380 | 4388 | -41746m | No | Yes | Yes | No | No | 1.2.5.2.35.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.35.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 10/1/26 | Thu 10/1/26 | Brad Meseck | 1997 | 1999 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Serial Numbers | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.35.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.35.3 | NA | 4388 | 4387 | 4389 | -41746m | No | Yes | Yes | No | No | 1.2.5.2.35.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.35.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 1998 | 2000 |  | NA | PTM_CM48_Equipment_Master_Serial Numbers | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.35.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.35.4 | NA | 4389 | 4388 | 4390 | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.35.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.35.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Brad Meseck | 1999 | 2001 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Serial Numbers | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.35.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.35.5 | NA | 4390 | 4389 | 4391 | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.35.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.35.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 10/1/26 | Thu 10/1/26 | Data Migration Team | 2000 | 2002 |  | NA | PTM_CM48_Equipment_Master_Serial Numbers | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.35.4 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.5.2.35.6 | NA | 4391 | 4390 | 4392 | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.35.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.35.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/1/26 | Fri 10/2/26 | Brad Meseck | 2001 | 2004 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Serial Numbers | Thu 10/1/26 | Fri 10/2/26 | 1.2.5.2.35.5 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.5.2.36.1 | NA | 4392 | 4391 | 4394 | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.35.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.36 | Auto Scheduled | 0% | PTM_CM48_Equipment_Master_Service | No | 6.78d | Thu 9/24/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 10/2/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 4393 |  |  | -86.97d | Yes | Yes | Yes | No | No | 1.2.5.2.36 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.36.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Fri 10/2/26 | Fri 10/2/26 | Brad Meseck | 2002 | 2005 |  | NA | PTM_CM48_Equipment_Master_Service | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.35.6 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.5.2.36.2 | NA | 4394 | 4392 | 4395 | -41746m | No | Yes | Yes | No | No | 1.2.5.2.36.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.36.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Fri 10/2/26 | Fri 10/2/26 | Brad Meseck | 2004 | 2006 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Service | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.36.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.5.2.36.3 | NA | 4395 | 4394 | 4396 | -41746m | No | Yes | Yes | No | No | 1.2.5.2.36.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.36.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Fri 10/2/26 | Fri 10/2/26 | Data Migration Team | 2005 | 2007 |  | NA | PTM_CM48_Equipment_Master_Service | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.36.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.5.2.36.4 | NA | 4396 | 4395 | 4397 | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.36.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.36.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Brad Meseck | 2006 | 2008 | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Service | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.36.3 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible | 1.2.5.2.36.5 | NA | 4397 | 4396 | 4398 | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.36.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.36.5 | Auto Scheduled | 0% | Load | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Data Migration Team | 2007 |  |  | NA | PTM_CM48_Equipment_Master_Service | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.36.4 | Tue 4/21/26 | Tue 4/21/26 | Finish No Earlier Than |  | Tue 4/21/26 | 4398 | 4397 |  | -695.77h | No | Yes | Yes | No | No | 1.2.5.2.36.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.36.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Thu 9/24/26 | Brad Meseck |  |  | Matt Palastro, Dave Duda | NA | PTM_CM48_Equipment_Master_Service | Thu 9/24/26 | Thu 9/24/26 |  | Tue 4/21/26 | Tue 4/21/26 | Start No Earlier Than |  | Tue 4/21/26 | 4399 |  |  | -644.52h | No | Yes | Yes | No | No | 1.2.5.2.36.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.37 | Auto Scheduled | 0% | VC_Object Dependencies | No | 0.63d | Thu 9/24/26 | Thu 9/24/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 4400 |  |  | -82.69d | Yes | Yes | Yes | No | No | 1.2.5.2.37 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.37.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Eric Heisler | 1771 | 2012 |  | NA | VC_Object Dependencies | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.5.2.37.2 | NA | 4401 | 4161 | 4402 | -661.52h | No | Yes | Yes | No | No | 1.2.5.2.37.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.37.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Thu 9/24/26 | Eric Heisler | 2011 | 2014 | Matt Palastro, Dave Duda | NA | VC_Object Dependencies | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.37.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.5.2.38.1 | NA | 4402 | 4401 | 4404 | -661.52h | No | Yes | Yes | No | No | 1.2.5.2.37.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.38 | Auto Scheduled | 0% | VC_Characteristics | No | 0.63d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 4403 |  |  | -82.69d | Yes | Yes | Yes | No | No | 1.2.5.2.38 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.38.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Eric Heisler | 2012 | 2015 |  | NA | VC_Characteristics | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.37.2 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.5.2.38.2 | NA | 4404 | 4402 | 4405 | -661.52h | No | Yes | Yes | No | No | 1.2.5.2.38.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.38.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Fri 9/25/26 | Eric Heisler | 2014 | 2017 | Matt Palastro, Dave Duda | NA | VC_Characteristics | Thu 9/24/26 | Fri 9/25/26 | 1.2.5.2.38.1 | Mon 4/6/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.39.1 | NA | 4405 | 4404 | 4407 | -661.52h | No | Yes | Yes | No | No | 1.2.5.2.38.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.39 | Auto Scheduled | 0% | VC_Classes | No | 0.63d | Fri 9/25/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Fri 9/25/26 |  | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible |  | NA | 4406 |  |  | -82.69d | Yes | Yes | Yes | No | No | 1.2.5.2.39 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.39.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Fri 9/25/26 | Fri 9/25/26 | Eric Heisler | 2015 | 2018 |  | NA | VC_Classes | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.38.2 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.39.2 | NA | 4407 | 4405 | 4408 | -661.52h | No | Yes | Yes | No | No | 1.2.5.2.39.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.39.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 9/25/26 | Fri 9/25/26 | Eric Heisler | 2017 | 2023 | Matt Palastro, Dave Duda | NA | VC_Classes | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.39.1 | Tue 4/7/26 | Tue 4/7/26 | As Soon As Possible | 1.2.5.2.41.1 | NA | 4408 | 4407 | 4413 | -661.52h | No | Yes | Yes | No | No | 1.2.5.2.39.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.40 | Auto Scheduled | 0% | VC_Classification (Class Type 200) | No | 0.63d | Tue 9/29/26 | Tue 9/29/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Tue 9/29/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4409 |  |  | -84.03d | Yes | Yes | Yes | No | No | 1.2.5.2.40 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.40.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 1939 | 2021 |  | NA | VC_Classification (Class Type 200) | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.26.6 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.40.2 | NA | 4410 | 4329 | 4411 | -672.27h | No | Yes | Yes | No | No | 1.2.5.2.40.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.40.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 2020 |  | Matt Palastro, Dave Duda | NA | VC_Classification (Class Type 200) | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.40.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4411 | 4410 |  | -672.27h | No | Yes | Yes | No | No | 1.2.5.2.40.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.41 | Auto Scheduled | 0% | VC_Dependency Nets | No | 0.63d | Tue 9/29/26 | Tue 9/29/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Tue 9/29/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4412 |  |  | -84.03d | Yes | Yes | Yes | No | No | 1.2.5.2.41 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.41.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 19332018 | 2024 |  | NA | VC_Dependency Nets | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.26,1.2.5.2.39.2 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.41.2 | NA | 4413 | 43234408 | 4414 | -672.27h | No | Yes | Yes | No | No | 1.2.5.2.41.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.41.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 2023 |  | Matt Palastro, Dave Duda | NA | VC_Dependency Nets | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.41.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4414 | 4413 |  | -672.27h | No | Yes | Yes | No | No | 1.2.5.2.41.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.42 | Auto Scheduled | 0% | VC_Configuration Profiles | No | 0.63d | Tue 9/29/26 | Tue 9/29/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Tue 9/29/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4415 |  |  | -86d | Yes | Yes | Yes | No | No | 1.2.5.2.42 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.42.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 1933 | 2027 |  | NA | VC_Configuration Profiles | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.26 | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.42.2 | NA | 4416 | 4323 | 4417 | -688.02h | No | Yes | Yes | No | No | 1.2.5.2.42.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.42.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 2026 | 20352029 | Matt Palastro, Dave Duda | NA | VC_Configuration Profiles | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.42.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.45.1,1.2.5.2.43.1 | NA | 4417 | 4416 | 44254419 | -688.02h | No | Yes | Yes | No | No | 1.2.5.2.42.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.43 | Auto Scheduled | 0% | VC_Variant Tables | No | 0.63d | Tue 9/29/26 | Wed 9/30/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Wed 9/30/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4418 |  |  | -85.28d | Yes | Yes | Yes | No | No | 1.2.5.2.43 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.43.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Tue 9/29/26 | Wed 9/30/26 | Eric Heisler | 2027 | 2030 |  | NA | VC_Variant Tables | Tue 9/29/26 | Wed 9/30/26 | 1.2.5.2.42.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.43.2 | NA | 4419 | 4417 | 4420 | -682.27h | No | Yes | Yes | No | No | 1.2.5.2.43.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.43.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Wed 9/30/26 | Eric Heisler | 2029 | 2032 | Matt Palastro, Dave Duda | NA | VC_Variant Tables | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.43.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.44.1 | NA | 4420 | 4419 | 4422 | -682.27h | No | Yes | Yes | No | No | 1.2.5.2.43.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.44 | Auto Scheduled | 0% | VC_Variant Tables Content | No | 0.63d | Wed 9/30/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Wed 9/30/26 | Thu 10/1/26 |  | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4421 |  |  | -85.28d | Yes | Yes | Yes | No | No | 1.2.5.2.44 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.44.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Eric Heisler | 2030 | 2033 |  | NA | VC_Variant Tables Content | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.43.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.44.2 | NA | 4422 | 4420 | 4423 | -682.27h | No | Yes | Yes | No | No | 1.2.5.2.44.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.44.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Thu 10/1/26 | Eric Heisler | 2032 |  | Matt Palastro, Dave Duda | NA | VC_Variant Tables Content | Wed 9/30/26 | Thu 10/1/26 | 1.2.5.2.44.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4423 | 4422 |  | -682.27h | No | Yes | Yes | No | No | 1.2.5.2.44.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.45 | Auto Scheduled | 0% | VC_Characteristic Groups | No | 1.97d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4424 |  |  | -86d | Yes | Yes | Yes | No | No | 1.2.5.2.45 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.45.1 | Auto Scheduled | 0% | Run ALE Transaction to QS5 from DS4 130 | No | 12.75h | Tue 9/29/26 | Thu 10/1/26 | Eric Heisler | 2027 | 2036 |  | NA | VC_Characteristic Groups | Tue 9/29/26 | Thu 10/1/26 | 1.2.5.2.42.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.5.2.45.2 | Fri 4/17/26 | 4425 | 4417 | 4426 | -688.02h | No | Yes | Yes | No | No | 1.2.5.2.45.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.45.2 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/1/26 | Thu 10/1/26 | Eric Heisler | 2035 |  | Matt Palastro, Dave Duda | NA | VC_Characteristic Groups | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.45.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4426 | 4425 |  | -688.02h | No | Yes | Yes | No | No | 1.2.5.2.45.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.46 | Auto Scheduled | 0% | PTM_CM52_Super_BOM | No | 4.09d | Tue 9/29/26 | Mon 10/5/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Mon 10/5/26 |  | Wed 4/15/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4427 |  |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.5.2.46 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.46.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 1939 | 2039 |  | NA | PTM_CM52_Super_BOM | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.26.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.46.2 | NA | 4428 | 4329 | 4429 | -43561m | No | Yes | Yes | No | No | 1.2.5.2.46.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.46.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Eric Heisler | 2038 | 2040 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.46.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.46.3 | NA | 4429 | 4428 | 4430 | -43561m | No | Yes | Yes | No | No | 1.2.5.2.46.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.46.3 | Auto Scheduled | 0% | Simulate Load | No | 24.75h | Tue 9/29/26 | Fri 10/2/26 | Data Migration Team | 2039 | 2041 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Tue 9/29/26 | Fri 10/2/26 | 1.2.5.2.46.2 | Wed 4/15/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.5.2.46.4 | Mon 4/20/26 | 4430 | 4429 | 4431 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.46.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.46.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Eric Heisler | 2040 | 2042 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.46.3 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.5.2.46.5 | Fri 4/17/26 | 4431 | 4430 | 4432 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.46.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.46.5 | Auto Scheduled | 0% | Load | No | 2h | Fri 10/2/26 | Mon 10/5/26 | Data Migration Team | 2041 | 2043 |  | NA | PTM_CM52_Super_BOM | Fri 10/2/26 | Mon 10/5/26 | 1.2.5.2.46.4 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than | 1.2.5.2.46.6 | Fri 4/17/26 | 4432 | 4431 | 4433 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.46.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.46.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Mon 10/5/26 | Mon 10/5/26 | Eric Heisler | 2042 | 2045 | Matt Palastro, Dave Duda | NA | PTM_CM52_Super_BOM | Mon 10/5/26 | Mon 10/5/26 | 1.2.5.2.46.5 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.47.1 | NA | 4433 | 4432 | 4435 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.46.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.47 | Auto Scheduled | 0% | PTM_CM53_Super_Routing | No | 2.13d | Mon 10/5/26 | Wed 10/7/26 |  |  |  |  | NA | Master Data Loads | Mon 10/5/26 | Wed 10/7/26 |  | Thu 4/16/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 4434 |  |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.5.2.47 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.47.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Mon 10/5/26 | Mon 10/5/26 | Eric Heisler | 2043 | 2046 |  | NA | PTM_CM53_Super_Routing | Mon 10/5/26 | Mon 10/5/26 | 1.2.5.2.46.6 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.47.2 | NA | 4435 | 4433 | 4436 | -43561m | No | Yes | Yes | No | No | 1.2.5.2.47.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.47.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Mon 10/5/26 | Mon 10/5/26 | Eric Heisler | 2045 | 2047 | Matt Palastro, Dave Duda | NA | PTM_CM53_Super_Routing | Mon 10/5/26 | Mon 10/5/26 | 1.2.5.2.47.1 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.47.3 | NA | 4436 | 4435 | 4437 | -43561m | No | Yes | Yes | No | No | 1.2.5.2.47.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.47.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Mon 10/5/26 | Tue 10/6/26 | Data Migration Team | 2046 | 2048 |  | NA | PTM_CM53_Super_Routing | Mon 10/5/26 | Tue 10/6/26 | 1.2.5.2.47.2 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.47.4 | NA | 4437 | 4436 | 4438 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.47.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.47.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Tue 10/6/26 | Tue 10/6/26 | Eric Heisler | 2047 | 2049 | Matt Palastro, Dave Duda | NA | PTM_CM53_Super_Routing | Tue 10/6/26 | Tue 10/6/26 | 1.2.5.2.47.3 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.47.5 | NA | 4438 | 4437 | 4439 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.47.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.47.5 | Auto Scheduled | 0% | Load | No | 2h | Tue 10/6/26 | Wed 10/7/26 | Data Migration Team | 2048 | 20502052 |  | NA | PTM_CM53_Super_Routing | Tue 10/6/26 | Wed 10/7/26 | 1.2.5.2.47.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.47.6,1.2.5.2.48.1 | NA | 4439 | 4438 | 44404442 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.47.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.47.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 10/7/26 | Wed 10/7/26 | Eric Heisler | 2049 |  | Matt Palastro, Dave Duda | NA | PTM_CM53_Super_Routing | Wed 10/7/26 | Wed 10/7/26 | 1.2.5.2.47.5 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 4440 | 4439 |  | -717.02h | No | Yes | Yes | No | No | 1.2.5.2.47.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.48 | Auto Scheduled | 0% | VC_VK30 Pricing Variant | No | 0.69d | Wed 10/7/26 | Wed 10/7/26 |  |  |  |  | NA | Master Data Loads | Wed 10/7/26 | Wed 10/7/26 |  | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible |  | NA | 4441 |  |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.5.2.48 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.48.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Wed 10/7/26 | Wed 10/7/26 | Eric Heisler | 2049 | 2053 | Matt Palastro, Dave Duda | NA | VC_VK30 Pricing Variant | Wed 10/7/26 | Wed 10/7/26 | 1.2.5.2.47.5 | Fri 4/17/26 | Fri 4/17/26 | Start No Earlier Than | 1.2.5.2.48.2 | Mon 4/6/26 | 4442 | 4439 | 4443 | -43561m | No | Yes | Yes | No | No | 1.2.5.2.48.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.48.2 | Auto Scheduled | 0% | Load | No | 2h | Wed 10/7/26 | Wed 10/7/26 | Eric Heisler | 2052 | 2054 |  | NA | VC_VK30 Pricing Variant | Wed 10/7/26 | Wed 10/7/26 | 1.2.5.2.48.1 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.48.3 | NA | 4443 | 4442 | 4444 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.48.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.48.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 10/7/26 | Wed 10/7/26 | Eric Heisler | 2053 | 2056 | Matt Palastro, Dave Duda | NA | VC_VK30 Pricing Variant | Wed 10/7/26 | Wed 10/7/26 | 1.2.5.2.48.2 | Fri 4/17/26 | Mon 4/20/26 | As Soon As Possible | 1.2.5.2.49.1 | NA | 4444 | 4443 | 4446 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.48.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.49 | Auto Scheduled | 0% | OTC_CM22_Pricing_Condition | No | 0.69d | Wed 10/7/26 | Thu 10/8/26 |  |  |  |  | NA | Master Data Loads | Wed 10/7/26 | Thu 10/8/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 4445 |  |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.5.2.49 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.49.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Wed 10/7/26 | Wed 10/7/26 | Ric Haraida | 2054 | 2057 | Matt Palastro, Dave Duda | NA | OTC_CM22_Pricing_Condition | Wed 10/7/26 | Wed 10/7/26 | 1.2.5.2.48.3 | Mon 4/20/26 | Mon 4/20/26 | Start No Earlier Than | 1.2.5.2.49.2 | Mon 4/6/26 | 4446 | 4444 | 4447 | -43561m | No | Yes | Yes | No | No | 1.2.5.2.49.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.49.2 | Auto Scheduled | 0% | Load | No | 2h | Wed 10/7/26 | Thu 10/8/26 | Ric Haraida | 2056 | 20582060 |  | NA | OTC_CM22_Pricing_Condition | Wed 10/7/26 | Thu 10/8/26 | 1.2.5.2.49.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.5.2.49.3,1.2.5.2.50.1 | NA | 4447 | 4446 | 44484450 | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.49.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.49.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/8/26 | Thu 10/8/26 | Ric Haraida,Kim Kolesar | 2057 |  | Matt Palastro, Dave Duda,kim | NA | OTC_CM22_Pricing_Condition | Thu 10/8/26 | Thu 10/8/26 | 1.2.5.2.49.2 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 4448 | 4447 |  | -725.02h | No | Yes | Yes | No | No | 1.2.5.2.49.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.50 | Auto Scheduled | 0% | OTC_CM21_CMIR | No | 0.5d | Thu 10/8/26 | Thu 10/8/26 |  |  |  |  | NA | Master Data Loads | Thu 10/8/26 | Thu 10/8/26 |  | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 4449 |  |  | -90.75d | Yes | Yes | Yes | No | No | 1.2.5.2.50 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.50.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 10/8/26 | Thu 10/8/26 | Ric Haraida | 20572068 | 2061 |  | NA | OTC_CM21_CMIR | Thu 10/8/26 | Thu 10/8/26 | 1.2.5.2.49.2,1.2.5.2.51.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.5.2.50.2 | NA | 4450 | 44474458 | 4451 | -43561m | No | Yes | Yes | No | No | 1.2.5.2.50.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.50.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 10/8/26 | Thu 10/8/26 | Ric Haraida | 2060 | 2062 | Kim | NA | OTC_CM21_CMIR | Thu 10/8/26 | Thu 10/8/26 | 1.2.5.2.50.1 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.5.2.50.3 | NA | 4451 | 4450 | 4452 | -43561m | No | Yes | Yes | No | No | 1.2.5.2.50.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.50.3 | Auto Scheduled | 0% | Simulate Load | No | 0h | Thu 10/8/26 | Thu 10/8/26 | Data Migration Team | 2061 | 2063 |  | NA | OTC_CM21_CMIR | Thu 10/8/26 | Thu 10/8/26 | 1.2.5.2.50.2 | Mon 4/20/26 | Mon 4/20/26 | As Soon As Possible | 1.2.5.2.50.4 | NA | 4452 | 4451 | 4453 | -726.02h | No | Yes | Yes | Yes | No | 1.2.5.2.50.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.50.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 0h | Thu 10/8/26 | Thu 10/8/26 | Ric Haraida | 2062 | 2064 | Kim | NA | OTC_CM21_CMIR | Thu 10/8/26 | Thu 10/8/26 | 1.2.5.2.50.3 | Mon 4/20/26 | Tue 4/21/26 | As Soon As Possible | 1.2.5.2.50.5 | NA | 4453 | 4452 | 4454 | -726.02h | No | Yes | Yes | Yes | No | 1.2.5.2.50.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.50.5 | Auto Scheduled | 0% | Load | No | 0h | Thu 10/8/26 | Thu 10/8/26 | Data Migration Team | 2063 | 2065 |  | NA | OTC_CM21_CMIR | Thu 10/8/26 | Thu 10/8/26 | 1.2.5.2.50.4 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible | 1.2.5.2.50.6 | NA | 4454 | 4453 | 4455 | -726.02h | No | Yes | Yes | Yes | No | 1.2.5.2.50.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.50.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 10/8/26 | Thu 10/8/26 | Ric Haraida | 2064 |  | Kim | NA | OTC_CM21_CMIR | Thu 10/8/26 | Thu 10/8/26 | 1.2.5.2.50.5 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 4455 | 4454 |  | -726.02h | No | Yes | Yes | No | No | 1.2.5.2.50.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.51 | Auto Scheduled | 0% | PTP_CM29_Source_List | No | 6.16d | Fri 9/25/26 | Mon 10/5/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Mon 10/5/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 4456 |  |  | -87.47d | Yes | Yes | Yes | No | No | 1.2.5.2.51 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.51.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Fri 9/25/26 | Fri 9/25/26 | Nevin Varkey | 19101917 |  | Sam | NA | PTP_CM29_Source_List | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.22.5,1.2.5.2.23.5 | Tue 4/14/26 | Tue 4/14/26 | Start No Earlier Than |  | Fri 4/17/26 | 4457 | 43004307 |  | -39061m | No | Yes | Yes | No | No | 1.2.5.2.51.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.51.2 | Auto Scheduled | 0% | Load | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Nevin Varkey | 1886 | 20602069 |  | NA | PTP_CM29_Source_List | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.18.6 | Mon 4/13/26 | Mon 4/13/26 | Finish No Earlier Than | 1.2.5.2.50.1,1.2.5.2.51.3 | Fri 4/17/26 | 4458 | 4276 | 44504459 | -700.77h | No | Yes | Yes | No | No | 1.2.5.2.51.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.51.3 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 10/2/26 | Mon 10/5/26 | Nevin Varkey | 2068 |  | Sam | NA | PTP_CM29_Source_List | Fri 10/2/26 | Mon 10/5/26 | 1.2.5.2.51.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4459 | 4458 |  | -699.77h | No | Yes | Yes | No | No | 1.2.5.2.51.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.52 | Auto Scheduled | 0% | RTR_CM11_Asset_Master | No | 6.63d | Thu 9/24/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 10/2/26 |  | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4460 |  |  | -86.81d | Yes | Yes | Yes | No | No | 1.2.5.2.52 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.52.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes |  | 20722126 |  | NA | RTR_CM11_Asset_Master | Thu 9/24/26 | Thu 9/24/26 |  | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.5.2.52.2,1.2.5.2.67.1 | Wed 4/15/26 | 4461 |  | 44624516 | -41671m | No | Yes | Yes | No | No | 1.2.5.2.52.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.52.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes,Femi Oguntala | 2071 | 2073 | Brian Wagner | NA | RTR_CM11_Asset_Master | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.52.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.52.3 | NA | 4462 | 4461 | 4463 | -41671m | No | Yes | Yes | No | No | 1.2.5.2.52.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.52.3 | Auto Scheduled | 0% | Simulate Load | No | 31h | Thu 9/24/26 | Wed 9/30/26 | Data Migration Team | 2072 | 2074 |  | NA | RTR_CM11_Asset_Master | Thu 9/24/26 | Wed 9/30/26 | 1.2.5.2.52.2 | Fri 4/10/26 | Fri 4/10/26 | Finish No Earlier Than | 1.2.5.2.52.4 | Mon 4/20/26 | 4463 | 4462 | 4464 | -694.52h | No | Yes | Yes | No | No | 1.2.5.2.52.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.52.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 16h | Wed 9/30/26 | Fri 10/2/26 | Kasey Hughes | 2073 | 2075 | Brian Wagner | NA | RTR_CM11_Asset_Master | Wed 9/30/26 | Fri 10/2/26 | 1.2.5.2.52.3 | Fri 4/10/26 | Fri 4/10/26 | Finish No Earlier Than | 1.2.5.2.52.5 | Fri 4/17/26 | 4464 | 4463 | 4465 | -694.52h | No | Yes | Yes | No | No | 1.2.5.2.52.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.52.5 | Auto Scheduled | 0% | Load | No | 2h | Fri 10/2/26 | Fri 10/2/26 | Data Migration Team | 2074 | 2076 |  | NA | RTR_CM11_Asset_Master | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.52.4 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.5.2.52.6 | Fri 4/17/26 | 4465 | 4464 | 4466 | -694.52h | No | Yes | Yes | No | No | 1.2.5.2.52.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.52.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Fri 10/2/26 | Fri 10/2/26 | Kasey Hughes | 2075 |  | Brian Wagner | NA | RTR_CM11_Asset_Master | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.52.5 | Fri 4/10/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4466 | 4465 |  | -694.52h | No | Yes | Yes | No | No | 1.2.5.2.52.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.53 | Auto Scheduled | 0% | PTM_CM50_Material Class | No | 2.13d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4467 |  |  | -86.1d | Yes | Yes | Yes | No | No | 1.2.5.2.53 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.53.1 | Auto Scheduled | 0% | Manual File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Sam | 1983 | 20792082 |  | NA | PTM_CM50_Material Class | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.33.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.53.2,1.2.5.2.54.1 | NA | 4468 | 4373 | 44694472 | -41326m | No | Yes | Yes | No | No | 1.2.5.2.53.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.53.2 | Auto Scheduled | 0% | Load | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Brad Meseck | 2078 | 2080 | Matt Palastro, Dave Duda | NA | PTM_CM50_Material Class | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.53.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.53.3 | NA | 4469 | 4468 | 4470 | -41326m | No | Yes | Yes | No | No | 1.2.5.2.53.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.53.3 | Auto Scheduled | 0% | Post Load Validation | No | 16h | Tue 9/29/26 | Thu 10/1/26 | Brad | 2079 |  | brad | NA | PTM_CM50_Material Class | Tue 9/29/26 | Thu 10/1/26 | 1.2.5.2.53.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than |  | Mon 4/20/26 | 4470 | 4469 |  | -688.77h | No | Yes | Yes | No | No | 1.2.5.2.53.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.54 | Auto Scheduled | 0% | PTM_CM55_Class assignment to materials | No | 1.13d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4471 |  |  | -85.16d | Yes | Yes | Yes | No | No | 1.2.5.2.54 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.54.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Tue 9/29/26 | Tue 9/29/26 | Sam | 2078 | 2083 |  | NA | PTM_CM55_Class assignment to materials | Tue 9/29/26 | Tue 9/29/26 | 1.2.5.2.53.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.54.2 | NA | 4472 | 4468 | 4473 | -40876m | No | Yes | Yes | No | No | 1.2.5.2.54.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.54.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Tue 9/29/26 | Wed 9/30/26 | Brad Meseck | 2082 | 2084 | Matt Palastro, Dave Duda | NA | PTM_CM55_Class assignment to materials | Tue 9/29/26 | Wed 9/30/26 | 1.2.5.2.54.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.54.3 | NA | 4473 | 4472 | 4474 | -40876m | No | Yes | Yes | No | No | 1.2.5.2.54.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.54.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 2083 | 2085 |  | NA | PTM_CM55_Class assignment to materials | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.54.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.54.4 | NA | 4474 | 4473 | 4475 | -681.27h | No | Yes | Yes | No | No | 1.2.5.2.54.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.54.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Brad Meseck | 2084 | 2086 | Matt Palastro, Dave Duda | NA | PTM_CM55_Class assignment to materials | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.54.3 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.54.5 | NA | 4475 | 4474 | 4476 | -681.27h | No | Yes | Yes | No | No | 1.2.5.2.54.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.54.5 | Auto Scheduled | 0% | Load | No | 2h | Wed 9/30/26 | Wed 9/30/26 | Data Migration Team | 2085 | 2087 |  | NA | PTM_CM55_Class assignment to materials | Wed 9/30/26 | Wed 9/30/26 | 1.2.5.2.54.4 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.54.6 | NA | 4476 | 4475 | 4477 | -681.27h | No | Yes | Yes | No | No | 1.2.5.2.54.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.54.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Wed 9/30/26 | Thu 10/1/26 | Brad Meseck | 2086 |  | Matt Palastro, Dave Duda | NA | PTM_CM55_Class assignment to materials | Wed 9/30/26 | Thu 10/1/26 | 1.2.5.2.54.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4477 | 4476 |  | -681.27h | No | Yes | Yes | No | No | 1.2.5.2.54.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.55 | Auto Scheduled | 0% | GTS - Material initial load from S4 (Run Interface) | No | 2.09d | Tue 9/29/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Tue 9/29/26 | Thu 10/1/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4478 |  |  | -89.03d | Yes | Yes | Yes | No | No | 1.2.5.2.55 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.55.1 | Auto Scheduled | 0% | Run material interface to GTS | No | 15.75h | Tue 9/29/26 | Thu 10/1/26 | James Van Riper | 1957 | 2090 |  | NA | GTS - Material initial load from S4 (Run Interface) | Tue 9/29/26 | Thu 10/1/26 | 1.2.5.2.29.3 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.5.2.55.2 | Fri 4/17/26 | 4479 | 4347 | 4480 | -712.27h | No | Yes | Yes | No | No | 1.2.5.2.55.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.55.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Thu 10/1/26 | Thu 10/1/26 | James Van Riper | 2089 | 2101 | Kim Kolesar | NA | GTS - Material initial load from S4 (Run Interface) | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.55.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.59.1 | NA | 4480 | 4479 | 4491 | -712.27h | No | Yes | Yes | No | No | 1.2.5.2.55.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.56 | Auto Scheduled | 0% | GTS - Customers initial load from S4 (Run Interface) | No | 0.25d | Thu 9/24/26 | Thu 9/24/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Thu 9/24/26 |  | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible |  | NA | 4481 |  |  | -80.44d | Yes | Yes | Yes | No | No | 1.2.5.2.56 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.56.1 | Auto Scheduled | 0% | Run material interface to GTS | No | 1h | Thu 9/24/26 | Thu 9/24/26 | James Van Riper |  | 2093 |  | NA | GTS - Customers initial load from S4 (Run Interface) | Thu 9/24/26 | Thu 9/24/26 |  | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.5.2.56.2 | Wed 4/15/26 | 4482 |  | 4483 | -643.52h | No | Yes | Yes | No | No | 1.2.5.2.56.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.56.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Thu 9/24/26 | Thu 9/24/26 | James Van Riper | 2092 |  | Kim Kolesar | NA | GTS - Customers initial load from S4 (Run Interface) | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.56.1 | Fri 4/10/26 | Fri 4/10/26 | Finish No Earlier Than |  | Mon 4/20/26 | 4483 | 4482 |  | -643.52h | No | Yes | Yes | No | No | 1.2.5.2.56.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.57 | Auto Scheduled | 0% | GTS - Vendors initial load from S4 (Run Interface) | No | 0.25d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 4484 |  |  | -81.69d | Yes | Yes | Yes | No | No | 1.2.5.2.57 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.57.1 | Auto Scheduled | 0% | Run material interface to GTS | No | 1h | Thu 9/24/26 | Fri 9/25/26 | James Van Riper | 1900 | 20962099 |  | NA | GTS - Vendors initial load from S4 (Run Interface) | Thu 9/24/26 | Fri 9/25/26 | 1.2.5.2.20.6 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible | 1.2.5.2.57.2,1.2.5.2.58.2 | NA | 4485 | 4290 | 44864489 | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.57.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.57.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 9/25/26 | Fri 9/25/26 | James Van Riper | 2095 |  | Kim Kolesar | NA | GTS - Vendors initial load from S4 (Run Interface) | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.57.1 | Wed 4/15/26 | Wed 4/15/26 | As Soon As Possible |  | NA | 4486 | 4485 |  | -650.52h | No | Yes | Yes | No | No | 1.2.5.2.57.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.58 | Auto Scheduled | 0% | GTS - ECCN - Create | No | 1.13d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Mon 4/6/26 | Mon 4/13/26 | As Soon As Possible |  | NA | 4487 |  |  | -81.31d | Yes | Yes | Yes | No | No | 1.2.5.2.58 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.58.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Thu 9/24/26 | Thu 9/24/26 | James Van Riper | 1771 |  |  | NA | GTS - ECCN - Create | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 4488 | 4161 |  | -642.52h | No | Yes | Yes | No | No | 1.2.5.2.58.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.58.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 9/25/26 | Fri 9/25/26 | James Van Riper | 2095 | 2119 | Kim Kolesar | NA | GTS - ECCN - Create | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.57.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.65.1 | NA | 4489 | 4485 | 4509 | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.58.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.59 | Auto Scheduled | 0% | GTS - ECCN - Assign | No | 0.25d | Thu 10/1/26 | Thu 10/1/26 |  |  |  |  | NA | Master Data Loads | Thu 10/1/26 | Thu 10/1/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4490 |  |  | -89.03d | Yes | Yes | Yes | No | No | 1.2.5.2.59 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.59.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Thu 10/1/26 | Thu 10/1/26 | James Van Riper | 2090 | 2102 |  | NA | GTS - ECCN - Assign | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.55.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.5.2.59.2 | Fri 4/17/26 | 4491 | 4480 | 4492 | -712.27h | No | Yes | Yes | No | No | 1.2.5.2.59.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.59.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Thu 10/1/26 | Thu 10/1/26 | James Van Riper | 2101 | 2107 | Kim Kolesar | NA | GTS - ECCN - Assign | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2.59.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.61.1 | NA | 4492 | 4491 | 4497 | -712.27h | No | Yes | Yes | No | No | 1.2.5.2.59.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.60 | Auto Scheduled | 0% | GTS - HTS - Create | No | 0.25d | Thu 9/24/26 | Thu 9/24/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Thu 9/24/26 |  | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 4493 |  |  | -80.44d | Yes | Yes | Yes | No | No | 1.2.5.2.60 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.60.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Thu 9/24/26 | Thu 9/24/26 | James Van Riper | 1771 | 2105 |  | NA | GTS - HTS - Create | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible | 1.2.5.2.60.2 | NA | 4494 | 4161 | 4495 | -643.52h | No | Yes | Yes | No | No | 1.2.5.2.60.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.60.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Thu 9/24/26 | Thu 9/24/26 | James Van Riper | 2104 |  | Kim Kolesar | NA | GTS - HTS - Create | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.60.1 | Mon 4/6/26 | Mon 4/6/26 | As Soon As Possible |  | NA | 4495 | 4494 |  | -643.52h | No | Yes | Yes | No | No | 1.2.5.2.60.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.61 | Auto Scheduled | 0% | GTS - HTS - Assign | No | 0.25d | Thu 10/1/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Thu 10/1/26 | Fri 10/2/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4496 |  |  | -89.03d | Yes | Yes | Yes | No | No | 1.2.5.2.61 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.61.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Thu 10/1/26 | Fri 10/2/26 | James Van Riper | 2102 | 210821102116 |  | NA | GTS - HTS - Assign | Thu 10/1/26 | Fri 10/2/26 | 1.2.5.2.59.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.61.2,1.2.5.2.62.1,1.2.5.2.64.1 | NA | 4497 | 4492 | 449845004506 | -712.27h | No | Yes | Yes | No | No | 1.2.5.2.61.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.61.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 2107 | 21232113 | Kim Kolesar | NA | GTS - HTS - Assign | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.61.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.66.1,1.2.5.2.63.1 | NA | 4498 | 4497 | 45134503 | -712.27h | No | Yes | Yes | No | No | 1.2.5.2.61.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.62 | Auto Scheduled | 0% | GTS - License - Create | No | 0.25d | Fri 10/2/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Fri 10/2/26 | Fri 10/2/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4499 |  |  | -86.63d | Yes | Yes | Yes | No | No | 1.2.5.2.62 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.62.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 21072123 | 2111 |  | NA | GTS - License - Create | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.61.1,1.2.5.2.66.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.62.2 | NA | 4500 | 44974513 | 4501 | -693.02h | No | Yes | Yes | No | No | 1.2.5.2.62.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.62.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 2110 |  | Kim Kolesar | NA | GTS - License - Create | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.62.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4501 | 4500 |  | -693.02h | No | Yes | Yes | No | No | 1.2.5.2.62.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.63 | Auto Scheduled | 0% | Commodity Code/Tarif | No | 2.78d | Fri 10/2/26 | Tue 10/6/26 |  |  |  |  | NA | Master Data Loads | Fri 10/2/26 | Tue 10/6/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4502 |  |  | -89.03d | Yes | Yes | Yes | No | No | 1.2.5.2.63 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.63.1 | Auto Scheduled | 0% | Load | No | 21.25h | Fri 10/2/26 | Tue 10/6/26 | James Van Riper | 2108 | 2114 |  | NA | Commodity Code/Tarif | Fri 10/2/26 | Tue 10/6/26 | 1.2.5.2.61.2 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.2.5.2.63.2 | Mon 4/20/26 | 4503 | 4498 | 4504 | -712.27h | No | Yes | Yes | No | No | 1.2.5.2.63.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.63.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Tue 10/6/26 | Tue 10/6/26 | James Van Riper | 2113 |  | Kim Kolesar | NA | Commodity Code/Tarif | Tue 10/6/26 | Tue 10/6/26 | 1.2.5.2.63.1 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than |  | Fri 4/17/26 | 4504 | 4503 |  | -712.27h | No | Yes | Yes | No | No | 1.2.5.2.63.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.64 | Auto Scheduled | 0% | SPL Master File | No | 0.25d | Fri 10/2/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Fri 10/2/26 | Fri 10/2/26 |  | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 4505 |  |  | -86.38d | Yes | Yes | Yes | No | No | 1.2.5.2.64 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.64.1 | Auto Scheduled | 0% | Load | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 2107 | 2117 |  | NA | SPL Master File | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.61.1 | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible | 1.2.5.2.64.2 | NA | 4506 | 4497 | 4507 | -691.02h | No | Yes | Yes | No | No | 1.2.5.2.64.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.64.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 2116 |  | Kim Kolesar | NA | SPL Master File | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.64.1 | Thu 3/13/25 | Thu 3/13/25 | As Soon As Possible |  | NA | 4507 | 4506 |  | -691.02h | No | Yes | Yes | No | No | 1.2.5.2.64.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.65 | Auto Scheduled | 0% | Initialize Embargo situation | No | 0.38d | Fri 9/25/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Fri 9/25/26 | Fri 9/25/26 |  | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 4508 |  |  | -81.69d | Yes | Yes | Yes | No | No | 1.2.5.2.65 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.65.1 | Auto Scheduled | 0% | Run report /SAPSLL/EMB_CNTRY_INIT | No | 1h | Fri 9/25/26 | Fri 9/25/26 | James Van Riper | 2099 | 2120 |  | NA | Initialize Embargo situation | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.58.2 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.65.2 | NA | 4509 | 4489 | 4510 | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.65.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.65.2 | Auto Scheduled | 0% | Set Embargo situations | No | 1h | Fri 9/25/26 | Fri 9/25/26 | James Van Riper | 2119 | 2121 |  | NA | Initialize Embargo situation | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.65.1 | Mon 4/13/26 | Mon 4/13/26 | As Soon As Possible | 1.2.5.2.65.3 | NA | 4510 | 4509 | 4511 | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.65.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.65.3 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 9/25/26 | Fri 9/25/26 | James Van Riper | 2120 |  | Kim Kolesar | NA | Initialize Embargo situation | Fri 9/25/26 | Fri 9/25/26 | 1.2.5.2.65.2 | Mon 4/13/26 | Tue 4/14/26 | As Soon As Possible |  | NA | 4511 | 4510 |  | -653.52h | No | Yes | Yes | No | No | 1.2.5.2.65.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.66 | Auto Scheduled | 0% | GTS - SPL (Sanctioned party list) | No | 0.25d | Fri 10/2/26 | Fri 10/2/26 |  |  |  |  | NA | Master Data Loads | Fri 10/2/26 | Fri 10/2/26 |  | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4512 |  |  | -86.63d | Yes | Yes | Yes | No | No | 1.2.5.2.66 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.66.1 | Auto Scheduled | 0% | Load Descartes XML File | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 2108 | 21102124 |  | NA | GTS - SPL (Sanctioned party list) | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.61.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.62.1,1.2.5.2.66.2 | NA | 4513 | 4498 | 45004514 | -693.02h | No | Yes | Yes | No | No | 1.2.5.2.66.1 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.66.2 | Auto Scheduled | 0% | Post Load Validation | No | 1h | Fri 10/2/26 | Fri 10/2/26 | James Van Riper | 2123 |  | Kim Kolesar | NA | GTS - SPL (Sanctioned party list) | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.2.66.1 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible |  | NA | 4514 | 4513 |  | -692.02h | No | Yes | Yes | No | No | 1.2.5.2.66.2 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.67 | Auto Scheduled | 0% | RTR_CM17_Project Definition / Builder | No | 1.13d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Fri 4/10/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4515 |  |  | -81.44d | Yes | Yes | Yes | No | No | 1.2.5.2.67 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.67.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 2071 | 21272133 |  | NA | RTR_CM17_Project Definition / Builder | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.52.1 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.5.2.67.2,1.2.5.2.68.1 | Mon 4/20/26 | 4516 | 4461 | 45174523 | -39091m | No | Yes | Yes | No | No | 1.2.5.2.67.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.67.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 2126 | 2128 | Brian Wagner | NA | RTR_CM17_Project Definition / Builder | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.67.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.67.3 | NA | 4517 | 4516 | 4518 | -39061m | No | Yes | Yes | No | No | 1.2.5.2.67.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.67.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 2127 | 2129 |  | NA | RTR_CM17_Project Definition / Builder | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.67.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.67.4 | NA | 4518 | 4517 | 4519 | -651.02h | No | Yes | Yes | No | No | 1.2.5.2.67.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.67.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 2128 | 2130 | Brian Wagner | NA | RTR_CM17_Project Definition / Builder | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.67.3 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.67.5 | NA | 4519 | 4518 | 4520 | -651.02h | No | Yes | Yes | No | No | 1.2.5.2.67.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.67.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 2129 | 2131 |  | NA | RTR_CM17_Project Definition / Builder | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.67.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.67.6 | NA | 4520 | 4519 | 4521 | -651.02h | No | Yes | Yes | No | No | 1.2.5.2.67.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.67.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Fri 9/25/26 | Kasey Hughes | 2130 |  | Brian Wagner | NA | RTR_CM17_Project Definition / Builder | Thu 9/24/26 | Fri 9/25/26 | 1.2.5.2.67.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4521 | 4520 |  | -651.02h | No | Yes | Yes | No | No | 1.2.5.2.67.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.68 | Auto Scheduled | 0% | RTR_CM18_WBS Element | No | 1.25d | Thu 9/24/26 | Fri 9/25/26 |  |  |  |  | NA | Master Data Loads | Thu 9/24/26 | Fri 9/25/26 |  | Fri 4/10/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4522 |  |  | -81.44d | Yes | Yes | Yes | No | No | 1.2.5.2.68 | 5 | No | 500 | Future Task | No | 0d
1.2.5.2.68.1 | Auto Scheduled | 0% | Load File Staged and Posted "Ready" | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 2126 | 2134 |  | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.67.1 | Fri 4/10/26 | Fri 4/10/26 | Start No Earlier Than | 1.2.5.2.68.2 | Fri 4/17/26 | 4523 | 4516 | 4524 | -39091m | No | Yes | Yes | No | No | 1.2.5.2.68.1 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.68.2 | Auto Scheduled | 0% | Pre Load Validation | No | 30m | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 2133 | 2135 | Brian Wagner | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.68.1 | Fri 4/10/26 | Fri 4/10/26 | As Soon As Possible | 1.2.5.2.68.3 | NA | 4524 | 4523 | 4525 | -39091m | No | Yes | Yes | No | No | 1.2.5.2.68.2 | 6 | No | 500 | Future Task | No | 0m
1.2.5.2.68.3 | Auto Scheduled | 0% | Simulate Load | No | 1h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 2134 | 2136 |  | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.68.2 | Thu 4/16/26 | Thu 4/16/26 | As Soon As Possible | 1.2.5.2.68.4 | NA | 4525 | 4524 | 4526 | -651.52h | No | Yes | Yes | No | No | 1.2.5.2.68.3 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.68.4 | Auto Scheduled | 0% | Error and Defect Mitigation | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Kasey Hughes | 2135 | 2137 | Brian Wagner | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.68.3 | Thu 4/16/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.68.5 | NA | 4526 | 4525 | 4527 | -651.52h | No | Yes | Yes | No | No | 1.2.5.2.68.4 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.68.5 | Auto Scheduled | 0% | Load | No | 2h | Thu 9/24/26 | Thu 9/24/26 | Data Migration Team | 2136 | 2138 |  | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Thu 9/24/26 | 1.2.5.2.68.4 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible | 1.2.5.2.68.6 | NA | 4527 | 4526 | 4528 | -651.52h | No | Yes | Yes | No | No | 1.2.5.2.68.5 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.68.6 | Auto Scheduled | 0% | Post Load Validation | No | 3h | Thu 9/24/26 | Fri 9/25/26 | Kasey Hughes | 2137 |  | Brian Wagner | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Fri 9/25/26 | 1.2.5.2.68.5 | Fri 4/17/26 | Fri 4/17/26 | As Soon As Possible |  | NA | 4528 | 4527 |  | -651.52h | No | Yes | Yes | No | No | 1.2.5.2.68.6 | 6 | No | 500 | Future Task | No | 0h
1.2.5.2.68.7 | Auto Scheduled | 0% | UAT Mock Data Loads Complete | No | 15m | Thu 9/24/26 | Thu 9/24/26 | Mark George |  |  |  | NA | RTR_CM18_WBS Element | Thu 9/24/26 | Thu 9/24/26 |  | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible |  | NA | 4529 |  |  | -38506m | No | Yes | Yes | Yes | No | 1.2.5.2.68.7 | 6 | No | 500 | Future Task | No | 0m
1.2.5.3 | Auto Scheduled | 0% | PROD Master Data Loads Complete | No | 0m | Thu 10/1/26 | Thu 10/1/26 |  | 1772 | 1000SS,999,2142SS,2141,2196 |  | NA | PROD Data Load Tasks P? | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.2 | NA | NA | As Soon As Possible | 1.2.2.4.1[SS],1.2.2.4,1.2.5.4.1[SS],1.2.5.4,1.3.3.8.1 | NA | 4530 | 4162 | 2945SS,2801,4532SS,4531,924 | -40891m | No | Yes | Yes | Yes | No | 1.2.5.3 | 4 | No | 500 | Future Task | No | 0m
1.2.5.4 | Auto Scheduled | 0% | Mock Transactional Data | No | 2d | Thu 10/1/26 | Mon 10/5/26 |  | 2140 | 2150 |  | NA | PROD Data Load Tasks P? | Thu 10/1/26 | Mon 10/5/26 | 1.2.5.3 | NA | NA | As Soon As Possible | 1.2.5.5 | NA | 4531 | 4530 | 4540 | -35.1d | Yes | Yes | Yes | No | No | 1.2.5.4 | 4 | No | 500 | Future Task | No | 0d
1.2.5.4.1 | Auto Scheduled | 0% | Inventory | No | 4h | Thu 10/1/26 | Thu 10/1/26 |  | 2140SS,998SS | 2.1432e+19 |  | NA | Mock Transactional Data | Thu 10/1/26 | Thu 10/1/26 | 1.2.5.3[SS],1.2.2.3[SS] | NA | NA | As Soon As Possible | 1.2.5.4.2,1.2.5.4.5,1.2.5.4.6,1.2.5.4.7,1.2.5.4.8 | NA | 4532 | 4530SS,2947SS | 4.5335e+19 | -280.77h | No | Yes | Yes | No | No | 1.2.5.4.1 | 5 | No | 500 | Future Task | No | 0h
1.2.5.4.2 | Auto Scheduled | 0% | Open AR | No | 4h | Thu 10/1/26 | Fri 10/2/26 |  | 2142 | 2144 |  | NA | Mock Transactional Data | Thu 10/1/26 | Fri 10/2/26 | 1.2.5.4.1 | NA | NA | As Soon As Possible | 1.2.5.4.3 | NA | 4533 | 4532 | 4534 | -280.77h | No | Yes | Yes | No | No | 1.2.5.4.2 | 5 | No | 500 | Future Task | No | 0h
1.2.5.4.3 | Auto Scheduled | 0% | Open AP | No | 4h | Fri 10/2/26 | Fri 10/2/26 |  | 2143 | 2145 |  | NA | Mock Transactional Data | Fri 10/2/26 | Fri 10/2/26 | 1.2.5.4.2 | NA | NA | As Soon As Possible | 1.2.5.4.4 | NA | 4534 | 4533 | 4535 | -280.77h | No | Yes | Yes | No | No | 1.2.5.4.3 | 5 | No | 500 | Future Task | No | 0h
1.2.5.4.4 | Auto Scheduled | 0% | Bank and Cash | No | 4h | Fri 10/2/26 | Mon 10/5/26 |  | 2144 |  |  | NA | Mock Transactional Data | Fri 10/2/26 | Mon 10/5/26 | 1.2.5.4.3 | NA | NA | As Soon As Possible |  | NA | 4535 | 4534 |  | -280.77h | No | Yes | Yes | No | No | 1.2.5.4.4 | 5 | No | 500 | Future Task | No | 0h
1.2.5.4.5 | Auto Scheduled | 0% | Open Purchase Orders(Manual) | No | 1d | Thu 10/1/26 | Fri 10/2/26 |  | 2142 |  |  | NA | Mock Transactional Data | Thu 10/1/26 | Fri 10/2/26 | 1.2.5.4.1 | NA | NA | As Soon As Possible |  | NA | 4536 | 4532 |  | -34.6d | No | Yes | Yes | No | No | 1.2.5.4.5 | 5 | No | 500 | Future Task | No | 0d
1.2.5.4.6 | Auto Scheduled | 0% | Open Sales Orders(Manual) | No | 1d | Thu 10/1/26 | Fri 10/2/26 |  | 2142 |  |  | NA | Mock Transactional Data | Thu 10/1/26 | Fri 10/2/26 | 1.2.5.4.1 | NA | NA | As Soon As Possible |  | NA | 4537 | 4532 |  | -34.6d | No | Yes | Yes | No | No | 1.2.5.4.6 | 5 | No | 500 | Future Task | No | 0d
1.2.5.4.7 | Auto Scheduled | 0% | Service Orders(Manual) | No | 0.5d | Thu 10/1/26 | Fri 10/2/26 |  | 2142 |  |  | NA | Mock Transactional Data | Thu 10/1/26 | Fri 10/2/26 | 1.2.5.4.1 | NA | NA | As Soon As Possible |  | NA | 4538 | 4532 |  | -34.1d | No | Yes | Yes | No | No | 1.2.5.4.7 | 5 | No | 500 | Future Task | No | 0d
1.2.5.4.8 | Auto Scheduled | 0% | Open Production Orders(Manual) | No | 1d | Thu 10/1/26 | Fri 10/2/26 |  | 2142 |  |  | NA | Mock Transactional Data | Thu 10/1/26 | Fri 10/2/26 | 1.2.5.4.1 | NA | NA | As Soon As Possible |  | NA | 4539 | 4532 |  | -34.6d | No | Yes | Yes | No | No | 1.2.5.4.8 | 5 | No | 500 | Future Task | No | 0d
1.2.5.5 | Auto Scheduled | 0% | PRO Data Loads Complete | No | 15m | Mon 10/5/26 | Mon 10/5/26 | Mark George | 2141 | 2167 |  | NA | PROD Data Load Tasks P? | Mon 10/5/26 | Mon 10/5/26 | 1.2.5.4 | Tue 4/21/26 | Tue 4/21/26 | As Soon As Possible | 1.3.3.4 | NA | 4540 | 4531 | 690 | -16846m | No | Yes | Yes | Yes | No | 1.2.5.5 | 4 | No | 500 | Future Task | No | 0m
1.3 | Auto Scheduled | 3% | Solution Readniess | No | 131.38d | Thu 4/16/26 | Fri 10/16/26 |  |  |  |  | Thu 4/16/26 | AMETEK Release-1, 3-Deployment Plan | Thu 4/16/26 | Fri 10/16/26 |  | Thu 4/16/26 | Thu 9/3/26 | As Soon As Possible |  | NA | 681 |  |  | 16.63d | Yes | Yes | No | No | No | 1.3 | 2 | No | 500 | Future Task | No | 16.63d
1.3.1 | Auto Scheduled | 4% | Business Process Design Documentation | No | 20d | Mon 5/4/26 | Fri 5/29/26 |  |  |  |  | Mon 5/4/26 | Solution Readniess | Mon 5/4/26 | Fri 5/29/26 |  | Fri 5/22/26 | Fri 5/22/26 | As Soon As Possible |  | NA | 843 |  |  | 116d | Yes | Yes | No | No | No | 1.3.1 | 3 | No | 500 | Future Task | No | 116d
1.3.1.1 | Auto Scheduled | 3% | FICO | No | 20d | Mon 5/4/26 | Fri 5/29/26 |  |  |  |  | Mon 5/4/26 | Business Process Design Documentation | Mon 5/4/26 | Fri 5/29/26 |  | Fri 5/22/26 | Fri 5/22/26 | As Soon As Possible |  | NA | 844 |  |  | 116d | No | Yes | No | No | No | 1.3.1.1 | 4 | No | 500 | Future Task | No | 116d
1.3.1.2 | Auto Scheduled | 4% | Order to Cash | No | 20d | Mon 5/4/26 | Fri 5/29/26 |  |  |  |  | Mon 5/4/26 | Business Process Design Documentation | Mon 5/4/26 | Fri 5/29/26 |  | Fri 5/22/26 | Fri 5/22/26 | As Soon As Possible |  | NA | 845 |  |  | 116d | No | Yes | No | No | No | 1.3.1.2 | 4 | No | 500 | Future Task | No | 116d
1.3.1.3 | Auto Scheduled | 4% | Procure to Pay | No | 20d | Mon 5/4/26 | Fri 5/29/26 |  |  |  |  | Mon 5/4/26 | Business Process Design Documentation | Mon 5/4/26 | Fri 5/29/26 |  | Fri 5/22/26 | Fri 5/22/26 | As Soon As Possible |  | NA | 846 |  |  | 116d | No | Yes | No | No | No | 1.3.1.3 | 4 | No | 500 | Future Task | No | 116d
1.3.1.4 | Auto Scheduled | 5% | Plan to Make | No | 20d | Mon 5/4/26 | Fri 5/29/26 |  |  |  |  | Mon 5/4/26 | Business Process Design Documentation | Mon 5/4/26 | Fri 5/29/26 |  | Fri 5/22/26 | Fri 5/22/26 | As Soon As Possible |  | NA | 847 |  |  | 116d | No | Yes | No | No | No | 1.3.1.4 | 4 | No | 500 | Future Task | No | 116d
1.3.2 | Auto Scheduled | 0% | Development RICEFW | No | 75d | Mon 5/4/26 | Fri 8/14/26 |  |  |  |  | Mon 5/4/26 | Solution Readniess | Mon 5/4/26 | Fri 8/14/26 |  | Fri 5/22/26 | Fri 5/22/26 | As Soon As Possible |  | NA | 835 |  |  | 61d | Yes | Yes | No | No | No | 1.3.2 | 3 | No | 500 | Future Task | No | 61d
1.3.2.1 | Auto Scheduled | 0% | Reports | No | 75d | Mon 5/4/26 | Fri 8/14/26 |  |  |  |  | NA | Development RICEFW | Mon 5/4/26 | Fri 8/14/26 |  | Fri 5/22/26 | Fri 5/22/26 | Finish No Earlier Than |  | Fri 8/14/26 | 836 |  |  | 61d | No | Yes | No | No | No | 1.3.2.1 | 4 | No | 500 | Future Task | No | 61d
1.3.2.2 | Auto Scheduled | 0% | Interfaces | No | 75d | Mon 5/4/26 | Fri 8/14/26 |  |  |  |  | NA | Development RICEFW | Mon 5/4/26 | Fri 8/14/26 |  | Fri 5/22/26 | Fri 5/22/26 | Start No Earlier Than |  | Mon 5/4/26 | 837 |  |  | 61d | No | Yes | No | No | No | 1.3.2.2 | 4 | No | 500 | Future Task | No | 61d
1.3.2.3 | Auto Scheduled | 0% | Enhanchments | No | 61d | Mon 5/4/26 | Fri 8/14/26 |  |  |  |  | Mon 5/4/26 | Development RICEFW | Mon 5/4/26 | Fri 8/14/26 |  | Fri 5/22/26 | Fri 5/22/26 | Finish No Earlier Than |  | Fri 8/14/26 | 838 |  |  | 61d | No | Yes | No | No | No | 1.3.2.3 | 4 | No | 500 | Future Task | No | 61d
1.3.2.4 | Auto Scheduled | 0% | Workflow | No | 75d | Mon 5/4/26 | Fri 8/14/26 |  |  |  |  | NA | Development RICEFW | Mon 5/4/26 | Fri 8/14/26 |  | Fri 5/22/26 | Fri 5/22/26 | Start No Earlier Than |  | Mon 5/4/26 | 839 |  |  | 61d | No | Yes | No | No | No | 1.3.2.4 | 4 | No | 500 | Future Task | No | 61d
1.3.2.5 | Auto Scheduled | 0% | Forms | No | 0d | Fri 8/14/26 | Fri 8/14/26 |  |  |  |  | NA | Development RICEFW | Fri 8/14/26 | Fri 8/14/26 |  | Fri 5/22/26 | Fri 5/22/26 | Finish No Earlier Than |  | Fri 8/14/26 | 840 |  |  | 61d | No | Yes | No | Yes | No | 1.3.2.5 | 4 | No | 500 | Future Task | No | 61d
1.3.3 | Auto Scheduled | 13% | Testing Cycles | No | 131.38d | Thu 4/16/26 | Fri 10/16/26 |  |  |  |  | Thu 4/16/26 | Solution Readniess | Thu 4/16/26 | Fri 10/16/26 |  | Thu 4/16/26 | Thu 9/3/26 | As Soon As Possible |  | NA | 18 |  |  | 16.63d | Yes | Yes | No | No | No | 1.3.3 | 3 | No | 500 | Future Task | No | 16.63d
1.3.3.1 | Auto Scheduled | 25% | Test Readiness Review (TRR) - ITC 1 | No | 1h | Thu 4/16/26 | Fri 5/1/26 |  | 628 | 216921712168 |  | Thu 4/16/26 | Testing Cycles | Thu 4/16/26 | Fri 5/1/26 | 1.2.1.70 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than | 1.3.3.5.1,1.3.3.5.3,1.3.3.5 | Thu 4/16/26 | 932 | 1170 | 834,684,19 | -87.75h | No | Yes | Yes | No | No | 1.3.3.1 | 4 | No | 500 | Future Task | No | 0h
1.3.3.2 | Auto Scheduled | 0% | Test Readiness Review (TRR) - ITC 2 | No | 1h | Mon 10/12/26 | Mon 10/12/26 |  | 10082180 | 2181 |  | NA | Testing Cycles | Mon 10/12/26 | Mon 10/12/26 | 1.2.2.5,1.3.3.6.5 | Thu 6/18/26 | Thu 6/18/26 | As Soon As Possible | 1.3.3.6.6 | NA | 2799 | 20522794 | 2793 | -726h | No | Yes | Yes | No | No | 1.3.3.2 | 4 | No | 500 | Future Task | No | 0h
1.3.3.3 | Auto Scheduled | 0% | Test Readiness Review (TRR) - ITC 3 | No | 1h | Tue 6/30/26 | Tue 6/30/26 |  | 21901388 | 2191 |  | NA | Testing Cycles | Tue 6/30/26 | Tue 6/30/26 | 1.3.3.7.5,1.2.3.5 | Thu 6/18/26 | Thu 6/18/26 | As Soon As Possible | 1.3.3.7.6 | NA | 931 | 9172421 | 916 | 68h | No | Yes | No | No | No | 1.3.3.3 | 4 | No | 500 | Future Task | No | 68h
1.3.3.4 | Auto Scheduled | 0% | Test Readiness Review (TRR) - UAT | No | 0h | Fri 10/16/26 | Fri 10/16/26 |  | 176921992150 | 2200 |  | NA | Testing Cycles | Fri 10/16/26 | Fri 10/16/26 | 1.2.4.5,1.3.3.8.4,1.2.5.5 | Thu 8/6/26 | Thu 8/6/26 | As Soon As Possible | 1.3.3.8.5 | NA | 690 | 29389264540 | 925 | -355h | No | Yes | Yes | Yes | No | 1.3.3.4 | 4 | No | 500 | Future Task | No | 0h
1.3.3.5 | Auto Scheduled | 37% | ITC-1 | No | 23.88d | Thu 4/16/26 | Tue 5/19/26 |  | 2164 |  |  | Thu 4/16/26 | Testing Cycles | Thu 4/16/26 | Tue 5/19/26 | 1.3.3.1 | Thu 4/16/26 | Thu 7/23/26 | As Soon As Possible |  | NA | 19 | 932 |  | 124d | Yes | Yes | No | No | No | 1.3.3.5 | 4 | No | 500 | Complete | No | 124d
1.3.3.5.1 | Auto Scheduled | 100% | Testing expectations | No | 1h | Thu 4/16/26 | Thu 4/16/26 | PMO | 2164 | 2170 |  | Thu 4/16/26 | ITC-1 | Thu 4/16/26 | Thu 4/16/26 | 1.3.3.1 | Thu 4/16/26 | Thu 4/16/26 | Start No Earlier Than | 1.3.3.5.2 | Wed 4/8/26 | 834 | 932 | 685 | 0h | No | Yes | No | No | No | 1.3.3.5.1 | 5 | No | 500 | Complete | No | 0h
1.3.3.5.2 | Auto Scheduled | 100% | Functional Smoke Testing | No | 5d | Mon 4/20/26 | Wed 4/29/26 |  | 2169 |  |  | Mon 4/20/26 | ITC-1 | Mon 4/20/26 | Wed 4/29/26 | 1.3.3.5.1 | Mon 4/20/26 | Fri 4/24/26 | Start No Earlier Than |  | Mon 4/20/26 | 685 | 834 |  | 0d | No | Yes | No | No | No | 1.3.3.5.2 | 5 | No | 500 | Complete | No | 0d
1.3.3.5.3 | Auto Scheduled | 100% | Assign Tester ID's | No | 2h | Thu 4/16/26 | Thu 4/23/26 |  | 2164 | 2172 |  | Thu 4/16/26 | ITC-1 | Thu 4/16/26 | Thu 4/23/26 | 1.3.3.1 | Thu 4/16/26 | Thu 4/16/26 | Finish No Earlier Than | 1.3.3.5.4 | Thu 3/13/25 | 684 | 932 | 686 | 0h | No | Yes | No | No | No | 1.3.3.5.3 | 5 | No | 500 | Complete | No | 0h
1.3.3.5.4 | Auto Scheduled | 25% | ITC-1 Team Testing | No | 15d | Mon 4/27/26 | Mon 5/18/26 |  | 2171 | 2173SS+4d |  | Mon 4/27/26 | ITC-1 | Mon 4/27/26 | Mon 5/18/26 | 1.3.3.5.3 | Mon 4/27/26 | Fri 5/15/26 | Start No Earlier Than | 1.3.3.5.5[SS+4d] | Mon 4/27/26 | 686 | 684 | 688SS+4d | 125.66d | No | Yes | No | No | No | 1.3.3.5.4 | 5 | No | 500 | Future Task | No | 3d
1.3.3.5.5 | Auto Scheduled | 25% | ITC-1 Defect Correction / Retesting / Mitigation / Close | No | 10d | Wed 5/6/26 | Tue 5/19/26 |  | 2172SS+4d | 2174FS-3d |  | Wed 5/6/26 | ITC-1 | Wed 5/6/26 | Tue 5/19/26 | 1.3.3.5.4[SS+4d] | Mon 5/18/26 | Fri 5/29/26 | As Soon As Possible | 1.3.3.5.6[FS-3d] | NA | 688 | 686SS+4d | 689FS-3d | 124d | No | Yes | No | No | No | 1.3.3.5.5 | 5 | No | 500 | Future Task | No | 0d
1.3.3.5.6 | Auto Scheduled | 0% | ITC-1 Gate Review | No | 8h | Fri 5/15/26 | Fri 5/15/26 |  | 2173FS-3d |  |  | NA | ITC-1 | Fri 5/15/26 | Fri 5/15/26 | 1.3.3.5.5[FS-3d] | Thu 7/23/26 | Thu 7/23/26 | As Soon As Possible |  | NA | 689 | 688FS-3d |  | 1008h | No | Yes | No | No | No | 1.3.3.5.6 | 5 | No | 500 | Future Task | No | 1008h
1.3.3.6 | Auto Scheduled | 0% | ITC-2 | No | 15.13d | Fri 5/29/26 | Fri 6/19/26 |  |  |  |  | NA | Testing Cycles | Fri 5/29/26 | Fri 6/19/26 |  | Thu 4/30/26 | Fri 7/24/26 | As Soon As Possible |  | NA | 2791 |  |  | -1.5d | Yes | Yes | Yes | No | No | 1.3.3.6 | 4 | No | 500 | Future Task | No | 0d
1.3.3.6.1 | Auto Scheduled | 0% | Assign Resources to Depolyment 1 locations | No | 2h | Fri 5/29/26 | Mon 6/1/26 | Renee | 998 | 2177SS |  | NA | ITC-2 | Fri 5/29/26 | Mon 6/1/26 | 1.2.2.3 | Thu 4/30/26 | Thu 4/30/26 | As Soon As Possible | 1.3.3.6.2[SS] | NA | 2792 | 2947 | 2795SS | -12h | No | Yes | Yes | No | No | 1.3.3.6.1 | 5 | No | 500 | Future Task | No | 0h
1.3.3.6.2 | Auto Scheduled | 0% | Assign Tester ID's | No | 2h | Fri 5/29/26 | Mon 6/1/26 | Security | 2176SS | 2178SS |  | NA | ITC-2 | Fri 5/29/26 | Mon 6/1/26 | 1.3.3.6.1[SS] | Thu 6/18/26 | Thu 6/18/26 | As Soon As Possible | 1.3.3.6.3[SS] | NA | 2795 | 2792SS | 2948SS | -12h | No | Yes | Yes | No | No | 1.3.3.6.2 | 5 | No | 500 | Future Task | No | 0h
1.3.3.6.3 | Auto Scheduled | 0% | Identify Data and Processes for ITC | No | 1d | Fri 5/29/26 | Mon 6/1/26 |  | 2177SS | 2179 |  | NA | ITC-2 | Fri 5/29/26 | Mon 6/1/26 | 1.3.3.6.2[SS] | NA | NA | As Soon As Possible | 1.3.3.6.4 | NA | 2948 | 2795SS | 2949 | -1.5d | No | Yes | Yes | No | No | 1.3.3.6.3 | 5 | No | 500 | Future Task | No | 0d
1.3.3.6.4 | Auto Scheduled | 0% | Run Costing for Data Identified(or ALL) | No | 4h | Mon 6/1/26 | Tue 6/2/26 |  | 2178 | 2180 |  | NA | ITC-2 | Mon 6/1/26 | Tue 6/2/26 | 1.3.3.6.3 | NA | NA | As Soon As Possible | 1.3.3.6.5 | NA | 2949 | 2948 | 2794 | -12h | No | Yes | Yes | No | No | 1.3.3.6.4 | 5 | No | 500 | Future Task | No | 0h
1.3.3.6.5 | Auto Scheduled | 0% | Functional Smoke Testing | No | 5d | Tue 6/2/26 | Tue 6/9/26 | Functional Leads | 2179 | 2165 |  | NA | ITC-2 | Tue 6/2/26 | Tue 6/9/26 | 1.3.3.6.4 | Thu 6/18/26 | Thu 6/25/26 | As Soon As Possible | 1.3.3.2 | NA | 2794 | 2949 | 2799 | -1.5d | No | Yes | Yes | No | No | 1.3.3.6.5 | 5 | No | 500 | Future Task | No | 0d
1.3.3.6.6 | Auto Scheduled | 0% | Test Kickoff | No | 1h | Mon 6/8/26 | Mon 6/8/26 | Renee | 2165 | 2182SS |  | NA | ITC-2 | Mon 6/8/26 | Mon 6/8/26 | 1.3.3.2 | Thu 6/18/26 | Thu 6/18/26 | Must Start On | 1.3.3.6.7[SS] | Mon 6/8/26 | 2793 | 2799 | 2796SS | -726h | No | Yes | Yes | No | No | 1.3.3.6.6 | 5 | No | 500 | Future Task | No | 0h
1.3.3.6.7 | Auto Scheduled | 0% | Team Testing | No | 10d | Mon 6/8/26 | Fri 6/19/26 |  | 2181SS | 2183SS+3d |  | NA | ITC-2 | Mon 6/8/26 | Fri 6/19/26 | 1.3.3.6.6[SS] | Mon 6/22/26 | Fri 7/17/26 | As Soon As Possible | 1.3.3.6.8[SS+3d] | NA | 2796 | 2793SS | 2797SS+3d | 101d | No | Yes | No | No | No | 1.3.3.6.7 | 5 | No | 500 | Future Task | No | 0d
1.3.3.6.8 | Auto Scheduled | 0% | Defect Correction / Retesting / Mitigation / Close | No | 5d | Thu 6/11/26 | Wed 6/17/26 |  | 2182SS+3d | 2184SS+4d |  | NA | ITC-2 | Thu 6/11/26 | Wed 6/17/26 | 1.3.3.6.7[SS+3d] | Mon 7/20/26 | Fri 7/24/26 | As Soon As Possible | 1.3.3.6.9[SS+4d] | NA | 2797 | 2796SS+3d | 2798SS+4d | 103d | No | Yes | No | No | No | 1.3.3.6.8 | 5 | No | 500 | Future Task | No | 0d
1.3.3.6.9 | Auto Scheduled | 0% | Gate Review | No | 1h | Wed 6/17/26 | Wed 6/17/26 |  | 2183SS+4d |  |  | NA | ITC-2 | Wed 6/17/26 | Wed 6/17/26 | 1.3.3.6.8[SS+4d] | Thu 7/23/26 | Thu 7/23/26 | As Soon As Possible |  | NA | 2798 | 2797SS+4d |  | 831h | No | Yes | No | No | No | 1.3.3.6.9 | 5 | No | 500 | Future Task | No | 831h
1.3.3.7 | Auto Scheduled | 0% | ITC-3 | No | 25.13d | Fri 6/19/26 | Fri 7/24/26 |  |  |  |  | NA | Testing Cycles | Fri 6/19/26 | Fri 7/24/26 |  | Thu 4/30/26 | Fri 7/24/26 | As Soon As Possible |  | NA | 915 |  |  | 8.5d | Yes | Yes | No | No | No | 1.3.3.7 | 4 | No | 500 | Future Task | No | 8.5d
1.3.3.7.1 | Auto Scheduled | 0% | Assign Resources to Depolyment 1 locations | No | 2h | Fri 6/19/26 | Mon 6/22/26 | Renee | 1378 | 2187SS |  | NA | ITC-3 | Fri 6/19/26 | Mon 6/22/26 | 1.2.3.3 | Thu 4/30/26 | Thu 4/30/26 | As Soon As Possible | 1.3.3.7.2[SS] | NA | 922 | 2958 | 918SS | 68h | No | Yes | No | No | No | 1.3.3.7.1 | 5 | No | 500 | Future Task | No | 0h
1.3.3.7.2 | Auto Scheduled | 0% | Assign Tester ID's | No | 2h | Fri 6/19/26 | Mon 6/22/26 | Security | 2186SS | 2188SS |  | NA | ITC-3 | Fri 6/19/26 | Mon 6/22/26 | 1.3.3.7.1[SS] | Thu 6/18/26 | Thu 6/18/26 | As Soon As Possible | 1.3.3.7.3[SS] | NA | 918 | 922SS | 2950SS | 68h | No | Yes | No | No | No | 1.3.3.7.2 | 5 | No | 500 | Future Task | No | 0h
1.3.3.7.3 | Auto Scheduled | 0% | Identify Data and Processes for ITC | No | 1d | Fri 6/19/26 | Mon 6/22/26 |  | 2187SS | 2189 |  | NA | ITC-3 | Fri 6/19/26 | Mon 6/22/26 | 1.3.3.7.2[SS] | NA | NA | As Soon As Possible | 1.3.3.7.4 | NA | 2950 | 918SS | 2951 | 8.5d | No | Yes | No | No | No | 1.3.3.7.3 | 5 | No | 500 | Future Task | No | 0d
1.3.3.7.4 | Auto Scheduled | 0% | Run Costing for Data Identified | No | 4h | Mon 6/22/26 | Tue 6/23/26 |  | 2188 | 2190 |  | NA | ITC-3 | Mon 6/22/26 | Tue 6/23/26 | 1.3.3.7.3 | NA | NA | As Soon As Possible | 1.3.3.7.5 | NA | 2951 | 2950 | 917 | 68h | No | Yes | No | No | No | 1.3.3.7.4 | 5 | No | 500 | Future Task | No | 0h
1.3.3.7.5 | Auto Scheduled | 0% | Functional Smoke Testing | No | 5d | Tue 6/23/26 | Tue 6/30/26 | Functional Leads | 2189 | 2166 |  | NA | ITC-3 | Tue 6/23/26 | Tue 6/30/26 | 1.3.3.7.4 | Thu 6/18/26 | Thu 6/25/26 | As Soon As Possible | 1.3.3.3 | NA | 917 | 2951 | 931 | 8.5d | No | Yes | No | No | No | 1.3.3.7.5 | 5 | No | 500 | Future Task | No | 0d
1.3.3.7.6 | Auto Scheduled | 0% | Test Kickoff | No | 1h | Mon 7/13/26 | Mon 7/13/26 | Renee | 2166 | 2192SS |  | NA | ITC-3 | Mon 7/13/26 | Mon 7/13/26 | 1.3.3.3 | Thu 6/18/26 | Thu 6/18/26 | Must Start On | 1.3.3.7.7[SS] | Mon 7/13/26 | 916 | 931 | 919SS | 0h | No | Yes | Yes | No | No | 1.3.3.7.6 | 5 | No | 500 | Future Task | No | 0h
1.3.3.7.7 | Auto Scheduled | 0% | Team Testing | No | 10d | Mon 7/13/26 | Fri 7/24/26 |  | 2191SS | 2193SS+3d |  | NA | ITC-3 | Mon 7/13/26 | Fri 7/24/26 | 1.3.3.7.6[SS] | Mon 6/22/26 | Fri 7/17/26 | As Soon As Possible | 1.3.3.7.8[SS+3d] | NA | 919 | 916SS | 923SS+3d | 76d | No | Yes | No | No | No | 1.3.3.7.7 | 5 | No | 500 | Future Task | No | 0d
1.3.3.7.8 | Auto Scheduled | 0% | Defect Correction / Retesting / Mitigation / Close | No | 5d | Thu 7/16/26 | Wed 7/22/26 |  | 2192SS+3d | 2194SS+4d |  | NA | ITC-3 | Thu 7/16/26 | Wed 7/22/26 | 1.3.3.7.7[SS+3d] | Mon 7/20/26 | Fri 7/24/26 | As Soon As Possible | 1.3.3.7.9[SS+4d] | NA | 923 | 919SS+3d | 921SS+4d | 78d | No | Yes | No | No | No | 1.3.3.7.8 | 5 | No | 500 | Future Task | No | 0d
1.3.3.7.9 | Auto Scheduled | 0% | Gate Review | No | 0h | Tue 7/21/26 | Tue 7/21/26 |  | 2193SS+4d |  |  | NA | ITC-3 | Tue 7/21/26 | Tue 7/21/26 | 1.3.3.7.8[SS+4d] | Thu 7/23/26 | Thu 7/23/26 | As Soon As Possible |  | NA | 921 | 923SS+4d |  | 632h | No | Yes | No | Yes | No | 1.3.3.7.9 | 5 | No | 500 | Future Task | No | 632h
1.3.3.8 | Auto Scheduled | 0% | UAT (DR) | No | 44.38d | Mon 8/17/26 | Fri 10/16/26 |  |  |  |  | NA | Testing Cycles | Mon 8/17/26 | Fri 10/16/26 |  | Thu 4/30/26 | Thu 9/3/26 | As Soon As Possible |  | NA | 22 |  |  | -5.75d | Yes | Yes | Yes | No | No | 1.3.3.8 | 4 | No | 500 | Future Task | No | 0d
1.3.3.8.1 | Auto Scheduled | 0% | Assign Resources to Depolyment 1 locations | No | 2h | Thu 10/8/26 | Thu 10/8/26 | Renee | 17592140 | 2197 |  | NA | UAT (DR) | Thu 10/8/26 | Thu 10/8/26 | 1.2.4.3,1.2.5.3 | Thu 4/30/26 | Thu 4/30/26 | As Soon As Possible | 1.3.3.8.2 | NA | 924 | 33604530 | 927 | -355h | No | Yes | Yes | No | No | 1.3.3.8.1 | 5 | No | 500 | Future Task | No | 0h
1.3.3.8.2 | Auto Scheduled | 0% | Assign Tester ID's | No | 2h | Thu 10/8/26 | Fri 10/9/26 | Security | 2196 | 2198SS |  | NA | UAT (DR) | Thu 10/8/26 | Fri 10/9/26 | 1.3.3.8.1 | Thu 8/6/26 | Thu 8/6/26 | As Soon As Possible | 1.3.3.8.3[SS] | NA | 927 | 924 | 3361SS | -355h | No | Yes | Yes | No | No | 1.3.3.8.2 | 5 | No | 500 | Future Task | No | 0h
1.3.3.8.3 | Auto Scheduled | 0% | Run Costing for Data Identified | No | 4h | Thu 10/8/26 | Fri 10/9/26 |  | 2197SS | 2199 |  | NA | UAT (DR) | Thu 10/8/26 | Fri 10/9/26 | 1.3.3.8.2[SS] | NA | NA | As Soon As Possible | 1.3.3.8.4 | NA | 3361 | 927SS | 926 | -355h | No | Yes | Yes | No | No | 1.3.3.8.3 | 5 | No | 500 | Future Task | No | 0h
1.3.3.8.4 | Auto Scheduled | 0% | Functional Smoke Testing | No | 5d | Fri 10/9/26 | Fri 10/16/26 | Functional Leads | 2198 | 2167 |  | NA | UAT (DR) | Fri 10/9/26 | Fri 10/16/26 | 1.3.3.8.3 | Mon 8/3/26 | Fri 8/7/26 | As Soon As Possible | 1.3.3.4 | NA | 926 | 3361 | 690 | -44.38d | No | Yes | Yes | No | No | 1.3.3.8.4 | 5 | No | 500 | Future Task | No | 0d
1.3.3.8.5 | Auto Scheduled | 0% | Test Kickoff | No | 1h | Mon 8/17/26 | Mon 8/17/26 | Renee | 2167 | 2201SS |  | NA | UAT (DR) | Mon 8/17/26 | Mon 8/17/26 | 1.3.3.4 | Thu 8/6/26 | Thu 8/6/26 | Must Start On | 1.3.3.8.6[SS] | Mon 8/17/26 | 925 | 690 | 928SS | -355h | No | Yes | Yes | No | No | 1.3.3.8.5 | 5 | No | 500 | Future Task | No | 0h
1.3.3.8.6 | Auto Scheduled | 0% | Team Testing | No | 10d | Mon 8/17/26 | Fri 8/28/26 |  | 2200SS | 2202SS+3d |  | NA | UAT (DR) | Mon 8/17/26 | Fri 8/28/26 | 1.3.3.8.5[SS] | Mon 8/10/26 | Fri 8/28/26 | As Soon As Possible | 1.3.3.8.7[SS+3d] | NA | 928 | 925SS | 3362SS+3d | 51d | No | Yes | No | No | No | 1.3.3.8.6 | 5 | No | 500 | Future Task | No | 0d
1.3.3.8.7 | Auto Scheduled | 0% | Defect Correction / Retesting / Mitigation / Close | No | 0d | Wed 8/19/26 | Wed 8/19/26 |  | 2201SS+3d | 2203SS+4d |  | NA | UAT (DR) | Wed 8/19/26 | Wed 8/19/26 | 1.3.3.8.6[SS+3d] | Mon 7/20/26 | Fri 7/24/26 | As Soon As Possible | 1.3.3.8.8[SS+4d] | NA | 3362 | 928SS+3d | 930SS+4d | 54d | No | Yes | No | Yes | No | 1.3.3.8.7 | 5 | No | 500 | Future Task | No | 0d
1.3.3.8.8 | Auto Scheduled | 0% | Gate Review | No | 0h | Tue 8/25/26 | Tue 8/25/26 |  | 2202SS+4d |  |  | NA | UAT (DR) | Tue 8/25/26 | Tue 8/25/26 | 1.3.3.8.7[SS+4d] | Thu 9/3/26 | Thu 9/3/26 | As Soon As Possible |  | NA | 930 | 3362SS+4d |  | 432h | No | Yes | No | Yes | No | 1.3.3.8.8 | 5 | No | 500 | Future Task | No | 432h
1.4 | Auto Scheduled | 38% | Business Readniess | No | 191d | Mon 2/16/26 | Mon 11/9/26 |  |  |  |  | Mon 2/16/26 | AMETEK Release-1, 3-Deployment Plan | Mon 2/16/26 | Mon 11/9/26 |  | Mon 2/16/26 | Fri 10/16/26 | As Soon As Possible |  | NA | 683 |  |  | 0d | Yes | Yes | Yes | No | No | 1.4 | 2 | No | 500 | Future Task | No | 0d
1.4.1 | Auto Scheduled | 38% | Training Readiness | No | 191d | Mon 2/16/26 | Mon 11/9/26 |  |  |  |  | Mon 2/16/26 | Business Readniess | Mon 2/16/26 | Mon 11/9/26 |  | Mon 2/16/26 | Fri 10/16/26 | As Soon As Possible |  | NA | 215 |  |  | 0d | Yes | Yes | Yes | No | No | 1.4.1 | 3 | No | 500 | Future Task | No | 0d
1.4.1.1 | Auto Scheduled | 44% | Content Development | No | 191d | Mon 2/16/26 | Mon 11/9/26 |  |  |  |  | Mon 2/16/26 | Training Readiness | Mon 2/16/26 | Mon 11/9/26 |  | Mon 2/16/26 | Mon 8/10/26 | As Soon As Possible |  | NA | 216 |  |  | 0d | Yes | Yes | Yes | No | No | 1.4.1.1 | 4 | No | 500 | Future Task | No | 0d
1.4.1.1.1 | Auto Scheduled | 46% | Verify Role Mapping Complete | No | 66d | Fri 5/1/26 | Fri 7/31/26 | Training |  | 2208SS,2212SS |  | Fri 5/1/26 | Content Development | Fri 5/1/26 | Fri 7/31/26 |  | Mon 2/16/26 | Mon 8/3/26 | Finish No Earlier Than | 1.4.1.1.2[SS],1.4.1.1.6[SS] | Fri 7/31/26 | 232 |  | 225SS,218SS | 71d | No | Yes | No | No | No | 1.4.1.1.1 | 5 | No | 500 | Future Task | No | 0d
1.4.1.1.2 | Auto Scheduled | 30% | Develop Curriculum | No | 66d | Fri 5/1/26 | Fri 7/31/26 | Training | 2207SS | 2209SS,2211 |  | Fri 5/1/26 | Content Development | Fri 5/1/26 | Fri 7/31/26 | 1.4.1.1.1[SS] | Mon 2/16/26 | Fri 6/5/26 | Finish No Earlier Than | 1.4.1.1.3[SS],1.4.1.1.5 | Fri 7/31/26 | 225 | 232SS | 4542SS,217 | 0d | No | Yes | Yes | No | No | 1.4.1.1.2 | 5 | No | 500 | Future Task | No | 0d
1.4.1.1.3 | Auto Scheduled | 35% | Develop Course ppts | No | 86d | Fri 5/1/26 | Fri 8/28/26 | Training | 2208SS | 2210SS,2213,2214 |  | Fri 5/1/26 | Content Development | Fri 5/1/26 | Fri 8/28/26 | 1.4.1.1.2[SS] | Mon 2/16/26 | Mon 8/3/26 | Finish No Earlier Than | 1.4.1.1.4[SS],1.4.1.1.7,1.4.1.2 | Fri 8/28/26 | 4542 | 225SS | 233SS,220,221 | 45d | No | Yes | No | No | No | 1.4.1.1.3 | 5 | No | 500 | Future Task | No | 0d
1.4.1.1.4 | Auto Scheduled | 21% | Develop Work Instructions | No | 86d | Fri 5/1/26 | Fri 8/28/26 | Training | 2209SS |  |  | Fri 5/1/26 | Content Development | Fri 5/1/26 | Fri 8/28/26 | 1.4.1.1.3[SS] | Mon 4/27/26 | Mon 8/3/26 | Finish No Earlier Than |  | Fri 8/28/26 | 233 | 4542SS |  | 51d | No | Yes | No | No | No | 1.4.1.1.4 | 5 | No | 500 | Future Task | No | 51d
1.4.1.1.5 | Auto Scheduled | 0% | Develop Training Data Sheets (Testing/Training) | No | 71d | Mon 8/3/26 | Mon 11/9/26 | Training | 2208 |  |  | NA | Content Development | Mon 8/3/26 | Mon 11/9/26 | 1.4.1.1.2 | Mon 4/27/26 | Mon 8/3/26 | Start No Earlier Than |  | Thu 4/30/26 | 217 | 225 |  | 0d | No | Yes | Yes | No | No | 1.4.1.1.5 | 5 | No | 500 | Future Task | No | 0d
1.4.1.1.6 | Auto Scheduled | 100% | Develop Train the Trainer | No | 120d | Mon 2/16/26 | Fri 7/31/26 | Training | 2207SS | 2216 |  | Mon 2/16/26 | Content Development | Mon 2/16/26 | Fri 7/31/26 | 1.4.1.1.1[SS] | Mon 2/16/26 | Fri 7/31/26 | Finish No Earlier Than | 1.4.1.3.1 | Fri 7/31/26 | 218 | 232SS | 247 | 0d | No | Yes | No | No | No | 1.4.1.1.6 | 5 | No | 500 | Complete | No | 0d
1.4.1.1.7 | Auto Scheduled | 0% | Publish Training Materials to SP/LMS | No | 6d | Mon 8/31/26 | Mon 9/7/26 | Training | 2209 |  |  | NA | Content Development | Mon 8/31/26 | Mon 9/7/26 | 1.4.1.1.3 | Mon 8/3/26 | Mon 8/10/26 | Finish No Earlier Than |  | Fri 8/28/26 | 220 | 4542 |  | 45d | No | Yes | No | No | No | 1.4.1.1.7 | 5 | No | 500 | Future Task | No | 45d
1.4.1.2 | Auto Scheduled | 0% | Talent LMS Application Setup | No | 1d | Mon 8/31/26 | Mon 8/31/26 |  | 2209 |  |  | NA | Training Readiness | Mon 8/31/26 | Mon 8/31/26 | 1.4.1.1.3 | Mon 8/10/26 | Mon 8/10/26 | Finish No Earlier Than |  | Fri 8/28/26 | 221 | 4542 |  | 50d | No | Yes | No | No | No | 1.4.1.2 | 4 | No | 500 | Future Task | No | 50d
1.4.1.3 | Auto Scheduled | 0% | Train the Trainer | No | 20d | Mon 8/3/26 | Fri 8/28/26 |  |  |  |  | NA | Training Readiness | Mon 8/3/26 | Fri 8/28/26 |  | Mon 8/3/26 | Fri 8/28/26 | As Soon As Possible |  | NA | 241 |  |  | 16d | Yes | Yes | No | No | No | 1.4.1.3 | 4 | No | 500 | Future Task | No | 16d
1.4.1.3.1 | Auto Scheduled | 0% | Deliver Train the Trainer (BPL->SME) | No | 20d | Mon 8/3/26 | Fri 8/28/26 | Training | 2212 | 2219 |  | NA | Train the Trainer | Mon 8/3/26 | Fri 8/28/26 | 1.4.1.1.6 | Mon 8/3/26 | Fri 8/28/26 | Finish No Earlier Than | 1.4.1.4.2 | Fri 8/28/26 | 247 | 218 | 246 | 16d | No | Yes | No | No | No | 1.4.1.3.1 | 5 | No | 500 | Future Task | No | 0d
1.4.1.4 | Auto Scheduled | 0% | End User Training Exeuction | No | 71d | Fri 7/10/26 | Fri 10/16/26 |  |  |  |  | NA | Training Readiness | Fri 7/10/26 | Fri 10/16/26 |  | Fri 7/10/26 | Fri 10/16/26 | As Soon As Possible |  | NA | 242 |  |  | 16d | Yes | Yes | No | No | No | 1.4.1.4 | 4 | No | 500 | Future Task | No | 16d
1.4.1.4.1 | Auto Scheduled | 0% | User Training Plan and Schedule | No | 136h | Fri 7/10/26 | Mon 8/3/26 | Training |  |  |  | NA | End User Training Exeuction | Fri 7/10/26 | Mon 8/3/26 |  | Fri 7/10/26 | Fri 7/10/26 | Finish No Earlier Than |  | Mon 8/3/26 | 913 |  |  | 560h | No | Yes | No | No | No | 1.4.1.4.1 | 5 | No | 500 | Future Task | No | 560h
1.4.1.4.2 | Auto Scheduled | 0% | Deliver End User Training | No | 35d | Mon 8/31/26 | Fri 10/16/26 | Training | 2216 |  |  | NA | End User Training Exeuction | Mon 8/31/26 | Fri 10/16/26 | 1.4.1.3.1 | Mon 8/31/26 | Fri 10/16/26 | Start No Earlier Than |  | Mon 3/9/26 | 246 | 247 |  | 16d | No | Yes | No | No | No | 1.4.1.4.2 | 5 | No | 500 | Future Task | No | 16d

## Task_Export_Table
ID | Unique_ID | Active | Task Mode | Task_Name | Duration | Type | Outline_Level | Baseline_Duration | Predecessors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Free_Slack | Total_Slack | Leveling_Delay | Percent_Complete | Actual_Start | Actual_Finish | Baseline_Start | Baseline_Finish | Constraint_Type | Constraint_Date | Stop | Resume | Created | Scheduled_Work | Baseline_Work | Actual_Work | Cost | Fixed_Cost | Baseline_Cost | Actual_Cost | Remaining_Cost | WBS | Priority | Milestone | Summary | Rollup | Text1 | Text2 | Text3 | Text4 | Text5 | Text6 | Text7 | Text8 | Text9 | Text10 | Cost1 | Cost2 | Cost3 | Duration1 | Duration2 | Duration3 | Flag1 | Flag2 | Flag3 | Flag4 | Flag5 | Flag6 | Flag7 | Flag8 | Flag9 | Flag10 | Marked | Number1 | Number2 | Number3 | Number4 | Number5 | Subproject_File
1 | 1 | Yes | Auto Scheduled | AMETEK Release-1, 3-Deployment Plan | 451d? | Fixed Duration | 1 | 435d |  | February 17, 2025 8:00 | November 9, 2026 5:00 | 2/17/25 8:00 | 11/9/26 5:00 | 2/17/25 8:00 | 11/9/26 5:00 | 0d? | 0d? | 0ed | 0.5 | 2/17/25 8:00 | NA | February 17, 2025 8:00 | October 16, 2026 5:00 | As Soon As Possible | NA | 3/13/25 9:00 | 3/13/25 9:00 | 3/13/25 11:03 | 9,032.28h | 5,387.75h | 2,726h | 0 | 0 | 0 | 0 | 0 | 1 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2 | 2 | Yes | Auto Scheduled | System Readiness | 439d? | Fixed Duration | 2 | 368.31d |  | February 17, 2025 8:00 | October 22, 2026 5:00 | 2/17/25 8:00 | 10/22/26 5:00 | 2/17/25 8:00 | 11/9/26 5:00 | 12d? | 12d? | 0ed | 0.81999999999999995 | 2/17/25 8:00 | NA | February 17, 2025 8:00 | July 16, 2026 10:30 | As Soon As Possible | NA | 3/13/25 9:00 | 3/13/25 9:00 | 3/13/25 11:04 | 828h | 506.5h | 227.25h | 0 | 0 | 0 | 0 | 0 | 1.1 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
3 | 5 | Yes | Auto Scheduled | Environment Schedule | 404d? | Fixed Duration | 3 | 350.31d |  | March 13, 2025 8:00 | September 29, 2026 5:00 | 3/13/25 8:00 | 9/29/26 5:00 | 3/13/25 8:00 | 11/9/26 5:00 | 29d? | 29d? | 0ed | 0.23999999999999999 | 3/13/25 8:00 | NA | March 13, 2025 8:00 | July 16, 2026 10:30 | As Soon As Possible | NA | 3/13/25 9:00 | 3/13/25 9:00 | 3/13/25 11:04 | 820h | 498.5h | 219.25h | 0 | 0 | 0 | 0 | 0 | 1.1.1 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
4 | 85 | Yes | Auto Scheduled | DS4-100 Config / Development Client | 0.75d | Fixed Duration | 4 | 0.75d |  | May 7, 2025 10:00 | May 7, 2025 5:00 | 5/7/25 10:00 | 5/7/25 5:00 | 5/7/25 10:00 | 5/7/25 5:00 | 0d | 0d | 0ed | 1 | 5/7/25 10:00 | 5/7/25 5:00 | May 7, 2025 10:00 | May 7, 2025 5:00 | As Soon As Possible | NA | 5/7/25 5:00 | 5/7/25 5:00 | 5/7/25 1:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.1 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
5 | 100 | Yes | Auto Scheduled | Copy DS4-100 to DS4-110 Dev | 6h | Fixed Units | 5 | 0.75d |  | May 7, 2025 10:00 | May 7, 2025 5:00 | 5/7/25 10:00 | 5/7/25 5:00 | 5/7/25 10:00 | 5/7/25 5:00 | 0h | 0h | 0ed | 1 | 5/7/25 10:00 | 5/7/25 5:00 | May 7, 2025 10:00 | May 7, 2025 5:00 | Finish No Earlier Than | 5/7/25 5:00 | 5/7/25 5:00 | 5/7/25 5:00 | 5/7/25 1:23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.1.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
6 | 86 | Yes | Auto Scheduled | DS4-110 Unit Test Client | 0.5d | Fixed Duration | 4 | 0.5d |  | May 8, 2025 8:00 | May 8, 2025 12:00 | 5/8/25 8:00 | 5/8/25 12:00 | 5/8/25 8:00 | 5/8/25 12:00 | 0d | 0d | 0ed | 1 | 5/8/25 8:00 | 5/8/25 12:00 | May 8, 2025 8:00 | May 8, 2025 12:00 | As Soon As Possible | NA | 5/8/25 10:00 | 5/8/25 10:00 | 5/7/25 1:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.2 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
7 | 106 | Yes | Auto Scheduled | List of functional users | 2h | Fixed Units | 5 | 0.25d | 5 | May 8, 2025 8:00 | May 8, 2025 10:00 | 5/8/25 8:00 | 5/8/25 10:00 | 5/8/25 8:00 | 5/8/25 10:00 | 0h | 0h | 0ed | 1 | 5/8/25 8:00 | 5/8/25 10:00 | May 8, 2025 8:00 | May 8, 2025 10:00 | As Soon As Possible | NA | 5/8/25 10:00 | 5/8/25 10:00 | 5/7/25 1:27 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.2.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
8 | 101 | Yes | Auto Scheduled | Security Role for Functional Team | 2h | Fixed Units | 5 | 0.25d | 7 | May 8, 2025 10:00 | May 8, 2025 12:00 | 5/8/25 10:00 | 5/8/25 12:00 | 5/8/25 10:00 | 5/8/25 12:00 | 0h | 0h | 0ed | 1 | 5/8/25 10:00 | 5/8/25 12:00 | May 8, 2025 10:00 | May 8, 2025 12:00 | As Soon As Possible | NA | 5/8/25 12:00 | 5/8/25 12:00 | 5/7/25 1:24 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.2.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
9 | 87 | Yes | Auto Scheduled | DS4-120 Data Dev Client | 0.5d | Fixed Duration | 4 | 0.5d |  | May 8, 2025 8:00 | May 8, 2025 12:00 | 5/8/25 8:00 | 5/8/25 12:00 | 5/8/25 8:00 | 5/8/25 12:00 | 0d | 0d | 0ed | 1 | 5/8/25 8:00 | 5/8/25 12:00 | May 8, 2025 8:00 | May 8, 2025 12:00 | As Soon As Possible | NA | 5/8/25 10:00 | 5/8/25 10:00 | 5/7/25 1:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.3 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
10 | 107 | Yes | Auto Scheduled | List of functional users | 2h | Fixed Units | 5 | 0.25d | 5 | May 8, 2025 8:00 | May 8, 2025 10:00 | 5/8/25 8:00 | 5/8/25 10:00 | 5/8/25 8:00 | 5/8/25 10:00 | 0h | 0h | 0ed | 1 | 5/8/25 8:00 | 5/8/25 10:00 | May 8, 2025 8:00 | May 8, 2025 10:00 | As Soon As Possible | NA | 5/8/25 10:00 | 5/8/25 10:00 | 5/7/25 1:28 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.3.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
11 | 104 | Yes | Auto Scheduled | Security Role for Data Team | 2h | Fixed Units | 5 | 0.25d | 10 | May 8, 2025 10:00 | May 8, 2025 12:00 | 5/8/25 10:00 | 5/8/25 12:00 | 5/8/25 10:00 | 5/8/25 12:00 | 0h | 0h | 0ed | 1 | 5/8/25 10:00 | 5/8/25 12:00 | May 8, 2025 10:00 | May 8, 2025 12:00 | As Soon As Possible | NA | 5/8/25 12:00 | 5/8/25 12:00 | 5/7/25 1:24 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.3.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
12 | 88 | Yes | Auto Scheduled | QS5 ITC-1 Refresh | 277.5d? | Fixed Duration | 4 | 277.5d |  | March 13, 2025 8:00 | April 6, 2026 12:00 | 3/13/25 8:00 | 4/6/26 12:00 | 3/13/25 8:00 | 4/6/26 12:00 | 0d? | 0d? | 0ed | 1 | 3/13/25 8:00 | 4/6/26 12:00 | March 13, 2025 8:00 | April 6, 2026 12:00 | As Soon As Possible | NA | 3/13/25 9:00 | 3/13/25 9:00 | 5/7/25 1:21 | 137h | 137h | 137h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
13 | 830 | Yes | Auto Scheduled | Change Request to NS2 | 1h | Fixed Units | 5 | 0.13d |  | March 13, 2025 8:00 | March 13, 2025 9:00 | 3/13/25 8:00 | 3/13/25 9:00 | 3/13/25 8:00 | 3/13/25 9:00 | 0h | 0h | 0ed | 1 | 3/13/25 8:00 | 3/13/25 9:00 | March 13, 2025 8:00 | March 13, 2025 9:00 | As Soon As Possible | NA | 3/13/25 9:00 | 3/13/25 9:00 | 3/30/26 2:11 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
14 | 669 | Yes | Auto Scheduled | Dev Environment Release from SAP | 0d | Fixed Units | 5 | 0d |  | January 8, 2026 8:00 | January 8, 2026 8:00 | 1/8/26 8:00 | 1/8/26 8:00 | 1/8/26 8:00 | 1/8/26 8:00 | 0d | 0d | 0ed | 1 | 1/8/26 8:00 | 1/8/26 8:00 | January 8, 2026 8:00 | January 8, 2026 8:00 | Start No Earlier Than | 1/8/26 8:00 | 1/8/26 8:00 | 1/8/26 8:00 | 12/18/25 5:34 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.2 | 500 | Yes | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
15 | 670 | Yes | Auto Scheduled | Release Setup ID's and Access | 1h | Fixed Units | 5 | 0.13d | 14 | January 8, 2026 8:00 | January 8, 2026 9:00 | 1/8/26 8:00 | 1/8/26 9:00 | 1/8/26 8:00 | 1/8/26 9:00 | 0h | 0h | 0ed | 1 | 1/8/26 8:00 | 1/8/26 9:00 | January 8, 2026 8:00 | January 8, 2026 9:00 | As Soon As Possible | NA | 1/8/26 9:00 | 1/8/26 9:00 | 1/8/26 11:38 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
16 | 654 | Yes | Auto Scheduled | Client Config / Validation | 1d | Fixed Units | 5 | 1d | 15 | February 2, 2026 8:00 | February 2, 2026 5:00 | 2/2/26 8:00 | 2/2/26 5:00 | 2/2/26 8:00 | 2/2/26 5:00 | 0d | 0d | 0ed | 1 | 2/2/26 8:00 | 2/2/26 5:00 | February 2, 2026 8:00 | February 2, 2026 5:00 | As Soon As Possible | NA | 2/2/26 5:00 | 2/2/26 5:00 | 12/16/25 8:19 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.4 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
17 | 640 | Yes | Auto Scheduled | Technical Transports / BP Setup | 1d | Fixed Units | 5 | 1d |  | February 4, 2026 8:00 | February 4, 2026 5:00 | 2/4/26 8:00 | 2/4/26 5:00 | 2/4/26 8:00 | 2/4/26 5:00 | 0d | 0d | 0ed | 1 | 2/4/26 8:00 | 2/4/26 5:00 | February 4, 2026 8:00 | February 4, 2026 5:00 | As Soon As Possible | NA | 2/4/26 5:00 | 2/4/26 5:00 | 12/16/25 8:14 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
18 | 655 | Yes | Auto Scheduled | Best Practice / Country Validation | 1d? | Fixed Units | 5 | 1d | 16 | February 3, 2026 8:00 | February 3, 2026 5:00 | 2/3/26 8:00 | 2/3/26 5:00 | 2/3/26 8:00 | 2/3/26 5:00 | 0d? | 0d? | 0ed | 1 | 2/3/26 8:00 | 2/3/26 5:00 | February 3, 2026 8:00 | February 3, 2026 5:00 | As Soon As Possible | NA | 2/3/26 5:00 | 2/3/26 5:00 | 12/16/25 8:19 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.6 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
19 | 641 | Yes | Auto Scheduled | Connect Systems and Validate | 1d | Fixed Units | 5 | 1d | 17 | February 5, 2026 8:00 | February 5, 2026 5:00 | 2/5/26 8:00 | 2/5/26 5:00 | 2/5/26 8:00 | 2/5/26 5:00 | 0d | 0d | 0ed | 1 | 2/5/26 8:00 | 2/5/26 5:00 | February 5, 2026 8:00 | February 5, 2026 5:00 | As Soon As Possible | NA | 2/5/26 5:00 | 2/5/26 5:00 | 12/16/25 8:14 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.7 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
20 | 674 | Yes | Auto Scheduled | Validate Syniti Connections to QS5 | 1d | Fixed Units | 5 | 1d | 17 | February 5, 2026 8:00 | February 5, 2026 5:00 | 2/5/26 8:00 | 2/5/26 5:00 | 2/5/26 8:00 | 2/5/26 5:00 | 0d | 0d | 0ed | 1 | 2/5/26 8:00 | 2/5/26 5:00 | February 5, 2026 8:00 | February 5, 2026 5:00 | As Soon As Possible | NA | 2/5/26 5:00 | 2/5/26 5:00 | 1/8/26 11:52 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.8 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
21 | 642 | Yes | Auto Scheduled | Security Transports | 4h | Fixed Units | 5 | 0.5d | 17 | February 5, 2026 8:00 | February 5, 2026 12:00 | 2/5/26 8:00 | 2/5/26 12:00 | 2/5/26 8:00 | 2/5/26 12:00 | 0h | 0h | 0ed | 1 | 2/5/26 8:00 | 2/5/26 12:00 | February 5, 2026 8:00 | February 5, 2026 12:00 | As Soon As Possible | NA | 2/5/26 12:00 | 2/5/26 12:00 | 12/16/25 8:14 | 4h | 4h | 4h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.9 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
22 | 671 | Yes | Auto Scheduled | Security Manual Tasks | 1d | Fixed Units | 5 | 1d | 21 | February 5, 2026 1:00 | February 6, 2026 12:00 | 2/5/26 1:00 | 2/6/26 12:00 | 2/5/26 1:00 | 2/6/26 12:00 | 0d | 0d | 0ed | 1 | 2/5/26 1:00 | 2/6/26 12:00 | February 5, 2026 1:00 | February 6, 2026 12:00 | As Soon As Possible | NA | 2/6/26 12:00 | 2/6/26 12:00 | 1/8/26 11:43 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.10 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
23 | 643 | Yes | Auto Scheduled | Manual Technical Tasks | 1d | Fixed Units | 5 | 1d | 21 | February 5, 2026 1:00 | February 6, 2026 12:00 | 2/5/26 1:00 | 2/6/26 12:00 | 2/5/26 1:00 | 2/6/26 12:00 | 0d | 0d | 0ed | 1 | 2/5/26 1:00 | 2/6/26 12:00 | February 5, 2026 1:00 | February 6, 2026 12:00 | As Soon As Possible | NA | 2/6/26 12:00 | 2/6/26 12:00 | 12/16/25 8:14 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.11 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
24 | 644 | Yes | Auto Scheduled | Validate Fiori | 4h | Fixed Units | 5 | 0.5d | 23 | February 6, 2026 1:00 | February 6, 2026 5:00 | 2/6/26 1:00 | 2/6/26 5:00 | 2/6/26 1:00 | 2/6/26 5:00 | 0h | 0h | 0ed | 1 | 2/6/26 1:00 | 2/6/26 5:00 | February 6, 2026 1:00 | February 6, 2026 5:00 | As Soon As Possible | NA | 2/6/26 5:00 | 2/6/26 5:00 | 12/16/25 8:14 | 4h | 4h | 4h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.12 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
25 | 672 | Yes | Auto Scheduled | Fiori App Activation | 6h | Fixed Units | 5 | 0.75d | 24 | February 9, 2026 8:00 | February 9, 2026 3:00 | 2/9/26 8:00 | 2/9/26 3:00 | 2/9/26 8:00 | 2/9/26 3:00 | 0h | 0h | 0ed | 1 | 2/9/26 8:00 | 2/9/26 3:00 | February 9, 2026 8:00 | February 9, 2026 3:00 | As Soon As Possible | NA | 2/9/26 3:00 | 2/9/26 3:00 | 1/8/26 11:45 | 6h | 6h | 6h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.13 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
26 | 645 | Yes | Auto Scheduled | Download Transport List | 1h | Fixed Units | 5 | 0.13d | 24 | February 9, 2026 8:00 | February 9, 2026 9:00 | 2/9/26 8:00 | 2/9/26 9:00 | 2/9/26 8:00 | 2/9/26 9:00 | 0h | 0h | 0ed | 1 | 2/9/26 8:00 | 2/9/26 9:00 | February 9, 2026 8:00 | February 9, 2026 9:00 | As Soon As Possible | NA | 2/9/26 9:00 | 2/9/26 9:00 | 12/16/25 8:14 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.14 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
27 | 653 | Yes | Auto Scheduled | Business Functions Validation | 1d | Fixed Units | 5 | 1d | 24 | February 9, 2026 8:00 | February 9, 2026 5:00 | 2/9/26 8:00 | 2/9/26 5:00 | 2/9/26 8:00 | 2/9/26 5:00 | 0d | 0d | 0ed | 1 | 2/9/26 8:00 | 2/9/26 5:00 | February 9, 2026 8:00 | February 9, 2026 5:00 | Start No Earlier Than | 1/5/26 8:00 | 2/9/26 5:00 | 2/9/26 5:00 | 12/16/25 8:18 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.15 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
28 | 646 | Yes | Auto Scheduled | Functional Leads Validation of Transport List | 1h | Fixed Units | 5 | 0.13d | 26 | February 9, 2026 9:00 | February 9, 2026 10:00 | 2/9/26 9:00 | 2/9/26 10:00 | 2/9/26 9:00 | 2/9/26 10:00 | 0h | 0h | 0ed | 1 | 2/9/26 9:00 | 2/9/26 10:00 | February 9, 2026 9:00 | February 9, 2026 10:00 | As Soon As Possible | NA | 2/9/26 10:00 | 2/9/26 10:00 | 12/16/25 8:14 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.16 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
29 | 673 | Yes | Auto Scheduled | Release Security roles to Functional Team | 1h | Fixed Units | 5 | 0.13d | 28 | February 9, 2026 10:00 | February 9, 2026 11:00 | 2/9/26 10:00 | 2/9/26 11:00 | 2/9/26 10:00 | 2/9/26 11:00 | 0h | 0h | 0ed | 1 | 2/9/26 10:00 | 2/9/26 11:00 | February 9, 2026 10:00 | February 9, 2026 11:00 | As Soon As Possible | NA | 2/9/26 11:00 | 2/9/26 11:00 | 1/8/26 11:48 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.17 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
30 | 647 | Yes | Auto Scheduled | Release Transports to Client | 32.75d | Fixed Duration | 5 | 32.75d |  | February 9, 2026 10:00 | March 25, 2026 5:00 | 2/9/26 10:00 | 3/25/26 5:00 | 2/9/26 10:00 | 3/25/26 5:00 | 0d | 0d | 0ed | 1 | 2/9/26 10:00 | 3/25/26 5:00 | February 9, 2026 10:00 | March 25, 2026 5:00 | As Soon As Possible | NA | 2/9/26 12:00 | 2/9/26 12:00 | 12/16/25 8:14 | 42h | 42h | 42h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.18 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
31 | 657 | Yes | Auto Scheduled | Import Group 1 - Ent Structure | 2h | Fixed Units | 6 | 0.25d | 28 | February 9, 2026 10:00 | February 9, 2026 12:00 | 2/9/26 10:00 | 2/9/26 12:00 | 2/9/26 10:00 | 2/9/26 12:00 | 0h | 0h | 0ed | 1 | 2/9/26 10:00 | 2/9/26 12:00 | February 9, 2026 10:00 | February 9, 2026 12:00 | As Soon As Possible | NA | 2/9/26 12:00 | 2/9/26 12:00 | 12/16/25 8:26 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.18.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
32 | 658 | Yes | Auto Scheduled | Manual activities group 1 | 20h | Fixed Units | 6 | 2.5d | 31 | March 19, 2026 8:00 | March 23, 2026 12:00 | 3/19/26 8:00 | 3/23/26 12:00 | 3/19/26 8:00 | 3/23/26 12:00 | 0h | 0h | 0ed | 1 | 3/19/26 8:00 | 3/23/26 12:00 | March 19, 2026 8:00 | March 23, 2026 12:00 | Finish No Earlier Than | 2/11/26 5:00 | 3/23/26 12:00 | 3/23/26 12:00 | 12/16/25 8:26 | 20h | 20h | 20h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.18.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
33 | 659 | Yes | Auto Scheduled | Import Group 2 - Core Transports | 2h | Fixed Units | 6 | 0.25d | 32 | March 23, 2026 1:00 | March 23, 2026 3:00 | 3/23/26 1:00 | 3/23/26 3:00 | 3/23/26 1:00 | 3/23/26 3:00 | 0h | 0h | 0ed | 1 | 3/23/26 1:00 | 3/23/26 3:00 | March 23, 2026 1:00 | March 23, 2026 3:00 | As Soon As Possible | NA | 3/23/26 3:00 | 3/23/26 3:00 | 12/16/25 8:26 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.18.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
34 | 660 | Yes | Auto Scheduled | Manual activities group 2 | 1d | Fixed Units | 6 | 1d | 33 | March 23, 2026 3:00 | March 24, 2026 3:00 | 3/23/26 3:00 | 3/24/26 3:00 | 3/23/26 3:00 | 3/24/26 3:00 | 0d | 0d | 0ed | 1 | 3/23/26 3:00 | 3/24/26 3:00 | March 23, 2026 3:00 | March 24, 2026 3:00 | As Soon As Possible | NA | 3/24/26 3:00 | 3/24/26 3:00 | 12/16/25 8:26 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.18.4 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
35 | 661 | Yes | Auto Scheduled | Import Group 3 - prior to transactions | 2h | Fixed Units | 6 | 0.25d | 34 | March 24, 2026 3:00 | March 24, 2026 5:00 | 3/24/26 3:00 | 3/24/26 5:00 | 3/24/26 3:00 | 3/24/26 5:00 | 0h | 0h | 0ed | 1 | 3/24/26 3:00 | 3/24/26 5:00 | March 24, 2026 3:00 | March 24, 2026 5:00 | As Soon As Possible | NA | 3/24/26 5:00 | 3/24/26 5:00 | 12/16/25 8:26 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.18.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
36 | 831 | Yes | Auto Scheduled | Manual Activities Group 3 | 1d | Fixed Units | 6 | 1d | 35 | March 25, 2026 8:00 | March 25, 2026 5:00 | 3/25/26 8:00 | 3/25/26 5:00 | 3/25/26 8:00 | 3/25/26 5:00 | 0d | 0d | 0ed | 1 | 3/25/26 8:00 | 3/25/26 5:00 | March 25, 2026 8:00 | March 25, 2026 5:00 | As Soon As Possible | NA | 3/25/26 5:00 | 3/25/26 5:00 | 3/30/26 2:21 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.18.6 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
37 | 662 | Yes | Auto Scheduled | Import Group 4 - workbench / dev work | 2h | Fixed Units | 5 | 0.25d |  | April 3, 2026 8:00 | April 3, 2026 10:00 | 4/3/26 8:00 | 4/3/26 10:00 | 4/3/26 8:00 | 4/3/26 10:00 | 0h | 0h | 0ed | 1 | 4/3/26 8:00 | 4/3/26 10:00 | April 3, 2026 8:00 | April 3, 2026 10:00 | Start No Earlier Than | 4/3/26 8:00 | 4/3/26 10:00 | 4/3/26 10:00 | 12/16/25 8:26 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.19 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
38 | 663 | Yes | Auto Scheduled | Import Group 5 - Config to support dev workbench | 2h | Fixed Units | 5 | 0.25d | 37 | April 3, 2026 10:00 | April 3, 2026 12:00 | 4/3/26 10:00 | 4/3/26 12:00 | 4/3/26 10:00 | 4/3/26 12:00 | 0h | 0h | 0ed | 1 | 4/3/26 10:00 | 4/3/26 12:00 | April 3, 2026 10:00 | April 3, 2026 12:00 | As Soon As Possible | NA | 4/3/26 12:00 | 4/3/26 12:00 | 12/16/25 8:26 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.20 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
39 | 833 | Yes | Auto Scheduled | Create Migration Data Project in DMC | 1d | Fixed Units | 5 | 1d | 38 | April 3, 2026 1:00 | April 6, 2026 12:00 | 4/3/26 1:00 | 4/6/26 12:00 | 4/3/26 1:00 | 4/6/26 12:00 | 0d | 0d | 0ed | 1 | 4/3/26 1:00 | 4/6/26 12:00 | April 3, 2026 1:00 | April 6, 2026 12:00 | As Soon As Possible | NA | 4/6/26 12:00 | 4/6/26 12:00 | 3/30/26 2:26 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.21 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
40 | 652 | Yes | Auto Scheduled | Environment Ready for Build | 0d | Fixed Units | 5 | 0d | 39 | April 6, 2026 12:00 | April 6, 2026 12:00 | 4/6/26 12:00 | 4/6/26 12:00 | 4/6/26 12:00 | 4/6/26 12:00 | 0d | 0d | 0ed | 1 | 4/6/26 12:00 | 4/6/26 12:00 | April 6, 2026 12:00 | April 6, 2026 12:00 | As Soon As Possible | NA | 4/6/26 12:00 | 4/6/26 12:00 | 12/16/25 8:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.4.22 | 500 | Yes | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
41 | 849 | Yes | Auto Scheduled | QS4 ITC-2 Refresh | 13.13d | Fixed Duration | 4 | 54.28d |  | April 27, 2026 8:00 | May 14, 2026 9:00 | 4/27/26 8:00 | 5/14/26 9:00 | 4/1/26 4:59 | 5/4/26 5:00 | 0d | -7.13d | 0ed | 0.51000000000000001 | 4/27/26 8:00 | NA | May 1, 2026 8:00 | July 16, 2026 10:15 | Start No Earlier Than | 4/27/26 8:00 | 4/27/26 5:00 | 4/27/26 5:00 | 3/31/26 7:06 | 160h | 184h | 82.25h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
42 | 3340 | Yes | Auto Scheduled | System Setup | 6d | Fixed Duration | 5 | 0d | 40 | April 27, 2026 8:00 | May 4, 2026 5:00 | 4/27/26 8:00 | 5/4/26 5:00 | 4/1/26 4:59 | 5/4/26 5:00 | 0d | 0d | 0ed | 0.80000000000000004 | 4/27/26 8:00 | NA | NA | NA | As Soon As Possible | NA | 4/27/26 5:00 | 4/27/26 5:00 | 4/29/26 3:04 | 103h | 0h | 82.25h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1 | 500 | No | Yes | Yes |  |  | Red | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
43 | 850 | Yes | Auto Scheduled | Dev Refresh Basis(Workinig with NS2) | 2d | Fixed Units | 6 | 0.13d |  | April 27, 2026 8:00 | April 28, 2026 5:00 | 4/27/26 8:00 | 4/28/26 5:00 | 4/27/26 8:00 | 4/28/26 5:00 | 0d | 0d | 0ed | 1 | 4/27/26 8:00 | 4/28/26 5:00 | May 1, 2026 8:00 | May 1, 2026 9:00 | Start No Earlier Than | 4/27/26 8:00 | 4/28/26 5:00 | 4/28/26 5:00 | 3/31/26 7:06 | 16h | 1h | 16h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.1 | 500 | No | No | No |  |  | GreenSquare | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | Yes | 0 | 0 | 0 | 0 | 0
44 | 853 | Yes | Auto Scheduled | Client Config / Validation | 1d | Fixed Units | 6 | 1d | 40 | April 27, 2026 8:00 | April 27, 2026 5:00 | 4/27/26 8:00 | 4/27/26 5:00 | 4/27/26 8:00 | 4/27/26 5:00 | 0d | 0d | 0ed | 1 | 4/27/26 8:00 | 4/27/26 5:00 | May 8, 2026 10:00 | May 11, 2026 10:00 | As Soon As Possible | NA | 4/27/26 5:00 | 4/27/26 5:00 | 3/31/26 7:06 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
45 | 854 | Yes | Auto Scheduled | Technical Transports / BP Setup | 1d | Fixed Units | 6 | 1d | 44 | April 28, 2026 8:00 | April 28, 2026 5:00 | 4/28/26 8:00 | 4/28/26 5:00 | 4/28/26 8:00 | 4/28/26 5:00 | 0d | 0d | 0ed | 1 | 4/28/26 8:00 | 4/28/26 5:00 | May 11, 2026 10:00 | May 12, 2026 10:00 | As Soon As Possible | NA | 4/28/26 5:00 | 4/28/26 5:00 | 3/31/26 7:06 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
46 | 855 | Yes | Auto Scheduled | Best Practice / Country Validation | 1d | Fixed Units | 6 | 1d | 45 | April 29, 2026 8:00 | April 29, 2026 5:00 | 4/29/26 8:00 | 4/29/26 5:00 | 4/29/26 8:00 | 4/29/26 5:00 | 0d | 0d | 0ed | 1 | 4/29/26 8:00 | 4/29/26 5:00 | May 12, 2026 10:00 | May 13, 2026 10:00 | As Soon As Possible | NA | 4/29/26 5:00 | 4/29/26 5:00 | 3/31/26 7:06 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.4 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
47 | 856 | Yes | Auto Scheduled | Connect Systems and Validate | 1d | Fixed Units | 6 | 1d | 46 | April 30, 2026 8:00 | April 30, 2026 5:00 | 4/30/26 8:00 | 4/30/26 5:00 | 4/30/26 8:00 | 4/30/26 5:00 | 0d | 0d | 0ed | 1 | 4/30/26 8:00 | 4/30/26 5:00 | May 13, 2026 10:00 | May 14, 2026 10:00 | As Soon As Possible | NA | 4/30/26 5:00 | 4/30/26 5:00 | 3/31/26 7:06 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
48 | 857 | Yes | Auto Scheduled | Validate Syniti Connections to QS5 | 1d | Fixed Units | 6 | 1d | 47 | May 1, 2026 8:00 | May 1, 2026 5:00 | 5/1/26 8:00 | 5/1/26 5:00 | 5/1/26 8:00 | 5/1/26 5:00 | 0d | 0d | 0ed | 1 | 5/1/26 8:00 | 5/1/26 5:00 | May 14, 2026 10:00 | May 15, 2026 10:00 | As Soon As Possible | NA | 5/1/26 5:00 | 5/1/26 5:00 | 3/31/26 7:06 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.6 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
49 | 858 | Yes | Auto Scheduled | Security Transports | 4h | Fixed Units | 6 | 0.5d | 48 | May 4, 2026 8:00 | May 4, 2026 12:00 | 5/4/26 8:00 | 5/4/26 12:00 | 5/4/26 8:00 | 5/4/26 12:00 | 0h | 0h | 0ed | 1 | 5/4/26 8:00 | 5/4/26 12:00 | May 15, 2026 10:00 | May 15, 2026 3:00 | As Soon As Possible | NA | 5/4/26 12:00 | 5/4/26 12:00 | 3/31/26 7:06 | 4h | 4h | 4h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.7 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
50 | 859 | Yes | Auto Scheduled | Security Manual Tasks | 1d | Fixed Units | 6 | 1d | 49SS | May 4, 2026 8:00 | May 4, 2026 5:00 | 5/4/26 8:00 | 5/4/26 5:00 | 5/4/26 8:00 | 5/4/26 5:00 | 0d | 0d | 0ed | 1 | 5/4/26 8:00 | 5/4/26 5:00 | May 15, 2026 3:00 | May 18, 2026 3:00 | As Soon As Possible | NA | 5/4/26 5:00 | 5/4/26 5:00 | 3/31/26 7:06 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.8 | 500 | No | No | No |  |  | GreenSquare | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
51 | 860 | Yes | Auto Scheduled | Manual Technical Tasks | 1d | Fixed Units | 6 | 1d | 50SS | May 4, 2026 8:00 | May 4, 2026 5:00 | 5/4/26 8:00 | 5/4/26 5:00 | 5/4/26 8:00 | 5/4/26 5:00 | 0d | 0d | 0ed | 1 | 5/4/26 8:00 | 5/4/26 5:00 | May 15, 2026 3:00 | May 18, 2026 3:00 | As Soon As Possible | NA | 5/4/26 5:00 | 5/4/26 5:00 | 3/31/26 7:06 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.9 | 500 | No | No | No |  |  | GreenSquare | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
52 | 861 | Yes | Auto Scheduled | Validate Fiori | 8h | Fixed Units | 6 | 0.5d | 50SS | May 4, 2026 8:00 | May 4, 2026 5:00 | 5/4/26 8:00 | 5/4/26 5:00 | 5/4/26 8:00 | 5/4/26 5:00 | 0h | -182.02h | 0ed | 0.25 | 5/4/26 8:00 | NA | May 18, 2026 3:00 | May 19, 2026 10:00 | As Soon As Possible | NA | 5/4/26 10:00 | 5/4/26 10:00 | 3/31/26 7:06 | 8h | 4h | 2h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.10 | 500 | No | No | No |  |  | Red | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
53 | 862 | Yes | Auto Scheduled | Fiori App Activation | 8h | Fixed Units | 6 | 0.75d | 52SS | May 4, 2026 8:00 | May 4, 2026 5:00 | 5/4/26 8:00 | 5/4/26 5:00 | 5/4/26 8:00 | 5/4/26 5:00 | 0h | -182.02h | 0ed | 0.25 | 5/4/26 8:00 | NA | May 19, 2026 10:00 | May 19, 2026 5:00 | As Soon As Possible | NA | 5/4/26 10:00 | 5/4/26 10:00 | 3/31/26 7:06 | 8h | 6h | 2h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.11 | 500 | No | No | No |  |  | Red | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
54 | 863 | Yes | Auto Scheduled | Download Transport List | 1h | Fixed Units | 6 | 0.13d | 53SS | May 4, 2026 8:00 | May 4, 2026 9:00 | 5/4/26 8:00 | 5/4/26 9:00 | 5/4/26 8:00 | 5/4/26 9:00 | 0h | -175.02h | 0ed | 0.25 | 5/4/26 8:00 | NA | May 19, 2026 10:00 | May 19, 2026 11:00 | As Soon As Possible | NA | 5/4/26 8:15 | 5/4/26 8:15 | 3/31/26 7:06 | 1h | 1h | 0.25h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.12 | 500 | No | No | No |  |  | Red | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
55 | 864 | Yes | Auto Scheduled | Business Functions Validation | 8h | Fixed Units | 6 | 1d | 52SS | May 4, 2026 8:00 | May 4, 2026 5:00 | 5/4/26 8:00 | 5/4/26 5:00 | 5/4/26 8:00 | 5/4/26 5:00 | 0h | -182.02h | 0ed | 0.25 | 5/4/26 8:00 | NA | May 19, 2026 10:00 | May 20, 2026 10:00 | As Soon As Possible | NA | 5/4/26 10:00 | 5/4/26 10:00 | 3/31/26 7:06 | 8h | 8h | 2h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.13 | 500 | No | No | No |  |  | Red | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
56 | 865 | Yes | Auto Scheduled | Functional Leads Validation of Transport List | 1h | Fixed Units | 6 | 0.13d | 53SS | May 4, 2026 8:00 | May 4, 2026 9:00 | 5/4/26 8:00 | 5/4/26 9:00 | 4/1/26 4:59 | 4/2/26 8:59 | 0h | -176.02h | 0ed | 0 | NA | NA | May 19, 2026 11:00 | May 19, 2026 12:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.14 | 500 | No | No | No |  |  | Red | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
57 | 866 | Yes | Auto Scheduled | Release Security roles to Functional Team | 1h | Fixed Units | 6 | 0.13d | 56 | May 4, 2026 9:00 | May 4, 2026 10:00 | 5/4/26 9:00 | 5/4/26 10:00 | 4/2/26 8:59 | 4/2/26 9:59 | 0h | -176.02h | 0ed | 0 | NA | NA | May 19, 2026 1:00 | May 19, 2026 2:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.1.15 | 500 | No | No | No |  |  | Red | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
58 | 867 | Yes | Auto Scheduled | Release Transports to Client | 6.56d | Fixed Duration | 5 | 5.25d | 42 | May 5, 2026 8:00 | May 13, 2026 1:30 | 5/5/26 8:00 | 5/13/26 1:30 | 4/2/26 9:59 | 4/10/26 3:29 | 0d | -22.75d | 0ed | 0 | NA | NA | May 19, 2026 1:00 | May 26, 2026 3:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 52.5h | 42h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
59 | 868 | Yes | Auto Scheduled | Import Group 1 - Ent Structure | 2h | Fixed Units | 6 | 0.25d | 56 | May 5, 2026 8:00 | May 5, 2026 10:00 | 5/5/26 8:00 | 5/5/26 10:00 | 4/2/26 9:59 | 4/2/26 11:59 | 0h | -182.02h | 0ed | 0 | NA | NA | May 19, 2026 1:00 | May 19, 2026 3:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.2.1 | 500 | No | No | No |  |  | Red | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
60 | 869 | Yes | Auto Scheduled | Manual activities group 1 | 20h | Fixed Units | 6 | 2.5d | 59 | May 5, 2026 10:00 | May 7, 2026 3:00 | 5/5/26 10:00 | 5/7/26 3:00 | 4/2/26 11:59 | 4/6/26 4:59 | 0h | -182.02h | 0ed | 0 | NA | NA | May 19, 2026 3:00 | May 22, 2026 10:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 20h | 20h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.2.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
61 | 870 | Yes | Auto Scheduled | Import Group 2 - Core Transports | 2h | Fixed Units | 6 | 0.25d | 60 | May 7, 2026 3:00 | May 7, 2026 5:00 | 5/7/26 3:00 | 5/7/26 5:00 | 4/6/26 4:59 | 4/7/26 9:59 | 0h | -182.02h | 0ed | 0 | NA | NA | May 22, 2026 10:00 | May 22, 2026 12:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.2.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
62 | 871 | Yes | Auto Scheduled | Manual activities group 2 | 1d | Fixed Units | 6 | 1d | 61 | May 8, 2026 8:00 | May 8, 2026 5:00 | 5/8/26 8:00 | 5/8/26 5:00 | 4/7/26 9:59 | 4/8/26 9:59 | 0d | -22.75d | 0ed | 0 | NA | NA | May 22, 2026 1:00 | May 25, 2026 12:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.2.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
63 | 872 | Yes | Auto Scheduled | Import Group 3 - prior to transactions | 2h | Fixed Units | 6 | 0.25d | 62 | May 11, 2026 8:00 | May 11, 2026 10:00 | 5/11/26 8:00 | 5/11/26 10:00 | 4/8/26 9:59 | 4/8/26 11:59 | 0h | -182.02h | 0ed | 0 | NA | NA | May 25, 2026 1:00 | May 25, 2026 3:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.2.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
64 | 873 | Yes | Auto Scheduled | Manual Activities Group 3 | 1d | Fixed Units | 6 | 1d | 63 | May 11, 2026 10:00 | May 12, 2026 10:00 | 5/11/26 10:00 | 5/12/26 10:00 | 4/8/26 11:59 | 4/9/26 11:59 | 0d | -22.75d | 0ed | 0 | NA | NA | May 25, 2026 3:00 | May 26, 2026 3:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.2.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
65 | 874 | Yes | Auto Scheduled | Import Group 4 - workbench / dev work | 2h | Fixed Units | 6 | 0.25d | 64 | May 12, 2026 10:00 | May 12, 2026 12:00 | 5/12/26 10:00 | 5/12/26 12:00 | 4/9/26 11:59 | 4/9/26 2:59 | 0h | -182.02h | 0ed | 0 | NA | NA | May 26, 2026 3:00 | May 26, 2026 5:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.2.7 | 500 | No | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
66 | 875 | Yes | Auto Scheduled | Import Group 5 - Config to support dev workbench | 8.5h | Fixed Units | 6 | 1.06d | 65 | May 12, 2026 1:00 | May 13, 2026 1:30 | 5/12/26 1:00 | 5/13/26 1:30 | 4/9/26 2:59 | 4/10/26 3:29 | 0h | -182.02h | 0ed | 0 | NA | NA | May 27, 2026 8:00 | May 28, 2026 8:30 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 8.5h | 8.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.2.8 | 500 | No | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
67 | 1226 | Yes | Auto Scheduled | Data Project Create | 0.56d | Fixed Duration | 5 | 1.06d | 66SS | May 13, 2026 1:30 | May 14, 2026 9:00 | 5/13/26 1:30 | 5/14/26 9:00 | 5/4/26 8:59 | 5/4/26 2:29 | 0d | -7.44d | 0ed | 0 | NA | NA | May 27, 2026 8:00 | May 28, 2026 8:30 | As Soon As Possible | NA | NA | NA | 4/8/26 9:03 | 4.5h | 8.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.3 | 500 | No | Yes | Yes |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | Yes | 0 | 0 | 0 | 0 | 0
68 | 1221 | Yes | Auto Scheduled | Open Client | 15m | Fixed Units | 6 | 0.03d | 66 | May 13, 2026 1:30 | May 13, 2026 1:45 | 5/13/26 1:30 | 5/13/26 1:45 | 5/4/26 8:59 | 5/4/26 9:14 | 0m | -3571m | 0ed | 0 | NA | NA | May 27, 2026 8:00 | May 27, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/8/26 9:01 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.3.1 | 500 | No | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
69 | 876 | Yes | Auto Scheduled | Create Migration Data Project in DMC | 4h | Fixed Units | 6 | 1d | 68 | May 13, 2026 1:45 | May 14, 2026 8:45 | 5/13/26 1:45 | 5/14/26 8:45 | 5/4/26 9:14 | 5/4/26 2:14 | 0h | -59.52h | 0ed | 0 | NA | NA | May 27, 2026 8:15 | May 28, 2026 8:15 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 4h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.3.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
70 | 1222 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 6 | 0.03d | 69 | May 14, 2026 8:45 | May 14, 2026 9:00 | 5/14/26 8:45 | 5/14/26 9:00 | 5/4/26 2:14 | 5/4/26 2:29 | 0m | -3571m | 0ed | 0 | NA | NA | May 28, 2026 8:15 | May 28, 2026 8:30 | As Soon As Possible | NA | NA | NA | 4/8/26 9:01 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.3.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
71 | 877 | Yes | Auto Scheduled | Environment Ready for Test | 0m | Fixed Units | 5 | 0d | 70 | May 14, 2026 9:00 | May 14, 2026 9:00 | 5/14/26 9:00 | 5/14/26 9:00 | 5/4/26 2:29 | 5/4/26 2:29 | 0m | -3571m | 0ed | 0 | NA | NA | July 16, 2026 10:15 | July 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 3/31/26 7:06 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.5.4 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
72 | 1284 | Yes | Auto Scheduled | QS5 ITC-3 Refresh | 9.44d | Fixed Duration | 4 | 54.28d |  | May 18, 2026 8:00 | May 29, 2026 11:30 | 5/18/26 8:00 | 5/29/26 11:30 | 4/10/26 3:29 | 6/5/26 5:00 | 0d | -25.19d | 0ed | 0 | NA | NA | May 1, 2026 8:00 | July 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 162h | 184h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
73 | 3339 | Yes | Auto Scheduled | System Setup | 8d | Fixed Duration | 5 | 0d | 58 | May 18, 2026 8:00 | May 27, 2026 5:00 | 5/18/26 8:00 | 5/27/26 5:00 | 4/10/26 3:29 | 6/5/26 5:00 | 0d | -25.19d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 3:04 | 105h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
74 | 1285 | Yes | Auto Scheduled | System Refresh Basis(Workinig with NS2) | 3d | Fixed Units | 6 | 0.13d |  | May 18, 2026 8:00 | May 20, 2026 5:00 | 5/18/26 8:00 | 5/20/26 5:00 | 5/18/26 8:00 | 5/20/26 5:00 | 0d | 0d | 0ed | 0 | NA | NA | May 1, 2026 8:00 | May 1, 2026 9:00 | Must Start On | 5/18/26 8:00 | NA | NA | 4/23/26 10:38 | 24h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | Yes | 0 | 0 | 0 | 0 | 0
75 | 1288 | Yes | Auto Scheduled | Client Config / Validation | 1d | Fixed Units | 6 | 1d | 74 | May 21, 2026 8:00 | May 21, 2026 5:00 | 5/21/26 8:00 | 5/21/26 5:00 | 4/10/26 3:29 | 4/13/26 3:29 | 0d | -28.19d | 0ed | 0 | NA | NA | May 8, 2026 10:00 | May 11, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
76 | 1289 | Yes | Auto Scheduled | Technical Transports / BP Setup | 1d | Fixed Units | 6 | 1d | 75 | May 22, 2026 8:00 | May 22, 2026 5:00 | 5/22/26 8:00 | 5/22/26 5:00 | 6/2/26 8:00 | 6/2/26 5:00 | 0d | 7d | 0ed | 0 | NA | NA | May 11, 2026 10:00 | May 12, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
77 | 1290 | Yes | Auto Scheduled | Best Practice / Country Validation | 1d | Fixed Units | 6 | 1d | 76 | May 25, 2026 8:00 | May 25, 2026 5:00 | 5/25/26 8:00 | 5/25/26 5:00 | 6/3/26 8:00 | 6/3/26 5:00 | 0d | 7d | 0ed | 0 | NA | NA | May 12, 2026 10:00 | May 13, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
78 | 1291 | Yes | Auto Scheduled | Connect Systems and Validate | 1d | Fixed Units | 6 | 1d | 77 | May 26, 2026 8:00 | May 26, 2026 5:00 | 5/26/26 8:00 | 5/26/26 5:00 | 6/4/26 8:00 | 6/4/26 5:00 | 0d | 7d | 0ed | 0 | NA | NA | May 13, 2026 10:00 | May 14, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
79 | 1292 | Yes | Auto Scheduled | Validate Syniti Connections to QS5 | 1d | Fixed Units | 6 | 1d | 78 | May 27, 2026 8:00 | May 27, 2026 5:00 | 5/27/26 8:00 | 5/27/26 5:00 | 6/5/26 8:00 | 6/5/26 5:00 | 7d | 7d | 0ed | 0 | NA | NA | May 14, 2026 10:00 | May 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
80 | 1293 | Yes | Auto Scheduled | Security Transports | 4h | Fixed Units | 6 | 0.5d | 75SS | May 21, 2026 8:00 | May 21, 2026 12:00 | 5/21/26 8:00 | 5/21/26 12:00 | 4/10/26 3:29 | 4/13/26 10:29 | 0h | -225.52h | 0ed | 0 | NA | NA | May 15, 2026 10:00 | May 15, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
81 | 1294 | Yes | Auto Scheduled | Security Manual Tasks | 1d | Fixed Units | 6 | 1d | 80 | May 21, 2026 1:00 | May 22, 2026 12:00 | 5/21/26 1:00 | 5/22/26 12:00 | 6/5/26 8:00 | 6/5/26 5:00 | 10.5d | 10.5d | 0ed | 0 | NA | NA | May 15, 2026 3:00 | May 18, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.8 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
82 | 1295 | Yes | Auto Scheduled | Manual Technical Tasks | 1d | Fixed Units | 6 | 1d | 80SS | May 21, 2026 8:00 | May 21, 2026 5:00 | 5/21/26 8:00 | 5/21/26 5:00 | 4/10/26 3:29 | 4/13/26 3:29 | 0d | -28.19d | 0ed | 0 | NA | NA | May 15, 2026 3:00 | May 18, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.9 | 500 | No | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | Yes | 0 | 0 | 0 | 0 | 0
83 | 1296 | Yes | Auto Scheduled | Validate Fiori | 4h | Fixed Units | 6 | 0.5d | 82SS | May 21, 2026 8:00 | May 21, 2026 12:00 | 5/21/26 8:00 | 5/21/26 12:00 | 6/5/26 1:00 | 6/5/26 5:00 | 92h | 92h | 0ed | 0 | NA | NA | May 18, 2026 3:00 | May 19, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.10 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
84 | 1297 | Yes | Auto Scheduled | Fiori App Activation | 6h | Fixed Units | 6 | 0.75d | 82SS | May 21, 2026 8:00 | May 21, 2026 3:00 | 5/21/26 8:00 | 5/21/26 3:00 | 4/10/26 3:29 | 4/13/26 1:29 | 0h | -225.52h | 0ed | 0 | NA | NA | May 19, 2026 10:00 | May 19, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.11 | 500 | No | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
85 | 1298 | Yes | Auto Scheduled | Download Transport List | 1h | Fixed Units | 6 | 0.13d | 84SS | May 21, 2026 8:00 | May 21, 2026 9:00 | 5/21/26 8:00 | 5/21/26 9:00 | 4/10/26 3:29 | 4/10/26 4:29 | 0h | -225.52h | 0ed | 0 | NA | NA | May 19, 2026 10:00 | May 19, 2026 11:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.12 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
86 | 1299 | Yes | Auto Scheduled | Business Functions Validation | 8h | Fixed Units | 6 | 1d | 85SS | May 21, 2026 8:00 | May 21, 2026 5:00 | 5/21/26 8:00 | 5/21/26 5:00 | 6/5/26 8:00 | 6/5/26 5:00 | 88h | 88h | 0ed | 0 | NA | NA | May 19, 2026 10:00 | May 20, 2026 10:00 | Start No Earlier Than | 1/5/26 8:00 | NA | NA | 4/23/26 10:38 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.13 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
87 | 1300 | Yes | Auto Scheduled | Functional Leads Validation of Transport | 1h | Fixed Units | 6 | 0.13d | 85SS | May 21, 2026 8:00 | May 21, 2026 9:00 | 5/21/26 8:00 | 5/21/26 9:00 | 4/10/26 3:29 | 4/10/26 4:29 | 0h | -225.52h | 0ed | 0 | NA | NA | May 19, 2026 11:00 | May 19, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.14 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
88 | 1301 | Yes | Auto Scheduled | Release Security roles to Functional Team | 1h | Fixed Units | 6 | 0.13d | 87SS | May 21, 2026 8:00 | May 21, 2026 9:00 | 5/21/26 8:00 | 5/21/26 9:00 | 6/5/26 4:00 | 6/5/26 5:00 | 95h | 95h | 0ed | 0 | NA | NA | May 19, 2026 1:00 | May 19, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.1.15 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
89 | 1302 | Yes | Auto Scheduled | Release Transports to Client | 6.31d | Fixed Duration | 5 | 5.25d | 87 | May 21, 2026 9:00 | May 29, 2026 11:30 | 5/21/26 9:00 | 5/29/26 11:30 | 4/10/26 4:29 | 6/5/26 5:00 | 0d | -28.19d | 0ed | 0 | NA | NA | May 19, 2026 1:00 | May 26, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 52.5h | 42h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.2 | 500 | No | Yes | Yes |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | Yes | 0 | 0 | 0 | 0 | 0
90 | 1303 | Yes | Auto Scheduled | Import Group 1 - Ent Structure | 2h | Fixed Units | 6 | 0.25d | 87 | May 21, 2026 9:00 | May 21, 2026 11:00 | 5/21/26 9:00 | 5/21/26 11:00 | 4/10/26 4:29 | 4/13/26 9:29 | 0h | -225.52h | 0ed | 0 | NA | NA | May 19, 2026 1:00 | May 19, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.2.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
91 | 1304 | Yes | Auto Scheduled | Manual activities group 1 | 20h | Fixed Units | 6 | 2.5d | 90 | May 21, 2026 11:00 | May 25, 2026 4:00 | 5/21/26 11:00 | 5/25/26 4:00 | 4/13/26 9:29 | 4/15/26 2:29 | 0h | -225.52h | 0ed | 0 | NA | NA | May 19, 2026 3:00 | May 22, 2026 10:00 | Finish No Earlier Than | 2/11/26 5:00 | NA | NA | 4/23/26 10:38 | 20h | 20h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.2.2 | 500 | No | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
92 | 1305 | Yes | Auto Scheduled | Import Group 2 - Core Transports | 2h | Fixed Units | 6 | 0.25d | 91 | May 25, 2026 4:00 | May 26, 2026 9:00 | 5/25/26 4:00 | 5/26/26 9:00 | 4/15/26 2:29 | 4/15/26 4:29 | 0h | -225.52h | 0ed | 0 | NA | NA | May 22, 2026 10:00 | May 22, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.2.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
93 | 1306 | Yes | Auto Scheduled | Manual activities group 2 | 1d | Fixed Units | 6 | 1d | 92 | May 26, 2026 9:00 | May 27, 2026 9:00 | 5/26/26 9:00 | 5/27/26 9:00 | 4/15/26 4:29 | 4/16/26 4:29 | 0d | -28.19d | 0ed | 0 | NA | NA | May 22, 2026 1:00 | May 25, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.2.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
94 | 1307 | Yes | Auto Scheduled | Import Group 3 - prior to transactions | 2h | Fixed Units | 6 | 0.25d | 93 | May 27, 2026 9:00 | May 27, 2026 11:00 | 5/27/26 9:00 | 5/27/26 11:00 | 4/16/26 4:29 | 4/17/26 9:29 | 0h | -225.52h | 0ed | 0 | NA | NA | May 25, 2026 1:00 | May 25, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.2.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
95 | 1308 | Yes | Auto Scheduled | Manual Activities Group 3 | 1d | Fixed Units | 6 | 1d | 94 | May 27, 2026 11:00 | May 28, 2026 11:00 | 5/27/26 11:00 | 5/28/26 11:00 | 4/17/26 9:29 | 4/20/26 9:29 | 0d | -28.19d | 0ed | 0 | NA | NA | May 25, 2026 3:00 | May 26, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.2.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
96 | 1309 | Yes | Auto Scheduled | Import Group 4 - workbench / dev work | 2h | Fixed Units | 6 | 0.25d | 95 | May 28, 2026 11:00 | May 28, 2026 2:00 | 5/28/26 11:00 | 5/28/26 2:00 | 6/4/26 4:30 | 6/5/26 9:30 | 0h | 44.5h | 0ed | 0 | NA | NA | May 26, 2026 3:00 | May 26, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.2.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
97 | 1310 | Yes | Auto Scheduled | Import Group 5 - Config to support dev workbench | 8.5h | Fixed Units | 6 | 1.06d | 96SS | May 28, 2026 11:00 | May 29, 2026 11:30 | 5/28/26 11:00 | 5/29/26 11:30 | 6/4/26 4:30 | 6/5/26 5:00 | 44.5h | 44.5h | 0ed | 0 | NA | NA | May 27, 2026 8:00 | May 28, 2026 8:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 8.5h | 8.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.2.8 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
98 | 1311 | Yes | Auto Scheduled | Data Project Create | 0.56d | Fixed Duration | 5 | 1.06d | 95 | May 28, 2026 11:00 | May 28, 2026 4:30 | 5/28/26 11:00 | 5/28/26 4:30 | 4/20/26 9:29 | 4/20/26 2:59 | 0d | -28.19d | 0ed | 0 | NA | NA | May 27, 2026 8:00 | May 28, 2026 8:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 4.5h | 8.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.3 | 500 | No | Yes | Yes |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | Yes | 0 | 0 | 0 | 0 | 0
99 | 1312 | Yes | Auto Scheduled | Open Client | 15m | Fixed Units | 6 | 0.03d | 95 | May 28, 2026 11:00 | May 28, 2026 11:15 | 5/28/26 11:00 | 5/28/26 11:15 | 4/20/26 9:29 | 4/20/26 9:44 | 0m | -13531m | 0ed | 0 | NA | NA | May 27, 2026 8:00 | May 27, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.3.1 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
100 | 1313 | Yes | Auto Scheduled | Create Migration Data Project in DMC | 4h | Fixed Units | 6 | 1d | 99 | May 28, 2026 11:15 | May 28, 2026 4:15 | 5/28/26 11:15 | 5/28/26 4:15 | 4/20/26 9:44 | 4/20/26 2:44 | 0h | -225.52h | 0ed | 0 | NA | NA | May 27, 2026 8:15 | May 28, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 4h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.3.2 | 500 | No | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
101 | 1314 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 6 | 0.03d | 100 | May 28, 2026 4:15 | May 28, 2026 4:30 | 5/28/26 4:15 | 5/28/26 4:30 | 4/20/26 2:44 | 4/20/26 2:59 | 0m | -13531m | 0ed | 0 | NA | NA | May 28, 2026 8:15 | May 28, 2026 8:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.3.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
102 | 1315 | Yes | Auto Scheduled | Environment Ready for Test | 0m | Fixed Units | 5 | 0d | 101 | May 28, 2026 4:30 | May 28, 2026 4:30 | 5/28/26 4:30 | 5/28/26 4:30 | 4/20/26 2:59 | 4/20/26 2:59 | 0m | -13531m | 0ed | 0 | NA | NA | July 16, 2026 10:15 | July 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:38 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.6.4 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
103 | 884 | Yes | Auto Scheduled | QS4 UAT Refresh | 13d | Fixed Duration | 4 | 350.31d |  | June 8, 2026 8:00 | June 24, 2026 5:00 | 6/8/26 8:00 | 6/24/26 5:00 | 4/20/26 2:59 | 6/9/26 5:00 | 0d | -34.25d | 0ed | 0 | NA | NA | March 13, 2025 8:00 | July 16, 2026 10:30 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 180.5h | 177.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
104 | 3338 | Yes | Auto Scheduled | System Setup | 8d | Fixed Duration | 5 | 0d | 102 | June 8, 2026 8:00 | June 17, 2026 5:00 | 6/8/26 8:00 | 6/17/26 5:00 | 4/20/26 2:59 | 6/9/26 5:00 | 0d | -34.25d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 3:03 | 130h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
105 | 885 | Yes | Auto Scheduled | System Refresh Basis(Workinig with NS2) | 2d | Fixed Units | 6 | 0.13d |  | June 8, 2026 8:00 | June 9, 2026 5:00 | 6/8/26 8:00 | 6/9/26 5:00 | 6/8/26 8:00 | 6/9/26 5:00 | 0d | 0d | 0ed | 0 | NA | NA | June 19, 2026 8:00 | June 19, 2026 9:00 | Must Start On | 6/8/26 8:00 | NA | NA | 3/31/26 7:17 | 16h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | Yes | 0 | 0 | 0 | 0 | 0
106 | 888 | Yes | Auto Scheduled | Client Config / Validation | 2d | Fixed Units | 6 | 1d | 105 | June 10, 2026 8:00 | June 11, 2026 5:00 | 6/10/26 8:00 | 6/11/26 5:00 | 4/20/26 2:59 | 4/22/26 2:59 | 0d | -36.25d | 0ed | 0 | NA | NA | June 26, 2026 10:00 | June 29, 2026 10:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 16h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
107 | 889 | Yes | Auto Scheduled | Technical Transports / BP Setup | 1d | Fixed Units | 6 | 1d | 106 | June 12, 2026 8:00 | June 12, 2026 5:00 | 6/12/26 8:00 | 6/12/26 5:00 | 4/22/26 2:59 | 4/23/26 2:59 | 0d | -36.25d | 0ed | 0 | NA | NA | June 29, 2026 10:00 | June 30, 2026 10:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
108 | 890 | Yes | Auto Scheduled | Best Practice / Country Validation | 1d | Fixed Units | 6 | 1d | 106 | June 12, 2026 8:00 | June 12, 2026 5:00 | 6/12/26 8:00 | 6/12/26 5:00 | 4/22/26 2:59 | 4/23/26 2:59 | 0d | -36.25d | 0ed | 0 | NA | NA | June 30, 2026 10:00 | July 1, 2026 10:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
109 | 891 | Yes | Auto Scheduled | Connect Systems and Validate | 2d | Fixed Units | 6 | 1d | 108 | June 15, 2026 8:00 | June 16, 2026 5:00 | 6/15/26 8:00 | 6/16/26 5:00 | 5/15/26 10:29 | 5/19/26 10:29 | 0d | -20.69d | 0ed | 0 | NA | NA | July 1, 2026 10:00 | July 2, 2026 10:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 16h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
110 | 892 | Yes | Auto Scheduled | Validate Syniti Connections to QS5 | 1d | Fixed Units | 6 | 1d | 109 | June 17, 2026 8:00 | June 17, 2026 5:00 | 6/17/26 8:00 | 6/17/26 5:00 | 5/19/26 10:29 | 5/20/26 10:29 | 0d | -20.69d | 0ed | 0 | NA | NA | July 2, 2026 10:00 | July 3, 2026 10:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
111 | 893 | Yes | Auto Scheduled | Security Transports | 1d | Fixed Units | 6 | 0.5d | 108,107 | June 15, 2026 8:00 | June 15, 2026 5:00 | 6/15/26 8:00 | 6/15/26 5:00 | 4/23/26 2:59 | 4/24/26 2:59 | 0d | -36.25d | 0ed | 0 | NA | NA | July 3, 2026 10:00 | July 3, 2026 3:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 8h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
112 | 894 | Yes | Auto Scheduled | Security Manual Tasks | 1d | Fixed Units | 6 | 1d | 111 | June 16, 2026 8:00 | June 16, 2026 5:00 | 6/16/26 8:00 | 6/16/26 5:00 | 5/19/26 10:29 | 5/20/26 10:29 | 0d | -19.69d | 0ed | 0 | NA | NA | July 3, 2026 3:00 | July 6, 2026 3:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.8 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
113 | 895 | Yes | Auto Scheduled | Manual Technical Tasks | 1d | Fixed Units | 6 | 1d | 111SS | June 15, 2026 8:00 | June 15, 2026 5:00 | 6/15/26 8:00 | 6/15/26 5:00 | 4/23/26 2:59 | 4/24/26 2:59 | 0d | -36.25d | 0ed | 0 | NA | NA | July 3, 2026 3:00 | July 6, 2026 3:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.9 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
114 | 896 | Yes | Auto Scheduled | Validate Fiori | 1d | Fixed Units | 6 | 0.5d | 113 | June 16, 2026 8:00 | June 16, 2026 5:00 | 6/16/26 8:00 | 6/16/26 5:00 | 4/24/26 2:59 | 4/27/26 2:59 | 0d | -36.25d | 0ed | 0 | NA | NA | July 6, 2026 3:00 | July 7, 2026 10:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 8h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.10 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
115 | 897 | Yes | Auto Scheduled | Fiori App Activation | 1d | Fixed Units | 6 | 0.75d | 114SS | June 16, 2026 8:00 | June 16, 2026 5:00 | 6/16/26 8:00 | 6/16/26 5:00 | 5/19/26 10:29 | 5/20/26 10:29 | 0d | -19.69d | 0ed | 0 | NA | NA | July 7, 2026 10:00 | July 7, 2026 5:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 8h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.11 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
116 | 898 | Yes | Auto Scheduled | Download Transport List | 1h | Fixed Units | 6 | 0.13d | 114SS | June 16, 2026 8:00 | June 16, 2026 9:00 | 6/16/26 8:00 | 6/16/26 9:00 | 5/20/26 9:29 | 5/20/26 10:29 | 0h | -150.52h | 0ed | 0 | NA | NA | July 7, 2026 10:00 | July 7, 2026 11:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.12 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
117 | 899 | Yes | Auto Scheduled | Business Functions Validation | 1d | Fixed Units | 6 | 1d | 114SS | June 16, 2026 8:00 | June 16, 2026 5:00 | 6/16/26 8:00 | 6/16/26 5:00 | 4/24/26 2:59 | 4/27/26 2:59 | 0d | -36.25d | 0ed | 0 | NA | NA | July 7, 2026 10:00 | July 8, 2026 10:00 | Start No Earlier Than | 1/5/26 8:00 | NA | NA | 3/31/26 7:17 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.13 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
118 | 900 | Yes | Auto Scheduled | Functional Leads Validation of Transport List | 1d | Fixed Units | 6 | 0.13d | 117SS | June 16, 2026 8:00 | June 16, 2026 5:00 | 6/16/26 8:00 | 6/16/26 5:00 | 4/24/26 2:59 | 4/27/26 2:59 | 0d | -36.25d | 0ed | 0 | NA | NA | July 7, 2026 11:00 | July 7, 2026 12:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 8h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.14 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
119 | 901 | Yes | Auto Scheduled | Release Security roles to Functional Team | 1h | Fixed Units | 6 | 0.13d | 118 | June 17, 2026 8:00 | June 17, 2026 9:00 | 6/17/26 8:00 | 6/17/26 9:00 | 4/27/26 2:59 | 4/27/26 3:59 | 0h | -290.02h | 0ed | 0 | NA | NA | July 7, 2026 1:00 | July 7, 2026 2:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.1.15 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
120 | 902 | Yes | Auto Scheduled | Release Transports to Client | 5.5d | Fixed Duration | 5 | 5.25d | 117SS | June 17, 2026 8:00 | June 24, 2026 12:00 | 6/17/26 8:00 | 6/24/26 12:00 | 4/27/26 2:59 | 5/5/26 9:59 | 0d | -36.25d | 0ed | 0 | NA | NA | July 7, 2026 1:00 | July 14, 2026 3:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 46h | 42h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.2 | 500 | No | Yes | Yes |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
121 | 903 | Yes | Auto Scheduled | Import Group 1 - Ent Structure | 2h | Fixed Units | 6 | 0.25d | 119SS | June 17, 2026 8:00 | June 17, 2026 10:00 | 6/17/26 8:00 | 6/17/26 10:00 | 4/27/26 2:59 | 4/27/26 4:59 | 0h | -290.02h | 0ed | 0 | NA | NA | July 7, 2026 1:00 | July 7, 2026 3:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.2.1 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
122 | 904 | Yes | Auto Scheduled | Manual activities group 1 | 20h | Fixed Units | 6 | 2.5d | 121 | June 17, 2026 10:00 | June 19, 2026 3:00 | 6/17/26 10:00 | 6/19/26 3:00 | 4/27/26 4:59 | 4/30/26 11:59 | 0h | -290.02h | 0ed | 0 | NA | NA | July 7, 2026 3:00 | July 10, 2026 10:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 20h | 20h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.2.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
123 | 905 | Yes | Auto Scheduled | Import Group 2 - Core Transports | 2h | Fixed Units | 6 | 0.25d | 122 | June 19, 2026 3:00 | June 19, 2026 5:00 | 6/19/26 3:00 | 6/19/26 5:00 | 4/30/26 11:59 | 4/30/26 2:59 | 0h | -290.02h | 0ed | 0 | NA | NA | July 10, 2026 10:00 | July 10, 2026 12:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.2.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
124 | 906 | Yes | Auto Scheduled | Manual activities group 2 | 1d | Fixed Units | 6 | 1d | 123 | June 22, 2026 8:00 | June 22, 2026 5:00 | 6/22/26 8:00 | 6/22/26 5:00 | 4/30/26 2:59 | 5/1/26 2:59 | 0d | -36.25d | 0ed | 0 | NA | NA | July 10, 2026 1:00 | July 13, 2026 12:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.2.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
125 | 907 | Yes | Auto Scheduled | Import Group 3 - prior to transactions | 2h | Fixed Units | 6 | 0.25d | 124 | June 23, 2026 8:00 | June 23, 2026 10:00 | 6/23/26 8:00 | 6/23/26 10:00 | 5/1/26 2:59 | 5/1/26 4:59 | 0h | -290.02h | 0ed | 0 | NA | NA | July 13, 2026 1:00 | July 13, 2026 3:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.2.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
126 | 908 | Yes | Auto Scheduled | Manual Activities Group 3 | 1d | Fixed Units | 6 | 1d | 125 | June 23, 2026 10:00 | June 24, 2026 10:00 | 6/23/26 10:00 | 6/24/26 10:00 | 5/1/26 4:59 | 5/4/26 4:59 | 0d | -36.25d | 0ed | 0 | NA | NA | July 13, 2026 3:00 | July 14, 2026 3:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.2.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
127 | 909 | Yes | Auto Scheduled | Import Group 4 - workbench / dev work | 2h | Fixed Units | 6 | 0.25d | 126 | June 24, 2026 10:00 | June 24, 2026 12:00 | 6/24/26 10:00 | 6/24/26 12:00 | 5/4/26 4:59 | 5/5/26 9:59 | 0h | -290.02h | 0ed | 0 | NA | NA | July 14, 2026 3:00 | July 14, 2026 5:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.2.7 | 500 | No | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
128 | 910 | Yes | Auto Scheduled | Import Group 5 - Config to support dev workbench | 2h | Fixed Units | 6 | 0.25d | 127SS | June 24, 2026 10:00 | June 24, 2026 12:00 | 6/24/26 10:00 | 6/24/26 12:00 | 5/4/26 4:59 | 5/5/26 9:59 | 0h | -290.02h | 0ed | 0 | NA | NA | July 15, 2026 8:00 | July 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.2.8 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
129 | 1227 | Yes | Auto Scheduled | Data Project Create | 0.5d | Fixed Duration | 5 | 1.06d |  | June 24, 2026 1:00 | June 24, 2026 5:00 | 6/24/26 1:00 | 6/24/26 5:00 | 5/19/26 3:29 | 5/20/26 10:29 | 0d | -25.69d | 0ed | 0 | NA | NA | July 15, 2026 10:00 | July 16, 2026 10:30 | As Soon As Possible | NA | NA | NA | 4/8/26 9:03 | 4.5h | 8.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.3 | 500 | No | Yes | Yes |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | Yes | 0 | 0 | 0 | 0 | 0
130 | 1228 | Yes | Auto Scheduled | Open Client | 15m | Fixed Units | 6 | 0.03d | 128 | June 24, 2026 1:00 | June 24, 2026 1:15 | 6/24/26 1:00 | 6/24/26 1:15 | 5/19/26 3:29 | 5/19/26 3:44 | 0m | -12331m | 0ed | 0 | NA | NA | July 15, 2026 10:00 | July 15, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/8/26 9:03 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.3.1 | 500 | No | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
131 | 1229 | Yes | Auto Scheduled | Create Migration Data Project in DMC | 4h | Fixed Units | 6 | 1d | 130SS | June 24, 2026 1:00 | June 24, 2026 5:00 | 6/24/26 1:00 | 6/24/26 5:00 | 5/19/26 3:29 | 5/20/26 10:29 | 0h | -205.52h | 0ed | 0 | NA | NA | July 15, 2026 10:15 | July 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/8/26 9:03 | 4h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.3.2 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
132 | 1230 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 6 | 0.03d | 130 | June 24, 2026 1:15 | June 24, 2026 1:30 | 6/24/26 1:15 | 6/24/26 1:30 | 5/20/26 10:14 | 5/20/26 10:29 | 0m | -12121m | 0ed | 0 | NA | NA | July 16, 2026 10:15 | July 16, 2026 10:30 | As Soon As Possible | NA | NA | NA | 4/8/26 9:03 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.3.3 | 500 | No | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
133 | 912 | Yes | Auto Scheduled | Environment Ready for Build | 0m | Fixed Units | 5 | 0d | 132 | June 24, 2026 1:30 | June 24, 2026 1:30 | 6/24/26 1:30 | 6/24/26 1:30 | 5/20/26 10:29 | 5/20/26 10:29 | 0m | -12121m | 0ed | 0 | NA | NA | March 13, 2025 8:00 | March 13, 2025 8:00 | As Soon As Possible | NA | NA | NA | 3/31/26 7:17 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.7.4 | 500 | Yes | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | Yes | 0 | 0 | 0 | 0 | 0
134 | 3367 | Yes | Auto Scheduled | P? Production System | 13.06d | Fixed Duration | 4 | 350.31d |  | September 7, 2026 8:00 | September 24, 2026 8:30 | 9/7/26 8:00 | 9/24/26 8:30 | 5/5/26 9:59 | 9/8/26 5:00 | 0d | -88.75d | 0ed | 0 | NA | NA | March 13, 2025 8:00 | July 16, 2026 10:30 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 180.5h | 177.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
135 | 3368 | Yes | Auto Scheduled | System Setup | 8d | Fixed Duration | 5 | 0d | 120 | September 7, 2026 8:00 | September 16, 2026 5:00 | 9/7/26 8:00 | 9/16/26 5:00 | 5/5/26 9:59 | 9/8/26 5:00 | 0d | -88.75d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 130h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
136 | 3369 | Yes | Auto Scheduled | System Refresh Basis(Workinig with NS2) | 2d | Fixed Units | 6 | 0.13d |  | September 7, 2026 8:00 | September 8, 2026 5:00 | 9/7/26 8:00 | 9/8/26 5:00 | 9/7/26 8:00 | 9/8/26 5:00 | 0d | 0d | 0ed | 0 | NA | NA | June 19, 2026 8:00 | June 19, 2026 9:00 | Must Start On | 9/7/26 8:00 | NA | NA | 4/30/26 1:10 | 16h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.1 | 500 | No | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | Yes | 0 | 0 | 0 | 0 | 0
137 | 3370 | Yes | Auto Scheduled | Client Config / Validation | 2d | Fixed Units | 6 | 1d | 136 | September 9, 2026 8:00 | September 10, 2026 5:00 | 9/9/26 8:00 | 9/10/26 5:00 | 5/5/26 9:59 | 5/7/26 9:59 | 0d | -90.75d | 0ed | 0 | NA | NA | June 26, 2026 10:00 | June 29, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 16h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
138 | 3371 | Yes | Auto Scheduled | Technical Transports / BP Setup | 1d | Fixed Units | 6 | 1d | 137 | September 11, 2026 8:00 | September 11, 2026 5:00 | 9/11/26 8:00 | 9/11/26 5:00 | 5/7/26 9:59 | 5/8/26 9:59 | 0d | -90.75d | 0ed | 0 | NA | NA | June 29, 2026 10:00 | June 30, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
139 | 3372 | Yes | Auto Scheduled | Best Practice / Country Validation | 1d | Fixed Units | 6 | 1d | 137 | September 11, 2026 8:00 | September 11, 2026 5:00 | 9/11/26 8:00 | 9/11/26 5:00 | 5/7/26 9:59 | 5/8/26 9:59 | 0d | -90.75d | 0ed | 0 | NA | NA | June 30, 2026 10:00 | July 1, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
140 | 3373 | Yes | Auto Scheduled | Connect Systems and Validate | 2d | Fixed Units | 6 | 1d | 139 | September 14, 2026 8:00 | September 15, 2026 5:00 | 9/14/26 8:00 | 9/15/26 5:00 | 5/15/26 10:29 | 5/19/26 10:29 | 0d | -85.69d | 0ed | 0 | NA | NA | July 1, 2026 10:00 | July 2, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 16h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
141 | 3374 | Yes | Auto Scheduled | Validate Syniti Connections to QS5 | 1d | Fixed Units | 6 | 1d | 140 | September 16, 2026 8:00 | September 16, 2026 5:00 | 9/16/26 8:00 | 9/16/26 5:00 | 5/19/26 10:29 | 5/20/26 10:29 | 0d | -85.69d | 0ed | 0 | NA | NA | July 2, 2026 10:00 | July 3, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
142 | 3375 | Yes | Auto Scheduled | Security Transports | 1d | Fixed Units | 6 | 0.5d | 138,139 | September 14, 2026 8:00 | September 14, 2026 5:00 | 9/14/26 8:00 | 9/14/26 5:00 | 5/8/26 9:59 | 5/11/26 9:59 | 0d | -90.75d | 0ed | 0 | NA | NA | July 3, 2026 10:00 | July 3, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 8h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
143 | 3376 | Yes | Auto Scheduled | Security Manual Tasks | 1d | Fixed Units | 6 | 1d | 142 | September 15, 2026 8:00 | September 15, 2026 5:00 | 9/15/26 8:00 | 9/15/26 5:00 | 5/19/26 10:29 | 5/20/26 10:29 | 0d | -84.69d | 0ed | 0 | NA | NA | July 3, 2026 3:00 | July 6, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.8 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
144 | 3377 | Yes | Auto Scheduled | Manual Technical Tasks | 1d | Fixed Units | 6 | 1d | 142SS | September 14, 2026 8:00 | September 14, 2026 5:00 | 9/14/26 8:00 | 9/14/26 5:00 | 5/8/26 9:59 | 5/11/26 9:59 | 0d | -90.75d | 0ed | 0 | NA | NA | July 3, 2026 3:00 | July 6, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.9 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
145 | 3378 | Yes | Auto Scheduled | Validate Fiori | 1d | Fixed Units | 6 | 0.5d | 144 | September 15, 2026 8:00 | September 15, 2026 5:00 | 9/15/26 8:00 | 9/15/26 5:00 | 5/11/26 9:59 | 5/12/26 9:59 | 0d | -90.75d | 0ed | 0 | NA | NA | July 6, 2026 3:00 | July 7, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 8h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.10 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
146 | 3379 | Yes | Auto Scheduled | Fiori App Activation | 1d | Fixed Units | 6 | 0.75d | 145SS | September 15, 2026 8:00 | September 15, 2026 5:00 | 9/15/26 8:00 | 9/15/26 5:00 | 5/19/26 10:29 | 5/20/26 10:29 | 0d | -84.69d | 0ed | 0 | NA | NA | July 7, 2026 10:00 | July 7, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 8h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.11 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
147 | 3380 | Yes | Auto Scheduled | Download Transport List | 1h | Fixed Units | 6 | 0.13d | 145 | September 16, 2026 8:00 | September 16, 2026 9:00 | 9/16/26 8:00 | 9/16/26 9:00 | 5/20/26 9:29 | 5/20/26 10:29 | 0h | -678.52h | 0ed | 0 | NA | NA | July 7, 2026 10:00 | July 7, 2026 11:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.12 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
148 | 3381 | Yes | Auto Scheduled | Business Functions Validation | 1d | Fixed Units | 6 | 1d | 145SS | September 15, 2026 8:00 | September 15, 2026 5:00 | 9/15/26 8:00 | 9/15/26 5:00 | 5/19/26 10:29 | 5/20/26 10:29 | 0d | -84.69d | 0ed | 0 | NA | NA | July 7, 2026 10:00 | July 8, 2026 10:00 | Start No Earlier Than | 1/5/26 8:00 | NA | NA | 4/30/26 1:10 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.13 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
149 | 3382 | Yes | Auto Scheduled | Functional Leads Validation of Transport List | 1d | Fixed Units | 6 | 0.13d | 145SS | September 15, 2026 8:00 | September 15, 2026 5:00 | 9/15/26 8:00 | 9/15/26 5:00 | 5/11/26 9:59 | 5/12/26 9:59 | 0d | -90.75d | 0ed | 0 | NA | NA | July 7, 2026 11:00 | July 7, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 8h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.14 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
150 | 3383 | Yes | Auto Scheduled | Release Security roles to Functional Team | 1h | Fixed Units | 6 | 0.13d | 149 | September 16, 2026 8:00 | September 16, 2026 9:00 | 9/16/26 8:00 | 9/16/26 9:00 | 5/20/26 9:29 | 5/20/26 10:29 | 0h | -678.52h | 0ed | 0 | NA | NA | July 7, 2026 1:00 | July 7, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.1.15 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
151 | 3384 | Yes | Auto Scheduled | Release Transports to Client | 5.5d | Fixed Duration | 5 | 5.25d | 149 | September 16, 2026 8:00 | September 23, 2026 12:00 | 9/16/26 8:00 | 9/23/26 12:00 | 5/12/26 9:59 | 5/19/26 2:59 | 0d | -90.75d | 0ed | 0 | NA | NA | July 7, 2026 1:00 | July 14, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 46h | 42h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.2 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
152 | 3385 | Yes | Auto Scheduled | Import Group 1 - Ent Structure | 2h | Fixed Units | 6 | 0.25d | 149 | September 16, 2026 8:00 | September 16, 2026 10:00 | 9/16/26 8:00 | 9/16/26 10:00 | 5/12/26 9:59 | 5/12/26 11:59 | 0h | -726.02h | 0ed | 0 | NA | NA | July 7, 2026 1:00 | July 7, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.2.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
153 | 3386 | Yes | Auto Scheduled | Manual activities group 1 | 20h | Fixed Units | 6 | 2.5d | 152 | September 16, 2026 10:00 | September 18, 2026 3:00 | 9/16/26 10:00 | 9/18/26 3:00 | 5/12/26 11:59 | 5/14/26 4:59 | 0h | -726.02h | 0ed | 0 | NA | NA | July 7, 2026 3:00 | July 10, 2026 10:00 | Finish No Earlier Than | 2/11/26 5:00 | NA | NA | 4/30/26 1:10 | 20h | 20h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.2.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
154 | 3387 | Yes | Auto Scheduled | Import Group 2 - Core Transports | 2h | Fixed Units | 6 | 0.25d | 153 | September 18, 2026 3:00 | September 18, 2026 5:00 | 9/18/26 3:00 | 9/18/26 5:00 | 5/14/26 4:59 | 5/15/26 9:59 | 0h | -726.02h | 0ed | 0 | NA | NA | July 10, 2026 10:00 | July 10, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.2.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
155 | 3388 | Yes | Auto Scheduled | Manual activities group 2 | 1d | Fixed Units | 6 | 1d | 154 | September 21, 2026 8:00 | September 21, 2026 5:00 | 9/21/26 8:00 | 9/21/26 5:00 | 5/15/26 9:59 | 5/18/26 9:59 | 0d | -90.75d | 0ed | 0 | NA | NA | July 10, 2026 1:00 | July 13, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.2.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
156 | 3389 | Yes | Auto Scheduled | Import Group 3 - prior to transactions | 2h | Fixed Units | 6 | 0.25d | 155 | September 22, 2026 8:00 | September 22, 2026 10:00 | 9/22/26 8:00 | 9/22/26 10:00 | 5/18/26 9:59 | 5/18/26 11:59 | 0h | -726.02h | 0ed | 0 | NA | NA | July 13, 2026 1:00 | July 13, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.2.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
157 | 3390 | Yes | Auto Scheduled | Manual Activities Group 3 | 1d | Fixed Units | 6 | 1d | 156 | September 22, 2026 10:00 | September 23, 2026 10:00 | 9/22/26 10:00 | 9/23/26 10:00 | 5/18/26 11:59 | 5/19/26 11:59 | 0d | -90.75d | 0ed | 0 | NA | NA | July 13, 2026 3:00 | July 14, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 8h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.2.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
158 | 3391 | Yes | Auto Scheduled | Import Group 4 - workbench / dev work | 2h | Fixed Units | 6 | 0.25d | 157 | September 23, 2026 10:00 | September 23, 2026 12:00 | 9/23/26 10:00 | 9/23/26 12:00 | 5/19/26 11:59 | 5/19/26 2:59 | 0h | -726.02h | 0ed | 0 | NA | NA | July 14, 2026 3:00 | July 14, 2026 5:00 | Start No Earlier Than | 4/3/25 8:00 | NA | NA | 4/30/26 1:10 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.2.7 | 500 | No | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
159 | 3392 | Yes | Auto Scheduled | Import Group 5 - Config to support dev workbench | 2h | Fixed Units | 6 | 0.25d | 158SS | September 23, 2026 10:00 | September 23, 2026 12:00 | 9/23/26 10:00 | 9/23/26 12:00 | 5/19/26 11:59 | 5/19/26 2:59 | 0h | -726.02h | 0ed | 0 | NA | NA | July 15, 2026 8:00 | July 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.2.8 | 500 | No | No | No |  |  | Black | SS_OPT | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | Yes | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
160 | 3393 | Yes | Auto Scheduled | Data Project Create | 0.56d | Fixed Duration | 5 | 1.06d |  | September 23, 2026 1:00 | September 24, 2026 8:30 | 9/23/26 1:00 | 9/24/26 8:30 | 5/19/26 2:59 | 5/20/26 10:29 | 0d | -90.75d | 0ed | 0 | NA | NA | July 15, 2026 10:00 | July 16, 2026 10:30 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 4.5h | 8.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.3 | 500 | No | Yes | Yes |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | Yes | 0 | 0 | 0 | 0 | 0
161 | 3394 | Yes | Auto Scheduled | Open Client | 15m | Fixed Units | 6 | 0.03d | 159 | September 23, 2026 1:00 | September 23, 2026 1:15 | 9/23/26 1:00 | 9/23/26 1:15 | 5/19/26 2:59 | 5/19/26 3:14 | 0m | -43561m | 0ed | 0 | NA | NA | July 15, 2026 10:00 | July 15, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.3.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
162 | 3395 | Yes | Auto Scheduled | Create Migration Data Project in DMC | 4h | Fixed Units | 6 | 1d | 161 | September 23, 2026 1:15 | September 24, 2026 8:15 | 9/23/26 1:15 | 9/24/26 8:15 | 5/19/26 3:14 | 5/20/26 10:14 | 0h | -726.02h | 0ed | 0 | NA | NA | July 15, 2026 10:15 | July 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 4h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.3.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
163 | 3396 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 6 | 0.03d | 162 | September 24, 2026 8:15 | September 24, 2026 8:30 | 9/24/26 8:15 | 9/24/26 8:30 | 5/20/26 10:14 | 5/20/26 10:29 | 0m | -43561m | 0ed | 0 | NA | NA | July 16, 2026 10:15 | July 16, 2026 10:30 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.3.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
164 | 3397 | Yes | Auto Scheduled | Environment Ready for Build | 0m | Fixed Units | 5 | 0d | 160 | September 24, 2026 8:30 | September 24, 2026 8:30 | 9/24/26 8:30 | 9/24/26 8:30 | 5/20/26 10:29 | 5/20/26 10:29 | 0m | -43561m | 0ed | 0 | NA | NA | March 13, 2025 8:00 | March 13, 2025 8:00 | As Soon As Possible | NA | NA | NA | 4/30/26 1:10 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.8.4 | 500 | Yes | No | No |  |  | Black | CRITICAL | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | Yes | 0 | 0 | 0 | 0 | 0
165 | 201 | Yes | Auto Scheduled | Prod (PS4) Setup | 17d | Fixed Duration | 4 | 17.38d |  | September 7, 2026 8:00 | September 29, 2026 5:00 | 9/7/26 8:00 | 9/29/26 5:00 | 10/16/26 8:00 | 11/9/26 5:00 | 29d | 29d | 0ed | 0 | NA | NA | March 13, 2025 8:00 | April 7, 2025 11:00 | Start No Earlier Than | 9/7/26 8:00 | NA | NA | 6/17/25 2:45 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.1.9 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
166 | 248 | Yes | Auto Scheduled | GRC Security Utility | 439d? | Fixed Duration | 3 | 296d |  | February 17, 2025 8:00 | October 22, 2026 5:00 | 2/17/25 8:00 | 10/22/26 5:00 | 2/17/25 8:00 | 11/9/26 5:00 | 12d? | 12d? | 0ed | 0.88 | 2/17/25 8:00 | NA | February 17, 2025 8:00 | April 6, 2026 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 7/14/25 9:04 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.2 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
167 | 299 | Yes | Auto Scheduled | Initiation & Planning | 262d | Fixed Duration | 4 | 262d |  | February 17, 2025 8:00 | February 17, 2026 5:00 | 2/17/25 8:00 | 2/17/26 5:00 | 2/17/25 8:00 | 2/17/26 5:00 | 0d | 0d | 0ed | 1 | 2/17/25 8:00 | 2/17/26 5:00 | February 17, 2025 8:00 | February 17, 2026 5:00 | As Soon As Possible | NA | 7/16/25 5:00 | 7/16/25 5:00 | 7/16/25 4:43 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.1 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
168 | 249 | Yes | Auto Scheduled | Project kickoff | 1d | Fixed Units | 5 | 1d |  | July 16, 2025 8:00 | July 16, 2025 5:00 | 7/16/25 8:00 | 7/16/25 5:00 | 7/16/25 8:00 | 7/16/25 5:00 | 0d | 0d | 0ed | 1 | 7/16/25 8:00 | 7/16/25 5:00 | July 16, 2025 8:00 | July 16, 2025 5:00 | Start No Earlier Than | 7/16/25 8:00 | 7/16/25 5:00 | 7/16/25 5:00 | 7/14/25 9:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.1.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
169 | 250 | Yes | Auto Scheduled | Requirement gathering | 130d | Fixed Units | 5 | 130d |  | February 17, 2025 8:00 | August 15, 2025 5:00 | 2/17/25 8:00 | 8/15/25 5:00 | 2/17/25 8:00 | 8/15/25 5:00 | 0d | 0d | 0ed | 1 | 2/17/25 8:00 | 8/15/25 5:00 | February 17, 2025 8:00 | August 15, 2025 5:00 | Start No Earlier Than | 2/16/25 8:00 | 8/15/25 5:00 | 8/15/25 5:00 | 7/14/25 9:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.1.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
170 | 251 | Yes | Auto Scheduled | Landscape design | 2d | Fixed Units | 5 | 2d | 169 | August 18, 2025 8:00 | August 19, 2025 5:00 | 8/18/25 8:00 | 8/19/25 5:00 | 8/18/25 8:00 | 8/19/25 5:00 | 0d | 0d | 0ed | 1 | 8/18/25 8:00 | 8/19/25 5:00 | August 18, 2025 8:00 | August 19, 2025 5:00 | Finish No Earlier Than | 8/19/25 5:00 | 8/19/25 5:00 | 8/19/25 5:00 | 7/14/25 9:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.1.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
171 | 252 | Yes | Auto Scheduled | Project plan finalization | 2d | Fixed Units | 5 | 2d |  | February 16, 2026 8:00 | February 17, 2026 5:00 | 2/16/26 8:00 | 2/17/26 5:00 | 2/16/26 8:00 | 2/17/26 5:00 | 0d | 0d | 0ed | 1 | 2/16/26 8:00 | 2/17/26 5:00 | February 16, 2026 8:00 | February 17, 2026 5:00 | Start No Earlier Than | 2/16/26 8:00 | 2/17/26 5:00 | 2/17/26 5:00 | 7/14/25 9:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.1.4 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
172 | 253 | Yes | Auto Scheduled | System Setup & Connectivity | 171d | Fixed Duration | 4 | 171d |  | July 28, 2025 8:00 | March 23, 2026 5:00 | 7/28/25 8:00 | 3/23/26 5:00 | 7/28/25 8:00 | 3/23/26 5:00 | 0d | 0d | 0ed | 1 | 7/28/25 8:00 | 3/23/26 5:00 | July 28, 2025 8:00 | March 23, 2026 5:00 | As Soon As Possible | NA | 8/1/25 5:00 | 8/1/25 5:00 | 7/14/25 9:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.2 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
173 | 254 | Yes | Auto Scheduled | Install GRC AC components | 5d | Fixed Units | 5 | 5d |  | July 28, 2025 8:00 | August 1, 2025 5:00 | 7/28/25 8:00 | 8/1/25 5:00 | 7/28/25 8:00 | 8/1/25 5:00 | 0d | 0d | 0ed | 1 | 7/28/25 8:00 | 8/1/25 5:00 | July 28, 2025 8:00 | August 1, 2025 5:00 | Start No Earlier Than | 7/28/25 8:00 | 8/1/25 5:00 | 8/1/25 5:00 | 7/14/25 9:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.2.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
174 | 258 | Yes | Auto Scheduled | Install plug-ins on target systems | 5d | Fixed Units | 5 | 5d | 171 | February 18, 2026 8:00 | February 24, 2026 5:00 | 2/18/26 8:00 | 2/24/26 5:00 | 2/18/26 8:00 | 2/24/26 5:00 | 0d | 0d | 0ed | 1 | 2/18/26 8:00 | 2/24/26 5:00 | February 18, 2026 8:00 | February 24, 2026 5:00 | As Soon As Possible | NA | 2/24/26 5:00 | 2/24/26 5:00 | 7/16/25 4:39 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.2.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
175 | 259 | Yes | Auto Scheduled | Post installation Steps | 5d | Fixed Units | 5 | 5d | 174 | February 25, 2026 8:00 | March 3, 2026 5:00 | 2/25/26 8:00 | 3/3/26 5:00 | 2/25/26 8:00 | 3/3/26 5:00 | 0d | 0d | 0ed | 1 | 2/25/26 8:00 | 3/3/26 5:00 | February 25, 2026 8:00 | March 3, 2026 5:00 | As Soon As Possible | NA | 3/3/26 5:00 | 3/3/26 5:00 | 7/16/25 4:39 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.2.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
176 | 260 | Yes | Auto Scheduled | Activate BC Sets | 2d | Fixed Units | 5 | 2d | 175 | March 4, 2026 8:00 | March 5, 2026 5:00 | 3/4/26 8:00 | 3/5/26 5:00 | 3/4/26 8:00 | 3/5/26 5:00 | 0d | 0d | 0ed | 1 | 3/4/26 8:00 | 3/5/26 5:00 | March 4, 2026 8:00 | March 5, 2026 5:00 | As Soon As Possible | NA | 3/5/26 5:00 | 3/5/26 5:00 | 7/16/25 4:39 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.2.4 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
177 | 261 | Yes | Auto Scheduled | Connector configuration (S4 / LDAP Connector) | 5d | Fixed Units | 5 | 5d | 176 | March 6, 2026 8:00 | March 12, 2026 5:00 | 3/6/26 8:00 | 3/12/26 5:00 | 3/6/26 8:00 | 3/12/26 5:00 | 0d | 0d | 0ed | 1 | 3/6/26 8:00 | 3/12/26 5:00 | March 6, 2026 8:00 | March 12, 2026 5:00 | As Soon As Possible | NA | 3/12/26 5:00 | 3/12/26 5:00 | 7/16/25 4:39 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.2.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
178 | 262 | Yes | Auto Scheduled | Initial configuration [GRC Parameter/Business Process/Sub Process and system Configuration] | 6d | Fixed Units | 5 | 6d | 177 | March 13, 2026 8:00 | March 20, 2026 5:00 | 3/13/26 8:00 | 3/20/26 5:00 | 3/13/26 8:00 | 3/20/26 5:00 | 0d | 0d | 0ed | 1 | 3/13/26 8:00 | 3/20/26 5:00 | March 13, 2026 8:00 | March 20, 2026 5:00 | As Soon As Possible | NA | 3/20/26 5:00 | 3/20/26 5:00 | 7/16/25 4:39 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.2.6 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
179 | 263 | Yes | Auto Scheduled | Transport setup | 1d | Fixed Units | 5 | 1d | 178 | March 23, 2026 8:00 | March 23, 2026 5:00 | 3/23/26 8:00 | 3/23/26 5:00 | 3/23/26 8:00 | 3/23/26 5:00 | 0d | 0d | 0ed | 1 | 3/23/26 8:00 | 3/23/26 5:00 | March 23, 2026 8:00 | March 23, 2026 5:00 | As Soon As Possible | NA | 3/23/26 5:00 | 3/23/26 5:00 | 7/16/25 4:39 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.2.7 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
180 | 264 | Yes | Auto Scheduled | Workflow setup | 10d | Fixed Duration | 4 | 10d |  | March 24, 2026 8:00 | April 6, 2026 5:00 | 3/24/26 8:00 | 4/6/26 5:00 | 3/24/26 8:00 | 4/6/26 5:00 | 0d | 0d | 0ed | 1 | 3/24/26 8:00 | 4/6/26 5:00 | March 24, 2026 8:00 | April 6, 2026 5:00 | As Soon As Possible | NA | 3/30/26 5:00 | 3/30/26 5:00 | 7/16/25 4:39 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.3 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
181 | 265 | Yes | Auto Scheduled | MSMP workflow configuration | 5d | Fixed Units | 5 | 5d | 179 | March 24, 2026 8:00 | March 30, 2026 5:00 | 3/24/26 8:00 | 3/30/26 5:00 | 3/24/26 8:00 | 3/30/26 5:00 | 0d | 0d | 0ed | 1 | 3/24/26 8:00 | 3/30/26 5:00 | March 24, 2026 8:00 | March 30, 2026 5:00 | As Soon As Possible | NA | 3/30/26 5:00 | 3/30/26 5:00 | 7/16/25 4:39 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.3.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
182 | 266 | Yes | Auto Scheduled | BRF+ decision tables | 5d | Fixed Units | 5 | 5d | 181 | March 31, 2026 8:00 | April 6, 2026 5:00 | 3/31/26 8:00 | 4/6/26 5:00 | 3/31/26 8:00 | 4/6/26 5:00 | 0d | 0d | 0ed | 1 | 3/31/26 8:00 | 4/6/26 5:00 | March 31, 2026 8:00 | April 6, 2026 5:00 | As Soon As Possible | NA | 4/6/26 5:00 | 4/6/26 5:00 | 7/16/25 4:39 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.3.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
183 | 267 | Yes | Auto Scheduled | Rule Set & Role Design | 311d? | Fixed Duration | 4 | 195d |  | March 13, 2025 8:00 | May 21, 2026 5:00 | 3/13/25 8:00 | 5/21/26 5:00 | 3/13/25 8:00 | 11/9/26 5:00 | 122d? | 122d? | 0ed | 0.77000000000000002 | 3/13/25 8:00 | NA | March 13, 2025 8:00 | December 10, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 7/16/25 4:39 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.2.4 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
184 | 268 | Yes | Auto Scheduled | Extract the default Global Ruleset from SAP | 4d | Fixed Units | 5 | 4d |  | September 2, 2025 8:00 | September 5, 2025 5:00 | 9/2/25 8:00 | 9/5/25 5:00 | 9/2/25 8:00 | 9/5/25 5:00 | 0d | 0d | 0ed | 1 | 9/2/25 8:00 | 9/5/25 5:00 | September 2, 2025 8:00 | September 5, 2025 5:00 | Start No Earlier Than | 9/2/25 8:00 | 9/5/25 5:00 | 9/5/25 5:00 | 7/16/25 4:39 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.4.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
185 | 269 | Yes | Auto Scheduled | Extract SU24 Details of transactions from global ruleset and Custom Transactions | 7d | Fixed Units | 5 | 7d | 184 | September 8, 2025 8:00 | September 16, 2025 5:00 | 9/8/25 8:00 | 9/16/25 5:00 | 9/8/25 8:00 | 9/16/25 5:00 | 0d | 0d | 0ed | 1 | 9/8/25 8:00 | 9/16/25 5:00 | September 8, 2025 8:00 | September 16, 2025 5:00 | As Soon As Possible | NA | 9/16/25 5:00 | 9/16/25 5:00 | 7/16/25 4:39 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.4.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
186 | 281 | Yes | Auto Scheduled | Prepare/Share the Ruleset Draft with all the functional leads for inputs | 6d | Fixed Units | 5 | 6d | 185 | September 17, 2025 8:00 | September 24, 2025 5:00 | 9/17/25 8:00 | 9/24/25 5:00 | 9/17/25 8:00 | 9/24/25 5:00 | 0d | 0d | 0ed | 1 | 9/17/25 8:00 | 9/24/25 5:00 | September 17, 2025 8:00 | September 24, 2025 5:00 | As Soon As Possible | NA | 9/24/25 5:00 | 9/24/25 5:00 | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.4.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
187 | 282 | Yes | Auto Scheduled | Schedule workshops to collect complete details of ruleset module wise and close the gaps | 26d | Fixed Units | 5 | 26d | 186 | September 25, 2025 8:00 | October 30, 2025 5:00 | 9/25/25 8:00 | 10/30/25 5:00 | 9/25/25 8:00 | 10/30/25 5:00 | 0d | 0d | 0ed | 1 | 9/25/25 8:00 | 10/30/25 5:00 | September 25, 2025 8:00 | October 30, 2025 5:00 | As Soon As Possible | NA | 10/30/25 5:00 | 10/30/25 5:00 | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.4.4 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
188 | 283 | Yes | Auto Scheduled | Final Review Rule Set and update the recommendations | 4d | Fixed Units | 5 | 4d | 187 | October 31, 2025 8:00 | May 4, 2026 1:48 | 10/31/25 8:00 | 5/4/26 1:48 | 10/31/25 8:00 | 11/9/26 5:00 | 135.4d | 135.4d | 0ed | 0.59999999999999998 | 10/31/25 8:00 | NA | October 31, 2025 8:00 | November 5, 2025 5:00 | As Soon As Possible | NA | 11/4/25 11:12 | 5/1/26 8:00 | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.4.5 | 500 | No | No | No |  |  | Red | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
189 | 284 | Yes | Auto Scheduled | Import rulesets into system | 4d | Fixed Units | 5 | 4d | 188 | November 6, 2025 8:00 | November 11, 2025 5:00 | 11/6/25 8:00 | 11/11/25 5:00 | 11/6/25 8:00 | 11/11/25 5:00 | 0d | 0d | 0ed | 1 | 11/6/25 8:00 | 11/11/25 5:00 | November 6, 2025 8:00 | November 11, 2025 5:00 | As Soon As Possible | NA | 11/11/25 5:00 | 11/11/25 5:00 | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.4.6 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
190 | 303 | Yes | Auto Scheduled | RCM Development | 1d? | Fixed Units | 5 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d? | 0d? | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 7/18/25 8:44 | 8h | 8h | 8h | 0 | 0 | 0 | 0 | 0 | 1.1.2.4.7 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
191 | 285 | Yes | Auto Scheduled | Setup Mitigation controls | 6d | Fixed Units | 5 | 6d | 189 | November 12, 2025 8:00 | November 19, 2025 5:00 | 11/12/25 8:00 | 11/19/25 5:00 | 11/12/25 8:00 | 11/19/25 5:00 | 0d | 0d | 0ed | 1 | 11/12/25 8:00 | 11/19/25 5:00 | November 12, 2025 8:00 | November 19, 2025 5:00 | As Soon As Possible | NA | 11/19/25 5:00 | 11/19/25 5:00 | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.4.8 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
192 | 286 | Yes | Auto Scheduled | Risk analysis on existing roles | 5d | Fixed Units | 5 | 5d | 191 | May 1, 2026 8:00 | May 7, 2026 5:00 | 5/1/26 8:00 | 5/7/26 5:00 | 10/20/26 8:00 | 10/26/26 5:00 | 0d | 122d | 0ed | 0 | NA | NA | November 20, 2025 8:00 | November 26, 2025 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.4.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
193 | 270 | Yes | Auto Scheduled | Role remediation planning - Can impact role design & Possible of retesting. | 10d | Fixed Units | 5 | 10d | 192 | May 8, 2026 8:00 | May 21, 2026 5:00 | 5/8/26 8:00 | 5/21/26 5:00 | 10/27/26 8:00 | 11/9/26 5:00 | 122d | 122d | 0ed | 0 | NA | NA | November 27, 2025 8:00 | December 10, 2025 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.4.10 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
194 | 271 | Yes | Auto Scheduled | Business Role Management | 10d | Fixed Duration | 4 | 10d |  | May 8, 2026 8:00 | May 21, 2026 5:00 | 5/8/26 8:00 | 5/21/26 5:00 | 10/27/26 8:00 | 11/9/26 5:00 | 122d | 122d | 0ed | 0 | NA | NA | November 27, 2025 8:00 | December 10, 2025 5:00 | As Soon As Possible | NA | NA | NA | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.5 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
195 | 272 | Yes | Auto Scheduled | Role Mapping with Business Process and Sub-Process /Functional Area | 5d | Fixed Units | 5 | 5d | 192 | May 8, 2026 8:00 | May 14, 2026 5:00 | 5/8/26 8:00 | 5/14/26 5:00 | 10/27/26 8:00 | 11/2/26 5:00 | 0d | 122d | 0ed | 0 | NA | NA | November 27, 2025 8:00 | December 3, 2025 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.5.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
196 | 273 | Yes | Auto Scheduled | Role Upload to SAP GRC | 5d | Fixed Units | 5 | 5d | 195 | May 15, 2026 8:00 | May 21, 2026 5:00 | 5/15/26 8:00 | 5/21/26 5:00 | 11/3/26 8:00 | 11/9/26 5:00 | 122d | 122d | 0ed | 0 | NA | NA | December 4, 2025 8:00 | December 10, 2025 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.5.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
197 | 274 | Yes | Auto Scheduled | Firefighter Configuration | 15d | Fixed Duration | 4 | 15d |  | May 1, 2026 8:00 | May 21, 2026 5:00 | 5/1/26 8:00 | 5/21/26 5:00 | 10/20/26 8:00 | 11/9/26 5:00 | 122d | 122d | 0ed | 0 | NA | NA | October 20, 2025 8:00 | November 7, 2025 5:00 | As Soon As Possible | NA | NA | NA | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.6 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
198 | 275 | Yes | Auto Scheduled | Firefighter ID setup | 5d | Fixed Units | 5 | 5d |  | May 1, 2026 8:00 | May 7, 2026 5:00 | 5/1/26 8:00 | 5/7/26 5:00 | 10/20/26 8:00 | 10/26/26 5:00 | 0d | 122d | 0ed | 0 | NA | NA | October 20, 2025 8:00 | October 24, 2025 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.6.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
199 | 276 | Yes | Auto Scheduled | Firefighter log settings | 5d | Fixed Units | 5 | 5d | 198 | May 8, 2026 8:00 | May 14, 2026 5:00 | 5/8/26 8:00 | 5/14/26 5:00 | 10/27/26 8:00 | 11/2/26 5:00 | 0d | 122d | 0ed | 0 | NA | NA | October 27, 2025 8:00 | October 31, 2025 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.6.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
200 | 277 | Yes | Auto Scheduled | Functional validation | 5d | Fixed Units | 5 | 5d | 199 | May 15, 2026 8:00 | May 21, 2026 5:00 | 5/15/26 8:00 | 5/21/26 5:00 | 11/3/26 8:00 | 11/9/26 5:00 | 122d | 122d | 0ed | 0 | NA | NA | November 3, 2025 8:00 | November 7, 2025 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.6.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
201 | 278 | Yes | Auto Scheduled | Testing & Training | 69d | Fixed Duration | 4 | 69d |  | May 1, 2026 8:00 | August 5, 2026 5:00 | 5/1/26 8:00 | 8/5/26 5:00 | 8/5/26 8:00 | 11/9/26 5:00 | 68d | 68d | 0ed | 0 | NA | NA | November 10, 2025 8:00 | February 12, 2026 5:00 | As Soon As Possible | NA | NA | NA | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.7 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
202 | 279 | Yes | Auto Scheduled | Unit testing | 9d | Fixed Units | 5 | 9d |  | May 1, 2026 8:00 | May 13, 2026 5:00 | 5/1/26 8:00 | 5/13/26 5:00 | 8/5/26 8:00 | 8/17/26 5:00 | 0d | 68d | 0ed | 0 | NA | NA | November 10, 2025 8:00 | November 20, 2025 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.7.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
203 | 280 | Yes | Auto Scheduled | Changes moved to Test System | 3d | Fixed Units | 5 | 3d | 202 | May 14, 2026 8:00 | May 18, 2026 5:00 | 5/14/26 8:00 | 5/18/26 5:00 | 8/18/26 8:00 | 8/20/26 5:00 | 0d | 68d | 0ed | 0 | NA | NA | November 21, 2025 8:00 | November 25, 2025 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:40 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.7.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
204 | 287 | Yes | Auto Scheduled | Connector configuration (S4 / LDAP Connector) | 3d | Fixed Units | 5 | 3d | 203 | May 19, 2026 8:00 | May 21, 2026 5:00 | 5/19/26 8:00 | 5/21/26 5:00 | 8/21/26 8:00 | 8/25/26 5:00 | 0d | 68d | 0ed | 0 | NA | NA | November 26, 2025 8:00 | November 28, 2025 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.7.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
205 | 288 | Yes | Auto Scheduled | Workflow Activation / Data load in Test System | 5d | Fixed Units | 5 | 5d | 204 | May 22, 2026 8:00 | May 28, 2026 5:00 | 5/22/26 8:00 | 5/28/26 5:00 | 8/26/26 8:00 | 9/1/26 5:00 | 0d | 68d | 0ed | 0 | NA | NA | December 1, 2025 8:00 | December 5, 2025 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.7.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
206 | 289 | Yes | Auto Scheduled | Integration testing - Smoke Test | 9d | Fixed Units | 5 | 9d | 205 | May 29, 2026 8:00 | June 10, 2026 5:00 | 5/29/26 8:00 | 6/10/26 5:00 | 9/2/26 8:00 | 9/14/26 5:00 | 0d | 68d | 0ed | 0 | NA | NA | December 8, 2025 8:00 | December 18, 2025 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.7.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
207 | 290 | Yes | Auto Scheduled | UAT (User Acceptance Testing) - ITC-3 - with roles | 16d | Fixed Units | 5 | 16d | 206 | June 11, 2026 8:00 | July 2, 2026 5:00 | 6/11/26 8:00 | 7/2/26 5:00 | 9/15/26 8:00 | 10/6/26 5:00 | 0d | 68d | 0ed | 0 | NA | NA | December 19, 2025 8:00 | January 9, 2026 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.7.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
208 | 291 | Yes | Auto Scheduled | Issue resolution | 10d | Fixed Units | 5 | 10d | 207 | July 3, 2026 8:00 | July 16, 2026 5:00 | 7/3/26 8:00 | 7/16/26 5:00 | 10/7/26 8:00 | 10/20/26 5:00 | 0d | 68d | 0ed | 0 | NA | NA | January 12, 2026 8:00 | January 23, 2026 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.7.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
209 | 292 | Yes | Auto Scheduled | End-user training | 6d | Fixed Units | 5 | 6d | 208 | July 17, 2026 8:00 | July 24, 2026 5:00 | 7/17/26 8:00 | 7/24/26 5:00 | 10/21/26 8:00 | 10/28/26 5:00 | 0d | 68d | 0ed | 0 | NA | NA | January 26, 2026 8:00 | February 2, 2026 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.7.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
210 | 293 | Yes | Auto Scheduled | Initiate Preparation of Cutover Plans | 8d | Fixed Units | 5 | 8d | 209 | July 27, 2026 8:00 | August 5, 2026 5:00 | 7/27/26 8:00 | 8/5/26 5:00 | 10/29/26 8:00 | 11/9/26 5:00 | 68d | 68d | 0ed | 0 | NA | NA | February 3, 2026 8:00 | February 12, 2026 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 7/16/25 4:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.7.9 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
211 | 294 | Yes | Auto Scheduled | Go-Live | 16d | Fixed Duration | 4 | 16d |  | October 1, 2026 8:00 | October 22, 2026 5:00 | 10/1/26 8:00 | 10/22/26 5:00 | 10/1/26 8:00 | 11/9/26 5:00 | 0d | 0d | 0ed | 0 | NA | NA | January 1, 2026 8:00 | January 22, 2026 5:00 | Start No Earlier Than | 9/24/26 8:00 | NA | NA | 7/16/25 4:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.8 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
212 | 297 | Yes | Auto Scheduled | Production deployment | 7d | Fixed Units | 5 | 7d | 134 | October 1, 2026 8:00 | October 9, 2026 5:00 | 10/1/26 8:00 | 10/9/26 5:00 | 10/1/26 8:00 | 10/9/26 5:00 | 0d | 0d | 0ed | 0 | NA | NA | January 1, 2026 8:00 | January 9, 2026 5:00 | Must Start On | 10/1/26 8:00 | NA | NA | 7/16/25 4:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.8.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
213 | 295 | Yes | Auto Scheduled | Execution of Cutover Plan(Business and Technical) | 7d | Fixed Units | 5 | 7d | 212SS | October 1, 2026 8:00 | October 9, 2026 5:00 | 10/1/26 8:00 | 10/9/26 5:00 | 10/19/26 8:00 | 10/27/26 5:00 | 0d | 12d | 0ed | 0 | NA | NA | January 1, 2026 8:00 | January 9, 2026 5:00 | As Soon As Possible | NA | NA | NA | 7/16/25 4:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.8.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
214 | 296 | Yes | Auto Scheduled | Final risk analysis | 7d | Fixed Units | 5 | 7d | 213 | October 12, 2026 8:00 | October 20, 2026 5:00 | 10/12/26 8:00 | 10/20/26 5:00 | 10/28/26 8:00 | 11/5/26 5:00 | 0d | 12d | 0ed | 0 | NA | NA | January 12, 2026 8:00 | January 20, 2026 5:00 | As Soon As Possible | NA | NA | NA | 7/16/25 4:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.8.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
215 | 298 | Yes | Auto Scheduled | Go-live (Technical) | 2d | Fixed Units | 5 | 2d | 214 | October 21, 2026 8:00 | October 22, 2026 5:00 | 10/21/26 8:00 | 10/22/26 5:00 | 11/6/26 8:00 | 11/9/26 5:00 | 12d | 12d | 0ed | 0 | NA | NA | January 21, 2026 8:00 | January 22, 2026 5:00 | As Soon As Possible | NA | NA | NA | 7/16/25 4:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.8.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
216 | 24 | Yes | Auto Scheduled | Functional Build Tasks | 119d | Fixed Duration | 4 | 119d |  | April 7, 2025 8:00 | September 18, 2025 5:00 | 4/7/25 8:00 | 9/18/25 5:00 | 4/7/25 8:00 | 9/18/25 5:00 | 0d | 0d | 0ed | 1 | 4/7/25 8:00 | 9/18/25 5:00 | April 7, 2025 8:00 | September 18, 2025 5:00 | As Soon As Possible | NA | 6/27/25 5:00 | 6/27/25 5:00 | 3/13/25 11:13 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
217 | 25 | Yes | Auto Scheduled | BPD Development / Configuration Specs | 119d | Fixed Duration | 5 | 119d |  | April 7, 2025 8:00 | September 18, 2025 5:00 | 4/7/25 8:00 | 9/18/25 5:00 | 4/7/25 8:00 | 9/18/25 5:00 | 0d | 0d | 0ed | 1 | 4/7/25 8:00 | 9/18/25 5:00 | April 7, 2025 8:00 | September 18, 2025 5:00 | As Soon As Possible | NA | 6/27/25 5:00 | 6/27/25 5:00 | 3/13/25 11:13 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
218 | 56 | Yes | Auto Scheduled | Master Data | 59d | Fixed Duration | 6 | 59d |  | June 16, 2025 8:00 | September 4, 2025 5:00 | 6/16/25 8:00 | 9/4/25 5:00 | 6/16/25 8:00 | 9/4/25 5:00 | 0d | 0d | 0ed | 1 | 6/16/25 8:00 | 9/4/25 5:00 | June 16, 2025 8:00 | September 4, 2025 5:00 | As Soon As Possible | NA | 7/15/25 5:00 | 7/15/25 5:00 | 3/13/25 11:18 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.1 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
219 | 57 | Yes | Auto Scheduled | In Draft | 22d | Fixed Units | 7 | 22d |  | June 16, 2025 8:00 | July 15, 2025 5:00 | 6/16/25 8:00 | 7/15/25 5:00 | 6/16/25 8:00 | 7/15/25 5:00 | 0d | 0d | 0ed | 1 | 6/16/25 8:00 | 7/15/25 5:00 | June 16, 2025 8:00 | July 15, 2025 5:00 | Finish No Earlier Than | 7/15/25 5:00 | 7/15/25 5:00 | 7/15/25 5:00 | 3/13/25 11:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.1.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
220 | 58 | Yes | Auto Scheduled | Complete - Ready for Security Review | 30d | Fixed Units | 7 | 30d |  | July 7, 2025 8:00 | August 15, 2025 5:00 | 7/7/25 8:00 | 8/15/25 5:00 | 7/7/25 8:00 | 8/15/25 5:00 | 0d | 0d | 0ed | 1 | 7/7/25 8:00 | 8/15/25 5:00 | July 7, 2025 8:00 | August 15, 2025 5:00 | Finish No Earlier Than | 8/15/25 5:00 | 8/15/25 5:00 | 8/15/25 5:00 | 3/13/25 11:15 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.1.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
221 | 133 | Yes | Auto Scheduled | Complete - Audit and Controls Review | 14d | Fixed Units | 7 | 14d | 220 | August 18, 2025 8:00 | September 4, 2025 5:00 | 8/18/25 8:00 | 9/4/25 5:00 | 8/18/25 8:00 | 9/4/25 5:00 | 0d | 0d | 0ed | 1 | 8/18/25 8:00 | 9/4/25 5:00 | August 18, 2025 8:00 | September 4, 2025 5:00 | As Soon As Possible | NA | 9/4/25 5:00 | 9/4/25 5:00 | 6/16/25 2:17 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.1.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
222 | 26 | Yes | Auto Scheduled | Finance | 104d | Fixed Duration | 6 | 104d |  | April 7, 2025 8:00 | August 28, 2025 5:00 | 4/7/25 8:00 | 8/28/25 5:00 | 4/7/25 8:00 | 8/28/25 5:00 | 0d | 0d | 0ed | 1 | 4/7/25 8:00 | 8/28/25 5:00 | April 7, 2025 8:00 | August 28, 2025 5:00 | As Soon As Possible | NA | 6/27/25 5:00 | 6/27/25 5:00 | 3/13/25 11:13 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.2 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
223 | 31 | Yes | Auto Scheduled | In Draft | 60d | Fixed Units | 7 | 60d |  | April 7, 2025 8:00 | June 27, 2025 5:00 | 4/7/25 8:00 | 6/27/25 5:00 | 4/7/25 8:00 | 6/27/25 5:00 | 0d | 0d | 0ed | 1 | 4/7/25 8:00 | 6/27/25 5:00 | April 7, 2025 8:00 | June 27, 2025 5:00 | Finish No Earlier Than | 6/27/25 5:00 | 6/27/25 5:00 | 6/27/25 5:00 | 3/13/25 11:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.2.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
224 | 32 | Yes | Auto Scheduled | Complete - Ready for Security Review | 80d | Fixed Units | 7 | 80d |  | April 21, 2025 8:00 | August 8, 2025 5:00 | 4/21/25 8:00 | 8/8/25 5:00 | 4/21/25 8:00 | 8/8/25 5:00 | 0d | 0d | 0ed | 1 | 4/21/25 8:00 | 8/8/25 5:00 | April 21, 2025 8:00 | August 8, 2025 5:00 | Start No Earlier Than | 4/21/25 8:00 | 8/8/25 5:00 | 8/8/25 5:00 | 3/13/25 11:15 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.2.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
225 | 134 | Yes | Auto Scheduled | Complete - Ready for Audit and Controls Review | 14d | Fixed Units | 7 | 14d | 224 | August 11, 2025 8:00 | August 28, 2025 5:00 | 8/11/25 8:00 | 8/28/25 5:00 | 8/11/25 8:00 | 8/28/25 5:00 | 0d | 0d | 0ed | 1 | 8/11/25 8:00 | 8/28/25 5:00 | August 11, 2025 8:00 | August 28, 2025 5:00 | As Soon As Possible | NA | 8/28/25 5:00 | 8/28/25 5:00 | 6/16/25 2:17 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.2.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
226 | 27 | Yes | Auto Scheduled | Plan to Make | 108d | Fixed Duration | 6 | 109d |  | April 8, 2025 8:00 | September 4, 2025 5:00 | 4/8/25 8:00 | 9/4/25 5:00 | 4/8/25 8:00 | 9/4/25 5:00 | 0d | 0d | 0ed | 1 | 4/8/25 8:00 | 9/4/25 5:00 | April 7, 2025 8:00 | September 4, 2025 5:00 | As Soon As Possible | NA | 7/21/25 5:00 | 7/21/25 5:00 | 3/13/25 11:13 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.3 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
227 | 33 | Yes | Auto Scheduled | In Draft | 75d | Fixed Units | 7 | 76d |  | April 8, 2025 8:00 | July 21, 2025 5:00 | 4/8/25 8:00 | 7/21/25 5:00 | 4/8/25 8:00 | 7/21/25 5:00 | 0d | 0d | 0ed | 1 | 4/8/25 8:00 | 7/21/25 5:00 | April 7, 2025 8:00 | July 21, 2025 5:00 | Finish No Earlier Than | 7/21/25 5:00 | 7/21/25 5:00 | 7/21/25 5:00 | 3/13/25 11:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.3.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
228 | 34 | Yes | Auto Scheduled | Complete - Ready for Security Review | 85d | Fixed Units | 7 | 85d |  | April 21, 2025 8:00 | August 15, 2025 5:00 | 4/21/25 8:00 | 8/15/25 5:00 | 4/21/25 8:00 | 8/15/25 5:00 | 0d | 0d | 0ed | 1 | 4/21/25 8:00 | 8/15/25 5:00 | April 21, 2025 8:00 | August 15, 2025 5:00 | Start No Earlier Than | 4/21/25 8:00 | 8/15/25 5:00 | 8/15/25 5:00 | 3/13/25 11:15 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.3.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
229 | 135 | Yes | Auto Scheduled | Complete - Ready for Audit and Controls Review | 14d | Fixed Units | 7 | 14d | 228 | August 18, 2025 8:00 | September 4, 2025 5:00 | 8/18/25 8:00 | 9/4/25 5:00 | 8/18/25 8:00 | 9/4/25 5:00 | 0d | 0d | 0ed | 1 | 8/18/25 8:00 | 9/4/25 5:00 | August 18, 2025 8:00 | September 4, 2025 5:00 | As Soon As Possible | NA | 9/4/25 5:00 | 9/4/25 5:00 | 6/16/25 2:17 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.3.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
230 | 28 | Yes | Auto Scheduled | Procure to Pay | 119d | Fixed Duration | 6 | 119d |  | April 7, 2025 8:00 | September 18, 2025 5:00 | 4/7/25 8:00 | 9/18/25 5:00 | 4/7/25 8:00 | 9/18/25 5:00 | 0d | 0d | 0ed | 1 | 4/7/25 8:00 | 9/18/25 5:00 | April 7, 2025 8:00 | September 18, 2025 5:00 | As Soon As Possible | NA | 8/18/25 5:00 | 8/18/25 5:00 | 3/13/25 11:13 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.4 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
231 | 35 | Yes | Auto Scheduled | In Draft | 96d | Fixed Units | 7 | 96d |  | April 7, 2025 8:00 | August 18, 2025 5:00 | 4/7/25 8:00 | 8/18/25 5:00 | 4/7/25 8:00 | 8/18/25 5:00 | 0d | 0d | 0ed | 1 | 4/7/25 8:00 | 8/18/25 5:00 | April 7, 2025 8:00 | August 18, 2025 5:00 | Finish No Earlier Than | 8/18/25 5:00 | 8/18/25 5:00 | 8/18/25 5:00 | 3/13/25 11:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.4.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
232 | 36 | Yes | Auto Scheduled | Complete - Ready for Security Review | 95d | Fixed Units | 7 | 95d |  | April 21, 2025 8:00 | August 29, 2025 5:00 | 4/21/25 8:00 | 8/29/25 5:00 | 4/21/25 8:00 | 8/29/25 5:00 | 0d | 0d | 0ed | 1 | 4/21/25 8:00 | 8/29/25 5:00 | April 21, 2025 8:00 | August 29, 2025 5:00 | Start No Earlier Than | 4/21/25 8:00 | 8/29/25 5:00 | 8/29/25 5:00 | 3/13/25 11:15 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.4.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
233 | 136 | Yes | Auto Scheduled | Complete - Ready for Audit and Controls Review | 14d | Fixed Units | 7 | 14d | 232 | September 1, 2025 8:00 | September 18, 2025 5:00 | 9/1/25 8:00 | 9/18/25 5:00 | 9/1/25 8:00 | 9/18/25 5:00 | 0d | 0d | 0ed | 1 | 9/1/25 8:00 | 9/18/25 5:00 | September 1, 2025 8:00 | September 18, 2025 5:00 | As Soon As Possible | NA | 9/18/25 5:00 | 9/18/25 5:00 | 6/16/25 2:17 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.4.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
234 | 29 | Yes | Auto Scheduled | Order to Cash | 99d | Fixed Duration | 6 | 99d |  | April 7, 2025 8:00 | August 21, 2025 5:00 | 4/7/25 8:00 | 8/21/25 5:00 | 4/7/25 8:00 | 8/21/25 5:00 | 0d | 0d | 0ed | 1 | 4/7/25 8:00 | 8/21/25 5:00 | April 7, 2025 8:00 | August 21, 2025 5:00 | As Soon As Possible | NA | 7/21/25 5:00 | 7/21/25 5:00 | 3/13/25 11:13 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.5 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
235 | 37 | Yes | Auto Scheduled | In Draft | 76d | Fixed Units | 7 | 76d |  | April 7, 2025 8:00 | July 21, 2025 5:00 | 4/7/25 8:00 | 7/21/25 5:00 | 4/7/25 8:00 | 7/21/25 5:00 | 0d | 0d | 0ed | 1 | 4/7/25 8:00 | 7/21/25 5:00 | April 7, 2025 8:00 | July 21, 2025 5:00 | Finish No Earlier Than | 7/21/25 5:00 | 7/21/25 5:00 | 7/21/25 5:00 | 3/13/25 11:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.5.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
236 | 38 | Yes | Auto Scheduled | Complete - Ready for Security Review | 75d | Fixed Units | 7 | 75d |  | April 21, 2025 8:00 | August 1, 2025 5:00 | 4/21/25 8:00 | 8/1/25 5:00 | 4/21/25 8:00 | 8/1/25 5:00 | 0d | 0d | 0ed | 1 | 4/21/25 8:00 | 8/1/25 5:00 | April 21, 2025 8:00 | August 1, 2025 5:00 | Start No Earlier Than | 4/21/25 8:00 | 8/1/25 5:00 | 8/1/25 5:00 | 3/13/25 11:15 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.5.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
237 | 137 | Yes | Auto Scheduled | Complete - Ready for Audit and Controls Review | 14d | Fixed Units | 7 | 14d | 236 | August 4, 2025 8:00 | August 21, 2025 5:00 | 8/4/25 8:00 | 8/21/25 5:00 | 8/4/25 8:00 | 8/21/25 5:00 | 0d | 0d | 0ed | 1 | 8/4/25 8:00 | 8/21/25 5:00 | August 4, 2025 8:00 | August 21, 2025 5:00 | As Soon As Possible | NA | 8/21/25 5:00 | 8/21/25 5:00 | 6/16/25 2:17 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.9.1.5.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
238 | 55 | Yes | Auto Scheduled | RICEFW Development Tasks (RICEFW Tracker) | 1d | Fixed Duration | 4 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:18 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
239 | 59 | Yes | Auto Scheduled | Finance and Controlling | 1d | Fixed Duration | 5 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:13 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.1 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
240 | 60 | Yes | Auto Scheduled | Specs Completed | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.1.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
241 | 61 | Yes | Auto Scheduled | Specs Assigned to Developer | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:15 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.1.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
242 | 71 | Yes | Auto Scheduled | Testing Complete | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.1.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
243 | 72 | Yes | Auto Scheduled | Assigned to Testing Cycle | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.1.4 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
244 | 62 | Yes | Auto Scheduled | Plan to Make | 1d | Fixed Duration | 5 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:13 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.2 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
245 | 73 | Yes | Auto Scheduled | Specs Completed | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.2.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
246 | 74 | Yes | Auto Scheduled | Specs Assigned to Developer | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:15 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.2.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
247 | 75 | Yes | Auto Scheduled | Testing Complete | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.2.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
248 | 76 | Yes | Auto Scheduled | Assigned to Testing Cycle | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.2.4 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
249 | 65 | Yes | Auto Scheduled | Procure to Pay | 1d | Fixed Duration | 5 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:13 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.3 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
250 | 77 | Yes | Auto Scheduled | Specs Completed | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.3.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
251 | 78 | Yes | Auto Scheduled | Specs Assigned to Developer | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:15 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.3.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
252 | 79 | Yes | Auto Scheduled | Testing Complete | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.3.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
253 | 80 | Yes | Auto Scheduled | Assigned to Testing Cycle | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.3.4 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
254 | 68 | Yes | Auto Scheduled | Order to Cash | 1d | Fixed Duration | 5 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:13 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.4 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
255 | 81 | Yes | Auto Scheduled | Specs Completed | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.4.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
256 | 82 | Yes | Auto Scheduled | Specs Assigned to Developer | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:15 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.4.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
257 | 83 | Yes | Auto Scheduled | Testing Complete | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.4.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
258 | 84 | Yes | Auto Scheduled | Assigned to Testing Cycle | 1d | Fixed Units | 6 | 1d |  | March 13, 2025 8:00 | March 13, 2025 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 3/13/25 8:00 | 3/13/25 5:00 | 0d | 0d | 0ed | 1 | 3/13/25 8:00 | 3/13/25 5:00 | March 13, 2025 8:00 | March 13, 2025 5:00 | As Soon As Possible | NA | 3/13/25 5:00 | 3/13/25 5:00 | 3/13/25 11:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1.2.10.4.4 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
259 | 682 | Yes | Auto Scheduled | Data Readiness | 135.66d | Fixed Duration | 2 | 288.81d |  | April 6, 2026 8:00 | October 12, 2026 2:15 | 4/6/26 8:00 | 10/12/26 2:15 | 4/6/26 8:00 | 10/8/26 2:01 | 0d | -2.03d | 0ed | 0.20000000000000001 | 4/6/26 8:00 | NA | March 13, 2025 8:00 | April 21, 2026 3:30 | As Soon As Possible | NA | 4/6/26 8:15 | 4/6/26 8:15 | 3/24/26 6:43 | 3,484.28h | 592.25h | 751.75h | 0 | 0 | 0 | 0 | 0 | 1.2 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
260 | 425 | Yes | Auto Scheduled | ITC1 Data Load Tasks QS5 | 13.66d | Fixed Duration | 3 | 288.78d |  | April 6, 2026 8:00 | April 23, 2026 2:15 | 4/6/26 8:00 | 4/23/26 2:15 | 4/6/26 8:00 | 4/23/26 2:15 | 0d | 0d | 0ed | 1 | 4/6/26 8:00 | 4/23/26 2:15 | March 13, 2025 8:00 | April 21, 2026 3:15 | As Soon As Possible | NA | 4/6/26 8:15 | 4/6/26 8:15 | 8/1/25 5:31 | 751.75h | 592h | 751.75h | 0 | 0 | 0 | 0 | 0 | 1.2.1 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
261 | 956 | Yes | Auto Scheduled | PMO Authorization to Start Data Loads | 15m | Fixed Units | 4 | 0.03d |  | April 6, 2026 8:00 | April 6, 2026 8:15 | 4/6/26 8:00 | 4/6/26 8:15 | 4/6/26 8:00 | 4/6/26 8:15 | 0m | 0m | 0ed | 1 | 4/6/26 8:00 | 4/6/26 8:15 | April 6, 2026 8:00 | April 6, 2026 8:15 | Start No Earlier Than | 4/6/26 8:00 | 4/6/26 8:15 | 4/6/26 8:15 | 4/1/26 1:46 | 0.25h | 0.25h | 0.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
262 | 755 | Yes | Auto Scheduled | RTR_CM02_Profit Center Hierarchy | 0.75d | Fixed Duration | 4 | 0.75d |  | April 6, 2026 8:15 | April 6, 2026 3:15 | 4/6/26 8:15 | 4/6/26 3:15 | 4/6/26 8:15 | 4/6/26 3:15 | 0d | 0d | 0ed | 1 | 4/6/26 8:15 | 4/6/26 3:15 | April 6, 2026 8:15 | April 6, 2026 3:15 | As Soon As Possible | NA | 4/6/26 9:15 | 4/6/26 9:15 | 3/25/26 2:32 | 6h | 6h | 6h | 0 | 0 | 0 | 0 | 0 | 1.2.1.2 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
263 | 777 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | Fixed Units | 5 | 0.13d | 261 | April 6, 2026 8:15 | April 6, 2026 9:15 | 4/6/26 8:15 | 4/6/26 9:15 | 4/6/26 8:15 | 4/6/26 9:15 | 0h | 0h | 0ed | 1 | 4/6/26 8:15 | 4/6/26 9:15 | April 6, 2026 8:15 | April 6, 2026 9:15 | Start No Earlier Than | 4/6/26 8:00 | 4/6/26 9:15 | 4/6/26 9:15 | 3/25/26 2:41 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
264 | 780 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 263 | April 6, 2026 9:15 | April 6, 2026 11:15 | 4/6/26 9:15 | 4/6/26 11:15 | 4/6/26 9:15 | 4/6/26 11:15 | 0h | 0h | 0ed | 1 | 4/6/26 9:15 | 4/6/26 11:15 | April 6, 2026 9:15 | April 6, 2026 11:15 | As Soon As Possible | NA | 4/6/26 11:15 | 4/6/26 11:15 | 3/25/26 2:41 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
265 | 781 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 264 | April 6, 2026 11:15 | April 6, 2026 3:15 | 4/6/26 11:15 | 4/6/26 3:15 | 4/6/26 11:15 | 4/6/26 3:15 | 0h | 0h | 0ed | 1 | 4/6/26 11:15 | 4/6/26 3:15 | April 6, 2026 11:15 | April 6, 2026 3:15 | As Soon As Possible | NA | 4/6/26 3:15 | 4/6/26 3:15 | 3/25/26 2:41 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.2.3 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
266 | 756 | Yes | Auto Scheduled | RTR_CM03_Cost Center Hierarchy | 0.75d | Fixed Duration | 4 | 0.75d | 262 | April 6, 2026 3:15 | April 7, 2026 1:15 | 4/6/26 3:15 | 4/7/26 1:15 | 4/6/26 3:15 | 4/7/26 1:15 | 0d | 0d | 0ed | 1 | 4/6/26 3:15 | 4/7/26 1:15 | April 6, 2026 3:15 | April 7, 2026 1:15 | As Soon As Possible | NA | 4/6/26 4:15 | 4/6/26 4:15 | 3/25/26 2:32 | 6h | 6h | 6h | 0 | 0 | 0 | 0 | 0 | 1.2.1.3 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
267 | 783 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | Fixed Units | 5 | 0.13d | 265 | April 6, 2026 3:15 | April 6, 2026 4:15 | 4/6/26 3:15 | 4/6/26 4:15 | 4/6/26 3:15 | 4/6/26 4:15 | 0h | 0h | 0ed | 1 | 4/6/26 3:15 | 4/6/26 4:15 | April 6, 2026 3:15 | April 6, 2026 4:15 | Start No Earlier Than | 4/6/26 8:00 | 4/6/26 4:15 | 4/6/26 4:15 | 3/25/26 2:45 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
268 | 786 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 267 | April 6, 2026 4:15 | April 7, 2026 9:15 | 4/6/26 4:15 | 4/7/26 9:15 | 4/6/26 4:15 | 4/7/26 9:15 | 0h | 0h | 0ed | 1 | 4/6/26 4:15 | 4/7/26 9:15 | April 6, 2026 4:15 | April 7, 2026 9:15 | As Soon As Possible | NA | 4/7/26 9:15 | 4/7/26 9:15 | 3/25/26 2:45 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
269 | 787 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 268 | April 7, 2026 9:15 | April 7, 2026 1:15 | 4/7/26 9:15 | 4/7/26 1:15 | 4/7/26 9:15 | 4/7/26 1:15 | 0h | 0h | 0ed | 1 | 4/7/26 9:15 | 4/7/26 1:15 | April 7, 2026 9:15 | April 7, 2026 1:15 | As Soon As Possible | NA | 4/7/26 1:15 | 4/7/26 1:15 | 3/25/26 2:45 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.3.3 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
270 | 740 | Yes | Auto Scheduled | RTR_CM01_GL_Account_Master to CC 1000 | 1.81d | Fixed Duration | 4 | 1.81d | 266 | April 7, 2026 1:15 | April 9, 2026 10:45 | 4/7/26 1:15 | 4/9/26 10:45 | 4/7/26 1:15 | 4/9/26 10:45 | 0d | 0d | 0ed | 1 | 4/7/26 1:15 | 4/9/26 10:45 | April 7, 2026 1:15 | April 9, 2026 10:45 | As Soon As Possible | NA | 4/7/26 2:15 | 4/7/26 2:15 | 3/25/26 2:32 | 16h | 16h | 16h | 0 | 0 | 0 | 0 | 0 | 1.2.1.4 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
271 | 958 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 5 | 0.13d | 269 | April 7, 2026 1:15 | April 7, 2026 2:15 | 4/7/26 1:15 | 4/7/26 2:15 | 4/7/26 1:15 | 4/7/26 2:15 | 0h | 0h | 0ed | 1 | 4/7/26 1:15 | 4/7/26 2:15 | April 7, 2026 1:15 | April 7, 2026 2:15 | Start No Earlier Than | 4/6/26 8:00 | 4/7/26 2:15 | 4/7/26 2:15 | 4/1/26 1:54 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
272 | 773 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 271 | April 7, 2026 2:15 | April 7, 2026 4:15 | 4/7/26 2:15 | 4/7/26 4:15 | 4/7/26 2:15 | 4/7/26 4:15 | 0h | 0h | 0ed | 1 | 4/7/26 2:15 | 4/7/26 4:15 | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | 4/7/26 4:15 | 4/7/26 4:15 | 3/25/26 2:35 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.2 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
273 | 774 | Yes | Auto Scheduled | Simulate Load | 6h | Fixed Units | 5 | 0.75d | 272 | April 7, 2026 4:15 | April 8, 2026 2:15 | 4/7/26 4:15 | 4/8/26 2:15 | 4/7/26 4:15 | 4/8/26 2:15 | 0h | 0h | 0ed | 1 | 4/7/26 4:15 | 4/8/26 2:15 | April 7, 2026 4:15 | April 8, 2026 2:15 | As Soon As Possible | NA | 4/8/26 2:15 | 4/8/26 2:15 | 3/25/26 2:35 | 6h | 6h | 6h | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
274 | 775 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 273 | April 8, 2026 8:15 | April 8, 2026 11:45 | 4/8/26 8:15 | 4/8/26 11:45 | 4/8/26 8:15 | 4/8/26 11:45 | 0h | 0h | 0ed | 1 | 4/8/26 8:15 | 4/8/26 11:45 | April 8, 2026 8:15 | April 8, 2026 11:45 | As Soon As Possible | NA | 4/8/26 11:45 | 4/8/26 11:45 | 3/25/26 2:35 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.4 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
275 | 795 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 274 | April 8, 2026 11:45 | April 8, 2026 1:45 | 4/8/26 11:45 | 4/8/26 1:45 | 4/8/26 11:45 | 4/8/26 1:45 | 0h | 0h | 0ed | 1 | 4/8/26 11:45 | 4/8/26 1:45 | April 8, 2026 11:45 | April 8, 2026 1:45 | As Soon As Possible | NA | 4/8/26 1:45 | 4/8/26 1:45 | 3/25/26 2:54 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
276 | 776 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 275 | April 8, 2026 1:45 | April 8, 2026 3:45 | 4/8/26 1:45 | 4/8/26 3:45 | 4/8/26 1:45 | 4/8/26 3:45 | 0h | 0h | 0ed | 1 | 4/8/26 1:45 | 4/8/26 3:45 | April 8, 2026 1:45 | April 8, 2026 3:45 | As Soon As Possible | NA | 4/8/26 3:45 | 4/8/26 3:45 | 3/25/26 2:35 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.6 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
277 | 1243 | Yes | Auto Scheduled | Extend GL to all Company Codes | 2h | Fixed Units | 5 | 0.25d | 276 | April 8, 2026 3:45 | April 9, 2026 8:45 | 4/8/26 3:45 | 4/9/26 8:45 | 4/8/26 3:45 | 4/9/26 8:45 | 0h | 0h | 0ed | 1 | 4/8/26 3:45 | 4/9/26 8:45 | April 8, 2026 3:45 | April 9, 2026 8:45 | As Soon As Possible | NA | 4/9/26 8:45 | 4/9/26 8:45 | 4/8/26 9:16 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.7 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
278 | 1244 | Yes | Auto Scheduled | Post GL Extention Validation | 2h | Fixed Units | 5 | 0.25d | 277 | April 9, 2026 8:45 | April 9, 2026 10:45 | 4/9/26 8:45 | 4/9/26 10:45 | 4/9/26 8:45 | 4/9/26 10:45 | 0h | 0h | 0ed | 1 | 4/9/26 8:45 | 4/9/26 10:45 | April 9, 2026 8:45 | April 9, 2026 10:45 | As Soon As Possible | NA | 4/9/26 10:45 | 4/9/26 10:45 | 4/8/26 9:43 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.1.4.8 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
279 | 759 | Yes | Auto Scheduled | RTR_CM05_Profit_Center | 1.13d | Fixed Duration | 4 | 1.13d | 270 | April 6, 2026 3:15 | April 7, 2026 4:15 | 4/6/26 3:15 | 4/7/26 4:15 | 4/6/26 3:15 | 4/7/26 4:15 | 0d | 0d | 0ed | 1 | 4/6/26 3:15 | 4/7/26 4:15 | April 6, 2026 3:15 | April 7, 2026 4:15 | As Soon As Possible | NA | 4/6/26 4:15 | 4/6/26 4:15 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.5 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
280 | 802 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 5 | 0.13d | 265 | April 6, 2026 3:15 | April 6, 2026 4:15 | 4/6/26 3:15 | 4/6/26 4:15 | 4/6/26 3:15 | 4/6/26 4:15 | 0h | 0h | 0ed | 1 | 4/6/26 3:15 | 4/6/26 4:15 | April 6, 2026 3:15 | April 6, 2026 4:15 | As Soon As Possible | NA | 4/6/26 4:15 | 4/6/26 4:15 | 3/30/26 6:34 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
281 | 803 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 280 | April 6, 2026 4:15 | April 7, 2026 9:15 | 4/6/26 4:15 | 4/7/26 9:15 | 4/6/26 4:15 | 4/7/26 9:15 | 0h | 0h | 0ed | 1 | 4/6/26 4:15 | 4/7/26 9:15 | April 6, 2026 4:15 | April 7, 2026 9:15 | As Soon As Possible | NA | 4/7/26 9:15 | 4/7/26 9:15 | 3/30/26 6:34 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.2 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
282 | 804 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 281 | April 7, 2026 9:15 | April 7, 2026 10:15 | 4/7/26 9:15 | 4/7/26 10:15 | 4/7/26 9:15 | 4/7/26 10:15 | 0h | 0h | 0ed | 1 | 4/7/26 9:15 | 4/7/26 10:15 | April 7, 2026 9:15 | April 7, 2026 10:15 | As Soon As Possible | NA | 4/7/26 10:15 | 4/7/26 10:15 | 3/30/26 6:34 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
283 | 805 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 282 | April 7, 2026 10:15 | April 7, 2026 1:15 | 4/7/26 10:15 | 4/7/26 1:15 | 4/7/26 10:15 | 4/7/26 1:15 | 0h | 0h | 0ed | 1 | 4/7/26 10:15 | 4/7/26 1:15 | April 7, 2026 10:15 | April 7, 2026 1:15 | As Soon As Possible | NA | 4/7/26 1:15 | 4/7/26 1:15 | 3/30/26 6:34 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.4 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
284 | 806 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 283 | April 7, 2026 1:15 | April 7, 2026 2:15 | 4/7/26 1:15 | 4/7/26 2:15 | 4/7/26 1:15 | 4/7/26 2:15 | 0h | 0h | 0ed | 1 | 4/7/26 1:15 | 4/7/26 2:15 | April 7, 2026 1:15 | April 7, 2026 2:15 | As Soon As Possible | NA | 4/7/26 2:15 | 4/7/26 2:15 | 3/30/26 6:34 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
285 | 807 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 284 | April 7, 2026 2:15 | April 7, 2026 4:15 | 4/7/26 2:15 | 4/7/26 4:15 | 4/7/26 2:15 | 4/7/26 4:15 | 0h | 0h | 0ed | 1 | 4/7/26 2:15 | 4/7/26 4:15 | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | 4/7/26 4:15 | 4/7/26 4:15 | 3/30/26 6:34 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.5.6 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
286 | 767 | Yes | Auto Scheduled | RTR_CM04_Cost_Center | 1.13d | Fixed Duration | 4 | 1.13d | 279 | April 7, 2026 4:15 | April 9, 2026 8:15 | 4/7/26 4:15 | 4/9/26 8:15 | 4/7/26 4:15 | 4/9/26 8:15 | 0d | 0d | 0ed | 1 | 4/7/26 4:15 | 4/9/26 8:15 | April 7, 2026 4:15 | April 9, 2026 8:15 | As Soon As Possible | NA | 4/8/26 8:15 | 4/8/26 8:15 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.6 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
287 | 959 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 5 | 0.13d | 285 | April 7, 2026 4:15 | April 8, 2026 8:15 | 4/7/26 4:15 | 4/8/26 8:15 | 4/7/26 4:15 | 4/8/26 8:15 | 0h | 0h | 0ed | 1 | 4/7/26 4:15 | 4/8/26 8:15 | April 7, 2026 4:15 | April 8, 2026 8:15 | As Soon As Possible | NA | 4/8/26 8:15 | 4/8/26 8:15 | 4/1/26 1:59 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.6.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
288 | 960 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 287 | April 8, 2026 8:15 | April 8, 2026 10:15 | 4/8/26 8:15 | 4/8/26 10:15 | 4/8/26 8:15 | 4/8/26 10:15 | 0h | 0h | 0ed | 1 | 4/8/26 8:15 | 4/8/26 10:15 | April 8, 2026 8:15 | April 8, 2026 10:15 | As Soon As Possible | NA | 4/8/26 10:15 | 4/8/26 10:15 | 4/1/26 1:59 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.6.2 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
289 | 961 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 288 | April 8, 2026 10:15 | April 8, 2026 11:15 | 4/8/26 10:15 | 4/8/26 11:15 | 4/8/26 10:15 | 4/8/26 11:15 | 0h | 0h | 0ed | 1 | 4/8/26 10:15 | 4/8/26 11:15 | April 8, 2026 10:15 | April 8, 2026 11:15 | As Soon As Possible | NA | 4/8/26 11:15 | 4/8/26 11:15 | 4/1/26 1:59 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.6.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
290 | 962 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 289 | April 8, 2026 11:15 | April 8, 2026 2:15 | 4/8/26 11:15 | 4/8/26 2:15 | 4/8/26 11:15 | 4/8/26 2:15 | 0h | 0h | 0ed | 1 | 4/8/26 11:15 | 4/8/26 2:15 | April 8, 2026 11:15 | April 8, 2026 2:15 | As Soon As Possible | NA | 4/8/26 2:15 | 4/8/26 2:15 | 4/1/26 1:59 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.6.4 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
291 | 963 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 290 | April 8, 2026 2:15 | April 8, 2026 3:15 | 4/8/26 2:15 | 4/8/26 3:15 | 4/8/26 2:15 | 4/8/26 3:15 | 0h | 0h | 0ed | 1 | 4/8/26 2:15 | 4/8/26 3:15 | April 8, 2026 2:15 | April 8, 2026 3:15 | As Soon As Possible | NA | 4/8/26 3:15 | 4/8/26 3:15 | 4/1/26 1:59 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.6.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
292 | 964 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 291 | April 8, 2026 3:15 | April 9, 2026 8:15 | 4/8/26 3:15 | 4/9/26 8:15 | 4/8/26 3:15 | 4/9/26 8:15 | 0h | 0h | 0ed | 1 | 4/8/26 3:15 | 4/9/26 8:15 | April 8, 2026 3:15 | April 9, 2026 8:15 | As Soon As Possible | NA | 4/9/26 8:15 | 4/9/26 8:15 | 4/1/26 1:59 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.6.6 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
293 | 881 | Yes | Auto Scheduled | Manual Configuration Activities in QS5 | 7.16d | Fixed Duration | 4 | 7.16d | 286 | April 6, 2026 1:00 | April 15, 2026 2:15 | 4/6/26 1:00 | 4/15/26 2:15 | 4/6/26 1:00 | 4/15/26 2:15 | 0d | 0d | 0ed | 1 | 4/6/26 1:00 | 4/15/26 2:15 | April 6, 2026 1:00 | April 15, 2026 2:15 | As Soon As Possible | NA | 4/6/26 1:30 | 4/6/26 1:30 | 3/31/26 7:06 | 43h | 43h | 43h | 0 | 0 | 0 | 0 | 0 | 1.2.1.7 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
294 | 1219 | Yes | Auto Scheduled | Open Client | 30m | Fixed Units | 5 | 0.06d |  | April 6, 2026 1:00 | April 6, 2026 1:30 | 4/6/26 1:00 | 4/6/26 1:30 | 4/6/26 1:00 | 4/6/26 1:30 | 0m | 0m | 0ed | 1 | 4/6/26 1:00 | 4/6/26 1:30 | April 6, 2026 1:00 | April 6, 2026 1:30 | As Soon As Possible | NA | 4/6/26 1:30 | 4/6/26 1:30 | 4/8/26 8:20 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.7.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
295 | 882 | Yes | Auto Scheduled | Service Enterprise Setup | 5d | Fixed Units | 5 | 5d | 270,262,266 | April 8, 2026 2:15 | April 15, 2026 2:15 | 4/8/26 2:15 | 4/15/26 2:15 | 4/8/26 2:15 | 4/15/26 2:15 | 0d | 0d | 0ed | 1 | 4/8/26 2:15 | 4/15/26 2:15 | April 8, 2026 2:15 | April 15, 2026 2:15 | As Soon As Possible | NA | 4/15/26 2:15 | 4/15/26 2:15 | 3/31/26 7:06 | 40h | 40h | 40h | 0 | 0 | 0 | 0 | 0 | 1.2.1.7.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
296 | 1220 | Yes | Auto Scheduled | Close Client | 30m | Fixed Units | 5 | 0.06d |  | April 6, 2026 1:00 | April 6, 2026 1:30 | 4/6/26 1:00 | 4/6/26 1:30 | 4/6/26 1:00 | 4/6/26 1:30 | 0m | 0m | 0ed | 1 | 4/6/26 1:00 | 4/6/26 1:30 | April 6, 2026 1:00 | April 6, 2026 1:30 | As Soon As Possible | NA | 4/6/26 1:30 | 4/6/26 1:30 | 4/8/26 8:20 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.7.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
297 | 883 | Yes | Auto Scheduled | Intercompany Business Partner Setup | 2h | Fixed Units | 5 | 0.25d | 262,266,278 | April 8, 2026 3:45 | April 9, 2026 8:45 | 4/8/26 3:45 | 4/9/26 8:45 | 4/8/26 3:45 | 4/9/26 8:45 | 0h | 0h | 0ed | 1 | 4/8/26 3:45 | 4/9/26 8:45 | April 8, 2026 3:45 | April 9, 2026 8:45 | As Soon As Possible | NA | 4/9/26 8:45 | 4/9/26 8:45 | 3/31/26 7:06 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.7.4 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
298 | 760 | Yes | Auto Scheduled | RTR_CM09_Activity_Type | 1.22d | Fixed Duration | 4 | 1.22d | 286 | April 8, 2026 2:15 | April 9, 2026 4:00 | 4/8/26 2:15 | 4/9/26 4:00 | 4/8/26 2:15 | 4/9/26 4:00 | 0d | 0d | 0ed | 1 | 4/8/26 2:15 | 4/9/26 4:00 | April 8, 2026 2:15 | April 9, 2026 4:00 | As Soon As Possible | NA | 4/8/26 4:30 | 4/8/26 4:30 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.8 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
299 | 808 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 5 | 0.13d | 276 | April 8, 2026 2:15 | April 8, 2026 4:30 | 4/8/26 2:15 | 4/8/26 4:30 | 4/8/26 2:15 | 4/8/26 4:30 | 0h | 0h | 0ed | 1 | 4/8/26 2:15 | 4/8/26 4:30 | April 8, 2026 2:15 | April 8, 2026 4:30 | As Soon As Possible | NA | 4/8/26 4:30 | 4/8/26 4:30 | 3/30/26 6:35 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.8.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
300 | 809 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 299 | April 8, 2026 3:15 | April 9, 2026 9:00 | 4/8/26 3:15 | 4/9/26 9:00 | 4/8/26 3:15 | 4/9/26 9:00 | 0h | 0h | 0ed | 1 | 4/8/26 3:15 | 4/9/26 9:00 | April 8, 2026 3:15 | April 9, 2026 9:00 | As Soon As Possible | NA | 4/9/26 9:00 | 4/9/26 9:00 | 3/30/26 6:35 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.8.2 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
301 | 810 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 300 | April 9, 2026 9:00 | April 9, 2026 10:00 | 4/9/26 9:00 | 4/9/26 10:00 | 4/9/26 9:00 | 4/9/26 10:00 | 0h | 0h | 0ed | 1 | 4/9/26 9:00 | 4/9/26 10:00 | April 9, 2026 9:00 | April 9, 2026 10:00 | As Soon As Possible | NA | 4/9/26 10:00 | 4/9/26 10:00 | 3/30/26 6:35 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.8.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
302 | 811 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 301 | April 9, 2026 10:00 | April 9, 2026 12:00 | 4/9/26 10:00 | 4/9/26 12:00 | 4/9/26 10:00 | 4/9/26 12:00 | 0h | 0h | 0ed | 1 | 4/9/26 10:00 | 4/9/26 12:00 | April 9, 2026 10:00 | April 9, 2026 12:00 | As Soon As Possible | NA | 4/9/26 12:00 | 4/9/26 12:00 | 3/30/26 6:35 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.8.4 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
303 | 812 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 302 | April 9, 2026 1:00 | April 9, 2026 2:00 | 4/9/26 1:00 | 4/9/26 2:00 | 4/9/26 1:00 | 4/9/26 2:00 | 0h | 0h | 0ed | 1 | 4/9/26 1:00 | 4/9/26 2:00 | April 9, 2026 1:00 | April 9, 2026 2:00 | As Soon As Possible | NA | 4/9/26 2:00 | 4/9/26 2:00 | 3/30/26 6:35 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.8.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
304 | 813 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 303 | April 9, 2026 2:00 | April 9, 2026 4:00 | 4/9/26 2:00 | 4/9/26 4:00 | 4/9/26 2:00 | 4/9/26 4:00 | 0h | 0h | 0ed | 1 | 4/9/26 2:00 | 4/9/26 4:00 | April 9, 2026 2:00 | April 9, 2026 4:00 | As Soon As Possible | NA | 4/9/26 4:00 | 4/9/26 4:00 | 3/30/26 6:35 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.8.6 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
305 | 753 | Yes | Auto Scheduled | RTR_CM12_Activity Rates | 1.13d | Fixed Duration | 4 | 1.13d | 298 | April 7, 2026 1:15 | April 8, 2026 2:15 | 4/7/26 1:15 | 4/8/26 2:15 | 4/7/26 1:15 | 4/8/26 2:15 | 0d | 0d | 0ed | 1 | 4/7/26 1:15 | 4/8/26 2:15 | April 7, 2026 1:15 | April 8, 2026 2:15 | As Soon As Possible | NA | 4/7/26 2:15 | 4/7/26 2:15 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.9 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
306 | 965 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 5 | 0.13d | 269 | April 7, 2026 1:15 | April 7, 2026 2:15 | 4/7/26 1:15 | 4/7/26 2:15 | 4/7/26 1:15 | 4/7/26 2:15 | 0h | 0h | 0ed | 1 | 4/7/26 1:15 | 4/7/26 2:15 | April 7, 2026 1:15 | April 7, 2026 2:15 | As Soon As Possible | NA | 4/7/26 2:15 | 4/7/26 2:15 | 4/1/26 2:01 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.9.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
307 | 966 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 306 | April 7, 2026 2:15 | April 7, 2026 4:15 | 4/7/26 2:15 | 4/7/26 4:15 | 4/7/26 2:15 | 4/7/26 4:15 | 0h | 0h | 0ed | 1 | 4/7/26 2:15 | 4/7/26 4:15 | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | 4/7/26 4:15 | 4/7/26 4:15 | 4/1/26 2:01 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.9.2 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
308 | 967 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 307 | April 7, 2026 4:15 | April 8, 2026 8:15 | 4/7/26 4:15 | 4/8/26 8:15 | 4/7/26 4:15 | 4/8/26 8:15 | 0h | 0h | 0ed | 1 | 4/7/26 4:15 | 4/8/26 8:15 | April 7, 2026 4:15 | April 8, 2026 8:15 | As Soon As Possible | NA | 4/8/26 8:15 | 4/8/26 8:15 | 4/1/26 2:01 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.9.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
309 | 968 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 308 | April 8, 2026 8:15 | April 8, 2026 10:15 | 4/8/26 8:15 | 4/8/26 10:15 | 4/8/26 8:15 | 4/8/26 10:15 | 0h | 0h | 0ed | 1 | 4/8/26 8:15 | 4/8/26 10:15 | April 8, 2026 8:15 | April 8, 2026 10:15 | As Soon As Possible | NA | 4/8/26 10:15 | 4/8/26 10:15 | 4/1/26 2:01 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.9.4 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
310 | 969 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 309 | April 8, 2026 10:15 | April 8, 2026 11:15 | 4/8/26 10:15 | 4/8/26 11:15 | 4/8/26 10:15 | 4/8/26 11:15 | 0h | 0h | 0ed | 1 | 4/8/26 10:15 | 4/8/26 11:15 | April 8, 2026 10:15 | April 8, 2026 11:15 | As Soon As Possible | NA | 4/8/26 11:15 | 4/8/26 11:15 | 4/1/26 2:01 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.9.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
311 | 970 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 310 | April 8, 2026 11:15 | April 8, 2026 2:15 | 4/8/26 11:15 | 4/8/26 2:15 | 4/8/26 11:15 | 4/8/26 2:15 | 0h | 0h | 0ed | 1 | 4/8/26 11:15 | 4/8/26 2:15 | April 8, 2026 11:15 | April 8, 2026 2:15 | As Soon As Possible | NA | 4/8/26 2:15 | 4/8/26 2:15 | 4/1/26 2:01 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.9.6 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
312 | 757 | Yes | Auto Scheduled | RTR_CM06_Bank_master | 2.19d | Fixed Duration | 4 | 1.22d | 305 | April 14, 2026 8:00 | April 16, 2026 9:30 | 4/14/26 8:00 | 4/16/26 9:30 | 4/14/26 8:00 | 4/16/26 9:30 | 0d | 0d | 0ed | 1 | 4/14/26 8:00 | 4/16/26 9:30 | April 8, 2026 2:15 | April 9, 2026 4:00 | As Soon As Possible | NA | 4/14/26 9:00 | 4/14/26 9:00 | 3/25/26 2:32 | 13h | 9h | 13h | 0 | 0 | 0 | 0 | 0 | 1.2.1.10 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
313 | 789 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 5 | 0.13d | 276 | April 14, 2026 8:00 | April 14, 2026 9:00 | 4/14/26 8:00 | 4/14/26 9:00 | 4/14/26 8:00 | 4/14/26 9:00 | 0h | 0h | 0ed | 1 | 4/14/26 8:00 | 4/14/26 9:00 | April 8, 2026 2:15 | April 8, 2026 4:30 | As Soon As Possible | NA | 4/14/26 9:00 | 4/14/26 9:00 | 3/25/26 2:49 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.10.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
314 | 790 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 313 | April 14, 2026 9:00 | April 14, 2026 11:00 | 4/14/26 9:00 | 4/14/26 11:00 | 4/14/26 9:00 | 4/14/26 11:00 | 0h | 0h | 0ed | 1 | 4/14/26 9:00 | 4/14/26 11:00 | April 8, 2026 4:30 | April 9, 2026 9:30 | As Soon As Possible | NA | 4/14/26 11:00 | 4/14/26 11:00 | 3/25/26 2:49 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.10.2 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
315 | 791 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d |  | April 15, 2026 8:00 | April 15, 2026 9:00 | 4/15/26 8:00 | 4/15/26 9:00 | 4/15/26 8:00 | 4/15/26 9:00 | 0h | 0h | 0ed | 1 | 4/15/26 8:00 | 4/15/26 9:00 | April 9, 2026 9:30 | April 9, 2026 10:30 | Start No Earlier Than | 4/15/26 8:00 | 4/15/26 9:00 | 4/15/26 9:00 | 3/25/26 2:49 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.10.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
316 | 792 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 315 | April 15, 2026 9:00 | April 15, 2026 11:00 | 4/15/26 9:00 | 4/15/26 11:00 | 4/15/26 9:00 | 4/15/26 11:00 | 0h | 0h | 0ed | 1 | 4/15/26 9:00 | 4/15/26 11:00 | April 9, 2026 10:30 | April 9, 2026 1:30 | As Soon As Possible | NA | 4/15/26 11:00 | 4/15/26 11:00 | 3/25/26 2:49 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.10.4 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
317 | 793 | Yes | Auto Scheduled | Load | 5h | Fixed Units | 5 | 0.13d | 316 | April 15, 2026 11:00 | April 15, 2026 5:00 | 4/15/26 11:00 | 4/15/26 5:00 | 4/15/26 11:00 | 4/15/26 5:00 | 0h | 0h | 0ed | 1 | 4/15/26 11:00 | 4/15/26 5:00 | April 9, 2026 1:30 | April 9, 2026 2:30 | Finish No Earlier Than | 4/15/26 5:00 | 4/15/26 5:00 | 4/15/26 5:00 | 3/25/26 2:49 | 5h | 1h | 5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.10.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
318 | 794 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 317 | April 15, 2026 1:00 | April 16, 2026 9:30 | 4/15/26 1:00 | 4/16/26 9:30 | 4/15/26 1:00 | 4/16/26 9:30 | 0h | 0h | 0ed | 1 | 4/15/26 1:00 | 4/16/26 9:30 | April 9, 2026 8:00 | April 9, 2026 4:00 | Finish No Earlier Than | 4/14/26 5:00 | 4/16/26 9:30 | 4/16/26 9:30 | 3/25/26 2:49 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.10.6 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
319 | 758 | Yes | Auto Scheduled | RTR_CM08_Exchange_Rates | 1.13d | Fixed Duration | 4 | 1.13d | 312 | April 9, 2026 2:30 | April 10, 2026 3:30 | 4/9/26 2:30 | 4/10/26 3:30 | 4/9/26 2:30 | 4/10/26 3:30 | 0d | 0d | 0ed | 1 | 4/9/26 2:30 | 4/10/26 3:30 | April 9, 2026 2:30 | April 10, 2026 3:30 | As Soon As Possible | NA | 4/9/26 3:30 | 4/9/26 3:30 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.11 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
320 | 796 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 5 | 0.13d | 317 | April 9, 2026 2:30 | April 9, 2026 3:30 | 4/9/26 2:30 | 4/9/26 3:30 | 4/9/26 2:30 | 4/9/26 3:30 | 0h | 0h | 0ed | 1 | 4/9/26 2:30 | 4/9/26 3:30 | April 9, 2026 2:30 | April 9, 2026 3:30 | As Soon As Possible | NA | 4/9/26 3:30 | 4/9/26 3:30 | 3/30/26 6:34 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.11.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
321 | 797 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 320 | April 9, 2026 3:30 | April 10, 2026 8:30 | 4/9/26 3:30 | 4/10/26 8:30 | 4/9/26 3:30 | 4/10/26 8:30 | 0h | 0h | 0ed | 1 | 4/9/26 3:30 | 4/10/26 8:30 | April 9, 2026 3:30 | April 10, 2026 8:30 | As Soon As Possible | NA | 4/10/26 8:30 | 4/10/26 8:30 | 3/30/26 6:34 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.11.2 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
322 | 798 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 321 | April 10, 2026 8:30 | April 10, 2026 9:30 | 4/10/26 8:30 | 4/10/26 9:30 | 4/10/26 8:30 | 4/10/26 9:30 | 0h | 0h | 0ed | 1 | 4/10/26 8:30 | 4/10/26 9:30 | April 10, 2026 8:30 | April 10, 2026 9:30 | As Soon As Possible | NA | 4/10/26 9:30 | 4/10/26 9:30 | 3/30/26 6:34 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.11.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
323 | 799 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 322 | April 10, 2026 9:30 | April 10, 2026 11:30 | 4/10/26 9:30 | 4/10/26 11:30 | 4/10/26 9:30 | 4/10/26 11:30 | 0h | 0h | 0ed | 1 | 4/10/26 9:30 | 4/10/26 11:30 | April 10, 2026 9:30 | April 10, 2026 11:30 | As Soon As Possible | NA | 4/10/26 11:30 | 4/10/26 11:30 | 3/30/26 6:34 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.11.4 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
324 | 800 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 323 | April 10, 2026 11:30 | April 10, 2026 1:30 | 4/10/26 11:30 | 4/10/26 1:30 | 4/10/26 11:30 | 4/10/26 1:30 | 0h | 0h | 0ed | 1 | 4/10/26 11:30 | 4/10/26 1:30 | April 10, 2026 11:30 | April 10, 2026 1:30 | As Soon As Possible | NA | 4/10/26 1:30 | 4/10/26 1:30 | 3/30/26 6:34 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.11.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
325 | 801 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 324 | April 10, 2026 1:30 | April 10, 2026 3:30 | 4/10/26 1:30 | 4/10/26 3:30 | 4/10/26 1:30 | 4/10/26 3:30 | 0h | 0h | 0ed | 1 | 4/10/26 1:30 | 4/10/26 3:30 | April 10, 2026 1:30 | April 10, 2026 3:30 | As Soon As Possible | NA | 4/10/26 3:30 | 4/10/26 3:30 | 3/30/26 6:34 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.11.6 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
326 | 761 | Yes | Auto Scheduled | RTR_CM14_Cost Element_Group | 5.38d | Fixed Duration | 4 | 4.78d | 319 | April 15, 2026 8:00 | April 22, 2026 11:00 | 4/15/26 8:00 | 4/22/26 11:00 | 4/15/26 8:00 | 4/22/26 11:00 | 0d | 0d | 0ed | 1 | 4/15/26 8:00 | 4/22/26 11:00 | April 8, 2026 3:45 | April 15, 2026 2:00 | As Soon As Possible | NA | 4/15/26 8:30 | 4/15/26 8:30 | 3/25/26 2:32 | 78.5h | 38.25h | 78.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.12 | 500 | No | Yes | Yes |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
327 | 814 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 4.16d | 276 | April 15, 2026 8:00 | April 15, 2026 8:30 | 4/15/26 8:00 | 4/15/26 8:30 | 4/15/26 8:00 | 4/15/26 8:30 | 0m | 0m | 0ed | 1 | 4/15/26 8:00 | 4/15/26 8:30 | April 8, 2026 3:45 | April 14, 2026 5:00 | Finish No Earlier Than | 4/14/26 5:00 | 4/15/26 8:30 | 4/15/26 8:30 | 3/30/26 6:35 | 0.5h | 33.25h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.12.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
328 | 815 | Yes | Auto Scheduled | Load | 32h | Fixed Units | 5 | 0.25d | 327 | April 16, 2026 8:00 | April 21, 2026 5:00 | 4/16/26 8:00 | 4/21/26 5:00 | 4/16/26 8:00 | 4/21/26 5:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/21/26 5:00 | April 15, 2026 8:00 | April 15, 2026 10:00 | Finish No Earlier Than | 4/21/26 5:00 | 4/21/26 5:00 | 4/21/26 5:00 | 3/30/26 6:35 | 32h | 2h | 32h | 0 | 0 | 0 | 0 | 0 | 1.2.1.12.2 | 500 | No | No | No |  |  | GreenSquare | 2026-04-20 15:36 - jsw73 - Start ignored — already in progress | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
329 | 816 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 328 | April 22, 2026 8:00 | April 22, 2026 11:00 | 4/22/26 8:00 | 4/22/26 11:00 | 4/22/26 8:00 | 4/22/26 11:00 | 0h | 0h | 0ed | 1 | 4/22/26 8:00 | 4/22/26 11:00 | April 15, 2026 10:00 | April 15, 2026 2:00 | Start No Earlier Than | 4/17/26 8:00 | 4/22/26 11:00 | 4/22/26 11:00 | 3/30/26 6:35 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.12.3 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
330 | 764 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Bill-To | 2h | Fixed Units | 4 | 0d | 326 | April 16, 2026 8:00 | April 16, 2026 10:00 | 4/16/26 8:00 | 4/16/26 10:00 | 4/16/26 8:00 | 4/16/26 10:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 10:00 | April 16, 2025 8:00 | April 16, 2025 8:00 | As Soon As Possible | NA | 4/16/26 10:00 | 4/16/26 10:00 | 3/25/26 2:32 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.1.13 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
331 | 763 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Ship-To | 2.16d | Fixed Duration | 4 | 3.13d | 330 | April 8, 2026 3:45 | April 10, 2026 5:00 | 4/8/26 3:45 | 4/10/26 5:00 | 4/8/26 3:45 | 4/10/26 5:00 | 0d | 0d | 0ed | 1 | 4/8/26 3:45 | 4/10/26 5:00 | April 8, 2026 3:45 | April 13, 2026 4:45 | As Soon As Possible | NA | 4/8/26 4:15 | 4/8/26 4:15 | 3/25/26 2:32 | 13.25h | 36h | 13.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.14 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
332 | 823 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 276 | April 8, 2026 3:45 | April 8, 2026 4:15 | 4/8/26 3:45 | 4/8/26 4:15 | 4/8/26 3:45 | 4/8/26 4:15 | 0m | 0m | 0ed | 1 | 4/8/26 3:45 | 4/8/26 4:15 | April 8, 2026 3:45 | April 8, 2026 4:15 | As Soon As Possible | NA | 4/8/26 4:15 | 4/8/26 4:15 | 3/30/26 7:59 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.14.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
333 | 824 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 332 | April 8, 2026 4:15 | April 8, 2026 4:45 | 4/8/26 4:15 | 4/8/26 4:45 | 4/8/26 4:15 | 4/8/26 4:45 | 0m | 0m | 0ed | 1 | 4/8/26 4:15 | 4/8/26 4:45 | April 8, 2026 4:15 | April 8, 2026 4:45 | As Soon As Possible | NA | 4/8/26 4:45 | 4/8/26 4:45 | 3/30/26 7:59 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.14.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
334 | 1231 | Yes | Auto Scheduled | Open client for BP number range update | 30m | Fixed Units | 5 | 1d | 333 | April 8, 2026 4:45 | April 9, 2026 8:15 | 4/8/26 4:45 | 4/9/26 8:15 | 4/8/26 4:45 | 4/9/26 8:15 | 0m | 0m | 0ed | 1 | 4/8/26 4:45 | 4/9/26 8:15 | April 8, 2026 4:45 | April 9, 2026 4:45 | As Soon As Possible | NA | 4/9/26 8:15 | 4/9/26 8:15 | 4/8/26 9:06 | 0.5h | 8h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.14.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
335 | 1232 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 30m | Fixed Units | 5 | 1d | 334 | April 9, 2026 4:45 | April 10, 2026 8:15 | 4/9/26 4:45 | 4/10/26 8:15 | 4/9/26 4:45 | 4/10/26 8:15 | 0m | 0m | 0ed | 1 | 4/9/26 4:45 | 4/10/26 8:15 | April 9, 2026 4:45 | April 10, 2026 4:45 | As Soon As Possible | NA | 4/10/26 8:15 | 4/10/26 8:15 | 4/8/26 9:07 | 0.5h | 8h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.14.4 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
336 | 1233 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 5 | 1d | 335 | April 10, 2026 4:45 | April 10, 2026 5:00 | 4/10/26 4:45 | 4/10/26 5:00 | 4/10/26 4:45 | 4/10/26 5:00 | 0m | 0m | 0ed | 1 | 4/10/26 4:45 | 4/10/26 5:00 | April 10, 2026 4:45 | April 13, 2026 4:45 | As Soon As Possible | NA | 4/10/26 5:00 | 4/10/26 5:00 | 4/8/26 9:07 | 0.25h | 8h | 0.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.14.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
337 | 825 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 333 | April 8, 2026 4:45 | April 9, 2026 8:45 | 4/8/26 4:45 | 4/9/26 8:45 | 4/8/26 4:45 | 4/9/26 8:45 | 0h | 0h | 0ed | 1 | 4/8/26 4:45 | 4/9/26 8:45 | April 8, 2026 4:45 | April 9, 2026 8:45 | As Soon As Possible | NA | 4/9/26 8:45 | 4/9/26 8:45 | 3/30/26 7:59 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.14.6 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
338 | 826 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | Fixed Units | 5 | 0.5d | 337 | April 9, 2026 8:45 | April 9, 2026 1:45 | 4/9/26 8:45 | 4/9/26 1:45 | 4/9/26 8:45 | 4/9/26 1:45 | 0h | 0h | 0ed | 1 | 4/9/26 8:45 | 4/9/26 1:45 | April 9, 2026 8:45 | April 9, 2026 1:45 | As Soon As Possible | NA | 4/9/26 1:45 | 4/9/26 1:45 | 3/30/26 7:59 | 4h | 4h | 4h | 0 | 0 | 0 | 0 | 0 | 1.2.1.14.7 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
339 | 827 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 5 | 0.38d | 338 | April 9, 2026 1:45 | April 9, 2026 4:45 | 4/9/26 1:45 | 4/9/26 4:45 | 4/9/26 1:45 | 4/9/26 4:45 | 0h | 0h | 0ed | 1 | 4/9/26 1:45 | 4/9/26 4:45 | April 9, 2026 1:45 | April 9, 2026 4:45 | As Soon As Possible | NA | 4/9/26 4:45 | 4/9/26 4:45 | 3/30/26 7:59 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.14.8 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
340 | 828 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 339 | April 9, 2026 4:45 | April 10, 2026 10:45 | 4/9/26 4:45 | 4/10/26 10:45 | 4/9/26 4:45 | 4/10/26 10:45 | 0h | 0h | 0ed | 1 | 4/9/26 4:45 | 4/10/26 10:45 | April 9, 2026 4:45 | April 10, 2026 10:45 | As Soon As Possible | NA | 4/10/26 10:45 | 4/10/26 10:45 | 3/30/26 7:59 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.14.9 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
341 | 762 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Sold-To | 1.63d | Fixed Duration | 4 | 1.63d | 331 | April 8, 2026 4:45 | April 10, 2026 1:45 | 4/8/26 4:45 | 4/10/26 1:45 | 4/8/26 4:45 | 4/10/26 1:45 | 0d | 0d | 0ed | 1 | 4/8/26 4:45 | 4/10/26 1:45 | April 8, 2026 4:45 | April 10, 2026 1:45 | As Soon As Possible | NA | 4/9/26 8:15 | 4/9/26 8:15 | 3/25/26 2:32 | 11.75h | 11.75h | 11.75h | 0 | 0 | 0 | 0 | 0 | 1.2.1.15 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
342 | 817 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 333 | April 8, 2026 4:45 | April 9, 2026 8:15 | 4/8/26 4:45 | 4/9/26 8:15 | 4/8/26 4:45 | 4/9/26 8:15 | 0m | 0m | 0ed | 1 | 4/8/26 4:45 | 4/9/26 8:15 | April 8, 2026 4:45 | April 9, 2026 8:15 | As Soon As Possible | NA | 4/9/26 8:15 | 4/9/26 8:15 | 3/30/26 7:57 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.15.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
343 | 818 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 342 | April 9, 2026 8:15 | April 9, 2026 8:45 | 4/9/26 8:15 | 4/9/26 8:45 | 4/9/26 8:15 | 4/9/26 8:45 | 0m | 0m | 0ed | 1 | 4/9/26 8:15 | 4/9/26 8:45 | April 9, 2026 8:15 | April 9, 2026 8:45 | As Soon As Possible | NA | 4/9/26 8:45 | 4/9/26 8:45 | 3/30/26 7:57 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.15.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
344 | 819 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 337,278 | April 9, 2026 10:45 | April 9, 2026 11:45 | 4/9/26 10:45 | 4/9/26 11:45 | 4/9/26 10:45 | 4/9/26 11:45 | 0h | 0h | 0ed | 1 | 4/9/26 10:45 | 4/9/26 11:45 | April 9, 2026 10:45 | April 9, 2026 11:45 | As Soon As Possible | NA | 4/9/26 11:45 | 4/9/26 11:45 | 3/30/26 7:57 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.15.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
345 | 820 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | Fixed Units | 5 | 0.38d | 344 | April 9, 2026 11:45 | April 9, 2026 3:45 | 4/9/26 11:45 | 4/9/26 3:45 | 4/9/26 11:45 | 4/9/26 3:45 | 0h | 0h | 0ed | 1 | 4/9/26 11:45 | 4/9/26 3:45 | April 9, 2026 11:45 | April 9, 2026 3:45 | As Soon As Possible | NA | 4/9/26 3:45 | 4/9/26 3:45 | 3/30/26 7:57 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.15.4 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
346 | 821 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 5 | 0.38d | 345 | April 9, 2026 3:45 | April 10, 2026 9:45 | 4/9/26 3:45 | 4/10/26 9:45 | 4/9/26 3:45 | 4/10/26 9:45 | 0h | 0h | 0ed | 1 | 4/9/26 3:45 | 4/10/26 9:45 | April 9, 2026 3:45 | April 10, 2026 9:45 | As Soon As Possible | NA | 4/10/26 9:45 | 4/10/26 9:45 | 3/30/26 7:57 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.15.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
347 | 822 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 346 | April 10, 2026 9:45 | April 10, 2026 1:45 | 4/10/26 9:45 | 4/10/26 1:45 | 4/10/26 9:45 | 4/10/26 1:45 | 0h | 0h | 0ed | 1 | 4/10/26 9:45 | 4/10/26 1:45 | April 10, 2026 9:45 | April 10, 2026 1:45 | As Soon As Possible | NA | 4/10/26 1:45 | 4/10/26 1:45 | 3/30/26 7:57 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.15.6 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
348 | 1240 | Yes | Auto Scheduled | Open client for BP number range update | 15m | Fixed Units | 5 | 0.03d | 337 | April 9, 2026 8:45 | April 9, 2026 9:00 | 4/9/26 8:45 | 4/9/26 9:00 | 4/9/26 8:45 | 4/9/26 9:00 | 0m | 0m | 0ed | 1 | 4/9/26 8:45 | 4/9/26 9:00 | April 9, 2026 8:45 | April 9, 2026 9:00 | As Soon As Possible | NA | 4/9/26 9:00 | 4/9/26 9:00 | 4/8/26 9:09 | 0.25h | 0.25h | 0.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.15.7 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
349 | 1241 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 15m | Fixed Units | 5 | 0.03d | 348 | April 9, 2026 9:00 | April 9, 2026 9:15 | 4/9/26 9:00 | 4/9/26 9:15 | 4/9/26 9:00 | 4/9/26 9:15 | 0m | 0m | 0ed | 1 | 4/9/26 9:00 | 4/9/26 9:15 | April 9, 2026 9:00 | April 9, 2026 9:15 | As Soon As Possible | NA | 4/9/26 9:15 | 4/9/26 9:15 | 4/8/26 9:09 | 0.25h | 0.25h | 0.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.15.8 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
350 | 1242 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 5 | 0.03d | 349 | April 9, 2026 9:15 | April 9, 2026 9:30 | 4/9/26 9:15 | 4/9/26 9:30 | 4/9/26 9:15 | 4/9/26 9:30 | 0m | 0m | 0ed | 1 | 4/9/26 9:15 | 4/9/26 9:30 | April 9, 2026 9:15 | April 9, 2026 9:30 | As Soon As Possible | NA | 4/9/26 9:30 | 4/9/26 9:30 | 4/8/26 9:09 | 0.25h | 0.25h | 0.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.15.9 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
351 | 765 | Yes | Auto Scheduled | PTP_CM27_Vendor Master as Customer - FLCU01 | 2.31d | Fixed Duration | 4 | 2.31d | 341 | April 10, 2026 9:45 | April 14, 2026 1:15 | 4/10/26 9:45 | 4/14/26 1:15 | 4/10/26 9:45 | 4/14/26 1:15 | 0d | 0d | 0ed | 1 | 4/10/26 9:45 | 4/14/26 1:15 | April 10, 2026 9:45 | April 14, 2026 1:15 | As Soon As Possible | NA | 4/10/26 10:45 | 4/10/26 10:45 | 3/25/26 2:32 | 19.25h | 19.25h | 19.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.16 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
352 | 972 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 5 | 0.13d | 346 | April 10, 2026 9:45 | April 10, 2026 10:45 | 4/10/26 9:45 | 4/10/26 10:45 | 4/10/26 9:45 | 4/10/26 10:45 | 0h | 0h | 0ed | 1 | 4/10/26 9:45 | 4/10/26 10:45 | April 10, 2026 9:45 | April 10, 2026 10:45 | As Soon As Possible | NA | 4/10/26 10:45 | 4/10/26 10:45 | 4/1/26 2:18 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.16.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
353 | 973 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 352 | April 10, 2026 10:45 | April 10, 2026 1:45 | 4/10/26 10:45 | 4/10/26 1:45 | 4/10/26 10:45 | 4/10/26 1:45 | 0h | 0h | 0ed | 1 | 4/10/26 10:45 | 4/10/26 1:45 | April 10, 2026 10:45 | April 10, 2026 1:45 | As Soon As Possible | NA | 4/10/26 1:45 | 4/10/26 1:45 | 4/1/26 2:18 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.16.2 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
354 | 974 | Yes | Auto Scheduled | Simulate Load | 11.25h | Fixed Units | 5 | 1.41d | 353,318 | April 10, 2026 1:45 | April 13, 2026 5:00 | 4/10/26 1:45 | 4/13/26 5:00 | 4/10/26 1:45 | 4/13/26 5:00 | 0h | 0h | 0ed | 1 | 4/10/26 1:45 | 4/13/26 5:00 | April 10, 2026 1:45 | April 13, 2026 5:00 | Finish No Earlier Than | 4/13/26 5:00 | 4/13/26 5:00 | 4/13/26 5:00 | 4/1/26 2:18 | 11.25h | 11.25h | 11.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.16.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
355 | 975 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 354 | April 10, 2026 2:45 | April 14, 2026 9:30 | 4/10/26 2:45 | 4/14/26 9:30 | 4/10/26 2:45 | 4/14/26 9:30 | 0h | 0h | 0ed | 1 | 4/10/26 2:45 | 4/14/26 9:30 | April 10, 2026 2:45 | April 14, 2026 9:30 | As Soon As Possible | NA | 4/14/26 9:30 | 4/14/26 9:30 | 4/1/26 2:18 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.16.4 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
356 | 976 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 355 | April 10, 2026 4:45 | April 14, 2026 10:15 | 4/10/26 4:45 | 4/14/26 10:15 | 4/10/26 4:45 | 4/14/26 10:15 | 0h | 0h | 0ed | 1 | 4/10/26 4:45 | 4/14/26 10:15 | April 10, 2026 4:45 | April 14, 2026 10:15 | As Soon As Possible | NA | 4/14/26 10:15 | 4/14/26 10:15 | 4/1/26 2:18 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.16.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
357 | 977 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 356 | April 14, 2026 10:15 | April 14, 2026 1:15 | 4/14/26 10:15 | 4/14/26 1:15 | 4/14/26 10:15 | 4/14/26 1:15 | 0h | 0h | 0ed | 1 | 4/14/26 10:15 | 4/14/26 1:15 | April 14, 2026 10:15 | April 14, 2026 1:15 | As Soon As Possible | NA | 4/14/26 1:15 | 4/14/26 1:15 | 4/1/26 2:18 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.16.6 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
358 | 771 | Yes | Auto Scheduled | OTC_CM23_Customer_Hierarchy | 3.03d | Fixed Duration | 4 | 0.69d | 351 | April 10, 2026 9:45 | April 15, 2026 10:00 | 4/10/26 9:45 | 4/15/26 10:00 | 4/10/26 9:45 | 4/15/26 10:00 | 0d | 0d | 0ed | 1 | 4/10/26 9:45 | 4/15/26 10:00 | April 10, 2026 9:45 | April 10, 2026 4:15 | As Soon As Possible | NA | 4/10/26 10:15 | 4/10/26 10:15 | 3/25/26 2:32 | 5.5h | 5.5h | 5.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.17 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
359 | 984 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 346 | April 10, 2026 9:45 | April 10, 2026 10:15 | 4/10/26 9:45 | 4/10/26 10:15 | 4/10/26 9:45 | 4/10/26 10:15 | 0m | 0m | 0ed | 1 | 4/10/26 9:45 | 4/10/26 10:15 | April 10, 2026 9:45 | April 10, 2026 10:15 | Start No Earlier Than | 4/6/26 8:00 | 4/10/26 10:15 | 4/10/26 10:15 | 4/1/26 2:20 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.17.1 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
360 | 985 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 359 | April 15, 2026 8:00 | April 15, 2026 10:00 | 4/15/26 8:00 | 4/15/26 10:00 | 4/15/26 8:00 | 4/15/26 10:00 | 0h | 0h | 0ed | 1 | 4/15/26 8:00 | 4/15/26 10:00 | April 10, 2026 10:15 | April 10, 2026 1:15 | Start No Earlier Than | 4/15/26 8:00 | 4/15/26 10:00 | 4/15/26 10:00 | 4/1/26 2:20 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.17.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
361 | 986 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 360 | April 10, 2026 1:15 | April 10, 2026 4:15 | 4/10/26 1:15 | 4/10/26 4:15 | 4/10/26 1:15 | 4/10/26 4:15 | 0h | 0h | 0ed | 1 | 4/10/26 1:15 | 4/10/26 4:15 | April 10, 2026 1:15 | April 10, 2026 4:15 | As Soon As Possible | NA | 4/10/26 4:15 | 4/10/26 4:15 | 4/1/26 2:20 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.17.3 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
362 | 766 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Z001 - External Sales Rep | 3.38d | Fixed Duration | 4 | 1.13d | 358 | April 10, 2026 9:45 | April 15, 2026 1:45 | 4/10/26 9:45 | 4/15/26 1:45 | 4/10/26 9:45 | 4/15/26 1:45 | 0d | 0d | 0ed | 1 | 4/10/26 9:45 | 4/15/26 1:45 | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | 4/10/26 10:45 | 4/10/26 10:45 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.18 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
363 | 987 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 5 | 0.13d | 346 | April 10, 2026 9:45 | April 10, 2026 10:45 | 4/10/26 9:45 | 4/10/26 10:45 | 4/10/26 9:45 | 4/10/26 10:45 | 0h | 0h | 0ed | 1 | 4/10/26 9:45 | 4/10/26 10:45 | April 10, 2026 9:45 | April 10, 2026 10:45 | As Soon As Possible | NA | 4/10/26 10:45 | 4/10/26 10:45 | 4/1/26 2:21 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.18.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
364 | 988 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 363 | April 10, 2026 10:45 | April 10, 2026 1:45 | 4/10/26 10:45 | 4/10/26 1:45 | 4/10/26 10:45 | 4/10/26 1:45 | 0h | 0h | 0ed | 1 | 4/10/26 10:45 | 4/10/26 1:45 | April 10, 2026 10:45 | April 10, 2026 1:45 | As Soon As Possible | NA | 4/10/26 1:45 | 4/10/26 1:45 | 4/1/26 2:21 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.18.2 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
365 | 989 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 364,318 | April 10, 2026 1:45 | April 10, 2026 2:45 | 4/10/26 1:45 | 4/10/26 2:45 | 4/10/26 1:45 | 4/10/26 2:45 | 0h | 0h | 0ed | 1 | 4/10/26 1:45 | 4/10/26 2:45 | April 10, 2026 1:45 | April 10, 2026 2:45 | As Soon As Possible | NA | 4/10/26 2:45 | 4/10/26 2:45 | 4/1/26 2:21 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.18.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
366 | 990 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 365 | April 15, 2026 8:00 | April 15, 2026 10:00 | 4/15/26 8:00 | 4/15/26 10:00 | 4/15/26 8:00 | 4/15/26 10:00 | 0h | 0h | 0ed | 1 | 4/15/26 8:00 | 4/15/26 10:00 | April 10, 2026 2:45 | April 10, 2026 4:45 | As Soon As Possible | NA | 4/15/26 10:00 | 4/15/26 10:00 | 4/1/26 2:21 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.18.4 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
367 | 991 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 366 | April 10, 2026 4:45 | April 15, 2026 10:45 | 4/10/26 4:45 | 4/15/26 10:45 | 4/10/26 4:45 | 4/15/26 10:45 | 0h | 0h | 0ed | 1 | 4/10/26 4:45 | 4/15/26 10:45 | April 10, 2026 4:45 | April 13, 2026 8:45 | As Soon As Possible | NA | 4/15/26 10:45 | 4/15/26 10:45 | 4/1/26 2:21 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.18.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
368 | 992 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 367 | April 15, 2026 10:45 | April 15, 2026 1:45 | 4/15/26 10:45 | 4/15/26 1:45 | 4/15/26 10:45 | 4/15/26 1:45 | 0h | 0h | 0ed | 1 | 4/15/26 10:45 | 4/15/26 1:45 | April 13, 2026 8:45 | April 13, 2026 10:45 | As Soon As Possible | NA | 4/15/26 1:45 | 4/15/26 1:45 | 4/1/26 2:21 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.18.6 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
369 | 768 | Yes | Auto Scheduled | RTR_CM10_Credit_Management_Role | 5.56d | Fixed Duration | 4 | 1.13d | 362 | April 10, 2026 9:45 | April 17, 2026 3:15 | 4/10/26 9:45 | 4/17/26 3:15 | 4/10/26 9:45 | 4/17/26 3:15 | 0d | 0d | 0ed | 1 | 4/10/26 9:45 | 4/17/26 3:15 | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | 4/10/26 10:15 | 4/10/26 10:15 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.19 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
370 | 993 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 346 | April 10, 2026 9:45 | April 10, 2026 10:15 | 4/10/26 9:45 | 4/10/26 10:15 | 4/10/26 9:45 | 4/10/26 10:15 | 0m | 0m | 0ed | 1 | 4/10/26 9:45 | 4/10/26 10:15 | April 10, 2026 9:45 | April 10, 2026 10:15 | As Soon As Possible | NA | 4/10/26 10:15 | 4/10/26 10:15 | 4/1/26 2:22 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.19.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
371 | 994 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 370 | April 10, 2026 10:15 | April 10, 2026 10:45 | 4/10/26 10:15 | 4/10/26 10:45 | 4/10/26 10:15 | 4/10/26 10:45 | 0m | 0m | 0ed | 1 | 4/10/26 10:15 | 4/10/26 10:45 | April 10, 2026 10:15 | April 10, 2026 10:45 | As Soon As Possible | NA | 4/10/26 10:45 | 4/10/26 10:45 | 4/1/26 2:22 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.19.2 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
372 | 995 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 371 | April 17, 2026 8:00 | April 17, 2026 9:00 | 4/17/26 8:00 | 4/17/26 9:00 | 4/17/26 8:00 | 4/17/26 9:00 | 0h | 0h | 0ed | 1 | 4/17/26 8:00 | 4/17/26 9:00 | April 10, 2026 10:45 | April 10, 2026 11:45 | As Soon As Possible | NA | 4/17/26 9:00 | 4/17/26 9:00 | 4/1/26 2:22 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.19.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
373 | 996 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 372 | April 17, 2026 8:00 | April 17, 2026 10:30 | 4/17/26 8:00 | 4/17/26 10:30 | 4/17/26 8:00 | 4/17/26 10:30 | 0h | 0h | 0ed | 1 | 4/17/26 8:00 | 4/17/26 10:30 | April 10, 2026 11:45 | April 10, 2026 2:45 | As Soon As Possible | NA | 4/17/26 10:30 | 4/17/26 10:30 | 4/1/26 2:22 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.19.4 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
374 | 997 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 373 | April 17, 2026 8:00 | April 17, 2026 12:00 | 4/17/26 8:00 | 4/17/26 12:00 | 4/17/26 8:00 | 4/17/26 12:00 | 0h | 0h | 0ed | 1 | 4/17/26 8:00 | 4/17/26 12:00 | April 10, 2026 2:45 | April 10, 2026 4:45 | As Soon As Possible | NA | 4/17/26 12:00 | 4/17/26 12:00 | 4/1/26 2:22 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.19.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
375 | 998 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 374 | April 17, 2026 8:00 | April 17, 2026 3:15 | 4/17/26 8:00 | 4/17/26 3:15 | 4/17/26 8:00 | 4/17/26 3:15 | 0h | 0h | 0ed | 1 | 4/17/26 8:00 | 4/17/26 3:15 | April 10, 2026 4:45 | April 13, 2026 10:45 | As Soon As Possible | NA | 4/17/26 3:15 | 4/17/26 3:15 | 4/1/26 2:22 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.19.6 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
376 | 752 | Yes | Auto Scheduled | PTP_CM27_Vendor Master | 3.72d | Fixed Duration | 4 | 2.91d | 369 | April 10, 2026 10:45 | April 16, 2026 8:30 | 4/10/26 10:45 | 4/16/26 8:30 | 4/10/26 10:45 | 4/16/26 8:30 | 0d | 0d | 0ed | 1 | 4/10/26 10:45 | 4/16/26 8:30 | April 10, 2026 10:45 | April 15, 2026 10:00 | As Soon As Possible | NA | 4/10/26 11:45 | 4/10/26 11:45 | 3/25/26 2:32 | 10.25h | 9h | 10.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.20 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
377 | 999 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 5 | 0.13d | 363 | April 10, 2026 10:45 | April 10, 2026 11:45 | 4/10/26 10:45 | 4/10/26 11:45 | 4/10/26 10:45 | 4/10/26 11:45 | 0h | 0h | 0ed | 1 | 4/10/26 10:45 | 4/10/26 11:45 | April 10, 2026 10:45 | April 10, 2026 11:45 | As Soon As Possible | NA | 4/10/26 11:45 | 4/10/26 11:45 | 4/1/26 2:24 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.20.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
378 | 1000 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 377 | April 10, 2026 11:45 | April 10, 2026 2:45 | 4/10/26 11:45 | 4/10/26 2:45 | 4/10/26 11:45 | 4/10/26 2:45 | 0h | 0h | 0ed | 1 | 4/10/26 11:45 | 4/10/26 2:45 | April 10, 2026 11:45 | April 10, 2026 2:45 | As Soon As Possible | NA | 4/10/26 2:45 | 4/10/26 2:45 | 4/1/26 2:24 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.20.2 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
379 | 1001 | Yes | Auto Scheduled | Simulate Load | 2.25h | Fixed Units | 5 | 0.13d | 378 | April 10, 2026 2:45 | April 10, 2026 5:00 | 4/10/26 2:45 | 4/10/26 5:00 | 4/10/26 2:45 | 4/10/26 5:00 | 0h | 0h | 0ed | 1 | 4/10/26 2:45 | 4/10/26 5:00 | April 10, 2026 2:45 | April 14, 2026 2:00 | Finish No Earlier Than | 4/10/26 5:00 | 4/10/26 5:00 | 4/10/26 5:00 | 4/1/26 2:24 | 2.25h | 1h | 2.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.20.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
380 | 1002 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 379 | April 13, 2026 8:00 | April 13, 2026 2:30 | 4/13/26 8:00 | 4/13/26 2:30 | 4/13/26 8:00 | 4/13/26 2:30 | 0h | 0h | 0ed | 1 | 4/13/26 8:00 | 4/13/26 2:30 | April 14, 2026 2:00 | April 14, 2026 4:00 | As Soon As Possible | NA | 4/13/26 2:30 | 4/13/26 2:30 | 4/1/26 2:24 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.20.4 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
381 | 1003 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d |  | April 15, 2026 2:30 | April 15, 2026 3:30 | 4/15/26 2:30 | 4/15/26 3:30 | 4/15/26 2:30 | 4/15/26 3:30 | 0h | 0h | 0ed | 1 | 4/15/26 2:30 | 4/15/26 3:30 | April 14, 2026 4:00 | April 14, 2026 5:00 | As Soon As Possible | NA | 4/15/26 3:30 | 4/15/26 3:30 | 4/1/26 2:24 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.20.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
382 | 1004 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 381 | April 15, 2026 3:30 | April 16, 2026 8:30 | 4/15/26 3:30 | 4/16/26 8:30 | 4/15/26 3:30 | 4/16/26 8:30 | 0h | 0h | 0ed | 1 | 4/15/26 3:30 | 4/16/26 8:30 | April 15, 2026 8:00 | April 15, 2026 10:00 | As Soon As Possible | NA | 4/16/26 8:30 | 4/16/26 8:30 | 4/1/26 2:24 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.20.6 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
383 | 692 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | 0.88d | Fixed Duration | 4 | 3.16d | 376 | April 16, 2026 8:00 | April 16, 2026 4:00 | 4/16/26 8:00 | 4/16/26 4:00 | 4/16/26 8:00 | 4/16/26 4:00 | 0d | 0d | 0ed | 1 | 4/16/26 8:00 | 4/16/26 4:00 | April 10, 2026 11:45 | April 15, 2026 2:00 | As Soon As Possible | NA | 4/16/26 9:00 | 4/16/26 9:00 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.21 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
384 | 1005 | Yes | Auto Scheduled | Extract File(Will Extract from LFA1) | 1h | Fixed Units | 5 | 0.13d |  | April 16, 2026 8:00 | April 16, 2026 9:00 | 4/16/26 8:00 | 4/16/26 9:00 | 4/16/26 8:00 | 4/16/26 9:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 9:00 | April 10, 2026 11:45 | April 10, 2026 1:45 | Start No Earlier Than | 4/16/26 8:00 | 4/16/26 9:00 | 4/16/26 9:00 | 4/1/26 2:33 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.21.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
385 | 1006 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 384 | April 16, 2026 9:00 | April 16, 2026 11:00 | 4/16/26 9:00 | 4/16/26 11:00 | 4/16/26 9:00 | 4/16/26 11:00 | 0h | 0h | 0ed | 1 | 4/16/26 9:00 | 4/16/26 11:00 | April 10, 2026 1:45 | April 10, 2026 3:45 | As Soon As Possible | NA | 4/16/26 11:00 | 4/16/26 11:00 | 4/1/26 2:33 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.21.2 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
386 | 1007 | Yes | Auto Scheduled | Simulate Load/ Not Needed | 1h | Fixed Units | 5 | 0.13d | 385 | April 16, 2026 11:00 | April 16, 2026 12:00 | 4/16/26 11:00 | 4/16/26 12:00 | 4/16/26 11:00 | 4/16/26 12:00 | 0h | 0h | 0ed | 1 | 4/16/26 11:00 | 4/16/26 12:00 | April 10, 2026 3:45 | April 10, 2026 4:45 | As Soon As Possible | NA | 4/16/26 12:00 | 4/16/26 12:00 | 4/1/26 2:33 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.21.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
387 | 1008 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 386 | April 16, 2026 1:00 | April 16, 2026 3:00 | 4/16/26 1:00 | 4/16/26 3:00 | 4/16/26 1:00 | 4/16/26 3:00 | 0h | 0h | 0ed | 1 | 4/16/26 1:00 | 4/16/26 3:00 | April 10, 2026 4:45 | April 13, 2026 9:45 | As Soon As Possible | NA | 4/16/26 3:00 | 4/16/26 3:00 | 4/1/26 2:33 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.21.4 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
388 | 1009 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 386 | April 16, 2026 1:00 | April 16, 2026 2:00 | 4/16/26 1:00 | 4/16/26 2:00 | 4/16/26 1:00 | 4/16/26 2:00 | 0h | 0h | 0ed | 1 | 4/16/26 1:00 | 4/16/26 2:00 | April 15, 2026 10:00 | April 15, 2026 11:00 | As Soon As Possible | NA | 4/16/26 2:00 | 4/16/26 2:00 | 4/1/26 2:33 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.21.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
389 | 1010 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 388 | April 16, 2026 2:00 | April 16, 2026 4:00 | 4/16/26 2:00 | 4/16/26 4:00 | 4/16/26 2:00 | 4/16/26 4:00 | 0h | 0h | 0ed | 1 | 4/16/26 2:00 | 4/16/26 4:00 | April 15, 2026 11:00 | April 15, 2026 2:00 | As Soon As Possible | NA | 4/16/26 4:00 | 4/16/26 4:00 | 4/1/26 2:33 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.21.6 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
390 | 935 | Yes | Auto Scheduled | RTR_****_Credit Hierarchy | 1.38d | Fixed Duration | 4 | 1.25d | 383 | April 15, 2026 8:00 | April 16, 2026 11:00 | 4/15/26 8:00 | 4/16/26 11:00 | 4/15/26 8:00 | 4/16/26 11:00 | 0d | 0d | 0ed | 1 | 4/15/26 8:00 | 4/16/26 11:00 | April 10, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | 4/15/26 8:30 | 4/15/26 8:30 | 3/25/26 2:32 | 5.5h | 5.5h | 5.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.22 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
391 | 1011 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 373 | April 15, 2026 8:00 | April 15, 2026 8:30 | 4/15/26 8:00 | 4/15/26 8:30 | 4/15/26 8:00 | 4/15/26 8:30 | 0m | 0m | 0ed | 1 | 4/15/26 8:00 | 4/15/26 8:30 | April 10, 2026 2:45 | April 10, 2026 3:15 | Start No Earlier Than | 4/15/26 8:00 | 4/15/26 8:30 | 4/15/26 8:30 | 4/1/26 2:34 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.22.1 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
392 | 1012 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 375 | April 15, 2026 8:00 | April 15, 2026 10:00 | 4/15/26 8:00 | 4/15/26 10:00 | 4/15/26 8:00 | 4/15/26 10:00 | 0h | 0h | 0ed | 1 | 4/15/26 8:00 | 4/15/26 10:00 | April 13, 2026 10:45 | April 13, 2026 1:45 | As Soon As Possible | NA | 4/15/26 10:00 | 4/15/26 10:00 | 4/1/26 2:34 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.22.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
393 | 1013 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 392 | April 16, 2026 8:00 | April 16, 2026 11:00 | 4/16/26 8:00 | 4/16/26 11:00 | 4/16/26 8:00 | 4/16/26 11:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 11:00 | April 13, 2026 1:45 | April 13, 2026 4:45 | As Soon As Possible | NA | 4/16/26 11:00 | 4/16/26 11:00 | 4/1/26 2:34 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.22.3 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
394 | 693 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Supplier | 1.13d | Fixed Duration | 4 | 1.13d | 390 | April 13, 2026 11:45 | April 14, 2026 1:45 | 4/13/26 11:45 | 4/14/26 1:45 | 4/13/26 11:45 | 4/14/26 1:45 | 0d | 0d | 0ed | 1 | 4/13/26 11:45 | 4/14/26 1:45 | April 13, 2026 11:45 | April 14, 2026 1:45 | As Soon As Possible | NA | 4/13/26 1:15 | 4/13/26 1:15 | 3/25/26 2:32 | 15h | 15h | 15h | 0 | 0 | 0 | 0 | 0 | 1.2.1.23 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
395 | 1014 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 382 | April 13, 2026 11:45 | April 13, 2026 1:15 | 4/13/26 11:45 | 4/13/26 1:15 | 4/13/26 11:45 | 4/13/26 1:15 | 0m | 0m | 0ed | 1 | 4/13/26 11:45 | 4/13/26 1:15 | April 13, 2026 11:45 | April 13, 2026 1:15 | As Soon As Possible | NA | 4/13/26 1:15 | 4/13/26 1:15 | 4/1/26 2:36 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.23.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
396 | 1015 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 395 | April 13, 2026 1:15 | April 13, 2026 1:45 | 4/13/26 1:15 | 4/13/26 1:45 | 4/13/26 1:15 | 4/13/26 1:45 | 0m | 0m | 0ed | 1 | 4/13/26 1:15 | 4/13/26 1:45 | April 13, 2026 1:15 | April 13, 2026 1:45 | As Soon As Possible | NA | 4/13/26 1:45 | 4/13/26 1:45 | 4/1/26 2:36 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.23.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
397 | 1016 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 396 | April 13, 2026 1:45 | April 13, 2026 2:45 | 4/13/26 1:45 | 4/13/26 2:45 | 4/13/26 1:45 | 4/13/26 2:45 | 0h | 0h | 0ed | 1 | 4/13/26 1:45 | 4/13/26 2:45 | April 13, 2026 1:45 | April 13, 2026 2:45 | As Soon As Possible | NA | 4/13/26 2:45 | 4/13/26 2:45 | 4/1/26 2:36 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.23.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
398 | 1017 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 397 | April 13, 2026 2:45 | April 13, 2026 4:45 | 4/13/26 2:45 | 4/13/26 4:45 | 4/13/26 2:45 | 4/13/26 4:45 | 0h | 0h | 0ed | 1 | 4/13/26 2:45 | 4/13/26 4:45 | April 13, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | 4/13/26 4:45 | 4/13/26 4:45 | 4/1/26 2:36 | 4h | 4h | 4h | 0 | 0 | 0 | 0 | 0 | 1.2.1.23.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
399 | 1018 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 398 | April 13, 2026 4:45 | April 14, 2026 9:45 | 4/13/26 4:45 | 4/14/26 9:45 | 4/13/26 4:45 | 4/14/26 9:45 | 0h | 0h | 0ed | 1 | 4/13/26 4:45 | 4/14/26 9:45 | April 13, 2026 4:45 | April 14, 2026 9:45 | As Soon As Possible | NA | 4/14/26 9:45 | 4/14/26 9:45 | 4/1/26 2:36 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.23.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
400 | 1019 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 399 | April 14, 2026 9:45 | April 14, 2026 1:45 | 4/14/26 9:45 | 4/14/26 1:45 | 4/14/26 9:45 | 4/14/26 1:45 | 0h | 0h | 0ed | 1 | 4/14/26 9:45 | 4/14/26 1:45 | April 14, 2026 9:45 | April 14, 2026 1:45 | As Soon As Possible | NA | 4/14/26 1:45 | 4/14/26 1:45 | 4/1/26 2:36 | 6h | 6h | 6h | 0 | 0 | 0 | 0 | 0 | 1.2.1.23.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
401 | 1245 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Customer | 1.13d | Fixed Duration | 4 | 1.13d | 394 | April 13, 2026 11:45 | April 14, 2026 1:45 | 4/13/26 11:45 | 4/14/26 1:45 | 4/13/26 11:45 | 4/14/26 1:45 | 0d | 0d | 0ed | 1 | 4/13/26 11:45 | 4/14/26 1:45 | April 13, 2026 11:45 | April 14, 2026 1:45 | As Soon As Possible | NA | 4/13/26 1:15 | 4/13/26 1:15 | 4/8/26 1:33 | 15h | 15h | 15h | 0 | 0 | 0 | 0 | 0 | 1.2.1.24 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
402 | 1246 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d |  | April 13, 2026 11:45 | April 13, 2026 1:15 | 4/13/26 11:45 | 4/13/26 1:15 | 4/13/26 11:45 | 4/13/26 1:15 | 0m | 0m | 0ed | 1 | 4/13/26 11:45 | 4/13/26 1:15 | April 13, 2026 11:45 | April 13, 2026 1:15 | As Soon As Possible | NA | 4/13/26 1:15 | 4/13/26 1:15 | 4/8/26 1:33 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.24.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
403 | 1247 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d |  | April 13, 2026 1:15 | April 13, 2026 1:45 | 4/13/26 1:15 | 4/13/26 1:45 | 4/13/26 1:15 | 4/13/26 1:45 | 0m | 0m | 0ed | 1 | 4/13/26 1:15 | 4/13/26 1:45 | April 13, 2026 1:15 | April 13, 2026 1:45 | As Soon As Possible | NA | 4/13/26 1:45 | 4/13/26 1:45 | 4/8/26 1:33 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.24.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
404 | 1248 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 403 | April 13, 2026 1:45 | April 13, 2026 2:45 | 4/13/26 1:45 | 4/13/26 2:45 | 4/13/26 1:45 | 4/13/26 2:45 | 0h | 0h | 0ed | 1 | 4/13/26 1:45 | 4/13/26 2:45 | April 13, 2026 1:45 | April 13, 2026 2:45 | As Soon As Possible | NA | 4/13/26 2:45 | 4/13/26 2:45 | 4/8/26 1:33 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.24.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
405 | 1249 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 404 | April 13, 2026 2:45 | April 13, 2026 4:45 | 4/13/26 2:45 | 4/13/26 4:45 | 4/13/26 2:45 | 4/13/26 4:45 | 0h | 0h | 0ed | 1 | 4/13/26 2:45 | 4/13/26 4:45 | April 13, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | 4/13/26 4:45 | 4/13/26 4:45 | 4/8/26 1:33 | 4h | 4h | 4h | 0 | 0 | 0 | 0 | 0 | 1.2.1.24.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
406 | 1250 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 405 | April 13, 2026 4:45 | April 14, 2026 9:45 | 4/13/26 4:45 | 4/14/26 9:45 | 4/13/26 4:45 | 4/14/26 9:45 | 0h | 0h | 0ed | 1 | 4/13/26 4:45 | 4/14/26 9:45 | April 13, 2026 4:45 | April 14, 2026 9:45 | As Soon As Possible | NA | 4/14/26 9:45 | 4/14/26 9:45 | 4/8/26 1:33 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.24.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
407 | 1251 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 406 | April 14, 2026 9:45 | April 14, 2026 1:45 | 4/14/26 9:45 | 4/14/26 1:45 | 4/14/26 9:45 | 4/14/26 1:45 | 0h | 0h | 0ed | 1 | 4/14/26 9:45 | 4/14/26 1:45 | April 14, 2026 9:45 | April 14, 2026 1:45 | As Soon As Possible | NA | 4/14/26 1:45 | 4/14/26 1:45 | 4/8/26 1:33 | 6h | 6h | 6h | 0 | 0 | 0 | 0 | 0 | 1.2.1.24.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
408 | 741 | Yes | Auto Scheduled | PTP_CM26_Material_Master - All Types | 3.16d | Fixed Duration | 4 | 3.16d | 401 | April 10, 2026 10:45 | April 15, 2026 12:00 | 4/10/26 10:45 | 4/15/26 12:00 | 4/10/26 10:45 | 4/15/26 12:00 | 0d | 0d | 0ed | 1 | 4/10/26 10:45 | 4/15/26 12:00 | April 10, 2026 10:45 | April 15, 2026 12:00 | As Soon As Possible | NA | 4/13/26 9:30 | 4/13/26 9:30 | 3/25/26 2:32 | 19h | 19h | 19h | 0 | 0 | 0 | 0 | 0 | 1.2.1.25 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
409 | 1020 | Yes | Auto Scheduled | Extract File | 5h | Fixed Units | 5 | 0.63d | 384 | April 10, 2026 10:45 | April 13, 2026 9:30 | 4/10/26 10:45 | 4/13/26 9:30 | 4/10/26 10:45 | 4/13/26 9:30 | 0h | 0h | 0ed | 1 | 4/10/26 10:45 | 4/13/26 9:30 | April 10, 2026 10:45 | April 13, 2026 9:30 | As Soon As Possible | NA | 4/13/26 9:30 | 4/13/26 9:30 | 4/1/26 2:39 | 5h | 5h | 5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.25.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
410 | 1021 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 382 | April 13, 2026 11:45 | April 14, 2026 10:00 | 4/13/26 11:45 | 4/14/26 10:00 | 4/13/26 11:45 | 4/14/26 10:00 | 0h | 0h | 0ed | 1 | 4/13/26 11:45 | 4/14/26 10:00 | April 13, 2026 11:45 | April 14, 2026 10:00 | As Soon As Possible | NA | 4/14/26 10:00 | 4/14/26 10:00 | 4/1/26 2:39 | 4h | 4h | 4h | 0 | 0 | 0 | 0 | 0 | 1.2.1.25.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
411 | 1022 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 410 | April 14, 2026 10:00 | April 14, 2026 11:00 | 4/14/26 10:00 | 4/14/26 11:00 | 4/14/26 10:00 | 4/14/26 11:00 | 0h | 0h | 0ed | 1 | 4/14/26 10:00 | 4/14/26 11:00 | April 14, 2026 10:00 | April 14, 2026 11:00 | As Soon As Possible | NA | 4/14/26 11:00 | 4/14/26 11:00 | 4/1/26 2:39 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.25.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
412 | 1023 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | Fixed Units | 5 | 0.5d | 411 | April 14, 2026 11:00 | April 14, 2026 4:00 | 4/14/26 11:00 | 4/14/26 4:00 | 4/14/26 11:00 | 4/14/26 4:00 | 0h | 0h | 0ed | 1 | 4/14/26 11:00 | 4/14/26 4:00 | April 14, 2026 11:00 | April 14, 2026 4:00 | As Soon As Possible | NA | 4/14/26 4:00 | 4/14/26 4:00 | 4/1/26 2:39 | 4h | 4h | 4h | 0 | 0 | 0 | 0 | 0 | 1.2.1.25.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
413 | 1024 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 5 | 0.38d | 412 | April 14, 2026 4:00 | April 15, 2026 10:00 | 4/14/26 4:00 | 4/15/26 10:00 | 4/14/26 4:00 | 4/15/26 10:00 | 0h | 0h | 0ed | 1 | 4/14/26 4:00 | 4/15/26 10:00 | April 14, 2026 4:00 | April 15, 2026 10:00 | As Soon As Possible | NA | 4/15/26 10:00 | 4/15/26 10:00 | 4/1/26 2:39 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.25.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
414 | 1025 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 413 | April 15, 2026 10:00 | April 15, 2026 12:00 | 4/15/26 10:00 | 4/15/26 12:00 | 4/15/26 10:00 | 4/15/26 12:00 | 0h | 0h | 0ed | 1 | 4/15/26 10:00 | 4/15/26 12:00 | April 15, 2026 10:00 | April 15, 2026 12:00 | As Soon As Possible | NA | 4/15/26 12:00 | 4/15/26 12:00 | 4/1/26 2:39 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.25.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
415 | 748 | Yes | Auto Scheduled | PTP_CM26_Material_Master - SERV - Service Materials | 5.88d | Fixed Duration | 4 | 5.88d | 408 | April 7, 2026 4:15 | April 15, 2026 3:15 | 4/7/26 4:15 | 4/15/26 3:15 | 4/7/26 4:15 | 4/15/26 3:15 | 0d | 0d | 0ed | 1 | 4/7/26 4:15 | 4/15/26 3:15 | April 7, 2026 4:15 | April 15, 2026 3:15 | As Soon As Possible | NA | 4/7/26 4:45 | 4/7/26 4:45 | 3/25/26 2:32 | 15h | 15h | 15h | 0 | 0 | 0 | 0 | 0 | 1.2.1.26 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
416 | 1026 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 285 | April 7, 2026 4:15 | April 7, 2026 4:45 | 4/7/26 4:15 | 4/7/26 4:45 | 4/7/26 4:15 | 4/7/26 4:45 | 0m | 0m | 0ed | 1 | 4/7/26 4:15 | 4/7/26 4:45 | April 7, 2026 4:15 | April 7, 2026 4:45 | As Soon As Possible | NA | 4/7/26 4:45 | 4/7/26 4:45 | 4/1/26 2:43 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.26.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
417 | 1027 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 413 | April 14, 2026 2:45 | April 14, 2026 3:15 | 4/14/26 2:45 | 4/14/26 3:15 | 4/14/26 2:45 | 4/14/26 3:15 | 0m | 0m | 0ed | 1 | 4/14/26 2:45 | 4/14/26 3:15 | April 14, 2026 2:45 | April 14, 2026 3:15 | As Soon As Possible | NA | 4/14/26 3:15 | 4/14/26 3:15 | 4/1/26 2:43 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.26.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
418 | 1028 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 417 | April 14, 2026 3:15 | April 14, 2026 4:15 | 4/14/26 3:15 | 4/14/26 4:15 | 4/14/26 3:15 | 4/14/26 4:15 | 0h | 0h | 0ed | 1 | 4/14/26 3:15 | 4/14/26 4:15 | April 14, 2026 3:15 | April 14, 2026 4:15 | As Soon As Possible | NA | 4/14/26 4:15 | 4/14/26 4:15 | 4/1/26 2:43 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.26.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
419 | 1029 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 418 | April 14, 2026 4:15 | April 15, 2026 9:15 | 4/14/26 4:15 | 4/15/26 9:15 | 4/14/26 4:15 | 4/15/26 9:15 | 0h | 0h | 0ed | 1 | 4/14/26 4:15 | 4/15/26 9:15 | April 14, 2026 4:15 | April 15, 2026 9:15 | As Soon As Possible | NA | 4/15/26 9:15 | 4/15/26 9:15 | 4/1/26 2:43 | 4h | 4h | 4h | 0 | 0 | 0 | 0 | 0 | 1.2.1.26.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
420 | 1030 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 419 | April 15, 2026 9:15 | April 15, 2026 11:15 | 4/15/26 9:15 | 4/15/26 11:15 | 4/15/26 9:15 | 4/15/26 11:15 | 0h | 0h | 0ed | 1 | 4/15/26 9:15 | 4/15/26 11:15 | April 15, 2026 9:15 | April 15, 2026 11:15 | As Soon As Possible | NA | 4/15/26 11:15 | 4/15/26 11:15 | 4/1/26 2:43 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.26.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
421 | 1031 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 420 | April 15, 2026 11:15 | April 15, 2026 3:15 | 4/15/26 11:15 | 4/15/26 3:15 | 4/15/26 11:15 | 4/15/26 3:15 | 0h | 0h | 0ed | 1 | 4/15/26 11:15 | 4/15/26 3:15 | April 15, 2026 11:15 | April 15, 2026 3:15 | As Soon As Possible | NA | 4/15/26 3:15 | 4/15/26 3:15 | 4/1/26 2:43 | 6h | 6h | 6h | 0 | 0 | 0 | 0 | 0 | 1.2.1.26.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
422 | 749 | Yes | Auto Scheduled | PTP_CM26_Material_Master - KMAT - Configurable Materials | 5.88d | Fixed Duration | 4 | 5.88d | 415 | April 7, 2026 4:15 | April 15, 2026 3:15 | 4/7/26 4:15 | 4/15/26 3:15 | 4/7/26 4:15 | 4/15/26 3:15 | 0d | 0d | 0ed | 1 | 4/7/26 4:15 | 4/15/26 3:15 | April 7, 2026 4:15 | April 15, 2026 3:15 | As Soon As Possible | NA | 4/7/26 4:45 | 4/7/26 4:45 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.27 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
423 | 1032 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 285 | April 7, 2026 4:15 | April 7, 2026 4:45 | 4/7/26 4:15 | 4/7/26 4:45 | 4/7/26 4:15 | 4/7/26 4:45 | 0m | 0m | 0ed | 1 | 4/7/26 4:15 | 4/7/26 4:45 | April 7, 2026 4:15 | April 7, 2026 4:45 | As Soon As Possible | NA | 4/7/26 4:45 | 4/7/26 4:45 | 4/1/26 2:45 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.27.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
424 | 1033 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 413 | April 14, 2026 2:45 | April 14, 2026 3:15 | 4/14/26 2:45 | 4/14/26 3:15 | 4/14/26 2:45 | 4/14/26 3:15 | 0m | 0m | 0ed | 1 | 4/14/26 2:45 | 4/14/26 3:15 | April 14, 2026 2:45 | April 14, 2026 3:15 | As Soon As Possible | NA | 4/14/26 3:15 | 4/14/26 3:15 | 4/1/26 2:45 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.27.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
425 | 1034 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 424 | April 14, 2026 3:15 | April 14, 2026 4:15 | 4/14/26 3:15 | 4/14/26 4:15 | 4/14/26 3:15 | 4/14/26 4:15 | 0h | 0h | 0ed | 1 | 4/14/26 3:15 | 4/14/26 4:15 | April 14, 2026 3:15 | April 14, 2026 4:15 | As Soon As Possible | NA | 4/14/26 4:15 | 4/14/26 4:15 | 4/1/26 2:45 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.27.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
426 | 1035 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 425 | April 14, 2026 4:15 | April 15, 2026 9:15 | 4/14/26 4:15 | 4/15/26 9:15 | 4/14/26 4:15 | 4/15/26 9:15 | 0h | 0h | 0ed | 1 | 4/14/26 4:15 | 4/15/26 9:15 | April 14, 2026 4:15 | April 15, 2026 9:15 | As Soon As Possible | NA | 4/15/26 9:15 | 4/15/26 9:15 | 4/1/26 2:45 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.27.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
427 | 1036 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 426 | April 15, 2026 9:15 | April 15, 2026 11:15 | 4/15/26 9:15 | 4/15/26 11:15 | 4/15/26 9:15 | 4/15/26 11:15 | 0h | 0h | 0ed | 1 | 4/15/26 9:15 | 4/15/26 11:15 | April 15, 2026 9:15 | April 15, 2026 11:15 | As Soon As Possible | NA | 4/15/26 11:15 | 4/15/26 11:15 | 4/1/26 2:45 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.27.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
428 | 1037 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 427 | April 15, 2026 11:15 | April 15, 2026 3:15 | 4/15/26 11:15 | 4/15/26 3:15 | 4/15/26 11:15 | 4/15/26 3:15 | 0h | 0h | 0ed | 1 | 4/15/26 11:15 | 4/15/26 3:15 | April 15, 2026 11:15 | April 15, 2026 3:15 | As Soon As Possible | NA | 4/15/26 3:15 | 4/15/26 3:15 | 4/1/26 2:45 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.27.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
429 | 703 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Records | 1.59d | Fixed Duration | 4 | 1.28d |  | April 15, 2026 3:15 | April 17, 2026 11:00 | 4/15/26 3:15 | 4/17/26 11:00 | 4/15/26 3:15 | 4/17/26 11:00 | 0d | 0d | 0ed | 1 | 4/15/26 3:15 | 4/17/26 11:00 | April 15, 2026 10:00 | April 16, 2026 1:15 | As Soon As Possible | NA | 4/15/26 4:15 | 4/15/26 4:15 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.28 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
430 | 1038 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 5 | 0.13d | 414,428 | April 15, 2026 3:15 | April 15, 2026 4:15 | 4/15/26 3:15 | 4/15/26 4:15 | 4/15/26 3:15 | 4/15/26 4:15 | 0h | 0h | 0ed | 1 | 4/15/26 3:15 | 4/15/26 4:15 | April 15, 2026 3:15 | April 15, 2026 4:15 | As Soon As Possible | NA | 4/15/26 4:15 | 4/15/26 4:15 | 4/1/26 2:50 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.28.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
431 | 1039 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 430 | April 15, 2026 4:15 | April 16, 2026 9:15 | 4/15/26 4:15 | 4/16/26 9:15 | 4/15/26 4:15 | 4/16/26 9:15 | 0h | 0h | 0ed | 1 | 4/15/26 4:15 | 4/16/26 9:15 | April 15, 2026 4:15 | April 16, 2026 9:15 | As Soon As Possible | NA | 4/16/26 9:15 | 4/16/26 9:15 | 4/1/26 2:50 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.28.2 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
432 | 1040 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 431 | April 16, 2026 9:15 | April 16, 2026 10:15 | 4/16/26 9:15 | 4/16/26 10:15 | 4/16/26 9:15 | 4/16/26 10:15 | 0h | 0h | 0ed | 1 | 4/16/26 9:15 | 4/16/26 10:15 | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | 4/16/26 10:15 | 4/16/26 10:15 | 4/1/26 2:50 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.28.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
433 | 1041 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 432 | April 17, 2026 8:00 | April 17, 2026 10:00 | 4/17/26 8:00 | 4/17/26 10:00 | 4/17/26 8:00 | 4/17/26 10:00 | 0h | 0h | 0ed | 1 | 4/17/26 8:00 | 4/17/26 10:00 | April 16, 2026 10:15 | April 16, 2026 1:15 | Start No Earlier Than | 4/17/26 8:00 | 4/17/26 10:00 | 4/17/26 10:00 | 4/1/26 2:50 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.28.4 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
434 | 1042 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 382 | April 17, 2026 8:00 | April 17, 2026 9:00 | 4/17/26 8:00 | 4/17/26 9:00 | 4/17/26 8:00 | 4/17/26 9:00 | 0h | 0h | 0ed | 1 | 4/17/26 8:00 | 4/17/26 9:00 | April 15, 2026 10:00 | April 15, 2026 11:00 | Start No Earlier Than | 4/17/26 8:00 | 4/17/26 9:00 | 4/17/26 9:00 | 4/1/26 2:50 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.28.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
435 | 1043 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 434 | April 17, 2026 9:00 | April 17, 2026 11:00 | 4/17/26 9:00 | 4/17/26 11:00 | 4/17/26 9:00 | 4/17/26 11:00 | 0h | 0h | 0ed | 1 | 4/17/26 9:00 | 4/17/26 11:00 | April 15, 2026 11:00 | April 15, 2026 2:00 | Start No Earlier Than | 4/17/26 8:00 | 4/17/26 11:00 | 4/17/26 11:00 | 4/1/26 2:50 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.28.6 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
436 | 936 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record External Processing | 1.47d | Fixed Duration | 4 | 1.13d |  | April 15, 2026 3:15 | April 17, 2026 10:00 | 4/15/26 3:15 | 4/17/26 10:00 | 4/15/26 3:15 | 4/17/26 10:00 | 0d | 0d | 0ed | 1 | 4/15/26 3:15 | 4/17/26 10:00 | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | 4/15/26 3:45 | 4/15/26 3:45 | 4/1/26 1:26 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.29 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
437 | 1044 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 414,428 | April 15, 2026 3:15 | April 15, 2026 3:45 | 4/15/26 3:15 | 4/15/26 3:45 | 4/15/26 3:15 | 4/15/26 3:45 | 0m | 0m | 0ed | 1 | 4/15/26 3:15 | 4/15/26 3:45 | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | 4/15/26 3:45 | 4/15/26 3:45 | 4/1/26 2:51 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.29.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
438 | 1045 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 437 | April 15, 2026 3:45 | April 15, 2026 4:15 | 4/15/26 3:45 | 4/15/26 4:15 | 4/15/26 3:45 | 4/15/26 4:15 | 0m | 0m | 0ed | 1 | 4/15/26 3:45 | 4/15/26 4:15 | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | 4/15/26 4:15 | 4/15/26 4:15 | 4/1/26 2:51 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.29.2 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
439 | 1046 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 438 | April 16, 2026 8:00 | April 16, 2026 9:00 | 4/16/26 8:00 | 4/16/26 9:00 | 4/16/26 8:00 | 4/16/26 9:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 9:00 | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | 4/16/26 9:00 | 4/16/26 9:00 | 4/1/26 2:51 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.29.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
440 | 1047 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 439 | April 16, 2026 9:00 | April 16, 2026 11:00 | 4/16/26 9:00 | 4/16/26 11:00 | 4/16/26 9:00 | 4/16/26 11:00 | 0h | 0h | 0ed | 1 | 4/16/26 9:00 | 4/16/26 11:00 | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | 4/16/26 11:00 | 4/16/26 11:00 | 4/1/26 2:51 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.29.4 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
441 | 1048 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 440 | April 17, 2026 8:00 | April 17, 2026 10:00 | 4/17/26 8:00 | 4/17/26 10:00 | 4/17/26 8:00 | 4/17/26 10:00 | 0h | 0h | 0ed | 1 | 4/17/26 8:00 | 4/17/26 10:00 | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | 4/17/26 10:00 | 4/17/26 10:00 | 4/1/26 2:51 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.29.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
442 | 1049 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 441 | April 16, 2026 2:00 | April 16, 2026 5:00 | 4/16/26 2:00 | 4/16/26 5:00 | 4/16/26 2:00 | 4/16/26 5:00 | 0h | 0h | 0ed | 1 | 4/16/26 2:00 | 4/16/26 5:00 | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | 4/16/26 5:00 | 4/16/26 5:00 | 4/1/26 2:51 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.29.6 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
443 | 937 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | 1.13d | Fixed Duration | 4 | 1.13d |  | April 15, 2026 3:15 | April 16, 2026 4:15 | 4/15/26 3:15 | 4/16/26 4:15 | 4/15/26 3:15 | 4/16/26 4:15 | 0d | 0d | 0ed | 1 | 4/15/26 3:15 | 4/16/26 4:15 | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | 4/15/26 3:45 | 4/15/26 3:45 | 4/1/26 1:26 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.30 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
444 | 1050 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 414,428 | April 15, 2026 3:15 | April 15, 2026 3:45 | 4/15/26 3:15 | 4/15/26 3:45 | 4/15/26 3:15 | 4/15/26 3:45 | 0m | 0m | 0ed | 1 | 4/15/26 3:15 | 4/15/26 3:45 | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | 4/15/26 3:45 | 4/15/26 3:45 | 4/1/26 2:53 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.30.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
445 | 1051 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 444 | April 15, 2026 3:45 | April 15, 2026 4:15 | 4/15/26 3:45 | 4/15/26 4:15 | 4/15/26 3:45 | 4/15/26 4:15 | 0m | 0m | 0ed | 1 | 4/15/26 3:45 | 4/15/26 4:15 | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | 4/15/26 4:15 | 4/15/26 4:15 | 4/1/26 2:53 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.30.2 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
446 | 1052 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 445 | April 15, 2026 4:15 | April 16, 2026 8:15 | 4/15/26 4:15 | 4/16/26 8:15 | 4/15/26 4:15 | 4/16/26 8:15 | 0h | 0h | 0ed | 1 | 4/15/26 4:15 | 4/16/26 8:15 | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 8:15 | 4/1/26 2:53 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.30.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
447 | 1053 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 446 | April 16, 2026 8:15 | April 16, 2026 10:15 | 4/16/26 8:15 | 4/16/26 10:15 | 4/16/26 8:15 | 4/16/26 10:15 | 0h | 0h | 0ed | 1 | 4/16/26 8:15 | 4/16/26 10:15 | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | 4/16/26 10:15 | 4/16/26 10:15 | 4/1/26 2:53 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.30.4 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
448 | 1054 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 447 | April 16, 2026 10:15 | April 16, 2026 1:15 | 4/16/26 10:15 | 4/16/26 1:15 | 4/16/26 10:15 | 4/16/26 1:15 | 0h | 0h | 0ed | 1 | 4/16/26 10:15 | 4/16/26 1:15 | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | 4/16/26 1:15 | 4/16/26 1:15 | 4/1/26 2:53 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.30.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
449 | 1055 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 448 | April 16, 2026 1:15 | April 16, 2026 4:15 | 4/16/26 1:15 | 4/16/26 4:15 | 4/16/26 1:15 | 4/16/26 4:15 | 0h | 0h | 0ed | 1 | 4/16/26 1:15 | 4/16/26 4:15 | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | 4/16/26 4:15 | 4/16/26 4:15 | 4/1/26 2:53 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.30.6 | 500 | No | No | No |  | Sam Houff | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
450 | 694 | Yes | Auto Scheduled | PTM_CM31_BOM Conversion | 2.09d | Fixed Duration | 4 | 1.13d |  | April 15, 2026 4:15 | April 17, 2026 5:00 | 4/15/26 4:15 | 4/17/26 5:00 | 4/15/26 4:15 | 4/17/26 5:00 | 0d | 0d | 0ed | 1 | 4/15/26 4:15 | 4/17/26 5:00 | April 15, 2026 4:15 | April 17, 2026 8:15 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 8:15 | 3/25/26 2:32 | 19h | 9h | 19h | 0 | 0 | 0 | 0 | 0 | 1.2.1.31 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
451 | 1056 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 5 | 0.13d | 430 | April 15, 2026 4:15 | April 16, 2026 8:15 | 4/15/26 4:15 | 4/16/26 8:15 | 4/15/26 4:15 | 4/16/26 8:15 | 0h | 0h | 0ed | 1 | 4/15/26 4:15 | 4/16/26 8:15 | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 8:15 | 4/1/26 2:53 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.31.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
452 | 1057 | Yes | Auto Scheduled | Pre Load Validation | 0.5h | Fixed Units | 5 | 0.25d | 451 | April 16, 2026 8:15 | April 16, 2026 8:45 | 4/16/26 8:15 | 4/16/26 8:45 | 4/16/26 8:15 | 4/16/26 8:45 | 0h | 0h | 0ed | 1 | 4/16/26 8:15 | 4/16/26 8:45 | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | 4/16/26 8:45 | 4/16/26 8:45 | 4/1/26 2:53 | 0.5h | 2h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.31.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
453 | 1058 | Yes | Auto Scheduled | Simulate Load | 15.5h | Fixed Units | 5 | 0.13d | 452 | April 16, 2026 8:00 | April 17, 2026 5:00 | 4/16/26 8:00 | 4/17/26 5:00 | 4/16/26 8:00 | 4/17/26 5:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/17/26 5:00 | April 16, 2026 10:15 | April 16, 2026 11:15 | Finish No Earlier Than | 4/17/26 5:00 | 4/17/26 5:00 | 4/17/26 5:00 | 4/1/26 2:53 | 15.5h | 1h | 15.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.31.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
454 | 1059 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | Fixed Units | 5 | 0.25d | 453 | April 17, 2026 8:00 | April 17, 2026 8:30 | 4/17/26 8:00 | 4/17/26 8:30 | 4/17/26 8:00 | 4/17/26 8:30 | 0h | 0h | 0ed | 1 | 4/17/26 8:00 | 4/17/26 8:30 | April 16, 2026 11:15 | April 16, 2026 2:15 | Finish No Earlier Than | 4/17/26 5:00 | 4/17/26 8:30 | 4/17/26 8:30 | 4/1/26 2:53 | 0.5h | 2h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.31.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
455 | 1060 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 454 | April 17, 2026 8:00 | April 17, 2026 9:15 | 4/17/26 8:00 | 4/17/26 9:15 | 4/17/26 8:00 | 4/17/26 9:15 | 0h | 0h | 0ed | 1 | 4/17/26 8:00 | 4/17/26 9:15 | April 16, 2026 2:15 | April 16, 2026 3:15 | As Soon As Possible | NA | 4/17/26 9:15 | 4/17/26 9:15 | 4/1/26 2:53 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 4/1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
456 | 1061 | Yes | Auto Scheduled | Post Load Validation | 0.5h | Fixed Units | 5 | 0.25d | 455 | April 17, 2026 9:00 | April 17, 2026 9:38 | 4/17/26 9:00 | 4/17/26 9:38 | 4/17/26 9:00 | 4/17/26 9:38 | 0h | 0h | 0ed | 1 | 4/17/26 9:00 | 4/17/26 9:38 | April 16, 2026 3:15 | April 17, 2026 8:15 | Finish No Earlier Than | 4/16/26 5:00 | 4/17/26 9:38 | 4/17/26 9:38 | 4/1/26 2:53 | 0.5h | 2h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.31.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
457 | 695 | Yes | Auto Scheduled | PTM_CM40_Work Center Conversion | 0.38d | Fixed Duration | 4 | 2d |  | April 16, 2026 8:00 | April 16, 2026 11:00 | 4/16/26 8:00 | 4/16/26 11:00 | 4/16/26 8:00 | 4/16/26 11:00 | 0d | 0d | 0ed | 1 | 4/16/26 8:00 | 4/16/26 11:00 | April 16, 2026 8:15 | April 20, 2026 8:15 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 8:15 | 3/25/26 2:32 | 6.75h | 9h | 6.75h | 0 | 0 | 0 | 0 | 0 | 1.2.1.32 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
458 | 1062 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 5 | 0.13d | 451 | April 16, 2026 8:15 | April 16, 2026 9:15 | 4/16/26 8:15 | 4/16/26 9:15 | 4/16/26 8:15 | 4/16/26 9:15 | 0h | 0h | 0ed | 1 | 4/16/26 8:15 | 4/16/26 9:15 | April 16, 2026 8:15 | April 16, 2026 9:15 | As Soon As Possible | NA | 4/16/26 9:15 | 4/16/26 9:15 | 4/1/26 2:56 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.32.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
459 | 1063 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 456 | April 16, 2026 8:30 | April 16, 2026 10:30 | 4/16/26 8:30 | 4/16/26 10:30 | 4/16/26 8:30 | 4/16/26 10:30 | 0h | 0h | 0ed | 1 | 4/16/26 8:30 | 4/16/26 10:30 | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | 4/16/26 10:30 | 4/16/26 10:30 | 4/1/26 2:56 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.32.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
460 | 1064 | Yes | Auto Scheduled | Simulate Load | 0.25h | Fixed Units | 5 | 0.13d | 459 | April 16, 2026 8:00 | April 16, 2026 8:15 | 4/16/26 8:00 | 4/16/26 8:15 | 4/16/26 8:00 | 4/16/26 8:15 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 8:15 | April 17, 2026 10:15 | April 17, 2026 11:15 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 8:15 | 4/1/26 2:56 | 0.25h | 1h | 0.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.32.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
461 | 1065 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | Fixed Units | 5 | 0.25d | 460 | April 16, 2026 8:00 | April 16, 2026 8:30 | 4/16/26 8:00 | 4/16/26 8:30 | 4/16/26 8:00 | 4/16/26 8:30 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 8:30 | April 17, 2026 11:15 | April 17, 2026 2:15 | As Soon As Possible | NA | 4/16/26 8:30 | 4/16/26 8:30 | 4/1/26 2:56 | 0.5h | 2h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.32.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
462 | 1066 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 461 | April 16, 2026 8:00 | April 16, 2026 9:00 | 4/16/26 8:00 | 4/16/26 9:00 | 4/16/26 8:00 | 4/16/26 9:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 9:00 | April 17, 2026 2:15 | April 17, 2026 3:15 | As Soon As Possible | NA | 4/16/26 9:00 | 4/16/26 9:00 | 4/1/26 2:56 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.32.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
463 | 1067 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 462 | April 16, 2026 9:00 | April 16, 2026 11:00 | 4/16/26 9:00 | 4/16/26 11:00 | 4/16/26 9:00 | 4/16/26 11:00 | 0h | 0h | 0ed | 1 | 4/16/26 9:00 | 4/16/26 11:00 | April 17, 2026 3:15 | April 20, 2026 8:15 | As Soon As Possible | NA | 4/16/26 11:00 | 4/16/26 11:00 | 4/1/26 2:56 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.32.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
464 | 707 | Yes | Auto Scheduled | PTM_CM38_Routing Conversion | 2.75d | Fixed Duration | 4 | 2.88d |  | April 16, 2026 8:00 | April 20, 2026 3:00 | 4/16/26 8:00 | 4/20/26 3:00 | 4/16/26 8:00 | 4/20/26 3:00 | 0d | 0d | 0ed | 1 | 4/16/26 8:00 | 4/20/26 3:00 | April 16, 2026 9:15 | April 21, 2026 8:15 | As Soon As Possible | NA | 4/16/26 10:15 | 4/16/26 10:15 | 3/25/26 2:32 | 11h | 9h | 11h | 0 | 0 | 0 | 0 | 0 | 1.2.1.33 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
465 | 1075 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 5 | 0.13d | 458 | April 16, 2026 9:15 | April 16, 2026 10:15 | 4/16/26 9:15 | 4/16/26 10:15 | 4/16/26 9:15 | 4/16/26 10:15 | 0h | 0h | 0ed | 1 | 4/16/26 9:15 | 4/16/26 10:15 | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | 4/16/26 10:15 | 4/16/26 10:15 | 4/1/26 2:56 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.33.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
466 | 1076 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 5 | 0.25d | 463 | April 16, 2026 8:00 | April 16, 2026 1:30 | 4/16/26 8:00 | 4/16/26 1:30 | 4/16/26 8:00 | 4/16/26 1:30 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 1:30 | April 20, 2026 8:15 | April 20, 2026 10:15 | As Soon As Possible | NA | 4/16/26 1:30 | 4/16/26 1:30 | 4/1/26 2:56 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.33.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
467 | 1077 | Yes | Auto Scheduled | Simulate Load | 2h | Fixed Units | 5 | 0.13d | 466 | April 20, 2026 8:00 | April 20, 2026 10:00 | 4/20/26 8:00 | 4/20/26 10:00 | 4/20/26 8:00 | 4/20/26 10:00 | 0h | 0h | 0ed | 1 | 4/20/26 8:00 | 4/20/26 10:00 | April 20, 2026 10:15 | April 20, 2026 11:15 | Finish No Earlier Than | 4/17/26 5:00 | 4/20/26 10:00 | 4/20/26 10:00 | 4/1/26 2:56 | 2h | 1h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.33.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
468 | 1078 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | Fixed Units | 5 | 0.25d | 467SS | April 20, 2026 8:00 | April 20, 2026 11:00 | 4/20/26 8:00 | 4/20/26 11:00 | 4/20/26 8:00 | 4/20/26 11:00 | 0h | 0h | 0ed | 1 | 4/20/26 8:00 | 4/20/26 11:00 | April 20, 2026 11:15 | April 20, 2026 2:15 | Start No Earlier Than | 4/17/26 8:00 | 4/20/26 11:00 | 4/20/26 11:00 | 4/1/26 2:56 | 3h | 2h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.33.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
469 | 1079 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 468 | April 20, 2026 11:00 | April 20, 2026 12:00 | 4/20/26 11:00 | 4/20/26 12:00 | 4/20/26 11:00 | 4/20/26 12:00 | 0h | 0h | 0ed | 1 | 4/20/26 11:00 | 4/20/26 12:00 | April 20, 2026 2:15 | April 20, 2026 3:15 | Start No Earlier Than | 4/20/26 8:00 | 4/20/26 12:00 | 4/20/26 12:00 | 4/1/26 2:56 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.33.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
470 | 1080 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 5 | 0.25d | 469 | April 20, 2026 1:00 | April 20, 2026 3:00 | 4/20/26 1:00 | 4/20/26 3:00 | 4/20/26 1:00 | 4/20/26 3:00 | 0h | 0h | 0ed | 1 | 4/20/26 1:00 | 4/20/26 3:00 | April 20, 2026 3:15 | April 21, 2026 8:15 | Start No Earlier Than | 4/20/26 8:00 | 4/20/26 3:00 | 4/20/26 3:00 | 4/1/26 2:56 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.33.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
471 | 709 | Yes | Auto Scheduled | PTM_CM36_Production Version Conversion | 1.13d | Fixed Duration | 4 | 1.13d |  | April 20, 2026 8:00 | April 21, 2026 9:00 | 4/20/26 8:00 | 4/21/26 9:00 | 4/20/26 8:00 | 4/21/26 9:00 | 0d | 0d | 0ed | 1 | 4/20/26 8:00 | 4/21/26 9:00 | April 16, 2026 10:15 | April 17, 2026 11:15 | Start No Earlier Than | 4/17/26 8:00 | 4/20/26 8:30 | 4/20/26 8:30 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.34 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
472 | 1081 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 465 | April 20, 2026 8:00 | April 20, 2026 8:30 | 4/20/26 8:00 | 4/20/26 8:30 | 4/20/26 8:00 | 4/20/26 8:30 | 0m | 0m | 0ed | 1 | 4/20/26 8:00 | 4/20/26 8:30 | April 16, 2026 10:15 | April 16, 2026 10:45 | Start No Earlier Than | 4/20/26 8:00 | 4/20/26 8:30 | 4/20/26 8:30 | 4/2/26 5:28 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.34.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
473 | 1082 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 472 | April 20, 2026 8:30 | April 20, 2026 9:00 | 4/20/26 8:30 | 4/20/26 9:00 | 4/20/26 8:30 | 4/20/26 9:00 | 0m | 0m | 0ed | 1 | 4/20/26 8:30 | 4/20/26 9:00 | April 16, 2026 10:45 | April 16, 2026 11:15 | As Soon As Possible | NA | 4/20/26 9:00 | 4/20/26 9:00 | 4/2/26 5:28 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.34.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
474 | 1083 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 473 | April 20, 2026 9:00 | April 20, 2026 10:00 | 4/20/26 9:00 | 4/20/26 10:00 | 4/20/26 9:00 | 4/20/26 10:00 | 0h | 0h | 0ed | 1 | 4/20/26 9:00 | 4/20/26 10:00 | April 16, 2026 11:15 | April 16, 2026 1:15 | As Soon As Possible | NA | 4/20/26 10:00 | 4/20/26 10:00 | 4/2/26 5:28 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.34.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
475 | 1084 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 474 | April 20, 2026 10:00 | April 20, 2026 12:00 | 4/20/26 10:00 | 4/20/26 12:00 | 4/20/26 10:00 | 4/20/26 12:00 | 0h | 0h | 0ed | 1 | 4/20/26 10:00 | 4/20/26 12:00 | April 16, 2026 1:15 | April 16, 2026 3:15 | As Soon As Possible | NA | 4/20/26 12:00 | 4/20/26 12:00 | 4/2/26 5:28 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.34.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
476 | 1085 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 475 | April 20, 2026 1:00 | April 20, 2026 3:00 | 4/20/26 1:00 | 4/20/26 3:00 | 4/20/26 1:00 | 4/20/26 3:00 | 0h | 0h | 0ed | 1 | 4/20/26 1:00 | 4/20/26 3:00 | April 16, 2026 3:15 | April 17, 2026 8:15 | As Soon As Possible | NA | 4/20/26 3:00 | 4/20/26 3:00 | 4/2/26 5:28 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.34.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
477 | 1086 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 476 | April 20, 2026 3:00 | April 21, 2026 9:00 | 4/20/26 3:00 | 4/21/26 9:00 | 4/20/26 3:00 | 4/21/26 9:00 | 0h | 0h | 0ed | 1 | 4/20/26 3:00 | 4/21/26 9:00 | April 17, 2026 8:15 | April 17, 2026 11:15 | Finish No Earlier Than | 4/17/26 5:00 | 4/21/26 9:00 | 4/21/26 9:00 | 4/2/26 5:28 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.34.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
478 | 710 | Yes | Auto Scheduled | PTM_CM35_Inspection Plan | 1.13d | Fixed Duration | 4 | 1.13d |  | April 21, 2026 9:00 | April 22, 2026 10:00 | 4/21/26 9:00 | 4/22/26 10:00 | 4/21/26 9:00 | 4/22/26 10:00 | 0d | 0d | 0ed | 1 | 4/21/26 9:00 | 4/22/26 10:00 | April 17, 2026 11:15 | April 20, 2026 1:15 | As Soon As Possible | NA | 4/21/26 9:30 | 4/21/26 9:30 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.35 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
479 | 1088 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 477 | April 21, 2026 9:00 | April 21, 2026 9:30 | 4/21/26 9:00 | 4/21/26 9:30 | 4/21/26 9:00 | 4/21/26 9:30 | 0m | 0m | 0ed | 1 | 4/21/26 9:00 | 4/21/26 9:30 | April 17, 2026 11:15 | April 17, 2026 11:45 | As Soon As Possible | NA | 4/21/26 9:30 | 4/21/26 9:30 | 4/2/26 5:34 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.35.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
480 | 1089 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 479 | April 21, 2026 9:30 | April 21, 2026 10:00 | 4/21/26 9:30 | 4/21/26 10:00 | 4/21/26 9:30 | 4/21/26 10:00 | 0m | 0m | 0ed | 1 | 4/21/26 9:30 | 4/21/26 10:00 | April 17, 2026 11:45 | April 17, 2026 1:15 | As Soon As Possible | NA | 4/21/26 10:00 | 4/21/26 10:00 | 4/2/26 5:34 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.35.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
481 | 1090 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 480 | April 21, 2026 10:00 | April 21, 2026 11:00 | 4/21/26 10:00 | 4/21/26 11:00 | 4/21/26 10:00 | 4/21/26 11:00 | 0h | 0h | 0ed | 1 | 4/21/26 10:00 | 4/21/26 11:00 | April 17, 2026 1:15 | April 17, 2026 2:15 | As Soon As Possible | NA | 4/21/26 11:00 | 4/21/26 11:00 | 4/2/26 5:34 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.35.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
482 | 1091 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 481 | April 21, 2026 11:00 | April 21, 2026 2:00 | 4/21/26 11:00 | 4/21/26 2:00 | 4/21/26 11:00 | 4/21/26 2:00 | 0h | 0h | 0ed | 1 | 4/21/26 11:00 | 4/21/26 2:00 | April 17, 2026 2:15 | April 17, 2026 4:15 | As Soon As Possible | NA | 4/21/26 2:00 | 4/21/26 2:00 | 4/2/26 5:34 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.35.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
483 | 1092 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 482 | April 21, 2026 2:00 | April 21, 2026 4:00 | 4/21/26 2:00 | 4/21/26 4:00 | 4/21/26 2:00 | 4/21/26 4:00 | 0h | 0h | 0ed | 1 | 4/21/26 2:00 | 4/21/26 4:00 | April 17, 2026 4:15 | April 20, 2026 9:15 | Finish No Earlier Than | 4/17/26 5:00 | 4/21/26 4:00 | 4/21/26 4:00 | 4/2/26 5:34 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.35.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
484 | 1093 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 483 | April 21, 2026 4:00 | April 22, 2026 10:00 | 4/21/26 4:00 | 4/22/26 10:00 | 4/21/26 4:00 | 4/22/26 10:00 | 0h | 0h | 0ed | 1 | 4/21/26 4:00 | 4/22/26 10:00 | April 20, 2026 9:15 | April 20, 2026 1:15 | As Soon As Possible | NA | 4/22/26 10:00 | 4/22/26 10:00 | 4/2/26 5:34 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.35.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
485 | 1194 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Serial Numbers | 1.13d | Fixed Duration | 4 | 1.13d |  | April 21, 2026 9:30 | April 22, 2026 10:30 | 4/21/26 9:30 | 4/22/26 10:30 | 4/21/26 9:30 | 4/22/26 10:30 | 0d | 0d | 0ed | 1 | 4/21/26 9:30 | 4/22/26 10:30 | April 17, 2026 11:45 | April 20, 2026 1:45 | As Soon As Possible | NA | 4/21/26 10:00 | 4/21/26 10:00 | 4/2/26 10:29 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.36 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
486 | 1196 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 479 | April 21, 2026 9:30 | April 21, 2026 10:00 | 4/21/26 9:30 | 4/21/26 10:00 | 4/21/26 9:30 | 4/21/26 10:00 | 0m | 0m | 0ed | 1 | 4/21/26 9:30 | 4/21/26 10:00 | April 17, 2026 11:45 | April 17, 2026 1:15 | As Soon As Possible | NA | 4/21/26 10:00 | 4/21/26 10:00 | 4/2/26 10:31 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.36.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
487 | 1197 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 486 | April 21, 2026 10:00 | April 21, 2026 10:30 | 4/21/26 10:00 | 4/21/26 10:30 | 4/21/26 10:00 | 4/21/26 10:30 | 0m | 0m | 0ed | 1 | 4/21/26 10:00 | 4/21/26 10:30 | April 17, 2026 1:15 | April 17, 2026 1:45 | As Soon As Possible | NA | 4/21/26 10:30 | 4/21/26 10:30 | 4/2/26 10:31 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.36.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
488 | 1198 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 487 | April 21, 2026 10:30 | April 21, 2026 11:30 | 4/21/26 10:30 | 4/21/26 11:30 | 4/21/26 10:30 | 4/21/26 11:30 | 0h | 0h | 0ed | 1 | 4/21/26 10:30 | 4/21/26 11:30 | April 17, 2026 1:45 | April 17, 2026 2:45 | As Soon As Possible | NA | 4/21/26 11:30 | 4/21/26 11:30 | 4/2/26 10:31 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.36.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
489 | 1199 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 488 | April 21, 2026 11:30 | April 21, 2026 2:30 | 4/21/26 11:30 | 4/21/26 2:30 | 4/21/26 11:30 | 4/21/26 2:30 | 0h | 0h | 0ed | 1 | 4/21/26 11:30 | 4/21/26 2:30 | April 17, 2026 2:45 | April 17, 2026 4:45 | As Soon As Possible | NA | 4/21/26 2:30 | 4/21/26 2:30 | 4/2/26 10:31 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.36.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
490 | 1200 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 489 | April 21, 2026 2:30 | April 21, 2026 4:30 | 4/21/26 2:30 | 4/21/26 4:30 | 4/21/26 2:30 | 4/21/26 4:30 | 0h | 0h | 0ed | 1 | 4/21/26 2:30 | 4/21/26 4:30 | April 17, 2026 4:45 | April 20, 2026 9:45 | As Soon As Possible | NA | 4/21/26 4:30 | 4/21/26 4:30 | 4/2/26 10:31 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.36.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
491 | 1201 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 490 | April 21, 2026 4:30 | April 22, 2026 10:30 | 4/21/26 4:30 | 4/22/26 10:30 | 4/21/26 4:30 | 4/22/26 10:30 | 0h | 0h | 0ed | 1 | 4/21/26 4:30 | 4/22/26 10:30 | April 20, 2026 9:45 | April 20, 2026 1:45 | As Soon As Possible | NA | 4/22/26 10:30 | 4/22/26 10:30 | 4/2/26 10:31 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.36.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
492 | 1195 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Service | 2.06d | Fixed Duration | 4 | 1.13d |  | April 21, 2026 8:00 | April 23, 2026 8:30 | 4/21/26 8:00 | 4/23/26 8:30 | 4/21/26 8:00 | 4/23/26 8:30 | 0d | 0d | 0ed | 1 | 4/21/26 8:00 | 4/23/26 8:30 | April 20, 2026 1:45 | April 21, 2026 2:45 | As Soon As Possible | NA | 4/21/26 11:00 | 4/21/26 11:00 | 4/2/26 10:29 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.37 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
493 | 1202 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 491 | April 22, 2026 10:30 | April 22, 2026 11:00 | 4/22/26 10:30 | 4/22/26 11:00 | 4/22/26 10:30 | 4/22/26 11:00 | 0m | 0m | 0ed | 1 | 4/22/26 10:30 | 4/22/26 11:00 | April 20, 2026 1:45 | April 20, 2026 2:15 | As Soon As Possible | NA | 4/22/26 11:00 | 4/22/26 11:00 | 4/2/26 10:35 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.37.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
494 | 1203 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 493 | April 22, 2026 11:00 | April 22, 2026 11:30 | 4/22/26 11:00 | 4/22/26 11:30 | 4/22/26 11:00 | 4/22/26 11:30 | 0m | 0m | 0ed | 1 | 4/22/26 11:00 | 4/22/26 11:30 | April 20, 2026 2:15 | April 20, 2026 2:45 | As Soon As Possible | NA | 4/22/26 11:30 | 4/22/26 11:30 | 4/2/26 10:35 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.37.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
495 | 1204 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 494 | April 22, 2026 11:30 | April 22, 2026 1:30 | 4/22/26 11:30 | 4/22/26 1:30 | 4/22/26 11:30 | 4/22/26 1:30 | 0h | 0h | 0ed | 1 | 4/22/26 11:30 | 4/22/26 1:30 | April 20, 2026 2:45 | April 20, 2026 3:45 | As Soon As Possible | NA | 4/22/26 1:30 | 4/22/26 1:30 | 4/2/26 10:35 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.37.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
496 | 1205 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 495 | April 22, 2026 1:30 | April 22, 2026 3:30 | 4/22/26 1:30 | 4/22/26 3:30 | 4/22/26 1:30 | 4/22/26 3:30 | 0h | 0h | 0ed | 1 | 4/22/26 1:30 | 4/22/26 3:30 | April 20, 2026 3:45 | April 21, 2026 8:45 | As Soon As Possible | NA | 4/22/26 3:30 | 4/22/26 3:30 | 4/2/26 10:35 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.37.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
497 | 1206 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 496 | April 22, 2026 3:30 | April 23, 2026 8:30 | 4/22/26 3:30 | 4/23/26 8:30 | 4/22/26 3:30 | 4/23/26 8:30 | 0h | 0h | 0ed | 1 | 4/22/26 3:30 | 4/23/26 8:30 | April 21, 2026 8:45 | April 21, 2026 10:45 | Finish No Earlier Than | 4/21/26 5:00 | 4/23/26 8:30 | 4/23/26 8:30 | 4/2/26 10:35 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.37.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
498 | 1207 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d |  | April 21, 2026 8:00 | April 21, 2026 11:00 | 4/21/26 8:00 | 4/21/26 11:00 | 4/21/26 8:00 | 4/21/26 11:00 | 0h | 0h | 0ed | 1 | 4/21/26 8:00 | 4/21/26 11:00 | April 21, 2026 10:45 | April 21, 2026 2:45 | Start No Earlier Than | 4/21/26 8:00 | 4/21/26 11:00 | 4/21/26 11:00 | 4/2/26 10:35 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.37.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
499 | 938 | Yes | Auto Scheduled | VC_Object Dependencies | 0.63d | Fixed Duration | 4 | 0.63d |  | April 6, 2026 8:15 | April 6, 2026 2:15 | 4/6/26 8:15 | 4/6/26 2:15 | 4/6/26 8:15 | 4/6/26 2:15 | 0d | 0d | 0ed | 1 | 4/6/26 8:15 | 4/6/26 2:15 | April 6, 2026 8:15 | April 6, 2026 2:15 | As Soon As Possible | NA | 4/6/26 10:15 | 4/6/26 10:15 | 4/1/26 1:30 | 5h | 5h | 5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.38 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
500 | 1151 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 5 | 0.25d | 261 | April 6, 2026 8:15 | April 6, 2026 10:15 | 4/6/26 8:15 | 4/6/26 10:15 | 4/6/26 8:15 | 4/6/26 10:15 | 0h | 0h | 0ed | 1 | 4/6/26 8:15 | 4/6/26 10:15 | April 6, 2026 8:15 | April 6, 2026 10:15 | As Soon As Possible | NA | 4/6/26 10:15 | 4/6/26 10:15 | 4/2/26 6:13 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.38.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
501 | 1153 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 500 | April 6, 2026 10:15 | April 6, 2026 2:15 | 4/6/26 10:15 | 4/6/26 2:15 | 4/6/26 10:15 | 4/6/26 2:15 | 0h | 0h | 0ed | 1 | 4/6/26 10:15 | 4/6/26 2:15 | April 6, 2026 10:15 | April 6, 2026 2:15 | As Soon As Possible | NA | 4/6/26 2:15 | 4/6/26 2:15 | 4/2/26 6:14 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.38.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
502 | 939 | Yes | Auto Scheduled | VC_Characteristics | 0.63d | Fixed Duration | 4 | 0.63d |  | April 6, 2026 2:15 | April 7, 2026 10:15 | 4/6/26 2:15 | 4/7/26 10:15 | 4/6/26 2:15 | 4/7/26 10:15 | 0d | 0d | 0ed | 1 | 4/6/26 2:15 | 4/7/26 10:15 | April 6, 2026 2:15 | April 7, 2026 10:15 | As Soon As Possible | NA | 4/6/26 4:15 | 4/6/26 4:15 | 4/1/26 1:30 | 5h | 5h | 5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.39 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
503 | 1154 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 5 | 0.25d | 501 | April 6, 2026 2:15 | April 6, 2026 4:15 | 4/6/26 2:15 | 4/6/26 4:15 | 4/6/26 2:15 | 4/6/26 4:15 | 0h | 0h | 0ed | 1 | 4/6/26 2:15 | 4/6/26 4:15 | April 6, 2026 2:15 | April 6, 2026 4:15 | As Soon As Possible | NA | 4/6/26 4:15 | 4/6/26 4:15 | 4/2/26 6:15 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.39.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
504 | 1155 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 503 | April 6, 2026 4:15 | April 7, 2026 10:15 | 4/6/26 4:15 | 4/7/26 10:15 | 4/6/26 4:15 | 4/7/26 10:15 | 0h | 0h | 0ed | 1 | 4/6/26 4:15 | 4/7/26 10:15 | April 6, 2026 4:15 | April 7, 2026 10:15 | As Soon As Possible | NA | 4/7/26 10:15 | 4/7/26 10:15 | 4/2/26 6:15 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.39.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
505 | 940 | Yes | Auto Scheduled | VC_Classes | 0.63d | Fixed Duration | 4 | 0.63d |  | April 7, 2026 10:15 | April 7, 2026 4:15 | 4/7/26 10:15 | 4/7/26 4:15 | 4/7/26 10:15 | 4/7/26 4:15 | 0d | 0d | 0ed | 1 | 4/7/26 10:15 | 4/7/26 4:15 | April 7, 2026 10:15 | April 7, 2026 4:15 | As Soon As Possible | NA | 4/7/26 1:15 | 4/7/26 1:15 | 4/1/26 1:30 | 5h | 5h | 5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.40 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
506 | 1156 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 5 | 0.25d | 504 | April 7, 2026 10:15 | April 7, 2026 1:15 | 4/7/26 10:15 | 4/7/26 1:15 | 4/7/26 10:15 | 4/7/26 1:15 | 0h | 0h | 0ed | 1 | 4/7/26 10:15 | 4/7/26 1:15 | April 7, 2026 10:15 | April 7, 2026 1:15 | As Soon As Possible | NA | 4/7/26 1:15 | 4/7/26 1:15 | 4/2/26 6:16 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.40.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
507 | 1157 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 506 | April 7, 2026 1:15 | April 7, 2026 4:15 | 4/7/26 1:15 | 4/7/26 4:15 | 4/7/26 1:15 | 4/7/26 4:15 | 0h | 0h | 0ed | 1 | 4/7/26 1:15 | 4/7/26 4:15 | April 7, 2026 1:15 | April 7, 2026 4:15 | As Soon As Possible | NA | 4/7/26 4:15 | 4/7/26 4:15 | 4/2/26 6:16 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.40.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
508 | 941 | Yes | Auto Scheduled | VC_Classification (Class Type 200) | 0.63d | Fixed Duration | 4 | 0.63d |  | April 15, 2026 3:15 | April 16, 2026 11:15 | 4/15/26 3:15 | 4/16/26 11:15 | 4/15/26 3:15 | 4/16/26 11:15 | 0d | 0d | 0ed | 1 | 4/15/26 3:15 | 4/16/26 11:15 | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 8:15 | 4/1/26 1:30 | 5h | 5h | 5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.41 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
509 | 1158 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 5 | 0.25d | 428 | April 15, 2026 3:15 | April 16, 2026 8:15 | 4/15/26 3:15 | 4/16/26 8:15 | 4/15/26 3:15 | 4/16/26 8:15 | 0h | 0h | 0ed | 1 | 4/15/26 3:15 | 4/16/26 8:15 | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 8:15 | 4/2/26 6:16 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.41.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
510 | 1159 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 509 | April 16, 2026 8:15 | April 16, 2026 11:15 | 4/16/26 8:15 | 4/16/26 11:15 | 4/16/26 8:15 | 4/16/26 11:15 | 0h | 0h | 0ed | 1 | 4/16/26 8:15 | 4/16/26 11:15 | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | 4/16/26 11:15 | 4/16/26 11:15 | 4/2/26 6:16 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.41.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
511 | 942 | Yes | Auto Scheduled | VC_Dependency Nets | 0.63d | Fixed Duration | 4 | 0.63d |  | April 15, 2026 3:15 | April 16, 2026 11:15 | 4/15/26 3:15 | 4/16/26 11:15 | 4/15/26 3:15 | 4/16/26 11:15 | 0d | 0d | 0ed | 1 | 4/15/26 3:15 | 4/16/26 11:15 | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 8:15 | 4/1/26 1:30 | 5h | 5h | 5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.42 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
512 | 1160 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 5 | 0.25d | 507,422 | April 15, 2026 3:15 | April 16, 2026 8:15 | 4/15/26 3:15 | 4/16/26 8:15 | 4/15/26 3:15 | 4/16/26 8:15 | 0h | 0h | 0ed | 1 | 4/15/26 3:15 | 4/16/26 8:15 | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 8:15 | 4/2/26 6:17 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.42.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
513 | 1161 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 512 | April 16, 2026 8:15 | April 16, 2026 11:15 | 4/16/26 8:15 | 4/16/26 11:15 | 4/16/26 8:15 | 4/16/26 11:15 | 0h | 0h | 0ed | 1 | 4/16/26 8:15 | 4/16/26 11:15 | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | 4/16/26 11:15 | 4/16/26 11:15 | 4/2/26 6:17 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.42.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
514 | 943 | Yes | Auto Scheduled | VC_Configuration Profiles | 0.63d | Fixed Duration | 4 | 0.63d |  | April 15, 2026 3:15 | April 16, 2026 11:15 | 4/15/26 3:15 | 4/16/26 11:15 | 4/15/26 3:15 | 4/16/26 11:15 | 0d | 0d | 0ed | 1 | 4/15/26 3:15 | 4/16/26 11:15 | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 8:15 | 4/1/26 1:30 | 5h | 5h | 5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.43 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
515 | 1162 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 5 | 0.25d | 422 | April 15, 2026 3:15 | April 16, 2026 8:15 | 4/15/26 3:15 | 4/16/26 8:15 | 4/15/26 3:15 | 4/16/26 8:15 | 0h | 0h | 0ed | 1 | 4/15/26 3:15 | 4/16/26 8:15 | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 8:15 | 4/2/26 6:17 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.43.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
516 | 1163 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 515 | April 16, 2026 8:15 | April 16, 2026 11:15 | 4/16/26 8:15 | 4/16/26 11:15 | 4/16/26 8:15 | 4/16/26 11:15 | 0h | 0h | 0ed | 1 | 4/16/26 8:15 | 4/16/26 11:15 | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | 4/16/26 11:15 | 4/16/26 11:15 | 4/2/26 6:17 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.43.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
517 | 944 | Yes | Auto Scheduled | VC_Variant Tables | 0.63d | Fixed Duration | 4 | 0.63d |  | April 16, 2026 11:15 | April 17, 2026 8:15 | 4/16/26 11:15 | 4/17/26 8:15 | 4/16/26 11:15 | 4/17/26 8:15 | 0d | 0d | 0ed | 1 | 4/16/26 11:15 | 4/17/26 8:15 | April 16, 2026 11:15 | April 17, 2026 8:15 | As Soon As Possible | NA | 4/16/26 2:15 | 4/16/26 2:15 | 4/1/26 1:30 | 5h | 5h | 5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.44 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
518 | 1164 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 5 | 0.25d | 516 | April 16, 2026 11:15 | April 16, 2026 2:15 | 4/16/26 11:15 | 4/16/26 2:15 | 4/16/26 11:15 | 4/16/26 2:15 | 0h | 0h | 0ed | 1 | 4/16/26 11:15 | 4/16/26 2:15 | April 16, 2026 11:15 | April 16, 2026 2:15 | As Soon As Possible | NA | 4/16/26 2:15 | 4/16/26 2:15 | 4/2/26 6:18 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.44.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
519 | 1165 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 518 | April 16, 2026 2:15 | April 17, 2026 8:15 | 4/16/26 2:15 | 4/17/26 8:15 | 4/16/26 2:15 | 4/17/26 8:15 | 0h | 0h | 0ed | 1 | 4/16/26 2:15 | 4/17/26 8:15 | April 16, 2026 2:15 | April 17, 2026 8:15 | As Soon As Possible | NA | 4/17/26 8:15 | 4/17/26 8:15 | 4/2/26 6:18 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.44.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
520 | 945 | Yes | Auto Scheduled | VC_Variant Tables Content | 0.63d | Fixed Duration | 4 | 0.63d |  | April 17, 2026 8:15 | April 17, 2026 2:15 | 4/17/26 8:15 | 4/17/26 2:15 | 4/17/26 8:15 | 4/17/26 2:15 | 0d | 0d | 0ed | 1 | 4/17/26 8:15 | 4/17/26 2:15 | April 17, 2026 8:15 | April 17, 2026 2:15 | As Soon As Possible | NA | 4/17/26 10:15 | 4/17/26 10:15 | 4/1/26 1:30 | 5h | 5h | 5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.45 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
521 | 1166 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 5 | 0.25d | 519 | April 17, 2026 8:15 | April 17, 2026 10:15 | 4/17/26 8:15 | 4/17/26 10:15 | 4/17/26 8:15 | 4/17/26 10:15 | 0h | 0h | 0ed | 1 | 4/17/26 8:15 | 4/17/26 10:15 | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | 4/17/26 10:15 | 4/17/26 10:15 | 4/2/26 6:18 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.45.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
522 | 1167 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 521 | April 17, 2026 10:15 | April 17, 2026 2:15 | 4/17/26 10:15 | 4/17/26 2:15 | 4/17/26 10:15 | 4/17/26 2:15 | 0h | 0h | 0ed | 1 | 4/17/26 10:15 | 4/17/26 2:15 | April 17, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | 4/17/26 2:15 | 4/17/26 2:15 | 4/2/26 6:18 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.45.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
523 | 946 | Yes | Auto Scheduled | VC_Characteristic Groups | 1.97d | Fixed Duration | 4 | 0.63d |  | April 17, 2026 8:00 | April 20, 2026 4:45 | 4/17/26 8:00 | 4/20/26 4:45 | 4/17/26 8:00 | 4/20/26 4:45 | 0d | 0d | 0ed | 1 | 4/17/26 8:00 | 4/20/26 4:45 | April 16, 2026 11:15 | April 17, 2026 8:15 | As Soon As Possible | NA | 4/20/26 1:45 | 4/20/26 1:45 | 4/1/26 1:30 | 15.75h | 5h | 15.75h | 0 | 0 | 0 | 0 | 0 | 1.2.1.46 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
524 | 1168 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 12.75h | Fixed Units | 5 | 0.25d | 516 | April 17, 2026 8:00 | April 20, 2026 1:45 | 4/17/26 8:00 | 4/20/26 1:45 | 4/17/26 8:00 | 4/20/26 1:45 | 0h | 0h | 0ed | 1 | 4/17/26 8:00 | 4/20/26 1:45 | April 16, 2026 11:15 | April 16, 2026 2:15 | Finish No Earlier Than | 4/17/26 5:00 | 4/20/26 1:45 | 4/20/26 1:45 | 4/2/26 6:18 | 12.75h | 2h | 12.75h | 0 | 0 | 0 | 0 | 0 | 1.2.1.46.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
525 | 1169 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 524 | April 20, 2026 1:45 | April 20, 2026 4:45 | 4/20/26 1:45 | 4/20/26 4:45 | 4/20/26 1:45 | 4/20/26 4:45 | 0h | 0h | 0ed | 1 | 4/20/26 1:45 | 4/20/26 4:45 | April 16, 2026 2:15 | April 17, 2026 8:15 | As Soon As Possible | NA | 4/20/26 4:45 | 4/20/26 4:45 | 4/2/26 6:18 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.46.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
526 | 713 | Yes | Auto Scheduled | PTM_CM52_Super_BOM | 4.09d | Fixed Duration | 4 | 1.13d |  | April 15, 2026 3:15 | April 21, 2026 4:00 | 4/15/26 3:15 | 4/21/26 4:00 | 4/15/26 3:15 | 4/21/26 4:00 | 0d | 0d | 0ed | 1 | 4/15/26 3:15 | 4/21/26 4:00 | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | 4/15/26 3:45 | 4/15/26 3:45 | 3/25/26 2:32 | 32.75h | 9h | 32.75h | 0 | 0 | 0 | 0 | 0 | 1.2.1.47 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
527 | 1094 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 428 | April 15, 2026 3:15 | April 15, 2026 3:45 | 4/15/26 3:15 | 4/15/26 3:45 | 4/15/26 3:15 | 4/15/26 3:45 | 0m | 0m | 0ed | 1 | 4/15/26 3:15 | 4/15/26 3:45 | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | 4/15/26 3:45 | 4/15/26 3:45 | 4/2/26 5:35 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.47.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
528 | 1095 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 527 | April 15, 2026 3:45 | April 15, 2026 4:15 | 4/15/26 3:45 | 4/15/26 4:15 | 4/15/26 3:45 | 4/15/26 4:15 | 0m | 0m | 0ed | 1 | 4/15/26 3:45 | 4/15/26 4:15 | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | 4/15/26 4:15 | 4/15/26 4:15 | 4/2/26 5:35 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.47.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
529 | 1096 | Yes | Auto Scheduled | Simulate Load | 24.75h | Fixed Units | 5 | 0.13d | 528 | April 15, 2026 4:15 | April 20, 2026 5:00 | 4/15/26 4:15 | 4/20/26 5:00 | 4/15/26 4:15 | 4/20/26 5:00 | 0h | 0h | 0ed | 1 | 4/15/26 4:15 | 4/20/26 5:00 | April 15, 2026 4:15 | April 16, 2026 8:15 | Finish No Earlier Than | 4/20/26 5:00 | 4/20/26 5:00 | 4/20/26 5:00 | 4/2/26 5:35 | 24.75h | 1h | 24.75h | 0 | 0 | 0 | 0 | 0 | 1.2.1.47.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
530 | 1097 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 529 | April 21, 2026 8:00 | April 21, 2026 10:00 | 4/21/26 8:00 | 4/21/26 10:00 | 4/21/26 8:00 | 4/21/26 10:00 | 0h | 0h | 0ed | 1 | 4/21/26 8:00 | 4/21/26 10:00 | April 16, 2026 8:15 | April 16, 2026 10:15 | Finish No Earlier Than | 4/17/26 5:00 | 4/21/26 10:00 | 4/21/26 10:00 | 4/2/26 5:35 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.47.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
531 | 1098 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 530 | April 21, 2026 10:00 | April 21, 2026 12:00 | 4/21/26 10:00 | 4/21/26 12:00 | 4/21/26 10:00 | 4/21/26 12:00 | 0h | 0h | 0ed | 1 | 4/21/26 10:00 | 4/21/26 12:00 | April 16, 2026 10:15 | April 16, 2026 1:15 | Start No Earlier Than | 4/17/26 8:00 | 4/21/26 12:00 | 4/21/26 12:00 | 4/2/26 5:35 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.47.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
532 | 1099 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 531 | April 21, 2026 1:00 | April 21, 2026 4:00 | 4/21/26 1:00 | 4/21/26 4:00 | 4/21/26 1:00 | 4/21/26 4:00 | 0h | 0h | 0ed | 1 | 4/21/26 1:00 | 4/21/26 4:00 | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | 4/21/26 4:00 | 4/21/26 4:00 | 4/2/26 5:35 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.47.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
533 | 714 | Yes | Auto Scheduled | PTM_CM53_Super_Routing | 2d | Fixed Duration | 4 | 1.13d |  | April 16, 2026 8:00 | April 17, 2026 5:00 | 4/16/26 8:00 | 4/17/26 5:00 | 4/16/26 8:00 | 4/17/26 5:00 | 0d | 0d | 0ed | 1 | 4/16/26 8:00 | 4/17/26 5:00 | April 16, 2026 4:15 | April 20, 2026 8:15 | As Soon As Possible | NA | 4/16/26 4:45 | 4/16/26 4:45 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.48 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
534 | 1100 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 532 | April 16, 2026 4:15 | April 16, 2026 4:45 | 4/16/26 4:15 | 4/16/26 4:45 | 4/16/26 4:15 | 4/16/26 4:45 | 0m | 0m | 0ed | 1 | 4/16/26 4:15 | 4/16/26 4:45 | April 16, 2026 4:15 | April 16, 2026 4:45 | As Soon As Possible | NA | 4/16/26 4:45 | 4/16/26 4:45 | 4/2/26 5:36 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.48.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
535 | 1101 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 534 | April 16, 2026 4:45 | April 17, 2026 8:15 | 4/16/26 4:45 | 4/17/26 8:15 | 4/16/26 4:45 | 4/17/26 8:15 | 0m | 0m | 0ed | 1 | 4/16/26 4:45 | 4/17/26 8:15 | April 16, 2026 4:45 | April 17, 2026 8:15 | As Soon As Possible | NA | 4/17/26 8:15 | 4/17/26 8:15 | 4/2/26 5:36 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.48.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
536 | 1102 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 535 | April 16, 2026 8:00 | April 17, 2026 9:00 | 4/16/26 8:00 | 4/17/26 9:00 | 4/16/26 8:00 | 4/17/26 9:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/17/26 9:00 | April 17, 2026 8:15 | April 17, 2026 9:15 | As Soon As Possible | NA | 4/17/26 9:00 | 4/17/26 9:00 | 4/2/26 5:36 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.48.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
537 | 1103 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 536 | April 17, 2026 9:00 | April 17, 2026 11:00 | 4/17/26 9:00 | 4/17/26 11:00 | 4/17/26 9:00 | 4/17/26 11:00 | 0h | 0h | 0ed | 1 | 4/17/26 9:00 | 4/17/26 11:00 | April 17, 2026 9:15 | April 17, 2026 11:15 | As Soon As Possible | NA | 4/17/26 11:00 | 4/17/26 11:00 | 4/2/26 5:36 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.48.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
538 | 1104 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 537 | April 17, 2026 11:00 | April 17, 2026 2:00 | 4/17/26 11:00 | 4/17/26 2:00 | 4/17/26 11:00 | 4/17/26 2:00 | 0h | 0h | 0ed | 1 | 4/17/26 11:00 | 4/17/26 2:00 | April 17, 2026 11:15 | April 17, 2026 2:15 | As Soon As Possible | NA | 4/17/26 2:00 | 4/17/26 2:00 | 4/2/26 5:36 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.48.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
539 | 1105 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 538 | April 17, 2026 2:00 | April 17, 2026 5:00 | 4/17/26 2:00 | 4/17/26 5:00 | 4/17/26 2:00 | 4/17/26 5:00 | 0h | 0h | 0ed | 1 | 4/17/26 2:00 | 4/17/26 5:00 | April 17, 2026 2:15 | April 20, 2026 8:15 | As Soon As Possible | NA | 4/17/26 5:00 | 4/17/26 5:00 | 4/2/26 5:36 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.48.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
540 | 949 | Yes | Auto Scheduled | VC_VK30 Pricing Variant | 0.38d | Fixed Duration | 4 | 0.69d |  | April 16, 2026 8:00 | April 16, 2026 11:00 | 4/16/26 8:00 | 4/16/26 11:00 | 4/16/26 8:00 | 4/16/26 11:00 | 0d | 0d | 0ed | 1 | 4/16/26 8:00 | 4/16/26 11:00 | April 17, 2026 2:15 | April 20, 2026 10:45 | As Soon As Possible | NA | 4/16/26 8:30 | 4/16/26 8:30 | 4/1/26 1:34 | 5.5h | 5.5h | 5.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.49 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
541 | 1106 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 538 | April 16, 2026 8:00 | April 16, 2026 8:30 | 4/16/26 8:00 | 4/16/26 8:30 | 4/16/26 8:00 | 4/16/26 8:30 | 0m | 0m | 0ed | 1 | 4/16/26 8:00 | 4/16/26 8:30 | April 17, 2026 2:15 | April 17, 2026 2:45 | Start No Earlier Than | 4/6/26 8:00 | 4/16/26 8:30 | 4/16/26 8:30 | 4/2/26 5:37 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.49.1 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
542 | 1107 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 541 | April 16, 2026 8:00 | April 16, 2026 10:00 | 4/16/26 8:00 | 4/16/26 10:00 | 4/16/26 8:00 | 4/16/26 10:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 10:00 | April 17, 2026 2:45 | April 17, 2026 4:45 | As Soon As Possible | NA | 4/16/26 10:00 | 4/16/26 10:00 | 4/2/26 5:37 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.49.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
543 | 1108 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 542 | April 16, 2026 8:00 | April 16, 2026 11:00 | 4/16/26 8:00 | 4/16/26 11:00 | 4/16/26 8:00 | 4/16/26 11:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 11:00 | April 17, 2026 4:45 | April 20, 2026 10:45 | As Soon As Possible | NA | 4/16/26 11:00 | 4/16/26 11:00 | 4/2/26 5:37 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.49.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
544 | 951 | Yes | Auto Scheduled | OTC_CM22_Pricing_Condition | 1.38d | Fixed Duration | 4 | 0.69d |  | April 15, 2026 8:00 | April 16, 2026 11:00 | 4/15/26 8:00 | 4/16/26 11:00 | 4/15/26 8:00 | 4/16/26 11:00 | 0d | 0d | 0ed | 1 | 4/15/26 8:00 | 4/16/26 11:00 | April 20, 2026 10:45 | April 21, 2026 8:15 | As Soon As Possible | NA | 4/15/26 8:30 | 4/15/26 8:30 | 3/25/26 2:32 | 8.5h | 5.5h | 8.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.50 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
545 | 1109 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 543 | April 15, 2026 8:00 | April 15, 2026 8:30 | 4/15/26 8:00 | 4/15/26 8:30 | 4/15/26 8:00 | 4/15/26 8:30 | 0m | 0m | 0ed | 1 | 4/15/26 8:00 | 4/15/26 8:30 | April 20, 2026 10:45 | April 20, 2026 11:15 | Start No Earlier Than | 4/6/26 8:00 | 4/15/26 8:30 | 4/15/26 8:30 | 4/2/26 5:38 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.50.1 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
546 | 1110 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 545 | April 15, 2026 8:00 | April 15, 2026 10:00 | 4/15/26 8:00 | 4/15/26 10:00 | 4/15/26 8:00 | 4/15/26 10:00 | 0h | 0h | 0ed | 1 | 4/15/26 8:00 | 4/15/26 10:00 | April 20, 2026 11:15 | April 20, 2026 2:15 | As Soon As Possible | NA | 4/15/26 10:00 | 4/15/26 10:00 | 4/2/26 5:38 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.50.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
547 | 1111 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 546 | April 16, 2026 8:00 | April 16, 2026 11:00 | 4/16/26 8:00 | 4/16/26 11:00 | 4/16/26 8:00 | 4/16/26 11:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 11:00 | April 20, 2026 2:15 | April 21, 2026 8:15 | As Soon As Possible | NA | 4/16/26 11:00 | 4/16/26 11:00 | 4/2/26 5:38 | 6h | 3h | 6h | 0 | 0 | 0 | 0 | 0 | 1.2.1.50.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda,kim | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
548 | 691 | Yes | Auto Scheduled | OTC_CM21_CMIR | 2.72d | Fixed Duration | 4 | 1.13d |  | April 16, 2026 8:00 | April 20, 2026 2:45 | 4/16/26 8:00 | 4/20/26 2:45 | 4/16/26 8:00 | 4/20/26 2:45 | 0d | 0d | 0ed | 1 | 4/16/26 8:00 | 4/20/26 2:45 | April 20, 2026 2:15 | April 21, 2026 3:15 | As Soon As Possible | NA | 4/16/26 8:00 | 4/16/26 8:00 | 3/25/26 2:32 | 4h | 9h | 4h | 0 | 0 | 0 | 0 | 0 | 1.2.1.51 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
549 | 1112 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 546,557 | April 20, 2026 2:15 | April 20, 2026 2:45 | 4/20/26 2:15 | 4/20/26 2:45 | 4/20/26 2:15 | 4/20/26 2:45 | 0m | 0m | 0ed | 1 | 4/20/26 2:15 | 4/20/26 2:45 | April 20, 2026 2:15 | April 20, 2026 2:45 | As Soon As Possible | NA | 4/20/26 2:45 | 4/20/26 2:45 | 4/2/26 5:40 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.51.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
550 | 1113 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 549 | April 16, 2026 8:00 | April 16, 2026 8:30 | 4/16/26 8:00 | 4/16/26 8:30 | 4/16/26 8:00 | 4/16/26 8:30 | 0m | 0m | 0ed | 1 | 4/16/26 8:00 | 4/16/26 8:30 | April 20, 2026 2:45 | April 20, 2026 3:15 | As Soon As Possible | NA | 4/16/26 8:30 | 4/16/26 8:30 | 4/2/26 5:40 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.51.2 | 500 | No | No | No |  | Kim | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
551 | 1114 | Yes | Auto Scheduled | Simulate Load | 0h | Fixed Units | 5 | 0.13d | 550 | April 16, 2026 8:00 | April 16, 2026 8:00 | 4/16/26 8:00 | 4/16/26 8:00 | 4/16/26 8:00 | 4/16/26 8:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 8:00 | April 20, 2026 3:15 | April 20, 2026 4:15 | As Soon As Possible | NA | 4/16/26 8:00 | 4/16/26 8:00 | 4/2/26 5:40 | 0h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.1.51.3 | 500 | Yes | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
552 | 1115 | Yes | Auto Scheduled | Error and Defect Mitigation | 0h | Fixed Units | 5 | 0.25d | 551 | April 16, 2026 8:00 | April 16, 2026 8:00 | 4/16/26 8:00 | 4/16/26 8:00 | 4/16/26 8:00 | 4/16/26 8:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 8:00 | April 20, 2026 4:15 | April 21, 2026 9:15 | As Soon As Possible | NA | 4/16/26 8:00 | 4/16/26 8:00 | 4/2/26 5:40 | 0h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.1.51.4 | 500 | Yes | No | No |  | Kim | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
553 | 1116 | Yes | Auto Scheduled | Load | 0h | Fixed Units | 5 | 0.25d | 552 | April 16, 2026 8:00 | April 16, 2026 8:00 | 4/16/26 8:00 | 4/16/26 8:00 | 4/16/26 8:00 | 4/16/26 8:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 8:00 | April 21, 2026 9:15 | April 21, 2026 11:15 | As Soon As Possible | NA | 4/16/26 8:00 | 4/16/26 8:00 | 4/2/26 5:40 | 0h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.1.51.5 | 500 | Yes | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
554 | 1117 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 553 | April 16, 2026 8:00 | April 16, 2026 11:00 | 4/16/26 8:00 | 4/16/26 11:00 | 4/16/26 8:00 | 4/16/26 11:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:00 | 4/16/26 11:00 | April 21, 2026 11:15 | April 21, 2026 3:15 | As Soon As Possible | NA | 4/16/26 11:00 | 4/16/26 11:00 | 4/2/26 5:40 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.51.6 | 500 | No | No | No |  | Kim | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
555 | 704 | Yes | Auto Scheduled | PTP_CM29_Source_List | 1.41d | Fixed Duration | 4 | 0.94d |  | April 17, 2026 8:00 | April 20, 2026 11:15 | 4/17/26 8:00 | 4/20/26 11:15 | 4/17/26 8:00 | 4/20/26 11:15 | 0d | 0d | 0ed | 1 | 4/17/26 8:00 | 4/20/26 11:15 | April 13, 2026 10:45 | April 14, 2026 10:15 | As Soon As Possible | NA | 4/17/26 8:30 | 4/17/26 8:30 | 3/25/26 2:32 | 5.5h | 5.5h | 5.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.52 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
556 | 1118 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 399,406 | April 17, 2026 8:00 | April 17, 2026 8:30 | 4/17/26 8:00 | 4/17/26 8:30 | 4/17/26 8:00 | 4/17/26 8:30 | 0m | 0m | 0ed | 1 | 4/17/26 8:00 | 4/17/26 8:30 | April 14, 2026 9:45 | April 14, 2026 10:15 | Start No Earlier Than | 4/17/26 8:00 | 4/17/26 8:30 | 4/17/26 8:30 | 4/2/26 5:41 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.52.1 | 500 | No | No | No |  | Sam | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
557 | 1119 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 375 | April 17, 2026 3:15 | April 20, 2026 8:15 | 4/17/26 3:15 | 4/20/26 8:15 | 4/17/26 3:15 | 4/20/26 8:15 | 0h | 0h | 0ed | 1 | 4/17/26 3:15 | 4/20/26 8:15 | April 13, 2026 10:45 | April 13, 2026 1:45 | Finish No Earlier Than | 4/17/26 5:00 | 4/20/26 8:15 | 4/20/26 8:15 | 4/2/26 5:41 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.52.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
558 | 1120 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 557 | April 20, 2026 8:15 | April 20, 2026 11:15 | 4/20/26 8:15 | 4/20/26 11:15 | 4/20/26 8:15 | 4/20/26 11:15 | 0h | 0h | 0ed | 1 | 4/20/26 8:15 | 4/20/26 11:15 | April 13, 2026 1:45 | April 13, 2026 4:45 | As Soon As Possible | NA | 4/20/26 11:15 | 4/20/26 11:15 | 4/2/26 5:41 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.52.3 | 500 | No | No | No |  | Sam | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
559 | 702 | Yes | Auto Scheduled | RTR_CM11_Asset_Master | 6.63d | Fixed Duration | 4 | 1.13d |  | April 15, 2026 8:00 | April 23, 2026 2:00 | 4/15/26 8:00 | 4/23/26 2:00 | 4/15/26 8:00 | 4/23/26 2:00 | 0d | 0d | 0ed | 1 | 4/15/26 8:00 | 4/23/26 2:00 | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | 4/15/26 8:30 | 4/15/26 8:30 | 3/25/26 2:32 | 53.5h | 9h | 53.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.53 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
560 | 1121 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d |  | April 15, 2026 8:00 | April 15, 2026 8:30 | 4/15/26 8:00 | 4/15/26 8:30 | 4/15/26 8:00 | 4/15/26 8:30 | 0m | 0m | 0ed | 1 | 4/15/26 8:00 | 4/15/26 8:30 | April 10, 2026 9:45 | April 10, 2026 10:15 | Start No Earlier Than | 4/15/26 8:00 | 4/15/26 8:30 | 4/15/26 8:30 | 4/2/26 5:43 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.53.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
561 | 1122 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 560 | April 15, 2026 8:30 | April 15, 2026 9:00 | 4/15/26 8:30 | 4/15/26 9:00 | 4/15/26 8:30 | 4/15/26 9:00 | 0m | 0m | 0ed | 1 | 4/15/26 8:30 | 4/15/26 9:00 | April 10, 2026 10:15 | April 10, 2026 10:45 | As Soon As Possible | NA | 4/15/26 9:00 | 4/15/26 9:00 | 4/2/26 5:43 | 1h | 0.5h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.53.2 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
562 | 1123 | Yes | Auto Scheduled | Simulate Load | 31h | Fixed Units | 5 | 0.13d | 561 | April 15, 2026 9:00 | April 20, 2026 5:00 | 4/15/26 9:00 | 4/20/26 5:00 | 4/15/26 9:00 | 4/20/26 5:00 | 0h | 0h | 0ed | 1 | 4/15/26 9:00 | 4/20/26 5:00 | April 10, 2026 10:45 | April 10, 2026 11:45 | Finish No Earlier Than | 4/20/26 5:00 | 4/20/26 5:00 | 4/20/26 5:00 | 4/2/26 5:43 | 31h | 1h | 31h | 0 | 0 | 0 | 0 | 0 | 1.2.1.53.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
563 | 1124 | Yes | Auto Scheduled | Error and Defect Mitigation | 16h | Fixed Units | 5 | 0.25d | 562 | April 21, 2026 8:00 | April 22, 2026 5:00 | 4/21/26 8:00 | 4/22/26 5:00 | 4/21/26 8:00 | 4/22/26 5:00 | 0h | 0h | 0ed | 1 | 4/21/26 8:00 | 4/22/26 5:00 | April 10, 2026 11:45 | April 10, 2026 2:45 | Finish No Earlier Than | 4/17/26 5:00 | 4/22/26 5:00 | 4/22/26 5:00 | 4/2/26 5:43 | 16h | 2h | 16h | 0 | 0 | 0 | 0 | 0 | 1.2.1.53.4 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
564 | 1125 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 563 | April 23, 2026 8:00 | April 23, 2026 10:00 | 4/23/26 8:00 | 4/23/26 10:00 | 4/23/26 8:00 | 4/23/26 10:00 | 0h | 0h | 0ed | 1 | 4/23/26 8:00 | 4/23/26 10:00 | April 10, 2026 2:45 | April 10, 2026 4:45 | Start No Earlier Than | 4/17/26 8:00 | 4/23/26 10:00 | 4/23/26 10:00 | 4/2/26 5:43 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.53.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
565 | 1126 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 564 | April 23, 2026 10:00 | April 23, 2026 2:00 | 4/23/26 10:00 | 4/23/26 2:00 | 4/23/26 10:00 | 4/23/26 2:00 | 0h | 0h | 0ed | 1 | 4/23/26 10:00 | 4/23/26 2:00 | April 10, 2026 4:45 | April 13, 2026 10:45 | As Soon As Possible | NA | 4/23/26 2:00 | 4/23/26 2:00 | 4/2/26 5:43 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.53.6 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
566 | 712 | Yes | Auto Scheduled | PTM_CM50_Material Class | 2.66d | Fixed Duration | 4 | 0.25d |  | April 16, 2026 10:45 | April 20, 2026 5:00 | 4/16/26 10:45 | 4/20/26 5:00 | 4/16/26 10:45 | 4/20/26 5:00 | 0d | 0d | 0ed | 1 | 4/16/26 10:45 | 4/20/26 5:00 | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | 4/16/26 11:15 | 4/16/26 11:15 | 3/25/26 2:32 | 17h | 2h | 17h | 0 | 0 | 0 | 0 | 0 | 1.2.1.54 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
567 | 1127 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 472 | April 16, 2026 10:45 | April 16, 2026 11:15 | 4/16/26 10:45 | 4/16/26 11:15 | 4/16/26 10:45 | 4/16/26 11:15 | 0m | 0m | 0ed | 1 | 4/16/26 10:45 | 4/16/26 11:15 | April 16, 2026 10:45 | April 16, 2026 11:15 | As Soon As Possible | NA | 4/16/26 11:15 | 4/16/26 11:15 | 4/2/26 5:46 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.54.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
568 | 1128 | Yes | Auto Scheduled | Load | 30m | Fixed Units | 5 | 0.06d | 567 | April 16, 2026 11:15 | April 16, 2026 11:45 | 4/16/26 11:15 | 4/16/26 11:45 | 4/16/26 11:15 | 4/16/26 11:45 | 0m | 0m | 0ed | 1 | 4/16/26 11:15 | 4/16/26 11:45 | April 16, 2026 11:15 | April 16, 2026 11:45 | As Soon As Possible | NA | 4/16/26 11:45 | 4/16/26 11:45 | 4/2/26 5:46 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.54.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
569 | 1129 | Yes | Auto Scheduled | Post Load Validation | 16h | Fixed Units | 5 | 0.13d | 568 | April 17, 2026 8:00 | April 20, 2026 5:00 | 4/17/26 8:00 | 4/20/26 5:00 | 4/17/26 8:00 | 4/20/26 5:00 | 0h | 0h | 0ed | 1 | 4/17/26 8:00 | 4/20/26 5:00 | April 16, 2026 11:45 | April 16, 2026 1:45 | Finish No Earlier Than | 4/20/26 5:00 | 4/20/26 5:00 | 4/20/26 5:00 | 4/2/26 5:46 | 16h | 1h | 16h | 0 | 0 | 0 | 0 | 0 | 1.2.1.54.3 | 500 | No | No | No |  | brad | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
570 | 715 | Yes | Auto Scheduled | PTM_CM55_Class assignment to materials | 1.13d | Fixed Duration | 4 | 1.13d |  | April 16, 2026 11:15 | April 17, 2026 1:15 | 4/16/26 11:15 | 4/17/26 1:15 | 4/16/26 11:15 | 4/17/26 1:15 | 0d | 0d | 0ed | 1 | 4/16/26 11:15 | 4/17/26 1:15 | April 16, 2026 11:15 | April 17, 2026 1:15 | As Soon As Possible | NA | 4/16/26 11:45 | 4/16/26 11:45 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.55 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
571 | 1133 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 567 | April 16, 2026 11:15 | April 16, 2026 11:45 | 4/16/26 11:15 | 4/16/26 11:45 | 4/16/26 11:15 | 4/16/26 11:45 | 0m | 0m | 0ed | 1 | 4/16/26 11:15 | 4/16/26 11:45 | April 16, 2026 11:15 | April 16, 2026 11:45 | As Soon As Possible | NA | 4/16/26 11:45 | 4/16/26 11:45 | 4/2/26 5:49 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.55.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
572 | 1134 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 571 | April 16, 2026 11:45 | April 16, 2026 1:15 | 4/16/26 11:45 | 4/16/26 1:15 | 4/16/26 11:45 | 4/16/26 1:15 | 0m | 0m | 0ed | 1 | 4/16/26 11:45 | 4/16/26 1:15 | April 16, 2026 11:45 | April 16, 2026 1:15 | As Soon As Possible | NA | 4/16/26 1:15 | 4/16/26 1:15 | 4/2/26 5:49 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.55.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
573 | 1135 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 572 | April 16, 2026 1:15 | April 16, 2026 2:15 | 4/16/26 1:15 | 4/16/26 2:15 | 4/16/26 1:15 | 4/16/26 2:15 | 0h | 0h | 0ed | 1 | 4/16/26 1:15 | 4/16/26 2:15 | April 16, 2026 1:15 | April 16, 2026 2:15 | As Soon As Possible | NA | 4/16/26 2:15 | 4/16/26 2:15 | 4/2/26 5:49 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.55.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
574 | 1136 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 573 | April 16, 2026 2:15 | April 16, 2026 4:15 | 4/16/26 2:15 | 4/16/26 4:15 | 4/16/26 2:15 | 4/16/26 4:15 | 0h | 0h | 0ed | 1 | 4/16/26 2:15 | 4/16/26 4:15 | April 16, 2026 2:15 | April 16, 2026 4:15 | As Soon As Possible | NA | 4/16/26 4:15 | 4/16/26 4:15 | 4/2/26 5:49 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.55.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
575 | 1137 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 574 | April 16, 2026 4:15 | April 17, 2026 9:15 | 4/16/26 4:15 | 4/17/26 9:15 | 4/16/26 4:15 | 4/17/26 9:15 | 0h | 0h | 0ed | 1 | 4/16/26 4:15 | 4/17/26 9:15 | April 16, 2026 4:15 | April 17, 2026 9:15 | As Soon As Possible | NA | 4/17/26 9:15 | 4/17/26 9:15 | 4/2/26 5:49 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.55.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
576 | 1138 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 575 | April 17, 2026 9:15 | April 17, 2026 1:15 | 4/17/26 9:15 | 4/17/26 1:15 | 4/17/26 9:15 | 4/17/26 1:15 | 0h | 0h | 0ed | 1 | 4/17/26 9:15 | 4/17/26 1:15 | April 17, 2026 9:15 | April 17, 2026 1:15 | As Soon As Possible | NA | 4/17/26 1:15 | 4/17/26 1:15 | 4/2/26 5:49 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.55.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
577 | 952 | Yes | Auto Scheduled | GTS - Material initial load from S4 (Run Interface) | 2.09d | Fixed Duration | 4 | 0.25d |  | April 16, 2026 8:15 | April 20, 2026 9:00 | 4/16/26 8:15 | 4/20/26 9:00 | 4/16/26 8:15 | 4/20/26 9:00 | 0d | 0d | 0ed | 1 | 4/16/26 8:15 | 4/20/26 9:00 | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | 4/17/26 5:00 | 4/17/26 5:00 | 4/1/26 1:39 | 16.75h | 2h | 16.75h | 0 | 0 | 0 | 0 | 0 | 1.2.1.56 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
578 | 1171 | Yes | Auto Scheduled | Run material interface to GTS | 15.75h | Fixed Units | 5 | 0.13d | 446 | April 16, 2026 8:15 | April 17, 2026 5:00 | 4/16/26 8:15 | 4/17/26 5:00 | 4/16/26 8:15 | 4/17/26 5:00 | 0h | 0h | 0ed | 1 | 4/16/26 8:15 | 4/17/26 5:00 | April 16, 2026 8:15 | April 16, 2026 9:15 | Finish No Earlier Than | 4/17/26 5:00 | 4/17/26 5:00 | 4/17/26 5:00 | 4/2/26 7:53 | 15.75h | 1h | 15.75h | 0 | 0 | 0 | 0 | 0 | 1.2.1.56.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
579 | 1173 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 5 | 0.13d | 578 | April 20, 2026 8:00 | April 20, 2026 9:00 | 4/20/26 8:00 | 4/20/26 9:00 | 4/20/26 8:00 | 4/20/26 9:00 | 0h | 0h | 0ed | 1 | 4/20/26 8:00 | 4/20/26 9:00 | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | 4/20/26 9:00 | 4/20/26 9:00 | 4/2/26 7:55 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.56.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
580 | 953 | Yes | Auto Scheduled | GTS - Customers initial load from S4 (Run Interface) | 4d | Fixed Duration | 4 | 0.25d |  | April 15, 2026 8:00 | April 20, 2026 5:00 | 4/15/26 8:00 | 4/20/26 5:00 | 4/15/26 8:00 | 4/20/26 5:00 | 0d | 0d | 0ed | 1 | 4/15/26 8:00 | 4/20/26 5:00 | April 10, 2026 1:45 | April 10, 2026 3:45 | As Soon As Possible | NA | 4/15/26 9:00 | 4/15/26 9:00 | 4/1/26 1:39 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.57 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
581 | 1174 | Yes | Auto Scheduled | Run material interface to GTS | 1h | Fixed Units | 5 | 0.13d |  | April 15, 2026 8:00 | April 15, 2026 9:00 | 4/15/26 8:00 | 4/15/26 9:00 | 4/15/26 8:00 | 4/15/26 9:00 | 0h | 0h | 0ed | 1 | 4/15/26 8:00 | 4/15/26 9:00 | April 10, 2026 1:45 | April 10, 2026 2:45 | Start No Earlier Than | 4/15/26 8:00 | 4/15/26 9:00 | 4/15/26 9:00 | 4/2/26 7:56 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.57.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
582 | 1175 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 5 | 0.13d | 581 | April 20, 2026 4:00 | April 20, 2026 5:00 | 4/20/26 4:00 | 4/20/26 5:00 | 4/20/26 4:00 | 4/20/26 5:00 | 0h | 0h | 0ed | 1 | 4/20/26 4:00 | 4/20/26 5:00 | April 10, 2026 2:45 | April 10, 2026 3:45 | Finish No Earlier Than | 4/20/26 5:00 | 4/20/26 5:00 | 4/20/26 5:00 | 4/2/26 7:56 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.57.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
583 | 954 | Yes | Auto Scheduled | GTS - Vendors initial load from S4 (Run Interface) | 0.25d | Fixed Duration | 4 | 0.25d |  | April 16, 2026 4:00 | April 17, 2026 9:00 | 4/16/26 4:00 | 4/17/26 9:00 | 4/16/26 4:00 | 4/17/26 9:00 | 0d | 0d | 0ed | 1 | 4/16/26 4:00 | 4/17/26 9:00 | April 15, 2026 2:00 | April 15, 2026 4:00 | As Soon As Possible | NA | 4/16/26 5:00 | 4/16/26 5:00 | 4/1/26 1:39 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.58 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
584 | 1176 | Yes | Auto Scheduled | Run material interface to GTS | 1h | Fixed Units | 5 | 0.13d | 389 | April 16, 2026 4:00 | April 16, 2026 5:00 | 4/16/26 4:00 | 4/16/26 5:00 | 4/16/26 4:00 | 4/16/26 5:00 | 0h | 0h | 0ed | 1 | 4/16/26 4:00 | 4/16/26 5:00 | April 15, 2026 2:00 | April 15, 2026 3:00 | As Soon As Possible | NA | 4/16/26 5:00 | 4/16/26 5:00 | 4/2/26 7:56 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.58.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
585 | 1177 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 5 | 0.13d | 584 | April 17, 2026 8:00 | April 17, 2026 9:00 | 4/17/26 8:00 | 4/17/26 9:00 | 4/17/26 8:00 | 4/17/26 9:00 | 0h | 0h | 0ed | 1 | 4/17/26 8:00 | 4/17/26 9:00 | April 15, 2026 3:00 | April 15, 2026 4:00 | As Soon As Possible | NA | 4/17/26 9:00 | 4/17/26 9:00 | 4/2/26 7:56 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.58.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
586 | 698 | Yes | Auto Scheduled | GTS - ECCN - Create | 5.63d | Fixed Duration | 4 | 5.63d |  | April 6, 2026 8:15 | April 13, 2026 2:15 | 4/6/26 8:15 | 4/13/26 2:15 | 4/6/26 8:15 | 4/13/26 2:15 | 0d | 0d | 0ed | 1 | 4/6/26 8:15 | 4/13/26 2:15 | April 6, 2026 8:15 | April 13, 2026 2:15 | As Soon As Possible | NA | 4/6/26 9:15 | 4/6/26 9:15 | 3/25/26 2:32 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.59 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
587 | 1178 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 5 | 0.13d | 261 | April 6, 2026 8:15 | April 6, 2026 9:15 | 4/6/26 8:15 | 4/6/26 9:15 | 4/6/26 8:15 | 4/6/26 9:15 | 0h | 0h | 0ed | 1 | 4/6/26 8:15 | 4/6/26 9:15 | April 6, 2026 8:15 | April 6, 2026 9:15 | As Soon As Possible | NA | 4/6/26 9:15 | 4/6/26 9:15 | 4/2/26 7:58 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.59.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
588 | 1179 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 5 | 0.13d | 584 | April 13, 2026 1:15 | April 13, 2026 2:15 | 4/13/26 1:15 | 4/13/26 2:15 | 4/13/26 1:15 | 4/13/26 2:15 | 0h | 0h | 0ed | 1 | 4/13/26 1:15 | 4/13/26 2:15 | April 13, 2026 1:15 | April 13, 2026 2:15 | As Soon As Possible | NA | 4/13/26 2:15 | 4/13/26 2:15 | 4/2/26 7:58 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.59.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
589 | 699 | Yes | Auto Scheduled | GTS - ECCN - Assign | 0.25d | Fixed Duration | 4 | 0.25d |  | April 16, 2026 10:15 | April 16, 2026 1:15 | 4/16/26 10:15 | 4/16/26 1:15 | 4/16/26 10:15 | 4/16/26 1:15 | 0d | 0d | 0ed | 1 | 4/16/26 10:15 | 4/16/26 1:15 | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | 4/16/26 11:15 | 4/16/26 11:15 | 3/25/26 2:32 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.60 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
590 | 1180 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 5 | 0.13d | 579 | April 16, 2026 10:15 | April 16, 2026 11:15 | 4/16/26 10:15 | 4/16/26 11:15 | 4/16/26 10:15 | 4/16/26 11:15 | 0h | 0h | 0ed | 1 | 4/16/26 10:15 | 4/16/26 11:15 | April 16, 2026 10:15 | April 16, 2026 11:15 | Finish No Earlier Than | 4/17/26 5:00 | 4/16/26 11:15 | 4/16/26 11:15 | 4/2/26 7:59 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.60.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
591 | 1181 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 5 | 0.13d | 590 | April 16, 2026 11:15 | April 16, 2026 1:15 | 4/16/26 11:15 | 4/16/26 1:15 | 4/16/26 11:15 | 4/16/26 1:15 | 0h | 0h | 0ed | 1 | 4/16/26 11:15 | 4/16/26 1:15 | April 16, 2026 11:15 | April 16, 2026 1:15 | As Soon As Possible | NA | 4/16/26 1:15 | 4/16/26 1:15 | 4/2/26 7:59 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.60.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
592 | 700 | Yes | Auto Scheduled | GTS - HTS - Create | 0.25d | Fixed Duration | 4 | 0.25d |  | April 6, 2026 8:15 | April 6, 2026 10:15 | 4/6/26 8:15 | 4/6/26 10:15 | 4/6/26 8:15 | 4/6/26 10:15 | 0d | 0d | 0ed | 1 | 4/6/26 8:15 | 4/6/26 10:15 | April 6, 2026 8:15 | April 6, 2026 10:15 | As Soon As Possible | NA | 4/6/26 9:15 | 4/6/26 9:15 | 3/25/26 2:32 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.61 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
593 | 1182 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 5 | 0.13d | 261 | April 6, 2026 8:15 | April 6, 2026 9:15 | 4/6/26 8:15 | 4/6/26 9:15 | 4/6/26 8:15 | 4/6/26 9:15 | 0h | 0h | 0ed | 1 | 4/6/26 8:15 | 4/6/26 9:15 | April 6, 2026 8:15 | April 6, 2026 9:15 | As Soon As Possible | NA | 4/6/26 9:15 | 4/6/26 9:15 | 4/2/26 8:01 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.61.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
594 | 1183 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 5 | 0.13d | 593 | April 6, 2026 9:15 | April 6, 2026 10:15 | 4/6/26 9:15 | 4/6/26 10:15 | 4/6/26 9:15 | 4/6/26 10:15 | 0h | 0h | 0ed | 1 | 4/6/26 9:15 | 4/6/26 10:15 | April 6, 2026 9:15 | April 6, 2026 10:15 | As Soon As Possible | NA | 4/6/26 10:15 | 4/6/26 10:15 | 4/2/26 8:01 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.61.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
595 | 701 | Yes | Auto Scheduled | GTS - HTS - Assign | 0.25d | Fixed Duration | 4 | 0.25d |  | April 16, 2026 8:45 | April 16, 2026 10:45 | 4/16/26 8:45 | 4/16/26 10:45 | 4/16/26 8:45 | 4/16/26 10:45 | 0d | 0d | 0ed | 1 | 4/16/26 8:45 | 4/16/26 10:45 | April 16, 2026 8:45 | April 16, 2026 10:45 | As Soon As Possible | NA | 4/16/26 9:45 | 4/16/26 9:45 | 3/25/26 2:32 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.62 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
596 | 1184 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 5 | 0.13d | 591 | April 16, 2026 8:45 | April 16, 2026 9:45 | 4/16/26 8:45 | 4/16/26 9:45 | 4/16/26 8:45 | 4/16/26 9:45 | 0h | 0h | 0ed | 1 | 4/16/26 8:45 | 4/16/26 9:45 | April 16, 2026 8:45 | April 16, 2026 9:45 | As Soon As Possible | NA | 4/16/26 9:45 | 4/16/26 9:45 | 4/2/26 8:01 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.62.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
597 | 1185 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 5 | 0.13d | 596 | April 16, 2026 9:45 | April 16, 2026 10:45 | 4/16/26 9:45 | 4/16/26 10:45 | 4/16/26 9:45 | 4/16/26 10:45 | 0h | 0h | 0ed | 1 | 4/16/26 9:45 | 4/16/26 10:45 | April 16, 2026 9:45 | April 16, 2026 10:45 | As Soon As Possible | NA | 4/16/26 10:45 | 4/16/26 10:45 | 4/2/26 8:01 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.62.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
598 | 706 | Yes | Auto Scheduled | GTS - License - Create | 0.25d | Fixed Duration | 4 | 0.25d |  | April 16, 2026 11:45 | April 16, 2026 2:45 | 4/16/26 11:45 | 4/16/26 2:45 | 4/16/26 11:45 | 4/16/26 2:45 | 0d | 0d | 0ed | 1 | 4/16/26 11:45 | 4/16/26 2:45 | April 16, 2026 11:45 | April 16, 2026 2:45 | As Soon As Possible | NA | 4/16/26 1:45 | 4/16/26 1:45 | 3/25/26 2:32 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.63 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
599 | 1186 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 5 | 0.13d | 596,612 | April 16, 2026 11:45 | April 16, 2026 1:45 | 4/16/26 11:45 | 4/16/26 1:45 | 4/16/26 11:45 | 4/16/26 1:45 | 0h | 0h | 0ed | 1 | 4/16/26 11:45 | 4/16/26 1:45 | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | 4/16/26 1:45 | 4/16/26 1:45 | 4/2/26 8:01 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.63.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
600 | 1187 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 5 | 0.13d | 599 | April 16, 2026 1:45 | April 16, 2026 2:45 | 4/16/26 1:45 | 4/16/26 2:45 | 4/16/26 1:45 | 4/16/26 2:45 | 0h | 0h | 0ed | 1 | 4/16/26 1:45 | 4/16/26 2:45 | April 16, 2026 1:45 | April 16, 2026 2:45 | As Soon As Possible | NA | 4/16/26 2:45 | 4/16/26 2:45 | 4/2/26 8:01 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.63.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
601 | 1213 | Yes | Auto Scheduled | Commodity Code/Tarif | 2.78d | Fixed Duration | 4 | 0.25d |  | April 16, 2026 10:45 | April 21, 2026 9:00 | 4/16/26 10:45 | 4/21/26 9:00 | 4/16/26 10:45 | 4/21/26 9:00 | 0d | 0d | 0ed | 1 | 4/16/26 10:45 | 4/21/26 9:00 | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | 4/20/26 5:00 | 4/20/26 5:00 | 4/7/26 9:27 | 22.25h | 2h | 22.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.64 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
602 | 1214 | Yes | Auto Scheduled | Load | 21.25h | Fixed Units | 5 | 0.13d | 597 | April 16, 2026 10:45 | April 20, 2026 5:00 | 4/16/26 10:45 | 4/20/26 5:00 | 4/16/26 10:45 | 4/20/26 5:00 | 0h | 0h | 0ed | 1 | 4/16/26 10:45 | 4/20/26 5:00 | April 16, 2026 10:45 | April 16, 2026 11:45 | Finish No Earlier Than | 4/20/26 5:00 | 4/20/26 5:00 | 4/20/26 5:00 | 4/7/26 9:27 | 21.25h | 1h | 21.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.64.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
603 | 1215 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 5 | 0.13d | 602 | April 21, 2026 8:00 | April 21, 2026 9:00 | 4/21/26 8:00 | 4/21/26 9:00 | 4/21/26 8:00 | 4/21/26 9:00 | 0h | 0h | 0ed | 1 | 4/21/26 8:00 | 4/21/26 9:00 | April 16, 2026 11:45 | April 16, 2026 1:45 | Start No Earlier Than | 4/17/26 8:00 | 4/21/26 9:00 | 4/21/26 9:00 | 4/7/26 9:27 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.64.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
604 | 1216 | Yes | Auto Scheduled | SPL Master File | 1.34d | Fixed Duration | 4 | 0.25d |  | April 15, 2026 8:00 | April 16, 2026 10:45 | 4/15/26 8:00 | 4/16/26 10:45 | 4/15/26 8:00 | 4/16/26 10:45 | 0d | 0d | 0ed | 1 | 4/15/26 8:00 | 4/16/26 10:45 | March 13, 2025 8:00 | March 13, 2025 10:00 | As Soon As Possible | NA | 4/15/26 9:00 | 4/15/26 9:00 | 4/7/26 9:30 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.65 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
605 | 1217 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 5 | 0.13d | 596 | April 16, 2026 9:45 | April 16, 2026 10:45 | 4/16/26 9:45 | 4/16/26 10:45 | 4/16/26 9:45 | 4/16/26 10:45 | 0h | 0h | 0ed | 1 | 4/16/26 9:45 | 4/16/26 10:45 | March 13, 2025 8:00 | March 13, 2025 9:00 | As Soon As Possible | NA | 4/16/26 10:45 | 4/16/26 10:45 | 4/7/26 9:30 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.65.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
606 | 1218 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 5 | 0.13d | 605 | April 15, 2026 8:00 | April 15, 2026 9:00 | 4/15/26 8:00 | 4/15/26 9:00 | 4/15/26 8:00 | 4/15/26 9:00 | 0h | 0h | 0ed | 1 | 4/15/26 8:00 | 4/15/26 9:00 | March 13, 2025 9:00 | March 13, 2025 10:00 | As Soon As Possible | NA | 4/15/26 9:00 | 4/15/26 9:00 | 4/7/26 9:30 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.65.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
607 | 1209 | Yes | Auto Scheduled | Initialize Embargo situation | 0.59d | Fixed Duration | 4 | 0.38d |  | April 13, 2026 2:15 | April 14, 2026 10:00 | 4/13/26 2:15 | 4/14/26 10:00 | 4/13/26 2:15 | 4/14/26 10:00 | 0d | 0d | 0ed | 1 | 4/13/26 2:15 | 4/14/26 10:00 | April 13, 2026 2:15 | April 14, 2026 8:15 | As Soon As Possible | NA | 4/13/26 3:15 | 4/13/26 3:15 | 4/7/26 9:24 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.66 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
608 | 1210 | Yes | Auto Scheduled | Run report /SAPSLL/EMB_CNTRY_INIT | 1h | Fixed Units | 5 | 0.13d | 588 | April 13, 2026 2:15 | April 13, 2026 3:15 | 4/13/26 2:15 | 4/13/26 3:15 | 4/13/26 2:15 | 4/13/26 3:15 | 0h | 0h | 0ed | 1 | 4/13/26 2:15 | 4/13/26 3:15 | April 13, 2026 2:15 | April 13, 2026 3:15 | As Soon As Possible | NA | 4/13/26 3:15 | 4/13/26 3:15 | 4/7/26 9:24 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.66.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
609 | 1211 | Yes | Auto Scheduled | Set Embargo situations | 1h | Fixed Units | 5 | 0.13d | 608 | April 14, 2026 8:00 | April 14, 2026 9:00 | 4/14/26 8:00 | 4/14/26 9:00 | 4/14/26 8:00 | 4/14/26 9:00 | 0h | 0h | 0ed | 1 | 4/14/26 8:00 | 4/14/26 9:00 | April 13, 2026 3:15 | April 13, 2026 4:15 | As Soon As Possible | NA | 4/14/26 9:00 | 4/14/26 9:00 | 4/7/26 9:24 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.66.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
610 | 1212 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 5 | 0.13d | 609 | April 14, 2026 9:00 | April 14, 2026 10:00 | 4/14/26 9:00 | 4/14/26 10:00 | 4/14/26 9:00 | 4/14/26 10:00 | 0h | 0h | 0ed | 1 | 4/14/26 9:00 | 4/14/26 10:00 | April 13, 2026 4:15 | April 14, 2026 8:15 | As Soon As Possible | NA | 4/14/26 10:00 | 4/14/26 10:00 | 4/7/26 9:26 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.66.3 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
611 | 955 | Yes | Auto Scheduled | GTS - SPL (Sanctioned party list) | 0.25d | Fixed Duration | 4 | 0.25d |  | April 16, 2026 10:45 | April 16, 2026 1:45 | 4/16/26 10:45 | 4/16/26 1:45 | 4/16/26 10:45 | 4/16/26 1:45 | 0d | 0d | 0ed | 1 | 4/16/26 10:45 | 4/16/26 1:45 | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | 4/16/26 11:45 | 4/16/26 11:45 | 4/1/26 1:40 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.67 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
612 | 1188 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 5 | 0.13d | 597 | April 16, 2026 10:45 | April 16, 2026 11:45 | 4/16/26 10:45 | 4/16/26 11:45 | 4/16/26 10:45 | 4/16/26 11:45 | 0h | 0h | 0ed | 1 | 4/16/26 10:45 | 4/16/26 11:45 | April 16, 2026 10:45 | April 16, 2026 11:45 | As Soon As Possible | NA | 4/16/26 11:45 | 4/16/26 11:45 | 4/2/26 8:02 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.67.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
613 | 1189 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 5 | 0.13d | 612 | April 16, 2026 11:45 | April 16, 2026 1:45 | 4/16/26 11:45 | 4/16/26 1:45 | 4/16/26 11:45 | 4/16/26 1:45 | 0h | 0h | 0ed | 1 | 4/16/26 11:45 | 4/16/26 1:45 | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | 4/16/26 1:45 | 4/16/26 1:45 | 4/2/26 8:02 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.67.2 | 500 | No | No | No |  | Kim Kolesar | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
614 | 950 | Yes | Auto Scheduled | RTR_CM17_Project Definition / Builder | 1.13d | Fixed Duration | 4 | 5.38d |  | April 20, 2026 8:00 | April 21, 2026 9:00 | 4/20/26 8:00 | 4/21/26 9:00 | 4/20/26 8:00 | 4/21/26 9:00 | 0d | 0d | 0ed | 1 | 4/20/26 8:00 | 4/21/26 9:00 | April 10, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | 4/20/26 8:30 | 4/20/26 8:30 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.68 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
615 | 1139 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 560 | April 20, 2026 8:00 | April 20, 2026 8:30 | 4/20/26 8:00 | 4/20/26 8:30 | 4/20/26 8:00 | 4/20/26 8:30 | 0m | 0m | 0ed | 1 | 4/20/26 8:00 | 4/20/26 8:30 | April 10, 2026 10:15 | April 10, 2026 10:45 | Start No Earlier Than | 4/20/26 8:00 | 4/20/26 8:30 | 4/20/26 8:30 | 4/2/26 5:52 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.68.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
616 | 1140 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 615 | April 20, 2026 8:30 | April 20, 2026 9:00 | 4/20/26 8:30 | 4/20/26 9:00 | 4/20/26 8:30 | 4/20/26 9:00 | 0m | 0m | 0ed | 1 | 4/20/26 8:30 | 4/20/26 9:00 | April 10, 2026 10:45 | April 10, 2026 11:15 | As Soon As Possible | NA | 4/20/26 9:00 | 4/20/26 9:00 | 4/2/26 5:52 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.68.2 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
617 | 1141 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 616 | April 20, 2026 9:00 | April 20, 2026 10:00 | 4/20/26 9:00 | 4/20/26 10:00 | 4/20/26 9:00 | 4/20/26 10:00 | 0h | 0h | 0ed | 1 | 4/20/26 9:00 | 4/20/26 10:00 | April 16, 2026 2:15 | April 16, 2026 3:15 | As Soon As Possible | NA | 4/20/26 10:00 | 4/20/26 10:00 | 4/2/26 5:52 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.68.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
618 | 1142 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 617 | April 20, 2026 10:00 | April 20, 2026 12:00 | 4/20/26 10:00 | 4/20/26 12:00 | 4/20/26 10:00 | 4/20/26 12:00 | 0h | 0h | 0ed | 1 | 4/20/26 10:00 | 4/20/26 12:00 | April 16, 2026 3:15 | April 17, 2026 8:15 | As Soon As Possible | NA | 4/20/26 12:00 | 4/20/26 12:00 | 4/2/26 5:52 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.68.4 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
619 | 1143 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 618 | April 20, 2026 1:00 | April 20, 2026 3:00 | 4/20/26 1:00 | 4/20/26 3:00 | 4/20/26 1:00 | 4/20/26 3:00 | 0h | 0h | 0ed | 1 | 4/20/26 1:00 | 4/20/26 3:00 | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | 4/20/26 3:00 | 4/20/26 3:00 | 4/2/26 5:52 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.68.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
620 | 1144 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 619 | April 20, 2026 3:00 | April 21, 2026 9:00 | 4/20/26 3:00 | 4/21/26 9:00 | 4/20/26 3:00 | 4/21/26 9:00 | 0h | 0h | 0ed | 1 | 4/20/26 3:00 | 4/21/26 9:00 | April 17, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | 4/21/26 9:00 | 4/21/26 9:00 | 4/2/26 5:52 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.68.6 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
621 | 754 | Yes | Auto Scheduled | RTR_CM18_WBS Element | 1.13d | Fixed Duration | 4 | 5.44d |  | April 20, 2026 8:30 | April 21, 2026 9:30 | 4/20/26 8:30 | 4/21/26 9:30 | 4/20/26 8:30 | 4/21/26 9:30 | 0d | 0d | 0ed | 1 | 4/20/26 8:30 | 4/21/26 9:30 | April 10, 2026 10:45 | April 17, 2026 3:15 | As Soon As Possible | NA | 4/20/26 9:00 | 4/20/26 9:00 | 3/25/26 2:32 | 9h | 9h | 9h | 0 | 0 | 0 | 0 | 0 | 1.2.1.69 | 500 | No | Yes | Yes |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
622 | 1145 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 5 | 0.06d | 615 | April 20, 2026 8:30 | April 20, 2026 9:00 | 4/20/26 8:30 | 4/20/26 9:00 | 4/20/26 8:30 | 4/20/26 9:00 | 0m | 0m | 0ed | 1 | 4/20/26 8:30 | 4/20/26 9:00 | April 10, 2026 10:45 | April 10, 2026 11:15 | Start No Earlier Than | 4/17/26 8:00 | 4/20/26 9:00 | 4/20/26 9:00 | 4/2/26 5:53 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.69.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
623 | 1146 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 5 | 0.06d | 622 | April 20, 2026 9:00 | April 20, 2026 9:30 | 4/20/26 9:00 | 4/20/26 9:30 | 4/20/26 9:00 | 4/20/26 9:30 | 0m | 0m | 0ed | 1 | 4/20/26 9:00 | 4/20/26 9:30 | April 10, 2026 11:15 | April 10, 2026 11:45 | As Soon As Possible | NA | 4/20/26 9:30 | 4/20/26 9:30 | 4/2/26 5:53 | 0.5h | 0.5h | 0.5h | 0 | 0 | 0 | 0 | 0 | 1.2.1.69.2 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
624 | 1147 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 5 | 0.13d | 623 | April 20, 2026 9:30 | April 20, 2026 10:30 | 4/20/26 9:30 | 4/20/26 10:30 | 4/20/26 9:30 | 4/20/26 10:30 | 0h | 0h | 0ed | 1 | 4/20/26 9:30 | 4/20/26 10:30 | April 16, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | 4/20/26 10:30 | 4/20/26 10:30 | 4/2/26 5:53 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.2.1.69.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
625 | 1148 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 5 | 0.25d | 624 | April 20, 2026 10:30 | April 20, 2026 1:30 | 4/20/26 10:30 | 4/20/26 1:30 | 4/20/26 10:30 | 4/20/26 1:30 | 0h | 0h | 0ed | 1 | 4/20/26 10:30 | 4/20/26 1:30 | April 16, 2026 4:15 | April 17, 2026 9:15 | As Soon As Possible | NA | 4/20/26 1:30 | 4/20/26 1:30 | 4/2/26 5:53 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.69.4 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
626 | 1149 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 5 | 0.25d | 625 | April 20, 2026 1:30 | April 20, 2026 3:30 | 4/20/26 1:30 | 4/20/26 3:30 | 4/20/26 1:30 | 4/20/26 3:30 | 0h | 0h | 0ed | 1 | 4/20/26 1:30 | 4/20/26 3:30 | April 17, 2026 9:15 | April 17, 2026 11:15 | As Soon As Possible | NA | 4/20/26 3:30 | 4/20/26 3:30 | 4/2/26 5:53 | 2h | 2h | 2h | 0 | 0 | 0 | 0 | 0 | 1.2.1.69.5 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
627 | 1150 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 5 | 0.38d | 626 | April 20, 2026 3:30 | April 21, 2026 9:30 | 4/20/26 3:30 | 4/21/26 9:30 | 4/20/26 3:30 | 4/21/26 9:30 | 0h | 0h | 0ed | 1 | 4/20/26 3:30 | 4/21/26 9:30 | April 17, 2026 11:15 | April 17, 2026 3:15 | As Soon As Possible | NA | 4/21/26 9:30 | 4/21/26 9:30 | 4/2/26 5:53 | 3h | 3h | 3h | 0 | 0 | 0 | 0 | 0 | 1.2.1.69.6 | 500 | No | No | No |  | Brian Wagner | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
628 | 1170 | Yes | Auto Scheduled | ITC1 Mock Data Loads Complete | 15m | Fixed Units | 4 | 0.03d |  | April 23, 2026 2:00 | April 23, 2026 2:15 | 4/23/26 2:00 | 4/23/26 2:15 | 4/23/26 2:00 | 4/23/26 2:15 | 0m | 0m | 0ed | 1 | 4/23/26 2:00 | 4/23/26 2:15 | April 21, 2026 3:15 | April 21, 2026 3:30 | As Soon As Possible | NA | 4/23/26 2:15 | 4/23/26 2:15 | 4/2/26 7:49 | 0.25h | 0.25h | 0.25h | 0 | 0 | 0 | 0 | 0 | 1.2.1.70 | 500 | Yes | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
629 | 2809 | Yes | Auto Scheduled | ITC2 Data Load Tasks QS4 | 105.63d | Fixed Duration | 3 | 0d | 260,41 | May 18, 2026 8:00 | October 12, 2026 2:00 | 5/18/26 8:00 | 10/12/26 2:00 | 5/4/26 2:29 | 6/5/26 4:00 | 0d | -90.75d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/23/26 1:03 | 657.5h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
630 | 1685 | Yes | Auto Scheduled | PMO Authorization to Start Data Loads | 2h | Fixed Units | 4 | 0.03d | 41 | May 18, 2026 8:00 | May 18, 2026 10:00 | 5/18/26 8:00 | 5/18/26 10:00 | 5/18/26 8:00 | 5/18/26 10:00 | 0h | 0h | 0ed | 0 | NA | NA | April 6, 2026 8:00 | April 6, 2026 8:15 | Must Start On | 5/18/26 8:00 | NA | NA | 4/23/26 10:49 | 2h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
631 | 2800 | Yes | Auto Scheduled | Master Data Loads | 9.63d | Fixed Duration | 4 | 0d | 630 | May 18, 2026 10:00 | May 29, 2026 4:00 | 5/18/26 10:00 | 5/29/26 4:00 | 5/4/26 2:29 | 5/18/26 10:29 | 0d | -9.56d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/23/26 11:42 | 655.5h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
632 | 1686 | Yes | Auto Scheduled | RTR_CM02_Profit Center Hierarchy | 0.75d | Fixed Duration | 5 | 0.75d |  | May 18, 2026 10:00 | May 18, 2026 5:00 | 5/18/26 10:00 | 5/18/26 5:00 | 5/4/26 2:29 | 5/5/26 11:29 | 0d | -9.56d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.1 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
633 | 1687 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d |  | May 18, 2026 10:00 | May 18, 2026 11:00 | 5/18/26 10:00 | 5/18/26 11:00 | 5/4/26 2:29 | 5/4/26 3:29 | 0h | -76.52h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.1.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
634 | 1688 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 633 | May 18, 2026 11:00 | May 18, 2026 2:00 | 5/18/26 11:00 | 5/18/26 2:00 | 5/4/26 3:29 | 5/5/26 8:29 | 0h | -76.52h | 0ed | 0 | NA | NA | April 6, 2026 9:15 | April 6, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.1.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
635 | 1689 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 634 | May 18, 2026 2:00 | May 18, 2026 5:00 | 5/18/26 2:00 | 5/18/26 5:00 | 5/5/26 8:29 | 5/5/26 11:29 | 0h | -76.52h | 0ed | 0 | NA | NA | April 6, 2026 11:15 | April 6, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.1.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
636 | 1690 | Yes | Auto Scheduled | RTR_CM03_Cost Center Hierarchy | 0.75d | Fixed Duration | 5 | 0.75d |  | May 19, 2026 8:00 | May 19, 2026 3:00 | 5/19/26 8:00 | 5/19/26 3:00 | 5/5/26 11:29 | 5/6/26 9:29 | 0d | -9.56d | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.2 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
637 | 1691 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 635 | May 19, 2026 8:00 | May 19, 2026 9:00 | 5/19/26 8:00 | 5/19/26 9:00 | 5/5/26 11:29 | 5/5/26 1:29 | 0h | -76.52h | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 6, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.2.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
638 | 1692 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 637 | May 19, 2026 9:00 | May 19, 2026 11:00 | 5/19/26 9:00 | 5/19/26 11:00 | 5/5/26 1:29 | 5/5/26 3:29 | 0h | -76.52h | 0ed | 0 | NA | NA | April 6, 2026 4:15 | April 7, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.2.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
639 | 1693 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 638 | May 19, 2026 11:00 | May 19, 2026 3:00 | 5/19/26 11:00 | 5/19/26 3:00 | 5/5/26 3:29 | 5/6/26 9:29 | 0h | -76.52h | 0ed | 0 | NA | NA | April 7, 2026 9:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.2.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
640 | 1694 | Yes | Auto Scheduled | RTR_CM01_GL_Account_Master to CC 1000 | 2.44d | Fixed Duration | 5 | 1.81d |  | May 19, 2026 3:00 | May 22, 2026 9:30 | 5/19/26 3:00 | 5/22/26 9:30 | 5/6/26 9:29 | 5/8/26 1:59 | 0d | -9.56d | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 9, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 16h | 16h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
641 | 1695 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 639 | May 19, 2026 3:00 | May 19, 2026 4:00 | 5/19/26 3:00 | 5/19/26 4:00 | 5/6/26 9:29 | 5/6/26 10:29 | 0h | -76.52h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
642 | 1696 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 641 | May 19, 2026 4:00 | May 20, 2026 9:00 | 5/19/26 4:00 | 5/20/26 9:00 | 5/6/26 10:29 | 5/6/26 1:29 | 0h | -76.52h | 0ed | 0 | NA | NA | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
643 | 1697 | Yes | Auto Scheduled | Simulate Load | 6h | Fixed Units | 6 | 0.75d | 642 | May 20, 2026 9:00 | May 20, 2026 4:00 | 5/20/26 9:00 | 5/20/26 4:00 | 5/6/26 1:29 | 5/7/26 10:29 | 0h | -76.52h | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
644 | 1698 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 643 | May 20, 2026 4:00 | May 21, 2026 10:30 | 5/20/26 4:00 | 5/21/26 10:30 | 5/7/26 10:29 | 5/7/26 2:59 | 0h | -76.52h | 0ed | 0 | NA | NA | April 8, 2026 8:15 | April 8, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
645 | 1699 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 644 | May 21, 2026 10:30 | May 21, 2026 11:30 | 5/21/26 10:30 | 5/21/26 11:30 | 5/7/26 2:59 | 5/7/26 3:59 | 0h | -76.52h | 0ed | 0 | NA | NA | April 8, 2026 11:45 | April 8, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
646 | 1700 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 645 | May 21, 2026 11:30 | May 21, 2026 2:30 | 5/21/26 11:30 | 5/21/26 2:30 | 5/7/26 3:59 | 5/8/26 8:59 | 0h | -76.52h | 0ed | 0 | NA | NA | April 8, 2026 1:45 | April 8, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
647 | 1701 | Yes | Auto Scheduled | Extend GL to all Company Codes | 2h | Fixed Units | 6 | 0.25d | 646 | May 21, 2026 2:30 | May 21, 2026 4:30 | 5/21/26 2:30 | 5/21/26 4:30 | 5/8/26 8:59 | 5/8/26 10:59 | 0h | -76.52h | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
648 | 1702 | Yes | Auto Scheduled | Post GL Extention Validation | 2h | Fixed Units | 6 | 0.25d | 647 | May 21, 2026 4:30 | May 22, 2026 9:30 | 5/21/26 4:30 | 5/22/26 9:30 | 5/8/26 10:59 | 5/8/26 1:59 | 0h | -76.52h | 0ed | 0 | NA | NA | April 9, 2026 8:45 | April 9, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.3.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
649 | 1703 | Yes | Auto Scheduled | RTR_CM05_Profit_Center | 1.13d | Fixed Duration | 5 | 1.13d |  | May 19, 2026 8:00 | May 20, 2026 9:00 | 5/19/26 8:00 | 5/20/26 9:00 | 5/7/26 8:29 | 5/8/26 9:29 | 0d | -7.94d | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.4 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
650 | 1704 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 635 | May 19, 2026 8:00 | May 19, 2026 9:00 | 5/19/26 8:00 | 5/19/26 9:00 | 5/7/26 8:29 | 5/7/26 9:29 | 0h | -63.52h | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 6, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.4.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
651 | 1705 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 650 | May 19, 2026 9:00 | May 19, 2026 11:00 | 5/19/26 9:00 | 5/19/26 11:00 | 5/7/26 9:29 | 5/7/26 11:29 | 0h | -63.52h | 0ed | 0 | NA | NA | April 6, 2026 4:15 | April 7, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.4.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
652 | 1706 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 651 | May 19, 2026 11:00 | May 19, 2026 12:00 | 5/19/26 11:00 | 5/19/26 12:00 | 5/7/26 11:29 | 5/7/26 1:29 | 0h | -63.52h | 0ed | 0 | NA | NA | April 7, 2026 9:15 | April 7, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.4.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
653 | 1707 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 652 | May 19, 2026 1:00 | May 19, 2026 3:00 | 5/19/26 1:00 | 5/19/26 3:00 | 5/7/26 1:29 | 5/7/26 3:29 | 0h | -63.52h | 0ed | 0 | NA | NA | April 7, 2026 10:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.4.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
654 | 1708 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 653 | May 19, 2026 3:00 | May 19, 2026 4:00 | 5/19/26 3:00 | 5/19/26 4:00 | 5/7/26 3:29 | 5/7/26 4:29 | 0h | -63.52h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.4.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
655 | 1709 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 654 | May 19, 2026 4:00 | May 20, 2026 9:00 | 5/19/26 4:00 | 5/20/26 9:00 | 5/7/26 4:29 | 5/8/26 9:29 | 0h | -63.52h | 0ed | 0 | NA | NA | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.4.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
656 | 1710 | Yes | Auto Scheduled | RTR_CM04_Cost_Center | 1.13d | Fixed Duration | 5 | 1.13d |  | May 20, 2026 9:00 | May 21, 2026 10:00 | 5/20/26 9:00 | 5/21/26 10:00 | 5/8/26 9:29 | 5/11/26 10:29 | 0d | -7.94d | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 9, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.5 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
657 | 1711 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 655 | May 20, 2026 9:00 | May 20, 2026 10:00 | 5/20/26 9:00 | 5/20/26 10:00 | 5/8/26 9:29 | 5/8/26 10:29 | 0h | -63.52h | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 8, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.5.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
658 | 1712 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 657 | May 20, 2026 10:00 | May 20, 2026 12:00 | 5/20/26 10:00 | 5/20/26 12:00 | 5/8/26 10:29 | 5/8/26 1:29 | 0h | -63.52h | 0ed | 0 | NA | NA | April 8, 2026 8:15 | April 8, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.5.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
659 | 1713 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 658 | May 20, 2026 1:00 | May 20, 2026 2:00 | 5/20/26 1:00 | 5/20/26 2:00 | 5/8/26 1:29 | 5/8/26 2:29 | 0h | -63.52h | 0ed | 0 | NA | NA | April 8, 2026 10:15 | April 8, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.5.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
660 | 1714 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 659 | May 20, 2026 2:00 | May 20, 2026 4:00 | 5/20/26 2:00 | 5/20/26 4:00 | 5/8/26 2:29 | 5/8/26 4:29 | 0h | -63.52h | 0ed | 0 | NA | NA | April 8, 2026 11:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.5.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
661 | 1715 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 660 | May 20, 2026 4:00 | May 20, 2026 5:00 | 5/20/26 4:00 | 5/20/26 5:00 | 5/8/26 4:29 | 5/11/26 8:29 | 0h | -63.52h | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 8, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.5.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
662 | 1716 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 661 | May 21, 2026 8:00 | May 21, 2026 10:00 | 5/21/26 8:00 | 5/21/26 10:00 | 5/11/26 8:29 | 5/11/26 10:29 | 0h | -63.52h | 0ed | 0 | NA | NA | April 8, 2026 3:15 | April 9, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.5.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
663 | 1717 | Yes | Auto Scheduled | Manual Configuration Activities in QS5 | 5.94d | Fixed Duration | 5 | 7.16d | 656 | May 21, 2026 10:00 | May 29, 2026 9:30 | 5/21/26 10:00 | 5/29/26 9:30 | 5/11/26 10:29 | 5/18/26 10:29 | 0d | -8.88d | 0ed | 0 | NA | NA | April 6, 2026 1:00 | April 15, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 43h | 43h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.6 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
664 | 1718 | Yes | Auto Scheduled | Open Client | 30m | Fixed Units | 6 | 0.06d |  | May 21, 2026 10:00 | May 21, 2026 10:30 | 5/21/26 10:00 | 5/21/26 10:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -1441m | 0ed | 0 | NA | NA | April 6, 2026 1:00 | April 6, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.6.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
665 | 1719 | Yes | Auto Scheduled | Service Enterprise Setup | 5d | Fixed Units | 6 | 5d | 632,636,640 | May 22, 2026 9:30 | May 29, 2026 9:30 | 5/22/26 9:30 | 5/29/26 9:30 | 5/11/26 10:29 | 5/18/26 10:29 | 0d | -8.88d | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 15, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 40h | 40h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.6.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
666 | 1720 | Yes | Auto Scheduled | Close Client | 30m | Fixed Units | 6 | 0.06d |  | May 21, 2026 10:00 | May 21, 2026 10:30 | 5/21/26 10:00 | 5/21/26 10:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -1441m | 0ed | 0 | NA | NA | April 6, 2026 1:00 | April 6, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.6.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
667 | 1721 | Yes | Auto Scheduled | Intercompany Business Partner Setup | 2h | Fixed Units | 6 | 0.25d | 632,636,648 | May 22, 2026 9:30 | May 22, 2026 11:30 | 5/22/26 9:30 | 5/22/26 11:30 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -33.02h | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.6.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
668 | 1722 | Yes | Auto Scheduled | RTR_CM09_Activity_Type | 1.38d | Fixed Duration | 5 | 1.22d |  | May 21, 2026 2:30 | May 25, 2026 8:30 | 5/21/26 2:30 | 5/25/26 8:30 | 5/14/26 4:29 | 5/18/26 10:29 | 0d | -4.75d | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.7 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
669 | 1723 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 646 | May 21, 2026 2:30 | May 21, 2026 4:45 | 5/21/26 2:30 | 5/21/26 4:45 | 5/14/26 4:29 | 5/15/26 9:44 | 0h | -38.02h | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 8, 2026 4:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.7.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
670 | 1724 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 669 | May 21, 2026 4:45 | May 22, 2026 10:30 | 5/21/26 4:45 | 5/22/26 10:30 | 5/15/26 9:44 | 5/15/26 1:29 | 0h | -38.02h | 0ed | 0 | NA | NA | April 8, 2026 3:15 | April 9, 2026 9:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.7.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
671 | 1725 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 670 | May 22, 2026 10:30 | May 22, 2026 11:30 | 5/22/26 10:30 | 5/22/26 11:30 | 5/15/26 1:29 | 5/15/26 2:29 | 0h | -38.02h | 0ed | 0 | NA | NA | April 9, 2026 9:00 | April 9, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.7.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
672 | 1726 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 671 | May 22, 2026 11:30 | May 22, 2026 2:30 | 5/22/26 11:30 | 5/22/26 2:30 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -38.02h | 0ed | 0 | NA | NA | April 9, 2026 10:00 | April 9, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.7.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
673 | 1727 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 672 | May 22, 2026 2:30 | May 22, 2026 3:30 | 5/22/26 2:30 | 5/22/26 3:30 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -38.02h | 0ed | 0 | NA | NA | April 9, 2026 1:00 | April 9, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.7.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
674 | 1728 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 673 | May 22, 2026 3:30 | May 25, 2026 8:30 | 5/22/26 3:30 | 5/25/26 8:30 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -38.02h | 0ed | 0 | NA | NA | April 9, 2026 2:00 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.7.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
675 | 1729 | Yes | Auto Scheduled | RTR_CM12_Activity Rates | 1.13d | Fixed Duration | 5 | 1.13d |  | May 19, 2026 3:00 | May 20, 2026 4:00 | 5/19/26 3:00 | 5/20/26 4:00 | 5/15/26 9:29 | 5/18/26 10:29 | 0d | -2.56d | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.8 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
676 | 1730 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 639 | May 19, 2026 3:00 | May 19, 2026 4:00 | 5/19/26 3:00 | 5/19/26 4:00 | 5/15/26 9:29 | 5/15/26 10:29 | 0h | -20.52h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.8.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
677 | 1731 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 676 | May 19, 2026 4:00 | May 20, 2026 9:00 | 5/19/26 4:00 | 5/20/26 9:00 | 5/15/26 10:29 | 5/15/26 1:29 | 0h | -20.52h | 0ed | 0 | NA | NA | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.8.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
678 | 1732 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 677 | May 20, 2026 9:00 | May 20, 2026 10:00 | 5/20/26 9:00 | 5/20/26 10:00 | 5/15/26 1:29 | 5/15/26 2:29 | 0h | -20.52h | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 8, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.8.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
679 | 1733 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 678 | May 20, 2026 10:00 | May 20, 2026 12:00 | 5/20/26 10:00 | 5/20/26 12:00 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -20.52h | 0ed | 0 | NA | NA | April 8, 2026 8:15 | April 8, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.8.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
680 | 1734 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 679 | May 20, 2026 1:00 | May 20, 2026 2:00 | 5/20/26 1:00 | 5/20/26 2:00 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -20.52h | 0ed | 0 | NA | NA | April 8, 2026 10:15 | April 8, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.8.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
681 | 1735 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 680 | May 20, 2026 2:00 | May 20, 2026 4:00 | 5/20/26 2:00 | 5/20/26 4:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -20.52h | 0ed | 0 | NA | NA | April 8, 2026 11:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.8.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
682 | 1736 | Yes | Auto Scheduled | RTR_CM06_Bank_master | 3.81d | Fixed Duration | 5 | 1.22d |  | May 18, 2026 10:00 | May 22, 2026 8:30 | 5/18/26 10:00 | 5/22/26 8:30 | 5/8/26 9:29 | 5/18/26 10:29 | 0d | -6.06d | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 13h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.9 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
683 | 1737 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 646 | May 21, 2026 2:30 | May 21, 2026 3:30 | 5/21/26 2:30 | 5/21/26 3:30 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -30.02h | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 8, 2026 4:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.9.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
684 | 1738 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 683 | May 21, 2026 3:30 | May 22, 2026 8:30 | 5/21/26 3:30 | 5/22/26 8:30 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -30.02h | 0ed | 0 | NA | NA | April 8, 2026 4:30 | April 9, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.9.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
685 | 1739 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d |  | May 18, 2026 10:00 | May 18, 2026 11:00 | 5/18/26 10:00 | 5/18/26 11:00 | 5/8/26 9:29 | 5/8/26 10:29 | 0h | -48.52h | 0ed | 0 | NA | NA | April 9, 2026 9:30 | April 9, 2026 10:30 | Start No Earlier Than | 4/15/26 8:00 | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.9.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
686 | 1740 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 685 | May 18, 2026 11:00 | May 18, 2026 2:00 | 5/18/26 11:00 | 5/18/26 2:00 | 5/8/26 10:29 | 5/8/26 1:29 | 0h | -48.52h | 0ed | 0 | NA | NA | April 9, 2026 10:30 | April 9, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.9.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
687 | 1741 | Yes | Auto Scheduled | Load | 5h | Fixed Units | 6 | 0.13d | 686 | May 18, 2026 2:00 | May 19, 2026 10:00 | 5/18/26 2:00 | 5/19/26 10:00 | 5/8/26 1:29 | 5/11/26 9:29 | 0h | -48.52h | 0ed | 0 | NA | NA | April 9, 2026 1:30 | April 9, 2026 2:30 | Finish No Earlier Than | 4/15/26 5:00 | NA | NA | 4/23/26 10:49 | 5h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.9.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
688 | 1742 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 687 | May 19, 2026 10:00 | May 19, 2026 4:30 | 5/19/26 10:00 | 5/19/26 4:30 | 5/11/26 9:29 | 5/11/26 3:59 | 0h | -48.52h | 0ed | 0 | NA | NA | April 9, 2026 8:00 | April 9, 2026 4:00 | Finish No Earlier Than | 4/14/26 5:00 | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.9.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
689 | 1743 | Yes | Auto Scheduled | RTR_CM08_Exchange_Rates | 1.13d | Fixed Duration | 5 | 1.13d |  | May 19, 2026 10:00 | May 20, 2026 11:00 | 5/19/26 10:00 | 5/20/26 11:00 | 5/15/26 9:29 | 5/18/26 10:29 | 0d | -2.06d | 0ed | 0 | NA | NA | April 9, 2026 2:30 | April 10, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.10 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
690 | 1744 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 687 | May 19, 2026 10:00 | May 19, 2026 11:00 | 5/19/26 10:00 | 5/19/26 11:00 | 5/15/26 9:29 | 5/15/26 10:29 | 0h | -16.52h | 0ed | 0 | NA | NA | April 9, 2026 2:30 | April 9, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.10.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
691 | 1745 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 690 | May 19, 2026 11:00 | May 19, 2026 2:00 | 5/19/26 11:00 | 5/19/26 2:00 | 5/15/26 10:29 | 5/15/26 1:29 | 0h | -16.52h | 0ed | 0 | NA | NA | April 9, 2026 3:30 | April 10, 2026 8:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.10.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
692 | 1746 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 691 | May 19, 2026 2:00 | May 19, 2026 3:00 | 5/19/26 2:00 | 5/19/26 3:00 | 5/15/26 1:29 | 5/15/26 2:29 | 0h | -16.52h | 0ed | 0 | NA | NA | April 10, 2026 8:30 | April 10, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.10.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
693 | 1747 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 692 | May 19, 2026 3:00 | May 19, 2026 5:00 | 5/19/26 3:00 | 5/19/26 5:00 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -16.52h | 0ed | 0 | NA | NA | April 10, 2026 9:30 | April 10, 2026 11:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.10.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
694 | 1748 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 693 | May 20, 2026 8:00 | May 20, 2026 9:00 | 5/20/26 8:00 | 5/20/26 9:00 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -16.52h | 0ed | 0 | NA | NA | April 10, 2026 11:30 | April 10, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.10.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
695 | 1749 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 694 | May 20, 2026 9:00 | May 20, 2026 11:00 | 5/20/26 9:00 | 5/20/26 11:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -16.52h | 0ed | 0 | NA | NA | April 10, 2026 1:30 | April 10, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.10.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
696 | 1750 | Yes | Auto Scheduled | RTR_CM14_Cost Element_Group | 1.44d | Fixed Duration | 5 | 4.78d |  | May 21, 2026 2:30 | May 25, 2026 9:00 | 5/21/26 2:30 | 5/25/26 9:00 | 5/14/26 3:59 | 5/18/26 10:29 | 0d | -4.81d | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 22.5h | 38.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.11 | 500 | No | Yes | Yes |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
697 | 1751 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 4.16d | 646 | May 21, 2026 2:30 | May 21, 2026 3:00 | 5/21/26 2:30 | 5/21/26 3:00 | 5/14/26 3:59 | 5/14/26 4:29 | 0m | -2311m | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 14, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 33.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.11.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
698 | 1752 | Yes | Auto Scheduled | Load | 8h | Fixed Units | 6 | 0.25d | 697 | May 21, 2026 3:00 | May 22, 2026 3:00 | 5/21/26 3:00 | 5/22/26 3:00 | 5/14/26 4:29 | 5/15/26 4:29 | 0h | -38.52h | 0ed | 0 | NA | NA | April 15, 2026 8:00 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 8h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.11.2 | 500 | No | No | No |  |  | Black | 2026-04-20 15:36 - jsw73 - Start ignored — already in progress | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
699 | 1753 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 698 | May 22, 2026 3:00 | May 25, 2026 9:00 | 5/22/26 3:00 | 5/25/26 9:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -38.52h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 2:00 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.11.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
700 | 1754 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Bill-To | 2h | Fixed Units | 5 | 0d |  | May 18, 2026 10:00 | May 18, 2026 12:00 | 5/18/26 10:00 | 5/18/26 12:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -1.52h | 0ed | 0 | NA | NA | April 16, 2025 8:00 | April 16, 2025 8:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.12 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
701 | 1755 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Ship-To | 1.5d | Fixed Duration | 5 | 3.13d |  | May 21, 2026 2:30 | May 25, 2026 9:30 | 5/21/26 2:30 | 5/25/26 9:30 | 5/8/26 10:59 | 5/18/26 10:29 | 0d | -9.31d | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 13.25h | 36h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.13 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
702 | 1756 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 646 | May 21, 2026 2:30 | May 21, 2026 3:00 | 5/21/26 2:30 | 5/21/26 3:00 | 5/8/26 10:59 | 5/8/26 11:29 | 0m | -4471m | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 8, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.13.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
703 | 1757 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 702 | May 21, 2026 3:00 | May 21, 2026 3:30 | 5/21/26 3:00 | 5/21/26 3:30 | 5/8/26 11:29 | 5/8/26 11:59 | 0m | -4471m | 0ed | 0 | NA | NA | April 8, 2026 4:15 | April 8, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.13.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
704 | 1758 | Yes | Auto Scheduled | Open client for BP number range update | 30m | Fixed Units | 6 | 1d | 703 | May 21, 2026 3:30 | May 21, 2026 4:00 | 5/21/26 3:30 | 5/21/26 4:00 | 5/18/26 9:14 | 5/18/26 9:44 | 0m | -1756m | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 9, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.13.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
705 | 1759 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 30m | Fixed Units | 6 | 1d | 704 | May 21, 2026 4:00 | May 21, 2026 4:30 | 5/21/26 4:00 | 5/21/26 4:30 | 5/18/26 9:44 | 5/18/26 10:14 | 0m | -1756m | 0ed | 0 | NA | NA | April 9, 2026 4:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.13.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
706 | 1760 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 6 | 1d | 705 | May 21, 2026 4:30 | May 21, 2026 4:45 | 5/21/26 4:30 | 5/21/26 4:45 | 5/18/26 10:14 | 5/18/26 10:29 | 0m | -1756m | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.25h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.13.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
707 | 1761 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 703 | May 21, 2026 3:30 | May 21, 2026 4:30 | 5/21/26 3:30 | 5/21/26 4:30 | 5/8/26 11:59 | 5/8/26 1:59 | 0h | -74.52h | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.13.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
708 | 1762 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | Fixed Units | 6 | 0.5d | 707 | May 21, 2026 4:30 | May 22, 2026 11:30 | 5/21/26 4:30 | 5/22/26 11:30 | 5/15/26 8:29 | 5/15/26 1:29 | 0h | -39.02h | 0ed | 0 | NA | NA | April 9, 2026 8:45 | April 9, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.13.7 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
709 | 1763 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 6 | 0.38d | 708 | May 22, 2026 11:30 | May 22, 2026 3:30 | 5/22/26 11:30 | 5/22/26 3:30 | 5/15/26 1:29 | 5/15/26 4:29 | 0h | -39.02h | 0ed | 0 | NA | NA | April 9, 2026 1:45 | April 9, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.13.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
710 | 1764 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 709 | May 22, 2026 3:30 | May 25, 2026 9:30 | 5/22/26 3:30 | 5/25/26 9:30 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -39.02h | 0ed | 0 | NA | NA | April 9, 2026 4:45 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.13.9 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
711 | 1765 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Sold-To | 1.63d | Fixed Duration | 5 | 1.63d |  | May 21, 2026 3:30 | May 25, 2026 11:30 | 5/21/26 3:30 | 5/25/26 11:30 | 5/8/26 1:59 | 5/18/26 10:29 | 0d | -9.19d | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 11.75h | 11.75h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.14 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
712 | 1766 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 703 | May 21, 2026 3:30 | May 21, 2026 4:00 | 5/21/26 3:30 | 5/21/26 4:00 | 5/18/26 9:29 | 5/18/26 9:59 | 0m | -1741m | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 9, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.14.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
713 | 1767 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 712 | May 21, 2026 4:00 | May 21, 2026 4:30 | 5/21/26 4:00 | 5/21/26 4:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -1741m | 0ed | 0 | NA | NA | April 9, 2026 8:15 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.14.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
714 | 1768 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 648,707 | May 22, 2026 9:30 | May 22, 2026 10:30 | 5/22/26 9:30 | 5/22/26 10:30 | 5/8/26 1:59 | 5/8/26 2:59 | 0h | -76.52h | 0ed | 0 | NA | NA | April 9, 2026 10:45 | April 9, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.14.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
715 | 1769 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | Fixed Units | 6 | 0.38d | 714 | May 22, 2026 10:30 | May 22, 2026 2:30 | 5/22/26 10:30 | 5/22/26 2:30 | 5/8/26 2:59 | 5/11/26 8:59 | 0h | -76.52h | 0ed | 0 | NA | NA | April 9, 2026 11:45 | April 9, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.14.4 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
716 | 1770 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 6 | 0.38d | 715 | May 22, 2026 2:30 | May 25, 2026 8:30 | 5/22/26 2:30 | 5/25/26 8:30 | 5/11/26 8:59 | 5/11/26 11:59 | 0h | -76.52h | 0ed | 0 | NA | NA | April 9, 2026 3:45 | April 10, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.14.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
717 | 1771 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 716 | May 25, 2026 8:30 | May 25, 2026 11:30 | 5/25/26 8:30 | 5/25/26 11:30 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -41.02h | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.14.6 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
718 | 1772 | Yes | Auto Scheduled | Open client for BP number range update | 15m | Fixed Units | 6 | 0.03d | 707 | May 21, 2026 4:30 | May 21, 2026 4:45 | 5/21/26 4:30 | 5/21/26 4:45 | 5/18/26 9:44 | 5/18/26 9:59 | 0m | -1786m | 0ed | 0 | NA | NA | April 9, 2026 8:45 | April 9, 2026 9:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.14.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
719 | 1773 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 15m | Fixed Units | 6 | 0.03d | 718 | May 21, 2026 4:45 | May 21, 2026 5:00 | 5/21/26 4:45 | 5/21/26 5:00 | 5/18/26 9:59 | 5/18/26 10:14 | 0m | -1786m | 0ed | 0 | NA | NA | April 9, 2026 9:00 | April 9, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.14.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
720 | 1774 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 6 | 0.03d | 719 | May 22, 2026 8:00 | May 22, 2026 8:15 | 5/22/26 8:00 | 5/22/26 8:15 | 5/18/26 10:14 | 5/18/26 10:29 | 0m | -1786m | 0ed | 0 | NA | NA | April 9, 2026 9:15 | April 9, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.14.9 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
721 | 1775 | Yes | Auto Scheduled | PTP_CM27_Vendor Master as Customer - FLCU01 | 4.81d | Fixed Duration | 5 | 2.31d |  | May 25, 2026 8:30 | May 29, 2026 4:00 | 5/25/26 8:30 | 5/29/26 4:00 | 5/11/26 11:59 | 5/18/26 10:29 | 0d | -9.56d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 14, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 19.25h | 19.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.15 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
722 | 1776 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 716 | May 25, 2026 8:30 | May 25, 2026 9:30 | 5/25/26 8:30 | 5/25/26 9:30 | 5/11/26 11:59 | 5/11/26 1:59 | 0h | -76.52h | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.15.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
723 | 1777 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 722 | May 25, 2026 9:30 | May 25, 2026 11:30 | 5/25/26 9:30 | 5/25/26 11:30 | 5/11/26 1:59 | 5/11/26 3:59 | 0h | -76.52h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.15.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
724 | 1778 | Yes | Auto Scheduled | Simulate Load | 11.25h | Fixed Units | 6 | 1.41d | 688,723 | May 25, 2026 11:30 | May 26, 2026 3:45 | 5/25/26 11:30 | 5/26/26 3:45 | 5/11/26 3:59 | 5/13/26 10:14 | 0h | -76.52h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 13, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 11.25h | 11.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.15.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
725 | 1779 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 724 | May 26, 2026 3:45 | May 28, 2026 10:30 | 5/26/26 3:45 | 5/28/26 10:30 | 5/13/26 10:14 | 5/14/26 2:59 | 0h | -76.52h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 14, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.15.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
726 | 1780 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 725 | May 28, 2026 10:30 | May 29, 2026 2:00 | 5/28/26 10:30 | 5/29/26 2:00 | 5/14/26 2:59 | 5/18/26 8:29 | 0h | -76.52h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 14, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.15.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
727 | 1781 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 726 | May 29, 2026 2:00 | May 29, 2026 4:00 | 5/29/26 2:00 | 5/29/26 4:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -76.52h | 0ed | 0 | NA | NA | April 14, 2026 10:15 | April 14, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.15.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
728 | 1782 | Yes | Auto Scheduled | OTC_CM23_Customer_Hierarchy | 0.69d | Fixed Duration | 5 | 0.69d |  | May 25, 2026 8:30 | May 25, 2026 3:00 | 5/25/26 8:30 | 5/25/26 3:00 | 5/15/26 1:59 | 5/18/26 10:29 | 0d | -5.44d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.16 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
729 | 1783 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 716 | May 25, 2026 8:30 | May 25, 2026 9:00 | 5/25/26 8:30 | 5/25/26 9:00 | 5/15/26 1:59 | 5/15/26 2:29 | 0m | -2611m | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.16.1 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
730 | 1784 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 729 | May 25, 2026 9:00 | May 25, 2026 11:00 | 5/25/26 9:00 | 5/25/26 11:00 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -43.52h | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.16.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
731 | 1785 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 730 | May 25, 2026 11:00 | May 25, 2026 3:00 | 5/25/26 11:00 | 5/25/26 3:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -43.52h | 0ed | 0 | NA | NA | April 10, 2026 1:15 | April 10, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.16.3 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
732 | 1786 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Z001 - External Sales Rep | 3.38d | Fixed Duration | 5 | 1.13d |  | May 25, 2026 8:30 | May 28, 2026 11:30 | 5/25/26 8:30 | 5/28/26 11:30 | 5/12/26 4:29 | 5/18/26 10:29 | 0d | -8.13d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.17 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
733 | 1787 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 716 | May 25, 2026 8:30 | May 25, 2026 9:30 | 5/25/26 8:30 | 5/25/26 9:30 | 5/12/26 4:29 | 5/13/26 8:29 | 0h | -65.02h | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.17.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
734 | 1788 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 733 | May 25, 2026 9:30 | May 25, 2026 11:30 | 5/25/26 9:30 | 5/25/26 11:30 | 5/13/26 8:29 | 5/13/26 10:29 | 0h | -65.02h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.17.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
735 | 1789 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 688,734 | May 25, 2026 11:30 | May 25, 2026 1:30 | 5/25/26 11:30 | 5/25/26 1:30 | 5/13/26 10:29 | 5/13/26 11:29 | 0h | -65.02h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.17.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
736 | 1790 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 735 | May 25, 2026 1:30 | May 25, 2026 3:30 | 5/25/26 1:30 | 5/25/26 3:30 | 5/13/26 11:29 | 5/13/26 2:29 | 0h | -65.02h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.17.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
737 | 1791 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 736 | May 25, 2026 3:30 | May 28, 2026 9:30 | 5/25/26 3:30 | 5/28/26 9:30 | 5/13/26 2:29 | 5/18/26 8:29 | 0h | -65.02h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.17.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
738 | 1792 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 737 | May 28, 2026 9:30 | May 28, 2026 11:30 | 5/28/26 9:30 | 5/28/26 11:30 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -65.02h | 0ed | 0 | NA | NA | April 13, 2026 8:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.17.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
739 | 1793 | Yes | Auto Scheduled | RTR_CM10_Credit_Management_Role | 1.84d | Fixed Duration | 5 | 1.13d |  | May 25, 2026 8:30 | May 26, 2026 4:15 | 5/25/26 8:30 | 5/26/26 4:15 | 5/13/26 2:44 | 5/15/26 1:29 | 0d | -7.35d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.18 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
740 | 1794 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 716 | May 25, 2026 8:30 | May 25, 2026 9:00 | 5/25/26 8:30 | 5/25/26 9:00 | 5/13/26 2:44 | 5/13/26 3:14 | 0m | -3526m | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.18.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
741 | 1795 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 740 | May 25, 2026 9:00 | May 25, 2026 9:30 | 5/25/26 9:00 | 5/25/26 9:30 | 5/13/26 3:14 | 5/13/26 3:44 | 0m | -3526m | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.18.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
742 | 1796 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 741 | May 25, 2026 9:30 | May 25, 2026 10:30 | 5/25/26 9:30 | 5/25/26 10:30 | 5/13/26 3:44 | 5/13/26 4:44 | 0h | -58.77h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.18.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
743 | 1797 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 742 | May 25, 2026 10:30 | May 25, 2026 2:00 | 5/25/26 10:30 | 5/25/26 2:00 | 5/13/26 4:44 | 5/14/26 10:14 | 0h | -58.77h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.18.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
744 | 1798 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 743 | May 25, 2026 2:00 | May 26, 2026 9:00 | 5/25/26 2:00 | 5/26/26 9:00 | 5/14/26 10:14 | 5/14/26 3:14 | 0h | -58.77h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.18.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
745 | 1799 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 744 | May 26, 2026 9:00 | May 26, 2026 4:15 | 5/26/26 9:00 | 5/26/26 4:15 | 5/14/26 3:14 | 5/15/26 1:29 | 0h | -58.77h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.18.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
746 | 1800 | Yes | Auto Scheduled | PTP_CM27_Vendor Master | 6.28d | Fixed Duration | 5 | 2.91d |  | May 18, 2026 10:00 | May 26, 2026 1:15 | 5/18/26 10:00 | 5/26/26 1:15 | 5/5/26 11:44 | 5/18/26 10:29 | 0d | -8.78d | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 10.25h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.19 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
747 | 1801 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 733 | May 25, 2026 9:30 | May 25, 2026 10:30 | 5/25/26 9:30 | 5/25/26 10:30 | 5/14/26 4:44 | 5/15/26 8:44 | 0h | -49.77h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.19.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
748 | 1802 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 747 | May 25, 2026 10:30 | May 25, 2026 1:30 | 5/25/26 10:30 | 5/25/26 1:30 | 5/15/26 8:44 | 5/15/26 10:44 | 0h | -49.77h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.19.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
749 | 1803 | Yes | Auto Scheduled | Simulate Load | 2.25h | Fixed Units | 6 | 0.13d | 748 | May 25, 2026 1:30 | May 25, 2026 3:45 | 5/25/26 1:30 | 5/25/26 3:45 | 5/15/26 10:44 | 5/15/26 1:59 | 0h | -49.77h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 14, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2.25h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.19.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
750 | 1804 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 749 | May 25, 2026 3:45 | May 26, 2026 1:15 | 5/25/26 3:45 | 5/26/26 1:15 | 5/15/26 1:59 | 5/18/26 10:29 | 0h | -49.77h | 0ed | 0 | NA | NA | April 14, 2026 2:00 | April 14, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.19.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
751 | 1805 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d |  | May 18, 2026 10:00 | May 18, 2026 11:00 | 5/18/26 10:00 | 5/18/26 11:00 | 5/5/26 11:44 | 5/5/26 1:44 | 0h | -70.27h | 0ed | 0 | NA | NA | April 14, 2026 4:00 | April 14, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.19.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
752 | 1806 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 751 | May 18, 2026 11:00 | May 18, 2026 2:00 | 5/18/26 11:00 | 5/18/26 2:00 | 5/5/26 1:44 | 5/5/26 3:44 | 0h | -70.27h | 0ed | 0 | NA | NA | April 15, 2026 8:00 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.19.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
753 | 1807 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | 0.88d | Fixed Duration | 5 | 3.16d |  | May 18, 2026 10:00 | May 19, 2026 9:00 | 5/18/26 10:00 | 5/19/26 9:00 | 5/14/26 3:29 | 5/18/26 10:29 | 0d | -1.44d | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.20 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
754 | 1808 | Yes | Auto Scheduled | Extract File(Will Extract from LFA1) | 1h | Fixed Units | 6 | 0.13d |  | May 18, 2026 10:00 | May 18, 2026 11:00 | 5/18/26 10:00 | 5/18/26 11:00 | 5/14/26 3:29 | 5/14/26 4:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.20.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
755 | 1809 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 754 | May 18, 2026 11:00 | May 18, 2026 2:00 | 5/18/26 11:00 | 5/18/26 2:00 | 5/14/26 4:29 | 5/15/26 9:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.20.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
756 | 1810 | Yes | Auto Scheduled | Simulate Load/ Not Needed | 1h | Fixed Units | 6 | 0.13d | 755 | May 18, 2026 2:00 | May 18, 2026 3:00 | 5/18/26 2:00 | 5/18/26 3:00 | 5/15/26 9:29 | 5/15/26 10:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 10, 2026 3:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.20.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
757 | 1811 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 756 | May 18, 2026 3:00 | May 18, 2026 5:00 | 5/18/26 3:00 | 5/18/26 5:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -5.52h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.20.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
758 | 1812 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 756 | May 18, 2026 3:00 | May 18, 2026 4:00 | 5/18/26 3:00 | 5/18/26 4:00 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 11:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.20.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
759 | 1813 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 758 | May 18, 2026 4:00 | May 19, 2026 9:00 | 5/18/26 4:00 | 5/19/26 9:00 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 15, 2026 11:00 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.20.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
760 | 1814 | Yes | Auto Scheduled | RTR_****_Credit Hierarchy | 1.91d | Fixed Duration | 5 | 1.25d |  | May 25, 2026 2:00 | May 27, 2026 1:15 | 5/25/26 2:00 | 5/27/26 1:15 | 5/15/26 2:29 | 5/18/26 10:29 | 0d | -7.22d | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.21 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
761 | 1815 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 743 | May 25, 2026 2:00 | May 25, 2026 2:30 | 5/25/26 2:00 | 5/25/26 2:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -2581m | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.21.1 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
762 | 1816 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 745 | May 26, 2026 4:15 | May 27, 2026 9:15 | 5/26/26 4:15 | 5/27/26 9:15 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -57.77h | 0ed | 0 | NA | NA | April 13, 2026 10:45 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.21.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
763 | 1817 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 762 | May 27, 2026 9:15 | May 27, 2026 1:15 | 5/27/26 9:15 | 5/27/26 1:15 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -57.77h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.21.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
764 | 1818 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Supplier | 1.13d | Fixed Duration | 5 | 1.13d |  | May 18, 2026 2:00 | May 19, 2026 3:00 | 5/18/26 2:00 | 5/19/26 3:00 | 5/15/26 9:29 | 5/18/26 10:29 | 0d | -1.44d | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 15h | 15h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.22 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
765 | 1819 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 752 | May 18, 2026 2:00 | May 18, 2026 2:30 | 5/18/26 2:00 | 5/18/26 2:30 | 5/15/26 9:29 | 5/15/26 9:59 | 0m | -691m | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 13, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.22.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
766 | 1820 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 765 | May 18, 2026 2:30 | May 18, 2026 3:00 | 5/18/26 2:30 | 5/18/26 3:00 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -691m | 0ed | 0 | NA | NA | April 13, 2026 1:15 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.22.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
767 | 1821 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 766 | May 18, 2026 3:00 | May 18, 2026 4:00 | 5/18/26 3:00 | 5/18/26 4:00 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.22.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
768 | 1822 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 767 | May 18, 2026 4:00 | May 19, 2026 9:00 | 5/18/26 4:00 | 5/19/26 9:00 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 13, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.22.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
769 | 1823 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 768 | May 19, 2026 9:00 | May 19, 2026 11:00 | 5/19/26 9:00 | 5/19/26 11:00 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 13, 2026 4:45 | April 14, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.22.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
770 | 1824 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 769 | May 19, 2026 11:00 | May 19, 2026 3:00 | 5/19/26 11:00 | 5/19/26 3:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 14, 2026 9:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.22.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
771 | 1825 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Customer | 1.06d | Fixed Duration | 5 | 1.13d |  | May 18, 2026 10:00 | May 19, 2026 10:30 | 5/18/26 10:00 | 5/19/26 10:30 | 5/15/26 9:59 | 5/18/26 10:29 | 0d | -1d | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 15h | 15h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.23 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
772 | 1826 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d |  | May 18, 2026 10:00 | May 18, 2026 10:30 | 5/18/26 10:00 | 5/18/26 10:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -1m | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 13, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.23.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
773 | 1827 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d |  | May 18, 2026 10:00 | May 18, 2026 10:30 | 5/18/26 10:00 | 5/18/26 10:30 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -481m | 0ed | 0 | NA | NA | April 13, 2026 1:15 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.23.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
774 | 1828 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 773 | May 18, 2026 10:30 | May 18, 2026 11:30 | 5/18/26 10:30 | 5/18/26 11:30 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -8.02h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.23.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
775 | 1829 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 774 | May 18, 2026 11:30 | May 18, 2026 2:30 | 5/18/26 11:30 | 5/18/26 2:30 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -8.02h | 0ed | 0 | NA | NA | April 13, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.23.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
776 | 1830 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 775 | May 18, 2026 2:30 | May 18, 2026 4:30 | 5/18/26 2:30 | 5/18/26 4:30 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -8.02h | 0ed | 0 | NA | NA | April 13, 2026 4:45 | April 14, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.23.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
777 | 1831 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 776 | May 18, 2026 4:30 | May 19, 2026 10:30 | 5/18/26 4:30 | 5/19/26 10:30 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -8.02h | 0ed | 0 | NA | NA | April 14, 2026 9:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.23.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
778 | 1832 | Yes | Auto Scheduled | PTP_CM26_Material_Master - All Types | 2.28d | Fixed Duration | 5 | 3.16d |  | May 18, 2026 11:00 | May 20, 2026 2:15 | 5/18/26 11:00 | 5/20/26 2:15 | 5/5/26 3:44 | 5/18/26 10:29 | 0d | -8.53d | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 15, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 19h | 19h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.24 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
779 | 1833 | Yes | Auto Scheduled | Extract File | 5h | Fixed Units | 6 | 0.63d | 754 | May 18, 2026 11:00 | May 19, 2026 9:45 | 5/18/26 11:00 | 5/19/26 9:45 | 5/15/26 11:44 | 5/18/26 10:29 | 0h | -7.27h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 13, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.24.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
780 | 1834 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 752 | May 18, 2026 2:00 | May 19, 2026 11:15 | 5/18/26 2:00 | 5/19/26 11:15 | 5/5/26 3:44 | 5/6/26 1:59 | 0h | -70.27h | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 14, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.24.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
781 | 1835 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 780 | May 19, 2026 11:15 | May 19, 2026 1:15 | 5/19/26 11:15 | 5/19/26 1:15 | 5/6/26 1:59 | 5/6/26 2:59 | 0h | -70.27h | 0ed | 0 | NA | NA | April 14, 2026 10:00 | April 14, 2026 11:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.24.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
782 | 1836 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | Fixed Units | 6 | 0.5d | 781 | May 19, 2026 1:15 | May 20, 2026 8:15 | 5/19/26 1:15 | 5/20/26 8:15 | 5/6/26 2:59 | 5/7/26 9:59 | 0h | -70.27h | 0ed | 0 | NA | NA | April 14, 2026 11:00 | April 14, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.24.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
783 | 1837 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 6 | 0.38d | 782 | May 20, 2026 8:15 | May 20, 2026 11:15 | 5/20/26 8:15 | 5/20/26 11:15 | 5/7/26 9:59 | 5/7/26 1:59 | 0h | -70.27h | 0ed | 0 | NA | NA | April 14, 2026 4:00 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.24.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
784 | 1838 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 783 | May 20, 2026 11:15 | May 20, 2026 2:15 | 5/20/26 11:15 | 5/20/26 2:15 | 5/8/26 11:29 | 5/8/26 2:29 | 0h | -63.77h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.24.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
785 | 1839 | Yes | Auto Scheduled | PTP_CM26_Material_Master - SERV - Service Materials | 1.34d | Fixed Duration | 5 | 5.88d |  | May 20, 2026 9:00 | May 21, 2026 11:45 | 5/20/26 9:00 | 5/21/26 11:45 | 5/15/26 9:59 | 5/18/26 10:29 | 0d | -3.16d | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 15h | 15h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.25 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
786 | 1840 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 655 | May 20, 2026 9:00 | May 20, 2026 9:30 | 5/20/26 9:00 | 5/20/26 9:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -901m | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 7, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.25.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
787 | 1841 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 783 | May 20, 2026 11:15 | May 20, 2026 11:45 | 5/20/26 11:15 | 5/20/26 11:45 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -1516m | 0ed | 0 | NA | NA | April 14, 2026 2:45 | April 14, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.25.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
788 | 1842 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 787 | May 20, 2026 11:45 | May 20, 2026 1:45 | 5/20/26 11:45 | 5/20/26 1:45 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -25.27h | 0ed | 0 | NA | NA | April 14, 2026 3:15 | April 14, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.25.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
789 | 1843 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 788 | May 20, 2026 1:45 | May 20, 2026 3:45 | 5/20/26 1:45 | 5/20/26 3:45 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -25.27h | 0ed | 0 | NA | NA | April 14, 2026 4:15 | April 15, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.25.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
790 | 1844 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 789 | May 20, 2026 3:45 | May 21, 2026 8:45 | 5/20/26 3:45 | 5/21/26 8:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -25.27h | 0ed | 0 | NA | NA | April 15, 2026 9:15 | April 15, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.25.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
791 | 1845 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 790 | May 21, 2026 8:45 | May 21, 2026 11:45 | 5/21/26 8:45 | 5/21/26 11:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -25.27h | 0ed | 0 | NA | NA | April 15, 2026 11:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.25.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
792 | 1846 | Yes | Auto Scheduled | PTP_CM26_Material_Master - KMAT - Configurable Materials | 1.34d | Fixed Duration | 5 | 5.88d |  | May 20, 2026 9:00 | May 21, 2026 11:45 | 5/20/26 9:00 | 5/21/26 11:45 | 5/7/26 1:59 | 5/13/26 2:44 | 0d | -8.5d | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.26 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
793 | 1847 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 655 | May 20, 2026 9:00 | May 20, 2026 9:30 | 5/20/26 9:00 | 5/20/26 9:30 | 5/13/26 2:14 | 5/13/26 2:44 | 0m | -2146m | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 7, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.26.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
794 | 1848 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 783 | May 20, 2026 11:15 | May 20, 2026 11:45 | 5/20/26 11:15 | 5/20/26 11:45 | 5/7/26 1:59 | 5/7/26 2:29 | 0m | -4216m | 0ed | 0 | NA | NA | April 14, 2026 2:45 | April 14, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.26.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
795 | 1849 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 794 | May 20, 2026 11:45 | May 20, 2026 1:45 | 5/20/26 11:45 | 5/20/26 1:45 | 5/7/26 2:29 | 5/7/26 3:29 | 0h | -70.27h | 0ed | 0 | NA | NA | April 14, 2026 3:15 | April 14, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.26.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
796 | 1850 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 795 | May 20, 2026 1:45 | May 20, 2026 3:45 | 5/20/26 1:45 | 5/20/26 3:45 | 5/7/26 3:29 | 5/8/26 8:29 | 0h | -70.27h | 0ed | 0 | NA | NA | April 14, 2026 4:15 | April 15, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.26.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
797 | 1851 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 796 | May 20, 2026 3:45 | May 21, 2026 8:45 | 5/20/26 3:45 | 5/21/26 8:45 | 5/8/26 8:29 | 5/8/26 10:29 | 0h | -70.27h | 0ed | 0 | NA | NA | April 15, 2026 9:15 | April 15, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.26.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
798 | 1852 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 797 | May 21, 2026 8:45 | May 21, 2026 11:45 | 5/21/26 8:45 | 5/21/26 11:45 | 5/8/26 10:29 | 5/8/26 2:29 | 0h | -70.27h | 0ed | 0 | NA | NA | April 15, 2026 11:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.26.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
799 | 1853 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Records | 3.59d | Fixed Duration | 5 | 1.28d |  | May 18, 2026 2:00 | May 22, 2026 9:45 | 5/18/26 2:00 | 5/22/26 9:45 | 5/11/26 2:22 | 5/18/26 10:29 | 0d | -4.96d | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.27 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
800 | 1854 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 784,798 | May 21, 2026 11:45 | May 21, 2026 1:45 | 5/21/26 11:45 | 5/21/26 1:45 | 5/11/26 2:22 | 5/11/26 3:22 | 0h | -62.39h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.27.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
801 | 1855 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 800 | May 21, 2026 1:45 | May 21, 2026 3:45 | 5/21/26 1:45 | 5/21/26 3:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -31.27h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.27.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
802 | 1856 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 801 | May 21, 2026 3:45 | May 21, 2026 4:45 | 5/21/26 3:45 | 5/21/26 4:45 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -31.27h | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.27.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
803 | 1857 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 802 | May 21, 2026 4:45 | May 22, 2026 9:45 | 5/21/26 4:45 | 5/22/26 9:45 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -31.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.27.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
804 | 1858 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 752 | May 18, 2026 2:00 | May 18, 2026 3:00 | 5/18/26 2:00 | 5/18/26 3:00 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -5.52h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 11:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.27.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
805 | 1859 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 804 | May 18, 2026 3:00 | May 18, 2026 5:00 | 5/18/26 3:00 | 5/18/26 5:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -5.52h | 0ed | 0 | NA | NA | April 15, 2026 11:00 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.27.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
806 | 1860 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record External Processing | 1.13d | Fixed Duration | 5 | 1.13d |  | May 21, 2026 11:45 | May 22, 2026 1:45 | 5/21/26 11:45 | 5/22/26 1:45 | 5/15/26 9:29 | 5/18/26 10:29 | 0d | -4.28d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.28 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
807 | 1861 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 784,798 | May 21, 2026 11:45 | May 21, 2026 1:15 | 5/21/26 11:45 | 5/21/26 1:15 | 5/15/26 9:29 | 5/15/26 9:59 | 0m | -2056m | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.28.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
808 | 1862 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 807 | May 21, 2026 1:15 | May 21, 2026 1:45 | 5/21/26 1:15 | 5/21/26 1:45 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -2056m | 0ed | 0 | NA | NA | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.28.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
809 | 1863 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 808 | May 21, 2026 1:45 | May 21, 2026 2:45 | 5/21/26 1:45 | 5/21/26 2:45 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -34.27h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.28.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
810 | 1864 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 809 | May 21, 2026 2:45 | May 21, 2026 4:45 | 5/21/26 2:45 | 5/21/26 4:45 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -34.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.28.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
811 | 1865 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 810 | May 21, 2026 4:45 | May 22, 2026 9:45 | 5/21/26 4:45 | 5/22/26 9:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -34.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.28.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
812 | 1866 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 811 | May 22, 2026 9:45 | May 22, 2026 1:45 | 5/22/26 9:45 | 5/22/26 1:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -34.27h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.28.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
813 | 1867 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | 1.13d | Fixed Duration | 5 | 1.13d |  | May 21, 2026 11:45 | May 22, 2026 1:45 | 5/21/26 11:45 | 5/22/26 1:45 | 5/8/26 2:29 | 5/18/26 10:29 | 0d | -8.78d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.29 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
814 | 1868 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 784,798 | May 21, 2026 11:45 | May 21, 2026 1:15 | 5/21/26 11:45 | 5/21/26 1:15 | 5/8/26 2:29 | 5/8/26 2:59 | 0m | -4216m | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.29.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
815 | 1869 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 814 | May 21, 2026 1:15 | May 21, 2026 1:45 | 5/21/26 1:15 | 5/21/26 1:45 | 5/8/26 2:59 | 5/8/26 3:29 | 0m | -4216m | 0ed | 0 | NA | NA | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.29.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
816 | 1870 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 815 | May 21, 2026 1:45 | May 21, 2026 2:45 | 5/21/26 1:45 | 5/21/26 2:45 | 5/8/26 3:29 | 5/8/26 4:29 | 0h | -70.27h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.29.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
817 | 1871 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 816 | May 21, 2026 2:45 | May 21, 2026 4:45 | 5/21/26 2:45 | 5/21/26 4:45 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -34.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.29.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
818 | 1872 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 817 | May 21, 2026 4:45 | May 22, 2026 9:45 | 5/21/26 4:45 | 5/22/26 9:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -34.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.29.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
819 | 1873 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 818 | May 22, 2026 9:45 | May 22, 2026 1:45 | 5/22/26 9:45 | 5/22/26 1:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -34.27h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.29.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
820 | 1874 | Yes | Auto Scheduled | PTM_CM31_BOM Conversion | 2.48d | Fixed Duration | 5 | 1.13d |  | May 21, 2026 1:45 | May 26, 2026 8:38 | 5/21/26 1:45 | 5/26/26 8:38 | 5/11/26 3:22 | 5/14/26 10:14 | 0d | -7.8d | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 19h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.30 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
821 | 1875 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 800 | May 21, 2026 1:45 | May 21, 2026 2:45 | 5/21/26 1:45 | 5/21/26 2:45 | 5/11/26 3:22 | 5/11/26 4:22 | 0h | -62.39h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.30.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
822 | 1876 | Yes | Auto Scheduled | Pre Load Validation | 0.5h | Fixed Units | 6 | 0.25d | 821 | May 21, 2026 2:45 | May 21, 2026 3:15 | 5/21/26 2:45 | 5/21/26 3:15 | 5/11/26 4:22 | 5/11/26 4:52 | 0h | -62.39h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.30.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
823 | 1877 | Yes | Auto Scheduled | Simulate Load | 15.5h | Fixed Units | 6 | 0.13d | 822 | May 21, 2026 3:15 | May 25, 2026 3:15 | 5/21/26 3:15 | 5/25/26 3:15 | 5/11/26 4:52 | 5/13/26 4:52 | 0h | -62.39h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 15.5h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.30.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
824 | 1878 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | Fixed Units | 6 | 0.25d | 823 | May 25, 2026 3:15 | May 25, 2026 3:45 | 5/25/26 3:15 | 5/25/26 3:45 | 5/13/26 4:52 | 5/14/26 8:22 | 0h | -62.39h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.30.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
825 | 1879 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 824 | May 25, 2026 3:45 | May 25, 2026 5:00 | 5/25/26 3:45 | 5/25/26 5:00 | 5/14/26 8:22 | 5/14/26 9:37 | 0h | -62.39h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 16, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 4/1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
826 | 1880 | Yes | Auto Scheduled | Post Load Validation | 0.5h | Fixed Units | 6 | 0.25d | 825 | May 26, 2026 8:00 | May 26, 2026 8:38 | 5/26/26 8:00 | 5/26/26 8:38 | 5/14/26 9:37 | 5/14/26 10:14 | 0h | -62.39h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.30.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
827 | 1881 | Yes | Auto Scheduled | PTM_CM40_Work Center Conversion | 3.08d | Fixed Duration | 5 | 2d |  | May 21, 2026 2:45 | May 26, 2026 3:23 | 5/21/26 2:45 | 5/26/26 3:23 | 5/12/26 4:59 | 5/14/26 4:59 | 0d | -7.8d | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 6.75h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.31 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
828 | 1882 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 821 | May 21, 2026 2:45 | May 21, 2026 3:45 | 5/21/26 2:45 | 5/21/26 3:45 | 5/12/26 4:59 | 5/13/26 8:59 | 0h | -53.77h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.31.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
829 | 1883 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 826 | May 26, 2026 8:38 | May 26, 2026 10:38 | 5/26/26 8:38 | 5/26/26 10:38 | 5/14/26 10:14 | 5/14/26 1:14 | 0h | -62.39h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.31.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
830 | 1884 | Yes | Auto Scheduled | Simulate Load | 0.25h | Fixed Units | 6 | 0.13d | 829 | May 26, 2026 10:38 | May 26, 2026 10:53 | 5/26/26 10:38 | 5/26/26 10:53 | 5/14/26 1:14 | 5/14/26 1:29 | 0h | -62.39h | 0ed | 0 | NA | NA | April 17, 2026 10:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.25h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.31.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
831 | 1885 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | Fixed Units | 6 | 0.25d | 830 | May 26, 2026 10:53 | May 26, 2026 11:23 | 5/26/26 10:53 | 5/26/26 11:23 | 5/14/26 1:29 | 5/14/26 1:59 | 0h | -62.39h | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.31.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
832 | 1886 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 831 | May 26, 2026 11:23 | May 26, 2026 1:23 | 5/26/26 11:23 | 5/26/26 1:23 | 5/14/26 1:59 | 5/14/26 2:59 | 0h | -62.39h | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 17, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.31.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
833 | 1887 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 832 | May 26, 2026 1:23 | May 26, 2026 3:23 | 5/26/26 1:23 | 5/26/26 3:23 | 5/14/26 2:59 | 5/14/26 4:59 | 0h | -62.39h | 0ed | 0 | NA | NA | April 17, 2026 3:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.31.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
834 | 1888 | Yes | Auto Scheduled | PTM_CM38_Routing Conversion | 4.27d | Fixed Duration | 5 | 2.88d |  | May 21, 2026 3:45 | May 28, 2026 8:53 | 5/21/26 3:45 | 5/28/26 8:53 | 5/13/26 8:59 | 5/18/26 10:29 | 0d | -7.8d | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 11h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.32 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
835 | 1889 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 828 | May 21, 2026 3:45 | May 21, 2026 4:45 | 5/21/26 3:45 | 5/21/26 4:45 | 5/13/26 8:59 | 5/13/26 9:59 | 0h | -53.77h | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.32.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
836 | 1890 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 833 | May 26, 2026 3:23 | May 27, 2026 10:53 | 5/26/26 3:23 | 5/27/26 10:53 | 5/14/26 4:59 | 5/15/26 1:29 | 0h | -62.39h | 0ed | 0 | NA | NA | April 20, 2026 8:15 | April 20, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.32.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
837 | 1891 | Yes | Auto Scheduled | Simulate Load | 2h | Fixed Units | 6 | 0.13d | 836 | May 27, 2026 10:53 | May 27, 2026 1:53 | 5/27/26 10:53 | 5/27/26 1:53 | 5/15/26 1:29 | 5/15/26 3:29 | 0h | -62.39h | 0ed | 0 | NA | NA | April 20, 2026 10:15 | April 20, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.32.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
838 | 1892 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | Fixed Units | 6 | 0.25d | 837SS | May 27, 2026 10:53 | May 27, 2026 2:53 | 5/27/26 10:53 | 5/27/26 2:53 | 5/15/26 1:29 | 5/15/26 4:29 | 0h | -62.39h | 0ed | 0 | NA | NA | April 20, 2026 11:15 | April 20, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.32.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
839 | 1893 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 838 | May 27, 2026 2:53 | May 27, 2026 3:53 | 5/27/26 2:53 | 5/27/26 3:53 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -62.39h | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 20, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.32.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
840 | 1894 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 839 | May 27, 2026 3:53 | May 28, 2026 8:53 | 5/27/26 3:53 | 5/28/26 8:53 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -62.39h | 0ed | 0 | NA | NA | April 20, 2026 3:15 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.32.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
841 | 1895 | Yes | Auto Scheduled | PTM_CM36_Production Version Conversion | 1.13d | Fixed Duration | 5 | 1.13d |  | May 21, 2026 4:45 | May 25, 2026 8:45 | 5/21/26 4:45 | 5/25/26 8:45 | 5/13/26 9:59 | 5/14/26 10:59 | 0d | -6.72d | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.33 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
842 | 1896 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 835 | May 21, 2026 4:45 | May 22, 2026 8:15 | 5/21/26 4:45 | 5/22/26 8:15 | 5/13/26 9:59 | 5/13/26 10:29 | 0m | -3226m | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.33.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
843 | 1897 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 842 | May 22, 2026 8:15 | May 22, 2026 8:45 | 5/22/26 8:15 | 5/22/26 8:45 | 5/13/26 10:29 | 5/13/26 10:59 | 0m | -3226m | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.33.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
844 | 1898 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 843 | May 22, 2026 8:45 | May 22, 2026 9:45 | 5/22/26 8:45 | 5/22/26 9:45 | 5/13/26 10:59 | 5/13/26 11:59 | 0h | -53.77h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.33.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
845 | 1899 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 844 | May 22, 2026 9:45 | May 22, 2026 11:45 | 5/22/26 9:45 | 5/22/26 11:45 | 5/13/26 11:59 | 5/13/26 2:59 | 0h | -53.77h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.33.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
846 | 1900 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 845 | May 22, 2026 11:45 | May 22, 2026 2:45 | 5/22/26 11:45 | 5/22/26 2:45 | 5/13/26 2:59 | 5/13/26 4:59 | 0h | -53.77h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.33.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
847 | 1901 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 846 | May 22, 2026 2:45 | May 25, 2026 8:45 | 5/22/26 2:45 | 5/25/26 8:45 | 5/13/26 4:59 | 5/14/26 10:59 | 0h | -53.77h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.33.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
848 | 1902 | Yes | Auto Scheduled | PTM_CM35_Inspection Plan | 1.13d | Fixed Duration | 5 | 1.13d |  | May 25, 2026 8:45 | May 26, 2026 9:45 | 5/25/26 8:45 | 5/26/26 9:45 | 5/14/26 10:59 | 5/18/26 10:29 | 0d | -6.72d | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 20, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.34 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
849 | 1903 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 847 | May 25, 2026 8:45 | May 25, 2026 9:15 | 5/25/26 8:45 | 5/25/26 9:15 | 5/14/26 10:59 | 5/14/26 11:29 | 0m | -3226m | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.34.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
850 | 1904 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 849 | May 25, 2026 9:15 | May 25, 2026 9:45 | 5/25/26 9:15 | 5/25/26 9:45 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -2836m | 0ed | 0 | NA | NA | April 17, 2026 11:45 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.34.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
851 | 1905 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 850 | May 25, 2026 9:45 | May 25, 2026 10:45 | 5/25/26 9:45 | 5/25/26 10:45 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -47.27h | 0ed | 0 | NA | NA | April 17, 2026 1:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.34.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
852 | 1906 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 851 | May 25, 2026 10:45 | May 25, 2026 1:45 | 5/25/26 10:45 | 5/25/26 1:45 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -47.27h | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 17, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.34.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
853 | 1907 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 852 | May 25, 2026 1:45 | May 25, 2026 3:45 | 5/25/26 1:45 | 5/25/26 3:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -47.27h | 0ed | 0 | NA | NA | April 17, 2026 4:15 | April 20, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.34.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
854 | 1908 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 853 | May 25, 2026 3:45 | May 26, 2026 9:45 | 5/25/26 3:45 | 5/26/26 9:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -47.27h | 0ed | 0 | NA | NA | April 20, 2026 9:15 | April 20, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.34.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
855 | 1909 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Serial Numbers | 1.13d | Fixed Duration | 5 | 1.13d |  | May 25, 2026 9:15 | May 26, 2026 10:15 | 5/25/26 9:15 | 5/26/26 10:15 | 5/14/26 11:29 | 5/15/26 1:29 | 0d | -6.72d | 0ed | 0 | NA | NA | April 17, 2026 11:45 | April 20, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.35 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
856 | 1910 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 849 | May 25, 2026 9:15 | May 25, 2026 9:45 | 5/25/26 9:15 | 5/25/26 9:45 | 5/14/26 11:29 | 5/14/26 11:59 | 0m | -3226m | 0ed | 0 | NA | NA | April 17, 2026 11:45 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.35.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
857 | 1911 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 856 | May 25, 2026 9:45 | May 25, 2026 10:15 | 5/25/26 9:45 | 5/25/26 10:15 | 5/14/26 11:59 | 5/14/26 1:29 | 0m | -3226m | 0ed | 0 | NA | NA | April 17, 2026 1:15 | April 17, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.35.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
858 | 1912 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 857 | May 25, 2026 10:15 | May 25, 2026 11:15 | 5/25/26 10:15 | 5/25/26 11:15 | 5/14/26 1:29 | 5/14/26 2:29 | 0h | -53.77h | 0ed | 0 | NA | NA | April 17, 2026 1:45 | April 17, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.35.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
859 | 1913 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 858 | May 25, 2026 11:15 | May 25, 2026 2:15 | 5/25/26 11:15 | 5/25/26 2:15 | 5/14/26 2:29 | 5/14/26 4:29 | 0h | -53.77h | 0ed | 0 | NA | NA | April 17, 2026 2:45 | April 17, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.35.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
860 | 1914 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 859 | May 25, 2026 2:15 | May 25, 2026 4:15 | 5/25/26 2:15 | 5/25/26 4:15 | 5/14/26 4:29 | 5/15/26 9:29 | 0h | -53.77h | 0ed | 0 | NA | NA | April 17, 2026 4:45 | April 20, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.35.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
861 | 1915 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 860 | May 25, 2026 4:15 | May 26, 2026 10:15 | 5/25/26 4:15 | 5/26/26 10:15 | 5/15/26 9:29 | 5/15/26 1:29 | 0h | -53.77h | 0ed | 0 | NA | NA | April 20, 2026 9:45 | April 20, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.35.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
862 | 1916 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Service | 6.78d | Fixed Duration | 5 | 1.13d |  | May 18, 2026 10:00 | May 27, 2026 8:15 | 5/18/26 10:00 | 5/27/26 8:15 | 5/15/26 1:29 | 5/18/26 10:29 | 0d | -6.72d | 0ed | 0 | NA | NA | April 20, 2026 1:45 | April 21, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.36 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
863 | 1917 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 861 | May 26, 2026 10:15 | May 26, 2026 10:45 | 5/26/26 10:15 | 5/26/26 10:45 | 5/15/26 1:29 | 5/15/26 1:59 | 0m | -3226m | 0ed | 0 | NA | NA | April 20, 2026 1:45 | April 20, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.36.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
864 | 1918 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 863 | May 26, 2026 10:45 | May 26, 2026 11:15 | 5/26/26 10:45 | 5/26/26 11:15 | 5/15/26 1:59 | 5/15/26 2:29 | 0m | -3226m | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 20, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.36.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
865 | 1919 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 864 | May 26, 2026 11:15 | May 26, 2026 1:15 | 5/26/26 11:15 | 5/26/26 1:15 | 5/15/26 2:29 | 5/15/26 3:29 | 0h | -53.77h | 0ed | 0 | NA | NA | April 20, 2026 2:45 | April 20, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.36.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
866 | 1920 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 865 | May 26, 2026 1:15 | May 26, 2026 3:15 | 5/26/26 1:15 | 5/26/26 3:15 | 5/15/26 3:29 | 5/18/26 8:29 | 0h | -53.77h | 0ed | 0 | NA | NA | April 20, 2026 3:45 | April 21, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.36.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
867 | 1921 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 866 | May 26, 2026 3:15 | May 27, 2026 8:15 | 5/26/26 3:15 | 5/27/26 8:15 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -53.77h | 0ed | 0 | NA | NA | April 21, 2026 8:45 | April 21, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.36.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
868 | 1922 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d |  | May 18, 2026 10:00 | May 18, 2026 2:00 | 5/18/26 10:00 | 5/18/26 2:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -2.52h | 0ed | 0 | NA | NA | April 21, 2026 10:45 | April 21, 2026 2:45 | Start No Earlier Than | 4/21/26 8:00 | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.36.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
869 | 1923 | Yes | Auto Scheduled | VC_Object Dependencies | 0.63d | Fixed Duration | 5 | 0.63d |  | May 18, 2026 10:00 | May 18, 2026 4:00 | 5/18/26 10:00 | 5/18/26 4:00 | 5/13/26 3:29 | 5/14/26 11:29 | 0d | -2.44d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.37 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
870 | 1924 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d |  | May 18, 2026 10:00 | May 18, 2026 12:00 | 5/18/26 10:00 | 5/18/26 12:00 | 5/13/26 3:29 | 5/14/26 8:29 | 0h | -19.52h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.37.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
871 | 1925 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 870 | May 18, 2026 1:00 | May 18, 2026 4:00 | 5/18/26 1:00 | 5/18/26 4:00 | 5/14/26 8:29 | 5/14/26 11:29 | 0h | -19.52h | 0ed | 0 | NA | NA | April 6, 2026 10:15 | April 6, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.37.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
872 | 1926 | Yes | Auto Scheduled | VC_Characteristics | 0.63d | Fixed Duration | 5 | 0.63d |  | May 18, 2026 4:00 | May 19, 2026 12:00 | 5/18/26 4:00 | 5/19/26 12:00 | 5/14/26 11:29 | 5/15/26 8:29 | 0d | -2.44d | 0ed | 0 | NA | NA | April 6, 2026 2:15 | April 7, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.38 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
873 | 1927 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 871 | May 18, 2026 4:00 | May 19, 2026 9:00 | 5/18/26 4:00 | 5/19/26 9:00 | 5/14/26 11:29 | 5/14/26 2:29 | 0h | -19.52h | 0ed | 0 | NA | NA | April 6, 2026 2:15 | April 6, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.38.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
874 | 1928 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 873 | May 19, 2026 9:00 | May 19, 2026 12:00 | 5/19/26 9:00 | 5/19/26 12:00 | 5/14/26 2:29 | 5/15/26 8:29 | 0h | -19.52h | 0ed | 0 | NA | NA | April 6, 2026 4:15 | April 7, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.38.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
875 | 1929 | Yes | Auto Scheduled | VC_Classes | 0.63d | Fixed Duration | 5 | 0.63d |  | May 19, 2026 1:00 | May 20, 2026 9:00 | 5/19/26 1:00 | 5/20/26 9:00 | 5/15/26 8:29 | 5/15/26 2:29 | 0d | -2.44d | 0ed | 0 | NA | NA | April 7, 2026 10:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.39 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
876 | 1930 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 874 | May 19, 2026 1:00 | May 19, 2026 3:00 | 5/19/26 1:00 | 5/19/26 3:00 | 5/15/26 8:29 | 5/15/26 10:29 | 0h | -19.52h | 0ed | 0 | NA | NA | April 7, 2026 10:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.39.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
877 | 1931 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 876 | May 19, 2026 3:00 | May 20, 2026 9:00 | 5/19/26 3:00 | 5/20/26 9:00 | 5/15/26 10:29 | 5/15/26 2:29 | 0h | -19.52h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.39.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
878 | 1932 | Yes | Auto Scheduled | VC_Classification (Class Type 200) | 0.63d | Fixed Duration | 5 | 0.63d |  | May 21, 2026 11:45 | May 22, 2026 8:45 | 5/21/26 11:45 | 5/22/26 8:45 | 5/15/26 2:29 | 5/18/26 10:29 | 0d | -3.78d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.40 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
879 | 1933 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 798 | May 21, 2026 11:45 | May 21, 2026 2:45 | 5/21/26 11:45 | 5/21/26 2:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -30.27h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.40.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
880 | 1934 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 879 | May 21, 2026 2:45 | May 22, 2026 8:45 | 5/21/26 2:45 | 5/22/26 8:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -30.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.40.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
881 | 1935 | Yes | Auto Scheduled | VC_Dependency Nets | 0.63d | Fixed Duration | 5 | 0.63d |  | May 21, 2026 11:45 | May 22, 2026 8:45 | 5/21/26 11:45 | 5/22/26 8:45 | 5/15/26 2:29 | 5/18/26 10:29 | 0d | -3.78d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.41 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
882 | 1936 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 792,877 | May 21, 2026 11:45 | May 21, 2026 2:45 | 5/21/26 11:45 | 5/21/26 2:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -30.27h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.41.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
883 | 1937 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 882 | May 21, 2026 2:45 | May 22, 2026 8:45 | 5/21/26 2:45 | 5/22/26 8:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -30.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.41.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
884 | 1938 | Yes | Auto Scheduled | VC_Configuration Profiles | 0.63d | Fixed Duration | 5 | 0.63d |  | May 21, 2026 11:45 | May 22, 2026 8:45 | 5/21/26 11:45 | 5/22/26 8:45 | 5/13/26 2:44 | 5/14/26 10:44 | 0d | -5.75d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.42 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
885 | 1939 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 792 | May 21, 2026 11:45 | May 21, 2026 2:45 | 5/21/26 11:45 | 5/21/26 2:45 | 5/13/26 2:44 | 5/13/26 4:44 | 0h | -46.02h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.42.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
886 | 1940 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 885 | May 21, 2026 2:45 | May 22, 2026 8:45 | 5/21/26 2:45 | 5/22/26 8:45 | 5/13/26 4:44 | 5/14/26 10:44 | 0h | -46.02h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.42.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
887 | 1941 | Yes | Auto Scheduled | VC_Variant Tables | 0.63d | Fixed Duration | 5 | 0.63d |  | May 22, 2026 8:45 | May 22, 2026 2:45 | 5/22/26 8:45 | 5/22/26 2:45 | 5/15/26 8:29 | 5/15/26 2:29 | 0d | -5.03d | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.43 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
888 | 1942 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 886 | May 22, 2026 8:45 | May 22, 2026 10:45 | 5/22/26 8:45 | 5/22/26 10:45 | 5/15/26 8:29 | 5/15/26 10:29 | 0h | -40.27h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.43.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
889 | 1943 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 888 | May 22, 2026 10:45 | May 22, 2026 2:45 | 5/22/26 10:45 | 5/22/26 2:45 | 5/15/26 10:29 | 5/15/26 2:29 | 0h | -40.27h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.43.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
890 | 1944 | Yes | Auto Scheduled | VC_Variant Tables Content | 0.63d | Fixed Duration | 5 | 0.63d |  | May 22, 2026 2:45 | May 25, 2026 10:45 | 5/22/26 2:45 | 5/25/26 10:45 | 5/15/26 2:29 | 5/18/26 10:29 | 0d | -5.03d | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.44 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
891 | 1945 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 889 | May 22, 2026 2:45 | May 22, 2026 4:45 | 5/22/26 2:45 | 5/22/26 4:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -40.27h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.44.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
892 | 1946 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 891 | May 22, 2026 4:45 | May 25, 2026 10:45 | 5/22/26 4:45 | 5/25/26 10:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -40.27h | 0ed | 0 | NA | NA | April 17, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.44.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
893 | 1947 | Yes | Auto Scheduled | VC_Characteristic Groups | 1.97d | Fixed Duration | 5 | 0.63d |  | May 22, 2026 8:45 | May 26, 2026 8:30 | 5/22/26 8:45 | 5/26/26 8:30 | 5/14/26 10:44 | 5/18/26 10:29 | 0d | -5.75d | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 15.75h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.45 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
894 | 1948 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 12.75h | Fixed Units | 6 | 0.25d | 886 | May 22, 2026 8:45 | May 25, 2026 2:30 | 5/22/26 8:45 | 5/25/26 2:30 | 5/14/26 10:44 | 5/15/26 4:29 | 0h | -46.02h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 12.75h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.45.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
895 | 1949 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 894 | May 25, 2026 2:30 | May 26, 2026 8:30 | 5/25/26 2:30 | 5/26/26 8:30 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -46.02h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.45.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
896 | 1950 | Yes | Auto Scheduled | PTM_CM52_Super_BOM | 2d | Fixed Duration | 5 | 1.13d |  | May 21, 2026 11:45 | May 25, 2026 11:45 | 5/21/26 11:45 | 5/25/26 11:45 | 5/11/26 8:29 | 5/13/26 8:29 | 0d | -8.41d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 16h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.46 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
897 | 1951 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 798 | May 21, 2026 11:45 | May 21, 2026 1:15 | 5/21/26 11:45 | 5/21/26 1:15 | 5/11/26 8:29 | 5/11/26 8:59 | 0m | -4036m | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.46.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
898 | 1952 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 897 | May 21, 2026 1:15 | May 21, 2026 1:45 | 5/21/26 1:15 | 5/21/26 1:45 | 5/11/26 8:59 | 5/11/26 9:29 | 0m | -4036m | 0ed | 0 | NA | NA | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.46.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
899 | 1953 | Yes | Auto Scheduled | Simulate Load | 8h | Fixed Units | 6 | 0.13d | 898 | May 21, 2026 1:45 | May 22, 2026 1:45 | 5/21/26 1:45 | 5/22/26 1:45 | 5/11/26 9:29 | 5/12/26 9:29 | 0h | -67.27h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 8h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.46.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
900 | 1954 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 899 | May 22, 2026 1:45 | May 22, 2026 3:45 | 5/22/26 1:45 | 5/22/26 3:45 | 5/12/26 9:29 | 5/12/26 11:29 | 0h | -67.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.46.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
901 | 1955 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 900 | May 22, 2026 3:45 | May 25, 2026 8:45 | 5/22/26 3:45 | 5/25/26 8:45 | 5/12/26 11:29 | 5/12/26 2:29 | 0h | -67.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.46.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
902 | 1956 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 901 | May 25, 2026 8:45 | May 25, 2026 11:45 | 5/25/26 8:45 | 5/25/26 11:45 | 5/12/26 2:29 | 5/13/26 8:29 | 0h | -67.27h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.46.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
903 | 1957 | Yes | Auto Scheduled | PTM_CM53_Super_Routing | 2.13d | Fixed Duration | 5 | 1.13d |  | May 25, 2026 11:45 | May 27, 2026 1:45 | 5/25/26 11:45 | 5/27/26 1:45 | 5/13/26 8:29 | 5/18/26 10:29 | 0d | -8.41d | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.47 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
904 | 1958 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 902 | May 25, 2026 11:45 | May 25, 2026 1:15 | 5/25/26 11:45 | 5/25/26 1:15 | 5/13/26 8:29 | 5/13/26 8:59 | 0m | -4036m | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 16, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.47.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
905 | 1959 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 904 | May 25, 2026 1:15 | May 25, 2026 1:45 | 5/25/26 1:15 | 5/25/26 1:45 | 5/13/26 8:59 | 5/13/26 9:29 | 0m | -4036m | 0ed | 0 | NA | NA | April 16, 2026 4:45 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.47.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
906 | 1960 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 905 | May 25, 2026 1:45 | May 26, 2026 2:45 | 5/25/26 1:45 | 5/26/26 2:45 | 5/13/26 9:29 | 5/14/26 10:29 | 0h | -67.27h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.47.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
907 | 1961 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 906 | May 26, 2026 2:45 | May 26, 2026 4:45 | 5/26/26 2:45 | 5/26/26 4:45 | 5/14/26 10:29 | 5/14/26 1:29 | 0h | -67.27h | 0ed | 0 | NA | NA | April 17, 2026 9:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.47.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
908 | 1962 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 907 | May 26, 2026 4:45 | May 27, 2026 9:45 | 5/26/26 4:45 | 5/27/26 9:45 | 5/14/26 1:29 | 5/14/26 3:29 | 0h | -67.27h | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.47.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
909 | 1963 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 908 | May 27, 2026 9:45 | May 27, 2026 1:45 | 5/27/26 9:45 | 5/27/26 1:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -58.27h | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.47.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
910 | 1964 | Yes | Auto Scheduled | VC_VK30 Pricing Variant | 0.69d | Fixed Duration | 5 | 0.69d |  | May 27, 2026 9:45 | May 27, 2026 4:15 | 5/27/26 9:45 | 5/27/26 4:15 | 5/14/26 3:29 | 5/15/26 11:59 | 0d | -8.41d | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 20, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.48 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
911 | 1965 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 908 | May 27, 2026 9:45 | May 27, 2026 10:15 | 5/27/26 9:45 | 5/27/26 10:15 | 5/14/26 3:29 | 5/14/26 3:59 | 0m | -4036m | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 17, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.48.1 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
912 | 1966 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 911 | May 27, 2026 10:15 | May 27, 2026 1:15 | 5/27/26 10:15 | 5/27/26 1:15 | 5/14/26 3:59 | 5/15/26 8:59 | 0h | -67.27h | 0ed | 0 | NA | NA | April 17, 2026 2:45 | April 17, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.48.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
913 | 1967 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 912 | May 27, 2026 1:15 | May 27, 2026 4:15 | 5/27/26 1:15 | 5/27/26 4:15 | 5/15/26 8:59 | 5/15/26 11:59 | 0h | -67.27h | 0ed | 0 | NA | NA | April 17, 2026 4:45 | April 20, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.48.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
914 | 1968 | Yes | Auto Scheduled | OTC_CM22_Pricing_Condition | 0.69d | Fixed Duration | 5 | 0.69d |  | May 27, 2026 4:15 | May 28, 2026 1:45 | 5/27/26 4:15 | 5/28/26 1:45 | 5/15/26 11:59 | 5/18/26 10:29 | 0d | -8.41d | 0ed | 0 | NA | NA | April 20, 2026 10:45 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 8.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.49 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
915 | 1969 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 913 | May 27, 2026 4:15 | May 27, 2026 4:45 | 5/27/26 4:15 | 5/27/26 4:45 | 5/15/26 11:59 | 5/15/26 1:29 | 0m | -4036m | 0ed | 0 | NA | NA | April 20, 2026 10:45 | April 20, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.49.1 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
916 | 1970 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 915 | May 27, 2026 4:45 | May 28, 2026 9:45 | 5/27/26 4:45 | 5/28/26 9:45 | 5/15/26 1:29 | 5/15/26 3:29 | 0h | -67.27h | 0ed | 0 | NA | NA | April 20, 2026 11:15 | April 20, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.49.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
917 | 1971 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 916 | May 28, 2026 9:45 | May 28, 2026 1:45 | 5/28/26 9:45 | 5/28/26 1:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -66.27h | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 6h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.49.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda,kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
918 | 1972 | Yes | Auto Scheduled | OTC_CM21_CMIR | 0.5d | Fixed Duration | 5 | 1.13d |  | May 28, 2026 9:45 | May 28, 2026 2:45 | 5/28/26 9:45 | 5/28/26 2:45 | 5/15/26 3:29 | 5/18/26 10:29 | 0d | -8.41d | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 21, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 4h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.50 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
919 | 1973 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 916,927 | May 28, 2026 9:45 | May 28, 2026 10:15 | 5/28/26 9:45 | 5/28/26 10:15 | 5/15/26 3:29 | 5/15/26 3:59 | 0m | -4036m | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 20, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.50.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
920 | 1974 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 919 | May 28, 2026 10:15 | May 28, 2026 10:45 | 5/28/26 10:15 | 5/28/26 10:45 | 5/15/26 3:59 | 5/15/26 4:29 | 0m | -4036m | 0ed | 0 | NA | NA | April 20, 2026 2:45 | April 20, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.50.2 | 500 | No | No | No |  | Kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
921 | 1975 | Yes | Auto Scheduled | Simulate Load | 0h | Fixed Units | 6 | 0.13d | 920 | May 28, 2026 10:45 | May 28, 2026 10:45 | 5/28/26 10:45 | 5/28/26 10:45 | 5/15/26 4:29 | 5/15/26 4:29 | 0h | -67.27h | 0ed | 0 | NA | NA | April 20, 2026 3:15 | April 20, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.50.3 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
922 | 1976 | Yes | Auto Scheduled | Error and Defect Mitigation | 0h | Fixed Units | 6 | 0.25d | 921 | May 28, 2026 10:45 | May 28, 2026 10:45 | 5/28/26 10:45 | 5/28/26 10:45 | 5/15/26 4:29 | 5/15/26 4:29 | 0h | -67.27h | 0ed | 0 | NA | NA | April 20, 2026 4:15 | April 21, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.50.4 | 500 | Yes | No | No |  | Kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
923 | 1977 | Yes | Auto Scheduled | Load | 0h | Fixed Units | 6 | 0.25d | 922 | May 28, 2026 10:45 | May 28, 2026 10:45 | 5/28/26 10:45 | 5/28/26 10:45 | 5/15/26 4:29 | 5/15/26 4:29 | 0h | -67.27h | 0ed | 0 | NA | NA | April 21, 2026 9:15 | April 21, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.50.5 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
924 | 1978 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 923 | May 28, 2026 10:45 | May 28, 2026 2:45 | 5/28/26 10:45 | 5/28/26 2:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -67.27h | 0ed | 0 | NA | NA | April 21, 2026 11:15 | April 21, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.50.6 | 500 | No | No | No |  | Kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
925 | 1979 | Yes | Auto Scheduled | PTP_CM29_Source_List | 6.16d | Fixed Duration | 5 | 0.94d |  | May 19, 2026 11:00 | May 27, 2026 1:15 | 5/19/26 11:00 | 5/27/26 1:15 | 5/15/26 1:29 | 5/18/26 10:29 | 0d | -7.22d | 0ed | 0 | NA | NA | April 13, 2026 10:45 | April 14, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.51 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
926 | 1980 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 769,776 | May 19, 2026 11:00 | May 19, 2026 11:30 | 5/19/26 11:00 | 5/19/26 11:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -541m | 0ed | 0 | NA | NA | April 14, 2026 9:45 | April 14, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.51.1 | 500 | No | No | No |  | Sam | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
927 | 1981 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 745 | May 26, 2026 4:15 | May 27, 2026 9:15 | 5/26/26 4:15 | 5/27/26 9:15 | 5/15/26 1:29 | 5/15/26 3:29 | 0h | -58.77h | 0ed | 0 | NA | NA | April 13, 2026 10:45 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.51.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
928 | 1982 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 927 | May 27, 2026 9:15 | May 27, 2026 1:15 | 5/27/26 9:15 | 5/27/26 1:15 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -57.77h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.51.3 | 500 | No | No | No |  | Sam | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
929 | 1983 | Yes | Auto Scheduled | RTR_CM11_Asset_Master | 3.75d | Fixed Duration | 5 | 1.13d |  | May 18, 2026 10:00 | May 21, 2026 5:00 | 5/18/26 10:00 | 5/21/26 5:00 | 5/12/26 1:29 | 5/18/26 10:29 | 0d | -3.69d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 30.5h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.52 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
930 | 1984 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d |  | May 18, 2026 10:00 | May 18, 2026 10:30 | 5/18/26 10:00 | 5/18/26 10:30 | 5/12/26 1:29 | 5/12/26 1:59 | 0m | -1771m | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.52.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
931 | 1985 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 930 | May 18, 2026 10:30 | May 18, 2026 11:00 | 5/18/26 10:30 | 5/18/26 11:00 | 5/12/26 1:59 | 5/12/26 2:29 | 0m | -1771m | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.52.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
932 | 1986 | Yes | Auto Scheduled | Simulate Load | 8h | Fixed Units | 6 | 0.13d | 931 | May 18, 2026 11:00 | May 19, 2026 11:00 | 5/18/26 11:00 | 5/19/26 11:00 | 5/12/26 2:29 | 5/13/26 2:29 | 0h | -29.52h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 8h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.52.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
933 | 1987 | Yes | Auto Scheduled | Error and Defect Mitigation | 16h | Fixed Units | 6 | 0.25d | 932 | May 19, 2026 11:00 | May 21, 2026 11:00 | 5/19/26 11:00 | 5/21/26 11:00 | 5/13/26 2:29 | 5/15/26 2:29 | 0h | -29.52h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 16h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.52.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
934 | 1988 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 933 | May 21, 2026 11:00 | May 21, 2026 2:00 | 5/21/26 11:00 | 5/21/26 2:00 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -29.52h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.52.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
935 | 1989 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 934 | May 21, 2026 2:00 | May 21, 2026 5:00 | 5/21/26 2:00 | 5/21/26 5:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -29.52h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.52.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
936 | 1990 | Yes | Auto Scheduled | PTM_CM50_Material Class | 2.13d | Fixed Duration | 5 | 0.25d |  | May 22, 2026 8:15 | May 26, 2026 9:15 | 5/22/26 8:15 | 5/26/26 9:15 | 5/14/26 9:29 | 5/18/26 10:29 | 0d | -5.85d | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 17h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.53 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
937 | 1991 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 842 | May 22, 2026 8:15 | May 22, 2026 8:45 | 5/22/26 8:15 | 5/22/26 8:45 | 5/14/26 9:29 | 5/14/26 9:59 | 0m | -2806m | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.53.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
938 | 1992 | Yes | Auto Scheduled | Load | 30m | Fixed Units | 6 | 0.06d | 937 | May 22, 2026 8:45 | May 22, 2026 9:15 | 5/22/26 8:45 | 5/22/26 9:15 | 5/14/26 9:59 | 5/14/26 10:29 | 0m | -2806m | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.53.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
939 | 1993 | Yes | Auto Scheduled | Post Load Validation | 16h | Fixed Units | 6 | 0.13d | 938 | May 22, 2026 9:15 | May 26, 2026 9:15 | 5/22/26 9:15 | 5/26/26 9:15 | 5/14/26 10:29 | 5/18/26 10:29 | 0h | -46.77h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 16h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.53.3 | 500 | No | No | No |  | brad | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
940 | 1994 | Yes | Auto Scheduled | PTM_CM55_Class assignment to materials | 1.13d | Fixed Duration | 5 | 1.13d |  | May 22, 2026 8:45 | May 25, 2026 9:45 | 5/22/26 8:45 | 5/25/26 9:45 | 5/15/26 9:29 | 5/18/26 10:29 | 0d | -4.91d | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.54 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
941 | 1995 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 937 | May 22, 2026 8:45 | May 22, 2026 9:15 | 5/22/26 8:45 | 5/22/26 9:15 | 5/15/26 9:29 | 5/15/26 9:59 | 0m | -2356m | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.54.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
942 | 1996 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 941 | May 22, 2026 9:15 | May 22, 2026 9:45 | 5/22/26 9:15 | 5/22/26 9:45 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -2356m | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.54.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
943 | 1997 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 942 | May 22, 2026 9:45 | May 22, 2026 10:45 | 5/22/26 9:45 | 5/22/26 10:45 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -39.27h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.54.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
944 | 1998 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 943 | May 22, 2026 10:45 | May 22, 2026 1:45 | 5/22/26 10:45 | 5/22/26 1:45 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -39.27h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.54.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
945 | 1999 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 944 | May 22, 2026 1:45 | May 22, 2026 3:45 | 5/22/26 1:45 | 5/22/26 3:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -39.27h | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 17, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.54.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
946 | 2000 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 945 | May 22, 2026 3:45 | May 25, 2026 9:45 | 5/22/26 3:45 | 5/25/26 9:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -39.27h | 0ed | 0 | NA | NA | April 17, 2026 9:15 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.54.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
947 | 2001 | Yes | Auto Scheduled | GTS - Material initial load from S4 (Run Interface) | 2.09d | Fixed Duration | 5 | 0.25d |  | May 21, 2026 2:45 | May 25, 2026 3:30 | 5/21/26 2:45 | 5/25/26 3:30 | 5/8/26 4:29 | 5/13/26 8:14 | 0d | -8.78d | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 16.75h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.55 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
948 | 2002 | Yes | Auto Scheduled | Run material interface to GTS | 15.75h | Fixed Units | 6 | 0.13d | 816 | May 21, 2026 2:45 | May 25, 2026 2:30 | 5/21/26 2:45 | 5/25/26 2:30 | 5/8/26 4:29 | 5/12/26 4:14 | 0h | -70.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 15.75h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.55.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
949 | 2003 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 948 | May 25, 2026 2:30 | May 25, 2026 3:30 | 5/25/26 2:30 | 5/25/26 3:30 | 5/12/26 4:14 | 5/13/26 8:14 | 0h | -70.27h | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.55.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
950 | 2004 | Yes | Auto Scheduled | GTS - Customers initial load from S4 (Run Interface) | 0.25d | Fixed Duration | 5 | 0.25d |  | May 18, 2026 10:00 | May 18, 2026 12:00 | 5/18/26 10:00 | 5/18/26 12:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0d | -0.19d | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.56 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
951 | 2005 | Yes | Auto Scheduled | Run material interface to GTS | 1h | Fixed Units | 6 | 0.13d |  | May 18, 2026 10:00 | May 18, 2026 11:00 | 5/18/26 10:00 | 5/18/26 11:00 | 5/18/26 8:29 | 5/18/26 9:29 | 0h | -1.52h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.56.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
952 | 2006 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 951 | May 18, 2026 11:00 | May 18, 2026 12:00 | 5/18/26 11:00 | 5/18/26 12:00 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -1.52h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.56.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
953 | 2007 | Yes | Auto Scheduled | GTS - Vendors initial load from S4 (Run Interface) | 0.25d | Fixed Duration | 5 | 0.25d |  | May 19, 2026 9:00 | May 19, 2026 11:00 | 5/19/26 9:00 | 5/19/26 11:00 | 5/15/26 2:29 | 5/18/26 10:29 | 0d | -1.44d | 0ed | 0 | NA | NA | April 15, 2026 2:00 | April 15, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.57 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
954 | 2008 | Yes | Auto Scheduled | Run material interface to GTS | 1h | Fixed Units | 6 | 0.13d | 759 | May 19, 2026 9:00 | May 19, 2026 10:00 | 5/19/26 9:00 | 5/19/26 10:00 | 5/15/26 2:29 | 5/15/26 3:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 15, 2026 2:00 | April 15, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.57.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
955 | 2009 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 954 | May 19, 2026 10:00 | May 19, 2026 11:00 | 5/19/26 10:00 | 5/19/26 11:00 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -8.52h | 0ed | 0 | NA | NA | April 15, 2026 3:00 | April 15, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.57.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
956 | 2010 | Yes | Auto Scheduled | GTS - ECCN - Create | 1.13d | Fixed Duration | 5 | 5.63d |  | May 18, 2026 10:00 | May 19, 2026 11:00 | 5/18/26 10:00 | 5/19/26 11:00 | 5/15/26 3:29 | 5/18/26 10:29 | 0d | -1.06d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 13, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.58 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
957 | 2011 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d |  | May 18, 2026 10:00 | May 18, 2026 11:00 | 5/18/26 10:00 | 5/18/26 11:00 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -0.52h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.58.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
958 | 2012 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 954 | May 19, 2026 10:00 | May 19, 2026 11:00 | 5/19/26 10:00 | 5/19/26 11:00 | 5/15/26 3:29 | 5/15/26 4:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 13, 2026 1:15 | April 13, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.58.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
959 | 2013 | Yes | Auto Scheduled | GTS - ECCN - Assign | 0.25d | Fixed Duration | 5 | 0.25d |  | May 25, 2026 3:30 | May 26, 2026 8:30 | 5/25/26 3:30 | 5/26/26 8:30 | 5/13/26 8:14 | 5/13/26 10:14 | 0d | -8.78d | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.59 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
960 | 2014 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 949 | May 25, 2026 3:30 | May 25, 2026 4:30 | 5/25/26 3:30 | 5/25/26 4:30 | 5/13/26 8:14 | 5/13/26 9:14 | 0h | -70.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.59.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
961 | 2015 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 960 | May 25, 2026 4:30 | May 26, 2026 8:30 | 5/25/26 4:30 | 5/26/26 8:30 | 5/13/26 9:14 | 5/13/26 10:14 | 0h | -70.27h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.59.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
962 | 2016 | Yes | Auto Scheduled | GTS - HTS - Create | 0.25d | Fixed Duration | 5 | 0.25d |  | May 18, 2026 10:00 | May 18, 2026 12:00 | 5/18/26 10:00 | 5/18/26 12:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0d | -0.19d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.60 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
963 | 2017 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d |  | May 18, 2026 10:00 | May 18, 2026 11:00 | 5/18/26 10:00 | 5/18/26 11:00 | 5/18/26 8:29 | 5/18/26 9:29 | 0h | -1.52h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.60.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
964 | 2018 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 963 | May 18, 2026 11:00 | May 18, 2026 12:00 | 5/18/26 11:00 | 5/18/26 12:00 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -1.52h | 0ed | 0 | NA | NA | April 6, 2026 9:15 | April 6, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.60.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
965 | 2019 | Yes | Auto Scheduled | GTS - HTS - Assign | 0.25d | Fixed Duration | 5 | 0.25d |  | May 26, 2026 8:30 | May 26, 2026 10:30 | 5/26/26 8:30 | 5/26/26 10:30 | 5/13/26 10:14 | 5/13/26 1:14 | 0d | -8.78d | 0ed | 0 | NA | NA | April 16, 2026 8:45 | April 16, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.61 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
966 | 2020 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 961 | May 26, 2026 8:30 | May 26, 2026 9:30 | 5/26/26 8:30 | 5/26/26 9:30 | 5/13/26 10:14 | 5/13/26 11:14 | 0h | -70.27h | 0ed | 0 | NA | NA | April 16, 2026 8:45 | April 16, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.61.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
967 | 2021 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 966 | May 26, 2026 9:30 | May 26, 2026 10:30 | 5/26/26 9:30 | 5/26/26 10:30 | 5/13/26 11:14 | 5/13/26 1:14 | 0h | -70.27h | 0ed | 0 | NA | NA | April 16, 2026 9:45 | April 16, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.61.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
968 | 2022 | Yes | Auto Scheduled | GTS - License - Create | 0.25d | Fixed Duration | 5 | 0.25d |  | May 26, 2026 11:30 | May 26, 2026 2:30 | 5/26/26 11:30 | 5/26/26 2:30 | 5/18/26 8:29 | 5/18/26 10:29 | 0d | -6.38d | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.62 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
969 | 2023 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 966,982 | May 26, 2026 11:30 | May 26, 2026 1:30 | 5/26/26 11:30 | 5/26/26 1:30 | 5/18/26 8:29 | 5/18/26 9:29 | 0h | -51.02h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.62.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
970 | 2024 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 969 | May 26, 2026 1:30 | May 26, 2026 2:30 | 5/26/26 1:30 | 5/26/26 2:30 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -51.02h | 0ed | 0 | NA | NA | April 16, 2026 1:45 | April 16, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.62.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
971 | 2025 | Yes | Auto Scheduled | Commodity Code/Tarif | 2.78d | Fixed Duration | 5 | 0.25d |  | May 26, 2026 10:30 | May 29, 2026 8:45 | 5/26/26 10:30 | 5/29/26 8:45 | 5/13/26 1:14 | 5/18/26 10:29 | 0d | -8.78d | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 22.25h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.63 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
972 | 2026 | Yes | Auto Scheduled | Load | 21.25h | Fixed Units | 6 | 0.13d | 967 | May 26, 2026 10:30 | May 28, 2026 4:45 | 5/26/26 10:30 | 5/28/26 4:45 | 5/13/26 1:14 | 5/18/26 9:29 | 0h | -70.27h | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 21.25h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.63.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
973 | 2027 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 972 | May 28, 2026 4:45 | May 29, 2026 8:45 | 5/28/26 4:45 | 5/29/26 8:45 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -70.27h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.63.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
974 | 2028 | Yes | Auto Scheduled | SPL Master File | 0.25d | Fixed Duration | 5 | 0.25d |  | May 26, 2026 9:30 | May 26, 2026 11:30 | 5/26/26 9:30 | 5/26/26 11:30 | 5/18/26 8:29 | 5/18/26 10:29 | 0d | -6.13d | 0ed | 0 | NA | NA | March 13, 2025 8:00 | March 13, 2025 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.64 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
975 | 2029 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 966 | May 26, 2026 9:30 | May 26, 2026 10:30 | 5/26/26 9:30 | 5/26/26 10:30 | 5/18/26 8:29 | 5/18/26 9:29 | 0h | -49.02h | 0ed | 0 | NA | NA | March 13, 2025 8:00 | March 13, 2025 9:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.64.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
976 | 2030 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 975 | May 26, 2026 10:30 | May 26, 2026 11:30 | 5/26/26 10:30 | 5/26/26 11:30 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -49.02h | 0ed | 0 | NA | NA | March 13, 2025 9:00 | March 13, 2025 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.64.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
977 | 2031 | Yes | Auto Scheduled | Initialize Embargo situation | 0.38d | Fixed Duration | 5 | 0.38d |  | May 19, 2026 11:00 | May 19, 2026 3:00 | 5/19/26 11:00 | 5/19/26 3:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0d | -1.44d | 0ed | 0 | NA | NA | April 13, 2026 2:15 | April 14, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.65 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
978 | 2032 | Yes | Auto Scheduled | Run report /SAPSLL/EMB_CNTRY_INIT | 1h | Fixed Units | 6 | 0.13d | 958 | May 19, 2026 11:00 | May 19, 2026 12:00 | 5/19/26 11:00 | 5/19/26 12:00 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 13, 2026 2:15 | April 13, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.65.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
979 | 2033 | Yes | Auto Scheduled | Set Embargo situations | 1h | Fixed Units | 6 | 0.13d | 978 | May 19, 2026 1:00 | May 19, 2026 2:00 | 5/19/26 1:00 | 5/19/26 2:00 | 5/18/26 8:29 | 5/18/26 9:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 13, 2026 3:15 | April 13, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.65.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
980 | 2034 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 979 | May 19, 2026 2:00 | May 19, 2026 3:00 | 5/19/26 2:00 | 5/19/26 3:00 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -11.52h | 0ed | 0 | NA | NA | April 13, 2026 4:15 | April 14, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.65.3 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
981 | 2035 | Yes | Auto Scheduled | GTS - SPL (Sanctioned party list) | 0.25d | Fixed Duration | 5 | 0.25d |  | May 26, 2026 10:30 | May 26, 2026 1:30 | 5/26/26 10:30 | 5/26/26 1:30 | 5/15/26 4:29 | 5/18/26 10:29 | 0d | -6.38d | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.66 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
982 | 2036 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 967 | May 26, 2026 10:30 | May 26, 2026 11:30 | 5/26/26 10:30 | 5/26/26 11:30 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -51.02h | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.66.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
983 | 2037 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 982 | May 26, 2026 11:30 | May 26, 2026 1:30 | 5/26/26 11:30 | 5/26/26 1:30 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -50.02h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.66.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
984 | 2038 | Yes | Auto Scheduled | RTR_CM17_Project Definition / Builder | 1.13d | Fixed Duration | 5 | 5.38d |  | May 18, 2026 10:30 | May 19, 2026 11:30 | 5/18/26 10:30 | 5/19/26 11:30 | 5/15/26 8:59 | 5/18/26 10:29 | 0d | -1.19d | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.67 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
985 | 2039 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 930 | May 18, 2026 10:30 | May 18, 2026 11:00 | 5/18/26 10:30 | 5/18/26 11:00 | 5/15/26 8:59 | 5/15/26 9:29 | 0m | -571m | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.67.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
986 | 2040 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 985 | May 18, 2026 11:00 | May 18, 2026 11:30 | 5/18/26 11:00 | 5/18/26 11:30 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -541m | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.67.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
987 | 2041 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 986 | May 18, 2026 11:30 | May 18, 2026 1:30 | 5/18/26 11:30 | 5/18/26 1:30 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -9.02h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 16, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.67.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
988 | 2042 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 987 | May 18, 2026 1:30 | May 18, 2026 3:30 | 5/18/26 1:30 | 5/18/26 3:30 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -9.02h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.67.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
989 | 2043 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 988 | May 18, 2026 3:30 | May 19, 2026 8:30 | 5/18/26 3:30 | 5/19/26 8:30 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -9.02h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.67.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
990 | 2044 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 989 | May 19, 2026 8:30 | May 19, 2026 11:30 | 5/19/26 8:30 | 5/19/26 11:30 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -9.02h | 0ed | 0 | NA | NA | April 17, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.67.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
991 | 2045 | Yes | Auto Scheduled | RTR_CM18_WBS Element | 1.13d | Fixed Duration | 5 | 5.44d |  | May 18, 2026 11:00 | May 19, 2026 12:00 | 5/18/26 11:00 | 5/19/26 12:00 | 5/15/26 9:29 | 5/18/26 10:29 | 0d | -1.19d | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 17, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.68 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
992 | 2046 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 985 | May 18, 2026 11:00 | May 18, 2026 11:30 | 5/18/26 11:00 | 5/18/26 11:30 | 5/15/26 9:29 | 5/15/26 9:59 | 0m | -571m | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.68.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
993 | 2047 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 992 | May 18, 2026 11:30 | May 18, 2026 12:00 | 5/18/26 11:30 | 5/18/26 12:00 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -571m | 0ed | 0 | NA | NA | April 10, 2026 11:15 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.68.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
994 | 2048 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 993 | May 18, 2026 1:00 | May 18, 2026 2:00 | 5/18/26 1:00 | 5/18/26 2:00 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -9.52h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.68.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
995 | 2049 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 994 | May 18, 2026 2:00 | May 18, 2026 4:00 | 5/18/26 2:00 | 5/18/26 4:00 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -9.52h | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 17, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.68.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
996 | 2050 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 995 | May 18, 2026 4:00 | May 19, 2026 9:00 | 5/18/26 4:00 | 5/19/26 9:00 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -9.52h | 0ed | 0 | NA | NA | April 17, 2026 9:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.68.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
997 | 2051 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 996 | May 19, 2026 9:00 | May 19, 2026 12:00 | 5/19/26 9:00 | 5/19/26 12:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -9.52h | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.2.68.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
998 | 2947 | Yes | Auto Scheduled | ITC2 Master Data Loads Complete | 0m | Fixed Units | 4 | 0d | 631 | May 29, 2026 4:00 | May 29, 2026 4:00 | 5/29/26 4:00 | 5/29/26 4:00 | 5/18/26 10:29 | 5/18/26 10:29 | 0m | -4591m | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/28/26 2:10 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.3 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
999 | 2801 | Yes | Auto Scheduled | Mock Transactional Data | 2d | Fixed Duration | 4 | 0d | 998,1759,2140 | October 8, 2026 2:00 | October 12, 2026 2:00 | 10/8/26 2:00 | 10/12/26 2:00 | 6/3/26 4:00 | 6/5/26 4:00 | 0d | -90.75d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/23/26 11:43 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.4 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1000 | 2945 | Yes | Auto Scheduled | Inventory | 4h | Fixed Units | 5 | 0d | 998SS,1759SS,2140SS | October 8, 2026 2:00 | October 9, 2026 9:00 | 10/8/26 2:00 | 10/9/26 9:00 | 6/3/26 4:00 | 6/4/26 11:00 | 0h | -726h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/28/26 1:04 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.4.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1001 | 2829 | Yes | Auto Scheduled | Open AR | 4h | Fixed Units | 5 | 0d | 1000 | October 9, 2026 9:00 | October 9, 2026 2:00 | 10/9/26 9:00 | 10/9/26 2:00 | 6/4/26 11:00 | 6/4/26 4:00 | 0h | -726h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/24/26 12:27 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.4.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1002 | 2824 | Yes | Auto Scheduled | Open AP | 4h | Fixed Units | 5 | 0d | 1001 | October 9, 2026 2:00 | October 12, 2026 9:00 | 10/9/26 2:00 | 10/12/26 9:00 | 6/4/26 4:00 | 6/5/26 11:00 | 0h | -726h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/24/26 12:25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.4.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1003 | 2821 | Yes | Auto Scheduled | Bank and Cash | 4h | Fixed Units | 5 | 0d | 1002 | October 12, 2026 9:00 | October 12, 2026 2:00 | 10/12/26 9:00 | 10/12/26 2:00 | 6/5/26 11:00 | 6/5/26 4:00 | 0h | -726h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/24/26 12:25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.4.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1004 | 2944 | Yes | Auto Scheduled | Open Purchase Orders(Manual) | 1d | Fixed Units | 5 | 0d | 1000 | October 9, 2026 9:00 | October 12, 2026 9:00 | 10/9/26 9:00 | 10/12/26 9:00 | 6/4/26 4:00 | 6/5/26 4:00 | 0d | -90.25d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/28/26 1:02 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.4.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1005 | 2838 | Yes | Auto Scheduled | Open Sales Orders(Manual) | 1d | Fixed Units | 5 | 0d | 1000 | October 9, 2026 9:00 | October 12, 2026 9:00 | 10/9/26 9:00 | 10/12/26 9:00 | 6/4/26 4:00 | 6/5/26 4:00 | 0d | -90.25d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/24/26 12:41 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.4.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1006 | 2860 | Yes | Auto Scheduled | Service Orders(Manual) | 0.5d | Fixed Units | 5 | 0d | 1000 | October 9, 2026 9:00 | October 9, 2026 2:00 | 10/9/26 9:00 | 10/9/26 2:00 | 6/5/26 11:00 | 6/5/26 4:00 | 0d | -89.75d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/24/26 12:50 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.4.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1007 | 2858 | Yes | Auto Scheduled | Open Production Orders(Manual) | 1d | Fixed Units | 5 | 0d | 1000 | October 9, 2026 9:00 | October 12, 2026 9:00 | 10/9/26 9:00 | 10/12/26 9:00 | 6/4/26 4:00 | 6/5/26 4:00 | 0d | -90.25d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/24/26 12:48 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.4.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1008 | 2052 | Yes | Auto Scheduled | ITC2 Mock Data Loads Complete | 0m | Fixed Units | 4 | 0.03d | 999 | October 12, 2026 2:00 | October 12, 2026 2:00 | 10/12/26 2:00 | 10/12/26 2:00 | 6/5/26 4:00 | 6/5/26 4:00 | 0m | -43560m | 0ed | 0 | NA | NA | April 21, 2026 3:15 | April 21, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:49 | 0h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.2.5 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1009 | 2053 | Yes | Auto Scheduled | ITC3 Data Load Tasks QS5 | 11.88d | Fixed Duration | 3 | 288.78d |  | June 8, 2026 8:00 | June 23, 2026 4:00 | 6/8/26 8:00 | 6/23/26 4:00 | 5/4/26 2:29 | 6/8/26 10:00 | 0d | -24.31d | 0ed | 0 | NA | NA | March 13, 2025 8:00 | April 21, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:50 | 657.5h | 592h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1010 | 2054 | Yes | Auto Scheduled | PMO Authorization to Start Data Loads | 2h | Fixed Units | 4 | 0.03d | 72 | June 8, 2026 8:00 | June 8, 2026 10:00 | 6/8/26 8:00 | 6/8/26 10:00 | 6/8/26 8:00 | 6/8/26 10:00 | 0h | 0h | 0ed | 0 | NA | NA | April 6, 2026 8:00 | April 6, 2026 8:15 | Must Start On | 6/8/26 8:00 | NA | NA | 4/23/26 10:50 | 2h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1011 | 2959 | Yes | Auto Scheduled | Master Data Loads | 9.63d | Fixed Duration | 4 | 0d | 1010 | June 8, 2026 10:00 | June 19, 2026 4:00 | 6/8/26 10:00 | 6/19/26 4:00 | 5/4/26 2:29 | 5/18/26 10:29 | 0d | -24.56d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 655.5h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1012 | 2960 | Yes | Auto Scheduled | RTR_CM02_Profit Center Hierarchy | 0.75d | Fixed Duration | 5 | 0.75d |  | June 8, 2026 10:00 | June 8, 2026 5:00 | 6/8/26 10:00 | 6/8/26 5:00 | 5/4/26 2:29 | 5/5/26 11:29 | 0d | -24.56d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.1 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1013 | 2961 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d |  | June 8, 2026 10:00 | June 8, 2026 11:00 | 6/8/26 10:00 | 6/8/26 11:00 | 5/4/26 2:29 | 5/4/26 3:29 | 0h | -196.52h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.1.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1014 | 2962 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1013 | June 8, 2026 11:00 | June 8, 2026 2:00 | 6/8/26 11:00 | 6/8/26 2:00 | 5/4/26 3:29 | 5/5/26 8:29 | 0h | -196.52h | 0ed | 0 | NA | NA | April 6, 2026 9:15 | April 6, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.1.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1015 | 2963 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1014 | June 8, 2026 2:00 | June 8, 2026 5:00 | 6/8/26 2:00 | 6/8/26 5:00 | 5/5/26 8:29 | 5/5/26 11:29 | 0h | -196.52h | 0ed | 0 | NA | NA | April 6, 2026 11:15 | April 6, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.1.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1016 | 2964 | Yes | Auto Scheduled | RTR_CM03_Cost Center Hierarchy | 0.75d | Fixed Duration | 5 | 0.75d |  | June 9, 2026 8:00 | June 9, 2026 3:00 | 6/9/26 8:00 | 6/9/26 3:00 | 5/5/26 11:29 | 5/6/26 9:29 | 0d | -24.56d | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1017 | 2965 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1015 | June 9, 2026 8:00 | June 9, 2026 9:00 | 6/9/26 8:00 | 6/9/26 9:00 | 5/5/26 11:29 | 5/5/26 1:29 | 0h | -196.52h | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 6, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1018 | 2966 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1017 | June 9, 2026 9:00 | June 9, 2026 11:00 | 6/9/26 9:00 | 6/9/26 11:00 | 5/5/26 1:29 | 5/5/26 3:29 | 0h | -196.52h | 0ed | 0 | NA | NA | April 6, 2026 4:15 | April 7, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1019 | 2967 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1018 | June 9, 2026 11:00 | June 9, 2026 3:00 | 6/9/26 11:00 | 6/9/26 3:00 | 5/5/26 3:29 | 5/6/26 9:29 | 0h | -196.52h | 0ed | 0 | NA | NA | April 7, 2026 9:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.2.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1020 | 2968 | Yes | Auto Scheduled | RTR_CM01_GL_Account_Master to CC 1000 | 2.44d | Fixed Duration | 5 | 1.81d |  | June 9, 2026 3:00 | June 12, 2026 9:30 | 6/9/26 3:00 | 6/12/26 9:30 | 5/6/26 9:29 | 5/8/26 1:59 | 0d | -24.56d | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 9, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 16h | 16h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1021 | 2969 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1019 | June 9, 2026 3:00 | June 9, 2026 4:00 | 6/9/26 3:00 | 6/9/26 4:00 | 5/6/26 9:29 | 5/6/26 10:29 | 0h | -196.52h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1022 | 2970 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1021 | June 9, 2026 4:00 | June 10, 2026 9:00 | 6/9/26 4:00 | 6/10/26 9:00 | 5/6/26 10:29 | 5/6/26 1:29 | 0h | -196.52h | 0ed | 0 | NA | NA | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1023 | 2971 | Yes | Auto Scheduled | Simulate Load | 6h | Fixed Units | 6 | 0.75d | 1022 | June 10, 2026 9:00 | June 10, 2026 4:00 | 6/10/26 9:00 | 6/10/26 4:00 | 5/6/26 1:29 | 5/7/26 10:29 | 0h | -196.52h | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1024 | 2972 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1023 | June 10, 2026 4:00 | June 11, 2026 10:30 | 6/10/26 4:00 | 6/11/26 10:30 | 5/7/26 10:29 | 5/7/26 2:59 | 0h | -196.52h | 0ed | 0 | NA | NA | April 8, 2026 8:15 | April 8, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1025 | 2973 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1024 | June 11, 2026 10:30 | June 11, 2026 11:30 | 6/11/26 10:30 | 6/11/26 11:30 | 5/7/26 2:59 | 5/7/26 3:59 | 0h | -196.52h | 0ed | 0 | NA | NA | April 8, 2026 11:45 | April 8, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1026 | 2974 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1025 | June 11, 2026 11:30 | June 11, 2026 2:30 | 6/11/26 11:30 | 6/11/26 2:30 | 5/7/26 3:59 | 5/8/26 8:59 | 0h | -196.52h | 0ed | 0 | NA | NA | April 8, 2026 1:45 | April 8, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1027 | 2975 | Yes | Auto Scheduled | Extend GL to all Company Codes | 2h | Fixed Units | 6 | 0.25d | 1026 | June 11, 2026 2:30 | June 11, 2026 4:30 | 6/11/26 2:30 | 6/11/26 4:30 | 5/8/26 8:59 | 5/8/26 10:59 | 0h | -196.52h | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1028 | 2976 | Yes | Auto Scheduled | Post GL Extention Validation | 2h | Fixed Units | 6 | 0.25d | 1027 | June 11, 2026 4:30 | June 12, 2026 9:30 | 6/11/26 4:30 | 6/12/26 9:30 | 5/8/26 10:59 | 5/8/26 1:59 | 0h | -196.52h | 0ed | 0 | NA | NA | April 9, 2026 8:45 | April 9, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.3.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1029 | 2977 | Yes | Auto Scheduled | RTR_CM05_Profit_Center | 1.13d | Fixed Duration | 5 | 1.13d |  | June 9, 2026 8:00 | June 10, 2026 9:00 | 6/9/26 8:00 | 6/10/26 9:00 | 5/7/26 8:29 | 5/8/26 9:29 | 0d | -22.94d | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.4 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1030 | 2978 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1015 | June 9, 2026 8:00 | June 9, 2026 9:00 | 6/9/26 8:00 | 6/9/26 9:00 | 5/7/26 8:29 | 5/7/26 9:29 | 0h | -183.52h | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 6, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.4.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1031 | 2979 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1030 | June 9, 2026 9:00 | June 9, 2026 11:00 | 6/9/26 9:00 | 6/9/26 11:00 | 5/7/26 9:29 | 5/7/26 11:29 | 0h | -183.52h | 0ed | 0 | NA | NA | April 6, 2026 4:15 | April 7, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.4.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1032 | 2980 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1031 | June 9, 2026 11:00 | June 9, 2026 12:00 | 6/9/26 11:00 | 6/9/26 12:00 | 5/7/26 11:29 | 5/7/26 1:29 | 0h | -183.52h | 0ed | 0 | NA | NA | April 7, 2026 9:15 | April 7, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.4.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1033 | 2981 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1032 | June 9, 2026 1:00 | June 9, 2026 3:00 | 6/9/26 1:00 | 6/9/26 3:00 | 5/7/26 1:29 | 5/7/26 3:29 | 0h | -183.52h | 0ed | 0 | NA | NA | April 7, 2026 10:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.4.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1034 | 2982 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1033 | June 9, 2026 3:00 | June 9, 2026 4:00 | 6/9/26 3:00 | 6/9/26 4:00 | 5/7/26 3:29 | 5/7/26 4:29 | 0h | -183.52h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.4.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1035 | 2983 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1034 | June 9, 2026 4:00 | June 10, 2026 9:00 | 6/9/26 4:00 | 6/10/26 9:00 | 5/7/26 4:29 | 5/8/26 9:29 | 0h | -183.52h | 0ed | 0 | NA | NA | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.4.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1036 | 2984 | Yes | Auto Scheduled | RTR_CM04_Cost_Center | 1.13d | Fixed Duration | 5 | 1.13d |  | June 10, 2026 9:00 | June 11, 2026 10:00 | 6/10/26 9:00 | 6/11/26 10:00 | 5/8/26 9:29 | 5/11/26 10:29 | 0d | -22.94d | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 9, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.5 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1037 | 2985 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1035 | June 10, 2026 9:00 | June 10, 2026 10:00 | 6/10/26 9:00 | 6/10/26 10:00 | 5/8/26 9:29 | 5/8/26 10:29 | 0h | -183.52h | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 8, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.5.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1038 | 2986 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1037 | June 10, 2026 10:00 | June 10, 2026 12:00 | 6/10/26 10:00 | 6/10/26 12:00 | 5/8/26 10:29 | 5/8/26 1:29 | 0h | -183.52h | 0ed | 0 | NA | NA | April 8, 2026 8:15 | April 8, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.5.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1039 | 2987 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1038 | June 10, 2026 1:00 | June 10, 2026 2:00 | 6/10/26 1:00 | 6/10/26 2:00 | 5/8/26 1:29 | 5/8/26 2:29 | 0h | -183.52h | 0ed | 0 | NA | NA | April 8, 2026 10:15 | April 8, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.5.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1040 | 2988 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1039 | June 10, 2026 2:00 | June 10, 2026 4:00 | 6/10/26 2:00 | 6/10/26 4:00 | 5/8/26 2:29 | 5/8/26 4:29 | 0h | -183.52h | 0ed | 0 | NA | NA | April 8, 2026 11:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.5.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1041 | 2989 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1040 | June 10, 2026 4:00 | June 10, 2026 5:00 | 6/10/26 4:00 | 6/10/26 5:00 | 5/8/26 4:29 | 5/11/26 8:29 | 0h | -183.52h | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 8, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.5.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1042 | 2990 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1041 | June 11, 2026 8:00 | June 11, 2026 10:00 | 6/11/26 8:00 | 6/11/26 10:00 | 5/11/26 8:29 | 5/11/26 10:29 | 0h | -183.52h | 0ed | 0 | NA | NA | April 8, 2026 3:15 | April 9, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.5.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1043 | 2991 | Yes | Auto Scheduled | Manual Configuration Activities in QS5 | 5.94d | Fixed Duration | 5 | 7.16d | 1036 | June 11, 2026 10:00 | June 19, 2026 9:30 | 6/11/26 10:00 | 6/19/26 9:30 | 5/11/26 10:29 | 5/18/26 10:29 | 0d | -23.88d | 0ed | 0 | NA | NA | April 6, 2026 1:00 | April 15, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 43h | 43h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.6 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1044 | 2992 | Yes | Auto Scheduled | Open Client | 30m | Fixed Units | 6 | 0.06d |  | June 11, 2026 10:00 | June 11, 2026 10:30 | 6/11/26 10:00 | 6/11/26 10:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -8641m | 0ed | 0 | NA | NA | April 6, 2026 1:00 | April 6, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.6.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1045 | 2993 | Yes | Auto Scheduled | Service Enterprise Setup | 5d | Fixed Units | 6 | 5d | 1012,1016,1020 | June 12, 2026 9:30 | June 19, 2026 9:30 | 6/12/26 9:30 | 6/19/26 9:30 | 5/11/26 10:29 | 5/18/26 10:29 | 0d | -23.88d | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 15, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 40h | 40h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.6.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1046 | 2994 | Yes | Auto Scheduled | Close Client | 30m | Fixed Units | 6 | 0.06d |  | June 11, 2026 10:00 | June 11, 2026 10:30 | 6/11/26 10:00 | 6/11/26 10:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -8641m | 0ed | 0 | NA | NA | April 6, 2026 1:00 | April 6, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.6.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1047 | 2995 | Yes | Auto Scheduled | Intercompany Business Partner Setup | 2h | Fixed Units | 6 | 0.25d | 1012,1016,1028 | June 12, 2026 9:30 | June 12, 2026 11:30 | 6/12/26 9:30 | 6/12/26 11:30 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -153.02h | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.6.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1048 | 2996 | Yes | Auto Scheduled | RTR_CM09_Activity_Type | 1.38d | Fixed Duration | 5 | 1.22d |  | June 11, 2026 2:30 | June 15, 2026 8:30 | 6/11/26 2:30 | 6/15/26 8:30 | 5/14/26 4:29 | 5/18/26 10:29 | 0d | -19.75d | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1049 | 2997 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1026 | June 11, 2026 2:30 | June 11, 2026 4:45 | 6/11/26 2:30 | 6/11/26 4:45 | 5/14/26 4:29 | 5/15/26 9:44 | 0h | -158.02h | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 8, 2026 4:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1050 | 2998 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1049 | June 11, 2026 4:45 | June 12, 2026 10:30 | 6/11/26 4:45 | 6/12/26 10:30 | 5/15/26 9:44 | 5/15/26 1:29 | 0h | -158.02h | 0ed | 0 | NA | NA | April 8, 2026 3:15 | April 9, 2026 9:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1051 | 2999 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1050 | June 12, 2026 10:30 | June 12, 2026 11:30 | 6/12/26 10:30 | 6/12/26 11:30 | 5/15/26 1:29 | 5/15/26 2:29 | 0h | -158.02h | 0ed | 0 | NA | NA | April 9, 2026 9:00 | April 9, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1052 | 3000 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1051 | June 12, 2026 11:30 | June 12, 2026 2:30 | 6/12/26 11:30 | 6/12/26 2:30 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -158.02h | 0ed | 0 | NA | NA | April 9, 2026 10:00 | April 9, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1053 | 3001 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1052 | June 12, 2026 2:30 | June 12, 2026 3:30 | 6/12/26 2:30 | 6/12/26 3:30 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -158.02h | 0ed | 0 | NA | NA | April 9, 2026 1:00 | April 9, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1054 | 3002 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1053 | June 12, 2026 3:30 | June 15, 2026 8:30 | 6/12/26 3:30 | 6/15/26 8:30 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -158.02h | 0ed | 0 | NA | NA | April 9, 2026 2:00 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.7.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1055 | 3003 | Yes | Auto Scheduled | RTR_CM12_Activity Rates | 1.13d | Fixed Duration | 5 | 1.13d |  | June 9, 2026 3:00 | June 10, 2026 4:00 | 6/9/26 3:00 | 6/10/26 4:00 | 5/15/26 9:29 | 5/18/26 10:29 | 0d | -17.56d | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1056 | 3004 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1019 | June 9, 2026 3:00 | June 9, 2026 4:00 | 6/9/26 3:00 | 6/9/26 4:00 | 5/15/26 9:29 | 5/15/26 10:29 | 0h | -140.52h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1057 | 3005 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1056 | June 9, 2026 4:00 | June 10, 2026 9:00 | 6/9/26 4:00 | 6/10/26 9:00 | 5/15/26 10:29 | 5/15/26 1:29 | 0h | -140.52h | 0ed | 0 | NA | NA | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1058 | 3006 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1057 | June 10, 2026 9:00 | June 10, 2026 10:00 | 6/10/26 9:00 | 6/10/26 10:00 | 5/15/26 1:29 | 5/15/26 2:29 | 0h | -140.52h | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 8, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1059 | 3007 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1058 | June 10, 2026 10:00 | June 10, 2026 12:00 | 6/10/26 10:00 | 6/10/26 12:00 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -140.52h | 0ed | 0 | NA | NA | April 8, 2026 8:15 | April 8, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1060 | 3008 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1059 | June 10, 2026 1:00 | June 10, 2026 2:00 | 6/10/26 1:00 | 6/10/26 2:00 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -140.52h | 0ed | 0 | NA | NA | April 8, 2026 10:15 | April 8, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1061 | 3009 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1060 | June 10, 2026 2:00 | June 10, 2026 4:00 | 6/10/26 2:00 | 6/10/26 4:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -140.52h | 0ed | 0 | NA | NA | April 8, 2026 11:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.8.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1062 | 3010 | Yes | Auto Scheduled | RTR_CM06_Bank_master | 3.81d | Fixed Duration | 5 | 1.22d |  | June 8, 2026 10:00 | June 12, 2026 8:30 | 6/8/26 10:00 | 6/12/26 8:30 | 5/8/26 9:29 | 5/18/26 10:29 | 0d | -21.06d | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 13h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.9 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1063 | 3011 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1026 | June 11, 2026 2:30 | June 11, 2026 3:30 | 6/11/26 2:30 | 6/11/26 3:30 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -150.02h | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 8, 2026 4:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.9.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1064 | 3012 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1063 | June 11, 2026 3:30 | June 12, 2026 8:30 | 6/11/26 3:30 | 6/12/26 8:30 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -150.02h | 0ed | 0 | NA | NA | April 8, 2026 4:30 | April 9, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.9.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1065 | 3013 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d |  | June 8, 2026 10:00 | June 8, 2026 11:00 | 6/8/26 10:00 | 6/8/26 11:00 | 5/8/26 9:29 | 5/8/26 10:29 | 0h | -168.52h | 0ed | 0 | NA | NA | April 9, 2026 9:30 | April 9, 2026 10:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.9.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1066 | 3014 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1065 | June 8, 2026 11:00 | June 8, 2026 2:00 | 6/8/26 11:00 | 6/8/26 2:00 | 5/8/26 10:29 | 5/8/26 1:29 | 0h | -168.52h | 0ed | 0 | NA | NA | April 9, 2026 10:30 | April 9, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.9.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1067 | 3015 | Yes | Auto Scheduled | Load | 5h | Fixed Units | 6 | 0.13d | 1066 | June 8, 2026 2:00 | June 9, 2026 10:00 | 6/8/26 2:00 | 6/9/26 10:00 | 5/8/26 1:29 | 5/11/26 9:29 | 0h | -168.52h | 0ed | 0 | NA | NA | April 9, 2026 1:30 | April 9, 2026 2:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.9.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1068 | 3016 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1067 | June 9, 2026 10:00 | June 9, 2026 4:30 | 6/9/26 10:00 | 6/9/26 4:30 | 5/11/26 9:29 | 5/11/26 3:59 | 0h | -168.52h | 0ed | 0 | NA | NA | April 9, 2026 8:00 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.9.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1069 | 3017 | Yes | Auto Scheduled | RTR_CM08_Exchange_Rates | 1.13d | Fixed Duration | 5 | 1.13d |  | June 9, 2026 10:00 | June 10, 2026 11:00 | 6/9/26 10:00 | 6/10/26 11:00 | 5/15/26 9:29 | 5/18/26 10:29 | 0d | -17.06d | 0ed | 0 | NA | NA | April 9, 2026 2:30 | April 10, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.10 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1070 | 3018 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1067 | June 9, 2026 10:00 | June 9, 2026 11:00 | 6/9/26 10:00 | 6/9/26 11:00 | 5/15/26 9:29 | 5/15/26 10:29 | 0h | -136.52h | 0ed | 0 | NA | NA | April 9, 2026 2:30 | April 9, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.10.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1071 | 3019 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1070 | June 9, 2026 11:00 | June 9, 2026 2:00 | 6/9/26 11:00 | 6/9/26 2:00 | 5/15/26 10:29 | 5/15/26 1:29 | 0h | -136.52h | 0ed | 0 | NA | NA | April 9, 2026 3:30 | April 10, 2026 8:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.10.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1072 | 3020 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1071 | June 9, 2026 2:00 | June 9, 2026 3:00 | 6/9/26 2:00 | 6/9/26 3:00 | 5/15/26 1:29 | 5/15/26 2:29 | 0h | -136.52h | 0ed | 0 | NA | NA | April 10, 2026 8:30 | April 10, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.10.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1073 | 3021 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1072 | June 9, 2026 3:00 | June 9, 2026 5:00 | 6/9/26 3:00 | 6/9/26 5:00 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -136.52h | 0ed | 0 | NA | NA | April 10, 2026 9:30 | April 10, 2026 11:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.10.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1074 | 3022 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1073 | June 10, 2026 8:00 | June 10, 2026 9:00 | 6/10/26 8:00 | 6/10/26 9:00 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -136.52h | 0ed | 0 | NA | NA | April 10, 2026 11:30 | April 10, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.10.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1075 | 3023 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1074 | June 10, 2026 9:00 | June 10, 2026 11:00 | 6/10/26 9:00 | 6/10/26 11:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -136.52h | 0ed | 0 | NA | NA | April 10, 2026 1:30 | April 10, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.10.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1076 | 3024 | Yes | Auto Scheduled | RTR_CM14_Cost Element_Group | 1.44d | Fixed Duration | 5 | 4.78d |  | June 11, 2026 2:30 | June 15, 2026 9:00 | 6/11/26 2:30 | 6/15/26 9:00 | 5/14/26 3:59 | 5/18/26 10:29 | 0d | -19.81d | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 22.5h | 38.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.11 | 500 | No | Yes | Yes |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1077 | 3025 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 4.16d | 1026 | June 11, 2026 2:30 | June 11, 2026 3:00 | 6/11/26 2:30 | 6/11/26 3:00 | 5/14/26 3:59 | 5/14/26 4:29 | 0m | -9511m | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 14, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 33.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.11.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1078 | 3026 | Yes | Auto Scheduled | Load | 8h | Fixed Units | 6 | 0.25d | 1077 | June 11, 2026 3:00 | June 12, 2026 3:00 | 6/11/26 3:00 | 6/12/26 3:00 | 5/14/26 4:29 | 5/15/26 4:29 | 0h | -158.52h | 0ed | 0 | NA | NA | April 15, 2026 8:00 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 8h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.11.2 | 500 | No | No | No |  |  | Black | 2026-04-20 15:36 - jsw73 - Start ignored — already in progress | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1079 | 3027 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1078 | June 12, 2026 3:00 | June 15, 2026 9:00 | 6/12/26 3:00 | 6/15/26 9:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -158.52h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.11.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1080 | 3028 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Bill-To | 2h | Fixed Units | 5 | 0d |  | June 8, 2026 10:00 | June 8, 2026 12:00 | 6/8/26 10:00 | 6/8/26 12:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -121.52h | 0ed | 0 | NA | NA | April 16, 2025 8:00 | April 16, 2025 8:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.12 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1081 | 3029 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Ship-To | 1.5d | Fixed Duration | 5 | 3.13d |  | June 11, 2026 2:30 | June 15, 2026 9:30 | 6/11/26 2:30 | 6/15/26 9:30 | 5/8/26 10:59 | 5/18/26 10:29 | 0d | -24.31d | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 13.25h | 36h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.13 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1082 | 3030 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1026 | June 11, 2026 2:30 | June 11, 2026 3:00 | 6/11/26 2:30 | 6/11/26 3:00 | 5/8/26 10:59 | 5/8/26 11:29 | 0m | -11671m | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 8, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.13.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1083 | 3031 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1082 | June 11, 2026 3:00 | June 11, 2026 3:30 | 6/11/26 3:00 | 6/11/26 3:30 | 5/8/26 11:29 | 5/8/26 11:59 | 0m | -11671m | 0ed | 0 | NA | NA | April 8, 2026 4:15 | April 8, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.13.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1084 | 3032 | Yes | Auto Scheduled | Open client for BP number range update | 30m | Fixed Units | 6 | 1d | 1083 | June 11, 2026 3:30 | June 11, 2026 4:00 | 6/11/26 3:30 | 6/11/26 4:00 | 5/18/26 9:14 | 5/18/26 9:44 | 0m | -8956m | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 9, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.13.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1085 | 3033 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 30m | Fixed Units | 6 | 1d | 1084 | June 11, 2026 4:00 | June 11, 2026 4:30 | 6/11/26 4:00 | 6/11/26 4:30 | 5/18/26 9:44 | 5/18/26 10:14 | 0m | -8956m | 0ed | 0 | NA | NA | April 9, 2026 4:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.13.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1086 | 3034 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 6 | 1d | 1085 | June 11, 2026 4:30 | June 11, 2026 4:45 | 6/11/26 4:30 | 6/11/26 4:45 | 5/18/26 10:14 | 5/18/26 10:29 | 0m | -8956m | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.25h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.13.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1087 | 3035 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1083 | June 11, 2026 3:30 | June 11, 2026 4:30 | 6/11/26 3:30 | 6/11/26 4:30 | 5/8/26 11:59 | 5/8/26 1:59 | 0h | -194.52h | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.13.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1088 | 3036 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | Fixed Units | 6 | 0.5d | 1087 | June 11, 2026 4:30 | June 12, 2026 11:30 | 6/11/26 4:30 | 6/12/26 11:30 | 5/15/26 8:29 | 5/15/26 1:29 | 0h | -159.02h | 0ed | 0 | NA | NA | April 9, 2026 8:45 | April 9, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.13.7 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1089 | 3037 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 6 | 0.38d | 1088 | June 12, 2026 11:30 | June 12, 2026 3:30 | 6/12/26 11:30 | 6/12/26 3:30 | 5/15/26 1:29 | 5/15/26 4:29 | 0h | -159.02h | 0ed | 0 | NA | NA | April 9, 2026 1:45 | April 9, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.13.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1090 | 3038 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1089 | June 12, 2026 3:30 | June 15, 2026 9:30 | 6/12/26 3:30 | 6/15/26 9:30 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -159.02h | 0ed | 0 | NA | NA | April 9, 2026 4:45 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.13.9 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1091 | 3039 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Sold-To | 1.63d | Fixed Duration | 5 | 1.63d |  | June 11, 2026 3:30 | June 15, 2026 11:30 | 6/11/26 3:30 | 6/15/26 11:30 | 5/8/26 1:59 | 5/18/26 10:29 | 0d | -24.19d | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 11.75h | 11.75h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.14 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1092 | 3040 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1083 | June 11, 2026 3:30 | June 11, 2026 4:00 | 6/11/26 3:30 | 6/11/26 4:00 | 5/18/26 9:29 | 5/18/26 9:59 | 0m | -8941m | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 9, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.14.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1093 | 3041 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1092 | June 11, 2026 4:00 | June 11, 2026 4:30 | 6/11/26 4:00 | 6/11/26 4:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -8941m | 0ed | 0 | NA | NA | April 9, 2026 8:15 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.14.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1094 | 3042 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1028,1087 | June 12, 2026 9:30 | June 12, 2026 10:30 | 6/12/26 9:30 | 6/12/26 10:30 | 5/8/26 1:59 | 5/8/26 2:59 | 0h | -196.52h | 0ed | 0 | NA | NA | April 9, 2026 10:45 | April 9, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.14.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1095 | 3043 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | Fixed Units | 6 | 0.38d | 1094 | June 12, 2026 10:30 | June 12, 2026 2:30 | 6/12/26 10:30 | 6/12/26 2:30 | 5/8/26 2:59 | 5/11/26 8:59 | 0h | -196.52h | 0ed | 0 | NA | NA | April 9, 2026 11:45 | April 9, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.14.4 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1096 | 3044 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 6 | 0.38d | 1095 | June 12, 2026 2:30 | June 15, 2026 8:30 | 6/12/26 2:30 | 6/15/26 8:30 | 5/11/26 8:59 | 5/11/26 11:59 | 0h | -196.52h | 0ed | 0 | NA | NA | April 9, 2026 3:45 | April 10, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.14.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1097 | 3045 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1096 | June 15, 2026 8:30 | June 15, 2026 11:30 | 6/15/26 8:30 | 6/15/26 11:30 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -161.02h | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.14.6 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1098 | 3046 | Yes | Auto Scheduled | Open client for BP number range update | 15m | Fixed Units | 6 | 0.03d | 1087 | June 11, 2026 4:30 | June 11, 2026 4:45 | 6/11/26 4:30 | 6/11/26 4:45 | 5/18/26 9:44 | 5/18/26 9:59 | 0m | -8986m | 0ed | 0 | NA | NA | April 9, 2026 8:45 | April 9, 2026 9:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.14.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1099 | 3047 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 15m | Fixed Units | 6 | 0.03d | 1098 | June 11, 2026 4:45 | June 11, 2026 5:00 | 6/11/26 4:45 | 6/11/26 5:00 | 5/18/26 9:59 | 5/18/26 10:14 | 0m | -8986m | 0ed | 0 | NA | NA | April 9, 2026 9:00 | April 9, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.14.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1100 | 3048 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 6 | 0.03d | 1099 | June 12, 2026 8:00 | June 12, 2026 8:15 | 6/12/26 8:00 | 6/12/26 8:15 | 5/18/26 10:14 | 5/18/26 10:29 | 0m | -8986m | 0ed | 0 | NA | NA | April 9, 2026 9:15 | April 9, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.14.9 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1101 | 3049 | Yes | Auto Scheduled | PTP_CM27_Vendor Master as Customer - FLCU01 | 4.81d | Fixed Duration | 5 | 2.31d |  | June 15, 2026 8:30 | June 19, 2026 4:00 | 6/15/26 8:30 | 6/19/26 4:00 | 5/11/26 11:59 | 5/18/26 10:29 | 0d | -24.56d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 14, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 19.25h | 19.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.15 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1102 | 3050 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1096 | June 15, 2026 8:30 | June 15, 2026 9:30 | 6/15/26 8:30 | 6/15/26 9:30 | 5/11/26 11:59 | 5/11/26 1:59 | 0h | -196.52h | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.15.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1103 | 3051 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1102 | June 15, 2026 9:30 | June 15, 2026 11:30 | 6/15/26 9:30 | 6/15/26 11:30 | 5/11/26 1:59 | 5/11/26 3:59 | 0h | -196.52h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.15.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1104 | 3052 | Yes | Auto Scheduled | Simulate Load | 11.25h | Fixed Units | 6 | 1.41d | 1068,1103 | June 15, 2026 11:30 | June 16, 2026 3:45 | 6/15/26 11:30 | 6/16/26 3:45 | 5/11/26 3:59 | 5/13/26 10:14 | 0h | -196.52h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 13, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 11.25h | 11.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.15.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1105 | 3053 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1104 | June 16, 2026 3:45 | June 18, 2026 10:30 | 6/16/26 3:45 | 6/18/26 10:30 | 5/13/26 10:14 | 5/14/26 2:59 | 0h | -196.52h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 14, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.15.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1106 | 3054 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1105 | June 18, 2026 10:30 | June 19, 2026 2:00 | 6/18/26 10:30 | 6/19/26 2:00 | 5/14/26 2:59 | 5/18/26 8:29 | 0h | -196.52h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 14, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.15.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1107 | 3055 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1106 | June 19, 2026 2:00 | June 19, 2026 4:00 | 6/19/26 2:00 | 6/19/26 4:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -196.52h | 0ed | 0 | NA | NA | April 14, 2026 10:15 | April 14, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.15.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1108 | 3056 | Yes | Auto Scheduled | OTC_CM23_Customer_Hierarchy | 0.69d | Fixed Duration | 5 | 0.69d |  | June 15, 2026 8:30 | June 15, 2026 3:00 | 6/15/26 8:30 | 6/15/26 3:00 | 5/15/26 1:59 | 5/18/26 10:29 | 0d | -20.44d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.16 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1109 | 3057 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1096 | June 15, 2026 8:30 | June 15, 2026 9:00 | 6/15/26 8:30 | 6/15/26 9:00 | 5/15/26 1:59 | 5/15/26 2:29 | 0m | -9811m | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.16.1 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1110 | 3058 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1109 | June 15, 2026 9:00 | June 15, 2026 11:00 | 6/15/26 9:00 | 6/15/26 11:00 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -163.52h | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.16.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1111 | 3059 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1110 | June 15, 2026 11:00 | June 15, 2026 3:00 | 6/15/26 11:00 | 6/15/26 3:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -163.52h | 0ed | 0 | NA | NA | April 10, 2026 1:15 | April 10, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.16.3 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1112 | 3060 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Z001 - External Sales Rep | 3.38d | Fixed Duration | 5 | 1.13d |  | June 15, 2026 8:30 | June 18, 2026 11:30 | 6/15/26 8:30 | 6/18/26 11:30 | 5/12/26 4:29 | 5/18/26 10:29 | 0d | -23.13d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.17 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1113 | 3061 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1096 | June 15, 2026 8:30 | June 15, 2026 9:30 | 6/15/26 8:30 | 6/15/26 9:30 | 5/12/26 4:29 | 5/13/26 8:29 | 0h | -185.02h | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.17.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1114 | 3062 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1113 | June 15, 2026 9:30 | June 15, 2026 11:30 | 6/15/26 9:30 | 6/15/26 11:30 | 5/13/26 8:29 | 5/13/26 10:29 | 0h | -185.02h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.17.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1115 | 3063 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1068,1114 | June 15, 2026 11:30 | June 15, 2026 1:30 | 6/15/26 11:30 | 6/15/26 1:30 | 5/13/26 10:29 | 5/13/26 11:29 | 0h | -185.02h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.17.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1116 | 3064 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1115 | June 15, 2026 1:30 | June 15, 2026 3:30 | 6/15/26 1:30 | 6/15/26 3:30 | 5/13/26 11:29 | 5/13/26 2:29 | 0h | -185.02h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.17.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1117 | 3065 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1116 | June 15, 2026 3:30 | June 18, 2026 9:30 | 6/15/26 3:30 | 6/18/26 9:30 | 5/13/26 2:29 | 5/18/26 8:29 | 0h | -185.02h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.17.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1118 | 3066 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1117 | June 18, 2026 9:30 | June 18, 2026 11:30 | 6/18/26 9:30 | 6/18/26 11:30 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -185.02h | 0ed | 0 | NA | NA | April 13, 2026 8:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.17.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1119 | 3067 | Yes | Auto Scheduled | RTR_CM10_Credit_Management_Role | 1.84d | Fixed Duration | 5 | 1.13d |  | June 15, 2026 8:30 | June 16, 2026 4:15 | 6/15/26 8:30 | 6/16/26 4:15 | 5/13/26 2:44 | 5/15/26 1:29 | 0d | -22.35d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.18 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1120 | 3068 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1096 | June 15, 2026 8:30 | June 15, 2026 9:00 | 6/15/26 8:30 | 6/15/26 9:00 | 5/13/26 2:44 | 5/13/26 3:14 | 0m | -10726m | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.18.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1121 | 3069 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1120 | June 15, 2026 9:00 | June 15, 2026 9:30 | 6/15/26 9:00 | 6/15/26 9:30 | 5/13/26 3:14 | 5/13/26 3:44 | 0m | -10726m | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.18.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1122 | 3070 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1121 | June 15, 2026 9:30 | June 15, 2026 10:30 | 6/15/26 9:30 | 6/15/26 10:30 | 5/13/26 3:44 | 5/13/26 4:44 | 0h | -178.77h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.18.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1123 | 3071 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1122 | June 15, 2026 10:30 | June 15, 2026 2:00 | 6/15/26 10:30 | 6/15/26 2:00 | 5/13/26 4:44 | 5/14/26 10:14 | 0h | -178.77h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.18.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1124 | 3072 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1123 | June 15, 2026 2:00 | June 16, 2026 9:00 | 6/15/26 2:00 | 6/16/26 9:00 | 5/14/26 10:14 | 5/14/26 3:14 | 0h | -178.77h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.18.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1125 | 3073 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1124 | June 16, 2026 9:00 | June 16, 2026 4:15 | 6/16/26 9:00 | 6/16/26 4:15 | 5/14/26 3:14 | 5/15/26 1:29 | 0h | -178.77h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.18.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1126 | 3074 | Yes | Auto Scheduled | PTP_CM27_Vendor Master | 6.28d | Fixed Duration | 5 | 2.91d |  | June 8, 2026 10:00 | June 16, 2026 1:15 | 6/8/26 10:00 | 6/16/26 1:15 | 5/5/26 11:44 | 5/18/26 10:29 | 0d | -23.78d | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 10.25h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.19 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1127 | 3075 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1113 | June 15, 2026 9:30 | June 15, 2026 10:30 | 6/15/26 9:30 | 6/15/26 10:30 | 5/14/26 4:44 | 5/15/26 8:44 | 0h | -169.77h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.19.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1128 | 3076 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1127 | June 15, 2026 10:30 | June 15, 2026 1:30 | 6/15/26 10:30 | 6/15/26 1:30 | 5/15/26 8:44 | 5/15/26 10:44 | 0h | -169.77h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.19.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1129 | 3077 | Yes | Auto Scheduled | Simulate Load | 2.25h | Fixed Units | 6 | 0.13d | 1128 | June 15, 2026 1:30 | June 15, 2026 3:45 | 6/15/26 1:30 | 6/15/26 3:45 | 5/15/26 10:44 | 5/15/26 1:59 | 0h | -169.77h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 14, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2.25h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.19.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1130 | 3078 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1129 | June 15, 2026 3:45 | June 16, 2026 1:15 | 6/15/26 3:45 | 6/16/26 1:15 | 5/15/26 1:59 | 5/18/26 10:29 | 0h | -169.77h | 0ed | 0 | NA | NA | April 14, 2026 2:00 | April 14, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.19.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1131 | 3079 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d |  | June 8, 2026 10:00 | June 8, 2026 11:00 | 6/8/26 10:00 | 6/8/26 11:00 | 5/5/26 11:44 | 5/5/26 1:44 | 0h | -190.27h | 0ed | 0 | NA | NA | April 14, 2026 4:00 | April 14, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.19.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1132 | 3080 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1131 | June 8, 2026 11:00 | June 8, 2026 2:00 | 6/8/26 11:00 | 6/8/26 2:00 | 5/5/26 1:44 | 5/5/26 3:44 | 0h | -190.27h | 0ed | 0 | NA | NA | April 15, 2026 8:00 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.19.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1133 | 3081 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | 0.88d | Fixed Duration | 5 | 3.16d |  | June 8, 2026 10:00 | June 9, 2026 9:00 | 6/8/26 10:00 | 6/9/26 9:00 | 5/14/26 3:29 | 5/18/26 10:29 | 0d | -16.44d | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.20 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1134 | 3082 | Yes | Auto Scheduled | Extract File(Will Extract from LFA1) | 1h | Fixed Units | 6 | 0.13d |  | June 8, 2026 10:00 | June 8, 2026 11:00 | 6/8/26 10:00 | 6/8/26 11:00 | 5/14/26 3:29 | 5/14/26 4:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.20.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1135 | 3083 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1134 | June 8, 2026 11:00 | June 8, 2026 2:00 | 6/8/26 11:00 | 6/8/26 2:00 | 5/14/26 4:29 | 5/15/26 9:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.20.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1136 | 3084 | Yes | Auto Scheduled | Simulate Load/ Not Needed | 1h | Fixed Units | 6 | 0.13d | 1135 | June 8, 2026 2:00 | June 8, 2026 3:00 | 6/8/26 2:00 | 6/8/26 3:00 | 5/15/26 9:29 | 5/15/26 10:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 10, 2026 3:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.20.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1137 | 3085 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1136 | June 8, 2026 3:00 | June 8, 2026 5:00 | 6/8/26 3:00 | 6/8/26 5:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -125.52h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.20.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1138 | 3086 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1136 | June 8, 2026 3:00 | June 8, 2026 4:00 | 6/8/26 3:00 | 6/8/26 4:00 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 11:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.20.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1139 | 3087 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1138 | June 8, 2026 4:00 | June 9, 2026 9:00 | 6/8/26 4:00 | 6/9/26 9:00 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 15, 2026 11:00 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.20.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1140 | 3088 | Yes | Auto Scheduled | RTR_****_Credit Hierarchy | 1.91d | Fixed Duration | 5 | 1.25d |  | June 15, 2026 2:00 | June 17, 2026 1:15 | 6/15/26 2:00 | 6/17/26 1:15 | 5/15/26 2:29 | 5/18/26 10:29 | 0d | -22.22d | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.21 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1141 | 3089 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1123 | June 15, 2026 2:00 | June 15, 2026 2:30 | 6/15/26 2:00 | 6/15/26 2:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -9781m | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.21.1 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1142 | 3090 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1125 | June 16, 2026 4:15 | June 17, 2026 9:15 | 6/16/26 4:15 | 6/17/26 9:15 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -177.77h | 0ed | 0 | NA | NA | April 13, 2026 10:45 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.21.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1143 | 3091 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1142 | June 17, 2026 9:15 | June 17, 2026 1:15 | 6/17/26 9:15 | 6/17/26 1:15 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -177.77h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.21.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1144 | 3092 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Supplier | 1.13d | Fixed Duration | 5 | 1.13d |  | June 8, 2026 2:00 | June 9, 2026 3:00 | 6/8/26 2:00 | 6/9/26 3:00 | 5/15/26 9:29 | 5/18/26 10:29 | 0d | -16.44d | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 15h | 15h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.22 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1145 | 3093 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1132 | June 8, 2026 2:00 | June 8, 2026 2:30 | 6/8/26 2:00 | 6/8/26 2:30 | 5/15/26 9:29 | 5/15/26 9:59 | 0m | -7891m | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 13, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.22.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1146 | 3094 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1145 | June 8, 2026 2:30 | June 8, 2026 3:00 | 6/8/26 2:30 | 6/8/26 3:00 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -7891m | 0ed | 0 | NA | NA | April 13, 2026 1:15 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.22.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1147 | 3095 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1146 | June 8, 2026 3:00 | June 8, 2026 4:00 | 6/8/26 3:00 | 6/8/26 4:00 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.22.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1148 | 3096 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1147 | June 8, 2026 4:00 | June 9, 2026 9:00 | 6/8/26 4:00 | 6/9/26 9:00 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 13, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.22.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1149 | 3097 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1148 | June 9, 2026 9:00 | June 9, 2026 11:00 | 6/9/26 9:00 | 6/9/26 11:00 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 13, 2026 4:45 | April 14, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.22.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1150 | 3098 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1149 | June 9, 2026 11:00 | June 9, 2026 3:00 | 6/9/26 11:00 | 6/9/26 3:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 14, 2026 9:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.22.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1151 | 3099 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Customer | 1.06d | Fixed Duration | 5 | 1.13d |  | June 8, 2026 10:00 | June 9, 2026 10:30 | 6/8/26 10:00 | 6/9/26 10:30 | 5/15/26 9:59 | 5/18/26 10:29 | 0d | -16d | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 15h | 15h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.23 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1152 | 3100 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d |  | June 8, 2026 10:00 | June 8, 2026 10:30 | 6/8/26 10:00 | 6/8/26 10:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -7201m | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 13, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.23.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1153 | 3101 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d |  | June 8, 2026 10:00 | June 8, 2026 10:30 | 6/8/26 10:00 | 6/8/26 10:30 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -7681m | 0ed | 0 | NA | NA | April 13, 2026 1:15 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.23.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1154 | 3102 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1153 | June 8, 2026 10:30 | June 8, 2026 11:30 | 6/8/26 10:30 | 6/8/26 11:30 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -128.02h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.23.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1155 | 3103 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1154 | June 8, 2026 11:30 | June 8, 2026 2:30 | 6/8/26 11:30 | 6/8/26 2:30 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -128.02h | 0ed | 0 | NA | NA | April 13, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.23.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1156 | 3104 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1155 | June 8, 2026 2:30 | June 8, 2026 4:30 | 6/8/26 2:30 | 6/8/26 4:30 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -128.02h | 0ed | 0 | NA | NA | April 13, 2026 4:45 | April 14, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.23.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1157 | 3105 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1156 | June 8, 2026 4:30 | June 9, 2026 10:30 | 6/8/26 4:30 | 6/9/26 10:30 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -128.02h | 0ed | 0 | NA | NA | April 14, 2026 9:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.23.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1158 | 3106 | Yes | Auto Scheduled | PTP_CM26_Material_Master - All Types | 2.28d | Fixed Duration | 5 | 3.16d |  | June 8, 2026 11:00 | June 10, 2026 2:15 | 6/8/26 11:00 | 6/10/26 2:15 | 5/5/26 3:44 | 5/18/26 10:29 | 0d | -23.53d | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 15, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 19h | 19h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.24 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1159 | 3107 | Yes | Auto Scheduled | Extract File | 5h | Fixed Units | 6 | 0.63d | 1134 | June 8, 2026 11:00 | June 9, 2026 9:45 | 6/8/26 11:00 | 6/9/26 9:45 | 5/15/26 11:44 | 5/18/26 10:29 | 0h | -127.27h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 13, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.24.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1160 | 3108 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1132 | June 8, 2026 2:00 | June 9, 2026 11:15 | 6/8/26 2:00 | 6/9/26 11:15 | 5/5/26 3:44 | 5/6/26 1:59 | 0h | -190.27h | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 14, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.24.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1161 | 3109 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1160 | June 9, 2026 11:15 | June 9, 2026 1:15 | 6/9/26 11:15 | 6/9/26 1:15 | 5/6/26 1:59 | 5/6/26 2:59 | 0h | -190.27h | 0ed | 0 | NA | NA | April 14, 2026 10:00 | April 14, 2026 11:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.24.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1162 | 3110 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | Fixed Units | 6 | 0.5d | 1161 | June 9, 2026 1:15 | June 10, 2026 8:15 | 6/9/26 1:15 | 6/10/26 8:15 | 5/6/26 2:59 | 5/7/26 9:59 | 0h | -190.27h | 0ed | 0 | NA | NA | April 14, 2026 11:00 | April 14, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.24.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1163 | 3111 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 6 | 0.38d | 1162 | June 10, 2026 8:15 | June 10, 2026 11:15 | 6/10/26 8:15 | 6/10/26 11:15 | 5/7/26 9:59 | 5/7/26 1:59 | 0h | -190.27h | 0ed | 0 | NA | NA | April 14, 2026 4:00 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.24.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1164 | 3112 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1163 | June 10, 2026 11:15 | June 10, 2026 2:15 | 6/10/26 11:15 | 6/10/26 2:15 | 5/8/26 11:29 | 5/8/26 2:29 | 0h | -183.77h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.24.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1165 | 3113 | Yes | Auto Scheduled | PTP_CM26_Material_Master - SERV - Service Materials | 1.34d | Fixed Duration | 5 | 5.88d |  | June 10, 2026 9:00 | June 11, 2026 11:45 | 6/10/26 9:00 | 6/11/26 11:45 | 5/15/26 9:59 | 5/18/26 10:29 | 0d | -18.16d | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 15h | 15h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.25 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1166 | 3114 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1035 | June 10, 2026 9:00 | June 10, 2026 9:30 | 6/10/26 9:00 | 6/10/26 9:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -8101m | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 7, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.25.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1167 | 3115 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1163 | June 10, 2026 11:15 | June 10, 2026 11:45 | 6/10/26 11:15 | 6/10/26 11:45 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -8716m | 0ed | 0 | NA | NA | April 14, 2026 2:45 | April 14, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.25.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1168 | 3116 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1167 | June 10, 2026 11:45 | June 10, 2026 1:45 | 6/10/26 11:45 | 6/10/26 1:45 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -145.27h | 0ed | 0 | NA | NA | April 14, 2026 3:15 | April 14, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.25.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1169 | 3117 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1168 | June 10, 2026 1:45 | June 10, 2026 3:45 | 6/10/26 1:45 | 6/10/26 3:45 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -145.27h | 0ed | 0 | NA | NA | April 14, 2026 4:15 | April 15, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.25.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1170 | 3118 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1169 | June 10, 2026 3:45 | June 11, 2026 8:45 | 6/10/26 3:45 | 6/11/26 8:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -145.27h | 0ed | 0 | NA | NA | April 15, 2026 9:15 | April 15, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.25.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1171 | 3119 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1170 | June 11, 2026 8:45 | June 11, 2026 11:45 | 6/11/26 8:45 | 6/11/26 11:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -145.27h | 0ed | 0 | NA | NA | April 15, 2026 11:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.25.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1172 | 3120 | Yes | Auto Scheduled | PTP_CM26_Material_Master - KMAT - Configurable Materials | 1.34d | Fixed Duration | 5 | 5.88d |  | June 10, 2026 9:00 | June 11, 2026 11:45 | 6/10/26 9:00 | 6/11/26 11:45 | 5/7/26 1:59 | 5/13/26 2:44 | 0d | -23.5d | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.26 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1173 | 3121 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1035 | June 10, 2026 9:00 | June 10, 2026 9:30 | 6/10/26 9:00 | 6/10/26 9:30 | 5/13/26 2:14 | 5/13/26 2:44 | 0m | -9346m | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 7, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.26.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1174 | 3122 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1163 | June 10, 2026 11:15 | June 10, 2026 11:45 | 6/10/26 11:15 | 6/10/26 11:45 | 5/7/26 1:59 | 5/7/26 2:29 | 0m | -11416m | 0ed | 0 | NA | NA | April 14, 2026 2:45 | April 14, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.26.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1175 | 3123 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1174 | June 10, 2026 11:45 | June 10, 2026 1:45 | 6/10/26 11:45 | 6/10/26 1:45 | 5/7/26 2:29 | 5/7/26 3:29 | 0h | -190.27h | 0ed | 0 | NA | NA | April 14, 2026 3:15 | April 14, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.26.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1176 | 3124 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1175 | June 10, 2026 1:45 | June 10, 2026 3:45 | 6/10/26 1:45 | 6/10/26 3:45 | 5/7/26 3:29 | 5/8/26 8:29 | 0h | -190.27h | 0ed | 0 | NA | NA | April 14, 2026 4:15 | April 15, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.26.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1177 | 3125 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1176 | June 10, 2026 3:45 | June 11, 2026 8:45 | 6/10/26 3:45 | 6/11/26 8:45 | 5/8/26 8:29 | 5/8/26 10:29 | 0h | -190.27h | 0ed | 0 | NA | NA | April 15, 2026 9:15 | April 15, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.26.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1178 | 3126 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1177 | June 11, 2026 8:45 | June 11, 2026 11:45 | 6/11/26 8:45 | 6/11/26 11:45 | 5/8/26 10:29 | 5/8/26 2:29 | 0h | -190.27h | 0ed | 0 | NA | NA | April 15, 2026 11:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.26.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1179 | 3127 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Records | 3.59d | Fixed Duration | 5 | 1.28d |  | June 8, 2026 2:00 | June 12, 2026 9:45 | 6/8/26 2:00 | 6/12/26 9:45 | 5/11/26 2:22 | 5/18/26 10:29 | 0d | -19.96d | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.27 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1180 | 3128 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1164,1178 | June 11, 2026 11:45 | June 11, 2026 1:45 | 6/11/26 11:45 | 6/11/26 1:45 | 5/11/26 2:22 | 5/11/26 3:22 | 0h | -182.39h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.27.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1181 | 3129 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1180 | June 11, 2026 1:45 | June 11, 2026 3:45 | 6/11/26 1:45 | 6/11/26 3:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -151.27h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.27.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1182 | 3130 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1181 | June 11, 2026 3:45 | June 11, 2026 4:45 | 6/11/26 3:45 | 6/11/26 4:45 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -151.27h | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.27.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1183 | 3131 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1182 | June 11, 2026 4:45 | June 12, 2026 9:45 | 6/11/26 4:45 | 6/12/26 9:45 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -151.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.27.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1184 | 3132 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1132 | June 8, 2026 2:00 | June 8, 2026 3:00 | 6/8/26 2:00 | 6/8/26 3:00 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -125.52h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 11:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.27.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1185 | 3133 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1184 | June 8, 2026 3:00 | June 8, 2026 5:00 | 6/8/26 3:00 | 6/8/26 5:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -125.52h | 0ed | 0 | NA | NA | April 15, 2026 11:00 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.27.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1186 | 3134 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record External Processing | 1.13d | Fixed Duration | 5 | 1.13d |  | June 11, 2026 11:45 | June 12, 2026 1:45 | 6/11/26 11:45 | 6/12/26 1:45 | 5/15/26 9:29 | 5/18/26 10:29 | 0d | -19.28d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.28 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1187 | 3135 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1164,1178 | June 11, 2026 11:45 | June 11, 2026 1:15 | 6/11/26 11:45 | 6/11/26 1:15 | 5/15/26 9:29 | 5/15/26 9:59 | 0m | -9256m | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.28.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1188 | 3136 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1187 | June 11, 2026 1:15 | June 11, 2026 1:45 | 6/11/26 1:15 | 6/11/26 1:45 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -9256m | 0ed | 0 | NA | NA | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.28.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1189 | 3137 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1188 | June 11, 2026 1:45 | June 11, 2026 2:45 | 6/11/26 1:45 | 6/11/26 2:45 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -154.27h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.28.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1190 | 3138 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1189 | June 11, 2026 2:45 | June 11, 2026 4:45 | 6/11/26 2:45 | 6/11/26 4:45 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -154.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.28.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1191 | 3139 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1190 | June 11, 2026 4:45 | June 12, 2026 9:45 | 6/11/26 4:45 | 6/12/26 9:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -154.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.28.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1192 | 3140 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1191 | June 12, 2026 9:45 | June 12, 2026 1:45 | 6/12/26 9:45 | 6/12/26 1:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -154.27h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.28.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1193 | 3141 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | 1.13d | Fixed Duration | 5 | 1.13d |  | June 11, 2026 11:45 | June 12, 2026 1:45 | 6/11/26 11:45 | 6/12/26 1:45 | 5/8/26 2:29 | 5/18/26 10:29 | 0d | -23.78d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.29 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1194 | 3142 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1164,1178 | June 11, 2026 11:45 | June 11, 2026 1:15 | 6/11/26 11:45 | 6/11/26 1:15 | 5/8/26 2:29 | 5/8/26 2:59 | 0m | -11416m | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.29.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1195 | 3143 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1194 | June 11, 2026 1:15 | June 11, 2026 1:45 | 6/11/26 1:15 | 6/11/26 1:45 | 5/8/26 2:59 | 5/8/26 3:29 | 0m | -11416m | 0ed | 0 | NA | NA | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.29.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1196 | 3144 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1195 | June 11, 2026 1:45 | June 11, 2026 2:45 | 6/11/26 1:45 | 6/11/26 2:45 | 5/8/26 3:29 | 5/8/26 4:29 | 0h | -190.27h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.29.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1197 | 3145 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1196 | June 11, 2026 2:45 | June 11, 2026 4:45 | 6/11/26 2:45 | 6/11/26 4:45 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -154.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.29.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1198 | 3146 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1197 | June 11, 2026 4:45 | June 12, 2026 9:45 | 6/11/26 4:45 | 6/12/26 9:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -154.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.29.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1199 | 3147 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1198 | June 12, 2026 9:45 | June 12, 2026 1:45 | 6/12/26 9:45 | 6/12/26 1:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -154.27h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.29.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1200 | 3148 | Yes | Auto Scheduled | PTM_CM31_BOM Conversion | 2.48d | Fixed Duration | 5 | 1.13d |  | June 11, 2026 1:45 | June 16, 2026 8:38 | 6/11/26 1:45 | 6/16/26 8:38 | 5/11/26 3:22 | 5/14/26 10:14 | 0d | -22.8d | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 19h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.30 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1201 | 3149 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1180 | June 11, 2026 1:45 | June 11, 2026 2:45 | 6/11/26 1:45 | 6/11/26 2:45 | 5/11/26 3:22 | 5/11/26 4:22 | 0h | -182.39h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.30.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1202 | 3150 | Yes | Auto Scheduled | Pre Load Validation | 0.5h | Fixed Units | 6 | 0.25d | 1201 | June 11, 2026 2:45 | June 11, 2026 3:15 | 6/11/26 2:45 | 6/11/26 3:15 | 5/11/26 4:22 | 5/11/26 4:52 | 0h | -182.39h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.30.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1203 | 3151 | Yes | Auto Scheduled | Simulate Load | 15.5h | Fixed Units | 6 | 0.13d | 1202 | June 11, 2026 3:15 | June 15, 2026 3:15 | 6/11/26 3:15 | 6/15/26 3:15 | 5/11/26 4:52 | 5/13/26 4:52 | 0h | -182.39h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 15.5h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.30.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1204 | 3152 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | Fixed Units | 6 | 0.25d | 1203 | June 15, 2026 3:15 | June 15, 2026 3:45 | 6/15/26 3:15 | 6/15/26 3:45 | 5/13/26 4:52 | 5/14/26 8:22 | 0h | -182.39h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.30.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1205 | 3153 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1204 | June 15, 2026 3:45 | June 15, 2026 5:00 | 6/15/26 3:45 | 6/15/26 5:00 | 5/14/26 8:22 | 5/14/26 9:37 | 0h | -182.39h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 16, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 4/1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1206 | 3154 | Yes | Auto Scheduled | Post Load Validation | 0.5h | Fixed Units | 6 | 0.25d | 1205 | June 16, 2026 8:00 | June 16, 2026 8:38 | 6/16/26 8:00 | 6/16/26 8:38 | 5/14/26 9:37 | 5/14/26 10:14 | 0h | -182.39h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.30.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1207 | 3155 | Yes | Auto Scheduled | PTM_CM40_Work Center Conversion | 3.08d | Fixed Duration | 5 | 2d |  | June 11, 2026 2:45 | June 16, 2026 3:23 | 6/11/26 2:45 | 6/16/26 3:23 | 5/12/26 4:59 | 5/14/26 4:59 | 0d | -22.8d | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 6.75h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.31 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1208 | 3156 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1201 | June 11, 2026 2:45 | June 11, 2026 3:45 | 6/11/26 2:45 | 6/11/26 3:45 | 5/12/26 4:59 | 5/13/26 8:59 | 0h | -173.77h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.31.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1209 | 3157 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1206 | June 16, 2026 8:38 | June 16, 2026 10:38 | 6/16/26 8:38 | 6/16/26 10:38 | 5/14/26 10:14 | 5/14/26 1:14 | 0h | -182.39h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.31.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1210 | 3158 | Yes | Auto Scheduled | Simulate Load | 0.25h | Fixed Units | 6 | 0.13d | 1209 | June 16, 2026 10:38 | June 16, 2026 10:53 | 6/16/26 10:38 | 6/16/26 10:53 | 5/14/26 1:14 | 5/14/26 1:29 | 0h | -182.39h | 0ed | 0 | NA | NA | April 17, 2026 10:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.25h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.31.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1211 | 3159 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | Fixed Units | 6 | 0.25d | 1210 | June 16, 2026 10:53 | June 16, 2026 11:23 | 6/16/26 10:53 | 6/16/26 11:23 | 5/14/26 1:29 | 5/14/26 1:59 | 0h | -182.39h | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.31.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1212 | 3160 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1211 | June 16, 2026 11:23 | June 16, 2026 1:23 | 6/16/26 11:23 | 6/16/26 1:23 | 5/14/26 1:59 | 5/14/26 2:59 | 0h | -182.39h | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 17, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.31.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1213 | 3161 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1212 | June 16, 2026 1:23 | June 16, 2026 3:23 | 6/16/26 1:23 | 6/16/26 3:23 | 5/14/26 2:59 | 5/14/26 4:59 | 0h | -182.39h | 0ed | 0 | NA | NA | April 17, 2026 3:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.31.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1214 | 3162 | Yes | Auto Scheduled | PTM_CM38_Routing Conversion | 4.27d | Fixed Duration | 5 | 2.88d |  | June 11, 2026 3:45 | June 18, 2026 8:53 | 6/11/26 3:45 | 6/18/26 8:53 | 5/13/26 8:59 | 5/18/26 10:29 | 0d | -22.8d | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 11h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.32 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1215 | 3163 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1208 | June 11, 2026 3:45 | June 11, 2026 4:45 | 6/11/26 3:45 | 6/11/26 4:45 | 5/13/26 8:59 | 5/13/26 9:59 | 0h | -173.77h | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.32.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1216 | 3164 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1213 | June 16, 2026 3:23 | June 17, 2026 10:53 | 6/16/26 3:23 | 6/17/26 10:53 | 5/14/26 4:59 | 5/15/26 1:29 | 0h | -182.39h | 0ed | 0 | NA | NA | April 20, 2026 8:15 | April 20, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.32.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1217 | 3165 | Yes | Auto Scheduled | Simulate Load | 2h | Fixed Units | 6 | 0.13d | 1216 | June 17, 2026 10:53 | June 17, 2026 1:53 | 6/17/26 10:53 | 6/17/26 1:53 | 5/15/26 1:29 | 5/15/26 3:29 | 0h | -182.39h | 0ed | 0 | NA | NA | April 20, 2026 10:15 | April 20, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.32.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1218 | 3166 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | Fixed Units | 6 | 0.25d | 1217SS | June 17, 2026 10:53 | June 17, 2026 2:53 | 6/17/26 10:53 | 6/17/26 2:53 | 5/15/26 1:29 | 5/15/26 4:29 | 0h | -182.39h | 0ed | 0 | NA | NA | April 20, 2026 11:15 | April 20, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.32.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1219 | 3167 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1218 | June 17, 2026 2:53 | June 17, 2026 3:53 | 6/17/26 2:53 | 6/17/26 3:53 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -182.39h | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 20, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.32.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1220 | 3168 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1219 | June 17, 2026 3:53 | June 18, 2026 8:53 | 6/17/26 3:53 | 6/18/26 8:53 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -182.39h | 0ed | 0 | NA | NA | April 20, 2026 3:15 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.32.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1221 | 3169 | Yes | Auto Scheduled | PTM_CM36_Production Version Conversion | 1.13d | Fixed Duration | 5 | 1.13d |  | June 11, 2026 4:45 | June 15, 2026 8:45 | 6/11/26 4:45 | 6/15/26 8:45 | 5/13/26 9:59 | 5/14/26 10:59 | 0d | -21.72d | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.33 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1222 | 3170 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1215 | June 11, 2026 4:45 | June 12, 2026 8:15 | 6/11/26 4:45 | 6/12/26 8:15 | 5/13/26 9:59 | 5/13/26 10:29 | 0m | -10426m | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 10:45 | Start No Earlier Than | 4/20/26 8:00 | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.33.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1223 | 3171 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1222 | June 12, 2026 8:15 | June 12, 2026 8:45 | 6/12/26 8:15 | 6/12/26 8:45 | 5/13/26 10:29 | 5/13/26 10:59 | 0m | -10426m | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.33.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1224 | 3172 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1223 | June 12, 2026 8:45 | June 12, 2026 9:45 | 6/12/26 8:45 | 6/12/26 9:45 | 5/13/26 10:59 | 5/13/26 11:59 | 0h | -173.77h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.33.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1225 | 3173 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1224 | June 12, 2026 9:45 | June 12, 2026 11:45 | 6/12/26 9:45 | 6/12/26 11:45 | 5/13/26 11:59 | 5/13/26 2:59 | 0h | -173.77h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.33.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1226 | 3174 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1225 | June 12, 2026 11:45 | June 12, 2026 2:45 | 6/12/26 11:45 | 6/12/26 2:45 | 5/13/26 2:59 | 5/13/26 4:59 | 0h | -173.77h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.33.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1227 | 3175 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1226 | June 12, 2026 2:45 | June 15, 2026 8:45 | 6/12/26 2:45 | 6/15/26 8:45 | 5/13/26 4:59 | 5/14/26 10:59 | 0h | -173.77h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.33.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1228 | 3176 | Yes | Auto Scheduled | PTM_CM35_Inspection Plan | 1.13d | Fixed Duration | 5 | 1.13d |  | June 15, 2026 8:45 | June 16, 2026 9:45 | 6/15/26 8:45 | 6/16/26 9:45 | 5/14/26 10:59 | 5/18/26 10:29 | 0d | -21.72d | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 20, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.34 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1229 | 3177 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1227 | June 15, 2026 8:45 | June 15, 2026 9:15 | 6/15/26 8:45 | 6/15/26 9:15 | 5/14/26 10:59 | 5/14/26 11:29 | 0m | -10426m | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.34.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1230 | 3178 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1229 | June 15, 2026 9:15 | June 15, 2026 9:45 | 6/15/26 9:15 | 6/15/26 9:45 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -10036m | 0ed | 0 | NA | NA | April 17, 2026 11:45 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.34.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1231 | 3179 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1230 | June 15, 2026 9:45 | June 15, 2026 10:45 | 6/15/26 9:45 | 6/15/26 10:45 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -167.27h | 0ed | 0 | NA | NA | April 17, 2026 1:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.34.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1232 | 3180 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1231 | June 15, 2026 10:45 | June 15, 2026 1:45 | 6/15/26 10:45 | 6/15/26 1:45 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -167.27h | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 17, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.34.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1233 | 3181 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1232 | June 15, 2026 1:45 | June 15, 2026 3:45 | 6/15/26 1:45 | 6/15/26 3:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -167.27h | 0ed | 0 | NA | NA | April 17, 2026 4:15 | April 20, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.34.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1234 | 3182 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1233 | June 15, 2026 3:45 | June 16, 2026 9:45 | 6/15/26 3:45 | 6/16/26 9:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -167.27h | 0ed | 0 | NA | NA | April 20, 2026 9:15 | April 20, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.34.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1235 | 3183 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Serial Numbers | 1.13d | Fixed Duration | 5 | 1.13d |  | June 15, 2026 9:15 | June 16, 2026 10:15 | 6/15/26 9:15 | 6/16/26 10:15 | 5/14/26 11:29 | 5/15/26 1:29 | 0d | -21.72d | 0ed | 0 | NA | NA | April 17, 2026 11:45 | April 20, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.35 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1236 | 3184 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1229 | June 15, 2026 9:15 | June 15, 2026 9:45 | 6/15/26 9:15 | 6/15/26 9:45 | 5/14/26 11:29 | 5/14/26 11:59 | 0m | -10426m | 0ed | 0 | NA | NA | April 17, 2026 11:45 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.35.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1237 | 3185 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1236 | June 15, 2026 9:45 | June 15, 2026 10:15 | 6/15/26 9:45 | 6/15/26 10:15 | 5/14/26 11:59 | 5/14/26 1:29 | 0m | -10426m | 0ed | 0 | NA | NA | April 17, 2026 1:15 | April 17, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.35.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1238 | 3186 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1237 | June 15, 2026 10:15 | June 15, 2026 11:15 | 6/15/26 10:15 | 6/15/26 11:15 | 5/14/26 1:29 | 5/14/26 2:29 | 0h | -173.77h | 0ed | 0 | NA | NA | April 17, 2026 1:45 | April 17, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.35.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1239 | 3187 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1238 | June 15, 2026 11:15 | June 15, 2026 2:15 | 6/15/26 11:15 | 6/15/26 2:15 | 5/14/26 2:29 | 5/14/26 4:29 | 0h | -173.77h | 0ed | 0 | NA | NA | April 17, 2026 2:45 | April 17, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.35.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1240 | 3188 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1239 | June 15, 2026 2:15 | June 15, 2026 4:15 | 6/15/26 2:15 | 6/15/26 4:15 | 5/14/26 4:29 | 5/15/26 9:29 | 0h | -173.77h | 0ed | 0 | NA | NA | April 17, 2026 4:45 | April 20, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.35.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1241 | 3189 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1240 | June 15, 2026 4:15 | June 16, 2026 10:15 | 6/15/26 4:15 | 6/16/26 10:15 | 5/15/26 9:29 | 5/15/26 1:29 | 0h | -173.77h | 0ed | 0 | NA | NA | April 20, 2026 9:45 | April 20, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.35.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1242 | 3190 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Service | 6.78d | Fixed Duration | 5 | 1.13d |  | June 8, 2026 10:00 | June 17, 2026 8:15 | 6/8/26 10:00 | 6/17/26 8:15 | 5/15/26 1:29 | 5/18/26 10:29 | 0d | -21.72d | 0ed | 0 | NA | NA | April 20, 2026 1:45 | April 21, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.36 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1243 | 3191 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1241 | June 16, 2026 10:15 | June 16, 2026 10:45 | 6/16/26 10:15 | 6/16/26 10:45 | 5/15/26 1:29 | 5/15/26 1:59 | 0m | -10426m | 0ed | 0 | NA | NA | April 20, 2026 1:45 | April 20, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.36.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1244 | 3192 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1243 | June 16, 2026 10:45 | June 16, 2026 11:15 | 6/16/26 10:45 | 6/16/26 11:15 | 5/15/26 1:59 | 5/15/26 2:29 | 0m | -10426m | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 20, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.36.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1245 | 3193 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1244 | June 16, 2026 11:15 | June 16, 2026 1:15 | 6/16/26 11:15 | 6/16/26 1:15 | 5/15/26 2:29 | 5/15/26 3:29 | 0h | -173.77h | 0ed | 0 | NA | NA | April 20, 2026 2:45 | April 20, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.36.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1246 | 3194 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1245 | June 16, 2026 1:15 | June 16, 2026 3:15 | 6/16/26 1:15 | 6/16/26 3:15 | 5/15/26 3:29 | 5/18/26 8:29 | 0h | -173.77h | 0ed | 0 | NA | NA | April 20, 2026 3:45 | April 21, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.36.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1247 | 3195 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1246 | June 16, 2026 3:15 | June 17, 2026 8:15 | 6/16/26 3:15 | 6/17/26 8:15 | 5/18/26 8:29 | 5/18/26 10:29 | 0h | -173.77h | 0ed | 0 | NA | NA | April 21, 2026 8:45 | April 21, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.36.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1248 | 3196 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d |  | June 8, 2026 10:00 | June 8, 2026 2:00 | 6/8/26 10:00 | 6/8/26 2:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -122.52h | 0ed | 0 | NA | NA | April 21, 2026 10:45 | April 21, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.36.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1249 | 3197 | Yes | Auto Scheduled | VC_Object Dependencies | 0.63d | Fixed Duration | 5 | 0.63d |  | June 8, 2026 10:00 | June 8, 2026 4:00 | 6/8/26 10:00 | 6/8/26 4:00 | 5/13/26 3:29 | 5/14/26 11:29 | 0d | -17.44d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.37 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1250 | 3198 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d |  | June 8, 2026 10:00 | June 8, 2026 12:00 | 6/8/26 10:00 | 6/8/26 12:00 | 5/13/26 3:29 | 5/14/26 8:29 | 0h | -139.52h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.37.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1251 | 3199 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1250 | June 8, 2026 1:00 | June 8, 2026 4:00 | 6/8/26 1:00 | 6/8/26 4:00 | 5/14/26 8:29 | 5/14/26 11:29 | 0h | -139.52h | 0ed | 0 | NA | NA | April 6, 2026 10:15 | April 6, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.37.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1252 | 3200 | Yes | Auto Scheduled | VC_Characteristics | 0.63d | Fixed Duration | 5 | 0.63d |  | June 8, 2026 4:00 | June 9, 2026 12:00 | 6/8/26 4:00 | 6/9/26 12:00 | 5/14/26 11:29 | 5/15/26 8:29 | 0d | -17.44d | 0ed | 0 | NA | NA | April 6, 2026 2:15 | April 7, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.38 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1253 | 3201 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1251 | June 8, 2026 4:00 | June 9, 2026 9:00 | 6/8/26 4:00 | 6/9/26 9:00 | 5/14/26 11:29 | 5/14/26 2:29 | 0h | -139.52h | 0ed | 0 | NA | NA | April 6, 2026 2:15 | April 6, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.38.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1254 | 3202 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1253 | June 9, 2026 9:00 | June 9, 2026 12:00 | 6/9/26 9:00 | 6/9/26 12:00 | 5/14/26 2:29 | 5/15/26 8:29 | 0h | -139.52h | 0ed | 0 | NA | NA | April 6, 2026 4:15 | April 7, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.38.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1255 | 3203 | Yes | Auto Scheduled | VC_Classes | 0.63d | Fixed Duration | 5 | 0.63d |  | June 9, 2026 1:00 | June 10, 2026 9:00 | 6/9/26 1:00 | 6/10/26 9:00 | 5/15/26 8:29 | 5/15/26 2:29 | 0d | -17.44d | 0ed | 0 | NA | NA | April 7, 2026 10:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.39 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1256 | 3204 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1254 | June 9, 2026 1:00 | June 9, 2026 3:00 | 6/9/26 1:00 | 6/9/26 3:00 | 5/15/26 8:29 | 5/15/26 10:29 | 0h | -139.52h | 0ed | 0 | NA | NA | April 7, 2026 10:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.39.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1257 | 3205 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1256 | June 9, 2026 3:00 | June 10, 2026 9:00 | 6/9/26 3:00 | 6/10/26 9:00 | 5/15/26 10:29 | 5/15/26 2:29 | 0h | -139.52h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.39.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1258 | 3206 | Yes | Auto Scheduled | VC_Classification (Class Type 200) | 0.63d | Fixed Duration | 5 | 0.63d |  | June 11, 2026 11:45 | June 12, 2026 8:45 | 6/11/26 11:45 | 6/12/26 8:45 | 5/15/26 2:29 | 5/18/26 10:29 | 0d | -18.78d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.40 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1259 | 3207 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1178 | June 11, 2026 11:45 | June 11, 2026 2:45 | 6/11/26 11:45 | 6/11/26 2:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -150.27h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.40.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1260 | 3208 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1259 | June 11, 2026 2:45 | June 12, 2026 8:45 | 6/11/26 2:45 | 6/12/26 8:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -150.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.40.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1261 | 3209 | Yes | Auto Scheduled | VC_Dependency Nets | 0.63d | Fixed Duration | 5 | 0.63d |  | June 11, 2026 11:45 | June 12, 2026 8:45 | 6/11/26 11:45 | 6/12/26 8:45 | 5/15/26 2:29 | 5/18/26 10:29 | 0d | -18.78d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.41 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1262 | 3210 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1172,1257 | June 11, 2026 11:45 | June 11, 2026 2:45 | 6/11/26 11:45 | 6/11/26 2:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -150.27h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.41.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1263 | 3211 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1262 | June 11, 2026 2:45 | June 12, 2026 8:45 | 6/11/26 2:45 | 6/12/26 8:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -150.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.41.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1264 | 3212 | Yes | Auto Scheduled | VC_Configuration Profiles | 0.63d | Fixed Duration | 5 | 0.63d |  | June 11, 2026 11:45 | June 12, 2026 8:45 | 6/11/26 11:45 | 6/12/26 8:45 | 5/13/26 2:44 | 5/14/26 10:44 | 0d | -20.75d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.42 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1265 | 3213 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1172 | June 11, 2026 11:45 | June 11, 2026 2:45 | 6/11/26 11:45 | 6/11/26 2:45 | 5/13/26 2:44 | 5/13/26 4:44 | 0h | -166.02h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.42.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1266 | 3214 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1265 | June 11, 2026 2:45 | June 12, 2026 8:45 | 6/11/26 2:45 | 6/12/26 8:45 | 5/13/26 4:44 | 5/14/26 10:44 | 0h | -166.02h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.42.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1267 | 3215 | Yes | Auto Scheduled | VC_Variant Tables | 0.63d | Fixed Duration | 5 | 0.63d |  | June 12, 2026 8:45 | June 12, 2026 2:45 | 6/12/26 8:45 | 6/12/26 2:45 | 5/15/26 8:29 | 5/15/26 2:29 | 0d | -20.03d | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.43 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1268 | 3216 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1266 | June 12, 2026 8:45 | June 12, 2026 10:45 | 6/12/26 8:45 | 6/12/26 10:45 | 5/15/26 8:29 | 5/15/26 10:29 | 0h | -160.27h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.43.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1269 | 3217 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1268 | June 12, 2026 10:45 | June 12, 2026 2:45 | 6/12/26 10:45 | 6/12/26 2:45 | 5/15/26 10:29 | 5/15/26 2:29 | 0h | -160.27h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.43.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1270 | 3218 | Yes | Auto Scheduled | VC_Variant Tables Content | 0.63d | Fixed Duration | 5 | 0.63d |  | June 12, 2026 2:45 | June 15, 2026 10:45 | 6/12/26 2:45 | 6/15/26 10:45 | 5/15/26 2:29 | 5/18/26 10:29 | 0d | -20.03d | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.44 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1271 | 3219 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1269 | June 12, 2026 2:45 | June 12, 2026 4:45 | 6/12/26 2:45 | 6/12/26 4:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -160.27h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.44.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1272 | 3220 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1271 | June 12, 2026 4:45 | June 15, 2026 10:45 | 6/12/26 4:45 | 6/15/26 10:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -160.27h | 0ed | 0 | NA | NA | April 17, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.44.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1273 | 3221 | Yes | Auto Scheduled | VC_Characteristic Groups | 1.97d | Fixed Duration | 5 | 0.63d |  | June 12, 2026 8:45 | June 16, 2026 8:30 | 6/12/26 8:45 | 6/16/26 8:30 | 5/14/26 10:44 | 5/18/26 10:29 | 0d | -20.75d | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 15.75h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.45 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1274 | 3222 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 12.75h | Fixed Units | 6 | 0.25d | 1266 | June 12, 2026 8:45 | June 15, 2026 2:30 | 6/12/26 8:45 | 6/15/26 2:30 | 5/14/26 10:44 | 5/15/26 4:29 | 0h | -166.02h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 12.75h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.45.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1275 | 3223 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1274 | June 15, 2026 2:30 | June 16, 2026 8:30 | 6/15/26 2:30 | 6/16/26 8:30 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -166.02h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.45.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1276 | 3224 | Yes | Auto Scheduled | PTM_CM52_Super_BOM | 2d | Fixed Duration | 5 | 1.13d |  | June 11, 2026 11:45 | June 15, 2026 11:45 | 6/11/26 11:45 | 6/15/26 11:45 | 5/11/26 8:29 | 5/13/26 8:29 | 0d | -23.41d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 16h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.46 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1277 | 3225 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1178 | June 11, 2026 11:45 | June 11, 2026 1:15 | 6/11/26 11:45 | 6/11/26 1:15 | 5/11/26 8:29 | 5/11/26 8:59 | 0m | -11236m | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.46.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1278 | 3226 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1277 | June 11, 2026 1:15 | June 11, 2026 1:45 | 6/11/26 1:15 | 6/11/26 1:45 | 5/11/26 8:59 | 5/11/26 9:29 | 0m | -11236m | 0ed | 0 | NA | NA | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.46.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1279 | 3227 | Yes | Auto Scheduled | Simulate Load | 8h | Fixed Units | 6 | 0.13d | 1278 | June 11, 2026 1:45 | June 12, 2026 1:45 | 6/11/26 1:45 | 6/12/26 1:45 | 5/11/26 9:29 | 5/12/26 9:29 | 0h | -187.27h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 8h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.46.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1280 | 3228 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1279 | June 12, 2026 1:45 | June 12, 2026 3:45 | 6/12/26 1:45 | 6/12/26 3:45 | 5/12/26 9:29 | 5/12/26 11:29 | 0h | -187.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.46.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1281 | 3229 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1280 | June 12, 2026 3:45 | June 15, 2026 8:45 | 6/12/26 3:45 | 6/15/26 8:45 | 5/12/26 11:29 | 5/12/26 2:29 | 0h | -187.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.46.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1282 | 3230 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1281 | June 15, 2026 8:45 | June 15, 2026 11:45 | 6/15/26 8:45 | 6/15/26 11:45 | 5/12/26 2:29 | 5/13/26 8:29 | 0h | -187.27h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.46.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1283 | 3231 | Yes | Auto Scheduled | PTM_CM53_Super_Routing | 2.13d | Fixed Duration | 5 | 1.13d |  | June 15, 2026 11:45 | June 17, 2026 1:45 | 6/15/26 11:45 | 6/17/26 1:45 | 5/13/26 8:29 | 5/18/26 10:29 | 0d | -23.41d | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.47 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1284 | 3232 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1282 | June 15, 2026 11:45 | June 15, 2026 1:15 | 6/15/26 11:45 | 6/15/26 1:15 | 5/13/26 8:29 | 5/13/26 8:59 | 0m | -11236m | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 16, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.47.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1285 | 3233 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1284 | June 15, 2026 1:15 | June 15, 2026 1:45 | 6/15/26 1:15 | 6/15/26 1:45 | 5/13/26 8:59 | 5/13/26 9:29 | 0m | -11236m | 0ed | 0 | NA | NA | April 16, 2026 4:45 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.47.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1286 | 3234 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1285 | June 15, 2026 1:45 | June 16, 2026 2:45 | 6/15/26 1:45 | 6/16/26 2:45 | 5/13/26 9:29 | 5/14/26 10:29 | 0h | -187.27h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.47.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1287 | 3235 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1286 | June 16, 2026 2:45 | June 16, 2026 4:45 | 6/16/26 2:45 | 6/16/26 4:45 | 5/14/26 10:29 | 5/14/26 1:29 | 0h | -187.27h | 0ed | 0 | NA | NA | April 17, 2026 9:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.47.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1288 | 3236 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1287 | June 16, 2026 4:45 | June 17, 2026 9:45 | 6/16/26 4:45 | 6/17/26 9:45 | 5/14/26 1:29 | 5/14/26 3:29 | 0h | -187.27h | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.47.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1289 | 3237 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1288 | June 17, 2026 9:45 | June 17, 2026 1:45 | 6/17/26 9:45 | 6/17/26 1:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -178.27h | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.47.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1290 | 3238 | Yes | Auto Scheduled | VC_VK30 Pricing Variant | 0.69d | Fixed Duration | 5 | 0.69d |  | June 17, 2026 9:45 | June 17, 2026 4:15 | 6/17/26 9:45 | 6/17/26 4:15 | 5/14/26 3:29 | 5/15/26 11:59 | 0d | -23.41d | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 20, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.48 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1291 | 3239 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1288 | June 17, 2026 9:45 | June 17, 2026 10:15 | 6/17/26 9:45 | 6/17/26 10:15 | 5/14/26 3:29 | 5/14/26 3:59 | 0m | -11236m | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 17, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.48.1 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1292 | 3240 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1291 | June 17, 2026 10:15 | June 17, 2026 1:15 | 6/17/26 10:15 | 6/17/26 1:15 | 5/14/26 3:59 | 5/15/26 8:59 | 0h | -187.27h | 0ed | 0 | NA | NA | April 17, 2026 2:45 | April 17, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.48.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1293 | 3241 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1292 | June 17, 2026 1:15 | June 17, 2026 4:15 | 6/17/26 1:15 | 6/17/26 4:15 | 5/15/26 8:59 | 5/15/26 11:59 | 0h | -187.27h | 0ed | 0 | NA | NA | April 17, 2026 4:45 | April 20, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.48.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1294 | 3242 | Yes | Auto Scheduled | OTC_CM22_Pricing_Condition | 0.69d | Fixed Duration | 5 | 0.69d |  | June 17, 2026 4:15 | June 18, 2026 1:45 | 6/17/26 4:15 | 6/18/26 1:45 | 5/15/26 11:59 | 5/18/26 10:29 | 0d | -23.41d | 0ed | 0 | NA | NA | April 20, 2026 10:45 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 8.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.49 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1295 | 3243 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1293 | June 17, 2026 4:15 | June 17, 2026 4:45 | 6/17/26 4:15 | 6/17/26 4:45 | 5/15/26 11:59 | 5/15/26 1:29 | 0m | -11236m | 0ed | 0 | NA | NA | April 20, 2026 10:45 | April 20, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.49.1 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1296 | 3244 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1295 | June 17, 2026 4:45 | June 18, 2026 9:45 | 6/17/26 4:45 | 6/18/26 9:45 | 5/15/26 1:29 | 5/15/26 3:29 | 0h | -187.27h | 0ed | 0 | NA | NA | April 20, 2026 11:15 | April 20, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.49.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1297 | 3245 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1296 | June 18, 2026 9:45 | June 18, 2026 1:45 | 6/18/26 9:45 | 6/18/26 1:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -186.27h | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 6h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.49.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda,kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1298 | 3246 | Yes | Auto Scheduled | OTC_CM21_CMIR | 0.5d | Fixed Duration | 5 | 1.13d |  | June 18, 2026 9:45 | June 18, 2026 2:45 | 6/18/26 9:45 | 6/18/26 2:45 | 5/15/26 3:29 | 5/18/26 10:29 | 0d | -23.41d | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 21, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 4h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.50 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1299 | 3247 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1296,1307 | June 18, 2026 9:45 | June 18, 2026 10:15 | 6/18/26 9:45 | 6/18/26 10:15 | 5/15/26 3:29 | 5/15/26 3:59 | 0m | -11236m | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 20, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.50.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1300 | 3248 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1299 | June 18, 2026 10:15 | June 18, 2026 10:45 | 6/18/26 10:15 | 6/18/26 10:45 | 5/15/26 3:59 | 5/15/26 4:29 | 0m | -11236m | 0ed | 0 | NA | NA | April 20, 2026 2:45 | April 20, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.50.2 | 500 | No | No | No |  | Kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1301 | 3249 | Yes | Auto Scheduled | Simulate Load | 0h | Fixed Units | 6 | 0.13d | 1300 | June 18, 2026 10:45 | June 18, 2026 10:45 | 6/18/26 10:45 | 6/18/26 10:45 | 5/15/26 4:29 | 5/15/26 4:29 | 0h | -187.27h | 0ed | 0 | NA | NA | April 20, 2026 3:15 | April 20, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.50.3 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1302 | 3250 | Yes | Auto Scheduled | Error and Defect Mitigation | 0h | Fixed Units | 6 | 0.25d | 1301 | June 18, 2026 10:45 | June 18, 2026 10:45 | 6/18/26 10:45 | 6/18/26 10:45 | 5/15/26 4:29 | 5/15/26 4:29 | 0h | -187.27h | 0ed | 0 | NA | NA | April 20, 2026 4:15 | April 21, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.50.4 | 500 | Yes | No | No |  | Kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1303 | 3251 | Yes | Auto Scheduled | Load | 0h | Fixed Units | 6 | 0.25d | 1302 | June 18, 2026 10:45 | June 18, 2026 10:45 | 6/18/26 10:45 | 6/18/26 10:45 | 5/15/26 4:29 | 5/15/26 4:29 | 0h | -187.27h | 0ed | 0 | NA | NA | April 21, 2026 9:15 | April 21, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.50.5 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1304 | 3252 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1303 | June 18, 2026 10:45 | June 18, 2026 2:45 | 6/18/26 10:45 | 6/18/26 2:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -187.27h | 0ed | 0 | NA | NA | April 21, 2026 11:15 | April 21, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.50.6 | 500 | No | No | No |  | Kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1305 | 3253 | Yes | Auto Scheduled | PTP_CM29_Source_List | 6.16d | Fixed Duration | 5 | 0.94d |  | June 9, 2026 11:00 | June 17, 2026 1:15 | 6/9/26 11:00 | 6/17/26 1:15 | 5/15/26 1:29 | 5/18/26 10:29 | 0d | -22.22d | 0ed | 0 | NA | NA | April 13, 2026 10:45 | April 14, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.51 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1306 | 3254 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1149,1156 | June 9, 2026 11:00 | June 9, 2026 11:30 | 6/9/26 11:00 | 6/9/26 11:30 | 5/18/26 9:59 | 5/18/26 10:29 | 0m | -7741m | 0ed | 0 | NA | NA | April 14, 2026 9:45 | April 14, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.51.1 | 500 | No | No | No |  | Sam | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1307 | 3255 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1125 | June 16, 2026 4:15 | June 17, 2026 9:15 | 6/16/26 4:15 | 6/17/26 9:15 | 5/15/26 1:29 | 5/15/26 3:29 | 0h | -178.77h | 0ed | 0 | NA | NA | April 13, 2026 10:45 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.51.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1308 | 3256 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1307 | June 17, 2026 9:15 | June 17, 2026 1:15 | 6/17/26 9:15 | 6/17/26 1:15 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -177.77h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.51.3 | 500 | No | No | No |  | Sam | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1309 | 3257 | Yes | Auto Scheduled | RTR_CM11_Asset_Master | 3.75d | Fixed Duration | 5 | 1.13d |  | June 8, 2026 10:00 | June 11, 2026 5:00 | 6/8/26 10:00 | 6/11/26 5:00 | 5/12/26 1:29 | 5/18/26 10:29 | 0d | -18.69d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 30.5h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.52 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1310 | 3258 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d |  | June 8, 2026 10:00 | June 8, 2026 10:30 | 6/8/26 10:00 | 6/8/26 10:30 | 5/12/26 1:29 | 5/12/26 1:59 | 0m | -8971m | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.52.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1311 | 3259 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1310 | June 8, 2026 10:30 | June 8, 2026 11:00 | 6/8/26 10:30 | 6/8/26 11:00 | 5/12/26 1:59 | 5/12/26 2:29 | 0m | -8971m | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.52.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1312 | 3260 | Yes | Auto Scheduled | Simulate Load | 8h | Fixed Units | 6 | 0.13d | 1311 | June 8, 2026 11:00 | June 9, 2026 11:00 | 6/8/26 11:00 | 6/9/26 11:00 | 5/12/26 2:29 | 5/13/26 2:29 | 0h | -149.52h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 8h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.52.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1313 | 3261 | Yes | Auto Scheduled | Error and Defect Mitigation | 16h | Fixed Units | 6 | 0.25d | 1312 | June 9, 2026 11:00 | June 11, 2026 11:00 | 6/9/26 11:00 | 6/11/26 11:00 | 5/13/26 2:29 | 5/15/26 2:29 | 0h | -149.52h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 16h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.52.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1314 | 3262 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1313 | June 11, 2026 11:00 | June 11, 2026 2:00 | 6/11/26 11:00 | 6/11/26 2:00 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -149.52h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.52.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1315 | 3263 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1314 | June 11, 2026 2:00 | June 11, 2026 5:00 | 6/11/26 2:00 | 6/11/26 5:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -149.52h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.52.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1316 | 3264 | Yes | Auto Scheduled | PTM_CM50_Material Class | 2.13d | Fixed Duration | 5 | 0.25d |  | June 12, 2026 8:15 | June 16, 2026 9:15 | 6/12/26 8:15 | 6/16/26 9:15 | 5/14/26 9:29 | 5/18/26 10:29 | 0d | -20.85d | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 17h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.53 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1317 | 3265 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1222 | June 12, 2026 8:15 | June 12, 2026 8:45 | 6/12/26 8:15 | 6/12/26 8:45 | 5/14/26 9:29 | 5/14/26 9:59 | 0m | -10006m | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.53.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1318 | 3266 | Yes | Auto Scheduled | Load | 30m | Fixed Units | 6 | 0.06d | 1317 | June 12, 2026 8:45 | June 12, 2026 9:15 | 6/12/26 8:45 | 6/12/26 9:15 | 5/14/26 9:59 | 5/14/26 10:29 | 0m | -10006m | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.53.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1319 | 3267 | Yes | Auto Scheduled | Post Load Validation | 16h | Fixed Units | 6 | 0.13d | 1318 | June 12, 2026 9:15 | June 16, 2026 9:15 | 6/12/26 9:15 | 6/16/26 9:15 | 5/14/26 10:29 | 5/18/26 10:29 | 0h | -166.77h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 16h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.53.3 | 500 | No | No | No |  | brad | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1320 | 3268 | Yes | Auto Scheduled | PTM_CM55_Class assignment to materials | 1.13d | Fixed Duration | 5 | 1.13d |  | June 12, 2026 8:45 | June 15, 2026 9:45 | 6/12/26 8:45 | 6/15/26 9:45 | 5/15/26 9:29 | 5/18/26 10:29 | 0d | -19.91d | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.54 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1321 | 3269 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1317 | June 12, 2026 8:45 | June 12, 2026 9:15 | 6/12/26 8:45 | 6/12/26 9:15 | 5/15/26 9:29 | 5/15/26 9:59 | 0m | -9556m | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.54.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1322 | 3270 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1321 | June 12, 2026 9:15 | June 12, 2026 9:45 | 6/12/26 9:15 | 6/12/26 9:45 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -9556m | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.54.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1323 | 3271 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1322 | June 12, 2026 9:45 | June 12, 2026 10:45 | 6/12/26 9:45 | 6/12/26 10:45 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -159.27h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.54.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1324 | 3272 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1323 | June 12, 2026 10:45 | June 12, 2026 1:45 | 6/12/26 10:45 | 6/12/26 1:45 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -159.27h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.54.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1325 | 3273 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1324 | June 12, 2026 1:45 | June 12, 2026 3:45 | 6/12/26 1:45 | 6/12/26 3:45 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -159.27h | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 17, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.54.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1326 | 3274 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1325 | June 12, 2026 3:45 | June 15, 2026 9:45 | 6/12/26 3:45 | 6/15/26 9:45 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -159.27h | 0ed | 0 | NA | NA | April 17, 2026 9:15 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.54.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1327 | 3275 | Yes | Auto Scheduled | GTS - Material initial load from S4 (Run Interface) | 2.09d | Fixed Duration | 5 | 0.25d |  | June 11, 2026 2:45 | June 15, 2026 3:30 | 6/11/26 2:45 | 6/15/26 3:30 | 5/8/26 4:29 | 5/13/26 8:14 | 0d | -23.78d | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 16.75h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.55 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1328 | 3276 | Yes | Auto Scheduled | Run material interface to GTS | 15.75h | Fixed Units | 6 | 0.13d | 1196 | June 11, 2026 2:45 | June 15, 2026 2:30 | 6/11/26 2:45 | 6/15/26 2:30 | 5/8/26 4:29 | 5/12/26 4:14 | 0h | -190.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 15.75h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.55.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1329 | 3277 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1328 | June 15, 2026 2:30 | June 15, 2026 3:30 | 6/15/26 2:30 | 6/15/26 3:30 | 5/12/26 4:14 | 5/13/26 8:14 | 0h | -190.27h | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.55.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1330 | 3278 | Yes | Auto Scheduled | GTS - Customers initial load from S4 (Run Interface) | 0.25d | Fixed Duration | 5 | 0.25d |  | June 8, 2026 10:00 | June 8, 2026 12:00 | 6/8/26 10:00 | 6/8/26 12:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0d | -15.19d | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.56 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1331 | 3279 | Yes | Auto Scheduled | Run material interface to GTS | 1h | Fixed Units | 6 | 0.13d |  | June 8, 2026 10:00 | June 8, 2026 11:00 | 6/8/26 10:00 | 6/8/26 11:00 | 5/18/26 8:29 | 5/18/26 9:29 | 0h | -121.52h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.56.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1332 | 3280 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1331 | June 8, 2026 11:00 | June 8, 2026 12:00 | 6/8/26 11:00 | 6/8/26 12:00 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -121.52h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.56.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1333 | 3281 | Yes | Auto Scheduled | GTS - Vendors initial load from S4 (Run Interface) | 0.25d | Fixed Duration | 5 | 0.25d |  | June 9, 2026 9:00 | June 9, 2026 11:00 | 6/9/26 9:00 | 6/9/26 11:00 | 5/15/26 2:29 | 5/18/26 10:29 | 0d | -16.44d | 0ed | 0 | NA | NA | April 15, 2026 2:00 | April 15, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.57 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1334 | 3282 | Yes | Auto Scheduled | Run material interface to GTS | 1h | Fixed Units | 6 | 0.13d | 1139 | June 9, 2026 9:00 | June 9, 2026 10:00 | 6/9/26 9:00 | 6/9/26 10:00 | 5/15/26 2:29 | 5/15/26 3:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 15, 2026 2:00 | April 15, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.57.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1335 | 3283 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1334 | June 9, 2026 10:00 | June 9, 2026 11:00 | 6/9/26 10:00 | 6/9/26 11:00 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -128.52h | 0ed | 0 | NA | NA | April 15, 2026 3:00 | April 15, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.57.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1336 | 3284 | Yes | Auto Scheduled | GTS - ECCN - Create | 1.13d | Fixed Duration | 5 | 5.63d |  | June 8, 2026 10:00 | June 9, 2026 11:00 | 6/8/26 10:00 | 6/9/26 11:00 | 5/15/26 3:29 | 5/18/26 10:29 | 0d | -16.06d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 13, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.58 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1337 | 3285 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d |  | June 8, 2026 10:00 | June 8, 2026 11:00 | 6/8/26 10:00 | 6/8/26 11:00 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -120.52h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.58.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1338 | 3286 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1334 | June 9, 2026 10:00 | June 9, 2026 11:00 | 6/9/26 10:00 | 6/9/26 11:00 | 5/15/26 3:29 | 5/15/26 4:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 13, 2026 1:15 | April 13, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.58.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1339 | 3287 | Yes | Auto Scheduled | GTS - ECCN - Assign | 0.25d | Fixed Duration | 5 | 0.25d |  | June 15, 2026 3:30 | June 16, 2026 8:30 | 6/15/26 3:30 | 6/16/26 8:30 | 5/13/26 8:14 | 5/13/26 10:14 | 0d | -23.78d | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.59 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1340 | 3288 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 1329 | June 15, 2026 3:30 | June 15, 2026 4:30 | 6/15/26 3:30 | 6/15/26 4:30 | 5/13/26 8:14 | 5/13/26 9:14 | 0h | -190.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.59.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1341 | 3289 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1340 | June 15, 2026 4:30 | June 16, 2026 8:30 | 6/15/26 4:30 | 6/16/26 8:30 | 5/13/26 9:14 | 5/13/26 10:14 | 0h | -190.27h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.59.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1342 | 3290 | Yes | Auto Scheduled | GTS - HTS - Create | 0.25d | Fixed Duration | 5 | 0.25d |  | June 8, 2026 10:00 | June 8, 2026 12:00 | 6/8/26 10:00 | 6/8/26 12:00 | 5/18/26 8:29 | 5/18/26 10:29 | 0d | -15.19d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.60 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1343 | 3291 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d |  | June 8, 2026 10:00 | June 8, 2026 11:00 | 6/8/26 10:00 | 6/8/26 11:00 | 5/18/26 8:29 | 5/18/26 9:29 | 0h | -121.52h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.60.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1344 | 3292 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1343 | June 8, 2026 11:00 | June 8, 2026 12:00 | 6/8/26 11:00 | 6/8/26 12:00 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -121.52h | 0ed | 0 | NA | NA | April 6, 2026 9:15 | April 6, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.60.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1345 | 3293 | Yes | Auto Scheduled | GTS - HTS - Assign | 0.25d | Fixed Duration | 5 | 0.25d |  | June 16, 2026 8:30 | June 16, 2026 10:30 | 6/16/26 8:30 | 6/16/26 10:30 | 5/13/26 10:14 | 5/13/26 1:14 | 0d | -23.78d | 0ed | 0 | NA | NA | April 16, 2026 8:45 | April 16, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.61 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1346 | 3294 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 1341 | June 16, 2026 8:30 | June 16, 2026 9:30 | 6/16/26 8:30 | 6/16/26 9:30 | 5/13/26 10:14 | 5/13/26 11:14 | 0h | -190.27h | 0ed | 0 | NA | NA | April 16, 2026 8:45 | April 16, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.61.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1347 | 3295 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1346 | June 16, 2026 9:30 | June 16, 2026 10:30 | 6/16/26 9:30 | 6/16/26 10:30 | 5/13/26 11:14 | 5/13/26 1:14 | 0h | -190.27h | 0ed | 0 | NA | NA | April 16, 2026 9:45 | April 16, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.61.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1348 | 3296 | Yes | Auto Scheduled | GTS - License - Create | 0.25d | Fixed Duration | 5 | 0.25d |  | June 16, 2026 11:30 | June 16, 2026 2:30 | 6/16/26 11:30 | 6/16/26 2:30 | 5/18/26 8:29 | 5/18/26 10:29 | 0d | -21.38d | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.62 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1349 | 3297 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 1346,1362 | June 16, 2026 11:30 | June 16, 2026 1:30 | 6/16/26 11:30 | 6/16/26 1:30 | 5/18/26 8:29 | 5/18/26 9:29 | 0h | -171.02h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.62.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1350 | 3298 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1349 | June 16, 2026 1:30 | June 16, 2026 2:30 | 6/16/26 1:30 | 6/16/26 2:30 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -171.02h | 0ed | 0 | NA | NA | April 16, 2026 1:45 | April 16, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.62.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1351 | 3299 | Yes | Auto Scheduled | Commodity Code/Tarif | 2.78d | Fixed Duration | 5 | 0.25d |  | June 16, 2026 10:30 | June 19, 2026 8:45 | 6/16/26 10:30 | 6/19/26 8:45 | 5/13/26 1:14 | 5/18/26 10:29 | 0d | -23.78d | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 22.25h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.63 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1352 | 3300 | Yes | Auto Scheduled | Load | 21.25h | Fixed Units | 6 | 0.13d | 1347 | June 16, 2026 10:30 | June 18, 2026 4:45 | 6/16/26 10:30 | 6/18/26 4:45 | 5/13/26 1:14 | 5/18/26 9:29 | 0h | -190.27h | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 21.25h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.63.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1353 | 3301 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1352 | June 18, 2026 4:45 | June 19, 2026 8:45 | 6/18/26 4:45 | 6/19/26 8:45 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -190.27h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.63.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1354 | 3302 | Yes | Auto Scheduled | SPL Master File | 0.25d | Fixed Duration | 5 | 0.25d |  | June 16, 2026 9:30 | June 16, 2026 11:30 | 6/16/26 9:30 | 6/16/26 11:30 | 5/18/26 8:29 | 5/18/26 10:29 | 0d | -21.13d | 0ed | 0 | NA | NA | March 13, 2025 8:00 | March 13, 2025 10:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.64 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1355 | 3303 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1346 | June 16, 2026 9:30 | June 16, 2026 10:30 | 6/16/26 9:30 | 6/16/26 10:30 | 5/18/26 8:29 | 5/18/26 9:29 | 0h | -169.02h | 0ed | 0 | NA | NA | March 13, 2025 8:00 | March 13, 2025 9:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.64.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1356 | 3304 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1355 | June 16, 2026 10:30 | June 16, 2026 11:30 | 6/16/26 10:30 | 6/16/26 11:30 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -169.02h | 0ed | 0 | NA | NA | March 13, 2025 9:00 | March 13, 2025 10:00 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.64.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1357 | 3305 | Yes | Auto Scheduled | Initialize Embargo situation | 0.38d | Fixed Duration | 5 | 0.38d |  | June 9, 2026 11:00 | June 9, 2026 3:00 | 6/9/26 11:00 | 6/9/26 3:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0d | -16.44d | 0ed | 0 | NA | NA | April 13, 2026 2:15 | April 14, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.65 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1358 | 3306 | Yes | Auto Scheduled | Run report /SAPSLL/EMB_CNTRY_INIT | 1h | Fixed Units | 6 | 0.13d | 1338 | June 9, 2026 11:00 | June 9, 2026 12:00 | 6/9/26 11:00 | 6/9/26 12:00 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 13, 2026 2:15 | April 13, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.65.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1359 | 3307 | Yes | Auto Scheduled | Set Embargo situations | 1h | Fixed Units | 6 | 0.13d | 1358 | June 9, 2026 1:00 | June 9, 2026 2:00 | 6/9/26 1:00 | 6/9/26 2:00 | 5/18/26 8:29 | 5/18/26 9:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 13, 2026 3:15 | April 13, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.65.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1360 | 3308 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1359 | June 9, 2026 2:00 | June 9, 2026 3:00 | 6/9/26 2:00 | 6/9/26 3:00 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -131.52h | 0ed | 0 | NA | NA | April 13, 2026 4:15 | April 14, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.65.3 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1361 | 3309 | Yes | Auto Scheduled | GTS - SPL (Sanctioned party list) | 0.25d | Fixed Duration | 5 | 0.25d |  | June 16, 2026 10:30 | June 16, 2026 1:30 | 6/16/26 10:30 | 6/16/26 1:30 | 5/15/26 4:29 | 5/18/26 10:29 | 0d | -21.38d | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.66 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1362 | 3310 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 1347 | June 16, 2026 10:30 | June 16, 2026 11:30 | 6/16/26 10:30 | 6/16/26 11:30 | 5/15/26 4:29 | 5/18/26 8:29 | 0h | -171.02h | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.66.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1363 | 3311 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1362 | June 16, 2026 11:30 | June 16, 2026 1:30 | 6/16/26 11:30 | 6/16/26 1:30 | 5/18/26 9:29 | 5/18/26 10:29 | 0h | -170.02h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.66.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1364 | 3312 | Yes | Auto Scheduled | RTR_CM17_Project Definition / Builder | 1.13d | Fixed Duration | 5 | 5.38d |  | June 8, 2026 10:30 | June 9, 2026 11:30 | 6/8/26 10:30 | 6/9/26 11:30 | 5/15/26 8:59 | 5/18/26 10:29 | 0d | -16.19d | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.67 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1365 | 3313 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1310 | June 8, 2026 10:30 | June 8, 2026 11:00 | 6/8/26 10:30 | 6/8/26 11:00 | 5/15/26 8:59 | 5/15/26 9:29 | 0m | -7771m | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.67.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1366 | 3314 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1365 | June 8, 2026 11:00 | June 8, 2026 11:30 | 6/8/26 11:00 | 6/8/26 11:30 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -7741m | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.67.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1367 | 3315 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1366 | June 8, 2026 11:30 | June 8, 2026 1:30 | 6/8/26 11:30 | 6/8/26 1:30 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -129.02h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 16, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.67.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1368 | 3316 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1367 | June 8, 2026 1:30 | June 8, 2026 3:30 | 6/8/26 1:30 | 6/8/26 3:30 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -129.02h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.67.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1369 | 3317 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1368 | June 8, 2026 3:30 | June 9, 2026 8:30 | 6/8/26 3:30 | 6/9/26 8:30 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -129.02h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.67.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1370 | 3318 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1369 | June 9, 2026 8:30 | June 9, 2026 11:30 | 6/9/26 8:30 | 6/9/26 11:30 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -129.02h | 0ed | 0 | NA | NA | April 17, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.67.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1371 | 3319 | Yes | Auto Scheduled | RTR_CM18_WBS Element | 1.13d | Fixed Duration | 5 | 5.44d |  | June 8, 2026 11:00 | June 9, 2026 12:00 | 6/8/26 11:00 | 6/9/26 12:00 | 5/15/26 9:29 | 5/18/26 10:29 | 0d | -16.19d | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 17, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.68 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1372 | 3320 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1365 | June 8, 2026 11:00 | June 8, 2026 11:30 | 6/8/26 11:00 | 6/8/26 11:30 | 5/15/26 9:29 | 5/15/26 9:59 | 0m | -7771m | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.68.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1373 | 3321 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1372 | June 8, 2026 11:30 | June 8, 2026 12:00 | 6/8/26 11:30 | 6/8/26 12:00 | 5/15/26 9:59 | 5/15/26 10:29 | 0m | -7771m | 0ed | 0 | NA | NA | April 10, 2026 11:15 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.68.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1374 | 3322 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1373 | June 8, 2026 1:00 | June 8, 2026 2:00 | 6/8/26 1:00 | 6/8/26 2:00 | 5/15/26 10:29 | 5/15/26 11:29 | 0h | -129.52h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.68.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1375 | 3323 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1374 | June 8, 2026 2:00 | June 8, 2026 4:00 | 6/8/26 2:00 | 6/8/26 4:00 | 5/15/26 11:29 | 5/15/26 2:29 | 0h | -129.52h | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 17, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.68.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1376 | 3324 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1375 | June 8, 2026 4:00 | June 9, 2026 9:00 | 6/8/26 4:00 | 6/9/26 9:00 | 5/15/26 2:29 | 5/15/26 4:29 | 0h | -129.52h | 0ed | 0 | NA | NA | April 17, 2026 9:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.68.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1377 | 3325 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1376 | June 9, 2026 9:00 | June 9, 2026 12:00 | 6/9/26 9:00 | 6/9/26 12:00 | 5/15/26 4:29 | 5/18/26 10:29 | 0h | -129.52h | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/29/26 1:17 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.2.68.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1378 | 2958 | Yes | Auto Scheduled | ITC3 Master Data Loads Complete | 0m | Fixed Units | 4 | 0d | 1011 | June 19, 2026 4:00 | June 19, 2026 4:00 | 6/19/26 4:00 | 6/19/26 4:00 | 5/18/26 10:29 | 5/18/26 10:29 | 0m | -11791m | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 12:43 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.3 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1379 | 3326 | Yes | Auto Scheduled | Mock Transactional Data | 2d | Fixed Duration | 4 | 0d | 1378 | June 19, 2026 4:00 | June 23, 2026 4:00 | 6/19/26 4:00 | 6/23/26 4:00 | 5/18/26 10:29 | 5/20/26 10:29 | 0d | -24.56d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 2:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.4 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1380 | 3330 | Yes | Auto Scheduled | Inventory | 4h | Fixed Units | 5 | 0d | 998SS | June 19, 2026 4:00 | June 22, 2026 11:00 | 6/19/26 4:00 | 6/22/26 11:00 | 5/18/26 10:29 | 5/18/26 3:29 | 0h | -196.52h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 2:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1381 | 3331 | Yes | Auto Scheduled | Open AR | 4h | Fixed Units | 5 | 0d | 1380 | June 22, 2026 11:00 | June 22, 2026 4:00 | 6/22/26 11:00 | 6/22/26 4:00 | 5/18/26 3:29 | 5/19/26 10:29 | 0h | -196.52h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 2:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1382 | 3332 | Yes | Auto Scheduled | Open AP | 4h | Fixed Units | 5 | 0d | 1381 | June 22, 2026 4:00 | June 23, 2026 11:00 | 6/22/26 4:00 | 6/23/26 11:00 | 5/19/26 10:29 | 5/19/26 3:29 | 0h | -196.52h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 2:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1383 | 3333 | Yes | Auto Scheduled | Bank and Cash | 4h | Fixed Units | 5 | 0d | 1382 | June 23, 2026 11:00 | June 23, 2026 4:00 | 6/23/26 11:00 | 6/23/26 4:00 | 5/19/26 3:29 | 5/20/26 10:29 | 0h | -196.52h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 2:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1384 | 3334 | Yes | Auto Scheduled | Open Purchase Orders(Manual) | 1d | Fixed Units | 5 | 0d | 1380 | June 22, 2026 11:00 | June 23, 2026 11:00 | 6/22/26 11:00 | 6/23/26 11:00 | 5/19/26 10:29 | 5/20/26 10:29 | 0d | -24.06d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 2:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1385 | 3335 | Yes | Auto Scheduled | Open Sales Orders(Manual) | 1d | Fixed Units | 5 | 0d | 1380 | June 22, 2026 11:00 | June 23, 2026 11:00 | 6/22/26 11:00 | 6/23/26 11:00 | 5/19/26 10:29 | 5/20/26 10:29 | 0d | -24.06d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 2:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1386 | 3336 | Yes | Auto Scheduled | Service Orders(Manual) | 0.5d | Fixed Units | 5 | 0d | 1380 | June 22, 2026 11:00 | June 22, 2026 4:00 | 6/22/26 11:00 | 6/22/26 4:00 | 5/19/26 3:29 | 5/20/26 10:29 | 0d | -23.56d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 2:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1387 | 3337 | Yes | Auto Scheduled | Open Production Orders(Manual) | 1d | Fixed Units | 5 | 0d | 1380 | June 22, 2026 11:00 | June 23, 2026 11:00 | 6/22/26 11:00 | 6/23/26 11:00 | 5/19/26 10:29 | 5/20/26 10:29 | 0d | -24.06d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/29/26 2:14 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.4.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1388 | 2421 | Yes | Auto Scheduled | ITC3 Mock Data Loads Complete | 0m | Fixed Units | 4 | 0.03d | 1379 | June 23, 2026 4:00 | June 23, 2026 4:00 | 6/23/26 4:00 | 6/23/26 4:00 | 5/20/26 10:29 | 5/20/26 10:29 | 0m | -11791m | 0ed | 0 | NA | NA | April 21, 2026 3:15 | April 21, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:50 | 0h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.3.5 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1389 | 2422 | Yes | Auto Scheduled | UAT Data Load Tasks QS4 | 80.66d | Fixed Duration | 3 | 288.78d | 1009,103,134 | June 22, 2026 8:00 | October 12, 2026 2:15 | 6/22/26 8:00 | 10/12/26 2:15 | 5/20/26 10:29 | 8/14/26 4:00 | 0d | -40.78d | 0ed | 0 | NA | NA | March 13, 2025 8:00 | April 21, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 708.77h | 592h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1390 | 2423 | Yes | Auto Scheduled | PMO Authorization to Start Data Loads | 1m | Fixed Units | 4 | 0.03d | 103,134 | June 22, 2026 8:00 | June 22, 2026 8:01 | 6/22/26 8:00 | 6/22/26 8:01 | 5/20/26 10:29 | 5/20/26 10:30 | 0m | -32670m | 0ed | 0 | NA | NA | April 6, 2026 8:00 | April 6, 2026 8:15 | Start No Later Than | 6/22/26 8:00 | NA | NA | 4/23/26 10:51 | 0.02h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1391 | 2898 | Yes | Auto Scheduled | Master Data Loads | 10.56d | Fixed Duration | 4 | 0d | 1390 | September 24, 2026 8:30 | October 8, 2026 2:00 | 9/24/26 8:30 | 10/8/26 2:00 | 5/20/26 10:30 | 6/3/26 4:00 | 0d | -90.75d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/24/26 12:51 | 708.5h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1392 | 2424 | Yes | Auto Scheduled | RTR_CM02_Profit Center Hierarchy | 0.75d | Fixed Duration | 5 | 0.75d |  | September 24, 2026 8:30 | September 24, 2026 3:30 | 9/24/26 8:30 | 9/24/26 3:30 | 5/21/26 10:00 | 5/21/26 5:00 | 0d | -89.81d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1393 | 2425 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1390 | September 24, 2026 8:30 | September 24, 2026 9:30 | 9/24/26 8:30 | 9/24/26 9:30 | 5/21/26 10:00 | 5/21/26 11:00 | 0h | -718.5h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 9:15 | Start No Earlier Than | 4/6/26 8:00 | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1394 | 2426 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1393 | September 24, 2026 9:30 | September 24, 2026 11:30 | 9/24/26 9:30 | 9/24/26 11:30 | 5/21/26 11:00 | 5/21/26 2:00 | 0h | -718.5h | 0ed | 0 | NA | NA | April 6, 2026 9:15 | April 6, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1395 | 2427 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1394 | September 24, 2026 11:30 | September 24, 2026 3:30 | 9/24/26 11:30 | 9/24/26 3:30 | 5/21/26 2:00 | 5/21/26 5:00 | 0h | -718.5h | 0ed | 0 | NA | NA | April 6, 2026 11:15 | April 6, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.1.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1396 | 2428 | Yes | Auto Scheduled | RTR_CM03_Cost Center Hierarchy | 0.75d | Fixed Duration | 5 | 0.75d |  | September 24, 2026 3:30 | September 25, 2026 1:30 | 9/24/26 3:30 | 9/25/26 1:30 | 5/22/26 8:00 | 5/22/26 3:00 | 0d | -89.81d | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1397 | 2429 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1395 | September 24, 2026 3:30 | September 24, 2026 4:30 | 9/24/26 3:30 | 9/24/26 4:30 | 5/22/26 8:00 | 5/22/26 9:00 | 0h | -718.5h | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 6, 2026 4:15 | Start No Earlier Than | 4/6/26 8:00 | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1398 | 2430 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1397 | September 24, 2026 4:30 | September 25, 2026 9:30 | 9/24/26 4:30 | 9/25/26 9:30 | 5/22/26 9:00 | 5/22/26 11:00 | 0h | -718.5h | 0ed | 0 | NA | NA | April 6, 2026 4:15 | April 7, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1399 | 2431 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1398 | September 25, 2026 9:30 | September 25, 2026 1:30 | 9/25/26 9:30 | 9/25/26 1:30 | 5/22/26 11:00 | 5/22/26 3:00 | 0h | -718.5h | 0ed | 0 | NA | NA | April 7, 2026 9:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.2.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1400 | 2432 | Yes | Auto Scheduled | RTR_CM01_GL_Account_Master to CC 1000 | 2.44d | Fixed Duration | 5 | 1.81d |  | September 25, 2026 1:30 | September 29, 2026 5:00 | 9/25/26 1:30 | 9/29/26 5:00 | 5/22/26 3:00 | 5/27/26 9:30 | 0d | -89.81d | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 9, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 16h | 16h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1401 | 2433 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1399 | September 25, 2026 1:30 | September 25, 2026 2:30 | 9/25/26 1:30 | 9/25/26 2:30 | 5/22/26 3:00 | 5/22/26 4:00 | 0h | -718.5h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 2:15 | Start No Earlier Than | 4/6/26 8:00 | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1402 | 2434 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1401 | September 25, 2026 2:30 | September 25, 2026 4:30 | 9/25/26 2:30 | 9/25/26 4:30 | 5/22/26 4:00 | 5/25/26 9:00 | 0h | -718.5h | 0ed | 0 | NA | NA | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1403 | 2435 | Yes | Auto Scheduled | Simulate Load | 6h | Fixed Units | 6 | 0.75d | 1402 | September 25, 2026 4:30 | September 28, 2026 2:30 | 9/25/26 4:30 | 9/28/26 2:30 | 5/25/26 9:00 | 5/25/26 4:00 | 0h | -718.5h | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1404 | 2436 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1403 | September 28, 2026 2:30 | September 29, 2026 9:00 | 9/28/26 2:30 | 9/29/26 9:00 | 5/25/26 4:00 | 5/26/26 10:30 | 0h | -718.5h | 0ed | 0 | NA | NA | April 8, 2026 8:15 | April 8, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1405 | 2437 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1404 | September 29, 2026 9:00 | September 29, 2026 10:00 | 9/29/26 9:00 | 9/29/26 10:00 | 5/26/26 10:30 | 5/26/26 11:30 | 0h | -718.5h | 0ed | 0 | NA | NA | April 8, 2026 11:45 | April 8, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1406 | 2438 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1405 | September 29, 2026 10:00 | September 29, 2026 12:00 | 9/29/26 10:00 | 9/29/26 12:00 | 5/26/26 11:30 | 5/26/26 2:30 | 0h | -718.5h | 0ed | 0 | NA | NA | April 8, 2026 1:45 | April 8, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1407 | 2439 | Yes | Auto Scheduled | Extend GL to all Company Codes | 2h | Fixed Units | 6 | 0.25d | 1406 | September 29, 2026 1:00 | September 29, 2026 3:00 | 9/29/26 1:00 | 9/29/26 3:00 | 5/26/26 2:30 | 5/26/26 4:30 | 0h | -718.5h | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1408 | 2440 | Yes | Auto Scheduled | Post GL Extention Validation | 2h | Fixed Units | 6 | 0.25d | 1407 | September 29, 2026 3:00 | September 29, 2026 5:00 | 9/29/26 3:00 | 9/29/26 5:00 | 5/26/26 4:30 | 5/27/26 9:30 | 0h | -718.5h | 0ed | 0 | NA | NA | April 9, 2026 8:45 | April 9, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.3.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1409 | 2441 | Yes | Auto Scheduled | RTR_CM05_Profit_Center | 1.13d | Fixed Duration | 5 | 1.13d |  | September 24, 2026 3:30 | September 25, 2026 4:30 | 9/24/26 3:30 | 9/25/26 4:30 | 5/29/26 8:45 | 6/1/26 9:45 | 0d | -84.72d | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1410 | 2442 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1395 | September 24, 2026 3:30 | September 24, 2026 4:30 | 9/24/26 3:30 | 9/24/26 4:30 | 5/29/26 8:45 | 5/29/26 9:45 | 0h | -677.75h | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 6, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1411 | 2443 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1410 | September 24, 2026 4:30 | September 25, 2026 9:30 | 9/24/26 4:30 | 9/25/26 9:30 | 5/29/26 9:45 | 5/29/26 11:45 | 0h | -677.75h | 0ed | 0 | NA | NA | April 6, 2026 4:15 | April 7, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1412 | 2444 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1411 | September 25, 2026 9:30 | September 25, 2026 10:30 | 9/25/26 9:30 | 9/25/26 10:30 | 5/29/26 11:45 | 5/29/26 1:45 | 0h | -677.75h | 0ed | 0 | NA | NA | April 7, 2026 9:15 | April 7, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1413 | 2445 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1412 | September 25, 2026 10:30 | September 25, 2026 1:30 | 9/25/26 10:30 | 9/25/26 1:30 | 5/29/26 1:45 | 5/29/26 3:45 | 0h | -677.75h | 0ed | 0 | NA | NA | April 7, 2026 10:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1414 | 2446 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1413 | September 25, 2026 1:30 | September 25, 2026 2:30 | 9/25/26 1:30 | 9/25/26 2:30 | 5/29/26 3:45 | 5/29/26 4:45 | 0h | -677.75h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1415 | 2447 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1414 | September 25, 2026 2:30 | September 25, 2026 4:30 | 9/25/26 2:30 | 9/25/26 4:30 | 5/29/26 4:45 | 6/1/26 9:45 | 0h | -677.75h | 0ed | 0 | NA | NA | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.4.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1416 | 2448 | Yes | Auto Scheduled | RTR_CM04_Cost_Center | 1.13d | Fixed Duration | 5 | 1.13d |  | September 25, 2026 4:30 | September 29, 2026 8:30 | 9/25/26 4:30 | 9/29/26 8:30 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -83.19d | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 9, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1417 | 2449 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1415 | September 25, 2026 4:30 | September 28, 2026 8:30 | 9/25/26 4:30 | 9/28/26 8:30 | 6/2/26 3:00 | 6/2/26 4:00 | 0h | -665.5h | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 8, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1418 | 2450 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1417 | September 28, 2026 8:30 | September 28, 2026 10:30 | 9/28/26 8:30 | 9/28/26 10:30 | 6/2/26 4:00 | 6/3/26 9:00 | 0h | -665.5h | 0ed | 0 | NA | NA | April 8, 2026 8:15 | April 8, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1419 | 2451 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1418 | September 28, 2026 10:30 | September 28, 2026 11:30 | 9/28/26 10:30 | 9/28/26 11:30 | 6/3/26 9:00 | 6/3/26 10:00 | 0h | -665.5h | 0ed | 0 | NA | NA | April 8, 2026 10:15 | April 8, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1420 | 2452 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1419 | September 28, 2026 11:30 | September 28, 2026 2:30 | 9/28/26 11:30 | 9/28/26 2:30 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -665.5h | 0ed | 0 | NA | NA | April 8, 2026 11:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1421 | 2453 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1420 | September 28, 2026 2:30 | September 28, 2026 3:30 | 9/28/26 2:30 | 9/28/26 3:30 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -665.5h | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 8, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1422 | 2454 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1421 | September 28, 2026 3:30 | September 29, 2026 8:30 | 9/28/26 3:30 | 9/29/26 8:30 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -665.5h | 0ed | 0 | NA | NA | April 8, 2026 3:15 | April 9, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.5.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1423 | 2455 | Yes | Auto Scheduled | Manual Configuration Activities in QS5 | 8.94d | Fixed Duration | 5 | 7.16d | 40 | September 24, 2026 8:30 | October 6, 2026 5:00 | 9/24/26 8:30 | 10/6/26 5:00 | 5/27/26 4:00 | 6/3/26 4:00 | 0d | -89.13d | 0ed | 0 | NA | NA | April 6, 2026 1:00 | April 15, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 43h | 43h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.6 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1424 | 2456 | Yes | Auto Scheduled | Open Client | 30m | Fixed Units | 6 | 0.06d |  | September 24, 2026 8:30 | September 24, 2026 9:00 | 9/24/26 8:30 | 9/24/26 9:00 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -38520m | 0ed | 0 | NA | NA | April 6, 2026 1:00 | April 6, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.6.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1425 | 2457 | Yes | Auto Scheduled | Service Enterprise Setup | 5d | Fixed Units | 6 | 5d | 1392,1396,1400 | September 30, 2026 8:00 | October 6, 2026 5:00 | 9/30/26 8:00 | 10/6/26 5:00 | 5/27/26 4:00 | 6/3/26 4:00 | 0d | -89.13d | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 15, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 40h | 40h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.6.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1426 | 2458 | Yes | Auto Scheduled | Close Client | 30m | Fixed Units | 6 | 0.06d |  | September 24, 2026 8:30 | September 24, 2026 9:00 | 9/24/26 8:30 | 9/24/26 9:00 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -38520m | 0ed | 0 | NA | NA | April 6, 2026 1:00 | April 6, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.6.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1427 | 2459 | Yes | Auto Scheduled | Intercompany Business Partner Setup | 2h | Fixed Units | 6 | 0.25d | 1392,1396,1408 | September 30, 2026 8:00 | September 30, 2026 10:00 | 9/30/26 8:00 | 9/30/26 10:00 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -675h | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.6.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1428 | 2460 | Yes | Auto Scheduled | RTR_CM09_Activity_Type | 1.38d | Fixed Duration | 5 | 1.22d |  | September 29, 2026 1:00 | September 30, 2026 4:00 | 9/29/26 1:00 | 9/30/26 4:00 | 6/2/26 1:00 | 6/3/26 4:00 | 0d | -85d | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.7 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1429 | 2461 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1406 | September 29, 2026 1:00 | September 29, 2026 3:15 | 9/29/26 1:00 | 9/29/26 3:15 | 6/2/26 1:00 | 6/2/26 3:15 | 0h | -680h | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 8, 2026 4:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.7.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1430 | 2462 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1429 | September 29, 2026 3:15 | September 30, 2026 9:00 | 9/29/26 3:15 | 9/30/26 9:00 | 6/2/26 3:15 | 6/3/26 9:00 | 0h | -680h | 0ed | 0 | NA | NA | April 8, 2026 3:15 | April 9, 2026 9:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.7.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1431 | 2463 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1430 | September 30, 2026 9:00 | September 30, 2026 10:00 | 9/30/26 9:00 | 9/30/26 10:00 | 6/3/26 9:00 | 6/3/26 10:00 | 0h | -680h | 0ed | 0 | NA | NA | April 9, 2026 9:00 | April 9, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.7.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1432 | 2464 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1431 | September 30, 2026 10:00 | September 30, 2026 12:00 | 9/30/26 10:00 | 9/30/26 12:00 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -680h | 0ed | 0 | NA | NA | April 9, 2026 10:00 | April 9, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.7.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1433 | 2465 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1432 | September 30, 2026 1:00 | September 30, 2026 2:00 | 9/30/26 1:00 | 9/30/26 2:00 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -680h | 0ed | 0 | NA | NA | April 9, 2026 1:00 | April 9, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.7.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1434 | 2466 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1433 | September 30, 2026 2:00 | September 30, 2026 4:00 | 9/30/26 2:00 | 9/30/26 4:00 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -680h | 0ed | 0 | NA | NA | April 9, 2026 2:00 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.7.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1435 | 2467 | Yes | Auto Scheduled | RTR_CM12_Activity Rates | 1.13d | Fixed Duration | 5 | 1.13d |  | September 25, 2026 1:30 | September 28, 2026 2:30 | 9/25/26 1:30 | 9/28/26 2:30 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -82.81d | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.8 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1436 | 2468 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1399 | September 25, 2026 1:30 | September 25, 2026 2:30 | 9/25/26 1:30 | 9/25/26 2:30 | 6/2/26 3:00 | 6/2/26 4:00 | 0h | -662.5h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.8.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1437 | 2469 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1436 | September 25, 2026 2:30 | September 25, 2026 4:30 | 9/25/26 2:30 | 9/25/26 4:30 | 6/2/26 4:00 | 6/3/26 9:00 | 0h | -662.5h | 0ed | 0 | NA | NA | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.8.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1438 | 2470 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1437 | September 25, 2026 4:30 | September 28, 2026 8:30 | 9/25/26 4:30 | 9/28/26 8:30 | 6/3/26 9:00 | 6/3/26 10:00 | 0h | -662.5h | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 8, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.8.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1439 | 2471 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1438 | September 28, 2026 8:30 | September 28, 2026 10:30 | 9/28/26 8:30 | 9/28/26 10:30 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -662.5h | 0ed | 0 | NA | NA | April 8, 2026 8:15 | April 8, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.8.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1440 | 2472 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1439 | September 28, 2026 10:30 | September 28, 2026 11:30 | 9/28/26 10:30 | 9/28/26 11:30 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -662.5h | 0ed | 0 | NA | NA | April 8, 2026 10:15 | April 8, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.8.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1441 | 2473 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1440 | September 28, 2026 11:30 | September 28, 2026 2:30 | 9/28/26 11:30 | 9/28/26 2:30 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -662.5h | 0ed | 0 | NA | NA | April 8, 2026 11:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.8.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1442 | 2474 | Yes | Auto Scheduled | RTR_CM06_Bank_master | 3.81d | Fixed Duration | 5 | 1.22d |  | September 24, 2026 8:30 | September 29, 2026 4:00 | 9/24/26 8:30 | 9/29/26 4:00 | 5/26/26 3:00 | 6/3/26 4:00 | 0d | -86.31d | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 13h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.9 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1443 | 2475 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1406 | September 29, 2026 1:00 | September 29, 2026 2:00 | 9/29/26 1:00 | 9/29/26 2:00 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -672h | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 8, 2026 4:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.9.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1444 | 2476 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1443 | September 29, 2026 2:00 | September 29, 2026 4:00 | 9/29/26 2:00 | 9/29/26 4:00 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -672h | 0ed | 0 | NA | NA | April 8, 2026 4:30 | April 9, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.9.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1445 | 2477 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d |  | September 24, 2026 8:30 | September 24, 2026 9:30 | 9/24/26 8:30 | 9/24/26 9:30 | 5/26/26 3:00 | 5/26/26 4:00 | 0h | -690.5h | 0ed | 0 | NA | NA | April 9, 2026 9:30 | April 9, 2026 10:30 | Start No Earlier Than | 4/15/26 8:00 | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.9.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1446 | 2478 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1445 | September 24, 2026 9:30 | September 24, 2026 11:30 | 9/24/26 9:30 | 9/24/26 11:30 | 5/26/26 4:00 | 5/27/26 9:00 | 0h | -690.5h | 0ed | 0 | NA | NA | April 9, 2026 10:30 | April 9, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.9.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1447 | 2479 | Yes | Auto Scheduled | Load | 5h | Fixed Units | 6 | 0.13d | 1446 | September 24, 2026 11:30 | September 25, 2026 8:30 | 9/24/26 11:30 | 9/25/26 8:30 | 5/27/26 9:00 | 5/27/26 3:00 | 0h | -690.5h | 0ed | 0 | NA | NA | April 9, 2026 1:30 | April 9, 2026 2:30 | Finish No Earlier Than | 4/15/26 5:00 | NA | NA | 4/23/26 10:51 | 5h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.9.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1448 | 2480 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1447 | September 25, 2026 8:30 | September 25, 2026 3:00 | 9/25/26 8:30 | 9/25/26 3:00 | 5/27/26 3:00 | 5/28/26 11:30 | 0h | -690.5h | 0ed | 0 | NA | NA | April 9, 2026 8:00 | April 9, 2026 4:00 | Finish No Earlier Than | 4/14/26 5:00 | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.9.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1449 | 2481 | Yes | Auto Scheduled | RTR_CM08_Exchange_Rates | 1.13d | Fixed Duration | 5 | 1.13d |  | September 25, 2026 8:30 | September 28, 2026 9:30 | 9/25/26 8:30 | 9/28/26 9:30 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -82.31d | 0ed | 0 | NA | NA | April 9, 2026 2:30 | April 10, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.10 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1450 | 2482 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1447 | September 25, 2026 8:30 | September 25, 2026 9:30 | 9/25/26 8:30 | 9/25/26 9:30 | 6/2/26 3:00 | 6/2/26 4:00 | 0h | -658.5h | 0ed | 0 | NA | NA | April 9, 2026 2:30 | April 9, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.10.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1451 | 2483 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1450 | September 25, 2026 9:30 | September 25, 2026 11:30 | 9/25/26 9:30 | 9/25/26 11:30 | 6/2/26 4:00 | 6/3/26 9:00 | 0h | -658.5h | 0ed | 0 | NA | NA | April 9, 2026 3:30 | April 10, 2026 8:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.10.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1452 | 2484 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1451 | September 25, 2026 11:30 | September 25, 2026 1:30 | 9/25/26 11:30 | 9/25/26 1:30 | 6/3/26 9:00 | 6/3/26 10:00 | 0h | -658.5h | 0ed | 0 | NA | NA | April 10, 2026 8:30 | April 10, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.10.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1453 | 2485 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1452 | September 25, 2026 1:30 | September 25, 2026 3:30 | 9/25/26 1:30 | 9/25/26 3:30 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -658.5h | 0ed | 0 | NA | NA | April 10, 2026 9:30 | April 10, 2026 11:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.10.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1454 | 2486 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1453 | September 25, 2026 3:30 | September 25, 2026 4:30 | 9/25/26 3:30 | 9/25/26 4:30 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -658.5h | 0ed | 0 | NA | NA | April 10, 2026 11:30 | April 10, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.10.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1455 | 2487 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1454 | September 25, 2026 4:30 | September 28, 2026 9:30 | 9/25/26 4:30 | 9/28/26 9:30 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -658.5h | 0ed | 0 | NA | NA | April 10, 2026 1:30 | April 10, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.10.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1456 | 2488 | Yes | Auto Scheduled | RTR_CM14_Cost Element_Group | 4.44d | Fixed Duration | 5 | 4.78d |  | September 29, 2026 1:00 | October 5, 2026 4:30 | 9/29/26 1:00 | 10/5/26 4:30 | 5/28/26 11:30 | 6/3/26 4:00 | 0d | -88.06d | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 35.5h | 38.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.11 | 500 | No | Yes | Yes |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1457 | 2489 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 4.16d | 1406 | September 29, 2026 1:00 | September 29, 2026 1:30 | 9/29/26 1:00 | 9/29/26 1:30 | 5/28/26 11:30 | 5/28/26 12:00 | 0m | -42270m | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 14, 2026 5:00 | Finish No Earlier Than | 4/14/26 5:00 | NA | NA | 4/23/26 10:51 | 0.5h | 33.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.11.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1458 | 2490 | Yes | Auto Scheduled | Load | 32h | Fixed Units | 6 | 0.25d | 1457 | September 29, 2026 1:30 | October 5, 2026 1:30 | 9/29/26 1:30 | 10/5/26 1:30 | 5/28/26 1:00 | 6/3/26 12:00 | 0h | -704.5h | 0ed | 0 | NA | NA | April 15, 2026 8:00 | April 15, 2026 10:00 | Finish No Earlier Than | 4/21/26 5:00 | NA | NA | 4/23/26 10:51 | 32h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.11.2 | 500 | No | No | No |  |  | Black | 2026-04-20 15:36 - jsw73 - Start ignored — already in progress | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1459 | 2491 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1458 | October 5, 2026 1:30 | October 5, 2026 4:30 | 10/5/26 1:30 | 10/5/26 4:30 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -704.5h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 2:00 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.11.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1460 | 2492 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Bill-To | 2h | Fixed Units | 5 | 0d |  | September 24, 2026 8:30 | September 24, 2026 10:30 | 9/24/26 8:30 | 9/24/26 10:30 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -643.5h | 0ed | 0 | NA | NA | April 16, 2025 8:00 | April 16, 2025 8:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.12 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1461 | 2493 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Ship-To | 1.5d | Fixed Duration | 5 | 3.13d |  | September 29, 2026 1:00 | September 30, 2026 5:00 | 9/29/26 1:00 | 9/30/26 5:00 | 5/26/26 4:30 | 6/3/26 4:00 | 0d | -89.56d | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 13.25h | 36h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.13 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1462 | 2494 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1406 | September 29, 2026 1:00 | September 29, 2026 1:30 | 9/29/26 1:00 | 9/29/26 1:30 | 5/26/26 4:30 | 5/26/26 5:00 | 0m | -42990m | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 8, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.13.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1463 | 2495 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1462 | September 29, 2026 1:30 | September 29, 2026 2:00 | 9/29/26 1:30 | 9/29/26 2:00 | 5/27/26 8:00 | 5/27/26 8:30 | 0m | -42990m | 0ed | 0 | NA | NA | April 8, 2026 4:15 | April 8, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.13.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1464 | 2496 | Yes | Auto Scheduled | Open client for BP number range update | 30m | Fixed Units | 6 | 1d | 1463 | September 29, 2026 2:00 | September 29, 2026 2:30 | 9/29/26 2:00 | 9/29/26 2:30 | 6/3/26 2:45 | 6/3/26 3:15 | 0m | -40275m | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 9, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.13.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1465 | 2497 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 30m | Fixed Units | 6 | 1d | 1464 | September 29, 2026 2:30 | September 29, 2026 3:00 | 9/29/26 2:30 | 9/29/26 3:00 | 6/3/26 3:15 | 6/3/26 3:45 | 0m | -40275m | 0ed | 0 | NA | NA | April 9, 2026 4:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.13.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1466 | 2498 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 6 | 1d | 1465 | September 29, 2026 3:00 | September 29, 2026 3:15 | 9/29/26 3:00 | 9/29/26 3:15 | 6/3/26 3:45 | 6/3/26 4:00 | 0m | -40275m | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.25h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.13.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1467 | 2499 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1463 | September 29, 2026 2:00 | September 29, 2026 3:00 | 9/29/26 2:00 | 9/29/26 3:00 | 5/27/26 8:30 | 5/27/26 9:30 | 0h | -716.5h | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.13.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1468 | 2500 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | Fixed Units | 6 | 0.5d | 1467 | September 29, 2026 3:00 | September 30, 2026 10:00 | 9/29/26 3:00 | 9/30/26 10:00 | 6/2/26 2:00 | 6/3/26 9:00 | 0h | -681h | 0ed | 0 | NA | NA | April 9, 2026 8:45 | April 9, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.13.7 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1469 | 2501 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 6 | 0.38d | 1468 | September 30, 2026 10:00 | September 30, 2026 2:00 | 9/30/26 10:00 | 9/30/26 2:00 | 6/3/26 9:00 | 6/3/26 12:00 | 0h | -681h | 0ed | 0 | NA | NA | April 9, 2026 1:45 | April 9, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.13.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1470 | 2502 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1469 | September 30, 2026 2:00 | September 30, 2026 5:00 | 9/30/26 2:00 | 9/30/26 5:00 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -681h | 0ed | 0 | NA | NA | April 9, 2026 4:45 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.13.9 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1471 | 2503 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Sold-To | 1.63d | Fixed Duration | 5 | 1.63d |  | September 29, 2026 2:00 | October 1, 2026 10:00 | 9/29/26 2:00 | 10/1/26 10:00 | 5/27/26 9:30 | 6/3/26 4:00 | 0d | -89.44d | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 11.75h | 11.75h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.14 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1472 | 2504 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1463 | September 29, 2026 2:00 | September 29, 2026 2:30 | 9/29/26 2:00 | 9/29/26 2:30 | 6/3/26 3:00 | 6/3/26 3:30 | 0m | -40260m | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 9, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.14.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1473 | 2505 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1472 | September 29, 2026 2:30 | September 29, 2026 3:00 | 9/29/26 2:30 | 9/29/26 3:00 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -40260m | 0ed | 0 | NA | NA | April 9, 2026 8:15 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.14.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1474 | 2506 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1408,1467 | September 30, 2026 8:00 | September 30, 2026 9:00 | 9/30/26 8:00 | 9/30/26 9:00 | 5/27/26 9:30 | 5/27/26 10:30 | 0h | -718.5h | 0ed | 0 | NA | NA | April 9, 2026 10:45 | April 9, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.14.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1475 | 2507 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | Fixed Units | 6 | 0.38d | 1474 | September 30, 2026 9:00 | September 30, 2026 12:00 | 9/30/26 9:00 | 9/30/26 12:00 | 5/27/26 10:30 | 5/27/26 2:30 | 0h | -718.5h | 0ed | 0 | NA | NA | April 9, 2026 11:45 | April 9, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.14.4 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1476 | 2508 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 6 | 0.38d | 1475 | September 30, 2026 1:00 | September 30, 2026 4:00 | 9/30/26 1:00 | 9/30/26 4:00 | 5/27/26 2:30 | 5/28/26 8:30 | 0h | -718.5h | 0ed | 0 | NA | NA | April 9, 2026 3:45 | April 10, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.14.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1477 | 2509 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1476 | September 30, 2026 4:00 | October 1, 2026 10:00 | 9/30/26 4:00 | 10/1/26 10:00 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -683h | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.14.6 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1478 | 2510 | Yes | Auto Scheduled | Open client for BP number range update | 15m | Fixed Units | 6 | 0.03d | 1467 | September 29, 2026 3:00 | September 29, 2026 3:15 | 9/29/26 3:00 | 9/29/26 3:15 | 6/3/26 3:15 | 6/3/26 3:30 | 0m | -40305m | 0ed | 0 | NA | NA | April 9, 2026 8:45 | April 9, 2026 9:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.14.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1479 | 2511 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 15m | Fixed Units | 6 | 0.03d | 1478 | September 29, 2026 3:15 | September 29, 2026 3:30 | 9/29/26 3:15 | 9/29/26 3:30 | 6/3/26 3:30 | 6/3/26 3:45 | 0m | -40305m | 0ed | 0 | NA | NA | April 9, 2026 9:00 | April 9, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.14.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1480 | 2512 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 6 | 0.03d | 1479 | September 29, 2026 3:30 | September 29, 2026 3:45 | 9/29/26 3:30 | 9/29/26 3:45 | 6/3/26 3:45 | 6/3/26 4:00 | 0m | -40305m | 0ed | 0 | NA | NA | April 9, 2026 9:15 | April 9, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.14.9 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1481 | 2513 | Yes | Auto Scheduled | PTP_CM27_Vendor Master as Customer - FLCU01 | 4.81d | Fixed Duration | 5 | 2.31d |  | September 30, 2026 4:00 | October 7, 2026 2:30 | 9/30/26 4:00 | 10/7/26 2:30 | 5/28/26 8:30 | 6/3/26 4:00 | 0d | -89.81d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 14, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 19.25h | 19.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.15 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1482 | 2514 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1476 | September 30, 2026 4:00 | September 30, 2026 5:00 | 9/30/26 4:00 | 9/30/26 5:00 | 5/28/26 8:30 | 5/28/26 9:30 | 0h | -718.5h | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.15.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1483 | 2515 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1482 | October 1, 2026 8:00 | October 1, 2026 10:00 | 10/1/26 8:00 | 10/1/26 10:00 | 5/28/26 9:30 | 5/28/26 11:30 | 0h | -718.5h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.15.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1484 | 2516 | Yes | Auto Scheduled | Simulate Load | 11.25h | Fixed Units | 6 | 1.41d | 1448,1483 | October 1, 2026 10:00 | October 2, 2026 2:15 | 10/1/26 10:00 | 10/2/26 2:15 | 5/28/26 11:30 | 5/29/26 3:45 | 0h | -718.5h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 13, 2026 5:00 | Finish No Earlier Than | 4/13/26 5:00 | NA | NA | 4/23/26 10:51 | 11.25h | 11.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.15.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1485 | 2517 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1484 | October 2, 2026 2:15 | October 6, 2026 9:00 | 10/2/26 2:15 | 10/6/26 9:00 | 5/29/26 3:45 | 6/2/26 10:30 | 0h | -718.5h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 14, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.15.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1486 | 2518 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1485 | October 6, 2026 9:00 | October 7, 2026 11:30 | 10/6/26 9:00 | 10/7/26 11:30 | 6/2/26 10:30 | 6/3/26 2:00 | 0h | -718.5h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 14, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.15.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1487 | 2519 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1486 | October 7, 2026 11:30 | October 7, 2026 2:30 | 10/7/26 11:30 | 10/7/26 2:30 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -718.5h | 0ed | 0 | NA | NA | April 14, 2026 10:15 | April 14, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.15.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1488 | 2520 | Yes | Auto Scheduled | OTC_CM23_Customer_Hierarchy | 0.69d | Fixed Duration | 5 | 0.69d |  | September 30, 2026 4:00 | October 1, 2026 1:30 | 9/30/26 4:00 | 10/1/26 1:30 | 6/3/26 9:30 | 6/3/26 4:00 | 0d | -85.69d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.16 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1489 | 2521 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1476 | September 30, 2026 4:00 | September 30, 2026 4:30 | 9/30/26 4:00 | 9/30/26 4:30 | 6/3/26 9:30 | 6/3/26 10:00 | 0m | -41130m | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:15 | Start No Earlier Than | 4/6/26 8:00 | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.16.1 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1490 | 2522 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1489 | September 30, 2026 4:30 | October 1, 2026 9:30 | 9/30/26 4:30 | 10/1/26 9:30 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -685.5h | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 1:15 | Start No Earlier Than | 4/15/26 8:00 | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.16.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1491 | 2523 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1490 | October 1, 2026 9:30 | October 1, 2026 1:30 | 10/1/26 9:30 | 10/1/26 1:30 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -685.5h | 0ed | 0 | NA | NA | April 10, 2026 1:15 | April 10, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.16.3 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1492 | 2524 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Z001 - External Sales Rep | 3.38d | Fixed Duration | 5 | 1.13d |  | September 30, 2026 4:00 | October 6, 2026 10:00 | 9/30/26 4:00 | 10/6/26 10:00 | 5/29/26 1:00 | 6/3/26 4:00 | 0d | -88.38d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.17 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1493 | 2525 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1476 | September 30, 2026 4:00 | September 30, 2026 5:00 | 9/30/26 4:00 | 9/30/26 5:00 | 5/29/26 1:00 | 5/29/26 2:00 | 0h | -707h | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.17.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1494 | 2526 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1493 | October 1, 2026 8:00 | October 1, 2026 10:00 | 10/1/26 8:00 | 10/1/26 10:00 | 5/29/26 2:00 | 5/29/26 4:00 | 0h | -707h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.17.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1495 | 2527 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1448,1494 | October 1, 2026 10:00 | October 1, 2026 11:00 | 10/1/26 10:00 | 10/1/26 11:00 | 5/29/26 4:00 | 5/29/26 5:00 | 0h | -707h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.17.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1496 | 2528 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1495 | October 1, 2026 11:00 | October 1, 2026 2:00 | 10/1/26 11:00 | 10/1/26 2:00 | 6/1/26 8:00 | 6/1/26 10:00 | 0h | -707h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.17.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1497 | 2529 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1496 | October 1, 2026 2:00 | October 5, 2026 5:00 | 10/1/26 2:00 | 10/5/26 5:00 | 6/1/26 10:00 | 6/3/26 2:00 | 0h | -707h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.17.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1498 | 2530 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1497 | October 6, 2026 8:00 | October 6, 2026 10:00 | 10/6/26 8:00 | 10/6/26 10:00 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -707h | 0ed | 0 | NA | NA | April 13, 2026 8:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.17.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1499 | 2531 | Yes | Auto Scheduled | RTR_CM10_Credit_Management_Role | 1.84d | Fixed Duration | 5 | 1.13d |  | September 30, 2026 4:00 | October 2, 2026 2:45 | 9/30/26 4:00 | 10/2/26 2:45 | 6/1/26 10:15 | 6/3/26 9:00 | 0d | -87.59d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.18 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1500 | 2532 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1476 | September 30, 2026 4:00 | September 30, 2026 4:30 | 9/30/26 4:00 | 9/30/26 4:30 | 6/1/26 10:15 | 6/1/26 10:45 | 0m | -42045m | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.18.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1501 | 2533 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1500 | September 30, 2026 4:30 | September 30, 2026 5:00 | 9/30/26 4:30 | 9/30/26 5:00 | 6/1/26 10:45 | 6/1/26 11:15 | 0m | -42045m | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.18.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1502 | 2534 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1501 | October 1, 2026 8:00 | October 1, 2026 9:00 | 10/1/26 8:00 | 10/1/26 9:00 | 6/1/26 11:15 | 6/1/26 1:15 | 0h | -700.75h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.18.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1503 | 2535 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1502 | October 1, 2026 9:00 | October 1, 2026 11:30 | 10/1/26 9:00 | 10/1/26 11:30 | 6/1/26 1:15 | 6/1/26 3:45 | 0h | -700.75h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.18.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1504 | 2536 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1503 | October 1, 2026 11:30 | October 1, 2026 4:30 | 10/1/26 11:30 | 10/1/26 4:30 | 6/1/26 3:45 | 6/2/26 10:45 | 0h | -700.75h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.18.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1505 | 2537 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1504 | October 1, 2026 4:30 | October 2, 2026 2:45 | 10/1/26 4:30 | 10/2/26 2:45 | 6/2/26 10:45 | 6/3/26 9:00 | 0h | -700.75h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.18.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1506 | 2538 | Yes | Auto Scheduled | PTP_CM27_Vendor Master | 6.28d | Fixed Duration | 5 | 2.91d |  | September 24, 2026 8:30 | October 2, 2026 10:45 | 9/24/26 8:30 | 10/2/26 10:45 | 5/20/26 10:30 | 6/3/26 4:00 | 0d | -90.75d | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 10.25h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.19 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1507 | 2539 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1493 | October 1, 2026 8:00 | October 1, 2026 9:00 | 10/1/26 8:00 | 10/1/26 9:00 | 6/2/26 1:15 | 6/2/26 2:15 | 0h | -691.75h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.19.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1508 | 2540 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1507 | October 1, 2026 9:00 | October 1, 2026 11:00 | 10/1/26 9:00 | 10/1/26 11:00 | 6/2/26 2:15 | 6/2/26 4:15 | 0h | -691.75h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.19.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1509 | 2541 | Yes | Auto Scheduled | Simulate Load | 2.25h | Fixed Units | 6 | 0.13d | 1508 | October 1, 2026 11:00 | October 1, 2026 2:15 | 10/1/26 11:00 | 10/1/26 2:15 | 6/2/26 4:15 | 6/3/26 9:30 | 0h | -691.75h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 14, 2026 2:00 | Finish No Earlier Than | 4/10/26 5:00 | NA | NA | 4/23/26 10:51 | 2.25h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.19.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1510 | 2542 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1509 | October 1, 2026 2:15 | October 2, 2026 10:45 | 10/1/26 2:15 | 10/2/26 10:45 | 6/3/26 9:30 | 6/3/26 4:00 | 0h | -691.75h | 0ed | 0 | NA | NA | April 14, 2026 2:00 | April 14, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.19.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1511 | 2543 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d |  | September 24, 2026 8:30 | September 24, 2026 9:30 | 9/24/26 8:30 | 9/24/26 9:30 | 5/20/26 10:30 | 5/20/26 11:30 | 0h | -726h | 0ed | 0 | NA | NA | April 14, 2026 4:00 | April 14, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.19.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1512 | 2544 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1511 | September 24, 2026 9:30 | September 24, 2026 11:30 | 9/24/26 9:30 | 9/24/26 11:30 | 5/20/26 11:30 | 5/20/26 2:30 | 0h | -726h | 0ed | 0 | NA | NA | April 15, 2026 8:00 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.19.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1513 | 2545 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | 0.88d | Fixed Duration | 5 | 3.16d |  | September 24, 2026 8:30 | September 24, 2026 4:30 | 9/24/26 8:30 | 9/24/26 4:30 | 6/2/26 11:00 | 6/3/26 4:00 | 0d | -81.69d | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.20 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1514 | 2546 | Yes | Auto Scheduled | Extract File(Will Extract from LFA1) | 1h | Fixed Units | 6 | 0.13d |  | September 24, 2026 8:30 | September 24, 2026 9:30 | 9/24/26 8:30 | 9/24/26 9:30 | 6/2/26 11:00 | 6/2/26 12:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 1:45 | Start No Earlier Than | 4/16/26 8:00 | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.20.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1515 | 2547 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1514 | September 24, 2026 9:30 | September 24, 2026 11:30 | 9/24/26 9:30 | 9/24/26 11:30 | 6/2/26 1:00 | 6/2/26 3:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.20.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1516 | 2548 | Yes | Auto Scheduled | Simulate Load/ Not Needed | 1h | Fixed Units | 6 | 0.13d | 1515 | September 24, 2026 11:30 | September 24, 2026 1:30 | 9/24/26 11:30 | 9/24/26 1:30 | 6/2/26 3:00 | 6/2/26 4:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 10, 2026 3:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.20.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1517 | 2549 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1516 | September 24, 2026 1:30 | September 24, 2026 3:30 | 9/24/26 1:30 | 9/24/26 3:30 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -647.5h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.20.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1518 | 2550 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1516 | September 24, 2026 1:30 | September 24, 2026 2:30 | 9/24/26 1:30 | 9/24/26 2:30 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 11:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.20.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1519 | 2551 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1518 | September 24, 2026 2:30 | September 24, 2026 4:30 | 9/24/26 2:30 | 9/24/26 4:30 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 15, 2026 11:00 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.20.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1520 | 2552 | Yes | Auto Scheduled | RTR_****_Credit Hierarchy | 1.91d | Fixed Duration | 5 | 1.25d |  | October 1, 2026 11:30 | October 5, 2026 10:45 | 10/1/26 11:30 | 10/5/26 10:45 | 6/3/26 10:00 | 6/3/26 4:00 | 0d | -87.47d | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.21 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1521 | 2553 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1503 | October 1, 2026 11:30 | October 1, 2026 12:00 | 10/1/26 11:30 | 10/1/26 12:00 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -41100m | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 3:15 | Start No Earlier Than | 4/15/26 8:00 | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.21.1 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1522 | 2554 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1505 | October 2, 2026 2:45 | October 2, 2026 4:45 | 10/2/26 2:45 | 10/2/26 4:45 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -699.75h | 0ed | 0 | NA | NA | April 13, 2026 10:45 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.21.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1523 | 2555 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1522 | October 2, 2026 4:45 | October 5, 2026 10:45 | 10/2/26 4:45 | 10/5/26 10:45 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -699.75h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.21.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1524 | 2556 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Supplier | 1.13d | Fixed Duration | 5 | 1.13d |  | September 24, 2026 11:30 | September 25, 2026 1:30 | 9/24/26 11:30 | 9/25/26 1:30 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -81.69d | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 15h | 15h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.22 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1525 | 2557 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1512 | September 24, 2026 11:30 | September 24, 2026 12:00 | 9/24/26 11:30 | 9/24/26 12:00 | 6/2/26 3:00 | 6/2/26 3:30 | 0m | -39210m | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 13, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.22.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1526 | 2558 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1525 | September 24, 2026 1:00 | September 24, 2026 1:30 | 9/24/26 1:00 | 9/24/26 1:30 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -39210m | 0ed | 0 | NA | NA | April 13, 2026 1:15 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.22.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1527 | 2559 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1526 | September 24, 2026 1:30 | September 24, 2026 2:30 | 9/24/26 1:30 | 9/24/26 2:30 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.22.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1528 | 2560 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1527 | September 24, 2026 2:30 | September 24, 2026 4:30 | 9/24/26 2:30 | 9/24/26 4:30 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 13, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.22.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1529 | 2561 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1528 | September 24, 2026 4:30 | September 25, 2026 9:30 | 9/24/26 4:30 | 9/25/26 9:30 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 13, 2026 4:45 | April 14, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.22.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1530 | 2562 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1529 | September 25, 2026 9:30 | September 25, 2026 1:30 | 9/25/26 9:30 | 9/25/26 1:30 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 14, 2026 9:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.22.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1531 | 2563 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Customer | 1.06d | Fixed Duration | 5 | 1.13d |  | September 24, 2026 8:30 | September 25, 2026 9:00 | 9/24/26 8:30 | 9/25/26 9:00 | 6/2/26 3:30 | 6/3/26 4:00 | 0d | -81.25d | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 15h | 15h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.23 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1532 | 2564 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d |  | September 24, 2026 8:30 | September 24, 2026 9:00 | 9/24/26 8:30 | 9/24/26 9:00 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -38520m | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 13, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.23.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1533 | 2565 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d |  | September 24, 2026 8:30 | September 24, 2026 9:00 | 9/24/26 8:30 | 9/24/26 9:00 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -39000m | 0ed | 0 | NA | NA | April 13, 2026 1:15 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.23.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1534 | 2566 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1533 | September 24, 2026 9:00 | September 24, 2026 10:00 | 9/24/26 9:00 | 9/24/26 10:00 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -650h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.23.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1535 | 2567 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1534 | September 24, 2026 10:00 | September 24, 2026 12:00 | 9/24/26 10:00 | 9/24/26 12:00 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -650h | 0ed | 0 | NA | NA | April 13, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.23.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1536 | 2568 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1535 | September 24, 2026 1:00 | September 24, 2026 3:00 | 9/24/26 1:00 | 9/24/26 3:00 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -650h | 0ed | 0 | NA | NA | April 13, 2026 4:45 | April 14, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.23.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1537 | 2569 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1536 | September 24, 2026 3:00 | September 25, 2026 9:00 | 9/24/26 3:00 | 9/25/26 9:00 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -650h | 0ed | 0 | NA | NA | April 14, 2026 9:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.23.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1538 | 2570 | Yes | Auto Scheduled | PTP_CM26_Material_Master - All Types | 2.28d | Fixed Duration | 5 | 3.16d |  | September 24, 2026 9:30 | September 28, 2026 11:45 | 9/24/26 9:30 | 9/28/26 11:45 | 5/20/26 2:30 | 6/3/26 4:00 | 0d | -90.5d | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 15, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 19h | 19h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.24 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1539 | 2571 | Yes | Auto Scheduled | Extract File | 5h | Fixed Units | 6 | 0.63d | 1514 | September 24, 2026 9:30 | September 25, 2026 8:15 | 9/24/26 9:30 | 9/25/26 8:15 | 6/3/26 8:15 | 6/3/26 4:00 | 0h | -649.25h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 13, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.24.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1540 | 2572 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1512 | September 24, 2026 11:30 | September 25, 2026 9:45 | 9/24/26 11:30 | 9/25/26 9:45 | 5/20/26 2:30 | 5/21/26 11:45 | 0h | -726h | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 14, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.24.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1541 | 2573 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1540 | September 25, 2026 9:45 | September 25, 2026 10:45 | 9/25/26 9:45 | 9/25/26 10:45 | 5/21/26 11:45 | 5/21/26 1:45 | 0h | -726h | 0ed | 0 | NA | NA | April 14, 2026 10:00 | April 14, 2026 11:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.24.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1542 | 2574 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | Fixed Units | 6 | 0.5d | 1541 | September 25, 2026 10:45 | September 25, 2026 3:45 | 9/25/26 10:45 | 9/25/26 3:45 | 5/21/26 1:45 | 5/22/26 8:45 | 0h | -726h | 0ed | 0 | NA | NA | April 14, 2026 11:00 | April 14, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.24.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1543 | 2575 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 6 | 0.38d | 1542 | September 25, 2026 3:45 | September 28, 2026 9:45 | 9/25/26 3:45 | 9/28/26 9:45 | 5/22/26 8:45 | 5/22/26 11:45 | 0h | -726h | 0ed | 0 | NA | NA | April 14, 2026 4:00 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.24.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1544 | 2576 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1543 | September 28, 2026 9:45 | September 28, 2026 11:45 | 9/28/26 9:45 | 9/28/26 11:45 | 5/27/26 8:00 | 5/27/26 10:00 | 0h | -705.75h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.24.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1545 | 2577 | Yes | Auto Scheduled | PTP_CM26_Material_Master - SERV - Service Materials | 1.34d | Fixed Duration | 5 | 5.88d |  | September 25, 2026 4:30 | September 29, 2026 10:15 | 9/25/26 4:30 | 9/29/26 10:15 | 6/2/26 3:30 | 6/3/26 4:00 | 0d | -83.41d | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 15h | 15h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.25 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1546 | 2578 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1415 | September 25, 2026 4:30 | September 25, 2026 5:00 | 9/25/26 4:30 | 9/25/26 5:00 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -39420m | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 7, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.25.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1547 | 2579 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1543 | September 28, 2026 9:45 | September 28, 2026 10:15 | 9/28/26 9:45 | 9/28/26 10:15 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -40035m | 0ed | 0 | NA | NA | April 14, 2026 2:45 | April 14, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.25.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1548 | 2580 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1547 | September 28, 2026 10:15 | September 28, 2026 11:15 | 9/28/26 10:15 | 9/28/26 11:15 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -667.25h | 0ed | 0 | NA | NA | April 14, 2026 3:15 | April 14, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.25.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1549 | 2581 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1548 | September 28, 2026 11:15 | September 28, 2026 2:15 | 9/28/26 11:15 | 9/28/26 2:15 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -667.25h | 0ed | 0 | NA | NA | April 14, 2026 4:15 | April 15, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.25.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1550 | 2582 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1549 | September 28, 2026 2:15 | September 28, 2026 4:15 | 9/28/26 2:15 | 9/28/26 4:15 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -667.25h | 0ed | 0 | NA | NA | April 15, 2026 9:15 | April 15, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.25.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1551 | 2583 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1550 | September 28, 2026 4:15 | September 29, 2026 10:15 | 9/28/26 4:15 | 9/29/26 10:15 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -667.25h | 0ed | 0 | NA | NA | April 15, 2026 11:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.25.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1552 | 2584 | Yes | Auto Scheduled | PTP_CM26_Material_Master - KMAT - Configurable Materials | 1.34d | Fixed Duration | 5 | 5.88d |  | September 25, 2026 4:30 | September 29, 2026 10:15 | 9/25/26 4:30 | 9/29/26 10:15 | 5/22/26 11:45 | 6/1/26 10:15 | 0d | -90.47d | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.26 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1553 | 2585 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1415 | September 25, 2026 4:30 | September 25, 2026 5:00 | 9/25/26 4:30 | 9/25/26 5:00 | 6/1/26 9:45 | 6/1/26 10:15 | 0m | -40665m | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 7, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.26.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1554 | 2586 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1543 | September 28, 2026 9:45 | September 28, 2026 10:15 | 9/28/26 9:45 | 9/28/26 10:15 | 5/22/26 11:45 | 5/22/26 1:15 | 0m | -43560m | 0ed | 0 | NA | NA | April 14, 2026 2:45 | April 14, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.26.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1555 | 2587 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1554 | September 28, 2026 10:15 | September 28, 2026 11:15 | 9/28/26 10:15 | 9/28/26 11:15 | 5/22/26 1:15 | 5/22/26 2:15 | 0h | -726h | 0ed | 0 | NA | NA | April 14, 2026 3:15 | April 14, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.26.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1556 | 2588 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1555 | September 28, 2026 11:15 | September 28, 2026 2:15 | 9/28/26 11:15 | 9/28/26 2:15 | 5/22/26 2:15 | 5/22/26 4:15 | 0h | -726h | 0ed | 0 | NA | NA | April 14, 2026 4:15 | April 15, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.26.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1557 | 2589 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1556 | September 28, 2026 2:15 | September 28, 2026 4:15 | 9/28/26 2:15 | 9/28/26 4:15 | 5/22/26 4:15 | 5/25/26 9:15 | 0h | -726h | 0ed | 0 | NA | NA | April 15, 2026 9:15 | April 15, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.26.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1558 | 2590 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1557 | September 28, 2026 4:15 | September 29, 2026 10:15 | 9/28/26 4:15 | 9/29/26 10:15 | 5/25/26 9:15 | 5/25/26 1:15 | 0h | -726h | 0ed | 0 | NA | NA | April 15, 2026 11:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.26.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1559 | 2591 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Records | 3.59d | Fixed Duration | 5 | 1.28d |  | September 24, 2026 11:30 | September 30, 2026 8:15 | 9/24/26 11:30 | 9/30/26 8:15 | 5/28/26 2:53 | 6/3/26 4:00 | 0d | -84.7d | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.27 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1560 | 2592 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1544,1558 | September 29, 2026 10:15 | September 29, 2026 11:15 | 9/29/26 10:15 | 9/29/26 11:15 | 5/28/26 2:53 | 5/28/26 3:53 | 0h | -700.38h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.27.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1561 | 2593 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1560 | September 29, 2026 11:15 | September 29, 2026 2:15 | 9/29/26 11:15 | 9/29/26 2:15 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -673.25h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.27.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1562 | 2594 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1561 | September 29, 2026 2:15 | September 29, 2026 3:15 | 9/29/26 2:15 | 9/29/26 3:15 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -673.25h | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.27.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1563 | 2595 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1562 | September 29, 2026 3:15 | September 30, 2026 8:15 | 9/29/26 3:15 | 9/30/26 8:15 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -673.25h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.27.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1564 | 2596 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1512 | September 24, 2026 11:30 | September 24, 2026 1:30 | 9/24/26 11:30 | 9/24/26 1:30 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -647.5h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 11:00 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.27.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1565 | 2597 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1564 | September 24, 2026 1:30 | September 24, 2026 3:30 | 9/24/26 1:30 | 9/24/26 3:30 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -647.5h | 0ed | 0 | NA | NA | April 15, 2026 11:00 | April 15, 2026 2:00 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.27.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1566 | 2598 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record External Processing | 1.13d | Fixed Duration | 5 | 1.13d |  | September 29, 2026 10:15 | September 30, 2026 11:15 | 9/29/26 10:15 | 9/30/26 11:15 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -84.53d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.28 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1567 | 2599 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1544,1558 | September 29, 2026 10:15 | September 29, 2026 10:45 | 9/29/26 10:15 | 9/29/26 10:45 | 6/2/26 3:00 | 6/2/26 3:30 | 0m | -40575m | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.28.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1568 | 2600 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1567 | September 29, 2026 10:45 | September 29, 2026 11:15 | 9/29/26 10:45 | 9/29/26 11:15 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -40575m | 0ed | 0 | NA | NA | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.28.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1569 | 2601 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1568 | September 29, 2026 11:15 | September 29, 2026 1:15 | 9/29/26 11:15 | 9/29/26 1:15 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -676.25h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.28.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1570 | 2602 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1569 | September 29, 2026 1:15 | September 29, 2026 3:15 | 9/29/26 1:15 | 9/29/26 3:15 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -676.25h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.28.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1571 | 2603 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1570 | September 29, 2026 3:15 | September 30, 2026 8:15 | 9/29/26 3:15 | 9/30/26 8:15 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -676.25h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.28.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1572 | 2604 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1571 | September 30, 2026 8:15 | September 30, 2026 11:15 | 9/30/26 8:15 | 9/30/26 11:15 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -676.25h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.28.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1573 | 2605 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | 1.13d | Fixed Duration | 5 | 1.13d |  | September 29, 2026 10:15 | September 30, 2026 11:15 | 9/29/26 10:15 | 9/30/26 11:15 | 5/27/26 10:00 | 6/3/26 4:00 | 0d | -89.03d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.29 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1574 | 2606 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1544,1558 | September 29, 2026 10:15 | September 29, 2026 10:45 | 9/29/26 10:15 | 9/29/26 10:45 | 5/27/26 10:00 | 5/27/26 10:30 | 0m | -42735m | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.29.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1575 | 2607 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1574 | September 29, 2026 10:45 | September 29, 2026 11:15 | 9/29/26 10:45 | 9/29/26 11:15 | 5/27/26 10:30 | 5/27/26 11:00 | 0m | -42735m | 0ed | 0 | NA | NA | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.29.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1576 | 2608 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1575 | September 29, 2026 11:15 | September 29, 2026 1:15 | 9/29/26 11:15 | 9/29/26 1:15 | 5/27/26 11:00 | 5/27/26 12:00 | 0h | -712.25h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.29.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1577 | 2609 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1576 | September 29, 2026 1:15 | September 29, 2026 3:15 | 9/29/26 1:15 | 9/29/26 3:15 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -676.25h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.29.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1578 | 2610 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1577 | September 29, 2026 3:15 | September 30, 2026 8:15 | 9/29/26 3:15 | 9/30/26 8:15 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -676.25h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.29.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1579 | 2611 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1578 | September 30, 2026 8:15 | September 30, 2026 11:15 | 9/30/26 8:15 | 9/30/26 11:15 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -676.25h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.29.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1580 | 2612 | Yes | Auto Scheduled | PTM_CM31_BOM Conversion | 2.48d | Fixed Duration | 5 | 1.13d |  | September 29, 2026 11:15 | October 1, 2026 4:08 | 9/29/26 11:15 | 10/1/26 4:08 | 5/28/26 3:53 | 6/2/26 10:45 | 0d | -87.55d | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 19h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.30 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1581 | 2613 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1560 | September 29, 2026 11:15 | September 29, 2026 1:15 | 9/29/26 11:15 | 9/29/26 1:15 | 5/28/26 3:53 | 5/28/26 4:53 | 0h | -700.38h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.30.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1582 | 2614 | Yes | Auto Scheduled | Pre Load Validation | 0.5h | Fixed Units | 6 | 0.25d | 1581 | September 29, 2026 1:15 | September 29, 2026 1:45 | 9/29/26 1:15 | 9/29/26 1:45 | 5/28/26 4:53 | 5/29/26 8:23 | 0h | -700.38h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.30.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1583 | 2615 | Yes | Auto Scheduled | Simulate Load | 15.5h | Fixed Units | 6 | 0.13d | 1582 | September 29, 2026 1:45 | October 1, 2026 1:45 | 9/29/26 1:45 | 10/1/26 1:45 | 5/29/26 8:23 | 6/2/26 8:23 | 0h | -700.38h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 11:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/23/26 10:51 | 15.5h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.30.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1584 | 2616 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | Fixed Units | 6 | 0.25d | 1583 | October 1, 2026 1:45 | October 1, 2026 2:15 | 10/1/26 1:45 | 10/1/26 2:15 | 6/2/26 8:23 | 6/2/26 8:53 | 0h | -700.38h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 2:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/23/26 10:51 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.30.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1585 | 2617 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1584 | October 1, 2026 2:15 | October 1, 2026 3:30 | 10/1/26 2:15 | 10/1/26 3:30 | 6/2/26 8:53 | 6/2/26 10:08 | 0h | -700.38h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 16, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 4/1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1586 | 2618 | Yes | Auto Scheduled | Post Load Validation | 0.5h | Fixed Units | 6 | 0.25d | 1585 | October 1, 2026 3:30 | October 1, 2026 4:08 | 10/1/26 3:30 | 10/1/26 4:08 | 6/2/26 10:08 | 6/2/26 10:45 | 0h | -700.38h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 17, 2026 8:15 | Finish No Earlier Than | 4/16/26 5:00 | NA | NA | 4/23/26 10:51 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.30.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1587 | 2619 | Yes | Auto Scheduled | PTM_CM40_Work Center Conversion | 3.08d | Fixed Duration | 5 | 2d |  | September 29, 2026 1:15 | October 2, 2026 1:53 | 9/29/26 1:15 | 10/2/26 1:53 | 5/29/26 1:30 | 6/3/26 8:30 | 0d | -87.55d | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 6.75h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.31 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1588 | 2620 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1581 | September 29, 2026 1:15 | September 29, 2026 2:15 | 9/29/26 1:15 | 9/29/26 2:15 | 5/29/26 1:30 | 5/29/26 2:30 | 0h | -695.75h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.31.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1589 | 2621 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1586 | October 1, 2026 4:08 | October 2, 2026 9:08 | 10/1/26 4:08 | 10/2/26 9:08 | 6/2/26 10:45 | 6/2/26 1:45 | 0h | -700.38h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.31.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1590 | 2622 | Yes | Auto Scheduled | Simulate Load | 0.25h | Fixed Units | 6 | 0.13d | 1589 | October 2, 2026 9:08 | October 2, 2026 9:23 | 10/2/26 9:08 | 10/2/26 9:23 | 6/2/26 1:45 | 6/2/26 2:00 | 0h | -700.38h | 0ed | 0 | NA | NA | April 17, 2026 10:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.25h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.31.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1591 | 2623 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | Fixed Units | 6 | 0.25d | 1590 | October 2, 2026 9:23 | October 2, 2026 9:53 | 10/2/26 9:23 | 10/2/26 9:53 | 6/2/26 2:00 | 6/2/26 2:30 | 0h | -700.38h | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.31.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1592 | 2624 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1591 | October 2, 2026 9:53 | October 2, 2026 10:53 | 10/2/26 9:53 | 10/2/26 10:53 | 6/2/26 2:30 | 6/2/26 3:30 | 0h | -700.38h | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 17, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.31.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1593 | 2625 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1592 | October 2, 2026 10:53 | October 2, 2026 1:53 | 10/2/26 10:53 | 10/2/26 1:53 | 6/2/26 3:30 | 6/3/26 8:30 | 0h | -700.38h | 0ed | 0 | NA | NA | April 17, 2026 3:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.31.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1594 | 2626 | Yes | Auto Scheduled | PTM_CM38_Routing Conversion | 4.27d | Fixed Duration | 5 | 2.88d |  | September 29, 2026 2:15 | October 5, 2026 4:23 | 9/29/26 2:15 | 10/5/26 4:23 | 5/29/26 2:30 | 6/3/26 4:00 | 0d | -88.05d | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 11h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.32 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1595 | 2627 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1588 | September 29, 2026 2:15 | September 29, 2026 3:15 | 9/29/26 2:15 | 9/29/26 3:15 | 5/29/26 2:30 | 5/29/26 3:30 | 0h | -695.75h | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.32.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1596 | 2628 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1593 | October 2, 2026 1:53 | October 5, 2026 9:23 | 10/2/26 1:53 | 10/5/26 9:23 | 6/3/26 8:30 | 6/3/26 2:00 | 0h | -700.38h | 0ed | 0 | NA | NA | April 20, 2026 8:15 | April 20, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.32.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1597 | 2629 | Yes | Auto Scheduled | Simulate Load | 2h | Fixed Units | 6 | 0.13d | 1596 | October 5, 2026 9:23 | October 5, 2026 11:23 | 10/5/26 9:23 | 10/5/26 11:23 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -700.38h | 0ed | 0 | NA | NA | April 20, 2026 10:15 | April 20, 2026 11:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/23/26 10:51 | 2h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.32.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1598 | 2630 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | Fixed Units | 6 | 0.25d | 1597SS | October 5, 2026 9:23 | October 5, 2026 1:23 | 10/5/26 9:23 | 10/5/26 1:23 | 6/3/26 9:00 | 6/3/26 12:00 | 0h | -704.38h | 0ed | 0 | NA | NA | April 20, 2026 11:15 | April 20, 2026 2:15 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/23/26 10:51 | 3h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.32.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1599 | 2631 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1598 | October 5, 2026 1:23 | October 5, 2026 2:23 | 10/5/26 1:23 | 10/5/26 2:23 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -704.38h | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 20, 2026 3:15 | Start No Earlier Than | 4/20/26 8:00 | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.32.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1600 | 2632 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1599 | October 5, 2026 2:23 | October 5, 2026 4:23 | 10/5/26 2:23 | 10/5/26 4:23 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -704.38h | 0ed | 0 | NA | NA | April 20, 2026 3:15 | April 21, 2026 8:15 | Start No Earlier Than | 4/20/26 8:00 | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.32.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1601 | 2633 | Yes | Auto Scheduled | PTM_CM36_Production Version Conversion | 1.13d | Fixed Duration | 5 | 1.13d |  | September 29, 2026 3:15 | September 30, 2026 4:15 | 9/29/26 3:15 | 9/30/26 4:15 | 5/29/26 3:30 | 6/1/26 4:30 | 0d | -86.97d | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.33 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1602 | 2634 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1595 | September 29, 2026 3:15 | September 29, 2026 3:45 | 9/29/26 3:15 | 9/29/26 3:45 | 5/29/26 3:30 | 5/29/26 4:00 | 0m | -41745m | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 10:45 | Start No Earlier Than | 4/20/26 8:00 | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.33.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1603 | 2635 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1602 | September 29, 2026 3:45 | September 29, 2026 4:15 | 9/29/26 3:45 | 9/29/26 4:15 | 5/29/26 4:00 | 5/29/26 4:30 | 0m | -41745m | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.33.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1604 | 2636 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1603 | September 29, 2026 4:15 | September 30, 2026 8:15 | 9/29/26 4:15 | 9/30/26 8:15 | 5/29/26 4:30 | 6/1/26 8:30 | 0h | -695.75h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.33.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1605 | 2637 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1604 | September 30, 2026 8:15 | September 30, 2026 10:15 | 9/30/26 8:15 | 9/30/26 10:15 | 6/1/26 8:30 | 6/1/26 10:30 | 0h | -695.75h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.33.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1606 | 2638 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1605 | September 30, 2026 10:15 | September 30, 2026 1:15 | 9/30/26 10:15 | 9/30/26 1:15 | 6/1/26 10:30 | 6/1/26 1:30 | 0h | -695.75h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.33.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1607 | 2639 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1606 | September 30, 2026 1:15 | September 30, 2026 4:15 | 9/30/26 1:15 | 9/30/26 4:15 | 6/1/26 1:30 | 6/1/26 4:30 | 0h | -695.75h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 11:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.33.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1608 | 2640 | Yes | Auto Scheduled | PTM_CM35_Inspection Plan | 1.13d | Fixed Duration | 5 | 1.13d |  | September 30, 2026 4:15 | October 2, 2026 8:15 | 9/30/26 4:15 | 10/2/26 8:15 | 6/1/26 4:30 | 6/3/26 4:00 | 0d | -86.97d | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 20, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.34 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1609 | 2641 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1607 | September 30, 2026 4:15 | September 30, 2026 4:45 | 9/30/26 4:15 | 9/30/26 4:45 | 6/1/26 4:30 | 6/1/26 5:00 | 0m | -41745m | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.34.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1610 | 2642 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1609 | September 30, 2026 4:45 | October 1, 2026 8:15 | 9/30/26 4:45 | 10/1/26 8:15 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -41355m | 0ed | 0 | NA | NA | April 17, 2026 11:45 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.34.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1611 | 2643 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1610 | October 1, 2026 8:15 | October 1, 2026 9:15 | 10/1/26 8:15 | 10/1/26 9:15 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -689.25h | 0ed | 0 | NA | NA | April 17, 2026 1:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.34.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1612 | 2644 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1611 | October 1, 2026 9:15 | October 1, 2026 11:15 | 10/1/26 9:15 | 10/1/26 11:15 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -689.25h | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 17, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.34.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1613 | 2645 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1612 | October 1, 2026 11:15 | October 1, 2026 2:15 | 10/1/26 11:15 | 10/1/26 2:15 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -689.25h | 0ed | 0 | NA | NA | April 17, 2026 4:15 | April 20, 2026 9:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.34.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1614 | 2646 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1613 | October 1, 2026 2:15 | October 2, 2026 8:15 | 10/1/26 2:15 | 10/2/26 8:15 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -689.25h | 0ed | 0 | NA | NA | April 20, 2026 9:15 | April 20, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.34.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1615 | 2647 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Serial Numbers | 1.13d | Fixed Duration | 5 | 1.13d |  | September 30, 2026 4:45 | October 2, 2026 8:45 | 9/30/26 4:45 | 10/2/26 8:45 | 6/2/26 8:00 | 6/3/26 9:00 | 0d | -86.97d | 0ed | 0 | NA | NA | April 17, 2026 11:45 | April 20, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.35 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1616 | 2648 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1609 | September 30, 2026 4:45 | October 1, 2026 8:15 | 9/30/26 4:45 | 10/1/26 8:15 | 6/2/26 8:00 | 6/2/26 8:30 | 0m | -41745m | 0ed | 0 | NA | NA | April 17, 2026 11:45 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.35.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1617 | 2649 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1616 | October 1, 2026 8:15 | October 1, 2026 8:45 | 10/1/26 8:15 | 10/1/26 8:45 | 6/2/26 8:30 | 6/2/26 9:00 | 0m | -41745m | 0ed | 0 | NA | NA | April 17, 2026 1:15 | April 17, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.35.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1618 | 2650 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1617 | October 1, 2026 8:45 | October 1, 2026 9:45 | 10/1/26 8:45 | 10/1/26 9:45 | 6/2/26 9:00 | 6/2/26 10:00 | 0h | -695.75h | 0ed | 0 | NA | NA | April 17, 2026 1:45 | April 17, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.35.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1619 | 2651 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1618 | October 1, 2026 9:45 | October 1, 2026 11:45 | 10/1/26 9:45 | 10/1/26 11:45 | 6/2/26 10:00 | 6/2/26 12:00 | 0h | -695.75h | 0ed | 0 | NA | NA | April 17, 2026 2:45 | April 17, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.35.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1620 | 2652 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1619 | October 1, 2026 11:45 | October 1, 2026 2:45 | 10/1/26 11:45 | 10/1/26 2:45 | 6/2/26 1:00 | 6/2/26 3:00 | 0h | -695.75h | 0ed | 0 | NA | NA | April 17, 2026 4:45 | April 20, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.35.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1621 | 2653 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1620 | October 1, 2026 2:45 | October 2, 2026 8:45 | 10/1/26 2:45 | 10/2/26 8:45 | 6/2/26 3:00 | 6/3/26 9:00 | 0h | -695.75h | 0ed | 0 | NA | NA | April 20, 2026 9:45 | April 20, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.35.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1622 | 2654 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Service | 6.78d | Fixed Duration | 5 | 1.13d |  | September 24, 2026 8:30 | October 2, 2026 3:45 | 9/24/26 8:30 | 10/2/26 3:45 | 6/3/26 9:00 | 6/3/26 4:00 | 0d | -86.97d | 0ed | 0 | NA | NA | April 20, 2026 1:45 | April 21, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.36 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1623 | 2655 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1621 | October 2, 2026 8:45 | October 2, 2026 9:15 | 10/2/26 8:45 | 10/2/26 9:15 | 6/3/26 9:00 | 6/3/26 9:30 | 0m | -41745m | 0ed | 0 | NA | NA | April 20, 2026 1:45 | April 20, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.36.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1624 | 2656 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1623 | October 2, 2026 9:15 | October 2, 2026 9:45 | 10/2/26 9:15 | 10/2/26 9:45 | 6/3/26 9:30 | 6/3/26 10:00 | 0m | -41745m | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 20, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.36.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1625 | 2657 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1624 | October 2, 2026 9:45 | October 2, 2026 10:45 | 10/2/26 9:45 | 10/2/26 10:45 | 6/3/26 10:00 | 6/3/26 11:00 | 0h | -695.75h | 0ed | 0 | NA | NA | April 20, 2026 2:45 | April 20, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.36.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1626 | 2658 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1625 | October 2, 2026 10:45 | October 2, 2026 1:45 | 10/2/26 10:45 | 10/2/26 1:45 | 6/3/26 11:00 | 6/3/26 2:00 | 0h | -695.75h | 0ed | 0 | NA | NA | April 20, 2026 3:45 | April 21, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.36.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1627 | 2659 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1626 | October 2, 2026 1:45 | October 2, 2026 3:45 | 10/2/26 1:45 | 10/2/26 3:45 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -695.75h | 0ed | 0 | NA | NA | April 21, 2026 8:45 | April 21, 2026 10:45 | Finish No Earlier Than | 4/21/26 5:00 | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.36.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1628 | 2660 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d |  | September 24, 2026 8:30 | September 24, 2026 11:30 | 9/24/26 8:30 | 9/24/26 11:30 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -644.5h | 0ed | 0 | NA | NA | April 21, 2026 10:45 | April 21, 2026 2:45 | Start No Earlier Than | 4/21/26 8:00 | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.36.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1629 | 2661 | Yes | Auto Scheduled | VC_Object Dependencies | 0.63d | Fixed Duration | 5 | 0.63d |  | September 24, 2026 8:30 | September 24, 2026 2:30 | 9/24/26 8:30 | 9/24/26 2:30 | 6/1/26 11:00 | 6/1/26 5:00 | 0d | -82.69d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.37 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1630 | 2662 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1390 | September 24, 2026 8:30 | September 24, 2026 10:30 | 9/24/26 8:30 | 9/24/26 10:30 | 6/1/26 11:00 | 6/1/26 2:00 | 0h | -661.5h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.37.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1631 | 2663 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1630 | September 24, 2026 10:30 | September 24, 2026 2:30 | 9/24/26 10:30 | 9/24/26 2:30 | 6/1/26 2:00 | 6/1/26 5:00 | 0h | -661.5h | 0ed | 0 | NA | NA | April 6, 2026 10:15 | April 6, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.37.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1632 | 2664 | Yes | Auto Scheduled | VC_Characteristics | 0.63d | Fixed Duration | 5 | 0.63d |  | September 24, 2026 2:30 | September 25, 2026 10:30 | 9/24/26 2:30 | 9/25/26 10:30 | 6/2/26 8:00 | 6/2/26 2:00 | 0d | -82.69d | 0ed | 0 | NA | NA | April 6, 2026 2:15 | April 7, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.38 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1633 | 2665 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1631 | September 24, 2026 2:30 | September 24, 2026 4:30 | 9/24/26 2:30 | 9/24/26 4:30 | 6/2/26 8:00 | 6/2/26 10:00 | 0h | -661.5h | 0ed | 0 | NA | NA | April 6, 2026 2:15 | April 6, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.38.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1634 | 2666 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1633 | September 24, 2026 4:30 | September 25, 2026 10:30 | 9/24/26 4:30 | 9/25/26 10:30 | 6/2/26 10:00 | 6/2/26 2:00 | 0h | -661.5h | 0ed | 0 | NA | NA | April 6, 2026 4:15 | April 7, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.38.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1635 | 2667 | Yes | Auto Scheduled | VC_Classes | 0.63d | Fixed Duration | 5 | 0.63d |  | September 25, 2026 10:30 | September 25, 2026 4:30 | 9/25/26 10:30 | 9/25/26 4:30 | 6/2/26 2:00 | 6/3/26 10:00 | 0d | -82.69d | 0ed | 0 | NA | NA | April 7, 2026 10:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.39 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1636 | 2668 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1634 | September 25, 2026 10:30 | September 25, 2026 1:30 | 9/25/26 10:30 | 9/25/26 1:30 | 6/2/26 2:00 | 6/2/26 4:00 | 0h | -661.5h | 0ed | 0 | NA | NA | April 7, 2026 10:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.39.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1637 | 2669 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1636 | September 25, 2026 1:30 | September 25, 2026 4:30 | 9/25/26 1:30 | 9/25/26 4:30 | 6/2/26 4:00 | 6/3/26 10:00 | 0h | -661.5h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.39.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1638 | 2670 | Yes | Auto Scheduled | VC_Classification (Class Type 200) | 0.63d | Fixed Duration | 5 | 0.63d |  | September 29, 2026 10:15 | September 29, 2026 4:15 | 9/29/26 10:15 | 9/29/26 4:15 | 6/3/26 10:00 | 6/3/26 4:00 | 0d | -84.03d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.40 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1639 | 2671 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1558 | September 29, 2026 10:15 | September 29, 2026 1:15 | 9/29/26 10:15 | 9/29/26 1:15 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -672.25h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.40.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1640 | 2672 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1639 | September 29, 2026 1:15 | September 29, 2026 4:15 | 9/29/26 1:15 | 9/29/26 4:15 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -672.25h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.40.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1641 | 2673 | Yes | Auto Scheduled | VC_Dependency Nets | 0.63d | Fixed Duration | 5 | 0.63d |  | September 29, 2026 10:15 | September 29, 2026 4:15 | 9/29/26 10:15 | 9/29/26 4:15 | 6/3/26 10:00 | 6/3/26 4:00 | 0d | -84.03d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.41 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1642 | 2674 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1552,1637 | September 29, 2026 10:15 | September 29, 2026 1:15 | 9/29/26 10:15 | 9/29/26 1:15 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -672.25h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.41.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1643 | 2675 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1642 | September 29, 2026 1:15 | September 29, 2026 4:15 | 9/29/26 1:15 | 9/29/26 4:15 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -672.25h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.41.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1644 | 2676 | Yes | Auto Scheduled | VC_Configuration Profiles | 0.63d | Fixed Duration | 5 | 0.63d |  | September 29, 2026 10:15 | September 29, 2026 4:15 | 9/29/26 10:15 | 9/29/26 4:15 | 6/1/26 10:15 | 6/1/26 4:15 | 0d | -86d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.42 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1645 | 2677 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1552 | September 29, 2026 10:15 | September 29, 2026 1:15 | 9/29/26 10:15 | 9/29/26 1:15 | 6/1/26 10:15 | 6/1/26 1:15 | 0h | -688h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.42.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1646 | 2678 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1645 | September 29, 2026 1:15 | September 29, 2026 4:15 | 9/29/26 1:15 | 9/29/26 4:15 | 6/1/26 1:15 | 6/1/26 4:15 | 0h | -688h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.42.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1647 | 2679 | Yes | Auto Scheduled | VC_Variant Tables | 0.63d | Fixed Duration | 5 | 0.63d |  | September 29, 2026 4:15 | September 30, 2026 1:15 | 9/29/26 4:15 | 9/30/26 1:15 | 6/2/26 2:00 | 6/3/26 10:00 | 0d | -85.28d | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.43 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1648 | 2680 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1646 | September 29, 2026 4:15 | September 30, 2026 9:15 | 9/29/26 4:15 | 9/30/26 9:15 | 6/2/26 2:00 | 6/2/26 4:00 | 0h | -682.25h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.43.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1649 | 2681 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1648 | September 30, 2026 9:15 | September 30, 2026 1:15 | 9/30/26 9:15 | 9/30/26 1:15 | 6/2/26 4:00 | 6/3/26 10:00 | 0h | -682.25h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.43.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1650 | 2682 | Yes | Auto Scheduled | VC_Variant Tables Content | 0.63d | Fixed Duration | 5 | 0.63d |  | September 30, 2026 1:15 | October 1, 2026 9:15 | 9/30/26 1:15 | 10/1/26 9:15 | 6/3/26 10:00 | 6/3/26 4:00 | 0d | -85.28d | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.44 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1651 | 2683 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1649 | September 30, 2026 1:15 | September 30, 2026 3:15 | 9/30/26 1:15 | 9/30/26 3:15 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -682.25h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.44.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1652 | 2684 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1651 | September 30, 2026 3:15 | October 1, 2026 9:15 | 9/30/26 3:15 | 10/1/26 9:15 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -682.25h | 0ed | 0 | NA | NA | April 17, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.44.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1653 | 2685 | Yes | Auto Scheduled | VC_Characteristic Groups | 1.97d | Fixed Duration | 5 | 0.63d |  | September 29, 2026 4:15 | October 1, 2026 4:00 | 9/29/26 4:15 | 10/1/26 4:00 | 6/1/26 4:15 | 6/3/26 4:00 | 0d | -86d | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 15.75h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.45 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1654 | 2686 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 12.75h | Fixed Units | 6 | 0.25d | 1646 | September 29, 2026 4:15 | October 1, 2026 12:00 | 9/29/26 4:15 | 10/1/26 12:00 | 6/1/26 4:15 | 6/3/26 12:00 | 0h | -688h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 2:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/23/26 10:51 | 12.75h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.45.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1655 | 2687 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1654 | October 1, 2026 1:00 | October 1, 2026 4:00 | 10/1/26 1:00 | 10/1/26 4:00 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -688h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.45.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1656 | 2688 | Yes | Auto Scheduled | PTM_CM52_Super_BOM | 4.09d | Fixed Duration | 5 | 1.13d |  | September 29, 2026 10:15 | October 5, 2026 11:00 | 9/29/26 10:15 | 10/5/26 11:00 | 5/25/26 1:15 | 5/29/26 2:00 | 0d | -90.75d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 32.75h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.46 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1657 | 2689 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1558 | September 29, 2026 10:15 | September 29, 2026 10:45 | 9/29/26 10:15 | 9/29/26 10:45 | 5/25/26 1:15 | 5/25/26 1:45 | 0m | -43560m | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.46.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1658 | 2690 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1657 | September 29, 2026 10:45 | September 29, 2026 11:15 | 9/29/26 10:45 | 9/29/26 11:15 | 5/25/26 1:45 | 5/25/26 2:15 | 0m | -43560m | 0ed | 0 | NA | NA | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.46.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1659 | 2691 | Yes | Auto Scheduled | Simulate Load | 24.75h | Fixed Units | 6 | 0.13d | 1658 | September 29, 2026 11:15 | October 2, 2026 12:00 | 9/29/26 11:15 | 10/2/26 12:00 | 5/25/26 2:15 | 5/28/26 3:00 | 0h | -726h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | Finish No Earlier Than | 4/20/26 5:00 | NA | NA | 4/23/26 10:51 | 24.75h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.46.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1660 | 2692 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1659 | October 2, 2026 1:00 | October 2, 2026 3:00 | 10/2/26 1:00 | 10/2/26 3:00 | 5/28/26 3:00 | 5/28/26 5:00 | 0h | -726h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.46.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1661 | 2693 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1660 | October 2, 2026 3:00 | October 2, 2026 5:00 | 10/2/26 3:00 | 10/2/26 5:00 | 5/29/26 8:00 | 5/29/26 10:00 | 0h | -726h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.46.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1662 | 2694 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1661 | October 5, 2026 8:00 | October 5, 2026 11:00 | 10/5/26 8:00 | 10/5/26 11:00 | 5/29/26 10:00 | 5/29/26 2:00 | 0h | -726h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.46.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1663 | 2695 | Yes | Auto Scheduled | PTM_CM53_Super_Routing | 2.13d | Fixed Duration | 5 | 1.13d |  | October 5, 2026 11:00 | October 7, 2026 12:00 | 10/5/26 11:00 | 10/7/26 12:00 | 5/29/26 2:00 | 6/3/26 4:00 | 0d | -90.75d | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.47 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1664 | 2696 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1662 | October 5, 2026 11:00 | October 5, 2026 11:30 | 10/5/26 11:00 | 10/5/26 11:30 | 5/29/26 2:00 | 5/29/26 2:30 | 0m | -43560m | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 16, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.47.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1665 | 2697 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1664 | October 5, 2026 11:30 | October 5, 2026 12:00 | 10/5/26 11:30 | 10/5/26 12:00 | 5/29/26 2:30 | 5/29/26 3:00 | 0m | -43560m | 0ed | 0 | NA | NA | April 16, 2026 4:45 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.47.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1666 | 2698 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1665 | October 5, 2026 1:00 | October 6, 2026 2:00 | 10/5/26 1:00 | 10/6/26 2:00 | 5/29/26 3:00 | 6/1/26 4:00 | 0h | -726h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.47.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1667 | 2699 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1666 | October 6, 2026 2:00 | October 6, 2026 4:00 | 10/6/26 2:00 | 10/6/26 4:00 | 6/1/26 4:00 | 6/2/26 9:00 | 0h | -726h | 0ed | 0 | NA | NA | April 17, 2026 9:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.47.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1668 | 2700 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1667 | October 6, 2026 4:00 | October 7, 2026 9:00 | 10/6/26 4:00 | 10/7/26 9:00 | 6/2/26 9:00 | 6/2/26 11:00 | 0h | -726h | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.47.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1669 | 2701 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1668 | October 7, 2026 9:00 | October 7, 2026 12:00 | 10/7/26 9:00 | 10/7/26 12:00 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -717h | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.47.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1670 | 2702 | Yes | Auto Scheduled | VC_VK30 Pricing Variant | 0.69d | Fixed Duration | 5 | 0.69d |  | October 7, 2026 9:00 | October 7, 2026 3:30 | 10/7/26 9:00 | 10/7/26 3:30 | 6/2/26 11:00 | 6/3/26 8:30 | 0d | -90.75d | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 20, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.48 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1671 | 2703 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1668 | October 7, 2026 9:00 | October 7, 2026 9:30 | 10/7/26 9:00 | 10/7/26 9:30 | 6/2/26 11:00 | 6/2/26 11:30 | 0m | -43560m | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 17, 2026 2:45 | Start No Earlier Than | 4/6/26 8:00 | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.48.1 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1672 | 2704 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1671 | October 7, 2026 9:30 | October 7, 2026 11:30 | 10/7/26 9:30 | 10/7/26 11:30 | 6/2/26 11:30 | 6/2/26 2:30 | 0h | -726h | 0ed | 0 | NA | NA | April 17, 2026 2:45 | April 17, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.48.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1673 | 2705 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1672 | October 7, 2026 11:30 | October 7, 2026 3:30 | 10/7/26 11:30 | 10/7/26 3:30 | 6/2/26 2:30 | 6/3/26 8:30 | 0h | -726h | 0ed | 0 | NA | NA | April 17, 2026 4:45 | April 20, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.48.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1674 | 2706 | Yes | Auto Scheduled | OTC_CM22_Pricing_Condition | 0.69d | Fixed Duration | 5 | 0.69d |  | October 7, 2026 3:30 | October 8, 2026 12:00 | 10/7/26 3:30 | 10/8/26 12:00 | 6/3/26 8:30 | 6/3/26 4:00 | 0d | -90.75d | 0ed | 0 | NA | NA | April 20, 2026 10:45 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 8.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.49 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1675 | 2707 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1673 | October 7, 2026 3:30 | October 7, 2026 4:00 | 10/7/26 3:30 | 10/7/26 4:00 | 6/3/26 8:30 | 6/3/26 9:00 | 0m | -43560m | 0ed | 0 | NA | NA | April 20, 2026 10:45 | April 20, 2026 11:15 | Start No Earlier Than | 4/6/26 8:00 | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.49.1 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1676 | 2708 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1675 | October 7, 2026 4:00 | October 8, 2026 9:00 | 10/7/26 4:00 | 10/8/26 9:00 | 6/3/26 9:00 | 6/3/26 11:00 | 0h | -726h | 0ed | 0 | NA | NA | April 20, 2026 11:15 | April 20, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.49.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1677 | 2709 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1676 | October 8, 2026 9:00 | October 8, 2026 12:00 | 10/8/26 9:00 | 10/8/26 12:00 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -725h | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 6h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.49.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda,kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1678 | 2710 | Yes | Auto Scheduled | OTC_CM21_CMIR | 0.5d | Fixed Duration | 5 | 1.13d |  | October 8, 2026 9:00 | October 8, 2026 2:00 | 10/8/26 9:00 | 10/8/26 2:00 | 6/3/26 11:00 | 6/3/26 4:00 | 0d | -90.75d | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 21, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 4h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.50 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1679 | 2711 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1676,1687 | October 8, 2026 9:00 | October 8, 2026 9:30 | 10/8/26 9:00 | 10/8/26 9:30 | 6/3/26 11:00 | 6/3/26 11:30 | 0m | -43560m | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 20, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.50.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1680 | 2712 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1679 | October 8, 2026 9:30 | October 8, 2026 10:00 | 10/8/26 9:30 | 10/8/26 10:00 | 6/3/26 11:30 | 6/3/26 12:00 | 0m | -43560m | 0ed | 0 | NA | NA | April 20, 2026 2:45 | April 20, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.50.2 | 500 | No | No | No |  | Kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1681 | 2713 | Yes | Auto Scheduled | Simulate Load | 0h | Fixed Units | 6 | 0.13d | 1680 | October 8, 2026 10:00 | October 8, 2026 10:00 | 10/8/26 10:00 | 10/8/26 10:00 | 6/3/26 1:00 | 6/3/26 1:00 | 0h | -726h | 0ed | 0 | NA | NA | April 20, 2026 3:15 | April 20, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.50.3 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1682 | 2714 | Yes | Auto Scheduled | Error and Defect Mitigation | 0h | Fixed Units | 6 | 0.25d | 1681 | October 8, 2026 10:00 | October 8, 2026 10:00 | 10/8/26 10:00 | 10/8/26 10:00 | 6/3/26 1:00 | 6/3/26 1:00 | 0h | -726h | 0ed | 0 | NA | NA | April 20, 2026 4:15 | April 21, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.50.4 | 500 | Yes | No | No |  | Kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1683 | 2715 | Yes | Auto Scheduled | Load | 0h | Fixed Units | 6 | 0.25d | 1682 | October 8, 2026 10:00 | October 8, 2026 10:00 | 10/8/26 10:00 | 10/8/26 10:00 | 6/3/26 1:00 | 6/3/26 1:00 | 0h | -726h | 0ed | 0 | NA | NA | April 21, 2026 9:15 | April 21, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.50.5 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1684 | 2716 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1683 | October 8, 2026 10:00 | October 8, 2026 2:00 | 10/8/26 10:00 | 10/8/26 2:00 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -726h | 0ed | 0 | NA | NA | April 21, 2026 11:15 | April 21, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.50.6 | 500 | No | No | No |  | Kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1685 | 2717 | Yes | Auto Scheduled | PTP_CM29_Source_List | 6.16d | Fixed Duration | 5 | 0.94d |  | September 25, 2026 9:30 | October 5, 2026 10:45 | 9/25/26 9:30 | 10/5/26 10:45 | 6/3/26 9:00 | 6/3/26 4:00 | 0d | -87.47d | 0ed | 0 | NA | NA | April 13, 2026 10:45 | April 14, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.51 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1686 | 2718 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1529,1536 | September 25, 2026 9:30 | September 25, 2026 10:00 | 9/25/26 9:30 | 9/25/26 10:00 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -39060m | 0ed | 0 | NA | NA | April 14, 2026 9:45 | April 14, 2026 10:15 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.51.1 | 500 | No | No | No |  | Sam | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1687 | 2719 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1505 | October 2, 2026 2:45 | October 2, 2026 4:45 | 10/2/26 2:45 | 10/2/26 4:45 | 6/3/26 9:00 | 6/3/26 11:00 | 0h | -700.75h | 0ed | 0 | NA | NA | April 13, 2026 10:45 | April 13, 2026 1:45 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.51.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1688 | 2720 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1687 | October 2, 2026 4:45 | October 5, 2026 10:45 | 10/2/26 4:45 | 10/5/26 10:45 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -699.75h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.51.3 | 500 | No | No | No |  | Sam | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1689 | 2721 | Yes | Auto Scheduled | RTR_CM11_Asset_Master | 6.63d | Fixed Duration | 5 | 1.13d |  | September 24, 2026 8:30 | October 2, 2026 2:30 | 9/24/26 8:30 | 10/2/26 2:30 | 5/26/26 10:00 | 6/3/26 4:00 | 0d | -86.81d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 53.5h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.52 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1690 | 2722 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d |  | September 24, 2026 8:30 | September 24, 2026 9:00 | 9/24/26 8:30 | 9/24/26 9:00 | 5/26/26 10:00 | 5/26/26 10:30 | 0m | -41670m | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:15 | Start No Earlier Than | 4/15/26 8:00 | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.52.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1691 | 2723 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1690 | September 24, 2026 9:00 | September 24, 2026 9:30 | 9/24/26 9:00 | 9/24/26 9:30 | 5/26/26 10:30 | 5/26/26 11:00 | 0m | -41670m | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.52.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1692 | 2724 | Yes | Auto Scheduled | Simulate Load | 31h | Fixed Units | 6 | 0.13d | 1691 | September 24, 2026 9:30 | September 30, 2026 8:30 | 9/24/26 9:30 | 9/30/26 8:30 | 5/26/26 11:00 | 6/1/26 10:00 | 0h | -694.5h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:45 | Finish No Earlier Than | 4/20/26 5:00 | NA | NA | 4/23/26 10:51 | 31h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.52.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1693 | 2725 | Yes | Auto Scheduled | Error and Defect Mitigation | 16h | Fixed Units | 6 | 0.25d | 1692 | September 30, 2026 8:30 | October 2, 2026 8:30 | 9/30/26 8:30 | 10/2/26 8:30 | 6/1/26 10:00 | 6/3/26 10:00 | 0h | -694.5h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 2:45 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/23/26 10:51 | 16h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.52.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1694 | 2726 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1693 | October 2, 2026 8:30 | October 2, 2026 10:30 | 10/2/26 8:30 | 10/2/26 10:30 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -694.5h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 4:45 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.52.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1695 | 2727 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1694 | October 2, 2026 10:30 | October 2, 2026 2:30 | 10/2/26 10:30 | 10/2/26 2:30 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -694.5h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.52.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1696 | 2728 | Yes | Auto Scheduled | PTM_CM50_Material Class | 2.13d | Fixed Duration | 5 | 0.25d |  | September 29, 2026 3:45 | October 1, 2026 4:45 | 9/29/26 3:45 | 10/1/26 4:45 | 6/1/26 3:00 | 6/3/26 4:00 | 0d | -86.09d | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 17h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.53 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1697 | 2729 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1602 | September 29, 2026 3:45 | September 29, 2026 4:15 | 9/29/26 3:45 | 9/29/26 4:15 | 6/1/26 3:00 | 6/1/26 3:30 | 0m | -41325m | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.53.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1698 | 2730 | Yes | Auto Scheduled | Load | 30m | Fixed Units | 6 | 0.06d | 1697 | September 29, 2026 4:15 | September 29, 2026 4:45 | 9/29/26 4:15 | 9/29/26 4:45 | 6/1/26 3:30 | 6/1/26 4:00 | 0m | -41325m | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.53.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1699 | 2731 | Yes | Auto Scheduled | Post Load Validation | 16h | Fixed Units | 6 | 0.13d | 1698 | September 29, 2026 4:45 | October 1, 2026 4:45 | 9/29/26 4:45 | 10/1/26 4:45 | 6/1/26 4:00 | 6/3/26 4:00 | 0h | -688.75h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | Finish No Earlier Than | 4/20/26 5:00 | NA | NA | 4/23/26 10:51 | 16h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.53.3 | 500 | No | No | No |  | brad | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1700 | 2732 | Yes | Auto Scheduled | PTM_CM55_Class assignment to materials | 1.13d | Fixed Duration | 5 | 1.13d |  | September 29, 2026 4:15 | October 1, 2026 8:15 | 9/29/26 4:15 | 10/1/26 8:15 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -85.16d | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.54 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1701 | 2733 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1697 | September 29, 2026 4:15 | September 29, 2026 4:45 | 9/29/26 4:15 | 9/29/26 4:45 | 6/2/26 3:00 | 6/2/26 3:30 | 0m | -40875m | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.54.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1702 | 2734 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1701 | September 29, 2026 4:45 | September 30, 2026 8:15 | 9/29/26 4:45 | 9/30/26 8:15 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -40875m | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.54.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1703 | 2735 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1702 | September 30, 2026 8:15 | September 30, 2026 9:15 | 9/30/26 8:15 | 9/30/26 9:15 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -681.25h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.54.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1704 | 2736 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1703 | September 30, 2026 9:15 | September 30, 2026 11:15 | 9/30/26 9:15 | 9/30/26 11:15 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -681.25h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.54.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1705 | 2737 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1704 | September 30, 2026 11:15 | September 30, 2026 2:15 | 9/30/26 11:15 | 9/30/26 2:15 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -681.25h | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 17, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.54.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1706 | 2738 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1705 | September 30, 2026 2:15 | October 1, 2026 8:15 | 9/30/26 2:15 | 10/1/26 8:15 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -681.25h | 0ed | 0 | NA | NA | April 17, 2026 9:15 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.54.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1707 | 2739 | Yes | Auto Scheduled | GTS - Material initial load from S4 (Run Interface) | 2.09d | Fixed Duration | 5 | 0.25d |  | September 29, 2026 1:15 | October 1, 2026 2:00 | 9/29/26 1:15 | 10/1/26 2:00 | 5/27/26 1:00 | 5/29/26 1:45 | 0d | -89.03d | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 16.75h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.55 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1708 | 2740 | Yes | Auto Scheduled | Run material interface to GTS | 15.75h | Fixed Units | 6 | 0.13d | 1576 | September 29, 2026 1:15 | October 1, 2026 12:00 | 9/29/26 1:15 | 10/1/26 12:00 | 5/27/26 1:00 | 5/29/26 11:45 | 0h | -712.25h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 9:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/23/26 10:51 | 15.75h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.55.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1709 | 2741 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1708 | October 1, 2026 1:00 | October 1, 2026 2:00 | 10/1/26 1:00 | 10/1/26 2:00 | 5/29/26 11:45 | 5/29/26 1:45 | 0h | -712.25h | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.55.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1710 | 2742 | Yes | Auto Scheduled | GTS - Customers initial load from S4 (Run Interface) | 0.25d | Fixed Duration | 5 | 0.25d |  | September 24, 2026 8:30 | September 24, 2026 10:30 | 9/24/26 8:30 | 9/24/26 10:30 | 6/3/26 2:00 | 6/3/26 4:00 | 0d | -80.44d | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.56 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1711 | 2743 | Yes | Auto Scheduled | Run material interface to GTS | 1h | Fixed Units | 6 | 0.13d |  | September 24, 2026 8:30 | September 24, 2026 9:30 | 9/24/26 8:30 | 9/24/26 9:30 | 6/3/26 2:00 | 6/3/26 3:00 | 0h | -643.5h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 2:45 | Start No Earlier Than | 4/15/26 8:00 | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.56.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1712 | 2744 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1711 | September 24, 2026 9:30 | September 24, 2026 10:30 | 9/24/26 9:30 | 9/24/26 10:30 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -643.5h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 3:45 | Finish No Earlier Than | 4/20/26 5:00 | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.56.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1713 | 2745 | Yes | Auto Scheduled | GTS - Vendors initial load from S4 (Run Interface) | 0.25d | Fixed Duration | 5 | 0.25d |  | September 24, 2026 4:30 | September 25, 2026 9:30 | 9/24/26 4:30 | 9/25/26 9:30 | 6/3/26 10:00 | 6/3/26 4:00 | 0d | -81.69d | 0ed | 0 | NA | NA | April 15, 2026 2:00 | April 15, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.57 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1714 | 2746 | Yes | Auto Scheduled | Run material interface to GTS | 1h | Fixed Units | 6 | 0.13d | 1519 | September 24, 2026 4:30 | September 25, 2026 8:30 | 9/24/26 4:30 | 9/25/26 8:30 | 6/3/26 10:00 | 6/3/26 11:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 15, 2026 2:00 | April 15, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.57.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1715 | 2747 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1714 | September 25, 2026 8:30 | September 25, 2026 9:30 | 9/25/26 8:30 | 9/25/26 9:30 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -650.5h | 0ed | 0 | NA | NA | April 15, 2026 3:00 | April 15, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.57.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1716 | 2748 | Yes | Auto Scheduled | GTS - ECCN - Create | 1.13d | Fixed Duration | 5 | 5.63d |  | September 24, 2026 8:30 | September 25, 2026 9:30 | 9/24/26 8:30 | 9/25/26 9:30 | 6/3/26 11:00 | 6/3/26 4:00 | 0d | -81.31d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 13, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.58 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1717 | 2749 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 1390 | September 24, 2026 8:30 | September 24, 2026 9:30 | 9/24/26 8:30 | 9/24/26 9:30 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -642.5h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.58.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1718 | 2750 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1714 | September 25, 2026 8:30 | September 25, 2026 9:30 | 9/25/26 8:30 | 9/25/26 9:30 | 6/3/26 11:00 | 6/3/26 12:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 13, 2026 1:15 | April 13, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.58.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1719 | 2751 | Yes | Auto Scheduled | GTS - ECCN - Assign | 0.25d | Fixed Duration | 5 | 0.25d |  | October 1, 2026 2:00 | October 1, 2026 4:00 | 10/1/26 2:00 | 10/1/26 4:00 | 5/29/26 1:45 | 5/29/26 3:45 | 0d | -89.03d | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.59 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1720 | 2752 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 1709 | October 1, 2026 2:00 | October 1, 2026 3:00 | 10/1/26 2:00 | 10/1/26 3:00 | 5/29/26 1:45 | 5/29/26 2:45 | 0h | -712.25h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 11:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.59.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1721 | 2753 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1720 | October 1, 2026 3:00 | October 1, 2026 4:00 | 10/1/26 3:00 | 10/1/26 4:00 | 5/29/26 2:45 | 5/29/26 3:45 | 0h | -712.25h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.59.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1722 | 2754 | Yes | Auto Scheduled | GTS - HTS - Create | 0.25d | Fixed Duration | 5 | 0.25d |  | September 24, 2026 8:30 | September 24, 2026 10:30 | 9/24/26 8:30 | 9/24/26 10:30 | 6/3/26 2:00 | 6/3/26 4:00 | 0d | -80.44d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.60 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1723 | 2755 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 1390 | September 24, 2026 8:30 | September 24, 2026 9:30 | 9/24/26 8:30 | 9/24/26 9:30 | 6/3/26 2:00 | 6/3/26 3:00 | 0h | -643.5h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.60.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1724 | 2756 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1723 | September 24, 2026 9:30 | September 24, 2026 10:30 | 9/24/26 9:30 | 9/24/26 10:30 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -643.5h | 0ed | 0 | NA | NA | April 6, 2026 9:15 | April 6, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.60.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1725 | 2757 | Yes | Auto Scheduled | GTS - HTS - Assign | 0.25d | Fixed Duration | 5 | 0.25d |  | October 1, 2026 4:00 | October 2, 2026 9:00 | 10/1/26 4:00 | 10/2/26 9:00 | 5/29/26 3:45 | 6/1/26 8:45 | 0d | -89.03d | 0ed | 0 | NA | NA | April 16, 2026 8:45 | April 16, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.61 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1726 | 2758 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 1721 | October 1, 2026 4:00 | October 1, 2026 5:00 | 10/1/26 4:00 | 10/1/26 5:00 | 5/29/26 3:45 | 5/29/26 4:45 | 0h | -712.25h | 0ed | 0 | NA | NA | April 16, 2026 8:45 | April 16, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.61.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1727 | 2759 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1726 | October 2, 2026 8:00 | October 2, 2026 9:00 | 10/2/26 8:00 | 10/2/26 9:00 | 5/29/26 4:45 | 6/1/26 8:45 | 0h | -712.25h | 0ed | 0 | NA | NA | April 16, 2026 9:45 | April 16, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.61.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1728 | 2760 | Yes | Auto Scheduled | GTS - License - Create | 0.25d | Fixed Duration | 5 | 0.25d |  | October 2, 2026 10:00 | October 2, 2026 12:00 | 10/2/26 10:00 | 10/2/26 12:00 | 6/3/26 2:00 | 6/3/26 4:00 | 0d | -86.63d | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.62 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1729 | 2761 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 1726,1742 | October 2, 2026 10:00 | October 2, 2026 11:00 | 10/2/26 10:00 | 10/2/26 11:00 | 6/3/26 2:00 | 6/3/26 3:00 | 0h | -693h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.62.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1730 | 2762 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1729 | October 2, 2026 11:00 | October 2, 2026 12:00 | 10/2/26 11:00 | 10/2/26 12:00 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -693h | 0ed | 0 | NA | NA | April 16, 2026 1:45 | April 16, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.62.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1731 | 2763 | Yes | Auto Scheduled | Commodity Code/Tarif | 2.78d | Fixed Duration | 5 | 0.25d |  | October 2, 2026 9:00 | October 6, 2026 4:15 | 10/2/26 9:00 | 10/6/26 4:15 | 6/1/26 8:45 | 6/3/26 4:00 | 0d | -89.03d | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 22.25h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.63 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1732 | 2764 | Yes | Auto Scheduled | Load | 21.25h | Fixed Units | 6 | 0.13d | 1727 | October 2, 2026 9:00 | October 6, 2026 3:15 | 10/2/26 9:00 | 10/6/26 3:15 | 6/1/26 8:45 | 6/3/26 3:00 | 0h | -712.25h | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:45 | Finish No Earlier Than | 4/20/26 5:00 | NA | NA | 4/23/26 10:51 | 21.25h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.63.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1733 | 2765 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1732 | October 6, 2026 3:15 | October 6, 2026 4:15 | 10/6/26 3:15 | 10/6/26 4:15 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -712.25h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.63.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1734 | 2766 | Yes | Auto Scheduled | SPL Master File | 0.25d | Fixed Duration | 5 | 0.25d |  | October 2, 2026 8:00 | October 2, 2026 10:00 | 10/2/26 8:00 | 10/2/26 10:00 | 6/3/26 2:00 | 6/3/26 4:00 | 0d | -86.38d | 0ed | 0 | NA | NA | March 13, 2025 8:00 | March 13, 2025 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.64 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1735 | 2767 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1726 | October 2, 2026 8:00 | October 2, 2026 9:00 | 10/2/26 8:00 | 10/2/26 9:00 | 6/3/26 2:00 | 6/3/26 3:00 | 0h | -691h | 0ed | 0 | NA | NA | March 13, 2025 8:00 | March 13, 2025 9:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.64.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1736 | 2768 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1735 | October 2, 2026 9:00 | October 2, 2026 10:00 | 10/2/26 9:00 | 10/2/26 10:00 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -691h | 0ed | 0 | NA | NA | March 13, 2025 9:00 | March 13, 2025 10:00 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.64.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1737 | 2769 | Yes | Auto Scheduled | Initialize Embargo situation | 0.38d | Fixed Duration | 5 | 0.38d |  | September 25, 2026 9:30 | September 25, 2026 1:30 | 9/25/26 9:30 | 9/25/26 1:30 | 6/3/26 1:00 | 6/3/26 4:00 | 0d | -81.69d | 0ed | 0 | NA | NA | April 13, 2026 2:15 | April 14, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.65 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1738 | 2770 | Yes | Auto Scheduled | Run report /SAPSLL/EMB_CNTRY_INIT | 1h | Fixed Units | 6 | 0.13d | 1718 | September 25, 2026 9:30 | September 25, 2026 10:30 | 9/25/26 9:30 | 9/25/26 10:30 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 13, 2026 2:15 | April 13, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.65.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1739 | 2771 | Yes | Auto Scheduled | Set Embargo situations | 1h | Fixed Units | 6 | 0.13d | 1738 | September 25, 2026 10:30 | September 25, 2026 11:30 | 9/25/26 10:30 | 9/25/26 11:30 | 6/3/26 2:00 | 6/3/26 3:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 13, 2026 3:15 | April 13, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.65.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1740 | 2772 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1739 | September 25, 2026 11:30 | September 25, 2026 1:30 | 9/25/26 11:30 | 9/25/26 1:30 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -653.5h | 0ed | 0 | NA | NA | April 13, 2026 4:15 | April 14, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.65.3 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1741 | 2773 | Yes | Auto Scheduled | GTS - SPL (Sanctioned party list) | 0.25d | Fixed Duration | 5 | 0.25d |  | October 2, 2026 9:00 | October 2, 2026 11:00 | 10/2/26 9:00 | 10/2/26 11:00 | 6/3/26 1:00 | 6/3/26 4:00 | 0d | -86.63d | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.66 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1742 | 2774 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 1727 | October 2, 2026 9:00 | October 2, 2026 10:00 | 10/2/26 9:00 | 10/2/26 10:00 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -693h | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.66.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1743 | 2775 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 1742 | October 2, 2026 10:00 | October 2, 2026 11:00 | 10/2/26 10:00 | 10/2/26 11:00 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -692h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.66.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1744 | 2776 | Yes | Auto Scheduled | RTR_CM17_Project Definition / Builder | 1.13d | Fixed Duration | 5 | 5.38d |  | September 24, 2026 9:00 | September 25, 2026 10:00 | 9/24/26 9:00 | 9/25/26 10:00 | 6/2/26 2:30 | 6/3/26 4:00 | 0d | -81.44d | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.67 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1745 | 2777 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1690 | September 24, 2026 9:00 | September 24, 2026 9:30 | 9/24/26 9:00 | 9/24/26 9:30 | 6/2/26 2:30 | 6/2/26 3:00 | 0m | -39090m | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 10:45 | Start No Earlier Than | 4/20/26 8:00 | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.67.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1746 | 2778 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1745 | September 24, 2026 9:30 | September 24, 2026 10:00 | 9/24/26 9:30 | 9/24/26 10:00 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -39060m | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.67.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1747 | 2779 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1746 | September 24, 2026 10:00 | September 24, 2026 11:00 | 9/24/26 10:00 | 9/24/26 11:00 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -651h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 16, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.67.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1748 | 2780 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1747 | September 24, 2026 11:00 | September 24, 2026 2:00 | 9/24/26 11:00 | 9/24/26 2:00 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -651h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.67.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1749 | 2781 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1748 | September 24, 2026 2:00 | September 24, 2026 4:00 | 9/24/26 2:00 | 9/24/26 4:00 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -651h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.67.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1750 | 2782 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1749 | September 24, 2026 4:00 | September 25, 2026 10:00 | 9/24/26 4:00 | 9/25/26 10:00 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -651h | 0ed | 0 | NA | NA | April 17, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.67.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1751 | 2783 | Yes | Auto Scheduled | RTR_CM18_WBS Element | 1.25d | Fixed Duration | 5 | 5.44d |  | September 24, 2026 8:30 | September 25, 2026 10:30 | 9/24/26 8:30 | 9/25/26 10:30 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -81.44d | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 17, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 9.25h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.68 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1752 | 2784 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1745 | September 24, 2026 9:30 | September 24, 2026 10:00 | 9/24/26 9:30 | 9/24/26 10:00 | 6/2/26 3:00 | 6/2/26 3:30 | 0m | -39090m | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:15 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.68.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1753 | 2785 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1752 | September 24, 2026 10:00 | September 24, 2026 10:30 | 9/24/26 10:00 | 9/24/26 10:30 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -39090m | 0ed | 0 | NA | NA | April 10, 2026 11:15 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.68.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1754 | 2786 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1753 | September 24, 2026 10:30 | September 24, 2026 11:30 | 9/24/26 10:30 | 9/24/26 11:30 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -651.5h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.68.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1755 | 2787 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1754 | September 24, 2026 11:30 | September 24, 2026 2:30 | 9/24/26 11:30 | 9/24/26 2:30 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -651.5h | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 17, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.68.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1756 | 2788 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1755 | September 24, 2026 2:30 | September 24, 2026 4:30 | 9/24/26 2:30 | 9/24/26 4:30 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -651.5h | 0ed | 0 | NA | NA | April 17, 2026 9:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.68.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1757 | 2789 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1756 | September 24, 2026 4:30 | September 25, 2026 10:30 | 9/24/26 4:30 | 9/25/26 10:30 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -651.5h | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.68.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1758 | 2790 | Yes | Auto Scheduled | UAT Mock Data Loads Complete | 15m | Fixed Units | 6 | 0.03d |  | September 24, 2026 8:30 | September 24, 2026 8:45 | 9/24/26 8:30 | 9/24/26 8:45 | 6/3/26 3:45 | 6/3/26 4:00 | 0m | -38505m | 0ed | 0 | NA | NA | April 21, 2026 3:15 | April 21, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/23/26 10:51 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.2.68.7 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1759 | 3360 | Yes | Auto Scheduled | UAT Master Data Loads Complete | 0m | Fixed Units | 4 | 0d | 1391 | October 8, 2026 2:00 | October 8, 2026 2:00 | 10/8/26 2:00 | 10/8/26 2:00 | 6/3/26 4:00 | 6/3/26 4:00 | 0m | -43560m | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 7:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.3 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1760 | 3350 | Yes | Auto Scheduled | Mock Transactional Data | 2d | Fixed Duration | 4 | 0d | 1759 | October 8, 2026 2:00 | October 12, 2026 2:00 | 10/8/26 2:00 | 10/12/26 2:00 | 8/12/26 3:45 | 8/14/26 3:45 | 0d | -40.78d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 6:46 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.4 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1761 | 3351 | Yes | Auto Scheduled | Inventory | 4h | Fixed Units | 5 | 0d | 998SS,1759SS | October 8, 2026 2:00 | October 9, 2026 9:00 | 10/8/26 2:00 | 10/9/26 9:00 | 8/12/26 3:45 | 8/13/26 10:45 | 0h | -326.25h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 6:46 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1762 | 3352 | Yes | Auto Scheduled | Open AR | 4h | Fixed Units | 5 | 0d | 1761 | October 9, 2026 9:00 | October 9, 2026 2:00 | 10/9/26 9:00 | 10/9/26 2:00 | 8/13/26 10:45 | 8/13/26 3:45 | 0h | -326.25h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 6:46 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1763 | 3353 | Yes | Auto Scheduled | Open AP | 4h | Fixed Units | 5 | 0d | 1762 | October 9, 2026 2:00 | October 12, 2026 9:00 | 10/9/26 2:00 | 10/12/26 9:00 | 8/13/26 3:45 | 8/14/26 10:45 | 0h | -326.25h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 6:46 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1764 | 3354 | Yes | Auto Scheduled | Bank and Cash | 4h | Fixed Units | 5 | 0d | 1763 | October 12, 2026 9:00 | October 12, 2026 2:00 | 10/12/26 9:00 | 10/12/26 2:00 | 8/14/26 10:45 | 8/14/26 3:45 | 0h | -326.25h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 6:46 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1765 | 3355 | Yes | Auto Scheduled | Open Purchase Orders(Manual) | 1d | Fixed Units | 5 | 0d | 1761 | October 9, 2026 9:00 | October 12, 2026 9:00 | 10/9/26 9:00 | 10/12/26 9:00 | 8/13/26 3:45 | 8/14/26 3:45 | 0d | -40.28d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 6:46 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1766 | 3356 | Yes | Auto Scheduled | Open Sales Orders(Manual) | 1d | Fixed Units | 5 | 0d | 1761 | October 9, 2026 9:00 | October 12, 2026 9:00 | 10/9/26 9:00 | 10/12/26 9:00 | 8/13/26 3:45 | 8/14/26 3:45 | 0d | -40.28d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 6:46 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1767 | 3357 | Yes | Auto Scheduled | Service Orders(Manual) | 0.5d | Fixed Units | 5 | 0d | 1761 | October 9, 2026 9:00 | October 9, 2026 2:00 | 10/9/26 9:00 | 10/9/26 2:00 | 8/14/26 10:45 | 8/14/26 3:45 | 0d | -39.78d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 6:46 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1768 | 3358 | Yes | Auto Scheduled | Open Production Orders(Manual) | 1d | Fixed Units | 5 | 0d | 1761 | October 9, 2026 9:00 | October 12, 2026 9:00 | 10/9/26 9:00 | 10/12/26 9:00 | 8/13/26 3:45 | 8/14/26 3:45 | 0d | -40.28d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 6:46 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.4.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1769 | 2938 | Yes | Auto Scheduled | UAT Mock Data Loads Complete | 15m | Fixed Units | 4 | 0.03d | 1760 | October 12, 2026 2:00 | October 12, 2026 2:15 | 10/12/26 2:00 | 10/12/26 2:15 | 8/14/26 3:45 | 8/14/26 4:00 | 0m | -19575m | 0ed | 0 | NA | NA | April 21, 2026 3:15 | April 21, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/24/26 5:27 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.4.5 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1770 | 4160 | Yes | Auto Scheduled | PROD Data Load Tasks P? | 10.56d | Fixed Duration | 3 | 288.78d | 134 | September 24, 2026 8:30 | October 8, 2026 2:01 | 9/24/26 8:30 | 10/8/26 2:01 | 5/20/26 10:29 | 10/8/26 2:01 | 0d | -90.75d | 0ed | 0 | NA | NA | March 13, 2025 8:00 | April 21, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 708.77h | 592h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1771 | 4161 | Yes | Auto Scheduled | PMO Authorization to Start Data Loads | 1m | Fixed Units | 4 | 0.03d | 134 | September 24, 2026 8:30 | September 24, 2026 8:31 | 9/24/26 8:30 | 9/24/26 8:31 | 5/20/26 10:29 | 5/20/26 10:30 | 0m | -43561m | 0ed | 0 | NA | NA | April 6, 2026 8:00 | April 6, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.02h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1772 | 4162 | Yes | Manually Scheduled | Master Data Loads | 5d | Fixed Duration | 4 | 0d | 1771 | September 24, 2026 8:31 | October 1, 2026 8:31 | 9/24/26 8:31 | 10/1/26 8:31 | 9/24/26 8:31 | 10/1/26 8:31 | 0d | 0d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 708.5h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1773 | 4163 | Yes | Auto Scheduled | RTR_CM02_Profit Center Hierarchy | 0.75d | Fixed Duration | 5 | 0.75d |  | September 24, 2026 8:31 | September 24, 2026 3:31 | 9/24/26 8:31 | 9/24/26 3:31 | 5/21/26 10:00 | 5/21/26 5:00 | 0d | -89.81d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.1 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1774 | 4164 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1771 | September 24, 2026 8:31 | September 24, 2026 9:31 | 9/24/26 8:31 | 9/24/26 9:31 | 5/21/26 10:00 | 5/21/26 11:00 | 0h | -718.52h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 9:15 | Start No Earlier Than | 4/6/26 8:00 | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.1.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1775 | 4165 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1774 | September 24, 2026 9:31 | September 24, 2026 11:31 | 9/24/26 9:31 | 9/24/26 11:31 | 5/21/26 11:00 | 5/21/26 2:00 | 0h | -718.52h | 0ed | 0 | NA | NA | April 6, 2026 9:15 | April 6, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.1.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1776 | 4166 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1775 | September 24, 2026 11:31 | September 24, 2026 3:31 | 9/24/26 11:31 | 9/24/26 3:31 | 5/21/26 2:00 | 5/21/26 5:00 | 0h | -718.52h | 0ed | 0 | NA | NA | April 6, 2026 11:15 | April 6, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.1.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1777 | 4167 | Yes | Auto Scheduled | RTR_CM03_Cost Center Hierarchy | 0.75d | Fixed Duration | 5 | 0.75d |  | September 24, 2026 3:31 | September 25, 2026 1:31 | 9/24/26 3:31 | 9/25/26 1:31 | 5/22/26 8:00 | 5/22/26 3:00 | 0d | -89.81d | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1778 | 4168 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1776 | September 24, 2026 3:31 | September 24, 2026 4:31 | 9/24/26 3:31 | 9/24/26 4:31 | 5/22/26 8:00 | 5/22/26 9:00 | 0h | -718.52h | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 6, 2026 4:15 | Start No Earlier Than | 4/6/26 8:00 | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1779 | 4169 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1778 | September 24, 2026 4:31 | September 25, 2026 9:31 | 9/24/26 4:31 | 9/25/26 9:31 | 5/22/26 9:00 | 5/22/26 11:00 | 0h | -718.52h | 0ed | 0 | NA | NA | April 6, 2026 4:15 | April 7, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1780 | 4170 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1779 | September 25, 2026 9:31 | September 25, 2026 1:31 | 9/25/26 9:31 | 9/25/26 1:31 | 5/22/26 11:00 | 5/22/26 3:00 | 0h | -718.52h | 0ed | 0 | NA | NA | April 7, 2026 9:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.2.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1781 | 4171 | Yes | Auto Scheduled | RTR_CM01_GL_Account_Master to CC 1000 | 2.44d | Fixed Duration | 5 | 1.81d |  | September 25, 2026 1:31 | September 30, 2026 8:01 | 9/25/26 1:31 | 9/30/26 8:01 | 5/22/26 3:00 | 5/27/26 9:30 | 0d | -89.81d | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 9, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 16h | 16h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1782 | 4172 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1780 | September 25, 2026 1:31 | September 25, 2026 2:31 | 9/25/26 1:31 | 9/25/26 2:31 | 5/22/26 3:00 | 5/22/26 4:00 | 0h | -718.52h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 2:15 | Start No Earlier Than | 4/6/26 8:00 | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1783 | 4173 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1782 | September 25, 2026 2:31 | September 25, 2026 4:31 | 9/25/26 2:31 | 9/25/26 4:31 | 5/22/26 4:00 | 5/25/26 9:00 | 0h | -718.52h | 0ed | 0 | NA | NA | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1784 | 4174 | Yes | Auto Scheduled | Simulate Load | 6h | Fixed Units | 6 | 0.75d | 1783 | September 25, 2026 4:31 | September 28, 2026 2:31 | 9/25/26 4:31 | 9/28/26 2:31 | 5/25/26 9:00 | 5/25/26 4:00 | 0h | -718.52h | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1785 | 4175 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1784 | September 28, 2026 2:31 | September 29, 2026 9:01 | 9/28/26 2:31 | 9/29/26 9:01 | 5/25/26 4:00 | 5/26/26 10:30 | 0h | -718.52h | 0ed | 0 | NA | NA | April 8, 2026 8:15 | April 8, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1786 | 4176 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1785 | September 29, 2026 9:01 | September 29, 2026 10:01 | 9/29/26 9:01 | 9/29/26 10:01 | 5/26/26 10:30 | 5/26/26 11:30 | 0h | -718.52h | 0ed | 0 | NA | NA | April 8, 2026 11:45 | April 8, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1787 | 4177 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1786 | September 29, 2026 10:01 | September 29, 2026 1:01 | 9/29/26 10:01 | 9/29/26 1:01 | 5/26/26 11:30 | 5/26/26 2:30 | 0h | -718.52h | 0ed | 0 | NA | NA | April 8, 2026 1:45 | April 8, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1788 | 4178 | Yes | Auto Scheduled | Extend GL to all Company Codes | 2h | Fixed Units | 6 | 0.25d | 1787 | September 29, 2026 1:01 | September 29, 2026 3:01 | 9/29/26 1:01 | 9/29/26 3:01 | 5/26/26 2:30 | 5/26/26 4:30 | 0h | -718.52h | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1789 | 4179 | Yes | Auto Scheduled | Post GL Extention Validation | 2h | Fixed Units | 6 | 0.25d | 1788 | September 29, 2026 3:01 | September 30, 2026 8:01 | 9/29/26 3:01 | 9/30/26 8:01 | 5/26/26 4:30 | 5/27/26 9:30 | 0h | -718.52h | 0ed | 0 | NA | NA | April 9, 2026 8:45 | April 9, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.3.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1790 | 4180 | Yes | Auto Scheduled | RTR_CM05_Profit_Center | 1.13d | Fixed Duration | 5 | 1.13d |  | September 24, 2026 3:31 | September 25, 2026 4:31 | 9/24/26 3:31 | 9/25/26 4:31 | 5/29/26 8:45 | 6/1/26 9:45 | 0d | -84.72d | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1791 | 4181 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1776 | September 24, 2026 3:31 | September 24, 2026 4:31 | 9/24/26 3:31 | 9/24/26 4:31 | 5/29/26 8:45 | 5/29/26 9:45 | 0h | -677.77h | 0ed | 0 | NA | NA | April 6, 2026 3:15 | April 6, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1792 | 4182 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1791 | September 24, 2026 4:31 | September 25, 2026 9:31 | 9/24/26 4:31 | 9/25/26 9:31 | 5/29/26 9:45 | 5/29/26 11:45 | 0h | -677.77h | 0ed | 0 | NA | NA | April 6, 2026 4:15 | April 7, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1793 | 4183 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1792 | September 25, 2026 9:31 | September 25, 2026 10:31 | 9/25/26 9:31 | 9/25/26 10:31 | 5/29/26 11:45 | 5/29/26 1:45 | 0h | -677.77h | 0ed | 0 | NA | NA | April 7, 2026 9:15 | April 7, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1794 | 4184 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1793 | September 25, 2026 10:31 | September 25, 2026 1:31 | 9/25/26 10:31 | 9/25/26 1:31 | 5/29/26 1:45 | 5/29/26 3:45 | 0h | -677.77h | 0ed | 0 | NA | NA | April 7, 2026 10:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1795 | 4185 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1794 | September 25, 2026 1:31 | September 25, 2026 2:31 | 9/25/26 1:31 | 9/25/26 2:31 | 5/29/26 3:45 | 5/29/26 4:45 | 0h | -677.77h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1796 | 4186 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1795 | September 25, 2026 2:31 | September 25, 2026 4:31 | 9/25/26 2:31 | 9/25/26 4:31 | 5/29/26 4:45 | 6/1/26 9:45 | 0h | -677.77h | 0ed | 0 | NA | NA | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.4.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1797 | 4187 | Yes | Auto Scheduled | RTR_CM04_Cost_Center | 1.13d | Fixed Duration | 5 | 1.13d |  | September 25, 2026 4:31 | September 29, 2026 8:31 | 9/25/26 4:31 | 9/29/26 8:31 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -83.19d | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 9, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1798 | 4188 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1796 | September 25, 2026 4:31 | September 28, 2026 8:31 | 9/25/26 4:31 | 9/28/26 8:31 | 6/2/26 3:00 | 6/2/26 4:00 | 0h | -665.52h | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 8, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1799 | 4189 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1798 | September 28, 2026 8:31 | September 28, 2026 10:31 | 9/28/26 8:31 | 9/28/26 10:31 | 6/2/26 4:00 | 6/3/26 9:00 | 0h | -665.52h | 0ed | 0 | NA | NA | April 8, 2026 8:15 | April 8, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1800 | 4190 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1799 | September 28, 2026 10:31 | September 28, 2026 11:31 | 9/28/26 10:31 | 9/28/26 11:31 | 6/3/26 9:00 | 6/3/26 10:00 | 0h | -665.52h | 0ed | 0 | NA | NA | April 8, 2026 10:15 | April 8, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1801 | 4191 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1800 | September 28, 2026 11:31 | September 28, 2026 2:31 | 9/28/26 11:31 | 9/28/26 2:31 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -665.52h | 0ed | 0 | NA | NA | April 8, 2026 11:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1802 | 4192 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1801 | September 28, 2026 2:31 | September 28, 2026 3:31 | 9/28/26 2:31 | 9/28/26 3:31 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -665.52h | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 8, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1803 | 4193 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1802 | September 28, 2026 3:31 | September 29, 2026 8:31 | 9/28/26 3:31 | 9/29/26 8:31 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -665.52h | 0ed | 0 | NA | NA | April 8, 2026 3:15 | April 9, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.5.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1804 | 4194 | Yes | Auto Scheduled | Manual Configuration Activities in QS5 | 8.94d | Fixed Duration | 5 | 7.16d | 40 | September 24, 2026 8:31 | October 7, 2026 8:01 | 9/24/26 8:31 | 10/7/26 8:01 | 5/27/26 4:00 | 6/3/26 4:00 | 0d | -89.13d | 0ed | 0 | NA | NA | April 6, 2026 1:00 | April 15, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 43h | 43h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.6 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1805 | 4195 | Yes | Auto Scheduled | Open Client | 30m | Fixed Units | 6 | 0.06d |  | September 24, 2026 8:31 | September 24, 2026 9:01 | 9/24/26 8:31 | 9/24/26 9:01 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -38521m | 0ed | 0 | NA | NA | April 6, 2026 1:00 | April 6, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.6.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1806 | 4196 | Yes | Auto Scheduled | Service Enterprise Setup | 5d | Fixed Units | 6 | 5d | 1773,1777,1781 | September 30, 2026 8:01 | October 7, 2026 8:01 | 9/30/26 8:01 | 10/7/26 8:01 | 5/27/26 4:00 | 6/3/26 4:00 | 0d | -89.13d | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 15, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 40h | 40h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.6.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1807 | 4197 | Yes | Auto Scheduled | Close Client | 30m | Fixed Units | 6 | 0.06d |  | September 24, 2026 8:31 | September 24, 2026 9:01 | 9/24/26 8:31 | 9/24/26 9:01 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -38521m | 0ed | 0 | NA | NA | April 6, 2026 1:00 | April 6, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.6.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1808 | 4198 | Yes | Auto Scheduled | Intercompany Business Partner Setup | 2h | Fixed Units | 6 | 0.25d | 1773,1777,1789 | September 30, 2026 8:01 | September 30, 2026 10:01 | 9/30/26 8:01 | 9/30/26 10:01 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -675.02h | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.6.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1809 | 4199 | Yes | Auto Scheduled | RTR_CM09_Activity_Type | 1.38d | Fixed Duration | 5 | 1.22d |  | September 29, 2026 1:01 | September 30, 2026 4:01 | 9/29/26 1:01 | 9/30/26 4:01 | 6/2/26 1:00 | 6/3/26 4:00 | 0d | -85d | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.7 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1810 | 4200 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1787 | September 29, 2026 1:01 | September 29, 2026 3:16 | 9/29/26 1:01 | 9/29/26 3:16 | 6/2/26 1:00 | 6/2/26 3:15 | 0h | -680.02h | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 8, 2026 4:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.7.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1811 | 4201 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1810 | September 29, 2026 3:16 | September 30, 2026 9:01 | 9/29/26 3:16 | 9/30/26 9:01 | 6/2/26 3:15 | 6/3/26 9:00 | 0h | -680.02h | 0ed | 0 | NA | NA | April 8, 2026 3:15 | April 9, 2026 9:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.7.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1812 | 4202 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1811 | September 30, 2026 9:01 | September 30, 2026 10:01 | 9/30/26 9:01 | 9/30/26 10:01 | 6/3/26 9:00 | 6/3/26 10:00 | 0h | -680.02h | 0ed | 0 | NA | NA | April 9, 2026 9:00 | April 9, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.7.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1813 | 4203 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1812 | September 30, 2026 10:01 | September 30, 2026 1:01 | 9/30/26 10:01 | 9/30/26 1:01 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -680.02h | 0ed | 0 | NA | NA | April 9, 2026 10:00 | April 9, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.7.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1814 | 4204 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1813 | September 30, 2026 1:01 | September 30, 2026 2:01 | 9/30/26 1:01 | 9/30/26 2:01 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -680.02h | 0ed | 0 | NA | NA | April 9, 2026 1:00 | April 9, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.7.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1815 | 4205 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1814 | September 30, 2026 2:01 | September 30, 2026 4:01 | 9/30/26 2:01 | 9/30/26 4:01 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -680.02h | 0ed | 0 | NA | NA | April 9, 2026 2:00 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.7.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1816 | 4206 | Yes | Auto Scheduled | RTR_CM12_Activity Rates | 1.13d | Fixed Duration | 5 | 1.13d |  | September 25, 2026 1:31 | September 28, 2026 2:31 | 9/25/26 1:31 | 9/28/26 2:31 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -82.81d | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.8 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1817 | 4207 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1780 | September 25, 2026 1:31 | September 25, 2026 2:31 | 9/25/26 1:31 | 9/25/26 2:31 | 6/2/26 3:00 | 6/2/26 4:00 | 0h | -662.52h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.8.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1818 | 4208 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1817 | September 25, 2026 2:31 | September 25, 2026 4:31 | 9/25/26 2:31 | 9/25/26 4:31 | 6/2/26 4:00 | 6/3/26 9:00 | 0h | -662.52h | 0ed | 0 | NA | NA | April 7, 2026 2:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.8.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1819 | 4209 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1818 | September 25, 2026 4:31 | September 28, 2026 8:31 | 9/25/26 4:31 | 9/28/26 8:31 | 6/3/26 9:00 | 6/3/26 10:00 | 0h | -662.52h | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 8, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.8.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1820 | 4210 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1819 | September 28, 2026 8:31 | September 28, 2026 10:31 | 9/28/26 8:31 | 9/28/26 10:31 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -662.52h | 0ed | 0 | NA | NA | April 8, 2026 8:15 | April 8, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.8.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1821 | 4211 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1820 | September 28, 2026 10:31 | September 28, 2026 11:31 | 9/28/26 10:31 | 9/28/26 11:31 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -662.52h | 0ed | 0 | NA | NA | April 8, 2026 10:15 | April 8, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.8.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1822 | 4212 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1821 | September 28, 2026 11:31 | September 28, 2026 2:31 | 9/28/26 11:31 | 9/28/26 2:31 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -662.52h | 0ed | 0 | NA | NA | April 8, 2026 11:15 | April 8, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.8.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1823 | 4213 | Yes | Auto Scheduled | RTR_CM06_Bank_master | 3.81d | Fixed Duration | 5 | 1.22d |  | September 24, 2026 8:31 | September 29, 2026 4:01 | 9/24/26 8:31 | 9/29/26 4:01 | 5/26/26 3:00 | 6/3/26 4:00 | 0d | -86.31d | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 9, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 13h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.9 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1824 | 4214 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1787 | September 29, 2026 1:01 | September 29, 2026 2:01 | 9/29/26 1:01 | 9/29/26 2:01 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -672.02h | 0ed | 0 | NA | NA | April 8, 2026 2:15 | April 8, 2026 4:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.9.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1825 | 4215 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1824 | September 29, 2026 2:01 | September 29, 2026 4:01 | 9/29/26 2:01 | 9/29/26 4:01 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -672.02h | 0ed | 0 | NA | NA | April 8, 2026 4:30 | April 9, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.9.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1826 | 4216 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d |  | September 24, 2026 8:31 | September 24, 2026 9:31 | 9/24/26 8:31 | 9/24/26 9:31 | 5/26/26 3:00 | 5/26/26 4:00 | 0h | -690.52h | 0ed | 0 | NA | NA | April 9, 2026 9:30 | April 9, 2026 10:30 | Start No Earlier Than | 4/15/26 8:00 | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.9.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1827 | 4217 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1826 | September 24, 2026 9:31 | September 24, 2026 11:31 | 9/24/26 9:31 | 9/24/26 11:31 | 5/26/26 4:00 | 5/27/26 9:00 | 0h | -690.52h | 0ed | 0 | NA | NA | April 9, 2026 10:30 | April 9, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.9.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1828 | 4218 | Yes | Auto Scheduled | Load | 5h | Fixed Units | 6 | 0.13d | 1827 | September 24, 2026 11:31 | September 25, 2026 8:31 | 9/24/26 11:31 | 9/25/26 8:31 | 5/27/26 9:00 | 5/27/26 3:00 | 0h | -690.52h | 0ed | 0 | NA | NA | April 9, 2026 1:30 | April 9, 2026 2:30 | Finish No Earlier Than | 4/15/26 5:00 | NA | NA | 4/30/26 2:05 | 5h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.9.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1829 | 4219 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1828 | September 25, 2026 8:31 | September 25, 2026 3:01 | 9/25/26 8:31 | 9/25/26 3:01 | 5/27/26 3:00 | 5/28/26 11:30 | 0h | -690.52h | 0ed | 0 | NA | NA | April 9, 2026 8:00 | April 9, 2026 4:00 | Finish No Earlier Than | 4/14/26 5:00 | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.9.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1830 | 4220 | Yes | Auto Scheduled | RTR_CM08_Exchange_Rates | 1.13d | Fixed Duration | 5 | 1.13d |  | September 25, 2026 8:31 | September 28, 2026 9:31 | 9/25/26 8:31 | 9/28/26 9:31 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -82.31d | 0ed | 0 | NA | NA | April 9, 2026 2:30 | April 10, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.10 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1831 | 4221 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | Fixed Units | 6 | 0.13d | 1828 | September 25, 2026 8:31 | September 25, 2026 9:31 | 9/25/26 8:31 | 9/25/26 9:31 | 6/2/26 3:00 | 6/2/26 4:00 | 0h | -658.52h | 0ed | 0 | NA | NA | April 9, 2026 2:30 | April 9, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.10.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1832 | 4222 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1831 | September 25, 2026 9:31 | September 25, 2026 11:31 | 9/25/26 9:31 | 9/25/26 11:31 | 6/2/26 4:00 | 6/3/26 9:00 | 0h | -658.52h | 0ed | 0 | NA | NA | April 9, 2026 3:30 | April 10, 2026 8:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.10.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1833 | 4223 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1832 | September 25, 2026 11:31 | September 25, 2026 1:31 | 9/25/26 11:31 | 9/25/26 1:31 | 6/3/26 9:00 | 6/3/26 10:00 | 0h | -658.52h | 0ed | 0 | NA | NA | April 10, 2026 8:30 | April 10, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.10.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1834 | 4224 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1833 | September 25, 2026 1:31 | September 25, 2026 3:31 | 9/25/26 1:31 | 9/25/26 3:31 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -658.52h | 0ed | 0 | NA | NA | April 10, 2026 9:30 | April 10, 2026 11:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.10.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1835 | 4225 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1834 | September 25, 2026 3:31 | September 25, 2026 4:31 | 9/25/26 3:31 | 9/25/26 4:31 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -658.52h | 0ed | 0 | NA | NA | April 10, 2026 11:30 | April 10, 2026 1:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.10.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1836 | 4226 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1835 | September 25, 2026 4:31 | September 28, 2026 9:31 | 9/25/26 4:31 | 9/28/26 9:31 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -658.52h | 0ed | 0 | NA | NA | April 10, 2026 1:30 | April 10, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.10.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1837 | 4227 | Yes | Auto Scheduled | RTR_CM14_Cost Element_Group | 4.44d | Fixed Duration | 5 | 4.78d |  | September 29, 2026 1:01 | October 5, 2026 4:31 | 9/29/26 1:01 | 10/5/26 4:31 | 5/28/26 11:30 | 6/3/26 4:00 | 0d | -88.06d | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 35.5h | 38.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.11 | 500 | No | Yes | Yes |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1838 | 4228 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 4.16d | 1787 | September 29, 2026 1:01 | September 29, 2026 1:31 | 9/29/26 1:01 | 9/29/26 1:31 | 5/28/26 11:30 | 5/28/26 12:00 | 0m | -42271m | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 14, 2026 5:00 | Finish No Earlier Than | 4/14/26 5:00 | NA | NA | 4/30/26 2:05 | 0.5h | 33.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.11.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1839 | 4229 | Yes | Auto Scheduled | Load | 32h | Fixed Units | 6 | 0.25d | 1838 | September 29, 2026 1:31 | October 5, 2026 1:31 | 9/29/26 1:31 | 10/5/26 1:31 | 5/28/26 1:00 | 6/3/26 12:00 | 0h | -704.52h | 0ed | 0 | NA | NA | April 15, 2026 8:00 | April 15, 2026 10:00 | Finish No Earlier Than | 4/21/26 5:00 | NA | NA | 4/30/26 2:05 | 32h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.11.2 | 500 | No | No | No |  |  | Black | 2026-04-20 15:36 - jsw73 - Start ignored — already in progress | [6 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1840 | 4230 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1839 | October 5, 2026 1:31 | October 5, 2026 4:31 | 10/5/26 1:31 | 10/5/26 4:31 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -704.52h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 2:00 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.11.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1841 | 4231 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Bill-To | 2h | Fixed Units | 5 | 0d |  | September 24, 2026 8:31 | September 24, 2026 10:31 | 9/24/26 8:31 | 9/24/26 10:31 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -643.52h | 0ed | 0 | NA | NA | April 16, 2025 8:00 | April 16, 2025 8:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.12 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1842 | 4232 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Ship-To | 1.5d | Fixed Duration | 5 | 3.13d |  | September 29, 2026 1:01 | October 1, 2026 8:01 | 9/29/26 1:01 | 10/1/26 8:01 | 5/26/26 4:30 | 6/3/26 4:00 | 0d | -89.56d | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 13.25h | 36h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.13 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1843 | 4233 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1787 | September 29, 2026 1:01 | September 29, 2026 1:31 | 9/29/26 1:01 | 9/29/26 1:31 | 5/26/26 4:30 | 5/26/26 5:00 | 0m | -42991m | 0ed | 0 | NA | NA | April 8, 2026 3:45 | April 8, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.13.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1844 | 4234 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1843 | September 29, 2026 1:31 | September 29, 2026 2:01 | 9/29/26 1:31 | 9/29/26 2:01 | 5/27/26 8:00 | 5/27/26 8:30 | 0m | -42991m | 0ed | 0 | NA | NA | April 8, 2026 4:15 | April 8, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.13.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1845 | 4235 | Yes | Auto Scheduled | Open client for BP number range update | 30m | Fixed Units | 6 | 1d | 1844 | September 29, 2026 2:01 | September 29, 2026 2:31 | 9/29/26 2:01 | 9/29/26 2:31 | 6/3/26 2:45 | 6/3/26 3:15 | 0m | -40276m | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 9, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.13.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1846 | 4236 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 30m | Fixed Units | 6 | 1d | 1845 | September 29, 2026 2:31 | September 29, 2026 3:01 | 9/29/26 2:31 | 9/29/26 3:01 | 6/3/26 3:15 | 6/3/26 3:45 | 0m | -40276m | 0ed | 0 | NA | NA | April 9, 2026 4:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.13.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1847 | 4237 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 6 | 1d | 1846 | September 29, 2026 3:01 | September 29, 2026 3:16 | 9/29/26 3:01 | 9/29/26 3:16 | 6/3/26 3:45 | 6/3/26 4:00 | 0m | -40276m | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.25h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.13.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1848 | 4238 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1844 | September 29, 2026 2:01 | September 29, 2026 3:01 | 9/29/26 2:01 | 9/29/26 3:01 | 5/27/26 8:30 | 5/27/26 9:30 | 0h | -716.52h | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.13.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1849 | 4239 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | Fixed Units | 6 | 0.5d | 1848 | September 29, 2026 3:01 | September 30, 2026 10:01 | 9/29/26 3:01 | 9/30/26 10:01 | 6/2/26 2:00 | 6/3/26 9:00 | 0h | -681.02h | 0ed | 0 | NA | NA | April 9, 2026 8:45 | April 9, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.13.7 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1850 | 4240 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 6 | 0.38d | 1849 | September 30, 2026 10:01 | September 30, 2026 2:01 | 9/30/26 10:01 | 9/30/26 2:01 | 6/3/26 9:00 | 6/3/26 12:00 | 0h | -681.02h | 0ed | 0 | NA | NA | April 9, 2026 1:45 | April 9, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.13.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1851 | 4241 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1850 | September 30, 2026 2:01 | October 1, 2026 8:01 | 9/30/26 2:01 | 10/1/26 8:01 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -681.02h | 0ed | 0 | NA | NA | April 9, 2026 4:45 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.13.9 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1852 | 4242 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Sold-To | 1.63d | Fixed Duration | 5 | 1.63d |  | September 29, 2026 2:01 | October 1, 2026 10:01 | 9/29/26 2:01 | 10/1/26 10:01 | 5/27/26 9:30 | 6/3/26 4:00 | 0d | -89.44d | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 11.75h | 11.75h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.14 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1853 | 4243 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1844 | September 29, 2026 2:01 | September 29, 2026 2:31 | 9/29/26 2:01 | 9/29/26 2:31 | 6/3/26 3:00 | 6/3/26 3:30 | 0m | -40261m | 0ed | 0 | NA | NA | April 8, 2026 4:45 | April 9, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.14.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1854 | 4244 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1853 | September 29, 2026 2:31 | September 29, 2026 3:01 | 9/29/26 2:31 | 9/29/26 3:01 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -40261m | 0ed | 0 | NA | NA | April 9, 2026 8:15 | April 9, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.14.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1855 | 4245 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1789,1848 | September 30, 2026 8:01 | September 30, 2026 9:01 | 9/30/26 8:01 | 9/30/26 9:01 | 5/27/26 9:30 | 5/27/26 10:30 | 0h | -718.52h | 0ed | 0 | NA | NA | April 9, 2026 10:45 | April 9, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.14.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1856 | 4246 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | Fixed Units | 6 | 0.38d | 1855 | September 30, 2026 9:01 | September 30, 2026 1:01 | 9/30/26 9:01 | 9/30/26 1:01 | 5/27/26 10:30 | 5/27/26 2:30 | 0h | -718.52h | 0ed | 0 | NA | NA | April 9, 2026 11:45 | April 9, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.14.4 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1857 | 4247 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 6 | 0.38d | 1856 | September 30, 2026 1:01 | September 30, 2026 4:01 | 9/30/26 1:01 | 9/30/26 4:01 | 5/27/26 2:30 | 5/28/26 8:30 | 0h | -718.52h | 0ed | 0 | NA | NA | April 9, 2026 3:45 | April 10, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.14.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1858 | 4248 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1857 | September 30, 2026 4:01 | October 1, 2026 10:01 | 9/30/26 4:01 | 10/1/26 10:01 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -683.02h | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.14.6 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1859 | 4249 | Yes | Auto Scheduled | Open client for BP number range update | 15m | Fixed Units | 6 | 0.03d | 1848 | September 29, 2026 3:01 | September 29, 2026 3:16 | 9/29/26 3:01 | 9/29/26 3:16 | 6/3/26 3:15 | 6/3/26 3:30 | 0m | -40306m | 0ed | 0 | NA | NA | April 9, 2026 8:45 | April 9, 2026 9:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.14.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1860 | 4250 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 15m | Fixed Units | 6 | 0.03d | 1859 | September 29, 2026 3:16 | September 29, 2026 3:31 | 9/29/26 3:16 | 9/29/26 3:31 | 6/3/26 3:30 | 6/3/26 3:45 | 0m | -40306m | 0ed | 0 | NA | NA | April 9, 2026 9:00 | April 9, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.14.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1861 | 4251 | Yes | Auto Scheduled | Close Client | 15m | Fixed Units | 6 | 0.03d | 1860 | September 29, 2026 3:31 | September 29, 2026 3:46 | 9/29/26 3:31 | 9/29/26 3:46 | 6/3/26 3:45 | 6/3/26 4:00 | 0m | -40306m | 0ed | 0 | NA | NA | April 9, 2026 9:15 | April 9, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.14.9 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1862 | 4252 | Yes | Auto Scheduled | PTP_CM27_Vendor Master as Customer - FLCU01 | 4.81d | Fixed Duration | 5 | 2.31d |  | September 30, 2026 4:01 | October 7, 2026 2:31 | 9/30/26 4:01 | 10/7/26 2:31 | 5/28/26 8:30 | 6/3/26 4:00 | 0d | -89.81d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 14, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 19.25h | 19.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.15 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1863 | 4253 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1857 | September 30, 2026 4:01 | October 1, 2026 8:01 | 9/30/26 4:01 | 10/1/26 8:01 | 5/28/26 8:30 | 5/28/26 9:30 | 0h | -718.52h | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.15.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1864 | 4254 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1863 | October 1, 2026 8:01 | October 1, 2026 10:01 | 10/1/26 8:01 | 10/1/26 10:01 | 5/28/26 9:30 | 5/28/26 11:30 | 0h | -718.52h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.15.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1865 | 4255 | Yes | Auto Scheduled | Simulate Load | 11.25h | Fixed Units | 6 | 1.41d | 1829,1864 | October 1, 2026 10:01 | October 2, 2026 2:16 | 10/1/26 10:01 | 10/2/26 2:16 | 5/28/26 11:30 | 5/29/26 3:45 | 0h | -718.52h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 13, 2026 5:00 | Finish No Earlier Than | 4/13/26 5:00 | NA | NA | 4/30/26 2:05 | 11.25h | 11.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.15.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1866 | 4256 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1865 | October 2, 2026 2:16 | October 6, 2026 9:01 | 10/2/26 2:16 | 10/6/26 9:01 | 5/29/26 3:45 | 6/2/26 10:30 | 0h | -718.52h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 14, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.15.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1867 | 4257 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1866 | October 6, 2026 9:01 | October 7, 2026 11:31 | 10/6/26 9:01 | 10/7/26 11:31 | 6/2/26 10:30 | 6/3/26 2:00 | 0h | -718.52h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 14, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.15.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1868 | 4258 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1867 | October 7, 2026 11:31 | October 7, 2026 2:31 | 10/7/26 11:31 | 10/7/26 2:31 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -718.52h | 0ed | 0 | NA | NA | April 14, 2026 10:15 | April 14, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.15.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1869 | 4259 | Yes | Auto Scheduled | OTC_CM23_Customer_Hierarchy | 0.69d | Fixed Duration | 5 | 0.69d |  | September 30, 2026 4:01 | October 1, 2026 1:31 | 9/30/26 4:01 | 10/1/26 1:31 | 6/3/26 9:30 | 6/3/26 4:00 | 0d | -85.69d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.16 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1870 | 4260 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1857 | September 30, 2026 4:01 | September 30, 2026 4:31 | 9/30/26 4:01 | 9/30/26 4:31 | 6/3/26 9:30 | 6/3/26 10:00 | 0m | -41131m | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:15 | Start No Earlier Than | 4/6/26 8:00 | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.16.1 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1871 | 4261 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1870 | September 30, 2026 4:31 | October 1, 2026 9:31 | 9/30/26 4:31 | 10/1/26 9:31 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -685.52h | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 1:15 | Start No Earlier Than | 4/15/26 8:00 | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.16.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1872 | 4262 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1871 | October 1, 2026 9:31 | October 1, 2026 1:31 | 10/1/26 9:31 | 10/1/26 1:31 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -685.52h | 0ed | 0 | NA | NA | April 10, 2026 1:15 | April 10, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.16.3 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1873 | 4263 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Z001 - External Sales Rep | 3.38d | Fixed Duration | 5 | 1.13d |  | September 30, 2026 4:01 | October 6, 2026 10:01 | 9/30/26 4:01 | 10/6/26 10:01 | 5/29/26 1:00 | 6/3/26 4:00 | 0d | -88.38d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.17 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1874 | 4264 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1857 | September 30, 2026 4:01 | October 1, 2026 8:01 | 9/30/26 4:01 | 10/1/26 8:01 | 5/29/26 1:00 | 5/29/26 2:00 | 0h | -707.02h | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.17.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1875 | 4265 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1874 | October 1, 2026 8:01 | October 1, 2026 10:01 | 10/1/26 8:01 | 10/1/26 10:01 | 5/29/26 2:00 | 5/29/26 4:00 | 0h | -707.02h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.17.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1876 | 4266 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1829,1875 | October 1, 2026 10:01 | October 1, 2026 11:01 | 10/1/26 10:01 | 10/1/26 11:01 | 5/29/26 4:00 | 5/29/26 5:00 | 0h | -707.02h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.17.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1877 | 4267 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1876 | October 1, 2026 11:01 | October 1, 2026 2:01 | 10/1/26 11:01 | 10/1/26 2:01 | 6/1/26 8:00 | 6/1/26 10:00 | 0h | -707.02h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.17.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1878 | 4268 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1877 | October 1, 2026 2:01 | October 6, 2026 8:01 | 10/1/26 2:01 | 10/6/26 8:01 | 6/1/26 10:00 | 6/3/26 2:00 | 0h | -707.02h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.17.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1879 | 4269 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1878 | October 6, 2026 8:01 | October 6, 2026 10:01 | 10/6/26 8:01 | 10/6/26 10:01 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -707.02h | 0ed | 0 | NA | NA | April 13, 2026 8:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.17.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1880 | 4270 | Yes | Auto Scheduled | RTR_CM10_Credit_Management_Role | 1.84d | Fixed Duration | 5 | 1.13d |  | September 30, 2026 4:01 | October 2, 2026 2:46 | 9/30/26 4:01 | 10/2/26 2:46 | 6/1/26 10:15 | 6/3/26 9:00 | 0d | -87.6d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.18 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1881 | 4271 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1857 | September 30, 2026 4:01 | September 30, 2026 4:31 | 9/30/26 4:01 | 9/30/26 4:31 | 6/1/26 10:15 | 6/1/26 10:45 | 0m | -42046m | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.18.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1882 | 4272 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1881 | September 30, 2026 4:31 | October 1, 2026 8:01 | 9/30/26 4:31 | 10/1/26 8:01 | 6/1/26 10:45 | 6/1/26 11:15 | 0m | -42046m | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.18.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1883 | 4273 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1882 | October 1, 2026 8:01 | October 1, 2026 9:01 | 10/1/26 8:01 | 10/1/26 9:01 | 6/1/26 11:15 | 6/1/26 1:15 | 0h | -700.77h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.18.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1884 | 4274 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1883 | October 1, 2026 9:01 | October 1, 2026 11:31 | 10/1/26 9:01 | 10/1/26 11:31 | 6/1/26 1:15 | 6/1/26 3:45 | 0h | -700.77h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.18.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1885 | 4275 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1884 | October 1, 2026 11:31 | October 1, 2026 4:31 | 10/1/26 11:31 | 10/1/26 4:31 | 6/1/26 3:45 | 6/2/26 10:45 | 0h | -700.77h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.18.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1886 | 4276 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1885 | October 1, 2026 4:31 | October 2, 2026 2:46 | 10/1/26 4:31 | 10/2/26 2:46 | 6/2/26 10:45 | 6/3/26 9:00 | 0h | -700.77h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.18.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1887 | 4277 | Yes | Auto Scheduled | PTP_CM27_Vendor Master | 6.28d | Fixed Duration | 5 | 2.91d |  | September 24, 2026 8:31 | October 2, 2026 10:46 | 9/24/26 8:31 | 10/2/26 10:46 | 5/20/26 10:30 | 6/3/26 4:00 | 0d | -90.75d | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 10.25h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.19 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1888 | 4278 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1874 | October 1, 2026 8:01 | October 1, 2026 9:01 | 10/1/26 8:01 | 10/1/26 9:01 | 6/2/26 1:15 | 6/2/26 2:15 | 0h | -691.77h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.19.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1889 | 4279 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1888 | October 1, 2026 9:01 | October 1, 2026 11:01 | 10/1/26 9:01 | 10/1/26 11:01 | 6/2/26 2:15 | 6/2/26 4:15 | 0h | -691.77h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.19.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1890 | 4280 | Yes | Auto Scheduled | Simulate Load | 2.25h | Fixed Units | 6 | 0.13d | 1889 | October 1, 2026 11:01 | October 1, 2026 2:16 | 10/1/26 11:01 | 10/1/26 2:16 | 6/2/26 4:15 | 6/3/26 9:30 | 0h | -691.77h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 14, 2026 2:00 | Finish No Earlier Than | 4/10/26 5:00 | NA | NA | 4/30/26 2:05 | 2.25h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.19.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1891 | 4281 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1890 | October 1, 2026 2:16 | October 2, 2026 10:46 | 10/1/26 2:16 | 10/2/26 10:46 | 6/3/26 9:30 | 6/3/26 4:00 | 0h | -691.77h | 0ed | 0 | NA | NA | April 14, 2026 2:00 | April 14, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.19.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1892 | 4282 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d |  | September 24, 2026 8:31 | September 24, 2026 9:31 | 9/24/26 8:31 | 9/24/26 9:31 | 5/20/26 10:30 | 5/20/26 11:30 | 0h | -726.02h | 0ed | 0 | NA | NA | April 14, 2026 4:00 | April 14, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.19.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1893 | 4283 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1892 | September 24, 2026 9:31 | September 24, 2026 11:31 | 9/24/26 9:31 | 9/24/26 11:31 | 5/20/26 11:30 | 5/20/26 2:30 | 0h | -726.02h | 0ed | 0 | NA | NA | April 15, 2026 8:00 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.19.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1894 | 4284 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | 0.88d | Fixed Duration | 5 | 3.16d |  | September 24, 2026 8:31 | September 24, 2026 4:31 | 9/24/26 8:31 | 9/24/26 4:31 | 6/2/26 11:00 | 6/3/26 4:00 | 0d | -81.69d | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.20 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1895 | 4285 | Yes | Auto Scheduled | Extract File(Will Extract from LFA1) | 1h | Fixed Units | 6 | 0.13d |  | September 24, 2026 8:31 | September 24, 2026 9:31 | 9/24/26 8:31 | 9/24/26 9:31 | 6/2/26 11:00 | 6/2/26 12:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 1:45 | Start No Earlier Than | 4/16/26 8:00 | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.20.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1896 | 4286 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1895 | September 24, 2026 9:31 | September 24, 2026 11:31 | 9/24/26 9:31 | 9/24/26 11:31 | 6/2/26 1:00 | 6/2/26 3:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.20.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1897 | 4287 | Yes | Auto Scheduled | Simulate Load/ Not Needed | 1h | Fixed Units | 6 | 0.13d | 1896 | September 24, 2026 11:31 | September 24, 2026 1:31 | 9/24/26 11:31 | 9/24/26 1:31 | 6/2/26 3:00 | 6/2/26 4:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 10, 2026 3:45 | April 10, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.20.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1898 | 4288 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1897 | September 24, 2026 1:31 | September 24, 2026 3:31 | 9/24/26 1:31 | 9/24/26 3:31 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -647.52h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.20.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1899 | 4289 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1897 | September 24, 2026 1:31 | September 24, 2026 2:31 | 9/24/26 1:31 | 9/24/26 2:31 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 11:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.20.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1900 | 4290 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1899 | September 24, 2026 2:31 | September 24, 2026 4:31 | 9/24/26 2:31 | 9/24/26 4:31 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 15, 2026 11:00 | April 15, 2026 2:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.20.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1901 | 4291 | Yes | Auto Scheduled | RTR_****_Credit Hierarchy | 1.91d | Fixed Duration | 5 | 1.25d |  | October 1, 2026 11:31 | October 5, 2026 10:46 | 10/1/26 11:31 | 10/5/26 10:46 | 6/3/26 10:00 | 6/3/26 4:00 | 0d | -87.47d | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.21 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1902 | 4292 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1884 | October 1, 2026 11:31 | October 1, 2026 1:01 | 10/1/26 11:31 | 10/1/26 1:01 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -41101m | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 3:15 | Start No Earlier Than | 4/15/26 8:00 | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.21.1 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1903 | 4293 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1886 | October 2, 2026 2:46 | October 2, 2026 4:46 | 10/2/26 2:46 | 10/2/26 4:46 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -699.77h | 0ed | 0 | NA | NA | April 13, 2026 10:45 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.21.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1904 | 4294 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1903 | October 2, 2026 4:46 | October 5, 2026 10:46 | 10/2/26 4:46 | 10/5/26 10:46 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -699.77h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.21.3 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1905 | 4295 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Supplier | 1.13d | Fixed Duration | 5 | 1.13d |  | September 24, 2026 11:31 | September 25, 2026 1:31 | 9/24/26 11:31 | 9/25/26 1:31 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -81.69d | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 15h | 15h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.22 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1906 | 4296 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1893 | September 24, 2026 11:31 | September 24, 2026 1:01 | 9/24/26 11:31 | 9/24/26 1:01 | 6/2/26 3:00 | 6/2/26 3:30 | 0m | -39211m | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 13, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.22.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1907 | 4297 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1906 | September 24, 2026 1:01 | September 24, 2026 1:31 | 9/24/26 1:01 | 9/24/26 1:31 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -39211m | 0ed | 0 | NA | NA | April 13, 2026 1:15 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.22.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1908 | 4298 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1907 | September 24, 2026 1:31 | September 24, 2026 2:31 | 9/24/26 1:31 | 9/24/26 2:31 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.22.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1909 | 4299 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1908 | September 24, 2026 2:31 | September 24, 2026 4:31 | 9/24/26 2:31 | 9/24/26 4:31 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 13, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.22.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1910 | 4300 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1909 | September 24, 2026 4:31 | September 25, 2026 9:31 | 9/24/26 4:31 | 9/25/26 9:31 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 13, 2026 4:45 | April 14, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.22.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1911 | 4301 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1910 | September 25, 2026 9:31 | September 25, 2026 1:31 | 9/25/26 9:31 | 9/25/26 1:31 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 14, 2026 9:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.22.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1912 | 4302 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Customer | 1.06d | Fixed Duration | 5 | 1.13d |  | September 24, 2026 8:31 | September 25, 2026 9:01 | 9/24/26 8:31 | 9/25/26 9:01 | 6/2/26 3:30 | 6/3/26 4:00 | 0d | -81.25d | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 15h | 15h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.23 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1913 | 4303 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d |  | September 24, 2026 8:31 | September 24, 2026 9:01 | 9/24/26 8:31 | 9/24/26 9:01 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -38521m | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 13, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.23.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1914 | 4304 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d |  | September 24, 2026 8:31 | September 24, 2026 9:01 | 9/24/26 8:31 | 9/24/26 9:01 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -39001m | 0ed | 0 | NA | NA | April 13, 2026 1:15 | April 13, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.23.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1915 | 4305 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1914 | September 24, 2026 9:01 | September 24, 2026 10:01 | 9/24/26 9:01 | 9/24/26 10:01 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -650.02h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.23.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1916 | 4306 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1915 | September 24, 2026 10:01 | September 24, 2026 1:01 | 9/24/26 10:01 | 9/24/26 1:01 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -650.02h | 0ed | 0 | NA | NA | April 13, 2026 2:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.23.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1917 | 4307 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1916 | September 24, 2026 1:01 | September 24, 2026 3:01 | 9/24/26 1:01 | 9/24/26 3:01 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -650.02h | 0ed | 0 | NA | NA | April 13, 2026 4:45 | April 14, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.23.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1918 | 4308 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1917 | September 24, 2026 3:01 | September 25, 2026 9:01 | 9/24/26 3:01 | 9/25/26 9:01 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -650.02h | 0ed | 0 | NA | NA | April 14, 2026 9:45 | April 14, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.23.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1919 | 4309 | Yes | Auto Scheduled | PTP_CM26_Material_Master - All Types | 2.28d | Fixed Duration | 5 | 3.16d |  | September 24, 2026 9:31 | September 28, 2026 11:46 | 9/24/26 9:31 | 9/28/26 11:46 | 5/20/26 2:30 | 6/3/26 4:00 | 0d | -90.5d | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 15, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 19h | 19h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.24 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1920 | 4310 | Yes | Auto Scheduled | Extract File | 5h | Fixed Units | 6 | 0.63d | 1895 | September 24, 2026 9:31 | September 25, 2026 8:16 | 9/24/26 9:31 | 9/25/26 8:16 | 6/3/26 8:15 | 6/3/26 4:00 | 0h | -649.27h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 13, 2026 9:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.24.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1921 | 4311 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1893 | September 24, 2026 11:31 | September 25, 2026 9:46 | 9/24/26 11:31 | 9/25/26 9:46 | 5/20/26 2:30 | 5/21/26 11:45 | 0h | -726.02h | 0ed | 0 | NA | NA | April 13, 2026 11:45 | April 14, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.24.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1922 | 4312 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1921 | September 25, 2026 9:46 | September 25, 2026 10:46 | 9/25/26 9:46 | 9/25/26 10:46 | 5/21/26 11:45 | 5/21/26 1:45 | 0h | -726.02h | 0ed | 0 | NA | NA | April 14, 2026 10:00 | April 14, 2026 11:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.24.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1923 | 4313 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | Fixed Units | 6 | 0.5d | 1922 | September 25, 2026 10:46 | September 25, 2026 3:46 | 9/25/26 10:46 | 9/25/26 3:46 | 5/21/26 1:45 | 5/22/26 8:45 | 0h | -726.02h | 0ed | 0 | NA | NA | April 14, 2026 11:00 | April 14, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.24.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1924 | 4314 | Yes | Auto Scheduled | Load | 3h | Fixed Units | 6 | 0.38d | 1923 | September 25, 2026 3:46 | September 28, 2026 9:46 | 9/25/26 3:46 | 9/28/26 9:46 | 5/22/26 8:45 | 5/22/26 11:45 | 0h | -726.02h | 0ed | 0 | NA | NA | April 14, 2026 4:00 | April 15, 2026 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.24.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1925 | 4315 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1924 | September 28, 2026 9:46 | September 28, 2026 11:46 | 9/28/26 9:46 | 9/28/26 11:46 | 5/27/26 8:00 | 5/27/26 10:00 | 0h | -705.77h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.24.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1926 | 4316 | Yes | Auto Scheduled | PTP_CM26_Material_Master - SERV - Service Materials | 1.34d | Fixed Duration | 5 | 5.88d |  | September 25, 2026 4:31 | September 29, 2026 10:16 | 9/25/26 4:31 | 9/29/26 10:16 | 6/2/26 3:30 | 6/3/26 4:00 | 0d | -83.41d | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 15h | 15h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.25 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1927 | 4317 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1796 | September 25, 2026 4:31 | September 28, 2026 8:01 | 9/25/26 4:31 | 9/28/26 8:01 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -39421m | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 7, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.25.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1928 | 4318 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1924 | September 28, 2026 9:46 | September 28, 2026 10:16 | 9/28/26 9:46 | 9/28/26 10:16 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -40036m | 0ed | 0 | NA | NA | April 14, 2026 2:45 | April 14, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.25.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1929 | 4319 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1928 | September 28, 2026 10:16 | September 28, 2026 11:16 | 9/28/26 10:16 | 9/28/26 11:16 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -667.27h | 0ed | 0 | NA | NA | April 14, 2026 3:15 | April 14, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.25.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1930 | 4320 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1929 | September 28, 2026 11:16 | September 28, 2026 2:16 | 9/28/26 11:16 | 9/28/26 2:16 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -667.27h | 0ed | 0 | NA | NA | April 14, 2026 4:15 | April 15, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 4h | 4h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.25.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1931 | 4321 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1930 | September 28, 2026 2:16 | September 28, 2026 4:16 | 9/28/26 2:16 | 9/28/26 4:16 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -667.27h | 0ed | 0 | NA | NA | April 15, 2026 9:15 | April 15, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.25.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1932 | 4322 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1931 | September 28, 2026 4:16 | September 29, 2026 10:16 | 9/28/26 4:16 | 9/29/26 10:16 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -667.27h | 0ed | 0 | NA | NA | April 15, 2026 11:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 6h | 6h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.25.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1933 | 4323 | Yes | Auto Scheduled | PTP_CM26_Material_Master - KMAT - Configurable Materials | 1.34d | Fixed Duration | 5 | 5.88d |  | September 25, 2026 4:31 | September 29, 2026 10:16 | 9/25/26 4:31 | 9/29/26 10:16 | 5/22/26 11:45 | 6/1/26 10:15 | 0d | -90.47d | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.26 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1934 | 4324 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1796 | September 25, 2026 4:31 | September 28, 2026 8:01 | 9/25/26 4:31 | 9/28/26 8:01 | 6/1/26 9:45 | 6/1/26 10:15 | 0m | -40666m | 0ed | 0 | NA | NA | April 7, 2026 4:15 | April 7, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.26.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1935 | 4325 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1924 | September 28, 2026 9:46 | September 28, 2026 10:16 | 9/28/26 9:46 | 9/28/26 10:16 | 5/22/26 11:45 | 5/22/26 1:15 | 0m | -43561m | 0ed | 0 | NA | NA | April 14, 2026 2:45 | April 14, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.26.2 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1936 | 4326 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1935 | September 28, 2026 10:16 | September 28, 2026 11:16 | 9/28/26 10:16 | 9/28/26 11:16 | 5/22/26 1:15 | 5/22/26 2:15 | 0h | -726.02h | 0ed | 0 | NA | NA | April 14, 2026 3:15 | April 14, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.26.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1937 | 4327 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1936 | September 28, 2026 11:16 | September 28, 2026 2:16 | 9/28/26 11:16 | 9/28/26 2:16 | 5/22/26 2:15 | 5/22/26 4:15 | 0h | -726.02h | 0ed | 0 | NA | NA | April 14, 2026 4:15 | April 15, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.26.4 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1938 | 4328 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1937 | September 28, 2026 2:16 | September 28, 2026 4:16 | 9/28/26 2:16 | 9/28/26 4:16 | 5/22/26 4:15 | 5/25/26 9:15 | 0h | -726.02h | 0ed | 0 | NA | NA | April 15, 2026 9:15 | April 15, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.26.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1939 | 4329 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1938 | September 28, 2026 4:16 | September 29, 2026 10:16 | 9/28/26 4:16 | 9/29/26 10:16 | 5/25/26 9:15 | 5/25/26 1:15 | 0h | -726.02h | 0ed | 0 | NA | NA | April 15, 2026 11:15 | April 15, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.26.6 | 500 | No | No | No |  | Sam Houff,Kim Kolesar,Matt | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1940 | 4330 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Records | 3.59d | Fixed Duration | 5 | 1.28d |  | September 24, 2026 11:31 | September 30, 2026 8:16 | 9/24/26 11:31 | 9/30/26 8:16 | 5/28/26 2:53 | 6/3/26 4:00 | 0d | -84.71d | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.27 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1941 | 4331 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1925,1939 | September 29, 2026 10:16 | September 29, 2026 11:16 | 9/29/26 10:16 | 9/29/26 11:16 | 5/28/26 2:53 | 5/28/26 3:53 | 0h | -700.39h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.27.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1942 | 4332 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1941 | September 29, 2026 11:16 | September 29, 2026 2:16 | 9/29/26 11:16 | 9/29/26 2:16 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -673.27h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.27.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1943 | 4333 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1942 | September 29, 2026 2:16 | September 29, 2026 3:16 | 9/29/26 2:16 | 9/29/26 3:16 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -673.27h | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.27.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1944 | 4334 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1943 | September 29, 2026 3:16 | September 30, 2026 8:16 | 9/29/26 3:16 | 9/30/26 8:16 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -673.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.27.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1945 | 4335 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1893 | September 24, 2026 11:31 | September 24, 2026 1:31 | 9/24/26 11:31 | 9/24/26 1:31 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -647.52h | 0ed | 0 | NA | NA | April 15, 2026 10:00 | April 15, 2026 11:00 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.27.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1946 | 4336 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1945 | September 24, 2026 1:31 | September 24, 2026 3:31 | 9/24/26 1:31 | 9/24/26 3:31 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -647.52h | 0ed | 0 | NA | NA | April 15, 2026 11:00 | April 15, 2026 2:00 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.27.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1947 | 4337 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record External Processing | 1.13d | Fixed Duration | 5 | 1.13d |  | September 29, 2026 10:16 | September 30, 2026 11:16 | 9/29/26 10:16 | 9/30/26 11:16 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -84.53d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.28 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1948 | 4338 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1925,1939 | September 29, 2026 10:16 | September 29, 2026 10:46 | 9/29/26 10:16 | 9/29/26 10:46 | 6/2/26 3:00 | 6/2/26 3:30 | 0m | -40576m | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.28.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1949 | 4339 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1948 | September 29, 2026 10:46 | September 29, 2026 11:16 | 9/29/26 10:46 | 9/29/26 11:16 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -40576m | 0ed | 0 | NA | NA | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.28.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1950 | 4340 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1949 | September 29, 2026 11:16 | September 29, 2026 1:16 | 9/29/26 11:16 | 9/29/26 1:16 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -676.27h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.28.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1951 | 4341 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1950 | September 29, 2026 1:16 | September 29, 2026 3:16 | 9/29/26 1:16 | 9/29/26 3:16 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -676.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.28.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1952 | 4342 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1951 | September 29, 2026 3:16 | September 30, 2026 8:16 | 9/29/26 3:16 | 9/30/26 8:16 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -676.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.28.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1953 | 4343 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1952 | September 30, 2026 8:16 | September 30, 2026 11:16 | 9/30/26 8:16 | 9/30/26 11:16 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -676.27h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.28.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1954 | 4344 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | 1.13d | Fixed Duration | 5 | 1.13d |  | September 29, 2026 10:16 | September 30, 2026 11:16 | 9/29/26 10:16 | 9/30/26 11:16 | 5/27/26 10:00 | 6/3/26 4:00 | 0d | -89.03d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.29 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1955 | 4345 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1925,1939 | September 29, 2026 10:16 | September 29, 2026 10:46 | 9/29/26 10:16 | 9/29/26 10:46 | 5/27/26 10:00 | 5/27/26 10:30 | 0m | -42736m | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.29.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1956 | 4346 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1955 | September 29, 2026 10:46 | September 29, 2026 11:16 | 9/29/26 10:46 | 9/29/26 11:16 | 5/27/26 10:30 | 5/27/26 11:00 | 0m | -42736m | 0ed | 0 | NA | NA | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.29.2 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1957 | 4347 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1956 | September 29, 2026 11:16 | September 29, 2026 1:16 | 9/29/26 11:16 | 9/29/26 1:16 | 5/27/26 11:00 | 5/27/26 12:00 | 0h | -712.27h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.29.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1958 | 4348 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1957 | September 29, 2026 1:16 | September 29, 2026 3:16 | 9/29/26 1:16 | 9/29/26 3:16 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -676.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.29.4 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1959 | 4349 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1958 | September 29, 2026 3:16 | September 30, 2026 8:16 | 9/29/26 3:16 | 9/30/26 8:16 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -676.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.29.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1960 | 4350 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1959 | September 30, 2026 8:16 | September 30, 2026 11:16 | 9/30/26 8:16 | 9/30/26 11:16 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -676.27h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.29.6 | 500 | No | No | No |  | Sam Houff | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1961 | 4351 | Yes | Auto Scheduled | PTM_CM31_BOM Conversion | 2.48d | Fixed Duration | 5 | 1.13d |  | September 29, 2026 11:16 | October 1, 2026 4:09 | 9/29/26 11:16 | 10/1/26 4:09 | 5/28/26 3:53 | 6/2/26 10:45 | 0d | -87.55d | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 19h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.30 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1962 | 4352 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1941 | September 29, 2026 11:16 | September 29, 2026 1:16 | 9/29/26 11:16 | 9/29/26 1:16 | 5/28/26 3:53 | 5/28/26 4:53 | 0h | -700.39h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.30.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1963 | 4353 | Yes | Auto Scheduled | Pre Load Validation | 0.5h | Fixed Units | 6 | 0.25d | 1962 | September 29, 2026 1:16 | September 29, 2026 1:46 | 9/29/26 1:16 | 9/29/26 1:46 | 5/28/26 4:53 | 5/29/26 8:23 | 0h | -700.39h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.30.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1964 | 4354 | Yes | Auto Scheduled | Simulate Load | 15.5h | Fixed Units | 6 | 0.13d | 1963 | September 29, 2026 1:46 | October 1, 2026 1:46 | 9/29/26 1:46 | 10/1/26 1:46 | 5/29/26 8:23 | 6/2/26 8:23 | 0h | -700.39h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 11:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/30/26 2:05 | 15.5h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.30.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1965 | 4355 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | Fixed Units | 6 | 0.25d | 1964 | October 1, 2026 1:46 | October 1, 2026 2:16 | 10/1/26 1:46 | 10/1/26 2:16 | 6/2/26 8:23 | 6/2/26 8:53 | 0h | -700.39h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 2:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/30/26 2:05 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.30.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1966 | 4356 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1965 | October 1, 2026 2:16 | October 1, 2026 3:31 | 10/1/26 2:16 | 10/1/26 3:31 | 6/2/26 8:53 | 6/2/26 10:08 | 0h | -700.39h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 16, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 4/1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1967 | 4357 | Yes | Auto Scheduled | Post Load Validation | 0.5h | Fixed Units | 6 | 0.25d | 1966 | October 1, 2026 3:31 | October 1, 2026 4:09 | 10/1/26 3:31 | 10/1/26 4:09 | 6/2/26 10:08 | 6/2/26 10:45 | 0h | -700.39h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 17, 2026 8:15 | Finish No Earlier Than | 4/16/26 5:00 | NA | NA | 4/30/26 2:05 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.30.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1968 | 4358 | Yes | Auto Scheduled | PTM_CM40_Work Center Conversion | 3.08d | Fixed Duration | 5 | 2d |  | September 29, 2026 1:16 | October 2, 2026 1:54 | 9/29/26 1:16 | 10/2/26 1:54 | 5/29/26 1:30 | 6/3/26 8:30 | 0d | -87.55d | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 6.75h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.31 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1969 | 4359 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1962 | September 29, 2026 1:16 | September 29, 2026 2:16 | 9/29/26 1:16 | 9/29/26 2:16 | 5/29/26 1:30 | 5/29/26 2:30 | 0h | -695.77h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.31.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1970 | 4360 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1967 | October 1, 2026 4:09 | October 2, 2026 9:09 | 10/1/26 4:09 | 10/2/26 9:09 | 6/2/26 10:45 | 6/2/26 1:45 | 0h | -700.39h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.31.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1971 | 4361 | Yes | Auto Scheduled | Simulate Load | 0.25h | Fixed Units | 6 | 0.13d | 1970 | October 2, 2026 9:09 | October 2, 2026 9:24 | 10/2/26 9:09 | 10/2/26 9:24 | 6/2/26 1:45 | 6/2/26 2:00 | 0h | -700.39h | 0ed | 0 | NA | NA | April 17, 2026 10:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.25h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.31.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1972 | 4362 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | Fixed Units | 6 | 0.25d | 1971 | October 2, 2026 9:24 | October 2, 2026 9:54 | 10/2/26 9:24 | 10/2/26 9:54 | 6/2/26 2:00 | 6/2/26 2:30 | 0h | -700.39h | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.31.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1973 | 4363 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1972 | October 2, 2026 9:54 | October 2, 2026 10:54 | 10/2/26 9:54 | 10/2/26 10:54 | 6/2/26 2:30 | 6/2/26 3:30 | 0h | -700.39h | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 17, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.31.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1974 | 4364 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1973 | October 2, 2026 10:54 | October 2, 2026 1:54 | 10/2/26 10:54 | 10/2/26 1:54 | 6/2/26 3:30 | 6/3/26 8:30 | 0h | -700.39h | 0ed | 0 | NA | NA | April 17, 2026 3:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.31.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1975 | 4365 | Yes | Auto Scheduled | PTM_CM38_Routing Conversion | 4.27d | Fixed Duration | 5 | 2.88d |  | September 29, 2026 2:16 | October 5, 2026 4:24 | 9/29/26 2:16 | 10/5/26 4:24 | 5/29/26 2:30 | 6/3/26 4:00 | 0d | -88.05d | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 11h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.32 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1976 | 4366 | Yes | Auto Scheduled | Extract File | 1h | Fixed Units | 6 | 0.13d | 1969 | September 29, 2026 2:16 | September 29, 2026 3:16 | 9/29/26 2:16 | 9/29/26 3:16 | 5/29/26 2:30 | 5/29/26 3:30 | 0h | -695.77h | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.32.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1977 | 4367 | Yes | Auto Scheduled | Pre Load Validation | 2h | Fixed Units | 6 | 0.25d | 1974 | October 2, 2026 1:54 | October 5, 2026 9:24 | 10/2/26 1:54 | 10/5/26 9:24 | 6/3/26 8:30 | 6/3/26 2:00 | 0h | -700.39h | 0ed | 0 | NA | NA | April 20, 2026 8:15 | April 20, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.32.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1978 | 4368 | Yes | Auto Scheduled | Simulate Load | 2h | Fixed Units | 6 | 0.13d | 1977 | October 5, 2026 9:24 | October 5, 2026 11:24 | 10/5/26 9:24 | 10/5/26 11:24 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -700.39h | 0ed | 0 | NA | NA | April 20, 2026 10:15 | April 20, 2026 11:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/30/26 2:05 | 2h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.32.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1979 | 4369 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | Fixed Units | 6 | 0.25d | 1978SS | October 5, 2026 9:24 | October 5, 2026 1:24 | 10/5/26 9:24 | 10/5/26 1:24 | 6/3/26 9:00 | 6/3/26 12:00 | 0h | -704.39h | 0ed | 0 | NA | NA | April 20, 2026 11:15 | April 20, 2026 2:15 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/30/26 2:05 | 3h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.32.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1980 | 4370 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 1979 | October 5, 2026 1:24 | October 5, 2026 2:24 | 10/5/26 1:24 | 10/5/26 2:24 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -704.39h | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 20, 2026 3:15 | Start No Earlier Than | 4/20/26 8:00 | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.32.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1981 | 4371 | Yes | Auto Scheduled | Post Load Validation | 2h | Fixed Units | 6 | 0.25d | 1980 | October 5, 2026 2:24 | October 5, 2026 4:24 | 10/5/26 2:24 | 10/5/26 4:24 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -704.39h | 0ed | 0 | NA | NA | April 20, 2026 3:15 | April 21, 2026 8:15 | Start No Earlier Than | 4/20/26 8:00 | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.32.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1982 | 4372 | Yes | Auto Scheduled | PTM_CM36_Production Version Conversion | 1.13d | Fixed Duration | 5 | 1.13d |  | September 29, 2026 3:16 | September 30, 2026 4:16 | 9/29/26 3:16 | 9/30/26 4:16 | 5/29/26 3:30 | 6/1/26 4:30 | 0d | -86.97d | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.33 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1983 | 4373 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1976 | September 29, 2026 3:16 | September 29, 2026 3:46 | 9/29/26 3:16 | 9/29/26 3:46 | 5/29/26 3:30 | 5/29/26 4:00 | 0m | -41746m | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 10:45 | Start No Earlier Than | 4/20/26 8:00 | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.33.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1984 | 4374 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1983 | September 29, 2026 3:46 | September 29, 2026 4:16 | 9/29/26 3:46 | 9/29/26 4:16 | 5/29/26 4:00 | 5/29/26 4:30 | 0m | -41746m | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.33.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1985 | 4375 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1984 | September 29, 2026 4:16 | September 30, 2026 8:16 | 9/29/26 4:16 | 9/30/26 8:16 | 5/29/26 4:30 | 6/1/26 8:30 | 0h | -695.77h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.33.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1986 | 4376 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1985 | September 30, 2026 8:16 | September 30, 2026 10:16 | 9/30/26 8:16 | 9/30/26 10:16 | 6/1/26 8:30 | 6/1/26 10:30 | 0h | -695.77h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.33.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1987 | 4377 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1986 | September 30, 2026 10:16 | September 30, 2026 1:16 | 9/30/26 10:16 | 9/30/26 1:16 | 6/1/26 10:30 | 6/1/26 1:30 | 0h | -695.77h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.33.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1988 | 4378 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1987 | September 30, 2026 1:16 | September 30, 2026 4:16 | 9/30/26 1:16 | 9/30/26 4:16 | 6/1/26 1:30 | 6/1/26 4:30 | 0h | -695.77h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 11:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.33.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1989 | 4379 | Yes | Auto Scheduled | PTM_CM35_Inspection Plan | 1.13d | Fixed Duration | 5 | 1.13d |  | September 30, 2026 4:16 | October 2, 2026 8:16 | 9/30/26 4:16 | 10/2/26 8:16 | 6/1/26 4:30 | 6/3/26 4:00 | 0d | -86.97d | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 20, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.34 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1990 | 4380 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1988 | September 30, 2026 4:16 | September 30, 2026 4:46 | 9/30/26 4:16 | 9/30/26 4:46 | 6/1/26 4:30 | 6/1/26 5:00 | 0m | -41746m | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.34.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1991 | 4381 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1990 | September 30, 2026 4:46 | October 1, 2026 8:16 | 9/30/26 4:46 | 10/1/26 8:16 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -41356m | 0ed | 0 | NA | NA | April 17, 2026 11:45 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.34.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1992 | 4382 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1991 | October 1, 2026 8:16 | October 1, 2026 9:16 | 10/1/26 8:16 | 10/1/26 9:16 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -689.27h | 0ed | 0 | NA | NA | April 17, 2026 1:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.34.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1993 | 4383 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1992 | October 1, 2026 9:16 | October 1, 2026 11:16 | 10/1/26 9:16 | 10/1/26 11:16 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -689.27h | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 17, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.34.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1994 | 4384 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1993 | October 1, 2026 11:16 | October 1, 2026 2:16 | 10/1/26 11:16 | 10/1/26 2:16 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -689.27h | 0ed | 0 | NA | NA | April 17, 2026 4:15 | April 20, 2026 9:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.34.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1995 | 4385 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 1994 | October 1, 2026 2:16 | October 2, 2026 8:16 | 10/1/26 2:16 | 10/2/26 8:16 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -689.27h | 0ed | 0 | NA | NA | April 20, 2026 9:15 | April 20, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.34.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1996 | 4386 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Serial Numbers | 1.13d | Fixed Duration | 5 | 1.13d |  | September 30, 2026 4:46 | October 2, 2026 8:46 | 9/30/26 4:46 | 10/2/26 8:46 | 6/2/26 8:00 | 6/3/26 9:00 | 0d | -86.97d | 0ed | 0 | NA | NA | April 17, 2026 11:45 | April 20, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.35 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1997 | 4387 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1990 | September 30, 2026 4:46 | October 1, 2026 8:16 | 9/30/26 4:46 | 10/1/26 8:16 | 6/2/26 8:00 | 6/2/26 8:30 | 0m | -41746m | 0ed | 0 | NA | NA | April 17, 2026 11:45 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.35.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1998 | 4388 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 1997 | October 1, 2026 8:16 | October 1, 2026 8:46 | 10/1/26 8:16 | 10/1/26 8:46 | 6/2/26 8:30 | 6/2/26 9:00 | 0m | -41746m | 0ed | 0 | NA | NA | April 17, 2026 1:15 | April 17, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.35.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1999 | 4389 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 1998 | October 1, 2026 8:46 | October 1, 2026 9:46 | 10/1/26 8:46 | 10/1/26 9:46 | 6/2/26 9:00 | 6/2/26 10:00 | 0h | -695.77h | 0ed | 0 | NA | NA | April 17, 2026 1:45 | April 17, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.35.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2000 | 4390 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 1999 | October 1, 2026 9:46 | October 1, 2026 11:46 | 10/1/26 9:46 | 10/1/26 11:46 | 6/2/26 10:00 | 6/2/26 12:00 | 0h | -695.77h | 0ed | 0 | NA | NA | April 17, 2026 2:45 | April 17, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.35.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2001 | 4391 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 2000 | October 1, 2026 11:46 | October 1, 2026 2:46 | 10/1/26 11:46 | 10/1/26 2:46 | 6/2/26 1:00 | 6/2/26 3:00 | 0h | -695.77h | 0ed | 0 | NA | NA | April 17, 2026 4:45 | April 20, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.35.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2002 | 4392 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2001 | October 1, 2026 2:46 | October 2, 2026 8:46 | 10/1/26 2:46 | 10/2/26 8:46 | 6/2/26 3:00 | 6/3/26 9:00 | 0h | -695.77h | 0ed | 0 | NA | NA | April 20, 2026 9:45 | April 20, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.35.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2003 | 4393 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Service | 6.78d | Fixed Duration | 5 | 1.13d |  | September 24, 2026 8:31 | October 2, 2026 3:46 | 9/24/26 8:31 | 10/2/26 3:46 | 6/3/26 9:00 | 6/3/26 4:00 | 0d | -86.97d | 0ed | 0 | NA | NA | April 20, 2026 1:45 | April 21, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.36 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2004 | 4394 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 2002 | October 2, 2026 8:46 | October 2, 2026 9:16 | 10/2/26 8:46 | 10/2/26 9:16 | 6/3/26 9:00 | 6/3/26 9:30 | 0m | -41746m | 0ed | 0 | NA | NA | April 20, 2026 1:45 | April 20, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.36.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2005 | 4395 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 2004 | October 2, 2026 9:16 | October 2, 2026 9:46 | 10/2/26 9:16 | 10/2/26 9:46 | 6/3/26 9:30 | 6/3/26 10:00 | 0m | -41746m | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 20, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.36.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2006 | 4396 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 2005 | October 2, 2026 9:46 | October 2, 2026 10:46 | 10/2/26 9:46 | 10/2/26 10:46 | 6/3/26 10:00 | 6/3/26 11:00 | 0h | -695.77h | 0ed | 0 | NA | NA | April 20, 2026 2:45 | April 20, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.36.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2007 | 4397 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 2006 | October 2, 2026 10:46 | October 2, 2026 1:46 | 10/2/26 10:46 | 10/2/26 1:46 | 6/3/26 11:00 | 6/3/26 2:00 | 0h | -695.77h | 0ed | 0 | NA | NA | April 20, 2026 3:45 | April 21, 2026 8:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.36.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2008 | 4398 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 2007 | October 2, 2026 1:46 | October 2, 2026 3:46 | 10/2/26 1:46 | 10/2/26 3:46 | 6/3/26 2:00 | 6/3/26 4:00 | 0h | -695.77h | 0ed | 0 | NA | NA | April 21, 2026 8:45 | April 21, 2026 10:45 | Finish No Earlier Than | 4/21/26 5:00 | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.36.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2009 | 4399 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d |  | September 24, 2026 8:31 | September 24, 2026 11:31 | 9/24/26 8:31 | 9/24/26 11:31 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -644.52h | 0ed | 0 | NA | NA | April 21, 2026 10:45 | April 21, 2026 2:45 | Start No Earlier Than | 4/21/26 8:00 | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.36.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2010 | 4400 | Yes | Auto Scheduled | VC_Object Dependencies | 0.63d | Fixed Duration | 5 | 0.63d |  | September 24, 2026 8:31 | September 24, 2026 2:31 | 9/24/26 8:31 | 9/24/26 2:31 | 6/1/26 11:00 | 6/1/26 5:00 | 0d | -82.69d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.37 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2011 | 4401 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1771 | September 24, 2026 8:31 | September 24, 2026 10:31 | 9/24/26 8:31 | 9/24/26 10:31 | 6/1/26 11:00 | 6/1/26 2:00 | 0h | -661.52h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.37.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2012 | 4402 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2011 | September 24, 2026 10:31 | September 24, 2026 2:31 | 9/24/26 10:31 | 9/24/26 2:31 | 6/1/26 2:00 | 6/1/26 5:00 | 0h | -661.52h | 0ed | 0 | NA | NA | April 6, 2026 10:15 | April 6, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.37.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2013 | 4403 | Yes | Auto Scheduled | VC_Characteristics | 0.63d | Fixed Duration | 5 | 0.63d |  | September 24, 2026 2:31 | September 25, 2026 10:31 | 9/24/26 2:31 | 9/25/26 10:31 | 6/2/26 8:00 | 6/2/26 2:00 | 0d | -82.69d | 0ed | 0 | NA | NA | April 6, 2026 2:15 | April 7, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.38 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2014 | 4404 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 2012 | September 24, 2026 2:31 | September 24, 2026 4:31 | 9/24/26 2:31 | 9/24/26 4:31 | 6/2/26 8:00 | 6/2/26 10:00 | 0h | -661.52h | 0ed | 0 | NA | NA | April 6, 2026 2:15 | April 6, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.38.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2015 | 4405 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2014 | September 24, 2026 4:31 | September 25, 2026 10:31 | 9/24/26 4:31 | 9/25/26 10:31 | 6/2/26 10:00 | 6/2/26 2:00 | 0h | -661.52h | 0ed | 0 | NA | NA | April 6, 2026 4:15 | April 7, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.38.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2016 | 4406 | Yes | Auto Scheduled | VC_Classes | 0.63d | Fixed Duration | 5 | 0.63d |  | September 25, 2026 10:31 | September 25, 2026 4:31 | 9/25/26 10:31 | 9/25/26 4:31 | 6/2/26 2:00 | 6/3/26 10:00 | 0d | -82.69d | 0ed | 0 | NA | NA | April 7, 2026 10:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.39 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2017 | 4407 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 2015 | September 25, 2026 10:31 | September 25, 2026 1:31 | 9/25/26 10:31 | 9/25/26 1:31 | 6/2/26 2:00 | 6/2/26 4:00 | 0h | -661.52h | 0ed | 0 | NA | NA | April 7, 2026 10:15 | April 7, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.39.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2018 | 4408 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2017 | September 25, 2026 1:31 | September 25, 2026 4:31 | 9/25/26 1:31 | 9/25/26 4:31 | 6/2/26 4:00 | 6/3/26 10:00 | 0h | -661.52h | 0ed | 0 | NA | NA | April 7, 2026 1:15 | April 7, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.39.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2019 | 4409 | Yes | Auto Scheduled | VC_Classification (Class Type 200) | 0.63d | Fixed Duration | 5 | 0.63d |  | September 29, 2026 10:16 | September 29, 2026 4:16 | 9/29/26 10:16 | 9/29/26 4:16 | 6/3/26 10:00 | 6/3/26 4:00 | 0d | -84.03d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.40 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2020 | 4410 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1939 | September 29, 2026 10:16 | September 29, 2026 1:16 | 9/29/26 10:16 | 9/29/26 1:16 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -672.27h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.40.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2021 | 4411 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2020 | September 29, 2026 1:16 | September 29, 2026 4:16 | 9/29/26 1:16 | 9/29/26 4:16 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -672.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.40.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2022 | 4412 | Yes | Auto Scheduled | VC_Dependency Nets | 0.63d | Fixed Duration | 5 | 0.63d |  | September 29, 2026 10:16 | September 29, 2026 4:16 | 9/29/26 10:16 | 9/29/26 4:16 | 6/3/26 10:00 | 6/3/26 4:00 | 0d | -84.03d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.41 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2023 | 4413 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1933,2018 | September 29, 2026 10:16 | September 29, 2026 1:16 | 9/29/26 10:16 | 9/29/26 1:16 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -672.27h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.41.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2024 | 4414 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2023 | September 29, 2026 1:16 | September 29, 2026 4:16 | 9/29/26 1:16 | 9/29/26 4:16 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -672.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.41.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2025 | 4415 | Yes | Auto Scheduled | VC_Configuration Profiles | 0.63d | Fixed Duration | 5 | 0.63d |  | September 29, 2026 10:16 | September 29, 2026 4:16 | 9/29/26 10:16 | 9/29/26 4:16 | 6/1/26 10:15 | 6/1/26 4:15 | 0d | -86d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.42 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2026 | 4416 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 1933 | September 29, 2026 10:16 | September 29, 2026 1:16 | 9/29/26 10:16 | 9/29/26 1:16 | 6/1/26 10:15 | 6/1/26 1:15 | 0h | -688.02h | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.42.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2027 | 4417 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2026 | September 29, 2026 1:16 | September 29, 2026 4:16 | 9/29/26 1:16 | 9/29/26 4:16 | 6/1/26 1:15 | 6/1/26 4:15 | 0h | -688.02h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.42.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2028 | 4418 | Yes | Auto Scheduled | VC_Variant Tables | 0.63d | Fixed Duration | 5 | 0.63d |  | September 29, 2026 4:16 | September 30, 2026 1:16 | 9/29/26 4:16 | 9/30/26 1:16 | 6/2/26 2:00 | 6/3/26 10:00 | 0d | -85.28d | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.43 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2029 | 4419 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 2027 | September 29, 2026 4:16 | September 30, 2026 9:16 | 9/29/26 4:16 | 9/30/26 9:16 | 6/2/26 2:00 | 6/2/26 4:00 | 0h | -682.27h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.43.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2030 | 4420 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2029 | September 30, 2026 9:16 | September 30, 2026 1:16 | 9/30/26 9:16 | 9/30/26 1:16 | 6/2/26 4:00 | 6/3/26 10:00 | 0h | -682.27h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.43.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2031 | 4421 | Yes | Auto Scheduled | VC_Variant Tables Content | 0.63d | Fixed Duration | 5 | 0.63d |  | September 30, 2026 1:16 | October 1, 2026 9:16 | 9/30/26 1:16 | 10/1/26 9:16 | 6/3/26 10:00 | 6/3/26 4:00 | 0d | -85.28d | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.44 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2032 | 4422 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | Fixed Units | 6 | 0.25d | 2030 | September 30, 2026 1:16 | September 30, 2026 3:16 | 9/30/26 1:16 | 9/30/26 3:16 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -682.27h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.44.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2033 | 4423 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2032 | September 30, 2026 3:16 | October 1, 2026 9:16 | 9/30/26 3:16 | 10/1/26 9:16 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -682.27h | 0ed | 0 | NA | NA | April 17, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.44.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2034 | 4424 | Yes | Auto Scheduled | VC_Characteristic Groups | 1.97d | Fixed Duration | 5 | 0.63d |  | September 29, 2026 4:16 | October 1, 2026 4:01 | 9/29/26 4:16 | 10/1/26 4:01 | 6/1/26 4:15 | 6/3/26 4:00 | 0d | -86d | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 15.75h | 5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.45 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2035 | 4425 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 12.75h | Fixed Units | 6 | 0.25d | 2027 | September 29, 2026 4:16 | October 1, 2026 1:01 | 9/29/26 4:16 | 10/1/26 1:01 | 6/1/26 4:15 | 6/3/26 12:00 | 0h | -688.02h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 2:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/30/26 2:05 | 12.75h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.45.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2036 | 4426 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2035 | October 1, 2026 1:01 | October 1, 2026 4:01 | 10/1/26 1:01 | 10/1/26 4:01 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -688.02h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.45.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2037 | 4427 | Yes | Auto Scheduled | PTM_CM52_Super_BOM | 4.09d | Fixed Duration | 5 | 1.13d |  | September 29, 2026 10:16 | October 5, 2026 11:01 | 9/29/26 10:16 | 10/5/26 11:01 | 5/25/26 1:15 | 5/29/26 2:00 | 0d | -90.75d | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 32.75h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.46 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2038 | 4428 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1939 | September 29, 2026 10:16 | September 29, 2026 10:46 | 9/29/26 10:16 | 9/29/26 10:46 | 5/25/26 1:15 | 5/25/26 1:45 | 0m | -43561m | 0ed | 0 | NA | NA | April 15, 2026 3:15 | April 15, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.46.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2039 | 4429 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 2038 | September 29, 2026 10:46 | September 29, 2026 11:16 | 9/29/26 10:46 | 9/29/26 11:16 | 5/25/26 1:45 | 5/25/26 2:15 | 0m | -43561m | 0ed | 0 | NA | NA | April 15, 2026 3:45 | April 15, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.46.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2040 | 4430 | Yes | Auto Scheduled | Simulate Load | 24.75h | Fixed Units | 6 | 0.13d | 2039 | September 29, 2026 11:16 | October 2, 2026 1:01 | 9/29/26 11:16 | 10/2/26 1:01 | 5/25/26 2:15 | 5/28/26 3:00 | 0h | -726.02h | 0ed | 0 | NA | NA | April 15, 2026 4:15 | April 16, 2026 8:15 | Finish No Earlier Than | 4/20/26 5:00 | NA | NA | 4/30/26 2:05 | 24.75h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.46.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2041 | 4431 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 2040 | October 2, 2026 1:01 | October 2, 2026 3:01 | 10/2/26 1:01 | 10/2/26 3:01 | 5/28/26 3:00 | 5/28/26 5:00 | 0h | -726.02h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.46.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2042 | 4432 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 2041 | October 2, 2026 3:01 | October 5, 2026 8:01 | 10/2/26 3:01 | 10/5/26 8:01 | 5/29/26 8:00 | 5/29/26 10:00 | 0h | -726.02h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.46.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2043 | 4433 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2042 | October 5, 2026 8:01 | October 5, 2026 11:01 | 10/5/26 8:01 | 10/5/26 11:01 | 5/29/26 10:00 | 5/29/26 2:00 | 0h | -726.02h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.46.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2044 | 4434 | Yes | Auto Scheduled | PTM_CM53_Super_Routing | 2.13d | Fixed Duration | 5 | 1.13d |  | October 5, 2026 11:01 | October 7, 2026 1:01 | 10/5/26 11:01 | 10/7/26 1:01 | 5/29/26 2:00 | 6/3/26 4:00 | 0d | -90.75d | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.47 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2045 | 4435 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 2043 | October 5, 2026 11:01 | October 5, 2026 11:31 | 10/5/26 11:01 | 10/5/26 11:31 | 5/29/26 2:00 | 5/29/26 2:30 | 0m | -43561m | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 16, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.47.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2046 | 4436 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 2045 | October 5, 2026 11:31 | October 5, 2026 1:01 | 10/5/26 11:31 | 10/5/26 1:01 | 5/29/26 2:30 | 5/29/26 3:00 | 0m | -43561m | 0ed | 0 | NA | NA | April 16, 2026 4:45 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.47.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2047 | 4437 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 2046 | October 5, 2026 1:01 | October 6, 2026 2:01 | 10/5/26 1:01 | 10/6/26 2:01 | 5/29/26 3:00 | 6/1/26 4:00 | 0h | -726.02h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.47.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2048 | 4438 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 2047 | October 6, 2026 2:01 | October 6, 2026 4:01 | 10/6/26 2:01 | 10/6/26 4:01 | 6/1/26 4:00 | 6/2/26 9:00 | 0h | -726.02h | 0ed | 0 | NA | NA | April 17, 2026 9:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.47.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2049 | 4439 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 2048 | October 6, 2026 4:01 | October 7, 2026 9:01 | 10/6/26 4:01 | 10/7/26 9:01 | 6/2/26 9:00 | 6/2/26 11:00 | 0h | -726.02h | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.47.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2050 | 4440 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2049 | October 7, 2026 9:01 | October 7, 2026 1:01 | 10/7/26 9:01 | 10/7/26 1:01 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -717.02h | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 20, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.47.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2051 | 4441 | Yes | Auto Scheduled | VC_VK30 Pricing Variant | 0.69d | Fixed Duration | 5 | 0.69d |  | October 7, 2026 9:01 | October 7, 2026 3:31 | 10/7/26 9:01 | 10/7/26 3:31 | 6/2/26 11:00 | 6/3/26 8:30 | 0d | -90.75d | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 20, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.48 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2052 | 4442 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 2049 | October 7, 2026 9:01 | October 7, 2026 9:31 | 10/7/26 9:01 | 10/7/26 9:31 | 6/2/26 11:00 | 6/2/26 11:30 | 0m | -43561m | 0ed | 0 | NA | NA | April 17, 2026 2:15 | April 17, 2026 2:45 | Start No Earlier Than | 4/6/26 8:00 | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.48.1 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2053 | 4443 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 2052 | October 7, 2026 9:31 | October 7, 2026 11:31 | 10/7/26 9:31 | 10/7/26 11:31 | 6/2/26 11:30 | 6/2/26 2:30 | 0h | -726.02h | 0ed | 0 | NA | NA | April 17, 2026 2:45 | April 17, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.48.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2054 | 4444 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2053 | October 7, 2026 11:31 | October 7, 2026 3:31 | 10/7/26 11:31 | 10/7/26 3:31 | 6/2/26 2:30 | 6/3/26 8:30 | 0h | -726.02h | 0ed | 0 | NA | NA | April 17, 2026 4:45 | April 20, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.48.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2055 | 4445 | Yes | Auto Scheduled | OTC_CM22_Pricing_Condition | 0.69d | Fixed Duration | 5 | 0.69d |  | October 7, 2026 3:31 | October 8, 2026 1:01 | 10/7/26 3:31 | 10/8/26 1:01 | 6/3/26 8:30 | 6/3/26 4:00 | 0d | -90.75d | 0ed | 0 | NA | NA | April 20, 2026 10:45 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 8.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.49 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2056 | 4446 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 2054 | October 7, 2026 3:31 | October 7, 2026 4:01 | 10/7/26 3:31 | 10/7/26 4:01 | 6/3/26 8:30 | 6/3/26 9:00 | 0m | -43561m | 0ed | 0 | NA | NA | April 20, 2026 10:45 | April 20, 2026 11:15 | Start No Earlier Than | 4/6/26 8:00 | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.49.1 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2057 | 4447 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 2056 | October 7, 2026 4:01 | October 8, 2026 9:01 | 10/7/26 4:01 | 10/8/26 9:01 | 6/3/26 9:00 | 6/3/26 11:00 | 0h | -726.02h | 0ed | 0 | NA | NA | April 20, 2026 11:15 | April 20, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.49.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2058 | 4448 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2057 | October 8, 2026 9:01 | October 8, 2026 1:01 | 10/8/26 9:01 | 10/8/26 1:01 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -725.02h | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 21, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 6h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.49.3 | 500 | No | No | No |  | Matt Palastro, Dave Duda,kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2059 | 4449 | Yes | Auto Scheduled | OTC_CM21_CMIR | 0.5d | Fixed Duration | 5 | 1.13d |  | October 8, 2026 9:01 | October 8, 2026 2:01 | 10/8/26 9:01 | 10/8/26 2:01 | 6/3/26 11:00 | 6/3/26 4:00 | 0d | -90.75d | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 21, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 4h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.50 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2060 | 4450 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 2057,2068 | October 8, 2026 9:01 | October 8, 2026 9:31 | 10/8/26 9:01 | 10/8/26 9:31 | 6/3/26 11:00 | 6/3/26 11:30 | 0m | -43561m | 0ed | 0 | NA | NA | April 20, 2026 2:15 | April 20, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.50.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2061 | 4451 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 2060 | October 8, 2026 9:31 | October 8, 2026 10:01 | 10/8/26 9:31 | 10/8/26 10:01 | 6/3/26 11:30 | 6/3/26 12:00 | 0m | -43561m | 0ed | 0 | NA | NA | April 20, 2026 2:45 | April 20, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.50.2 | 500 | No | No | No |  | Kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2062 | 4452 | Yes | Auto Scheduled | Simulate Load | 0h | Fixed Units | 6 | 0.13d | 2061 | October 8, 2026 10:01 | October 8, 2026 10:01 | 10/8/26 10:01 | 10/8/26 10:01 | 6/3/26 1:00 | 6/3/26 1:00 | 0h | -726.02h | 0ed | 0 | NA | NA | April 20, 2026 3:15 | April 20, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.50.3 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2063 | 4453 | Yes | Auto Scheduled | Error and Defect Mitigation | 0h | Fixed Units | 6 | 0.25d | 2062 | October 8, 2026 10:01 | October 8, 2026 10:01 | 10/8/26 10:01 | 10/8/26 10:01 | 6/3/26 1:00 | 6/3/26 1:00 | 0h | -726.02h | 0ed | 0 | NA | NA | April 20, 2026 4:15 | April 21, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.50.4 | 500 | Yes | No | No |  | Kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2064 | 4454 | Yes | Auto Scheduled | Load | 0h | Fixed Units | 6 | 0.25d | 2063 | October 8, 2026 10:01 | October 8, 2026 10:01 | 10/8/26 10:01 | 10/8/26 10:01 | 6/3/26 1:00 | 6/3/26 1:00 | 0h | -726.02h | 0ed | 0 | NA | NA | April 21, 2026 9:15 | April 21, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.50.5 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2065 | 4455 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2064 | October 8, 2026 10:01 | October 8, 2026 2:01 | 10/8/26 10:01 | 10/8/26 2:01 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -726.02h | 0ed | 0 | NA | NA | April 21, 2026 11:15 | April 21, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.50.6 | 500 | No | No | No |  | Kim | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2066 | 4456 | Yes | Auto Scheduled | PTP_CM29_Source_List | 6.16d | Fixed Duration | 5 | 0.94d |  | September 25, 2026 9:31 | October 5, 2026 10:46 | 9/25/26 9:31 | 10/5/26 10:46 | 6/3/26 9:00 | 6/3/26 4:00 | 0d | -87.47d | 0ed | 0 | NA | NA | April 13, 2026 10:45 | April 14, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 5.5h | 5.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.51 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2067 | 4457 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1910,1917 | September 25, 2026 9:31 | September 25, 2026 10:01 | 9/25/26 9:31 | 9/25/26 10:01 | 6/3/26 3:30 | 6/3/26 4:00 | 0m | -39061m | 0ed | 0 | NA | NA | April 14, 2026 9:45 | April 14, 2026 10:15 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.51.1 | 500 | No | No | No |  | Sam | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2068 | 4458 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 1886 | October 2, 2026 2:46 | October 2, 2026 4:46 | 10/2/26 2:46 | 10/2/26 4:46 | 6/3/26 9:00 | 6/3/26 11:00 | 0h | -700.77h | 0ed | 0 | NA | NA | April 13, 2026 10:45 | April 13, 2026 1:45 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.51.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2069 | 4459 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2068 | October 2, 2026 4:46 | October 5, 2026 10:46 | 10/2/26 4:46 | 10/5/26 10:46 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -699.77h | 0ed | 0 | NA | NA | April 13, 2026 1:45 | April 13, 2026 4:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.51.3 | 500 | No | No | No |  | Sam | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2070 | 4460 | Yes | Auto Scheduled | RTR_CM11_Asset_Master | 6.63d | Fixed Duration | 5 | 1.13d |  | September 24, 2026 8:31 | October 2, 2026 2:31 | 9/24/26 8:31 | 10/2/26 2:31 | 5/26/26 10:00 | 6/3/26 4:00 | 0d | -86.81d | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 53.5h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.52 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2071 | 4461 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d |  | September 24, 2026 8:31 | September 24, 2026 9:01 | 9/24/26 8:31 | 9/24/26 9:01 | 5/26/26 10:00 | 5/26/26 10:30 | 0m | -41671m | 0ed | 0 | NA | NA | April 10, 2026 9:45 | April 10, 2026 10:15 | Start No Earlier Than | 4/15/26 8:00 | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.52.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2072 | 4462 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 2071 | September 24, 2026 9:01 | September 24, 2026 9:31 | 9/24/26 9:01 | 9/24/26 9:31 | 5/26/26 10:30 | 5/26/26 11:00 | 0m | -41671m | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.52.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2073 | 4463 | Yes | Auto Scheduled | Simulate Load | 31h | Fixed Units | 6 | 0.13d | 2072 | September 24, 2026 9:31 | September 30, 2026 8:31 | 9/24/26 9:31 | 9/30/26 8:31 | 5/26/26 11:00 | 6/1/26 10:00 | 0h | -694.52h | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:45 | Finish No Earlier Than | 4/20/26 5:00 | NA | NA | 4/30/26 2:05 | 31h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.52.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2074 | 4464 | Yes | Auto Scheduled | Error and Defect Mitigation | 16h | Fixed Units | 6 | 0.25d | 2073 | September 30, 2026 8:31 | October 2, 2026 8:31 | 9/30/26 8:31 | 10/2/26 8:31 | 6/1/26 10:00 | 6/3/26 10:00 | 0h | -694.52h | 0ed | 0 | NA | NA | April 10, 2026 11:45 | April 10, 2026 2:45 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/30/26 2:05 | 16h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.52.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2075 | 4465 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 2074 | October 2, 2026 8:31 | October 2, 2026 10:31 | 10/2/26 8:31 | 10/2/26 10:31 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -694.52h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 4:45 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.52.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2076 | 4466 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2075 | October 2, 2026 10:31 | October 2, 2026 2:31 | 10/2/26 10:31 | 10/2/26 2:31 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -694.52h | 0ed | 0 | NA | NA | April 10, 2026 4:45 | April 13, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.52.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2077 | 4467 | Yes | Auto Scheduled | PTM_CM50_Material Class | 2.13d | Fixed Duration | 5 | 0.25d |  | September 29, 2026 3:46 | October 1, 2026 4:46 | 9/29/26 3:46 | 10/1/26 4:46 | 6/1/26 3:00 | 6/3/26 4:00 | 0d | -86.1d | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 17h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.53 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2078 | 4468 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 1983 | September 29, 2026 3:46 | September 29, 2026 4:16 | 9/29/26 3:46 | 9/29/26 4:16 | 6/1/26 3:00 | 6/1/26 3:30 | 0m | -41326m | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.53.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2079 | 4469 | Yes | Auto Scheduled | Load | 30m | Fixed Units | 6 | 0.06d | 2078 | September 29, 2026 4:16 | September 29, 2026 4:46 | 9/29/26 4:16 | 9/29/26 4:46 | 6/1/26 3:30 | 6/1/26 4:00 | 0m | -41326m | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.53.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2080 | 4470 | Yes | Auto Scheduled | Post Load Validation | 16h | Fixed Units | 6 | 0.13d | 2079 | September 29, 2026 4:46 | October 1, 2026 4:46 | 9/29/26 4:46 | 10/1/26 4:46 | 6/1/26 4:00 | 6/3/26 4:00 | 0h | -688.77h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | Finish No Earlier Than | 4/20/26 5:00 | NA | NA | 4/30/26 2:05 | 16h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.53.3 | 500 | No | No | No |  | brad | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2081 | 4471 | Yes | Auto Scheduled | PTM_CM55_Class assignment to materials | 1.13d | Fixed Duration | 5 | 1.13d |  | September 29, 2026 4:16 | October 1, 2026 8:16 | 9/29/26 4:16 | 10/1/26 8:16 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -85.16d | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.54 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2082 | 4472 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 2078 | September 29, 2026 4:16 | September 29, 2026 4:46 | 9/29/26 4:16 | 9/29/26 4:46 | 6/2/26 3:00 | 6/2/26 3:30 | 0m | -40876m | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.54.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2083 | 4473 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 2082 | September 29, 2026 4:46 | September 30, 2026 8:16 | 9/29/26 4:46 | 9/30/26 8:16 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -40876m | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.54.2 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2084 | 4474 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 2083 | September 30, 2026 8:16 | September 30, 2026 9:16 | 9/30/26 8:16 | 9/30/26 9:16 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -681.27h | 0ed | 0 | NA | NA | April 16, 2026 1:15 | April 16, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.54.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2085 | 4475 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 2084 | September 30, 2026 9:16 | September 30, 2026 11:16 | 9/30/26 9:16 | 9/30/26 11:16 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -681.27h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.54.4 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2086 | 4476 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 2085 | September 30, 2026 11:16 | September 30, 2026 2:16 | 9/30/26 11:16 | 9/30/26 2:16 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -681.27h | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 17, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.54.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2087 | 4477 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2086 | September 30, 2026 2:16 | October 1, 2026 8:16 | 9/30/26 2:16 | 10/1/26 8:16 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -681.27h | 0ed | 0 | NA | NA | April 17, 2026 9:15 | April 17, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.54.6 | 500 | No | No | No |  | Matt Palastro, Dave Duda | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2088 | 4478 | Yes | Auto Scheduled | GTS - Material initial load from S4 (Run Interface) | 2.09d | Fixed Duration | 5 | 0.25d |  | September 29, 2026 1:16 | October 1, 2026 2:01 | 9/29/26 1:16 | 10/1/26 2:01 | 5/27/26 1:00 | 5/29/26 1:45 | 0d | -89.03d | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 16.75h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.55 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2089 | 4479 | Yes | Auto Scheduled | Run material interface to GTS | 15.75h | Fixed Units | 6 | 0.13d | 1957 | September 29, 2026 1:16 | October 1, 2026 1:01 | 9/29/26 1:16 | 10/1/26 1:01 | 5/27/26 1:00 | 5/29/26 11:45 | 0h | -712.27h | 0ed | 0 | NA | NA | April 16, 2026 8:15 | April 16, 2026 9:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/30/26 2:05 | 15.75h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.55.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2090 | 4480 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 2089 | October 1, 2026 1:01 | October 1, 2026 2:01 | 10/1/26 1:01 | 10/1/26 2:01 | 5/29/26 11:45 | 5/29/26 1:45 | 0h | -712.27h | 0ed | 0 | NA | NA | April 16, 2026 9:15 | April 16, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.55.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2091 | 4481 | Yes | Auto Scheduled | GTS - Customers initial load from S4 (Run Interface) | 0.25d | Fixed Duration | 5 | 0.25d |  | September 24, 2026 8:31 | September 24, 2026 10:31 | 9/24/26 8:31 | 9/24/26 10:31 | 6/3/26 2:00 | 6/3/26 4:00 | 0d | -80.44d | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 3:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.56 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2092 | 4482 | Yes | Auto Scheduled | Run material interface to GTS | 1h | Fixed Units | 6 | 0.13d |  | September 24, 2026 8:31 | September 24, 2026 9:31 | 9/24/26 8:31 | 9/24/26 9:31 | 6/3/26 2:00 | 6/3/26 3:00 | 0h | -643.52h | 0ed | 0 | NA | NA | April 10, 2026 1:45 | April 10, 2026 2:45 | Start No Earlier Than | 4/15/26 8:00 | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.56.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2093 | 4483 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 2092 | September 24, 2026 9:31 | September 24, 2026 10:31 | 9/24/26 9:31 | 9/24/26 10:31 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -643.52h | 0ed | 0 | NA | NA | April 10, 2026 2:45 | April 10, 2026 3:45 | Finish No Earlier Than | 4/20/26 5:00 | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.56.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2094 | 4484 | Yes | Auto Scheduled | GTS - Vendors initial load from S4 (Run Interface) | 0.25d | Fixed Duration | 5 | 0.25d |  | September 24, 2026 4:31 | September 25, 2026 9:31 | 9/24/26 4:31 | 9/25/26 9:31 | 6/3/26 10:00 | 6/3/26 4:00 | 0d | -81.69d | 0ed | 0 | NA | NA | April 15, 2026 2:00 | April 15, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.57 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2095 | 4485 | Yes | Auto Scheduled | Run material interface to GTS | 1h | Fixed Units | 6 | 0.13d | 1900 | September 24, 2026 4:31 | September 25, 2026 8:31 | 9/24/26 4:31 | 9/25/26 8:31 | 6/3/26 10:00 | 6/3/26 11:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 15, 2026 2:00 | April 15, 2026 3:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.57.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2096 | 4486 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 2095 | September 25, 2026 8:31 | September 25, 2026 9:31 | 9/25/26 8:31 | 9/25/26 9:31 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -650.52h | 0ed | 0 | NA | NA | April 15, 2026 3:00 | April 15, 2026 4:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.57.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2097 | 4487 | Yes | Auto Scheduled | GTS - ECCN - Create | 1.13d | Fixed Duration | 5 | 5.63d |  | September 24, 2026 8:31 | September 25, 2026 9:31 | 9/24/26 8:31 | 9/25/26 9:31 | 6/3/26 11:00 | 6/3/26 4:00 | 0d | -81.31d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 13, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.58 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2098 | 4488 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 1771 | September 24, 2026 8:31 | September 24, 2026 9:31 | 9/24/26 8:31 | 9/24/26 9:31 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -642.52h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.58.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2099 | 4489 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 2095 | September 25, 2026 8:31 | September 25, 2026 9:31 | 9/25/26 8:31 | 9/25/26 9:31 | 6/3/26 11:00 | 6/3/26 12:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 13, 2026 1:15 | April 13, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.58.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2100 | 4490 | Yes | Auto Scheduled | GTS - ECCN - Assign | 0.25d | Fixed Duration | 5 | 0.25d |  | October 1, 2026 2:01 | October 1, 2026 4:01 | 10/1/26 2:01 | 10/1/26 4:01 | 5/29/26 1:45 | 5/29/26 3:45 | 0d | -89.03d | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.59 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2101 | 4491 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 2090 | October 1, 2026 2:01 | October 1, 2026 3:01 | 10/1/26 2:01 | 10/1/26 3:01 | 5/29/26 1:45 | 5/29/26 2:45 | 0h | -712.27h | 0ed | 0 | NA | NA | April 16, 2026 10:15 | April 16, 2026 11:15 | Finish No Earlier Than | 4/17/26 5:00 | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.59.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2102 | 4492 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 2101 | October 1, 2026 3:01 | October 1, 2026 4:01 | 10/1/26 3:01 | 10/1/26 4:01 | 5/29/26 2:45 | 5/29/26 3:45 | 0h | -712.27h | 0ed | 0 | NA | NA | April 16, 2026 11:15 | April 16, 2026 1:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.59.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2103 | 4493 | Yes | Auto Scheduled | GTS - HTS - Create | 0.25d | Fixed Duration | 5 | 0.25d |  | September 24, 2026 8:31 | September 24, 2026 10:31 | 9/24/26 8:31 | 9/24/26 10:31 | 6/3/26 2:00 | 6/3/26 4:00 | 0d | -80.44d | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.60 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2104 | 4494 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 1771 | September 24, 2026 8:31 | September 24, 2026 9:31 | 9/24/26 8:31 | 9/24/26 9:31 | 6/3/26 2:00 | 6/3/26 3:00 | 0h | -643.52h | 0ed | 0 | NA | NA | April 6, 2026 8:15 | April 6, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.60.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2105 | 4495 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 2104 | September 24, 2026 9:31 | September 24, 2026 10:31 | 9/24/26 9:31 | 9/24/26 10:31 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -643.52h | 0ed | 0 | NA | NA | April 6, 2026 9:15 | April 6, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.60.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2106 | 4496 | Yes | Auto Scheduled | GTS - HTS - Assign | 0.25d | Fixed Duration | 5 | 0.25d |  | October 1, 2026 4:01 | October 2, 2026 9:01 | 10/1/26 4:01 | 10/2/26 9:01 | 5/29/26 3:45 | 6/1/26 8:45 | 0d | -89.03d | 0ed | 0 | NA | NA | April 16, 2026 8:45 | April 16, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.61 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2107 | 4497 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 2102 | October 1, 2026 4:01 | October 2, 2026 8:01 | 10/1/26 4:01 | 10/2/26 8:01 | 5/29/26 3:45 | 5/29/26 4:45 | 0h | -712.27h | 0ed | 0 | NA | NA | April 16, 2026 8:45 | April 16, 2026 9:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.61.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2108 | 4498 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 2107 | October 2, 2026 8:01 | October 2, 2026 9:01 | 10/2/26 8:01 | 10/2/26 9:01 | 5/29/26 4:45 | 6/1/26 8:45 | 0h | -712.27h | 0ed | 0 | NA | NA | April 16, 2026 9:45 | April 16, 2026 10:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.61.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2109 | 4499 | Yes | Auto Scheduled | GTS - License - Create | 0.25d | Fixed Duration | 5 | 0.25d |  | October 2, 2026 10:01 | October 2, 2026 1:01 | 10/2/26 10:01 | 10/2/26 1:01 | 6/3/26 2:00 | 6/3/26 4:00 | 0d | -86.63d | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.62 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2110 | 4500 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 2107,2123 | October 2, 2026 10:01 | October 2, 2026 11:01 | 10/2/26 10:01 | 10/2/26 11:01 | 6/3/26 2:00 | 6/3/26 3:00 | 0h | -693.02h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.62.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2111 | 4501 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 2110 | October 2, 2026 11:01 | October 2, 2026 1:01 | 10/2/26 11:01 | 10/2/26 1:01 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -693.02h | 0ed | 0 | NA | NA | April 16, 2026 1:45 | April 16, 2026 2:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.62.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2112 | 4502 | Yes | Auto Scheduled | Commodity Code/Tarif | 2.78d | Fixed Duration | 5 | 0.25d |  | October 2, 2026 9:01 | October 6, 2026 4:16 | 10/2/26 9:01 | 10/6/26 4:16 | 6/1/26 8:45 | 6/3/26 4:00 | 0d | -89.03d | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 22.25h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.63 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2113 | 4503 | Yes | Auto Scheduled | Load | 21.25h | Fixed Units | 6 | 0.13d | 2108 | October 2, 2026 9:01 | October 6, 2026 3:16 | 10/2/26 9:01 | 10/6/26 3:16 | 6/1/26 8:45 | 6/3/26 3:00 | 0h | -712.27h | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:45 | Finish No Earlier Than | 4/20/26 5:00 | NA | NA | 4/30/26 2:05 | 21.25h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.63.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2114 | 4504 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 2113 | October 6, 2026 3:16 | October 6, 2026 4:16 | 10/6/26 3:16 | 10/6/26 4:16 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -712.27h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.63.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2115 | 4505 | Yes | Auto Scheduled | SPL Master File | 0.25d | Fixed Duration | 5 | 0.25d |  | October 2, 2026 8:01 | October 2, 2026 10:01 | 10/2/26 8:01 | 10/2/26 10:01 | 6/3/26 2:00 | 6/3/26 4:00 | 0d | -86.38d | 0ed | 0 | NA | NA | March 13, 2025 8:00 | March 13, 2025 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.64 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2116 | 4506 | Yes | Auto Scheduled | Load | 1h | Fixed Units | 6 | 0.13d | 2107 | October 2, 2026 8:01 | October 2, 2026 9:01 | 10/2/26 8:01 | 10/2/26 9:01 | 6/3/26 2:00 | 6/3/26 3:00 | 0h | -691.02h | 0ed | 0 | NA | NA | March 13, 2025 8:00 | March 13, 2025 9:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.64.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2117 | 4507 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 2116 | October 2, 2026 9:01 | October 2, 2026 10:01 | 10/2/26 9:01 | 10/2/26 10:01 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -691.02h | 0ed | 0 | NA | NA | March 13, 2025 9:00 | March 13, 2025 10:00 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.64.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2118 | 4508 | Yes | Auto Scheduled | Initialize Embargo situation | 0.38d | Fixed Duration | 5 | 0.38d |  | September 25, 2026 9:31 | September 25, 2026 1:31 | 9/25/26 9:31 | 9/25/26 1:31 | 6/3/26 1:00 | 6/3/26 4:00 | 0d | -81.69d | 0ed | 0 | NA | NA | April 13, 2026 2:15 | April 14, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.65 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2119 | 4509 | Yes | Auto Scheduled | Run report /SAPSLL/EMB_CNTRY_INIT | 1h | Fixed Units | 6 | 0.13d | 2099 | September 25, 2026 9:31 | September 25, 2026 10:31 | 9/25/26 9:31 | 9/25/26 10:31 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 13, 2026 2:15 | April 13, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.65.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2120 | 4510 | Yes | Auto Scheduled | Set Embargo situations | 1h | Fixed Units | 6 | 0.13d | 2119 | September 25, 2026 10:31 | September 25, 2026 11:31 | 9/25/26 10:31 | 9/25/26 11:31 | 6/3/26 2:00 | 6/3/26 3:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 13, 2026 3:15 | April 13, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.65.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2121 | 4511 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 2120 | September 25, 2026 11:31 | September 25, 2026 1:31 | 9/25/26 11:31 | 9/25/26 1:31 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -653.52h | 0ed | 0 | NA | NA | April 13, 2026 4:15 | April 14, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.65.3 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2122 | 4512 | Yes | Auto Scheduled | GTS - SPL (Sanctioned party list) | 0.25d | Fixed Duration | 5 | 0.25d |  | October 2, 2026 9:01 | October 2, 2026 11:01 | 10/2/26 9:01 | 10/2/26 11:01 | 6/3/26 1:00 | 6/3/26 4:00 | 0d | -86.63d | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.66 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2123 | 4513 | Yes | Auto Scheduled | Load Descartes XML File | 1h | Fixed Units | 6 | 0.13d | 2108 | October 2, 2026 9:01 | October 2, 2026 10:01 | 10/2/26 9:01 | 10/2/26 10:01 | 6/3/26 1:00 | 6/3/26 2:00 | 0h | -693.02h | 0ed | 0 | NA | NA | April 16, 2026 10:45 | April 16, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.66.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2124 | 4514 | Yes | Auto Scheduled | Post Load Validation | 1h | Fixed Units | 6 | 0.13d | 2123 | October 2, 2026 10:01 | October 2, 2026 11:01 | 10/2/26 10:01 | 10/2/26 11:01 | 6/3/26 3:00 | 6/3/26 4:00 | 0h | -692.02h | 0ed | 0 | NA | NA | April 16, 2026 11:45 | April 16, 2026 1:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.66.2 | 500 | No | No | No |  | Kim Kolesar | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2125 | 4515 | Yes | Auto Scheduled | RTR_CM17_Project Definition / Builder | 1.13d | Fixed Duration | 5 | 5.38d |  | September 24, 2026 9:01 | September 25, 2026 10:01 | 9/24/26 9:01 | 9/25/26 10:01 | 6/2/26 2:30 | 6/3/26 4:00 | 0d | -81.44d | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.67 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2126 | 4516 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 2071 | September 24, 2026 9:01 | September 24, 2026 9:31 | 9/24/26 9:01 | 9/24/26 9:31 | 6/2/26 2:30 | 6/2/26 3:00 | 0m | -39091m | 0ed | 0 | NA | NA | April 10, 2026 10:15 | April 10, 2026 10:45 | Start No Earlier Than | 4/20/26 8:00 | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.67.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2127 | 4517 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 2126 | September 24, 2026 9:31 | September 24, 2026 10:01 | 9/24/26 9:31 | 9/24/26 10:01 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -39061m | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.67.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2128 | 4518 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 2127 | September 24, 2026 10:01 | September 24, 2026 11:01 | 9/24/26 10:01 | 9/24/26 11:01 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -651.02h | 0ed | 0 | NA | NA | April 16, 2026 2:15 | April 16, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.67.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2129 | 4519 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 2128 | September 24, 2026 11:01 | September 24, 2026 2:01 | 9/24/26 11:01 | 9/24/26 2:01 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -651.02h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 17, 2026 8:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.67.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2130 | 4520 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 2129 | September 24, 2026 2:01 | September 24, 2026 4:01 | 9/24/26 2:01 | 9/24/26 4:01 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -651.02h | 0ed | 0 | NA | NA | April 17, 2026 8:15 | April 17, 2026 10:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.67.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2131 | 4521 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2130 | September 24, 2026 4:01 | September 25, 2026 10:01 | 9/24/26 4:01 | 9/25/26 10:01 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -651.02h | 0ed | 0 | NA | NA | April 17, 2026 10:15 | April 17, 2026 2:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.67.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2132 | 4522 | Yes | Auto Scheduled | RTR_CM18_WBS Element | 1.25d | Fixed Duration | 5 | 5.44d |  | September 24, 2026 8:31 | September 25, 2026 10:31 | 9/24/26 8:31 | 9/25/26 10:31 | 6/2/26 3:00 | 6/3/26 4:00 | 0d | -81.44d | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 17, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 9.25h | 9h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.68 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2133 | 4523 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | Fixed Units | 6 | 0.06d | 2126 | September 24, 2026 9:31 | September 24, 2026 10:01 | 9/24/26 9:31 | 9/24/26 10:01 | 6/2/26 3:00 | 6/2/26 3:30 | 0m | -39091m | 0ed | 0 | NA | NA | April 10, 2026 10:45 | April 10, 2026 11:15 | Start No Earlier Than | 4/17/26 8:00 | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.68.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2134 | 4524 | Yes | Auto Scheduled | Pre Load Validation | 30m | Fixed Units | 6 | 0.06d | 2133 | September 24, 2026 10:01 | September 24, 2026 10:31 | 9/24/26 10:01 | 9/24/26 10:31 | 6/2/26 3:30 | 6/2/26 4:00 | 0m | -39091m | 0ed | 0 | NA | NA | April 10, 2026 11:15 | April 10, 2026 11:45 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.5h | 0.5h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.68.2 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2135 | 4525 | Yes | Auto Scheduled | Simulate Load | 1h | Fixed Units | 6 | 0.13d | 2134 | September 24, 2026 10:31 | September 24, 2026 11:31 | 9/24/26 10:31 | 9/24/26 11:31 | 6/2/26 4:00 | 6/2/26 5:00 | 0h | -651.52h | 0ed | 0 | NA | NA | April 16, 2026 3:15 | April 16, 2026 4:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.68.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2136 | 4526 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | Fixed Units | 6 | 0.25d | 2135 | September 24, 2026 11:31 | September 24, 2026 2:31 | 9/24/26 11:31 | 9/24/26 2:31 | 6/3/26 8:00 | 6/3/26 10:00 | 0h | -651.52h | 0ed | 0 | NA | NA | April 16, 2026 4:15 | April 17, 2026 9:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.68.4 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2137 | 4527 | Yes | Auto Scheduled | Load | 2h | Fixed Units | 6 | 0.25d | 2136 | September 24, 2026 2:31 | September 24, 2026 4:31 | 9/24/26 2:31 | 9/24/26 4:31 | 6/3/26 10:00 | 6/3/26 12:00 | 0h | -651.52h | 0ed | 0 | NA | NA | April 17, 2026 9:15 | April 17, 2026 11:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.68.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2138 | 4528 | Yes | Auto Scheduled | Post Load Validation | 3h | Fixed Units | 6 | 0.38d | 2137 | September 24, 2026 4:31 | September 25, 2026 10:31 | 9/24/26 4:31 | 9/25/26 10:31 | 6/3/26 1:00 | 6/3/26 4:00 | 0h | -651.52h | 0ed | 0 | NA | NA | April 17, 2026 11:15 | April 17, 2026 3:15 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 3h | 3h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.68.6 | 500 | No | No | No |  | Brian Wagner | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2139 | 4529 | Yes | Auto Scheduled | UAT Mock Data Loads Complete | 15m | Fixed Units | 6 | 0.03d |  | September 24, 2026 8:31 | September 24, 2026 8:46 | 9/24/26 8:31 | 9/24/26 8:46 | 6/3/26 3:45 | 6/3/26 4:00 | 0m | -38506m | 0ed | 0 | NA | NA | April 21, 2026 3:15 | April 21, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.2.68.7 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2140 | 4530 | Yes | Auto Scheduled | PROD Master Data Loads Complete | 0m | Fixed Units | 4 | 0d | 1772 | October 1, 2026 8:31 | October 1, 2026 8:31 | 10/1/26 8:31 | 10/1/26 8:31 | 6/3/26 4:00 | 6/3/26 4:00 | 0m | -40891m | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.3 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2141 | 4531 | Yes | Auto Scheduled | Mock Transactional Data | 2d | Fixed Duration | 4 | 0d | 2140 | October 1, 2026 8:31 | October 5, 2026 8:31 | 10/1/26 8:31 | 10/5/26 8:31 | 8/12/26 3:45 | 8/14/26 3:45 | 0d | -35.22d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.4 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2142 | 4532 | Yes | Auto Scheduled | Inventory | 4h | Fixed Units | 5 | 0d | 2140SS,998SS | October 1, 2026 8:31 | October 1, 2026 1:31 | 10/1/26 8:31 | 10/1/26 1:31 | 8/12/26 3:45 | 8/13/26 10:45 | 0h | -281.77h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2143 | 4533 | Yes | Auto Scheduled | Open AR | 4h | Fixed Units | 5 | 0d | 2142 | October 1, 2026 1:31 | October 2, 2026 8:31 | 10/1/26 1:31 | 10/2/26 8:31 | 8/13/26 10:45 | 8/13/26 3:45 | 0h | -281.77h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2144 | 4534 | Yes | Auto Scheduled | Open AP | 4h | Fixed Units | 5 | 0d | 2143 | October 2, 2026 8:31 | October 2, 2026 1:31 | 10/2/26 8:31 | 10/2/26 1:31 | 8/13/26 3:45 | 8/14/26 10:45 | 0h | -281.77h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2145 | 4535 | Yes | Auto Scheduled | Bank and Cash | 4h | Fixed Units | 5 | 0d | 2144 | October 2, 2026 1:31 | October 5, 2026 8:31 | 10/2/26 1:31 | 10/5/26 8:31 | 8/14/26 10:45 | 8/14/26 3:45 | 0h | -281.77h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2146 | 4536 | Yes | Auto Scheduled | Open Purchase Orders(Manual) | 1d | Fixed Units | 5 | 0d | 2142 | October 1, 2026 1:31 | October 2, 2026 1:31 | 10/1/26 1:31 | 10/2/26 1:31 | 8/13/26 3:45 | 8/14/26 3:45 | 0d | -34.72d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2147 | 4537 | Yes | Auto Scheduled | Open Sales Orders(Manual) | 1d | Fixed Units | 5 | 0d | 2142 | October 1, 2026 1:31 | October 2, 2026 1:31 | 10/1/26 1:31 | 10/2/26 1:31 | 8/13/26 3:45 | 8/14/26 3:45 | 0d | -34.72d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2148 | 4538 | Yes | Auto Scheduled | Service Orders(Manual) | 0.5d | Fixed Units | 5 | 0d | 2142 | October 1, 2026 1:31 | October 2, 2026 8:31 | 10/1/26 1:31 | 10/2/26 8:31 | 8/14/26 10:45 | 8/14/26 3:45 | 0d | -34.22d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2149 | 4539 | Yes | Auto Scheduled | Open Production Orders(Manual) | 1d | Fixed Units | 5 | 0d | 2142 | October 1, 2026 1:31 | October 2, 2026 1:31 | 10/1/26 1:31 | 10/2/26 1:31 | 8/13/26 3:45 | 8/14/26 3:45 | 0d | -34.72d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.4.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2150 | 4540 | Yes | Auto Scheduled | PRO Data Loads Complete | 15m | Fixed Units | 4 | 0.03d | 2141 | October 5, 2026 8:31 | October 5, 2026 8:46 | 10/5/26 8:31 | 10/5/26 8:46 | 8/14/26 3:45 | 8/14/26 4:00 | 0m | -16906m | 0ed | 0 | NA | NA | April 21, 2026 3:15 | April 21, 2026 3:30 | As Soon As Possible | NA | NA | NA | 4/30/26 2:05 | 0.25h | 0.25h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2.5.5 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2151 | 681 | Yes | Auto Scheduled | Solution Readniess | 131.5d | Fixed Duration | 2 | 100.13d |  | April 16, 2026 8:00 | October 16, 2026 12:00 | 4/16/26 8:00 | 10/16/26 12:00 | 4/16/26 8:00 | 11/9/26 5:00 | 16.5d | 16.5d | 0ed | 2.9999999999999999E-2 | 4/16/26 8:00 | NA | April 16, 2026 8:00 | September 3, 2026 9:00 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 10:00 | 3/24/26 6:38 | 136h | 89h | 1h | 0 | 0 | 0 | 0 | 0 | 1.3 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2152 | 843 | Yes | Auto Scheduled | Business Process Design Documentation | 20d | Fixed Duration | 3 | 1d |  | May 4, 2026 8:00 | May 29, 2026 5:00 | 5/4/26 8:00 | 5/29/26 5:00 | 5/4/26 8:00 | 11/9/26 5:00 | 116d | 116d | 0ed | 4.0000000000000001E-2 | 5/4/26 8:00 | NA | May 22, 2026 8:00 | May 22, 2026 5:00 | As Soon As Possible | NA | 5/4/26 1:48 | 5/4/26 1:48 | 3/30/26 3:42 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.1 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2153 | 844 | Yes | Auto Scheduled | FICO | 20d | Fixed Units | 4 | 1d |  | May 4, 2026 8:00 | May 29, 2026 5:00 | 5/4/26 8:00 | 5/29/26 5:00 | 5/4/26 8:00 | 11/9/26 5:00 | 116d | 116d | 0ed | 2.9999999999999999E-2 | 5/4/26 8:00 | NA | May 22, 2026 8:00 | May 22, 2026 5:00 | As Soon As Possible | NA | 5/4/26 1:48 | 5/4/26 1:48 | 3/30/26 3:42 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.1.1 | 500 | No | No | No |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2154 | 845 | Yes | Auto Scheduled | Order to Cash | 20d | Fixed Units | 4 | 1d |  | May 4, 2026 8:00 | May 29, 2026 5:00 | 5/4/26 8:00 | 5/29/26 5:00 | 5/4/26 8:00 | 11/9/26 5:00 | 116d | 116d | 0ed | 4.0000000000000001E-2 | 5/4/26 8:00 | NA | May 22, 2026 8:00 | May 22, 2026 5:00 | As Soon As Possible | NA | 5/4/26 3:48 | 5/4/26 3:48 | 3/30/26 3:42 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.1.2 | 500 | No | No | No |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2155 | 846 | Yes | Auto Scheduled | Procure to Pay | 20d | Fixed Units | 4 | 1d |  | May 4, 2026 8:00 | May 29, 2026 5:00 | 5/4/26 8:00 | 5/29/26 5:00 | 5/4/26 8:00 | 11/9/26 5:00 | 116d | 116d | 0ed | 4.0000000000000001E-2 | 5/4/26 8:00 | NA | May 22, 2026 8:00 | May 22, 2026 5:00 | As Soon As Possible | NA | 5/4/26 3:48 | 5/4/26 3:48 | 3/30/26 3:42 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.1.3 | 500 | No | No | No |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2156 | 847 | Yes | Auto Scheduled | Plan to Make | 20d | Fixed Units | 4 | 1d |  | May 4, 2026 8:00 | May 29, 2026 5:00 | 5/4/26 8:00 | 5/29/26 5:00 | 5/4/26 8:00 | 11/9/26 5:00 | 116d | 116d | 0ed | 5.0000000000000003E-2 | 5/4/26 8:00 | NA | May 22, 2026 8:00 | May 22, 2026 5:00 | As Soon As Possible | NA | 5/4/26 4:36 | 5/4/26 4:36 | 3/30/26 3:42 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.1.4 | 500 | No | No | No |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2157 | 835 | Yes | Auto Scheduled | Development RICEFW | 75d | Fixed Duration | 3 | 1d |  | May 4, 2026 8:00 | August 14, 2026 5:00 | 5/4/26 8:00 | 8/14/26 5:00 | 5/4/26 8:00 | 11/9/26 5:00 | 61d | 61d | 0ed | 0 | 5/4/26 8:00 | NA | May 22, 2026 8:00 | May 22, 2026 5:00 | As Soon As Possible | NA | 5/4/26 8:00 | 5/4/26 8:00 | 3/30/26 3:34 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2158 | 836 | Yes | Auto Scheduled | Reports | 75d | Fixed Units | 4 | 1d |  | May 4, 2026 8:00 | August 14, 2026 5:00 | 5/4/26 8:00 | 8/14/26 5:00 | 7/28/26 8:00 | 11/9/26 5:00 | 61d | 61d | 0ed | 0 | NA | NA | May 22, 2026 8:00 | May 22, 2026 5:00 | Finish No Earlier Than | 8/14/26 5:00 | NA | NA | 3/30/26 3:34 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.2.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2159 | 837 | Yes | Auto Scheduled | Interfaces | 75d | Fixed Units | 4 | 1d |  | May 4, 2026 8:00 | August 14, 2026 5:00 | 5/4/26 8:00 | 8/14/26 5:00 | 7/28/26 8:00 | 11/9/26 5:00 | 61d | 61d | 0ed | 0 | NA | NA | May 22, 2026 8:00 | May 22, 2026 5:00 | Start No Earlier Than | 5/4/26 8:00 | NA | NA | 3/30/26 3:34 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.2.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2160 | 838 | Yes | Auto Scheduled | Enhanchments | 61d | Fixed Units | 4 | 1d |  | May 4, 2026 8:00 | August 14, 2026 5:00 | 5/4/26 8:00 | 8/14/26 5:00 | 5/4/26 8:00 | 11/9/26 5:00 | 61d | 61d | 0ed | 0 | 5/4/26 8:00 | NA | May 22, 2026 8:00 | May 22, 2026 5:00 | Finish No Earlier Than | 8/14/26 5:00 | 5/4/26 10:24 | 5/22/26 10:24 | 3/30/26 3:34 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.2.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2161 | 839 | Yes | Auto Scheduled | Workflow | 75d | Fixed Units | 4 | 1d |  | May 4, 2026 8:00 | August 14, 2026 5:00 | 5/4/26 8:00 | 8/14/26 5:00 | 7/28/26 8:00 | 11/9/26 5:00 | 61d | 61d | 0ed | 0 | NA | NA | May 22, 2026 8:00 | May 22, 2026 5:00 | Start No Earlier Than | 5/4/26 8:00 | NA | NA | 3/30/26 3:34 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.2.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2162 | 840 | Yes | Auto Scheduled | Forms | 0d | Fixed Units | 4 | 1d |  | August 14, 2026 5:00 | August 14, 2026 5:00 | 8/14/26 5:00 | 8/14/26 5:00 | 11/9/26 5:00 | 11/9/26 5:00 | 61d | 61d | 0ed | 0 | NA | NA | May 22, 2026 8:00 | May 22, 2026 5:00 | Finish No Earlier Than | 8/14/26 5:00 | NA | NA | 3/30/26 3:35 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.2.5 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2163 | 18 | Yes | Auto Scheduled | Testing Cycles | 131.5d | Fixed Duration | 3 | 100.13d |  | April 16, 2026 8:00 | October 16, 2026 12:00 | 4/16/26 8:00 | 10/16/26 12:00 | 4/16/26 8:00 | 11/9/26 5:00 | 16.5d | 16.5d | 0ed | 0.13 | 4/16/26 8:00 | NA | April 16, 2026 8:00 | September 3, 2026 9:00 | As Soon As Possible | NA | 4/16/26 8:15 | 4/16/26 10:00 | 3/13/25 11:09 | 136h | 89h | 1h | 0 | 0 | 0 | 0 | 0 | 1.3.3 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2164 | 932 | Yes | Auto Scheduled | Test Readiness Review (TRR) - ITC 1 | 1h | Fixed Units | 4 | 0.13d | 628 | April 16, 2026 8:00 | May 1, 2026 8:45 | 4/16/26 8:00 | 5/1/26 8:45 | 4/16/26 8:00 | 4/16/26 9:00 | 0h | -87.75h | 0ed | 0.25 | 4/16/26 8:00 | NA | April 16, 2026 8:00 | April 16, 2026 9:00 | Start No Earlier Than | 4/16/26 8:00 | 4/16/26 8:15 | 5/1/26 8:00 | 3/31/26 9:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.1 | 500 | No | No | No |  |  | Red | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2165 | 2799 | Yes | Auto Scheduled | Test Readiness Review (TRR) - ITC 2 | 1h | Fixed Units | 4 | 0.13d | 1008,2180 | October 12, 2026 2:00 | October 12, 2026 3:00 | 10/12/26 2:00 | 10/12/26 3:00 | 6/5/26 4:00 | 6/5/26 5:00 | 0h | -726h | 0ed | 0 | NA | NA | June 18, 2026 8:00 | June 18, 2026 9:00 | As Soon As Possible | NA | NA | NA | 4/23/26 11:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2166 | 931 | Yes | Auto Scheduled | Test Readiness Review (TRR) - ITC 3 | 1h | Fixed Units | 4 | 0.13d | 2190,1388 | June 30, 2026 11:00 | June 30, 2026 12:00 | 6/30/26 11:00 | 6/30/26 12:00 | 7/10/26 4:00 | 7/10/26 5:00 | 68h | 68h | 0ed | 0 | NA | NA | June 18, 2026 8:00 | June 18, 2026 9:00 | As Soon As Possible | NA | NA | NA | 3/31/26 9:21 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2167 | 690 | Yes | Auto Scheduled | Test Readiness Review (TRR) - UAT | 1h | Fixed Units | 4 | 0.13d | 1769,2199,2150 | October 16, 2026 11:00 | October 16, 2026 12:00 | 10/16/26 11:00 | 10/16/26 12:00 | 8/14/26 4:00 | 8/14/26 5:00 | 0h | -356h | 0ed | 0 | NA | NA | August 6, 2026 8:00 | August 6, 2026 9:00 | As Soon As Possible | NA | NA | NA | 3/24/26 6:53 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2168 | 19 | Yes | Auto Scheduled | ITC-1 | 23.88d | Fixed Duration | 4 | 70d | 2164 | April 16, 2026 9:00 | May 19, 2026 5:00 | 4/16/26 9:00 | 5/19/26 5:00 | 4/16/26 9:00 | 11/9/26 5:00 | 124d | 124d | 0ed | 0.37 | 4/16/26 9:00 | NA | April 16, 2026 9:00 | July 23, 2026 9:00 | As Soon As Possible | NA | 4/16/26 10:00 | 4/16/26 10:00 | 3/13/25 11:10 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.3.3.5 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2169 | 834 | Yes | Auto Scheduled | Testing expectations | 1h | Fixed Units | 5 | 0.13d | 2164 | April 16, 2026 9:00 | April 16, 2026 10:00 | 4/16/26 9:00 | 4/16/26 10:00 | 4/16/26 9:00 | 4/16/26 10:00 | 0h | 0h | 0ed | 1 | 4/16/26 9:00 | 4/16/26 10:00 | April 16, 2026 9:00 | April 16, 2026 10:00 | Start No Earlier Than | 4/8/26 8:00 | 4/16/26 10:00 | 4/16/26 10:00 | 3/30/26 2:44 | 1h | 1h | 1h | 0 | 0 | 0 | 0 | 0 | 1.3.3.5.1 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2170 | 685 | Yes | Auto Scheduled | Functional Smoke Testing | 5d | Fixed Units | 5 | 5d | 2169 | April 20, 2026 8:00 | April 29, 2026 12:00 | 4/20/26 8:00 | 4/29/26 12:00 | 4/20/26 8:00 | 4/29/26 12:00 | 0d | 0d | 0ed | 1 | 4/20/26 8:00 | 4/29/26 12:00 | April 20, 2026 8:00 | April 24, 2026 5:00 | Start No Earlier Than | 4/20/26 8:00 | 4/29/26 12:00 | 4/29/26 12:00 | 3/24/26 6:46 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.5.2 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2171 | 684 | Yes | Auto Scheduled | Assign Tester ID's | 2h | Fixed Units | 5 | 0.25d | 2164 | April 16, 2026 9:00 | April 23, 2026 4:30 | 4/16/26 9:00 | 4/23/26 4:30 | 4/16/26 9:00 | 4/23/26 4:30 | 0h | 0h | 0ed | 1 | 4/16/26 9:00 | 4/23/26 4:30 | April 16, 2026 9:00 | April 16, 2026 11:00 | Finish No Earlier Than | 3/13/25 5:00 | 4/23/26 4:30 | 4/23/26 4:30 | 3/24/26 6:45 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.5.3 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2172 | 686 | Yes | Auto Scheduled | ITC-1 Team Testing | 15d | Fixed Units | 5 | 15d | 2171 | April 27, 2026 8:00 | May 18, 2026 10:45 | 4/27/26 8:00 | 5/18/26 10:45 | 4/27/26 8:00 | 11/9/26 5:00 | 3d | 125.66d | 0ed | 0.25 | 4/27/26 8:00 | NA | April 27, 2026 8:00 | May 15, 2026 5:00 | Start No Earlier Than | 4/27/26 8:00 | 4/30/26 3:00 | 5/1/26 8:45 | 3/24/26 6:47 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.5.4 | 500 | No | No | No |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2173 | 688 | Yes | Auto Scheduled | ITC-1 Defect Correction / Retesting / Mitigation / Close | 10d | Fixed Units | 5 | 10d | 2172SS+4d | May 6, 2026 8:00 | May 19, 2026 5:00 | 5/6/26 8:00 | 5/19/26 5:00 | 5/6/26 8:00 | 11/9/26 5:00 | 0d | 124d | 0ed | 0.25 | 5/6/26 8:00 | NA | May 18, 2026 8:00 | May 29, 2026 5:00 | As Soon As Possible | NA | 5/8/26 12:00 | 5/8/26 1:00 | 3/24/26 6:49 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.5.5 | 500 | No | No | No |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2174 | 689 | Yes | Auto Scheduled | ITC-1 Gate Review | 8h | Fixed Units | 5 | 0.13d | 2173FS-3d | May 15, 2026 8:00 | May 15, 2026 5:00 | 5/15/26 8:00 | 5/15/26 5:00 | 11/9/26 8:00 | 11/9/26 5:00 | 1008h | 1008h | 0ed | 0 | NA | NA | July 23, 2026 8:00 | July 23, 2026 9:00 | As Soon As Possible | NA | NA | NA | 3/24/26 6:52 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.5.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2175 | 2791 | Yes | Auto Scheduled | ITC-2 | 15.13d | Fixed Duration | 4 | 62d |  | May 29, 2026 4:00 | June 19, 2026 5:00 | 5/29/26 4:00 | 6/19/26 5:00 | 5/28/26 11:00 | 11/9/26 5:00 | 0d | -1.5d | 0ed | 0 | NA | NA | April 30, 2026 8:00 | July 24, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/23/26 11:05 | 45h | 44h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.6 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2176 | 2792 | Yes | Auto Scheduled | Assign Resources to Depolyment 1 locations | 2h | Fixed Units | 5 | 0.13d | 998 | May 29, 2026 4:00 | June 1, 2026 9:00 | 5/29/26 4:00 | 6/1/26 9:00 | 5/28/26 11:00 | 5/28/26 2:00 | 0h | -12h | 0ed | 0 | NA | NA | April 30, 2026 8:00 | April 30, 2026 9:00 | As Soon As Possible | NA | NA | NA | 4/23/26 11:05 | 2h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.6.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2177 | 2795 | Yes | Auto Scheduled | Assign Tester ID's | 2h | Fixed Units | 5 | 0.25d | 2176SS | May 29, 2026 4:00 | June 1, 2026 9:00 | 5/29/26 4:00 | 6/1/26 9:00 | 5/28/26 11:00 | 5/28/26 2:00 | 0h | -12h | 0ed | 0 | NA | NA | June 18, 2026 10:00 | June 18, 2026 12:00 | As Soon As Possible | NA | NA | NA | 4/23/26 11:05 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.6.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2178 | 2948 | Yes | Auto Scheduled | Identify Data and Processes for ITC | 1d | Fixed Units | 5 | 0d | 2177SS | May 29, 2026 4:00 | June 1, 2026 4:00 | 5/29/26 4:00 | 6/1/26 4:00 | 5/28/26 11:00 | 5/29/26 11:00 | 0d | -1.5d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/28/26 4:18 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.6.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2179 | 2949 | Yes | Auto Scheduled | Run Costing for Data Identified(or ALL) | 4h | Fixed Units | 5 | 0d | 2178 | June 1, 2026 4:00 | June 2, 2026 11:00 | 6/1/26 4:00 | 6/2/26 11:00 | 5/29/26 11:00 | 5/29/26 4:00 | 0h | -12h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/28/26 4:19 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.6.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2180 | 2794 | Yes | Auto Scheduled | Functional Smoke Testing | 5d | Fixed Units | 5 | 5d | 2179 | June 2, 2026 11:00 | June 9, 2026 11:00 | 6/2/26 11:00 | 6/9/26 11:00 | 5/29/26 4:00 | 6/5/26 4:00 | 0d | -1.5d | 0ed | 0 | NA | NA | June 18, 2026 9:00 | June 25, 2026 9:00 | As Soon As Possible | NA | NA | NA | 4/23/26 11:05 | 40h | 40h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.6.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2181 | 2793 | Yes | Auto Scheduled | Test Kickoff | 1h | Fixed Units | 5 | 0.13d | 2165 | June 8, 2026 8:00 | June 8, 2026 9:00 | 6/8/26 8:00 | 6/8/26 9:00 | 6/8/26 8:00 | 6/8/26 9:00 | 0h | -726h | 0ed | 0 | NA | NA | June 18, 2026 9:00 | June 18, 2026 10:00 | Must Start On | 6/8/26 8:00 | NA | NA | 4/23/26 11:05 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.6.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2182 | 2796 | Yes | Auto Scheduled | Team Testing | 10d | Fixed Units | 5 | 20d | 2181SS | June 8, 2026 8:00 | June 19, 2026 5:00 | 6/8/26 8:00 | 6/19/26 5:00 | 10/27/26 8:00 | 11/9/26 5:00 | 0d | 101d | 0ed | 0 | NA | NA | June 22, 2026 8:00 | July 17, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/23/26 11:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.6.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2183 | 2797 | Yes | Auto Scheduled | Defect Correction / Retesting / Mitigation / Close | 5d | Fixed Units | 5 | 5d | 2182SS+3d | June 11, 2026 8:00 | June 17, 2026 5:00 | 6/11/26 8:00 | 6/17/26 5:00 | 11/3/26 8:00 | 11/9/26 5:00 | 0d | 103d | 0ed | 0 | NA | NA | July 20, 2026 8:00 | July 24, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/23/26 11:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.6.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2184 | 2798 | Yes | Auto Scheduled | Gate Review | 1h | Fixed Units | 5 | 0.13d | 2183SS+4d | June 17, 2026 8:00 | June 17, 2026 9:00 | 6/17/26 8:00 | 6/17/26 9:00 | 11/9/26 4:00 | 11/9/26 5:00 | 831h | 831h | 0ed | 0 | NA | NA | July 23, 2026 8:00 | July 23, 2026 9:00 | As Soon As Possible | NA | NA | NA | 4/23/26 11:05 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.6.9 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2185 | 915 | Yes | Auto Scheduled | ITC-3 | 25.13d | Fixed Duration | 4 | 62d |  | June 19, 2026 4:00 | July 24, 2026 5:00 | 6/19/26 4:00 | 7/24/26 5:00 | 7/2/26 11:00 | 11/9/26 5:00 | 8.5d | 8.5d | 0ed | 0 | NA | NA | April 30, 2026 8:00 | July 24, 2026 5:00 | As Soon As Possible | NA | NA | NA | 3/31/26 8:55 | 45h | 44h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.7 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2186 | 922 | Yes | Auto Scheduled | Assign Resources to Depolyment 1 locations | 2h | Fixed Units | 5 | 0.13d | 1378 | June 19, 2026 4:00 | June 22, 2026 9:00 | 6/19/26 4:00 | 6/22/26 9:00 | 7/2/26 11:00 | 7/2/26 2:00 | 0h | 68h | 0ed | 0 | NA | NA | April 30, 2026 8:00 | April 30, 2026 9:00 | As Soon As Possible | NA | NA | NA | 3/31/26 9:02 | 2h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.7.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2187 | 918 | Yes | Auto Scheduled | Assign Tester ID's | 2h | Fixed Units | 5 | 0.25d | 2186SS | June 19, 2026 4:00 | June 22, 2026 9:00 | 6/19/26 4:00 | 6/22/26 9:00 | 7/2/26 11:00 | 7/2/26 2:00 | 0h | 68h | 0ed | 0 | NA | NA | June 18, 2026 10:00 | June 18, 2026 12:00 | As Soon As Possible | NA | NA | NA | 3/31/26 8:55 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.7.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2188 | 2950 | Yes | Auto Scheduled | Identify Data and Processes for ITC | 1d | Fixed Units | 5 | 0d | 2187SS | June 19, 2026 4:00 | June 22, 2026 4:00 | 6/19/26 4:00 | 6/22/26 4:00 | 7/2/26 11:00 | 7/3/26 11:00 | 0d | 8.5d | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/28/26 4:32 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.7.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2189 | 2951 | Yes | Auto Scheduled | Run Costing for Data Identified | 4h | Fixed Units | 5 | 0d | 2188 | June 22, 2026 4:00 | June 23, 2026 11:00 | 6/22/26 4:00 | 6/23/26 11:00 | 7/3/26 11:00 | 7/3/26 4:00 | 0h | 68h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/28/26 4:32 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.7.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2190 | 917 | Yes | Auto Scheduled | Functional Smoke Testing | 5d | Fixed Units | 5 | 5d | 2189 | June 23, 2026 11:00 | June 30, 2026 11:00 | 6/23/26 11:00 | 6/30/26 11:00 | 7/3/26 4:00 | 7/10/26 4:00 | 0d | 8.5d | 0ed | 0 | NA | NA | June 18, 2026 9:00 | June 25, 2026 9:00 | As Soon As Possible | NA | NA | NA | 3/31/26 8:55 | 40h | 40h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.7.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2191 | 916 | Yes | Auto Scheduled | Test Kickoff | 1h | Fixed Units | 5 | 0.13d | 2166 | July 13, 2026 8:00 | July 13, 2026 9:00 | 7/13/26 8:00 | 7/13/26 9:00 | 7/13/26 8:00 | 7/13/26 9:00 | 0h | 0h | 0ed | 0 | NA | NA | June 18, 2026 9:00 | June 18, 2026 10:00 | Must Start On | 7/13/26 8:00 | NA | NA | 3/31/26 8:55 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.7.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2192 | 919 | Yes | Auto Scheduled | Team Testing | 10d | Fixed Units | 5 | 20d | 2191SS | July 13, 2026 8:00 | July 24, 2026 5:00 | 7/13/26 8:00 | 7/24/26 5:00 | 10/27/26 8:00 | 11/9/26 5:00 | 0d | 76d | 0ed | 0 | NA | NA | June 22, 2026 8:00 | July 17, 2026 5:00 | As Soon As Possible | NA | NA | NA | 3/31/26 8:55 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.7.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2193 | 923 | Yes | Auto Scheduled | Defect Correction / Retesting / Mitigation / Close | 5d | Fixed Units | 5 | 5d | 2192SS+3d | July 16, 2026 8:00 | July 22, 2026 5:00 | 7/16/26 8:00 | 7/22/26 5:00 | 11/3/26 8:00 | 11/9/26 5:00 | 0d | 78d | 0ed | 0 | NA | NA | July 20, 2026 8:00 | July 24, 2026 5:00 | As Soon As Possible | NA | NA | NA | 3/31/26 9:09 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.7.8 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2194 | 921 | Yes | Auto Scheduled | Gate Review | 0h | Fixed Units | 5 | 0.13d | 2193SS+4d | July 21, 2026 5:00 | July 21, 2026 5:00 | 7/21/26 5:00 | 7/21/26 5:00 | 11/9/26 5:00 | 11/9/26 5:00 | 632h | 632h | 0ed | 0 | NA | NA | July 23, 2026 8:00 | July 23, 2026 9:00 | As Soon As Possible | NA | NA | NA | 3/31/26 8:55 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.7.9 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2195 | 22 | Yes | Auto Scheduled | UAT (DR) | 44.38d | Fixed Duration | 4 | 90.13d |  | August 17, 2026 8:00 | October 16, 2026 11:00 | 8/17/26 8:00 | 10/16/26 11:00 | 8/7/26 9:00 | 11/9/26 5:00 | 0d | -5.88d | 0ed | 0 | NA | NA | April 30, 2026 8:00 | September 3, 2026 9:00 | As Soon As Possible | NA | NA | NA | 3/13/25 11:10 | 45h | 44h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.8 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2196 | 924 | Yes | Auto Scheduled | Assign Resources to Depolyment 1 locations | 2h | Fixed Units | 5 | 0.13d | 1759,2140 | October 8, 2026 2:00 | October 8, 2026 4:00 | 10/8/26 2:00 | 10/8/26 4:00 | 8/7/26 9:00 | 8/7/26 11:00 | 0h | -356h | 0ed | 0 | NA | NA | April 30, 2026 8:00 | April 30, 2026 9:00 | As Soon As Possible | NA | NA | NA | 3/31/26 9:16 | 2h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.8.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2197 | 927 | Yes | Auto Scheduled | Assign Tester ID's | 2h | Fixed Units | 5 | 0.25d | 2196 | October 8, 2026 4:00 | October 9, 2026 9:00 | 10/8/26 4:00 | 10/9/26 9:00 | 8/7/26 11:00 | 8/7/26 2:00 | 0h | -356h | 0ed | 0 | NA | NA | August 6, 2026 10:00 | August 6, 2026 12:00 | As Soon As Possible | NA | NA | NA | 3/31/26 9:16 | 2h | 2h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.8.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2198 | 3361 | Yes | Auto Scheduled | Run Costing for Data Identified | 4h | Fixed Units | 5 | 0d | 2197SS | October 8, 2026 4:00 | October 9, 2026 11:00 | 10/8/26 4:00 | 10/9/26 11:00 | 8/7/26 11:00 | 8/7/26 4:00 | 0h | -356h | 0ed | 0 | NA | NA | NA | NA | As Soon As Possible | NA | NA | NA | 4/30/26 7:54 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.8.3 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2199 | 926 | Yes | Auto Scheduled | Functional Smoke Testing | 5d | Fixed Units | 5 | 5d | 2198 | October 9, 2026 11:00 | October 16, 2026 11:00 | 10/9/26 11:00 | 10/16/26 11:00 | 8/7/26 4:00 | 8/14/26 4:00 | 0d | -44.5d | 0ed | 0 | NA | NA | August 3, 2026 8:00 | August 7, 2026 5:00 | As Soon As Possible | NA | NA | NA | 3/31/26 9:16 | 40h | 40h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.8.4 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2200 | 925 | Yes | Auto Scheduled | Test Kickoff | 1h | Fixed Units | 5 | 0.13d | 2167 | August 17, 2026 8:00 | August 17, 2026 9:00 | 8/17/26 8:00 | 8/17/26 9:00 | 8/17/26 8:00 | 8/17/26 9:00 | 0h | -356h | 0ed | 0 | NA | NA | August 6, 2026 9:00 | August 6, 2026 10:00 | Must Start On | 8/17/26 8:00 | NA | NA | 3/31/26 9:16 | 1h | 1h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.8.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2201 | 928 | Yes | Auto Scheduled | Team Testing | 10d | Fixed Units | 5 | 15d | 2200SS | August 17, 2026 8:00 | August 28, 2026 5:00 | 8/17/26 8:00 | 8/28/26 5:00 | 10/27/26 8:00 | 11/9/26 5:00 | 0d | 51d | 0ed | 0 | NA | NA | August 10, 2026 8:00 | August 28, 2026 5:00 | As Soon As Possible | NA | NA | NA | 3/31/26 9:16 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.8.6 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2202 | 3362 | Yes | Auto Scheduled | Defect Correction / Retesting / Mitigation / Close | 0d | Fixed Units | 5 | 5d | 2201SS+3d | August 19, 2026 5:00 | August 19, 2026 5:00 | 8/19/26 5:00 | 8/19/26 5:00 | 11/4/26 8:00 | 11/4/26 8:00 | 0d | 54d | 0ed | 0 | NA | NA | July 20, 2026 8:00 | July 24, 2026 5:00 | As Soon As Possible | NA | NA | NA | 4/30/26 7:56 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.8.7 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2203 | 930 | Yes | Auto Scheduled | Gate Review | 0h | Fixed Units | 5 | 0.13d | 2202SS+4d | August 25, 2026 5:00 | August 25, 2026 5:00 | 8/25/26 5:00 | 8/25/26 5:00 | 11/9/26 5:00 | 11/9/26 5:00 | 432h | 432h | 0ed | 0 | NA | NA | September 3, 2026 8:00 | September 3, 2026 9:00 | As Soon As Possible | NA | NA | NA | 3/31/26 9:16 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3.3.8.8 | 500 | Yes | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2204 | 683 | Yes | Auto Scheduled | Business Readniess | 191d | Fixed Duration | 2 | 175d |  | February 16, 2026 8:00 | November 9, 2026 5:00 | 2/16/26 8:00 | 11/9/26 5:00 | 2/16/26 8:00 | 11/9/26 5:00 | 0d | 0d | 0ed | 0.38 | 2/16/26 8:00 | NA | February 16, 2026 8:00 | October 16, 2026 5:00 | As Soon As Possible | NA | 5/26/26 3:00 | 5/26/26 3:00 | 3/24/26 6:44 | 4,584h | 4,200h | 1,746h | 0 | 0 | 0 | 0 | 0 | 1.4 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2205 | 215 | Yes | Auto Scheduled | Training Readiness | 191d | Fixed Duration | 3 | 175d |  | February 16, 2026 8:00 | November 9, 2026 5:00 | 2/16/26 8:00 | 11/9/26 5:00 | 2/16/26 8:00 | 11/9/26 5:00 | 0d | 0d | 0ed | 0.38 | 2/16/26 8:00 | NA | February 16, 2026 8:00 | October 16, 2026 5:00 | As Soon As Possible | NA | 5/26/26 3:00 | 5/26/26 3:00 | 6/18/25 8:06 | 4,584h | 4,200h | 1,746h | 0 | 0 | 0 | 0 | 0 | 1.4.1 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2206 | 216 | Yes | Auto Scheduled | Content Development | 191d | Fixed Duration | 4 | 126d |  | February 16, 2026 8:00 | November 9, 2026 5:00 | 2/16/26 8:00 | 11/9/26 5:00 | 2/16/26 8:00 | 11/9/26 5:00 | 0d | 0d | 0ed | 0.44 | 2/16/26 8:00 | NA | February 16, 2026 8:00 | August 10, 2026 5:00 | As Soon As Possible | NA | 5/26/26 3:00 | 5/26/26 3:00 | 6/18/25 8:06 | 4,008h | 3,752h | 1,746h | 0 | 0 | 0 | 0 | 0 | 1.4.1.1 | 500 | No | Yes | Yes |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2207 | 232 | Yes | Auto Scheduled | Verify Role Mapping Complete | 66d | Fixed Units | 5 | 121d |  | May 1, 2026 8:00 | July 31, 2026 5:00 | 5/1/26 8:00 | 7/31/26 5:00 | 5/1/26 8:00 | 11/9/26 5:00 | 0d | 71d | 0ed | 0.46000000000000002 | 5/1/26 8:00 | NA | February 16, 2026 8:00 | August 3, 2026 5:00 | Finish No Earlier Than | 7/31/26 5:00 | 6/12/26 10:00 | 6/12/26 10:00 | 6/18/25 8:36 | 528h | 968h | 242h | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.1 | 500 | No | No | No |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2208 | 225 | Yes | Auto Scheduled | Develop Curriculum | 66d | Fixed Units | 5 | 80d | 2207SS | May 1, 2026 8:00 | July 31, 2026 5:00 | 5/1/26 8:00 | 7/31/26 5:00 | 5/1/26 8:00 | 7/31/26 5:00 | 0d | 0d | 0ed | 0.29999999999999999 | 5/1/26 8:00 | NA | February 16, 2026 8:00 | June 5, 2026 5:00 | Finish No Earlier Than | 7/31/26 5:00 | 5/28/26 5:00 | 5/29/26 8:00 | 6/18/25 8:36 | 528h | 640h | 160h | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.2 | 500 | No | No | No |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2209 | 4542 | Yes | Auto Scheduled | Develop Course ppts | 86d | Fixed Units | 5 | 121d | 2208SS | May 1, 2026 8:00 | August 28, 2026 5:00 | 5/1/26 8:00 | 8/28/26 5:00 | 5/1/26 8:00 | 10/30/26 5:00 | 0d | 45d | 0ed | 0.34999999999999998 | 5/1/26 8:00 | NA | February 16, 2026 8:00 | August 3, 2026 5:00 | Finish No Earlier Than | 8/28/26 5:00 | 6/12/26 10:00 | 6/12/26 10:00 | 5/4/26 2:12 | 688h | 968h | 242h | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.3 | 500 | No | No | No |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2210 | 233 | Yes | Auto Scheduled | Develop Work Instructions | 86d | Fixed Units | 5 | 71d | 2209SS | May 1, 2026 8:00 | August 28, 2026 5:00 | 5/1/26 8:00 | 8/28/26 5:00 | 5/1/26 8:00 | 11/9/26 5:00 | 51d | 51d | 0ed | 0.20999999999999999 | 5/1/26 8:00 | NA | April 27, 2026 8:00 | August 3, 2026 5:00 | Finish No Earlier Than | 8/28/26 5:00 | 5/26/26 3:00 | 5/26/26 3:00 | 6/18/25 8:36 | 688h | 568h | 142h | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.4 | 500 | No | No | No |  |  | GreenCircle | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2211 | 217 | Yes | Auto Scheduled | Develop Training Data Sheets (Testing/Training) | 71d | Fixed Units | 5 | 71d | 2208 | August 3, 2026 8:00 | November 9, 2026 5:00 | 8/3/26 8:00 | 11/9/26 5:00 | 8/3/26 8:00 | 11/9/26 5:00 | 0d | 0d | 0ed | 0 | NA | NA | April 27, 2026 8:00 | August 3, 2026 5:00 | Start No Earlier Than | 4/30/26 5:00 | NA | NA | 6/18/25 8:06 | 568h | 568h | 0h | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.5 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2212 | 218 | Yes | Auto Scheduled | Develop Train the Trainer | 120d | Fixed Units | 5 | 120d | 2207SS | February 16, 2026 8:00 | July 31, 2026 5:00 | 2/16/26 8:00 | 7/31/26 5:00 | 2/16/26 8:00 | 7/31/26 5:00 | 0d | 0d | 0ed | 1 | 2/16/26 8:00 | 7/31/26 5:00 | February 16, 2026 8:00 | July 31, 2026 5:00 | Finish No Earlier Than | 7/31/26 5:00 | 7/31/26 5:00 | 7/31/26 5:00 | 6/18/25 8:06 | 960h | 960h | 960h | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.6 | 500 | No | No | No |  |  | GreenSquare | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2213 | 220 | Yes | Auto Scheduled | Publish Training Materials to SP/LMS | 6d | Fixed Units | 5 | 6d | 2209 | August 31, 2026 8:00 | September 7, 2026 5:00 | 8/31/26 8:00 | 9/7/26 5:00 | 11/2/26 8:00 | 11/9/26 5:00 | 45d | 45d | 0ed | 0 | NA | NA | August 3, 2026 8:00 | August 10, 2026 5:00 | Finish No Earlier Than | 8/28/26 5:00 | NA | NA | 6/18/25 8:06 | 48h | 48h | 0h | 0 | 0 | 0 | 0 | 0 | 1.4.1.1.7 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2214 | 221 | Yes | Auto Scheduled | Talent LMS Application Setup | 1d | Fixed Units | 4 | 1d | 2209 | August 31, 2026 8:00 | August 31, 2026 5:00 | 8/31/26 8:00 | 8/31/26 5:00 | 11/9/26 8:00 | 11/9/26 5:00 | 50d | 50d | 0ed | 0 | NA | NA | August 10, 2026 8:00 | August 10, 2026 5:00 | Finish No Earlier Than | 8/28/26 5:00 | NA | NA | 6/18/25 8:06 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.4.1.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2215 | 241 | Yes | Auto Scheduled | Train the Trainer | 20d | Fixed Duration | 4 | 20d |  | August 3, 2026 8:00 | August 28, 2026 5:00 | 8/3/26 8:00 | 8/28/26 5:00 | 8/25/26 8:00 | 9/21/26 5:00 | 16d | 16d | 0ed | 0 | NA | NA | August 3, 2026 8:00 | August 28, 2026 5:00 | As Soon As Possible | NA | NA | NA | 6/18/25 9:20 | 160h | 160h | 0h | 0 | 0 | 0 | 0 | 0 | 1.4.1.3 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2216 | 247 | Yes | Auto Scheduled | Deliver Train the Trainer (BPL->SME) | 20d | Fixed Units | 5 | 20d | 2212 | August 3, 2026 8:00 | August 28, 2026 5:00 | 8/3/26 8:00 | 8/28/26 5:00 | 8/25/26 8:00 | 9/21/26 5:00 | 0d | 16d | 0ed | 0 | NA | NA | August 3, 2026 8:00 | August 28, 2026 5:00 | Finish No Earlier Than | 8/28/26 5:00 | NA | NA | 6/18/25 9:32 | 160h | 160h | 0h | 0 | 0 | 0 | 0 | 0 | 1.4.1.3.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2217 | 242 | Yes | Auto Scheduled | End User Training Exeuction | 71d | Fixed Duration | 4 | 71d |  | July 10, 2026 8:00 | October 16, 2026 5:00 | 7/10/26 8:00 | 10/16/26 5:00 | 9/22/26 8:00 | 11/9/26 5:00 | 16d | 16d | 0ed | 0 | NA | NA | July 10, 2026 8:00 | October 16, 2026 5:00 | As Soon As Possible | NA | NA | NA | 6/18/25 9:20 | 416h | 288h | 0h | 0 | 0 | 0 | 0 | 0 | 1.4.1.4 | 500 | No | Yes | Yes |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2218 | 913 | Yes | Auto Scheduled | User Training Plan and Schedule | 136h | Fixed Units | 5 | 1d |  | July 10, 2026 8:00 | August 3, 2026 5:00 | 7/10/26 8:00 | 8/3/26 5:00 | 10/16/26 8:00 | 11/9/26 5:00 | 560h | 560h | 0ed | 0 | NA | NA | July 10, 2026 8:00 | July 10, 2026 5:00 | Finish No Earlier Than | 8/3/26 5:00 | NA | NA | 3/31/26 8:45 | 136h | 8h | 0h | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.1 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2219 | 246 | Yes | Auto Scheduled | Deliver End User Training | 35d | Fixed Units | 5 | 35d | 2216 | August 31, 2026 8:00 | October 16, 2026 5:00 | 8/31/26 8:00 | 10/16/26 5:00 | 9/22/26 8:00 | 11/9/26 5:00 | 16d | 16d | 0ed | 0 | NA | NA | August 31, 2026 8:00 | October 16, 2026 5:00 | Start No Earlier Than | 3/9/26 8:00 | NA | NA | 6/18/25 9:26 | 280h | 280h | 0h | 0 | 0 | 0 | 0 | 0 | 1.4.1.4.2 | 500 | No | No | No |  |  | Black | [7 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0

## Sheet1
CPM CONSISTENCY CHECK — C-Suite Mandated Dates vs Current Plan (sourced from MSP)
Auto-refreshes from Constraints + MSP. Re-paste MSP and everything below recalculates. 🔴 LATE = plan finishes after mandate ¦ 🟡 AT RISK = within 5d ¦ 🟢 ON TIME = on/before mandate
Today: | 2026-05-06 |  | Project Finish (MSP): |  | 2025-02-17 |  | Days to Project Finish: |  | -443
📋 PARSED MANDATES — extracted from Constraints sheet
Phase | System | Refresh Start | Refresh End | Data Load Earliest Start | Testing Start | Testing End | Refresh Status | Data Load Status | Testing Status | Refresh Var (d) | Data Load Var (d) | Testing Var (d) | Why / Action
MC1/ITC1 | QS5 |  |  |  | 2026-04-27 | 2026-05-15 | N/A | N/A | 🟡 IN WINDOW |  |  | -9 | 🟡 Testing window active NOW.
MC2/ITC2 | QS4 | 2026-04-22 | 2026-05-18 |  | 2026-06-08 | 2026-06-19 | 🟡 IN WINDOW | N/A | ⏳ FUTURE | -14 |  | 33
MC2/ITC3 | QS5 |  | 2026-06-05 |  | 2026-07-13 | 2026-07-24 | N/A | N/A | ⏳ FUTURE |  |  | 68
MC3/UAT | QS4 (Post Refresh) |  | 2026-06-22 | 2026-06-22 | 2026-08-17 | 2026-08-28 | N/A | ⏳ FUTURE | ⏳ FUTURE |  | 47 | 103
🔍 TASK SCAN — MSP tasks matched to each phase mandate (live formulas against MSP)
Matching: REFRESH = name contains phase + "Refresh" ¦ DATA LOAD = phase + ("Data Load"/"Mock Data"/"Master Data") ¦ TESTING = phase summary section. Excludes summary roll-ups.
Phase | Category | Task UID | Task Name | Owner | MSP Start | MSP Finish | % Done | Total Slack | Mandated Start | Mandated End | Variance (d) | Status | Why / Action
MC1/ITC1 | REFRESH | NA | QS5 ITC-1 Refresh | 0 |  | 2025-03-13 | 100% | 0 |  |  |  | — | Mandate not set
MC1/ITC1 | DATA LOAD | NA | ITC1 Data Load Tasks QS5 | 629 |  | 2026-04-06 | 100% | 2809 |  |  |  | — | Mandate not set
MC1/ITC1 | DATA LOAD | NA | ITC1 Mock Data Loads Complete | 2164 |  | 2026-04-23 | 100% | 932 |  |  |  | — | Mandate not set
MC1/ITC1 | TESTING | Mon 4/27/26 | ITC-1 Team Testing | 2173SS+4d |  | 2026-04-27 | 25% | 688SS+4d | 2026-04-27 | 2026-05-15 | -18 | 🟢 ON TIME | ✅ Plan has 18d buffer before mandate.
MC1/ITC1 | TESTING | NA | ITC-1 Defect Correction / Retesting / Mitigation / Close | 2174FS-3d |  | 2026-05-06 | 25% | 689FS-3d | 2026-04-27 | 2026-05-15 | -9 | 🟢 ON TIME | ✅ Plan has 9d buffer before mandate.
MC1/ITC1 | TESTING | NA | ITC-1 Gate Review | 0 |  | 2026-05-15 | 0% | 0 | 2026-04-27 | 2026-05-15 | 0 | 🟡 AT RISK | 🟡 Buffer = 0d. Watch slippage; small delays will breach mandate.
MC2/ITC2 | REFRESH | Mon 4/27/26 | QS4 ITC-2 Refresh | 629630 |  | 2026-04-27 | 62% | 28091685 | 2026-04-22 | 2026-05-18 | -21 | 🟢 ON TIME | ✅ Plan has 21d buffer before mandate.
MC2/ITC2 | DATA LOAD | NA | ITC2 Data Load Tasks QS4 | 0 |  | 2026-05-18 | 0% | 0 |  |  |  | — | Mandate not set
MC2/ITC2 | DATA LOAD | NA | ITC2 Master Data Loads Complete | 1000SS,2176,1380SS,999,1761SS,2142SS |  | 2026-05-29 | 0% | 2945SS,2792,3330SS,2801,3351SS,4532SS |  |  |  | — | Mandate not set
MC2/ITC2 | DATA LOAD | NA | ITC2 Mock Data Loads Complete | 2165 |  | 2026-10-12 | 0% | 2799 |  |  |  | — | Mandate not set
MC2/ITC3 | REFRESH | NA | QS5 ITC-3 Refresh | 1010 |  | 2026-05-18 | 0% | 2054 |  | 2026-06-05 | -18 | 🟢 ON TIME | ✅ Plan has 18d buffer before mandate.
MC2/ITC3 | DATA LOAD | NA | ITC3 Data Load Tasks QS5 | 1389 |  | 2026-06-08 | 0% | 2422 |  |  |  | — | Mandate not set
MC2/ITC3 | DATA LOAD | NA | ITC3 Master Data Loads Complete | 21861379 |  | 2026-06-19 | 0% | 9223326 |  |  |  | — | Mandate not set
MC2/ITC3 | DATA LOAD | NA | ITC3 Mock Data Loads Complete | 2166 |  | 2026-06-23 | 0% | 931 |  |  |  | — | Mandate not set
MC3/UAT | REFRESH | NA | QS4 UAT Refresh | 13891390 |  | 2026-06-08 | 0% | 24222423 |  | 2026-06-22 | -14 | 🟢 ON TIME | ✅ Plan has 14d buffer before mandate.
MC3/UAT | DATA LOAD | NA | UAT Data Load Tasks QS4 | 0 |  | 2026-06-22 | 0% | 0 | 2026-06-22 | 2026-06-22 | 0 | 🟡 AT RISK | 🟡 Buffer = 0d. Watch slippage; small delays will breach mandate.
MC3/UAT | DATA LOAD | NA | UAT Mock Data Loads Complete | 0 |  | 2026-09-24 | 0% | 0 | 2026-06-22 | 2026-06-22 | 94 | 🔴 LATE | ⚠️ Plan finishes 94d AFTER mandate. Compress upstream or escalate to owner.
MC3/UAT | DATA LOAD | NA | UAT Master Data Loads Complete | 1000SS,999,1761SS,1760,2196 |  | 2026-10-08 | 0% | 2945SS,2801,3351SS,3350,924 | 2026-06-22 | 2026-06-22 | 108 | 🔴 LATE | ⚠️ Plan finishes 108d AFTER mandate. Compress upstream or escalate to owner.
MC3/UAT | DATA LOAD | NA | UAT Mock Data Loads Complete | 2167 |  | 2026-10-12 | 0% | 690 | 2026-06-22 | 2026-06-22 | 112 | 🔴 LATE | ⚠️ Plan finishes 112d AFTER mandate. Compress upstream or escalate to owner.
MC3/UAT | DATA LOAD | NA | UAT Mock Data Loads Complete | 0 |  | 2026-09-24 | 0% | 0 | 2026-06-22 | 2026-06-22 | 94 | 🔴 LATE | ⚠️ Plan finishes 94d AFTER mandate. Compress upstream or escalate to owner.
MC3/UAT | TESTING | Thu 4/30/26 | UAT (User Acceptance Testing) - ITC-3 - with roles | 208 |  | 2026-06-11 | 0% | 291 | 2026-08-17 | 2026-08-28 | -78 | 🟢 ON TIME | ✅ Plan has 78d buffer before mandate.
MC3/UAT | TESTING | NA | Test Readiness Review (TRR) - UAT | 2200 |  | 2026-10-16 | 0% | 925 | 2026-08-17 | 2026-08-28 | 49 | 🔴 LATE | ⚠️ Plan finishes 49d AFTER mandate. Compress upstream or escalate to owner.
Formulas:
Testing Start = IFERROR(DATEVALUE(TRIM(LEFT(SUBSTITUTE([1]Constraints!F2,"–","-"),FIND("-",SUBSTITUTE([1]Constraints!F2,"–","-"))-1))),"")
Testing End = IFERROR(DATEVALUE(TRIM(MID(SUBSTITUTE([1]Constraints!F2,"–","-"),FIND("-",SUBSTITUTE([1]Constraints!F2,"–","-"))+1,50))),"")
Testing End = IFERROR(IF(OR([1]MSP!G13="",[1]MSP!G13="NA"),"",DATEVALUE(MID([1]MSP!G13,5,99))),"")
Refresh Status = IF([Refresh Start]="","N/A",IF(TODAY()<[Refresh Start],"⏳ FUTURE",IF(TODAY()<=[Refresh End],"🟡 IN WINDOW","⏰ PAST")))
Data Load Status = IF([Data Load Earliest Start]="","N/A",IF(TODAY()<[Data Load Earliest Start],"⏳ FUTURE",IF(TODAY()=[Data Load Earliest Start],"🟡 TODAY","⏰ PAST")))
Testing Status = IF([Testing Start]="","N/A",IF(TODAY()<[Testing Start],"⏳ FUTURE",IF(TODAY()<=[Testing End],"🟡 IN WINDOW","⏰ PAST")))
Testing Status = '[1]CPM Consistency Check'!F7
Refresh Var (d) = IF([Refresh Start]="","",[Refresh Start]-TODAY())
Refresh Var (d) = '[1]CPM Consistency Check'!G7
Data Load Var (d) = IF([Data Load Earliest Start]="","",[Data Load Earliest Start]-TODAY())
Refresh Start = IFERROR(IF(OR(TRIM([1]Constraints!D3)="N/A",TRIM([1]Constraints!D3)=""),"",DATEVALUE(TRIM(LEFT([1]Constraints!D3,FIND("-",[1]Constraints!D3&"-")-1)))),"")
Data Load Earliest Start = IFERROR(IF(ISNUMBER(FIND("-",[1]Constraints!E5)),DATEVALUE(TRIM(MID([1]Constraints!E5,FIND("-",[1]Constraints!E5)+1,50))),DATEVALUE(TRIM([1]Constraints!E5))),"")