## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | AMETEK Release-1, 3-Deployment Plan | 451d? | February 17, 2025 8:00 | November 9, 2026 5:00 |  | 1
2 | Yes | Auto Scheduled | System Readiness | 439d? | February 17, 2025 8:00 | October 22, 2026 5:00 |  | 2
3 | Yes | Auto Scheduled | Environment Schedule | 404d? | March 13, 2025 8:00 | September 29, 2026 5:00 |  | 3
4 | Yes | Auto Scheduled | DS4-100 Config / Development Client | 0.75d | May 7, 2025 10:00 | May 7, 2025 5:00 |  | 4
5 | Yes | Auto Scheduled | Copy DS4-100 to DS4-110 Dev | 6h | May 7, 2025 10:00 | May 7, 2025 5:00 |  | 5
6 | Yes | Auto Scheduled | DS4-110 Unit Test Client | 0.5d | May 8, 2025 8:00 | May 8, 2025 12:00 |  | 4
7 | Yes | Auto Scheduled | List of functional users | 2h | May 8, 2025 8:00 | May 8, 2025 10:00 | 5 | 5
8 | Yes | Auto Scheduled | Security Role for Functional Team | 2h | May 8, 2025 10:00 | May 8, 2025 12:00 | 7 | 5
9 | Yes | Auto Scheduled | DS4-120 Data Dev Client | 0.5d | May 8, 2025 8:00 | May 8, 2025 12:00 |  | 4
10 | Yes | Auto Scheduled | List of functional users | 2h | May 8, 2025 8:00 | May 8, 2025 10:00 | 5 | 5
11 | Yes | Auto Scheduled | Security Role for Data Team | 2h | May 8, 2025 10:00 | May 8, 2025 12:00 | 10 | 5
12 | Yes | Auto Scheduled | QS5 ITC-1 Refresh | 277.5d? | March 13, 2025 8:00 | April 6, 2026 12:00 |  | 4
13 | Yes | Auto Scheduled | Change Request to NS2 | 1h | March 13, 2025 8:00 | March 13, 2025 9:00 |  | 5 | Required before the NS2 Tuesday CCB
14 | Yes | Auto Scheduled | Dev Environment Release from SAP | 0d | January 8, 2026 8:00 | January 8, 2026 8:00 |  | 5
15 | Yes | Auto Scheduled | Release Setup ID's and Access | 1h | January 8, 2026 8:00 | January 8, 2026 9:00 | 14 | 5
16 | Yes | Auto Scheduled | Client Config / Validation | 1d | February 2, 2026 8:00 | February 2, 2026 5:00 | 15 | 5
17 | Yes | Auto Scheduled | Technical Transports / BP Setup | 1d | February 4, 2026 8:00 | February 4, 2026 5:00 |  | 5
18 | Yes | Auto Scheduled | Best Practice / Country Validation | 1d? | February 3, 2026 8:00 | February 3, 2026 5:00 | 16 | 5
19 | Yes | Auto Scheduled | Connect Systems and Validate | 1d | February 5, 2026 8:00 | February 5, 2026 5:00 | 17 | 5
20 | Yes | Auto Scheduled | Validate Syniti Connections to QS5 | 1d | February 5, 2026 8:00 | February 5, 2026 5:00 | 17 | 5
21 | Yes | Auto Scheduled | Security Transports | 4h | February 5, 2026 8:00 | February 5, 2026 12:00 | 17 | 5
22 | Yes | Auto Scheduled | Security Manual Tasks | 1d | February 5, 2026 1:00 | February 6, 2026 12:00 | 21 | 5
23 | Yes | Auto Scheduled | Manual Technical Tasks | 1d | February 5, 2026 1:00 | February 6, 2026 12:00 | 21 | 5
24 | Yes | Auto Scheduled | Validate Fiori | 4h | February 6, 2026 1:00 | February 6, 2026 5:00 | 23 | 5
25 | Yes | Auto Scheduled | Fiori App Activation | 6h | February 9, 2026 8:00 | February 9, 2026 3:00 | 24 | 5
26 | Yes | Auto Scheduled | Download Transport List | 1h | February 9, 2026 8:00 | February 9, 2026 9:00 | 24 | 5
27 | Yes | Auto Scheduled | Business Functions Validation | 1d | February 9, 2026 8:00 | February 9, 2026 5:00 | 24 | 5
28 | Yes | Auto Scheduled | Functional Leads Validation of Transport List | 1h | February 9, 2026 9:00 | February 9, 2026 10:00 | 26 | 5
29 | Yes | Auto Scheduled | Release Security roles to Functional Team | 1h | February 9, 2026 10:00 | February 9, 2026 11:00 | 28 | 5
30 | Yes | Auto Scheduled | Release Transports to Client | 32.75d | February 9, 2026 10:00 | March 25, 2026 5:00 |  | 5
31 | Yes | Auto Scheduled | Import Group 1 - Ent Structure | 2h | February 9, 2026 10:00 | February 9, 2026 12:00 | 28 | 6
32 | Yes | Auto Scheduled | Manual activities group 1 | 20h | March 19, 2026 8:00 | March 23, 2026 12:00 | 31 | 6
33 | Yes | Auto Scheduled | Import Group 2 - Core Transports | 2h | March 23, 2026 1:00 | March 23, 2026 3:00 | 32 | 6
34 | Yes | Auto Scheduled | Manual activities group 2 | 1d | March 23, 2026 3:00 | March 24, 2026 3:00 | 33 | 6
35 | Yes | Auto Scheduled | Import Group 3 - prior to transactions | 2h | March 24, 2026 3:00 | March 24, 2026 5:00 | 34 | 6
36 | Yes | Auto Scheduled | Manual Activities Group 3 | 1d | March 25, 2026 8:00 | March 25, 2026 5:00 | 35 | 6
37 | Yes | Auto Scheduled | Import Group 4 - workbench / dev work | 2h | April 3, 2026 8:00 | April 3, 2026 10:00 |  | 5
38 | Yes | Auto Scheduled | Import Group 5 - Config to support dev workbench | 2h | April 3, 2026 10:00 | April 3, 2026 12:00 | 37 | 5
39 | Yes | Auto Scheduled | Create Migration Data Project in DMC | 1d | April 3, 2026 1:00 | April 6, 2026 12:00 | 38 | 5
40 | Yes | Auto Scheduled | Environment Ready for Build | 0d | April 6, 2026 12:00 | April 6, 2026 12:00 | 39 | 5
41 | Yes | Auto Scheduled | QS4 ITC-2 Refresh | 13.13d | April 27, 2026 8:00 | May 14, 2026 9:00 |  | 4
42 | Yes | Auto Scheduled | System Setup | 6d | April 27, 2026 8:00 | May 4, 2026 5:00 | 40 | 5
43 | Yes | Auto Scheduled | Dev Refresh Basis(Workinig with NS2) | 2d | April 27, 2026 8:00 | April 28, 2026 5:00 |  | 6 | Required before the NS2 Tuesday CCB
44 | Yes | Auto Scheduled | Client Config / Validation | 1d | April 27, 2026 8:00 | April 27, 2026 5:00 | 40 | 6
45 | Yes | Auto Scheduled | Technical Transports / BP Setup | 1d | April 28, 2026 8:00 | April 28, 2026 5:00 | 44 | 6
46 | Yes | Auto Scheduled | Best Practice / Country Validation | 1d | April 29, 2026 8:00 | April 29, 2026 5:00 | 45 | 6
47 | Yes | Auto Scheduled | Connect Systems and Validate | 1d | April 30, 2026 8:00 | April 30, 2026 5:00 | 46 | 6
48 | Yes | Auto Scheduled | Validate Syniti Connections to QS5 | 1d | May 1, 2026 8:00 | May 1, 2026 5:00 | 47 | 6
49 | Yes | Auto Scheduled | Security Transports | 4h | May 4, 2026 8:00 | May 4, 2026 12:00 | 48 | 6
50 | Yes | Auto Scheduled | Security Manual Tasks | 1d | May 4, 2026 8:00 | May 4, 2026 5:00 | 49SS | 6
51 | Yes | Auto Scheduled | Manual Technical Tasks | 1d | May 4, 2026 8:00 | May 4, 2026 5:00 | 50SS | 6
52 | Yes | Auto Scheduled | Validate Fiori | 8h | May 4, 2026 8:00 | May 4, 2026 5:00 | 50SS | 6
53 | Yes | Auto Scheduled | Fiori App Activation | 8h | May 4, 2026 8:00 | May 4, 2026 5:00 | 52SS | 6
54 | Yes | Auto Scheduled | Download Transport List | 1h | May 4, 2026 8:00 | May 4, 2026 9:00 | 53SS | 6
55 | Yes | Auto Scheduled | Business Functions Validation | 8h | May 4, 2026 8:00 | May 4, 2026 5:00 | 52SS | 6
56 | Yes | Auto Scheduled | Functional Leads Validation of Transport List | 1h | May 4, 2026 8:00 | May 4, 2026 9:00 | 53SS | 6
57 | Yes | Auto Scheduled | Release Security roles to Functional Team | 1h | May 4, 2026 9:00 | May 4, 2026 10:00 | 56 | 6
58 | Yes | Auto Scheduled | Release Transports to Client | 6.56d | May 5, 2026 8:00 | May 13, 2026 1:30 | 42 | 5
59 | Yes | Auto Scheduled | Import Group 1 - Ent Structure | 2h | May 5, 2026 8:00 | May 5, 2026 10:00 | 56 | 6
60 | Yes | Auto Scheduled | Manual activities group 1 | 20h | May 5, 2026 10:00 | May 7, 2026 3:00 | 59 | 6
61 | Yes | Auto Scheduled | Import Group 2 - Core Transports | 2h | May 7, 2026 3:00 | May 7, 2026 5:00 | 60 | 6
62 | Yes | Auto Scheduled | Manual activities group 2 | 1d | May 8, 2026 8:00 | May 8, 2026 5:00 | 61 | 6
63 | Yes | Auto Scheduled | Import Group 3 - prior to transactions | 2h | May 11, 2026 8:00 | May 11, 2026 10:00 | 62 | 6
64 | Yes | Auto Scheduled | Manual Activities Group 3 | 1d | May 11, 2026 10:00 | May 12, 2026 10:00 | 63 | 6
65 | Yes | Auto Scheduled | Import Group 4 - workbench / dev work | 2h | May 12, 2026 10:00 | May 12, 2026 12:00 | 64 | 6
66 | Yes | Auto Scheduled | Import Group 5 - Config to support dev workbench | 8.5h | May 12, 2026 1:00 | May 13, 2026 1:30 | 65 | 6
67 | Yes | Auto Scheduled | Data Project Create | 0.56d | May 13, 2026 1:30 | May 14, 2026 9:00 | 66SS | 5
68 | Yes | Auto Scheduled | Open Client | 15m | May 13, 2026 1:30 | May 13, 2026 1:45 | 66 | 6
69 | Yes | Auto Scheduled | Create Migration Data Project in DMC | 4h | May 13, 2026 1:45 | May 14, 2026 8:45 | 68 | 6
70 | Yes | Auto Scheduled | Close Client | 15m | May 14, 2026 8:45 | May 14, 2026 9:00 | 69 | 6
71 | Yes | Auto Scheduled | Environment Ready for Test | 0m | May 14, 2026 9:00 | May 14, 2026 9:00 | 70 | 5
72 | Yes | Auto Scheduled | QS5 ITC-3 Refresh | 9.44d | May 18, 2026 8:00 | May 29, 2026 11:30 |  | 4
73 | Yes | Auto Scheduled | System Setup | 8d | May 18, 2026 8:00 | May 27, 2026 5:00 | 58 | 5
74 | Yes | Auto Scheduled | System Refresh Basis(Workinig with NS2) | 3d | May 18, 2026 8:00 | May 20, 2026 5:00 |  | 6 | Required before the NS2 Tuesday CCB
75 | Yes | Auto Scheduled | Client Config / Validation | 1d | May 21, 2026 8:00 | May 21, 2026 5:00 | 74 | 6
76 | Yes | Auto Scheduled | Technical Transports / BP Setup | 1d | May 22, 2026 8:00 | May 22, 2026 5:00 | 75 | 6
77 | Yes | Auto Scheduled | Best Practice / Country Validation | 1d | May 25, 2026 8:00 | May 25, 2026 5:00 | 76 | 6
78 | Yes | Auto Scheduled | Connect Systems and Validate | 1d | May 26, 2026 8:00 | May 26, 2026 5:00 | 77 | 6
79 | Yes | Auto Scheduled | Validate Syniti Connections to QS5 | 1d | May 27, 2026 8:00 | May 27, 2026 5:00 | 78 | 6
80 | Yes | Auto Scheduled | Security Transports | 4h | May 21, 2026 8:00 | May 21, 2026 12:00 | 75SS | 6
81 | Yes | Auto Scheduled | Security Manual Tasks | 1d | May 21, 2026 1:00 | May 22, 2026 12:00 | 80 | 6
82 | Yes | Auto Scheduled | Manual Technical Tasks | 1d | May 21, 2026 8:00 | May 21, 2026 5:00 | 80SS | 6
83 | Yes | Auto Scheduled | Validate Fiori | 4h | May 21, 2026 8:00 | May 21, 2026 12:00 | 82SS | 6
84 | Yes | Auto Scheduled | Fiori App Activation | 6h | May 21, 2026 8:00 | May 21, 2026 3:00 | 82SS | 6
85 | Yes | Auto Scheduled | Download Transport List | 1h | May 21, 2026 8:00 | May 21, 2026 9:00 | 84SS | 6
86 | Yes | Auto Scheduled | Business Functions Validation | 8h | May 21, 2026 8:00 | May 21, 2026 5:00 | 85SS | 6
87 | Yes | Auto Scheduled | Functional Leads Validation of Transport | 1h | May 21, 2026 8:00 | May 21, 2026 9:00 | 85SS | 6
88 | Yes | Auto Scheduled | Release Security roles to Functional Team | 1h | May 21, 2026 8:00 | May 21, 2026 9:00 | 87SS | 6
89 | Yes | Auto Scheduled | Release Transports to Client | 6.31d | May 21, 2026 9:00 | May 29, 2026 11:30 | 87 | 5
90 | Yes | Auto Scheduled | Import Group 1 - Ent Structure | 2h | May 21, 2026 9:00 | May 21, 2026 11:00 | 87 | 6
91 | Yes | Auto Scheduled | Manual activities group 1 | 20h | May 21, 2026 11:00 | May 25, 2026 4:00 | 90 | 6
92 | Yes | Auto Scheduled | Import Group 2 - Core Transports | 2h | May 25, 2026 4:00 | May 26, 2026 9:00 | 91 | 6
93 | Yes | Auto Scheduled | Manual activities group 2 | 1d | May 26, 2026 9:00 | May 27, 2026 9:00 | 92 | 6
94 | Yes | Auto Scheduled | Import Group 3 - prior to transactions | 2h | May 27, 2026 9:00 | May 27, 2026 11:00 | 93 | 6
95 | Yes | Auto Scheduled | Manual Activities Group 3 | 1d | May 27, 2026 11:00 | May 28, 2026 11:00 | 94 | 6
96 | Yes | Auto Scheduled | Import Group 4 - workbench / dev work | 2h | May 28, 2026 11:00 | May 28, 2026 2:00 | 95 | 6
97 | Yes | Auto Scheduled | Import Group 5 - Config to support dev workbench | 8.5h | May 28, 2026 11:00 | May 29, 2026 11:30 | 96SS | 6
98 | Yes | Auto Scheduled | Data Project Create | 0.56d | May 28, 2026 11:00 | May 28, 2026 4:30 | 95 | 5
99 | Yes | Auto Scheduled | Open Client | 15m | May 28, 2026 11:00 | May 28, 2026 11:15 | 95 | 6
100 | Yes | Auto Scheduled | Create Migration Data Project in DMC | 4h | May 28, 2026 11:15 | May 28, 2026 4:15 | 99 | 6
101 | Yes | Auto Scheduled | Close Client | 15m | May 28, 2026 4:15 | May 28, 2026 4:30 | 100 | 6
102 | Yes | Auto Scheduled | Environment Ready for Test | 0m | May 28, 2026 4:30 | May 28, 2026 4:30 | 101 | 5
103 | Yes | Auto Scheduled | QS4 UAT Refresh | 13d | June 8, 2026 8:00 | June 24, 2026 5:00 |  | 4
104 | Yes | Auto Scheduled | System Setup | 8d | June 8, 2026 8:00 | June 17, 2026 5:00 | 102 | 5
105 | Yes | Auto Scheduled | System Refresh Basis(Workinig with NS2) | 2d | June 8, 2026 8:00 | June 9, 2026 5:00 |  | 6 | Required before the NS2 Tuesday CCB
106 | Yes | Auto Scheduled | Client Config / Validation | 2d | June 10, 2026 8:00 | June 11, 2026 5:00 | 105 | 6
107 | Yes | Auto Scheduled | Technical Transports / BP Setup | 1d | June 12, 2026 8:00 | June 12, 2026 5:00 | 106 | 6
108 | Yes | Auto Scheduled | Best Practice / Country Validation | 1d | June 12, 2026 8:00 | June 12, 2026 5:00 | 106 | 6
109 | Yes | Auto Scheduled | Connect Systems and Validate | 2d | June 15, 2026 8:00 | June 16, 2026 5:00 | 108 | 6
110 | Yes | Auto Scheduled | Validate Syniti Connections to QS5 | 1d | June 17, 2026 8:00 | June 17, 2026 5:00 | 109 | 6
111 | Yes | Auto Scheduled | Security Transports | 1d | June 15, 2026 8:00 | June 15, 2026 5:00 | 108,107 | 6
112 | Yes | Auto Scheduled | Security Manual Tasks | 1d | June 16, 2026 8:00 | June 16, 2026 5:00 | 111 | 6
113 | Yes | Auto Scheduled | Manual Technical Tasks | 1d | June 15, 2026 8:00 | June 15, 2026 5:00 | 111SS | 6
114 | Yes | Auto Scheduled | Validate Fiori | 1d | June 16, 2026 8:00 | June 16, 2026 5:00 | 113 | 6
115 | Yes | Auto Scheduled | Fiori App Activation | 1d | June 16, 2026 8:00 | June 16, 2026 5:00 | 114SS | 6
116 | Yes | Auto Scheduled | Download Transport List | 1h | June 16, 2026 8:00 | June 16, 2026 9:00 | 114SS | 6
117 | Yes | Auto Scheduled | Business Functions Validation | 1d | June 16, 2026 8:00 | June 16, 2026 5:00 | 114SS | 6
118 | Yes | Auto Scheduled | Functional Leads Validation of Transport List | 1d | June 16, 2026 8:00 | June 16, 2026 5:00 | 117SS | 6
119 | Yes | Auto Scheduled | Release Security roles to Functional Team | 1h | June 17, 2026 8:00 | June 17, 2026 9:00 | 118 | 6
120 | Yes | Auto Scheduled | Release Transports to Client | 5.5d | June 17, 2026 8:00 | June 24, 2026 12:00 | 117SS | 5
121 | Yes | Auto Scheduled | Import Group 1 - Ent Structure | 2h | June 17, 2026 8:00 | June 17, 2026 10:00 | 119SS | 6
122 | Yes | Auto Scheduled | Manual activities group 1 | 20h | June 17, 2026 10:00 | June 19, 2026 3:00 | 121 | 6
123 | Yes | Auto Scheduled | Import Group 2 - Core Transports | 2h | June 19, 2026 3:00 | June 19, 2026 5:00 | 122 | 6
124 | Yes | Auto Scheduled | Manual activities group 2 | 1d | June 22, 2026 8:00 | June 22, 2026 5:00 | 123 | 6
125 | Yes | Auto Scheduled | Import Group 3 - prior to transactions | 2h | June 23, 2026 8:00 | June 23, 2026 10:00 | 124 | 6
126 | Yes | Auto Scheduled | Manual Activities Group 3 | 1d | June 23, 2026 10:00 | June 24, 2026 10:00 | 125 | 6
127 | Yes | Auto Scheduled | Import Group 4 - workbench / dev work | 2h | June 24, 2026 10:00 | June 24, 2026 12:00 | 126 | 6
128 | Yes | Auto Scheduled | Import Group 5 - Config to support dev workbench | 2h | June 24, 2026 10:00 | June 24, 2026 12:00 | 127SS | 6
129 | Yes | Auto Scheduled | Data Project Create | 0.5d | June 24, 2026 1:00 | June 24, 2026 5:00 |  | 5
130 | Yes | Auto Scheduled | Open Client | 15m | June 24, 2026 1:00 | June 24, 2026 1:15 | 128 | 6
131 | Yes | Auto Scheduled | Create Migration Data Project in DMC | 4h | June 24, 2026 1:00 | June 24, 2026 5:00 | 130SS | 6
132 | Yes | Auto Scheduled | Close Client | 15m | June 24, 2026 1:15 | June 24, 2026 1:30 | 130 | 6
133 | Yes | Auto Scheduled | Environment Ready for Build | 0m | June 24, 2026 1:30 | June 24, 2026 1:30 | 132 | 5
134 | Yes | Auto Scheduled | P? Production System | 13.06d | September 7, 2026 8:00 | September 24, 2026 8:30 |  | 4
135 | Yes | Auto Scheduled | System Setup | 8d | September 7, 2026 8:00 | September 16, 2026 5:00 | 120 | 5
136 | Yes | Auto Scheduled | System Refresh Basis(Workinig with NS2) | 2d | September 7, 2026 8:00 | September 8, 2026 5:00 |  | 6 | Required before the NS2 Tuesday CCB
137 | Yes | Auto Scheduled | Client Config / Validation | 2d | September 9, 2026 8:00 | September 10, 2026 5:00 | 136 | 6
138 | Yes | Auto Scheduled | Technical Transports / BP Setup | 1d | September 11, 2026 8:00 | September 11, 2026 5:00 | 137 | 6
139 | Yes | Auto Scheduled | Best Practice / Country Validation | 1d | September 11, 2026 8:00 | September 11, 2026 5:00 | 137 | 6
140 | Yes | Auto Scheduled | Connect Systems and Validate | 2d | September 14, 2026 8:00 | September 15, 2026 5:00 | 139 | 6
141 | Yes | Auto Scheduled | Validate Syniti Connections to QS5 | 1d | September 16, 2026 8:00 | September 16, 2026 5:00 | 140 | 6
142 | Yes | Auto Scheduled | Security Transports | 1d | September 14, 2026 8:00 | September 14, 2026 5:00 | 138,139 | 6
143 | Yes | Auto Scheduled | Security Manual Tasks | 1d | September 15, 2026 8:00 | September 15, 2026 5:00 | 142 | 6
144 | Yes | Auto Scheduled | Manual Technical Tasks | 1d | September 14, 2026 8:00 | September 14, 2026 5:00 | 142SS | 6
145 | Yes | Auto Scheduled | Validate Fiori | 1d | September 15, 2026 8:00 | September 15, 2026 5:00 | 144 | 6
146 | Yes | Auto Scheduled | Fiori App Activation | 1d | September 15, 2026 8:00 | September 15, 2026 5:00 | 145SS | 6
147 | Yes | Auto Scheduled | Download Transport List | 1h | September 16, 2026 8:00 | September 16, 2026 9:00 | 145 | 6
148 | Yes | Auto Scheduled | Business Functions Validation | 1d | September 15, 2026 8:00 | September 15, 2026 5:00 | 145SS | 6
149 | Yes | Auto Scheduled | Functional Leads Validation of Transport List | 1d | September 15, 2026 8:00 | September 15, 2026 5:00 | 145SS | 6
150 | Yes | Auto Scheduled | Release Security roles to Functional Team | 1h | September 16, 2026 8:00 | September 16, 2026 9:00 | 149 | 6
151 | Yes | Auto Scheduled | Release Transports to Client | 5.5d | September 16, 2026 8:00 | September 23, 2026 12:00 | 149 | 5
152 | Yes | Auto Scheduled | Import Group 1 - Ent Structure | 2h | September 16, 2026 8:00 | September 16, 2026 10:00 | 149 | 6
153 | Yes | Auto Scheduled | Manual activities group 1 | 20h | September 16, 2026 10:00 | September 18, 2026 3:00 | 152 | 6
154 | Yes | Auto Scheduled | Import Group 2 - Core Transports | 2h | September 18, 2026 3:00 | September 18, 2026 5:00 | 153 | 6
155 | Yes | Auto Scheduled | Manual activities group 2 | 1d | September 21, 2026 8:00 | September 21, 2026 5:00 | 154 | 6
156 | Yes | Auto Scheduled | Import Group 3 - prior to transactions | 2h | September 22, 2026 8:00 | September 22, 2026 10:00 | 155 | 6
157 | Yes | Auto Scheduled | Manual Activities Group 3 | 1d | September 22, 2026 10:00 | September 23, 2026 10:00 | 156 | 6
158 | Yes | Auto Scheduled | Import Group 4 - workbench / dev work | 2h | September 23, 2026 10:00 | September 23, 2026 12:00 | 157 | 6
159 | Yes | Auto Scheduled | Import Group 5 - Config to support dev workbench | 2h | September 23, 2026 10:00 | September 23, 2026 12:00 | 158SS | 6
160 | Yes | Auto Scheduled | Data Project Create | 0.56d | September 23, 2026 1:00 | September 24, 2026 8:30 |  | 5
161 | Yes | Auto Scheduled | Open Client | 15m | September 23, 2026 1:00 | September 23, 2026 1:15 | 159 | 6
162 | Yes | Auto Scheduled | Create Migration Data Project in DMC | 4h | September 23, 2026 1:15 | September 24, 2026 8:15 | 161 | 6
163 | Yes | Auto Scheduled | Close Client | 15m | September 24, 2026 8:15 | September 24, 2026 8:30 | 162 | 6
164 | Yes | Auto Scheduled | Environment Ready for Build | 0m | September 24, 2026 8:30 | September 24, 2026 8:30 | 160 | 5
165 | Yes | Auto Scheduled | Prod (PS4) Setup | 17d | September 7, 2026 8:00 | September 29, 2026 5:00 |  | 4
166 | Yes | Auto Scheduled | GRC Security Utility | 439d? | February 17, 2025 8:00 | October 22, 2026 5:00 |  | 3 | NEEDS TO BE UPDATED
167 | Yes | Auto Scheduled | Initiation & Planning | 262d | February 17, 2025 8:00 | February 17, 2026 5:00 |  | 4
168 | Yes | Auto Scheduled | Project kickoff | 1d | July 16, 2025 8:00 | July 16, 2025 5:00 |  | 5
169 | Yes | Auto Scheduled | Requirement gathering | 130d | February 17, 2025 8:00 | August 15, 2025 5:00 |  | 5
170 | Yes | Auto Scheduled | Landscape design | 2d | August 18, 2025 8:00 | August 19, 2025 5:00 | 169 | 5
171 | Yes | Auto Scheduled | Project plan finalization | 2d | February 16, 2026 8:00 | February 17, 2026 5:00 |  | 5
172 | Yes | Auto Scheduled | System Setup & Connectivity | 171d | July 28, 2025 8:00 | March 23, 2026 5:00 |  | 4
173 | Yes | Auto Scheduled | Install GRC AC components | 5d | July 28, 2025 8:00 | August 1, 2025 5:00 |  | 5
174 | Yes | Auto Scheduled | Install plug-ins on target systems | 5d | February 18, 2026 8:00 | February 24, 2026 5:00 | 171 | 5
175 | Yes | Auto Scheduled | Post installation Steps | 5d | February 25, 2026 8:00 | March 3, 2026 5:00 | 174 | 5
176 | Yes | Auto Scheduled | Activate BC Sets | 2d | March 4, 2026 8:00 | March 5, 2026 5:00 | 175 | 5
177 | Yes | Auto Scheduled | Connector configuration (S4 / LDAP Connector) | 5d | March 6, 2026 8:00 | March 12, 2026 5:00 | 176 | 5
178 | Yes | Auto Scheduled | Initial configuration [GRC Parameter/Business Process/Sub Process and system Configuration] | 6d | March 13, 2026 8:00 | March 20, 2026 5:00 | 177 | 5
179 | Yes | Auto Scheduled | Transport setup | 1d | March 23, 2026 8:00 | March 23, 2026 5:00 | 178 | 5
180 | Yes | Auto Scheduled | Workflow setup | 10d | March 24, 2026 8:00 | April 6, 2026 5:00 |  | 4
181 | Yes | Auto Scheduled | MSMP workflow configuration | 5d | March 24, 2026 8:00 | March 30, 2026 5:00 | 179 | 5
182 | Yes | Auto Scheduled | BRF+ decision tables | 5d | March 31, 2026 8:00 | April 6, 2026 5:00 | 181 | 5
183 | Yes | Auto Scheduled | Rule Set & Role Design | 311d? | March 13, 2025 8:00 | May 21, 2026 5:00 |  | 4
184 | Yes | Auto Scheduled | Extract the default Global Ruleset from SAP | 4d | September 2, 2025 8:00 | September 5, 2025 5:00 |  | 5
185 | Yes | Auto Scheduled | Extract SU24 Details of transactions from global ruleset and Custom Transactions | 7d | September 8, 2025 8:00 | September 16, 2025 5:00 | 184 | 5
186 | Yes | Auto Scheduled | Prepare/Share the Ruleset Draft with all the functional leads for inputs | 6d | September 17, 2025 8:00 | September 24, 2025 5:00 | 185 | 5
187 | Yes | Auto Scheduled | Schedule workshops to collect complete details of ruleset module wise and close the gaps | 26d | September 25, 2025 8:00 | October 30, 2025 5:00 | 186 | 5
188 | Yes | Auto Scheduled | Final Review Rule Set and update the recommendations | 4d | October 31, 2025 8:00 | May 4, 2026 1:48 | 187 | 5
189 | Yes | Auto Scheduled | Import rulesets into system | 4d | November 6, 2025 8:00 | November 11, 2025 5:00 | 188 | 5
190 | Yes | Auto Scheduled | RCM Development | 1d? | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 5
191 | Yes | Auto Scheduled | Setup Mitigation controls | 6d | November 12, 2025 8:00 | November 19, 2025 5:00 | 189 | 5
192 | Yes | Auto Scheduled | Risk analysis on existing roles | 5d | May 1, 2026 8:00 | May 7, 2026 5:00 | 191 | 5
193 | Yes | Auto Scheduled | Role remediation planning - Can impact role design & Possible of retesting. | 10d | May 8, 2026 8:00 | May 21, 2026 5:00 | 192 | 5
194 | Yes | Auto Scheduled | Business Role Management | 10d | May 8, 2026 8:00 | May 21, 2026 5:00 |  | 4
195 | Yes | Auto Scheduled | Role Mapping with Business Process and Sub-Process /Functional Area | 5d | May 8, 2026 8:00 | May 14, 2026 5:00 | 192 | 5
196 | Yes | Auto Scheduled | Role Upload to SAP GRC | 5d | May 15, 2026 8:00 | May 21, 2026 5:00 | 195 | 5
197 | Yes | Auto Scheduled | Firefighter Configuration | 15d | May 1, 2026 8:00 | May 21, 2026 5:00 |  | 4
198 | Yes | Auto Scheduled | Firefighter ID setup | 5d | May 1, 2026 8:00 | May 7, 2026 5:00 |  | 5
199 | Yes | Auto Scheduled | Firefighter log settings | 5d | May 8, 2026 8:00 | May 14, 2026 5:00 | 198 | 5
200 | Yes | Auto Scheduled | Functional validation | 5d | May 15, 2026 8:00 | May 21, 2026 5:00 | 199 | 5
201 | Yes | Auto Scheduled | Testing & Training | 69d | May 1, 2026 8:00 | August 5, 2026 5:00 |  | 4
202 | Yes | Auto Scheduled | Unit testing | 9d | May 1, 2026 8:00 | May 13, 2026 5:00 |  | 5
203 | Yes | Auto Scheduled | Changes moved to Test System | 3d | May 14, 2026 8:00 | May 18, 2026 5:00 | 202 | 5
204 | Yes | Auto Scheduled | Connector configuration (S4 / LDAP Connector) | 3d | May 19, 2026 8:00 | May 21, 2026 5:00 | 203 | 5
205 | Yes | Auto Scheduled | Workflow Activation / Data load in Test System | 5d | May 22, 2026 8:00 | May 28, 2026 5:00 | 204 | 5
206 | Yes | Auto Scheduled | Integration testing - Smoke Test | 9d | May 29, 2026 8:00 | June 10, 2026 5:00 | 205 | 5
207 | Yes | Auto Scheduled | UAT (User Acceptance Testing) - ITC-3 - with roles | 16d | June 11, 2026 8:00 | July 2, 2026 5:00 | 206 | 5
208 | Yes | Auto Scheduled | Issue resolution | 10d | July 3, 2026 8:00 | July 16, 2026 5:00 | 207 | 5
209 | Yes | Auto Scheduled | End-user training | 6d | July 17, 2026 8:00 | July 24, 2026 5:00 | 208 | 5
210 | Yes | Auto Scheduled | Initiate Preparation of Cutover Plans | 8d | July 27, 2026 8:00 | August 5, 2026 5:00 | 209 | 5
211 | Yes | Auto Scheduled | Go-Live | 16d | October 1, 2026 8:00 | October 22, 2026 5:00 |  | 4
212 | Yes | Auto Scheduled | Production deployment | 7d | October 1, 2026 8:00 | October 9, 2026 5:00 | 134 | 5
213 | Yes | Auto Scheduled | Execution of Cutover Plan(Business and Technical) | 7d | October 1, 2026 8:00 | October 9, 2026 5:00 | 212SS | 5
214 | Yes | Auto Scheduled | Final risk analysis | 7d | October 12, 2026 8:00 | October 20, 2026 5:00 | 213 | 5
215 | Yes | Auto Scheduled | Go-live (Technical) | 2d | October 21, 2026 8:00 | October 22, 2026 5:00 | 214 | 5
216 | Yes | Auto Scheduled | Functional Build Tasks | 119d | April 7, 2025 8:00 | September 18, 2025 5:00 |  | 4
217 | Yes | Auto Scheduled | BPD Development / Configuration Specs | 119d | April 7, 2025 8:00 | September 18, 2025 5:00 |  | 5
218 | Yes | Auto Scheduled | Master Data | 59d | June 16, 2025 8:00 | September 4, 2025 5:00 |  | 6
219 | Yes | Auto Scheduled | In Draft | 22d | June 16, 2025 8:00 | July 15, 2025 5:00 |  | 7
220 | Yes | Auto Scheduled | Complete - Ready for Security Review | 30d | July 7, 2025 8:00 | August 15, 2025 5:00 |  | 7
221 | Yes | Auto Scheduled | Complete - Audit and Controls Review | 14d | August 18, 2025 8:00 | September 4, 2025 5:00 | 220 | 7
222 | Yes | Auto Scheduled | Finance | 104d | April 7, 2025 8:00 | August 28, 2025 5:00 |  | 6
223 | Yes | Auto Scheduled | In Draft | 60d | April 7, 2025 8:00 | June 27, 2025 5:00 |  | 7
224 | Yes | Auto Scheduled | Complete - Ready for Security Review | 80d | April 21, 2025 8:00 | August 8, 2025 5:00 |  | 7
225 | Yes | Auto Scheduled | Complete - Ready for Audit and Controls Review | 14d | August 11, 2025 8:00 | August 28, 2025 5:00 | 224 | 7
226 | Yes | Auto Scheduled | Plan to Make | 108d | April 8, 2025 8:00 | September 4, 2025 5:00 |  | 6
227 | Yes | Auto Scheduled | In Draft | 75d | April 8, 2025 8:00 | July 21, 2025 5:00 |  | 7
228 | Yes | Auto Scheduled | Complete - Ready for Security Review | 85d | April 21, 2025 8:00 | August 15, 2025 5:00 |  | 7
229 | Yes | Auto Scheduled | Complete - Ready for Audit and Controls Review | 14d | August 18, 2025 8:00 | September 4, 2025 5:00 | 228 | 7
230 | Yes | Auto Scheduled | Procure to Pay | 119d | April 7, 2025 8:00 | September 18, 2025 5:00 |  | 6
231 | Yes | Auto Scheduled | In Draft | 96d | April 7, 2025 8:00 | August 18, 2025 5:00 |  | 7
232 | Yes | Auto Scheduled | Complete - Ready for Security Review | 95d | April 21, 2025 8:00 | August 29, 2025 5:00 |  | 7
233 | Yes | Auto Scheduled | Complete - Ready for Audit and Controls Review | 14d | September 1, 2025 8:00 | September 18, 2025 5:00 | 232 | 7
234 | Yes | Auto Scheduled | Order to Cash | 99d | April 7, 2025 8:00 | August 21, 2025 5:00 |  | 6
235 | Yes | Auto Scheduled | In Draft | 76d | April 7, 2025 8:00 | July 21, 2025 5:00 |  | 7
236 | Yes | Auto Scheduled | Complete - Ready for Security Review | 75d | April 21, 2025 8:00 | August 1, 2025 5:00 |  | 7
237 | Yes | Auto Scheduled | Complete - Ready for Audit and Controls Review | 14d | August 4, 2025 8:00 | August 21, 2025 5:00 | 236 | 7
238 | Yes | Auto Scheduled | RICEFW Development Tasks (RICEFW Tracker) | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 4
239 | Yes | Auto Scheduled | Finance and Controlling | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 5
240 | Yes | Auto Scheduled | Specs Completed | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
241 | Yes | Auto Scheduled | Specs Assigned to Developer | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
242 | Yes | Auto Scheduled | Testing Complete | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
243 | Yes | Auto Scheduled | Assigned to Testing Cycle | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
244 | Yes | Auto Scheduled | Plan to Make | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 5
245 | Yes | Auto Scheduled | Specs Completed | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
246 | Yes | Auto Scheduled | Specs Assigned to Developer | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
247 | Yes | Auto Scheduled | Testing Complete | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
248 | Yes | Auto Scheduled | Assigned to Testing Cycle | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
249 | Yes | Auto Scheduled | Procure to Pay | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 5
250 | Yes | Auto Scheduled | Specs Completed | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
251 | Yes | Auto Scheduled | Specs Assigned to Developer | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
252 | Yes | Auto Scheduled | Testing Complete | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
253 | Yes | Auto Scheduled | Assigned to Testing Cycle | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
254 | Yes | Auto Scheduled | Order to Cash | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 5
255 | Yes | Auto Scheduled | Specs Completed | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
256 | Yes | Auto Scheduled | Specs Assigned to Developer | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
257 | Yes | Auto Scheduled | Testing Complete | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
258 | Yes | Auto Scheduled | Assigned to Testing Cycle | 1d | March 13, 2025 8:00 | March 13, 2025 5:00 |  | 6
259 | Yes | Auto Scheduled | Data Readiness | 135.66d | April 6, 2026 8:00 | October 12, 2026 2:15 |  | 2
260 | Yes | Auto Scheduled | ITC1 Data Load Tasks QS5 | 13.66d | April 6, 2026 8:00 | April 23, 2026 2:15 |  | 3
261 | Yes | Auto Scheduled | PMO Authorization to Start Data Loads | 15m | April 6, 2026 8:00 | April 6, 2026 8:15 |  | 4
262 | Yes | Auto Scheduled | RTR_CM02_Profit Center Hierarchy | 0.75d | April 6, 2026 8:15 | April 6, 2026 3:15 |  | 4
263 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | April 6, 2026 8:15 | April 6, 2026 9:15 | 261 | 5
264 | Yes | Auto Scheduled | Load | 2h | April 6, 2026 9:15 | April 6, 2026 11:15 | 263 | 5
265 | Yes | Auto Scheduled | Post Load Validation | 3h | April 6, 2026 11:15 | April 6, 2026 3:15 | 264 | 5
266 | Yes | Auto Scheduled | RTR_CM03_Cost Center Hierarchy | 0.75d | April 6, 2026 3:15 | April 7, 2026 1:15 | 262 | 4
267 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | April 6, 2026 3:15 | April 6, 2026 4:15 | 265 | 5
268 | Yes | Auto Scheduled | Load | 2h | April 6, 2026 4:15 | April 7, 2026 9:15 | 267 | 5
269 | Yes | Auto Scheduled | Post Load Validation | 3h | April 7, 2026 9:15 | April 7, 2026 1:15 | 268 | 5
270 | Yes | Auto Scheduled | RTR_CM01_GL_Account_Master to CC 1000 | 1.81d | April 7, 2026 1:15 | April 9, 2026 10:45 | 266 | 4
271 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | April 7, 2026 1:15 | April 7, 2026 2:15 | 269 | 5
272 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 7, 2026 2:15 | April 7, 2026 4:15 | 271 | 5
273 | Yes | Auto Scheduled | Simulate Load | 6h | April 7, 2026 4:15 | April 8, 2026 2:15 | 272 | 5
274 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 8, 2026 8:15 | April 8, 2026 11:45 | 273 | 5
275 | Yes | Auto Scheduled | Load | 1h | April 8, 2026 11:45 | April 8, 2026 1:45 | 274 | 5
276 | Yes | Auto Scheduled | Post Load Validation | 2h | April 8, 2026 1:45 | April 8, 2026 3:45 | 275 | 5
277 | Yes | Auto Scheduled | Extend GL to all Company Codes | 2h | April 8, 2026 3:45 | April 9, 2026 8:45 | 276 | 5
278 | Yes | Auto Scheduled | Post GL Extention Validation | 2h | April 9, 2026 8:45 | April 9, 2026 10:45 | 277 | 5
279 | Yes | Auto Scheduled | RTR_CM05_Profit_Center | 1.13d | April 6, 2026 3:15 | April 7, 2026 4:15 | 270 | 4
280 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | April 6, 2026 3:15 | April 6, 2026 4:15 | 265 | 5
281 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 6, 2026 4:15 | April 7, 2026 9:15 | 280 | 5
282 | Yes | Auto Scheduled | Simulate Load | 1h | April 7, 2026 9:15 | April 7, 2026 10:15 | 281 | 5
283 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 7, 2026 10:15 | April 7, 2026 1:15 | 282 | 5
284 | Yes | Auto Scheduled | Load | 1h | April 7, 2026 1:15 | April 7, 2026 2:15 | 283 | 5
285 | Yes | Auto Scheduled | Post Load Validation | 2h | April 7, 2026 2:15 | April 7, 2026 4:15 | 284 | 5
286 | Yes | Auto Scheduled | RTR_CM04_Cost_Center | 1.13d | April 7, 2026 4:15 | April 9, 2026 8:15 | 279 | 4
287 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | April 7, 2026 4:15 | April 8, 2026 8:15 | 285 | 5
288 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 8, 2026 8:15 | April 8, 2026 10:15 | 287 | 5
289 | Yes | Auto Scheduled | Simulate Load | 1h | April 8, 2026 10:15 | April 8, 2026 11:15 | 288 | 5
290 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 8, 2026 11:15 | April 8, 2026 2:15 | 289 | 5
291 | Yes | Auto Scheduled | Load | 1h | April 8, 2026 2:15 | April 8, 2026 3:15 | 290 | 5
292 | Yes | Auto Scheduled | Post Load Validation | 2h | April 8, 2026 3:15 | April 9, 2026 8:15 | 291 | 5
293 | Yes | Auto Scheduled | Manual Configuration Activities in QS5 | 7.16d | April 6, 2026 1:00 | April 15, 2026 2:15 | 286 | 4
294 | Yes | Auto Scheduled | Open Client | 30m | April 6, 2026 1:00 | April 6, 2026 1:30 |  | 5
295 | Yes | Auto Scheduled | Service Enterprise Setup | 5d | April 8, 2026 2:15 | April 15, 2026 2:15 | 270,262,266 | 5
296 | Yes | Auto Scheduled | Close Client | 30m | April 6, 2026 1:00 | April 6, 2026 1:30 |  | 5
297 | Yes | Auto Scheduled | Intercompany Business Partner Setup | 2h | April 8, 2026 3:45 | April 9, 2026 8:45 | 262,266,278 | 5
298 | Yes | Auto Scheduled | RTR_CM09_Activity_Type | 1.22d | April 8, 2026 2:15 | April 9, 2026 4:00 | 286 | 4
299 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | April 8, 2026 2:15 | April 8, 2026 4:30 | 276 | 5
300 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 8, 2026 3:15 | April 9, 2026 9:00 | 299 | 5
301 | Yes | Auto Scheduled | Simulate Load | 1h | April 9, 2026 9:00 | April 9, 2026 10:00 | 300 | 5
302 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 9, 2026 10:00 | April 9, 2026 12:00 | 301 | 5
303 | Yes | Auto Scheduled | Load | 1h | April 9, 2026 1:00 | April 9, 2026 2:00 | 302 | 5
304 | Yes | Auto Scheduled | Post Load Validation | 2h | April 9, 2026 2:00 | April 9, 2026 4:00 | 303 | 5
305 | Yes | Auto Scheduled | RTR_CM12_Activity Rates | 1.13d | April 7, 2026 1:15 | April 8, 2026 2:15 | 298 | 4
306 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | April 7, 2026 1:15 | April 7, 2026 2:15 | 269 | 5
307 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 7, 2026 2:15 | April 7, 2026 4:15 | 306 | 5
308 | Yes | Auto Scheduled | Simulate Load | 1h | April 7, 2026 4:15 | April 8, 2026 8:15 | 307 | 5
309 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 8, 2026 8:15 | April 8, 2026 10:15 | 308 | 5
310 | Yes | Auto Scheduled | Load | 1h | April 8, 2026 10:15 | April 8, 2026 11:15 | 309 | 5
311 | Yes | Auto Scheduled | Post Load Validation | 2h | April 8, 2026 11:15 | April 8, 2026 2:15 | 310 | 5
312 | Yes | Auto Scheduled | RTR_CM06_Bank_master | 2.19d | April 14, 2026 8:00 | April 16, 2026 9:30 | 305 | 4
313 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | April 14, 2026 8:00 | April 14, 2026 9:00 | 276 | 5
314 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 14, 2026 9:00 | April 14, 2026 11:00 | 313 | 5
315 | Yes | Auto Scheduled | Simulate Load | 1h | April 15, 2026 8:00 | April 15, 2026 9:00 |  | 5
316 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 15, 2026 9:00 | April 15, 2026 11:00 | 315 | 5
317 | Yes | Auto Scheduled | Load | 5h | April 15, 2026 11:00 | April 15, 2026 5:00 | 316 | 5
318 | Yes | Auto Scheduled | Post Load Validation | 2h | April 15, 2026 1:00 | April 16, 2026 9:30 | 317 | 5
319 | Yes | Auto Scheduled | RTR_CM08_Exchange_Rates | 1.13d | April 9, 2026 2:30 | April 10, 2026 3:30 | 312 | 4
320 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | April 9, 2026 2:30 | April 9, 2026 3:30 | 317 | 5
321 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 9, 2026 3:30 | April 10, 2026 8:30 | 320 | 5
322 | Yes | Auto Scheduled | Simulate Load | 1h | April 10, 2026 8:30 | April 10, 2026 9:30 | 321 | 5
323 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 10, 2026 9:30 | April 10, 2026 11:30 | 322 | 5
324 | Yes | Auto Scheduled | Load | 1h | April 10, 2026 11:30 | April 10, 2026 1:30 | 323 | 5
325 | Yes | Auto Scheduled | Post Load Validation | 2h | April 10, 2026 1:30 | April 10, 2026 3:30 | 324 | 5
326 | Yes | Auto Scheduled | RTR_CM14_Cost Element_Group | 5.38d | April 15, 2026 8:00 | April 22, 2026 11:00 | 319 | 4
327 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | April 15, 2026 8:00 | April 15, 2026 8:30 | 276 | 5
328 | Yes | Auto Scheduled | Load | 32h | April 16, 2026 8:00 | April 21, 2026 5:00 | 327 | 5
329 | Yes | Auto Scheduled | Post Load Validation | 3h | April 22, 2026 8:00 | April 22, 2026 11:00 | 328 | 5
330 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Bill-To | 2h | April 16, 2026 8:00 | April 16, 2026 10:00 | 326 | 4 | 4/20 Per OTC this is not needed for ITC1
331 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Ship-To | 2.16d | April 8, 2026 3:45 | April 10, 2026 5:00 | 330 | 4
332 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 8, 2026 3:45 | April 8, 2026 4:15 | 276 | 5
333 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 8, 2026 4:15 | April 8, 2026 4:45 | 332 | 5
334 | Yes | Auto Scheduled | Open client for BP number range update | 30m | April 8, 2026 4:45 | April 9, 2026 8:15 | 333 | 5
335 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 30m | April 9, 2026 4:45 | April 10, 2026 8:15 | 334 | 5
336 | Yes | Auto Scheduled | Close Client | 15m | April 10, 2026 4:45 | April 10, 2026 5:00 | 335 | 5
337 | Yes | Auto Scheduled | Simulate Load | 1h | April 8, 2026 4:45 | April 9, 2026 8:45 | 333 | 5
338 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | April 9, 2026 8:45 | April 9, 2026 1:45 | 337 | 5
339 | Yes | Auto Scheduled | Load | 3h | April 9, 2026 1:45 | April 9, 2026 4:45 | 338 | 5
340 | Yes | Auto Scheduled | Post Load Validation | 3h | April 9, 2026 4:45 | April 10, 2026 10:45 | 339 | 5
341 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Sold-To | 1.63d | April 8, 2026 4:45 | April 10, 2026 1:45 | 331 | 4
342 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 8, 2026 4:45 | April 9, 2026 8:15 | 333 | 5
343 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 9, 2026 8:15 | April 9, 2026 8:45 | 342 | 5
344 | Yes | Auto Scheduled | Simulate Load | 1h | April 9, 2026 10:45 | April 9, 2026 11:45 | 337,278 | 5
345 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | April 9, 2026 11:45 | April 9, 2026 3:45 | 344 | 5
346 | Yes | Auto Scheduled | Load | 3h | April 9, 2026 3:45 | April 10, 2026 9:45 | 345 | 5
347 | Yes | Auto Scheduled | Post Load Validation | 3h | April 10, 2026 9:45 | April 10, 2026 1:45 | 346 | 5
348 | Yes | Auto Scheduled | Open client for BP number range update | 15m | April 9, 2026 8:45 | April 9, 2026 9:00 | 337 | 5
349 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 15m | April 9, 2026 9:00 | April 9, 2026 9:15 | 348 | 5
350 | Yes | Auto Scheduled | Close Client | 15m | April 9, 2026 9:15 | April 9, 2026 9:30 | 349 | 5
351 | Yes | Auto Scheduled | PTP_CM27_Vendor Master as Customer - FLCU01 | 2.31d | April 10, 2026 9:45 | April 14, 2026 1:15 | 341 | 4
352 | Yes | Auto Scheduled | Extract File | 1h | April 10, 2026 9:45 | April 10, 2026 10:45 | 346 | 5
353 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 10, 2026 10:45 | April 10, 2026 1:45 | 352 | 5
354 | Yes | Auto Scheduled | Simulate Load | 11.25h | April 10, 2026 1:45 | April 13, 2026 5:00 | 353,318 | 5
355 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 10, 2026 2:45 | April 14, 2026 9:30 | 354 | 5
356 | Yes | Auto Scheduled | Load | 1h | April 10, 2026 4:45 | April 14, 2026 10:15 | 355 | 5
357 | Yes | Auto Scheduled | Post Load Validation | 2h | April 14, 2026 10:15 | April 14, 2026 1:15 | 356 | 5
358 | Yes | Auto Scheduled | OTC_CM23_Customer_Hierarchy | 3.03d | April 10, 2026 9:45 | April 15, 2026 10:00 | 351 | 4
359 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | April 10, 2026 9:45 | April 10, 2026 10:15 | 346 | 5
360 | Yes | Auto Scheduled | Load | 2h | April 15, 2026 8:00 | April 15, 2026 10:00 | 359 | 5
361 | Yes | Auto Scheduled | Post Load Validation | 3h | April 10, 2026 1:15 | April 10, 2026 4:15 | 360 | 5
362 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Z001 - External Sales Rep | 3.38d | April 10, 2026 9:45 | April 15, 2026 1:45 | 358 | 4
363 | Yes | Auto Scheduled | Extract File | 1h | April 10, 2026 9:45 | April 10, 2026 10:45 | 346 | 5
364 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 10, 2026 10:45 | April 10, 2026 1:45 | 363 | 5
365 | Yes | Auto Scheduled | Simulate Load | 1h | April 10, 2026 1:45 | April 10, 2026 2:45 | 364,318 | 5
366 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 15, 2026 8:00 | April 15, 2026 10:00 | 365 | 5
367 | Yes | Auto Scheduled | Load | 1h | April 10, 2026 4:45 | April 15, 2026 10:45 | 366 | 5
368 | Yes | Auto Scheduled | Post Load Validation | 2h | April 15, 2026 10:45 | April 15, 2026 1:45 | 367 | 5
369 | Yes | Auto Scheduled | RTR_CM10_Credit_Management_Role | 5.56d | April 10, 2026 9:45 | April 17, 2026 3:15 | 362 | 4
370 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 10, 2026 9:45 | April 10, 2026 10:15 | 346 | 5
371 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 10, 2026 10:15 | April 10, 2026 10:45 | 370 | 5
372 | Yes | Auto Scheduled | Simulate Load | 1h | April 17, 2026 8:00 | April 17, 2026 9:00 | 371 | 5 | 4/16 - Asked to reload per Brian
373 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 17, 2026 8:00 | April 17, 2026 10:30 | 372 | 5
374 | Yes | Auto Scheduled | Load | 2h | April 17, 2026 8:00 | April 17, 2026 12:00 | 373 | 5
375 | Yes | Auto Scheduled | Post Load Validation | 3h | April 17, 2026 8:00 | April 17, 2026 3:15 | 374 | 5 | 4/17 - Error on load,resolution identifed, Def899,Will manually change customer for IT1
376 | Yes | Auto Scheduled | PTP_CM27_Vendor Master | 3.72d | April 10, 2026 10:45 | April 16, 2026 8:30 | 369 | 4
377 | Yes | Auto Scheduled | Extract File | 1h | April 10, 2026 10:45 | April 10, 2026 11:45 | 363 | 5
378 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 10, 2026 11:45 | April 10, 2026 2:45 | 377 | 5
379 | Yes | Auto Scheduled | Simulate Load | 2.25h | April 10, 2026 2:45 | April 10, 2026 5:00 | 378 | 5 | First time simulation on 4/13
380 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 13, 2026 8:00 | April 13, 2026 2:30 | 379 | 5 | 4/14 - Ran into more errors and Manoj will follow up ib 2hrs....
381 | Yes | Auto Scheduled | Load | 1h | April 15, 2026 2:30 | April 15, 2026 3:30 |  | 5
382 | Yes | Auto Scheduled | Post Load Validation | 2h | April 15, 2026 3:30 | April 16, 2026 8:30 | 381 | 5 | 4/14 PTP Is complete
383 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | 0.88d | April 16, 2026 8:00 | April 16, 2026 4:00 | 376 | 4
384 | Yes | Auto Scheduled | Extract File(Will Extract from LFA1) | 1h | April 16, 2026 8:00 | April 16, 2026 9:00 |  | 5
385 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 16, 2026 9:00 | April 16, 2026 11:00 | 384 | 5
386 | Yes | Auto Scheduled | Simulate Load/ Not Needed | 1h | April 16, 2026 11:00 | April 16, 2026 12:00 | 385 | 5
387 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 16, 2026 1:00 | April 16, 2026 3:00 | 386 | 5 | 4/16 - Defect created no impact to ITC1
388 | Yes | Auto Scheduled | Load | 1h | April 16, 2026 1:00 | April 16, 2026 2:00 | 386 | 5
389 | Yes | Auto Scheduled | Post Load Validation | 2h | April 16, 2026 2:00 | April 16, 2026 4:00 | 388 | 5
390 | Yes | Auto Scheduled | RTR_****_Credit Hierarchy | 1.38d | April 15, 2026 8:00 | April 16, 2026 11:00 | 383 | 4
391 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | April 15, 2026 8:00 | April 15, 2026 8:30 | 373 | 5 | 4/16 -Completed
392 | Yes | Auto Scheduled | Load | 2h | April 15, 2026 8:00 | April 15, 2026 10:00 | 375 | 5
393 | Yes | Auto Scheduled | Post Load Validation | 3h | April 16, 2026 8:00 | April 16, 2026 11:00 | 392 | 5
394 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Supplier | 1.13d | April 13, 2026 11:45 | April 14, 2026 1:45 | 390 | 4
395 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 13, 2026 11:45 | April 13, 2026 1:15 | 382 | 5
396 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 13, 2026 1:15 | April 13, 2026 1:45 | 395 | 5
397 | Yes | Auto Scheduled | Simulate Load | 1h | April 13, 2026 1:45 | April 13, 2026 2:45 | 396 | 5
398 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 13, 2026 2:45 | April 13, 2026 4:45 | 397 | 5
399 | Yes | Auto Scheduled | Load | 2h | April 13, 2026 4:45 | April 14, 2026 9:45 | 398 | 5
400 | Yes | Auto Scheduled | Post Load Validation | 3h | April 14, 2026 9:45 | April 14, 2026 1:45 | 399 | 5
401 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Customer | 1.13d | April 13, 2026 11:45 | April 14, 2026 1:45 | 394 | 4
402 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 13, 2026 11:45 | April 13, 2026 1:15 |  | 5
403 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 13, 2026 1:15 | April 13, 2026 1:45 |  | 5
404 | Yes | Auto Scheduled | Simulate Load | 1h | April 13, 2026 1:45 | April 13, 2026 2:45 | 403 | 5
405 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 13, 2026 2:45 | April 13, 2026 4:45 | 404 | 5
406 | Yes | Auto Scheduled | Load | 2h | April 13, 2026 4:45 | April 14, 2026 9:45 | 405 | 5
407 | Yes | Auto Scheduled | Post Load Validation | 3h | April 14, 2026 9:45 | April 14, 2026 1:45 | 406 | 5
408 | Yes | Auto Scheduled | PTP_CM26_Material_Master - All Types | 3.16d | April 10, 2026 10:45 | April 15, 2026 12:00 | 401 | 4
409 | Yes | Auto Scheduled | Extract File | 5h | April 10, 2026 10:45 | April 13, 2026 9:30 | 384 | 5
410 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 13, 2026 11:45 | April 14, 2026 10:00 | 382 | 5
411 | Yes | Auto Scheduled | Simulate Load | 1h | April 14, 2026 10:00 | April 14, 2026 11:00 | 410 | 5
412 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | April 14, 2026 11:00 | April 14, 2026 4:00 | 411 | 5
413 | Yes | Auto Scheduled | Load | 3h | April 14, 2026 4:00 | April 15, 2026 10:00 | 412 | 5
414 | Yes | Auto Scheduled | Post Load Validation | 2h | April 15, 2026 10:00 | April 15, 2026 12:00 | 413 | 5
415 | Yes | Auto Scheduled | PTP_CM26_Material_Master - SERV - Service Materials | 5.88d | April 7, 2026 4:15 | April 15, 2026 3:15 | 408 | 4
416 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 7, 2026 4:15 | April 7, 2026 4:45 | 285 | 5
417 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 14, 2026 2:45 | April 14, 2026 3:15 | 413 | 5
418 | Yes | Auto Scheduled | Simulate Load | 1h | April 14, 2026 3:15 | April 14, 2026 4:15 | 417 | 5
419 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 14, 2026 4:15 | April 15, 2026 9:15 | 418 | 5
420 | Yes | Auto Scheduled | Load | 2h | April 15, 2026 9:15 | April 15, 2026 11:15 | 419 | 5
421 | Yes | Auto Scheduled | Post Load Validation | 3h | April 15, 2026 11:15 | April 15, 2026 3:15 | 420 | 5
422 | Yes | Auto Scheduled | PTP_CM26_Material_Master - KMAT - Configurable Materials | 5.88d | April 7, 2026 4:15 | April 15, 2026 3:15 | 415 | 4
423 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 7, 2026 4:15 | April 7, 2026 4:45 | 285 | 5
424 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 14, 2026 2:45 | April 14, 2026 3:15 | 413 | 5
425 | Yes | Auto Scheduled | Simulate Load | 1h | April 14, 2026 3:15 | April 14, 2026 4:15 | 424 | 5
426 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 14, 2026 4:15 | April 15, 2026 9:15 | 425 | 5
427 | Yes | Auto Scheduled | Load | 2h | April 15, 2026 9:15 | April 15, 2026 11:15 | 426 | 5
428 | Yes | Auto Scheduled | Post Load Validation | 3h | April 15, 2026 11:15 | April 15, 2026 3:15 | 427 | 5
429 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Records | 1.59d | April 15, 2026 3:15 | April 17, 2026 11:00 |  | 4
430 | Yes | Auto Scheduled | Extract File | 1h | April 15, 2026 3:15 | April 15, 2026 4:15 | 414,428 | 5 | 4/16 - Started extract
431 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 15, 2026 4:15 | April 16, 2026 9:15 | 430 | 5
432 | Yes | Auto Scheduled | Simulate Load | 1h | April 16, 2026 9:15 | April 16, 2026 10:15 | 431 | 5
433 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 17, 2026 8:00 | April 17, 2026 10:00 | 432 | 5
434 | Yes | Auto Scheduled | Load | 1h | April 17, 2026 8:00 | April 17, 2026 9:00 | 382 | 5
435 | Yes | Auto Scheduled | Post Load Validation | 2h | April 17, 2026 9:00 | April 17, 2026 11:00 | 434 | 5
436 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record External Processing | 1.47d | April 15, 2026 3:15 | April 17, 2026 10:00 |  | 4
437 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 15, 2026 3:15 | April 15, 2026 3:45 | 414,428 | 5
438 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 15, 2026 3:45 | April 15, 2026 4:15 | 437 | 5
439 | Yes | Auto Scheduled | Simulate Load | 1h | April 16, 2026 8:00 | April 16, 2026 9:00 | 438 | 5
440 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 16, 2026 9:00 | April 16, 2026 11:00 | 439 | 5
441 | Yes | Auto Scheduled | Load | 2h | April 17, 2026 8:00 | April 17, 2026 10:00 | 440 | 5
442 | Yes | Auto Scheduled | Post Load Validation | 3h | April 16, 2026 2:00 | April 16, 2026 5:00 | 441 | 5
443 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | 1.13d | April 15, 2026 3:15 | April 16, 2026 4:15 |  | 4
444 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 15, 2026 3:15 | April 15, 2026 3:45 | 414,428 | 5
445 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 15, 2026 3:45 | April 15, 2026 4:15 | 444 | 5
446 | Yes | Auto Scheduled | Simulate Load | 1h | April 15, 2026 4:15 | April 16, 2026 8:15 | 445 | 5 | 4/16 - Eror
447 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 16, 2026 8:15 | April 16, 2026 10:15 | 446 | 5
448 | Yes | Auto Scheduled | Load | 2h | April 16, 2026 10:15 | April 16, 2026 1:15 | 447 | 5
449 | Yes | Auto Scheduled | Post Load Validation | 3h | April 16, 2026 1:15 | April 16, 2026 4:15 | 448 | 5
450 | Yes | Auto Scheduled | PTM_CM31_BOM Conversion | 2.09d | April 15, 2026 4:15 | April 17, 2026 5:00 |  | 4
451 | Yes | Auto Scheduled | Extract File | 1h | April 15, 2026 4:15 | April 16, 2026 8:15 | 430 | 5
452 | Yes | Auto Scheduled | Pre Load Validation | 0.5h | April 16, 2026 8:15 | April 16, 2026 8:45 | 451 | 5
453 | Yes | Auto Scheduled | Simulate Load | 15.5h | April 16, 2026 8:00 | April 17, 2026 5:00 | 452 | 5
454 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | April 17, 2026 8:00 | April 17, 2026 8:30 | 453 | 5
455 | Yes | Auto Scheduled | Load | 1h | April 17, 2026 8:00 | April 17, 2026 9:15 | 454 | 5 | 4/17- Bom issues and not moving to routings...
456 | Yes | Auto Scheduled | Post Load Validation | 0.5h | April 17, 2026 9:00 | April 17, 2026 9:38 | 455 | 5 | 4/16 - updated to post load...
457 | Yes | Auto Scheduled | PTM_CM40_Work Center Conversion | 0.38d | April 16, 2026 8:00 | April 16, 2026 11:00 |  | 4
458 | Yes | Auto Scheduled | Extract File | 1h | April 16, 2026 8:15 | April 16, 2026 9:15 | 451 | 5
459 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 16, 2026 8:30 | April 16, 2026 10:30 | 456 | 5
460 | Yes | Auto Scheduled | Simulate Load | 0.25h | April 16, 2026 8:00 | April 16, 2026 8:15 | 459 | 5
461 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | April 16, 2026 8:00 | April 16, 2026 8:30 | 460 | 5 | 4/16- Defect created
462 | Yes | Auto Scheduled | Load | 1h | April 16, 2026 8:00 | April 16, 2026 9:00 | 461 | 5
463 | Yes | Auto Scheduled | Post Load Validation | 2h | April 16, 2026 9:00 | April 16, 2026 11:00 | 462 | 5
464 | Yes | Auto Scheduled | PTM_CM38_Routing Conversion | 2.75d | April 16, 2026 8:00 | April 20, 2026 3:00 |  | 4
465 | Yes | Auto Scheduled | Extract File | 1h | April 16, 2026 9:15 | April 16, 2026 10:15 | 458 | 5
466 | Yes | Auto Scheduled | Pre Load Validation | 2h | April 16, 2026 8:00 | April 16, 2026 1:30 | 463 | 5
467 | Yes | Auto Scheduled | Simulate Load | 2h | April 20, 2026 8:00 | April 20, 2026 10:00 | 466 | 5 | 4/20 Cost element has been resolved and now ready to run simulation again. Need to decide if we need to load all routings or load what we have that will load
468 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | April 20, 2026 8:00 | April 20, 2026 11:00 | 467SS | 5
469 | Yes | Auto Scheduled | Load | 1h | April 20, 2026 11:00 | April 20, 2026 12:00 | 468 | 5
470 | Yes | Auto Scheduled | Post Load Validation | 2h | April 20, 2026 1:00 | April 20, 2026 3:00 | 469 | 5
471 | Yes | Auto Scheduled | PTM_CM36_Production Version Conversion | 1.13d | April 20, 2026 8:00 | April 21, 2026 9:00 |  | 4
472 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 20, 2026 8:00 | April 20, 2026 8:30 | 465 | 5
473 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 20, 2026 8:30 | April 20, 2026 9:00 | 472 | 5
474 | Yes | Auto Scheduled | Simulate Load | 1h | April 20, 2026 9:00 | April 20, 2026 10:00 | 473 | 5
475 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 20, 2026 10:00 | April 20, 2026 12:00 | 474 | 5
476 | Yes | Auto Scheduled | Load | 2h | April 20, 2026 1:00 | April 20, 2026 3:00 | 475 | 5
477 | Yes | Auto Scheduled | Post Load Validation | 3h | April 20, 2026 3:00 | April 21, 2026 9:00 | 476 | 5
478 | Yes | Auto Scheduled | PTM_CM35_Inspection Plan | 1.13d | April 21, 2026 9:00 | April 22, 2026 10:00 |  | 4 | 4/17 - will manually load IP for ITC1
479 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 21, 2026 9:00 | April 21, 2026 9:30 | 477 | 5 | 4/20- Per Brad they will load manaually for ITC1
480 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 21, 2026 9:30 | April 21, 2026 10:00 | 479 | 5
481 | Yes | Auto Scheduled | Simulate Load | 1h | April 21, 2026 10:00 | April 21, 2026 11:00 | 480 | 5
482 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 21, 2026 11:00 | April 21, 2026 2:00 | 481 | 5
483 | Yes | Auto Scheduled | Load | 2h | April 21, 2026 2:00 | April 21, 2026 4:00 | 482 | 5
484 | Yes | Auto Scheduled | Post Load Validation | 3h | April 21, 2026 4:00 | April 22, 2026 10:00 | 483 | 5
485 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Serial Numbers | 1.13d | April 21, 2026 9:30 | April 22, 2026 10:30 |  | 4 | 4/17- will cherry pick equiments for testing ITC1/Smoke
486 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 21, 2026 9:30 | April 21, 2026 10:00 | 479 | 5
487 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 21, 2026 10:00 | April 21, 2026 10:30 | 486 | 5
488 | Yes | Auto Scheduled | Simulate Load | 1h | April 21, 2026 10:30 | April 21, 2026 11:30 | 487 | 5
489 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 21, 2026 11:30 | April 21, 2026 2:30 | 488 | 5
490 | Yes | Auto Scheduled | Load | 2h | April 21, 2026 2:30 | April 21, 2026 4:30 | 489 | 5
491 | Yes | Auto Scheduled | Post Load Validation | 3h | April 21, 2026 4:30 | April 22, 2026 10:30 | 490 | 5
492 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Service | 2.06d | April 21, 2026 8:00 | April 23, 2026 8:30 |  | 4 | 4/17- will cherry pick equiments for testing ITC1/Smoke
493 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 22, 2026 10:30 | April 22, 2026 11:00 | 491 | 5
494 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 22, 2026 11:00 | April 22, 2026 11:30 | 493 | 5
495 | Yes | Auto Scheduled | Simulate Load | 1h | April 22, 2026 11:30 | April 22, 2026 1:30 | 494 | 5
496 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 22, 2026 1:30 | April 22, 2026 3:30 | 495 | 5
497 | Yes | Auto Scheduled | Load | 2h | April 22, 2026 3:30 | April 23, 2026 8:30 | 496 | 5
498 | Yes | Auto Scheduled | Post Load Validation | 3h | April 21, 2026 8:00 | April 21, 2026 11:00 |  | 5
499 | Yes | Auto Scheduled | VC_Object Dependencies | 0.63d | April 6, 2026 8:15 | April 6, 2026 2:15 |  | 4
500 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | April 6, 2026 8:15 | April 6, 2026 10:15 | 261 | 5
501 | Yes | Auto Scheduled | Post Load Validation | 3h | April 6, 2026 10:15 | April 6, 2026 2:15 | 500 | 5
502 | Yes | Auto Scheduled | VC_Characteristics | 0.63d | April 6, 2026 2:15 | April 7, 2026 10:15 |  | 4
503 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | April 6, 2026 2:15 | April 6, 2026 4:15 | 501 | 5
504 | Yes | Auto Scheduled | Post Load Validation | 3h | April 6, 2026 4:15 | April 7, 2026 10:15 | 503 | 5
505 | Yes | Auto Scheduled | VC_Classes | 0.63d | April 7, 2026 10:15 | April 7, 2026 4:15 |  | 4
506 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | April 7, 2026 10:15 | April 7, 2026 1:15 | 504 | 5
507 | Yes | Auto Scheduled | Post Load Validation | 3h | April 7, 2026 1:15 | April 7, 2026 4:15 | 506 | 5
508 | Yes | Auto Scheduled | VC_Classification (Class Type 200) | 0.63d | April 15, 2026 3:15 | April 16, 2026 11:15 |  | 4
509 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | April 15, 2026 3:15 | April 16, 2026 8:15 | 428 | 5
510 | Yes | Auto Scheduled | Post Load Validation | 3h | April 16, 2026 8:15 | April 16, 2026 11:15 | 509 | 5
511 | Yes | Auto Scheduled | VC_Dependency Nets | 0.63d | April 15, 2026 3:15 | April 16, 2026 11:15 |  | 4
512 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | April 15, 2026 3:15 | April 16, 2026 8:15 | 507,422 | 5
513 | Yes | Auto Scheduled | Post Load Validation | 3h | April 16, 2026 8:15 | April 16, 2026 11:15 | 512 | 5
514 | Yes | Auto Scheduled | VC_Configuration Profiles | 0.63d | April 15, 2026 3:15 | April 16, 2026 11:15 |  | 4
515 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | April 15, 2026 3:15 | April 16, 2026 8:15 | 422 | 5
516 | Yes | Auto Scheduled | Post Load Validation | 3h | April 16, 2026 8:15 | April 16, 2026 11:15 | 515 | 5
517 | Yes | Auto Scheduled | VC_Variant Tables | 0.63d | April 16, 2026 11:15 | April 17, 2026 8:15 |  | 4
518 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | April 16, 2026 11:15 | April 16, 2026 2:15 | 516 | 5
519 | Yes | Auto Scheduled | Post Load Validation | 3h | April 16, 2026 2:15 | April 17, 2026 8:15 | 518 | 5
520 | Yes | Auto Scheduled | VC_Variant Tables Content | 0.63d | April 17, 2026 8:15 | April 17, 2026 2:15 |  | 4
521 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | April 17, 2026 8:15 | April 17, 2026 10:15 | 519 | 5
522 | Yes | Auto Scheduled | Post Load Validation | 3h | April 17, 2026 10:15 | April 17, 2026 2:15 | 521 | 5
523 | Yes | Auto Scheduled | VC_Characteristic Groups | 1.97d | April 17, 2026 8:00 | April 20, 2026 4:45 |  | 4 | 4/20- Defect - 963
524 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 12.75h | April 17, 2026 8:00 | April 20, 2026 1:45 | 516 | 5 | 4/17 - Authorization error/loaded but getting in app is issue. 4/20 Defect recorded and still open
525 | Yes | Auto Scheduled | Post Load Validation | 3h | April 20, 2026 1:45 | April 20, 2026 4:45 | 524 | 5
526 | Yes | Auto Scheduled | PTM_CM52_Super_BOM | 4.09d | April 15, 2026 3:15 | April 21, 2026 4:00 |  | 4 | 4/21- Pittsburg was loaded and working on remaining sites 4/20 - Working through errors with materials
527 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 15, 2026 3:15 | April 15, 2026 3:45 | 428 | 5
528 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 15, 2026 3:45 | April 15, 2026 4:15 | 527 | 5
529 | Yes | Auto Scheduled | Simulate Load | 24.75h | April 15, 2026 4:15 | April 20, 2026 5:00 | 528 | 5 | 4/17 - Have issues and Manoj to work with Chip
530 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 21, 2026 8:00 | April 21, 2026 10:00 | 529 | 5 | 4/16- Reviewing some errors , 4/17- Still running into errors
531 | Yes | Auto Scheduled | Load | 2h | April 21, 2026 10:00 | April 21, 2026 12:00 | 530 | 5
532 | Yes | Auto Scheduled | Post Load Validation | 3h | April 21, 2026 1:00 | April 21, 2026 4:00 | 531 | 5
533 | Yes | Auto Scheduled | PTM_CM53_Super_Routing | 2d | April 16, 2026 8:00 | April 17, 2026 5:00 |  | 4
534 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 16, 2026 4:15 | April 16, 2026 4:45 | 532 | 5
535 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 16, 2026 4:45 | April 17, 2026 8:15 | 534 | 5
536 | Yes | Auto Scheduled | Simulate Load | 1h | April 16, 2026 8:00 | April 17, 2026 9:00 | 535 | 5
537 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 17, 2026 9:00 | April 17, 2026 11:00 | 536 | 5
538 | Yes | Auto Scheduled | Load | 2h | April 17, 2026 11:00 | April 17, 2026 2:00 | 537 | 5
539 | Yes | Auto Scheduled | Post Load Validation | 3h | April 17, 2026 2:00 | April 17, 2026 5:00 | 538 | 5 | 4/22 -Loaded for Pittsburg
540 | Yes | Auto Scheduled | VC_VK30 Pricing Variant | 0.38d | April 16, 2026 8:00 | April 16, 2026 11:00 |  | 4
541 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | April 16, 2026 8:00 | April 16, 2026 8:30 | 538 | 5
542 | Yes | Auto Scheduled | Load | 2h | April 16, 2026 8:00 | April 16, 2026 10:00 | 541 | 5
543 | Yes | Auto Scheduled | Post Load Validation | 3h | April 16, 2026 8:00 | April 16, 2026 11:00 | 542 | 5
544 | Yes | Auto Scheduled | OTC_CM22_Pricing_Condition | 1.38d | April 15, 2026 8:00 | April 16, 2026 11:00 |  | 4
545 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | April 15, 2026 8:00 | April 15, 2026 8:30 | 543 | 5
546 | Yes | Auto Scheduled | Load | 2h | April 15, 2026 8:00 | April 15, 2026 10:00 | 545 | 5
547 | Yes | Auto Scheduled | Post Load Validation | 3h | April 16, 2026 8:00 | April 16, 2026 11:00 | 546 | 5 | 4/16 - Service to load
548 | Yes | Auto Scheduled | OTC_CM21_CMIR | 2.72d | April 16, 2026 8:00 | April 20, 2026 2:45 |  | 4
549 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 20, 2026 2:15 | April 20, 2026 2:45 | 546,557 | 5
550 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 16, 2026 8:00 | April 16, 2026 8:30 | 549 | 5
551 | Yes | Auto Scheduled | Simulate Load | 0h | April 16, 2026 8:00 | April 16, 2026 8:00 | 550 | 5
552 | Yes | Auto Scheduled | Error and Defect Mitigation | 0h | April 16, 2026 8:00 | April 16, 2026 8:00 | 551 | 5
553 | Yes | Auto Scheduled | Load | 0h | April 16, 2026 8:00 | April 16, 2026 8:00 | 552 | 5 | 4/16 - Load done
554 | Yes | Auto Scheduled | Post Load Validation | 3h | April 16, 2026 8:00 | April 16, 2026 11:00 | 553 | 5
555 | Yes | Auto Scheduled | PTP_CM29_Source_List | 1.41d | April 17, 2026 8:00 | April 20, 2026 11:15 |  | 4
556 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | April 17, 2026 8:00 | April 17, 2026 8:30 | 399,406 | 5 | 4/16 -
557 | Yes | Auto Scheduled | Load | 2h | April 17, 2026 3:15 | April 20, 2026 8:15 | 375 | 5
558 | Yes | Auto Scheduled | Post Load Validation | 3h | April 20, 2026 8:15 | April 20, 2026 11:15 | 557 | 5
559 | Yes | Auto Scheduled | RTR_CM11_Asset_Master | 6.63d | April 15, 2026 8:00 | April 23, 2026 2:00 |  | 4 | 4/20- Move to ITC2
560 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 15, 2026 8:00 | April 15, 2026 8:30 |  | 5
561 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 15, 2026 8:30 | April 15, 2026 9:00 | 560 | 5
562 | Yes | Auto Scheduled | Simulate Load | 31h | April 15, 2026 9:00 | April 20, 2026 5:00 | 561 | 5 | 4/17 - Going back and forth
563 | Yes | Auto Scheduled | Error and Defect Mitigation | 16h | April 21, 2026 8:00 | April 22, 2026 5:00 | 562 | 5
564 | Yes | Auto Scheduled | Load | 2h | April 23, 2026 8:00 | April 23, 2026 10:00 | 563 | 5
565 | Yes | Auto Scheduled | Post Load Validation | 3h | April 23, 2026 10:00 | April 23, 2026 2:00 | 564 | 5
566 | Yes | Auto Scheduled | PTM_CM50_Material Class | 2.66d | April 16, 2026 10:45 | April 20, 2026 5:00 |  | 4
567 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | April 16, 2026 10:45 | April 16, 2026 11:15 | 472 | 5
568 | Yes | Auto Scheduled | Load | 30m | April 16, 2026 11:15 | April 16, 2026 11:45 | 567 | 5 | 4/17 -Manually loaded
569 | Yes | Auto Scheduled | Post Load Validation | 16h | April 17, 2026 8:00 | April 20, 2026 5:00 | 568 | 5 | 4/16 - Will load manually
570 | Yes | Auto Scheduled | PTM_CM55_Class assignment to materials | 1.13d | April 16, 2026 11:15 | April 17, 2026 1:15 |  | 4 | 4/16 - Is not being loaded part of ITC1
571 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 16, 2026 11:15 | April 16, 2026 11:45 | 567 | 5
572 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 16, 2026 11:45 | April 16, 2026 1:15 | 571 | 5
573 | Yes | Auto Scheduled | Simulate Load | 1h | April 16, 2026 1:15 | April 16, 2026 2:15 | 572 | 5
574 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 16, 2026 2:15 | April 16, 2026 4:15 | 573 | 5
575 | Yes | Auto Scheduled | Load | 2h | April 16, 2026 4:15 | April 17, 2026 9:15 | 574 | 5
576 | Yes | Auto Scheduled | Post Load Validation | 3h | April 17, 2026 9:15 | April 17, 2026 1:15 | 575 | 5
577 | Yes | Auto Scheduled | GTS - Material initial load from S4 (Run Interface) | 2.09d | April 16, 2026 8:15 | April 20, 2026 9:00 |  | 4
578 | Yes | Auto Scheduled | Run material interface to GTS | 15.75h | April 16, 2026 8:15 | April 17, 2026 5:00 | 446 | 5
579 | Yes | Auto Scheduled | Post Load Validation | 1h | April 20, 2026 8:00 | April 20, 2026 9:00 | 578 | 5
580 | Yes | Auto Scheduled | GTS - Customers initial load from S4 (Run Interface) | 4d | April 15, 2026 8:00 | April 20, 2026 5:00 |  | 4
581 | Yes | Auto Scheduled | Run material interface to GTS | 1h | April 15, 2026 8:00 | April 15, 2026 9:00 |  | 5
582 | Yes | Auto Scheduled | Post Load Validation | 1h | April 20, 2026 4:00 | April 20, 2026 5:00 | 581 | 5 | 4/17 99% complete ran in to some erros with defect 934
583 | Yes | Auto Scheduled | GTS - Vendors initial load from S4 (Run Interface) | 0.25d | April 16, 2026 4:00 | April 17, 2026 9:00 |  | 4
584 | Yes | Auto Scheduled | Run material interface to GTS | 1h | April 16, 2026 4:00 | April 16, 2026 5:00 | 389 | 5 | 4/16- Have 3 records with issues
585 | Yes | Auto Scheduled | Post Load Validation | 1h | April 17, 2026 8:00 | April 17, 2026 9:00 | 584 | 5
586 | Yes | Auto Scheduled | GTS - ECCN - Create | 5.63d | April 6, 2026 8:15 | April 13, 2026 2:15 |  | 4
587 | Yes | Auto Scheduled | Load Descartes XML File | 1h | April 6, 2026 8:15 | April 6, 2026 9:15 | 261 | 5
588 | Yes | Auto Scheduled | Post Load Validation | 1h | April 13, 2026 1:15 | April 13, 2026 2:15 | 584 | 5
589 | Yes | Auto Scheduled | GTS - ECCN - Assign | 0.25d | April 16, 2026 10:15 | April 16, 2026 1:15 |  | 4
590 | Yes | Auto Scheduled | Load Descartes XML File | 1h | April 16, 2026 10:15 | April 16, 2026 11:15 | 579 | 5
591 | Yes | Auto Scheduled | Post Load Validation | 1h | April 16, 2026 11:15 | April 16, 2026 1:15 | 590 | 5
592 | Yes | Auto Scheduled | GTS - HTS - Create | 0.25d | April 6, 2026 8:15 | April 6, 2026 10:15 |  | 4
593 | Yes | Auto Scheduled | Load Descartes XML File | 1h | April 6, 2026 8:15 | April 6, 2026 9:15 | 261 | 5
594 | Yes | Auto Scheduled | Post Load Validation | 1h | April 6, 2026 9:15 | April 6, 2026 10:15 | 593 | 5
595 | Yes | Auto Scheduled | GTS - HTS - Assign | 0.25d | April 16, 2026 8:45 | April 16, 2026 10:45 |  | 4
596 | Yes | Auto Scheduled | Load Descartes XML File | 1h | April 16, 2026 8:45 | April 16, 2026 9:45 | 591 | 5
597 | Yes | Auto Scheduled | Post Load Validation | 1h | April 16, 2026 9:45 | April 16, 2026 10:45 | 596 | 5
598 | Yes | Auto Scheduled | GTS - License - Create | 0.25d | April 16, 2026 11:45 | April 16, 2026 2:45 |  | 4
599 | Yes | Auto Scheduled | Load Descartes XML File | 1h | April 16, 2026 11:45 | April 16, 2026 1:45 | 596,612 | 5 | 4/13 - Need to update dep.
600 | Yes | Auto Scheduled | Post Load Validation | 1h | April 16, 2026 1:45 | April 16, 2026 2:45 | 599 | 5
601 | Yes | Auto Scheduled | Commodity Code/Tarif | 2.78d | April 16, 2026 10:45 | April 21, 2026 9:00 |  | 4
602 | Yes | Auto Scheduled | Load | 21.25h | April 16, 2026 10:45 | April 20, 2026 5:00 | 597 | 5 | 4/17- wants to use the old load program
603 | Yes | Auto Scheduled | Post Load Validation | 1h | April 21, 2026 8:00 | April 21, 2026 9:00 | 602 | 5
604 | Yes | Auto Scheduled | SPL Master File | 1.34d | April 15, 2026 8:00 | April 16, 2026 10:45 |  | 4
605 | Yes | Auto Scheduled | Load | 1h | April 16, 2026 9:45 | April 16, 2026 10:45 | 596 | 5
606 | Yes | Auto Scheduled | Post Load Validation | 1h | April 15, 2026 8:00 | April 15, 2026 9:00 | 605 | 5
607 | Yes | Auto Scheduled | Initialize Embargo situation | 0.59d | April 13, 2026 2:15 | April 14, 2026 10:00 |  | 4
608 | Yes | Auto Scheduled | Run report /SAPSLL/EMB_CNTRY_INIT | 1h | April 13, 2026 2:15 | April 13, 2026 3:15 | 588 | 5
609 | Yes | Auto Scheduled | Set Embargo situations | 1h | April 14, 2026 8:00 | April 14, 2026 9:00 | 608 | 5 | 4/17 - Needs access
610 | Yes | Auto Scheduled | Post Load Validation | 1h | April 14, 2026 9:00 | April 14, 2026 10:00 | 609 | 5
611 | Yes | Auto Scheduled | GTS - SPL (Sanctioned party list) | 0.25d | April 16, 2026 10:45 | April 16, 2026 1:45 |  | 4
612 | Yes | Auto Scheduled | Load Descartes XML File | 1h | April 16, 2026 10:45 | April 16, 2026 11:45 | 597 | 5
613 | Yes | Auto Scheduled | Post Load Validation | 1h | April 16, 2026 11:45 | April 16, 2026 1:45 | 612 | 5
614 | Yes | Auto Scheduled | RTR_CM17_Project Definition / Builder | 1.13d | April 20, 2026 8:00 | April 21, 2026 9:00 |  | 4 | 4/20 - Will have files to load in the morning
615 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 20, 2026 8:00 | April 20, 2026 8:30 | 560 | 5
616 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 20, 2026 8:30 | April 20, 2026 9:00 | 615 | 5
617 | Yes | Auto Scheduled | Simulate Load | 1h | April 20, 2026 9:00 | April 20, 2026 10:00 | 616 | 5
618 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 20, 2026 10:00 | April 20, 2026 12:00 | 617 | 5
619 | Yes | Auto Scheduled | Load | 2h | April 20, 2026 1:00 | April 20, 2026 3:00 | 618 | 5
620 | Yes | Auto Scheduled | Post Load Validation | 3h | April 20, 2026 3:00 | April 21, 2026 9:00 | 619 | 5
621 | Yes | Auto Scheduled | RTR_CM18_WBS Element | 1.13d | April 20, 2026 8:30 | April 21, 2026 9:30 |  | 4
622 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | April 20, 2026 8:30 | April 20, 2026 9:00 | 615 | 5
623 | Yes | Auto Scheduled | Pre Load Validation | 30m | April 20, 2026 9:00 | April 20, 2026 9:30 | 622 | 5
624 | Yes | Auto Scheduled | Simulate Load | 1h | April 20, 2026 9:30 | April 20, 2026 10:30 | 623 | 5
625 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | April 20, 2026 10:30 | April 20, 2026 1:30 | 624 | 5
626 | Yes | Auto Scheduled | Load | 2h | April 20, 2026 1:30 | April 20, 2026 3:30 | 625 | 5
627 | Yes | Auto Scheduled | Post Load Validation | 3h | April 20, 2026 3:30 | April 21, 2026 9:30 | 626 | 5
628 | Yes | Auto Scheduled | ITC1 Mock Data Loads Complete | 15m | April 23, 2026 2:00 | April 23, 2026 2:15 |  | 4
629 | Yes | Auto Scheduled | ITC2 Data Load Tasks QS4 | 105.63d | May 18, 2026 8:00 | October 12, 2026 2:00 | 260,41 | 3
630 | Yes | Auto Scheduled | PMO Authorization to Start Data Loads | 2h | May 18, 2026 8:00 | May 18, 2026 10:00 | 41 | 4
631 | Yes | Auto Scheduled | Master Data Loads | 9.63d | May 18, 2026 10:00 | May 29, 2026 4:00 | 630 | 4
632 | Yes | Auto Scheduled | RTR_CM02_Profit Center Hierarchy | 0.75d | May 18, 2026 10:00 | May 18, 2026 5:00 |  | 5
633 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | May 18, 2026 10:00 | May 18, 2026 11:00 |  | 6
634 | Yes | Auto Scheduled | Load | 2h | May 18, 2026 11:00 | May 18, 2026 2:00 | 633 | 6
635 | Yes | Auto Scheduled | Post Load Validation | 3h | May 18, 2026 2:00 | May 18, 2026 5:00 | 634 | 6
636 | Yes | Auto Scheduled | RTR_CM03_Cost Center Hierarchy | 0.75d | May 19, 2026 8:00 | May 19, 2026 3:00 |  | 5
637 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | May 19, 2026 8:00 | May 19, 2026 9:00 | 635 | 6
638 | Yes | Auto Scheduled | Load | 2h | May 19, 2026 9:00 | May 19, 2026 11:00 | 637 | 6
639 | Yes | Auto Scheduled | Post Load Validation | 3h | May 19, 2026 11:00 | May 19, 2026 3:00 | 638 | 6
640 | Yes | Auto Scheduled | RTR_CM01_GL_Account_Master to CC 1000 | 2.44d | May 19, 2026 3:00 | May 22, 2026 9:30 |  | 5
641 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | May 19, 2026 3:00 | May 19, 2026 4:00 | 639 | 6
642 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 19, 2026 4:00 | May 20, 2026 9:00 | 641 | 6
643 | Yes | Auto Scheduled | Simulate Load | 6h | May 20, 2026 9:00 | May 20, 2026 4:00 | 642 | 6
644 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 20, 2026 4:00 | May 21, 2026 10:30 | 643 | 6
645 | Yes | Auto Scheduled | Load | 1h | May 21, 2026 10:30 | May 21, 2026 11:30 | 644 | 6
646 | Yes | Auto Scheduled | Post Load Validation | 2h | May 21, 2026 11:30 | May 21, 2026 2:30 | 645 | 6
647 | Yes | Auto Scheduled | Extend GL to all Company Codes | 2h | May 21, 2026 2:30 | May 21, 2026 4:30 | 646 | 6
648 | Yes | Auto Scheduled | Post GL Extention Validation | 2h | May 21, 2026 4:30 | May 22, 2026 9:30 | 647 | 6
649 | Yes | Auto Scheduled | RTR_CM05_Profit_Center | 1.13d | May 19, 2026 8:00 | May 20, 2026 9:00 |  | 5
650 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | May 19, 2026 8:00 | May 19, 2026 9:00 | 635 | 6
651 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 19, 2026 9:00 | May 19, 2026 11:00 | 650 | 6
652 | Yes | Auto Scheduled | Simulate Load | 1h | May 19, 2026 11:00 | May 19, 2026 12:00 | 651 | 6
653 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 19, 2026 1:00 | May 19, 2026 3:00 | 652 | 6
654 | Yes | Auto Scheduled | Load | 1h | May 19, 2026 3:00 | May 19, 2026 4:00 | 653 | 6
655 | Yes | Auto Scheduled | Post Load Validation | 2h | May 19, 2026 4:00 | May 20, 2026 9:00 | 654 | 6
656 | Yes | Auto Scheduled | RTR_CM04_Cost_Center | 1.13d | May 20, 2026 9:00 | May 21, 2026 10:00 |  | 5
657 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | May 20, 2026 9:00 | May 20, 2026 10:00 | 655 | 6
658 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 20, 2026 10:00 | May 20, 2026 12:00 | 657 | 6
659 | Yes | Auto Scheduled | Simulate Load | 1h | May 20, 2026 1:00 | May 20, 2026 2:00 | 658 | 6
660 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 20, 2026 2:00 | May 20, 2026 4:00 | 659 | 6
661 | Yes | Auto Scheduled | Load | 1h | May 20, 2026 4:00 | May 20, 2026 5:00 | 660 | 6
662 | Yes | Auto Scheduled | Post Load Validation | 2h | May 21, 2026 8:00 | May 21, 2026 10:00 | 661 | 6
663 | Yes | Auto Scheduled | Manual Configuration Activities in QS5 | 5.94d | May 21, 2026 10:00 | May 29, 2026 9:30 | 656 | 5
664 | Yes | Auto Scheduled | Open Client | 30m | May 21, 2026 10:00 | May 21, 2026 10:30 |  | 6
665 | Yes | Auto Scheduled | Service Enterprise Setup | 5d | May 22, 2026 9:30 | May 29, 2026 9:30 | 632,636,640 | 6
666 | Yes | Auto Scheduled | Close Client | 30m | May 21, 2026 10:00 | May 21, 2026 10:30 |  | 6
667 | Yes | Auto Scheduled | Intercompany Business Partner Setup | 2h | May 22, 2026 9:30 | May 22, 2026 11:30 | 632,636,648 | 6
668 | Yes | Auto Scheduled | RTR_CM09_Activity_Type | 1.38d | May 21, 2026 2:30 | May 25, 2026 8:30 |  | 5
669 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | May 21, 2026 2:30 | May 21, 2026 4:45 | 646 | 6
670 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 21, 2026 4:45 | May 22, 2026 10:30 | 669 | 6
671 | Yes | Auto Scheduled | Simulate Load | 1h | May 22, 2026 10:30 | May 22, 2026 11:30 | 670 | 6
672 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 22, 2026 11:30 | May 22, 2026 2:30 | 671 | 6
673 | Yes | Auto Scheduled | Load | 1h | May 22, 2026 2:30 | May 22, 2026 3:30 | 672 | 6
674 | Yes | Auto Scheduled | Post Load Validation | 2h | May 22, 2026 3:30 | May 25, 2026 8:30 | 673 | 6
675 | Yes | Auto Scheduled | RTR_CM12_Activity Rates | 1.13d | May 19, 2026 3:00 | May 20, 2026 4:00 |  | 5
676 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | May 19, 2026 3:00 | May 19, 2026 4:00 | 639 | 6
677 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 19, 2026 4:00 | May 20, 2026 9:00 | 676 | 6
678 | Yes | Auto Scheduled | Simulate Load | 1h | May 20, 2026 9:00 | May 20, 2026 10:00 | 677 | 6
679 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 20, 2026 10:00 | May 20, 2026 12:00 | 678 | 6
680 | Yes | Auto Scheduled | Load | 1h | May 20, 2026 1:00 | May 20, 2026 2:00 | 679 | 6
681 | Yes | Auto Scheduled | Post Load Validation | 2h | May 20, 2026 2:00 | May 20, 2026 4:00 | 680 | 6
682 | Yes | Auto Scheduled | RTR_CM06_Bank_master | 3.81d | May 18, 2026 10:00 | May 22, 2026 8:30 |  | 5
683 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | May 21, 2026 2:30 | May 21, 2026 3:30 | 646 | 6
684 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 21, 2026 3:30 | May 22, 2026 8:30 | 683 | 6
685 | Yes | Auto Scheduled | Simulate Load | 1h | May 18, 2026 10:00 | May 18, 2026 11:00 |  | 6
686 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 18, 2026 11:00 | May 18, 2026 2:00 | 685 | 6
687 | Yes | Auto Scheduled | Load | 5h | May 18, 2026 2:00 | May 19, 2026 10:00 | 686 | 6
688 | Yes | Auto Scheduled | Post Load Validation | 2h | May 19, 2026 10:00 | May 19, 2026 4:30 | 687 | 6
689 | Yes | Auto Scheduled | RTR_CM08_Exchange_Rates | 1.13d | May 19, 2026 10:00 | May 20, 2026 11:00 |  | 5
690 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | May 19, 2026 10:00 | May 19, 2026 11:00 | 687 | 6
691 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 19, 2026 11:00 | May 19, 2026 2:00 | 690 | 6
692 | Yes | Auto Scheduled | Simulate Load | 1h | May 19, 2026 2:00 | May 19, 2026 3:00 | 691 | 6
693 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 19, 2026 3:00 | May 19, 2026 5:00 | 692 | 6
694 | Yes | Auto Scheduled | Load | 1h | May 20, 2026 8:00 | May 20, 2026 9:00 | 693 | 6
695 | Yes | Auto Scheduled | Post Load Validation | 2h | May 20, 2026 9:00 | May 20, 2026 11:00 | 694 | 6
696 | Yes | Auto Scheduled | RTR_CM14_Cost Element_Group | 1.44d | May 21, 2026 2:30 | May 25, 2026 9:00 |  | 5
697 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | May 21, 2026 2:30 | May 21, 2026 3:00 | 646 | 6
698 | Yes | Auto Scheduled | Load | 8h | May 21, 2026 3:00 | May 22, 2026 3:00 | 697 | 6
699 | Yes | Auto Scheduled | Post Load Validation | 3h | May 22, 2026 3:00 | May 25, 2026 9:00 | 698 | 6
700 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Bill-To | 2h | May 18, 2026 10:00 | May 18, 2026 12:00 |  | 5 | 4/20 Per OTC this is not needed for ITC1
701 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Ship-To | 1.5d | May 21, 2026 2:30 | May 25, 2026 9:30 |  | 5
702 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 21, 2026 2:30 | May 21, 2026 3:00 | 646 | 6
703 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 21, 2026 3:00 | May 21, 2026 3:30 | 702 | 6
704 | Yes | Auto Scheduled | Open client for BP number range update | 30m | May 21, 2026 3:30 | May 21, 2026 4:00 | 703 | 6
705 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 30m | May 21, 2026 4:00 | May 21, 2026 4:30 | 704 | 6
706 | Yes | Auto Scheduled | Close Client | 15m | May 21, 2026 4:30 | May 21, 2026 4:45 | 705 | 6
707 | Yes | Auto Scheduled | Simulate Load | 1h | May 21, 2026 3:30 | May 21, 2026 4:30 | 703 | 6
708 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | May 21, 2026 4:30 | May 22, 2026 11:30 | 707 | 6
709 | Yes | Auto Scheduled | Load | 3h | May 22, 2026 11:30 | May 22, 2026 3:30 | 708 | 6
710 | Yes | Auto Scheduled | Post Load Validation | 3h | May 22, 2026 3:30 | May 25, 2026 9:30 | 709 | 6
711 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Sold-To | 1.63d | May 21, 2026 3:30 | May 25, 2026 11:30 |  | 5
712 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 21, 2026 3:30 | May 21, 2026 4:00 | 703 | 6
713 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 21, 2026 4:00 | May 21, 2026 4:30 | 712 | 6
714 | Yes | Auto Scheduled | Simulate Load | 1h | May 22, 2026 9:30 | May 22, 2026 10:30 | 648,707 | 6
715 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | May 22, 2026 10:30 | May 22, 2026 2:30 | 714 | 6
716 | Yes | Auto Scheduled | Load | 3h | May 22, 2026 2:30 | May 25, 2026 8:30 | 715 | 6
717 | Yes | Auto Scheduled | Post Load Validation | 3h | May 25, 2026 8:30 | May 25, 2026 11:30 | 716 | 6
718 | Yes | Auto Scheduled | Open client for BP number range update | 15m | May 21, 2026 4:30 | May 21, 2026 4:45 | 707 | 6
719 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 15m | May 21, 2026 4:45 | May 21, 2026 5:00 | 718 | 6
720 | Yes | Auto Scheduled | Close Client | 15m | May 22, 2026 8:00 | May 22, 2026 8:15 | 719 | 6
721 | Yes | Auto Scheduled | PTP_CM27_Vendor Master as Customer - FLCU01 | 4.81d | May 25, 2026 8:30 | May 29, 2026 4:00 |  | 5
722 | Yes | Auto Scheduled | Extract File | 1h | May 25, 2026 8:30 | May 25, 2026 9:30 | 716 | 6
723 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 25, 2026 9:30 | May 25, 2026 11:30 | 722 | 6
724 | Yes | Auto Scheduled | Simulate Load | 11.25h | May 25, 2026 11:30 | May 26, 2026 3:45 | 688,723 | 6
725 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 26, 2026 3:45 | May 28, 2026 10:30 | 724 | 6
726 | Yes | Auto Scheduled | Load | 1h | May 28, 2026 10:30 | May 29, 2026 2:00 | 725 | 6
727 | Yes | Auto Scheduled | Post Load Validation | 2h | May 29, 2026 2:00 | May 29, 2026 4:00 | 726 | 6
728 | Yes | Auto Scheduled | OTC_CM23_Customer_Hierarchy | 0.69d | May 25, 2026 8:30 | May 25, 2026 3:00 |  | 5
729 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | May 25, 2026 8:30 | May 25, 2026 9:00 | 716 | 6
730 | Yes | Auto Scheduled | Load | 2h | May 25, 2026 9:00 | May 25, 2026 11:00 | 729 | 6
731 | Yes | Auto Scheduled | Post Load Validation | 3h | May 25, 2026 11:00 | May 25, 2026 3:00 | 730 | 6
732 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Z001 - External Sales Rep | 3.38d | May 25, 2026 8:30 | May 28, 2026 11:30 |  | 5
733 | Yes | Auto Scheduled | Extract File | 1h | May 25, 2026 8:30 | May 25, 2026 9:30 | 716 | 6
734 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 25, 2026 9:30 | May 25, 2026 11:30 | 733 | 6
735 | Yes | Auto Scheduled | Simulate Load | 1h | May 25, 2026 11:30 | May 25, 2026 1:30 | 688,734 | 6
736 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 25, 2026 1:30 | May 25, 2026 3:30 | 735 | 6
737 | Yes | Auto Scheduled | Load | 1h | May 25, 2026 3:30 | May 28, 2026 9:30 | 736 | 6
738 | Yes | Auto Scheduled | Post Load Validation | 2h | May 28, 2026 9:30 | May 28, 2026 11:30 | 737 | 6
739 | Yes | Auto Scheduled | RTR_CM10_Credit_Management_Role | 1.84d | May 25, 2026 8:30 | May 26, 2026 4:15 |  | 5
740 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 25, 2026 8:30 | May 25, 2026 9:00 | 716 | 6
741 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 25, 2026 9:00 | May 25, 2026 9:30 | 740 | 6
742 | Yes | Auto Scheduled | Simulate Load | 1h | May 25, 2026 9:30 | May 25, 2026 10:30 | 741 | 6 | 4/16 - Asked to reload per Brian
743 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 25, 2026 10:30 | May 25, 2026 2:00 | 742 | 6
744 | Yes | Auto Scheduled | Load | 2h | May 25, 2026 2:00 | May 26, 2026 9:00 | 743 | 6
745 | Yes | Auto Scheduled | Post Load Validation | 3h | May 26, 2026 9:00 | May 26, 2026 4:15 | 744 | 6 | 4/17 - Error on load,resolution identifed, Def899,Will manually change customer for IT1
746 | Yes | Auto Scheduled | PTP_CM27_Vendor Master | 6.28d | May 18, 2026 10:00 | May 26, 2026 1:15 |  | 5
747 | Yes | Auto Scheduled | Extract File | 1h | May 25, 2026 9:30 | May 25, 2026 10:30 | 733 | 6
748 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 25, 2026 10:30 | May 25, 2026 1:30 | 747 | 6
749 | Yes | Auto Scheduled | Simulate Load | 2.25h | May 25, 2026 1:30 | May 25, 2026 3:45 | 748 | 6 | First time simulation on 4/13
750 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 25, 2026 3:45 | May 26, 2026 1:15 | 749 | 6 | 4/14 - Ran into more errors and Manoj will follow up ib 2hrs....
751 | Yes | Auto Scheduled | Load | 1h | May 18, 2026 10:00 | May 18, 2026 11:00 |  | 6
752 | Yes | Auto Scheduled | Post Load Validation | 2h | May 18, 2026 11:00 | May 18, 2026 2:00 | 751 | 6 | 4/14 PTP Is complete
753 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | 0.88d | May 18, 2026 10:00 | May 19, 2026 9:00 |  | 5
754 | Yes | Auto Scheduled | Extract File(Will Extract from LFA1) | 1h | May 18, 2026 10:00 | May 18, 2026 11:00 |  | 6
755 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 18, 2026 11:00 | May 18, 2026 2:00 | 754 | 6
756 | Yes | Auto Scheduled | Simulate Load/ Not Needed | 1h | May 18, 2026 2:00 | May 18, 2026 3:00 | 755 | 6
757 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 18, 2026 3:00 | May 18, 2026 5:00 | 756 | 6 | 4/16 - Defect created no impact to ITC1
758 | Yes | Auto Scheduled | Load | 1h | May 18, 2026 3:00 | May 18, 2026 4:00 | 756 | 6
759 | Yes | Auto Scheduled | Post Load Validation | 2h | May 18, 2026 4:00 | May 19, 2026 9:00 | 758 | 6
760 | Yes | Auto Scheduled | RTR_****_Credit Hierarchy | 1.91d | May 25, 2026 2:00 | May 27, 2026 1:15 |  | 5
761 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | May 25, 2026 2:00 | May 25, 2026 2:30 | 743 | 6 | 4/16 -Completed
762 | Yes | Auto Scheduled | Load | 2h | May 26, 2026 4:15 | May 27, 2026 9:15 | 745 | 6
763 | Yes | Auto Scheduled | Post Load Validation | 3h | May 27, 2026 9:15 | May 27, 2026 1:15 | 762 | 6
764 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Supplier | 1.13d | May 18, 2026 2:00 | May 19, 2026 3:00 |  | 5
765 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 18, 2026 2:00 | May 18, 2026 2:30 | 752 | 6
766 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 18, 2026 2:30 | May 18, 2026 3:00 | 765 | 6
767 | Yes | Auto Scheduled | Simulate Load | 1h | May 18, 2026 3:00 | May 18, 2026 4:00 | 766 | 6
768 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 18, 2026 4:00 | May 19, 2026 9:00 | 767 | 6
769 | Yes | Auto Scheduled | Load | 2h | May 19, 2026 9:00 | May 19, 2026 11:00 | 768 | 6
770 | Yes | Auto Scheduled | Post Load Validation | 3h | May 19, 2026 11:00 | May 19, 2026 3:00 | 769 | 6
771 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Customer | 1.06d | May 18, 2026 10:00 | May 19, 2026 10:30 |  | 5
772 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 18, 2026 10:00 | May 18, 2026 10:30 |  | 6
773 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 18, 2026 10:00 | May 18, 2026 10:30 |  | 6
774 | Yes | Auto Scheduled | Simulate Load | 1h | May 18, 2026 10:30 | May 18, 2026 11:30 | 773 | 6
775 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 18, 2026 11:30 | May 18, 2026 2:30 | 774 | 6
776 | Yes | Auto Scheduled | Load | 2h | May 18, 2026 2:30 | May 18, 2026 4:30 | 775 | 6
777 | Yes | Auto Scheduled | Post Load Validation | 3h | May 18, 2026 4:30 | May 19, 2026 10:30 | 776 | 6
778 | Yes | Auto Scheduled | PTP_CM26_Material_Master - All Types | 2.28d | May 18, 2026 11:00 | May 20, 2026 2:15 |  | 5
779 | Yes | Auto Scheduled | Extract File | 5h | May 18, 2026 11:00 | May 19, 2026 9:45 | 754 | 6
780 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 18, 2026 2:00 | May 19, 2026 11:15 | 752 | 6
781 | Yes | Auto Scheduled | Simulate Load | 1h | May 19, 2026 11:15 | May 19, 2026 1:15 | 780 | 6
782 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | May 19, 2026 1:15 | May 20, 2026 8:15 | 781 | 6
783 | Yes | Auto Scheduled | Load | 3h | May 20, 2026 8:15 | May 20, 2026 11:15 | 782 | 6
784 | Yes | Auto Scheduled | Post Load Validation | 2h | May 20, 2026 11:15 | May 20, 2026 2:15 | 783 | 6
785 | Yes | Auto Scheduled | PTP_CM26_Material_Master - SERV - Service Materials | 1.34d | May 20, 2026 9:00 | May 21, 2026 11:45 |  | 5
786 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 20, 2026 9:00 | May 20, 2026 9:30 | 655 | 6
787 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 20, 2026 11:15 | May 20, 2026 11:45 | 783 | 6
788 | Yes | Auto Scheduled | Simulate Load | 1h | May 20, 2026 11:45 | May 20, 2026 1:45 | 787 | 6
789 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 20, 2026 1:45 | May 20, 2026 3:45 | 788 | 6
790 | Yes | Auto Scheduled | Load | 2h | May 20, 2026 3:45 | May 21, 2026 8:45 | 789 | 6
791 | Yes | Auto Scheduled | Post Load Validation | 3h | May 21, 2026 8:45 | May 21, 2026 11:45 | 790 | 6
792 | Yes | Auto Scheduled | PTP_CM26_Material_Master - KMAT - Configurable Materials | 1.34d | May 20, 2026 9:00 | May 21, 2026 11:45 |  | 5
793 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 20, 2026 9:00 | May 20, 2026 9:30 | 655 | 6
794 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 20, 2026 11:15 | May 20, 2026 11:45 | 783 | 6
795 | Yes | Auto Scheduled | Simulate Load | 1h | May 20, 2026 11:45 | May 20, 2026 1:45 | 794 | 6
796 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 20, 2026 1:45 | May 20, 2026 3:45 | 795 | 6
797 | Yes | Auto Scheduled | Load | 2h | May 20, 2026 3:45 | May 21, 2026 8:45 | 796 | 6
798 | Yes | Auto Scheduled | Post Load Validation | 3h | May 21, 2026 8:45 | May 21, 2026 11:45 | 797 | 6
799 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Records | 3.59d | May 18, 2026 2:00 | May 22, 2026 9:45 |  | 5
800 | Yes | Auto Scheduled | Extract File | 1h | May 21, 2026 11:45 | May 21, 2026 1:45 | 784,798 | 6 | 4/16 - Started extract
801 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 21, 2026 1:45 | May 21, 2026 3:45 | 800 | 6
802 | Yes | Auto Scheduled | Simulate Load | 1h | May 21, 2026 3:45 | May 21, 2026 4:45 | 801 | 6
803 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 21, 2026 4:45 | May 22, 2026 9:45 | 802 | 6
804 | Yes | Auto Scheduled | Load | 1h | May 18, 2026 2:00 | May 18, 2026 3:00 | 752 | 6
805 | Yes | Auto Scheduled | Post Load Validation | 2h | May 18, 2026 3:00 | May 18, 2026 5:00 | 804 | 6
806 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record External Processing | 1.13d | May 21, 2026 11:45 | May 22, 2026 1:45 |  | 5
807 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 21, 2026 11:45 | May 21, 2026 1:15 | 784,798 | 6
808 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 21, 2026 1:15 | May 21, 2026 1:45 | 807 | 6
809 | Yes | Auto Scheduled | Simulate Load | 1h | May 21, 2026 1:45 | May 21, 2026 2:45 | 808 | 6
810 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 21, 2026 2:45 | May 21, 2026 4:45 | 809 | 6
811 | Yes | Auto Scheduled | Load | 2h | May 21, 2026 4:45 | May 22, 2026 9:45 | 810 | 6
812 | Yes | Auto Scheduled | Post Load Validation | 3h | May 22, 2026 9:45 | May 22, 2026 1:45 | 811 | 6
813 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | 1.13d | May 21, 2026 11:45 | May 22, 2026 1:45 |  | 5
814 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 21, 2026 11:45 | May 21, 2026 1:15 | 784,798 | 6
815 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 21, 2026 1:15 | May 21, 2026 1:45 | 814 | 6
816 | Yes | Auto Scheduled | Simulate Load | 1h | May 21, 2026 1:45 | May 21, 2026 2:45 | 815 | 6 | 4/16 - Eror
817 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 21, 2026 2:45 | May 21, 2026 4:45 | 816 | 6
818 | Yes | Auto Scheduled | Load | 2h | May 21, 2026 4:45 | May 22, 2026 9:45 | 817 | 6
819 | Yes | Auto Scheduled | Post Load Validation | 3h | May 22, 2026 9:45 | May 22, 2026 1:45 | 818 | 6
820 | Yes | Auto Scheduled | PTM_CM31_BOM Conversion | 2.48d | May 21, 2026 1:45 | May 26, 2026 8:38 |  | 5
821 | Yes | Auto Scheduled | Extract File | 1h | May 21, 2026 1:45 | May 21, 2026 2:45 | 800 | 6
822 | Yes | Auto Scheduled | Pre Load Validation | 0.5h | May 21, 2026 2:45 | May 21, 2026 3:15 | 821 | 6
823 | Yes | Auto Scheduled | Simulate Load | 15.5h | May 21, 2026 3:15 | May 25, 2026 3:15 | 822 | 6
824 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | May 25, 2026 3:15 | May 25, 2026 3:45 | 823 | 6
825 | Yes | Auto Scheduled | Load | 1h | May 25, 2026 3:45 | May 25, 2026 5:00 | 824 | 6 | 4/17- Bom issues and not moving to routings...
826 | Yes | Auto Scheduled | Post Load Validation | 0.5h | May 26, 2026 8:00 | May 26, 2026 8:38 | 825 | 6 | 4/16 - updated to post load...
827 | Yes | Auto Scheduled | PTM_CM40_Work Center Conversion | 3.08d | May 21, 2026 2:45 | May 26, 2026 3:23 |  | 5
828 | Yes | Auto Scheduled | Extract File | 1h | May 21, 2026 2:45 | May 21, 2026 3:45 | 821 | 6
829 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 26, 2026 8:38 | May 26, 2026 10:38 | 826 | 6
830 | Yes | Auto Scheduled | Simulate Load | 0.25h | May 26, 2026 10:38 | May 26, 2026 10:53 | 829 | 6
831 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | May 26, 2026 10:53 | May 26, 2026 11:23 | 830 | 6 | 4/16- Defect created
832 | Yes | Auto Scheduled | Load | 1h | May 26, 2026 11:23 | May 26, 2026 1:23 | 831 | 6
833 | Yes | Auto Scheduled | Post Load Validation | 2h | May 26, 2026 1:23 | May 26, 2026 3:23 | 832 | 6
834 | Yes | Auto Scheduled | PTM_CM38_Routing Conversion | 4.27d | May 21, 2026 3:45 | May 28, 2026 8:53 |  | 5
835 | Yes | Auto Scheduled | Extract File | 1h | May 21, 2026 3:45 | May 21, 2026 4:45 | 828 | 6
836 | Yes | Auto Scheduled | Pre Load Validation | 2h | May 26, 2026 3:23 | May 27, 2026 10:53 | 833 | 6
837 | Yes | Auto Scheduled | Simulate Load | 2h | May 27, 2026 10:53 | May 27, 2026 1:53 | 836 | 6 | 4/20 Cost element has been resolved and now ready to run simulation again. Need to decide if we need to load all routings or load what we have that will load
838 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | May 27, 2026 10:53 | May 27, 2026 2:53 | 837SS | 6
839 | Yes | Auto Scheduled | Load | 1h | May 27, 2026 2:53 | May 27, 2026 3:53 | 838 | 6
840 | Yes | Auto Scheduled | Post Load Validation | 2h | May 27, 2026 3:53 | May 28, 2026 8:53 | 839 | 6
841 | Yes | Auto Scheduled | PTM_CM36_Production Version Conversion | 1.13d | May 21, 2026 4:45 | May 25, 2026 8:45 |  | 5
842 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 21, 2026 4:45 | May 22, 2026 8:15 | 835 | 6
843 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 22, 2026 8:15 | May 22, 2026 8:45 | 842 | 6
844 | Yes | Auto Scheduled | Simulate Load | 1h | May 22, 2026 8:45 | May 22, 2026 9:45 | 843 | 6
845 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 22, 2026 9:45 | May 22, 2026 11:45 | 844 | 6
846 | Yes | Auto Scheduled | Load | 2h | May 22, 2026 11:45 | May 22, 2026 2:45 | 845 | 6
847 | Yes | Auto Scheduled | Post Load Validation | 3h | May 22, 2026 2:45 | May 25, 2026 8:45 | 846 | 6
848 | Yes | Auto Scheduled | PTM_CM35_Inspection Plan | 1.13d | May 25, 2026 8:45 | May 26, 2026 9:45 |  | 5 | 4/17 - will manually load IP for ITC1
849 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 25, 2026 8:45 | May 25, 2026 9:15 | 847 | 6 | 4/20- Per Brad they will load manaually for ITC1
850 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 25, 2026 9:15 | May 25, 2026 9:45 | 849 | 6
851 | Yes | Auto Scheduled | Simulate Load | 1h | May 25, 2026 9:45 | May 25, 2026 10:45 | 850 | 6
852 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 25, 2026 10:45 | May 25, 2026 1:45 | 851 | 6
853 | Yes | Auto Scheduled | Load | 2h | May 25, 2026 1:45 | May 25, 2026 3:45 | 852 | 6
854 | Yes | Auto Scheduled | Post Load Validation | 3h | May 25, 2026 3:45 | May 26, 2026 9:45 | 853 | 6
855 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Serial Numbers | 1.13d | May 25, 2026 9:15 | May 26, 2026 10:15 |  | 5 | 4/17- will cherry pick equiments for testing ITC1/Smoke
856 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 25, 2026 9:15 | May 25, 2026 9:45 | 849 | 6
857 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 25, 2026 9:45 | May 25, 2026 10:15 | 856 | 6
858 | Yes | Auto Scheduled | Simulate Load | 1h | May 25, 2026 10:15 | May 25, 2026 11:15 | 857 | 6
859 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 25, 2026 11:15 | May 25, 2026 2:15 | 858 | 6
860 | Yes | Auto Scheduled | Load | 2h | May 25, 2026 2:15 | May 25, 2026 4:15 | 859 | 6
861 | Yes | Auto Scheduled | Post Load Validation | 3h | May 25, 2026 4:15 | May 26, 2026 10:15 | 860 | 6
862 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Service | 6.78d | May 18, 2026 10:00 | May 27, 2026 8:15 |  | 5 | 4/17- will cherry pick equiments for testing ITC1/Smoke
863 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 26, 2026 10:15 | May 26, 2026 10:45 | 861 | 6
864 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 26, 2026 10:45 | May 26, 2026 11:15 | 863 | 6
865 | Yes | Auto Scheduled | Simulate Load | 1h | May 26, 2026 11:15 | May 26, 2026 1:15 | 864 | 6
866 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 26, 2026 1:15 | May 26, 2026 3:15 | 865 | 6
867 | Yes | Auto Scheduled | Load | 2h | May 26, 2026 3:15 | May 27, 2026 8:15 | 866 | 6
868 | Yes | Auto Scheduled | Post Load Validation | 3h | May 18, 2026 10:00 | May 18, 2026 2:00 |  | 6
869 | Yes | Auto Scheduled | VC_Object Dependencies | 0.63d | May 18, 2026 10:00 | May 18, 2026 4:00 |  | 5
870 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | May 18, 2026 10:00 | May 18, 2026 12:00 |  | 6
871 | Yes | Auto Scheduled | Post Load Validation | 3h | May 18, 2026 1:00 | May 18, 2026 4:00 | 870 | 6
872 | Yes | Auto Scheduled | VC_Characteristics | 0.63d | May 18, 2026 4:00 | May 19, 2026 12:00 |  | 5
873 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | May 18, 2026 4:00 | May 19, 2026 9:00 | 871 | 6
874 | Yes | Auto Scheduled | Post Load Validation | 3h | May 19, 2026 9:00 | May 19, 2026 12:00 | 873 | 6
875 | Yes | Auto Scheduled | VC_Classes | 0.63d | May 19, 2026 1:00 | May 20, 2026 9:00 |  | 5
876 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | May 19, 2026 1:00 | May 19, 2026 3:00 | 874 | 6
877 | Yes | Auto Scheduled | Post Load Validation | 3h | May 19, 2026 3:00 | May 20, 2026 9:00 | 876 | 6
878 | Yes | Auto Scheduled | VC_Classification (Class Type 200) | 0.63d | May 21, 2026 11:45 | May 22, 2026 8:45 |  | 5
879 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | May 21, 2026 11:45 | May 21, 2026 2:45 | 798 | 6
880 | Yes | Auto Scheduled | Post Load Validation | 3h | May 21, 2026 2:45 | May 22, 2026 8:45 | 879 | 6
881 | Yes | Auto Scheduled | VC_Dependency Nets | 0.63d | May 21, 2026 11:45 | May 22, 2026 8:45 |  | 5
882 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | May 21, 2026 11:45 | May 21, 2026 2:45 | 792,877 | 6
883 | Yes | Auto Scheduled | Post Load Validation | 3h | May 21, 2026 2:45 | May 22, 2026 8:45 | 882 | 6
884 | Yes | Auto Scheduled | VC_Configuration Profiles | 0.63d | May 21, 2026 11:45 | May 22, 2026 8:45 |  | 5
885 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | May 21, 2026 11:45 | May 21, 2026 2:45 | 792 | 6
886 | Yes | Auto Scheduled | Post Load Validation | 3h | May 21, 2026 2:45 | May 22, 2026 8:45 | 885 | 6
887 | Yes | Auto Scheduled | VC_Variant Tables | 0.63d | May 22, 2026 8:45 | May 22, 2026 2:45 |  | 5
888 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | May 22, 2026 8:45 | May 22, 2026 10:45 | 886 | 6
889 | Yes | Auto Scheduled | Post Load Validation | 3h | May 22, 2026 10:45 | May 22, 2026 2:45 | 888 | 6
890 | Yes | Auto Scheduled | VC_Variant Tables Content | 0.63d | May 22, 2026 2:45 | May 25, 2026 10:45 |  | 5
891 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | May 22, 2026 2:45 | May 22, 2026 4:45 | 889 | 6
892 | Yes | Auto Scheduled | Post Load Validation | 3h | May 22, 2026 4:45 | May 25, 2026 10:45 | 891 | 6
893 | Yes | Auto Scheduled | VC_Characteristic Groups | 1.97d | May 22, 2026 8:45 | May 26, 2026 8:30 |  | 5 | 4/20- Defect - 963
894 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 12.75h | May 22, 2026 8:45 | May 25, 2026 2:30 | 886 | 6 | 4/17 - Authorization error/loaded but getting in app is issue. 4/20 Defect recorded and still open
895 | Yes | Auto Scheduled | Post Load Validation | 3h | May 25, 2026 2:30 | May 26, 2026 8:30 | 894 | 6
896 | Yes | Auto Scheduled | PTM_CM52_Super_BOM | 2d | May 21, 2026 11:45 | May 25, 2026 11:45 |  | 5 | 4/21- Pittsburg was loaded and working on remaining sites 4/20 - Working through errors with materials
897 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 21, 2026 11:45 | May 21, 2026 1:15 | 798 | 6
898 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 21, 2026 1:15 | May 21, 2026 1:45 | 897 | 6
899 | Yes | Auto Scheduled | Simulate Load | 8h | May 21, 2026 1:45 | May 22, 2026 1:45 | 898 | 6 | 4/17 - Have issues and Manoj to work with Chip
900 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 22, 2026 1:45 | May 22, 2026 3:45 | 899 | 6 | 4/16- Reviewing some errors , 4/17- Still running into errors
901 | Yes | Auto Scheduled | Load | 2h | May 22, 2026 3:45 | May 25, 2026 8:45 | 900 | 6
902 | Yes | Auto Scheduled | Post Load Validation | 3h | May 25, 2026 8:45 | May 25, 2026 11:45 | 901 | 6
903 | Yes | Auto Scheduled | PTM_CM53_Super_Routing | 2.13d | May 25, 2026 11:45 | May 27, 2026 1:45 |  | 5
904 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 25, 2026 11:45 | May 25, 2026 1:15 | 902 | 6
905 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 25, 2026 1:15 | May 25, 2026 1:45 | 904 | 6
906 | Yes | Auto Scheduled | Simulate Load | 1h | May 25, 2026 1:45 | May 26, 2026 2:45 | 905 | 6
907 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 26, 2026 2:45 | May 26, 2026 4:45 | 906 | 6
908 | Yes | Auto Scheduled | Load | 2h | May 26, 2026 4:45 | May 27, 2026 9:45 | 907 | 6
909 | Yes | Auto Scheduled | Post Load Validation | 3h | May 27, 2026 9:45 | May 27, 2026 1:45 | 908 | 6 | 4/22 -Loaded for Pittsburg
910 | Yes | Auto Scheduled | VC_VK30 Pricing Variant | 0.69d | May 27, 2026 9:45 | May 27, 2026 4:15 |  | 5
911 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | May 27, 2026 9:45 | May 27, 2026 10:15 | 908 | 6
912 | Yes | Auto Scheduled | Load | 2h | May 27, 2026 10:15 | May 27, 2026 1:15 | 911 | 6
913 | Yes | Auto Scheduled | Post Load Validation | 3h | May 27, 2026 1:15 | May 27, 2026 4:15 | 912 | 6
914 | Yes | Auto Scheduled | OTC_CM22_Pricing_Condition | 0.69d | May 27, 2026 4:15 | May 28, 2026 1:45 |  | 5
915 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | May 27, 2026 4:15 | May 27, 2026 4:45 | 913 | 6
916 | Yes | Auto Scheduled | Load | 2h | May 27, 2026 4:45 | May 28, 2026 9:45 | 915 | 6
917 | Yes | Auto Scheduled | Post Load Validation | 3h | May 28, 2026 9:45 | May 28, 2026 1:45 | 916 | 6 | 4/16 - Service to load
918 | Yes | Auto Scheduled | OTC_CM21_CMIR | 0.5d | May 28, 2026 9:45 | May 28, 2026 2:45 |  | 5
919 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 28, 2026 9:45 | May 28, 2026 10:15 | 916,927 | 6
920 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 28, 2026 10:15 | May 28, 2026 10:45 | 919 | 6
921 | Yes | Auto Scheduled | Simulate Load | 0h | May 28, 2026 10:45 | May 28, 2026 10:45 | 920 | 6
922 | Yes | Auto Scheduled | Error and Defect Mitigation | 0h | May 28, 2026 10:45 | May 28, 2026 10:45 | 921 | 6
923 | Yes | Auto Scheduled | Load | 0h | May 28, 2026 10:45 | May 28, 2026 10:45 | 922 | 6 | 4/16 - Load done
924 | Yes | Auto Scheduled | Post Load Validation | 3h | May 28, 2026 10:45 | May 28, 2026 2:45 | 923 | 6
925 | Yes | Auto Scheduled | PTP_CM29_Source_List | 6.16d | May 19, 2026 11:00 | May 27, 2026 1:15 |  | 5
926 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | May 19, 2026 11:00 | May 19, 2026 11:30 | 769,776 | 6 | 4/16 -
927 | Yes | Auto Scheduled | Load | 2h | May 26, 2026 4:15 | May 27, 2026 9:15 | 745 | 6
928 | Yes | Auto Scheduled | Post Load Validation | 3h | May 27, 2026 9:15 | May 27, 2026 1:15 | 927 | 6
929 | Yes | Auto Scheduled | RTR_CM11_Asset_Master | 3.75d | May 18, 2026 10:00 | May 21, 2026 5:00 |  | 5 | 4/20- Move to ITC2
930 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 18, 2026 10:00 | May 18, 2026 10:30 |  | 6
931 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 18, 2026 10:30 | May 18, 2026 11:00 | 930 | 6
932 | Yes | Auto Scheduled | Simulate Load | 8h | May 18, 2026 11:00 | May 19, 2026 11:00 | 931 | 6 | 4/17 - Going back and forth
933 | Yes | Auto Scheduled | Error and Defect Mitigation | 16h | May 19, 2026 11:00 | May 21, 2026 11:00 | 932 | 6
934 | Yes | Auto Scheduled | Load | 2h | May 21, 2026 11:00 | May 21, 2026 2:00 | 933 | 6
935 | Yes | Auto Scheduled | Post Load Validation | 3h | May 21, 2026 2:00 | May 21, 2026 5:00 | 934 | 6
936 | Yes | Auto Scheduled | PTM_CM50_Material Class | 2.13d | May 22, 2026 8:15 | May 26, 2026 9:15 |  | 5
937 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | May 22, 2026 8:15 | May 22, 2026 8:45 | 842 | 6
938 | Yes | Auto Scheduled | Load | 30m | May 22, 2026 8:45 | May 22, 2026 9:15 | 937 | 6 | 4/17 -Manually loaded
939 | Yes | Auto Scheduled | Post Load Validation | 16h | May 22, 2026 9:15 | May 26, 2026 9:15 | 938 | 6 | 4/16 - Will load manually
940 | Yes | Auto Scheduled | PTM_CM55_Class assignment to materials | 1.13d | May 22, 2026 8:45 | May 25, 2026 9:45 |  | 5 | 4/16 - Is not being loaded part of ITC1
941 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 22, 2026 8:45 | May 22, 2026 9:15 | 937 | 6
942 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 22, 2026 9:15 | May 22, 2026 9:45 | 941 | 6
943 | Yes | Auto Scheduled | Simulate Load | 1h | May 22, 2026 9:45 | May 22, 2026 10:45 | 942 | 6
944 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 22, 2026 10:45 | May 22, 2026 1:45 | 943 | 6
945 | Yes | Auto Scheduled | Load | 2h | May 22, 2026 1:45 | May 22, 2026 3:45 | 944 | 6
946 | Yes | Auto Scheduled | Post Load Validation | 3h | May 22, 2026 3:45 | May 25, 2026 9:45 | 945 | 6
947 | Yes | Auto Scheduled | GTS - Material initial load from S4 (Run Interface) | 2.09d | May 21, 2026 2:45 | May 25, 2026 3:30 |  | 5
948 | Yes | Auto Scheduled | Run material interface to GTS | 15.75h | May 21, 2026 2:45 | May 25, 2026 2:30 | 816 | 6
949 | Yes | Auto Scheduled | Post Load Validation | 1h | May 25, 2026 2:30 | May 25, 2026 3:30 | 948 | 6
950 | Yes | Auto Scheduled | GTS - Customers initial load from S4 (Run Interface) | 0.25d | May 18, 2026 10:00 | May 18, 2026 12:00 |  | 5
951 | Yes | Auto Scheduled | Run material interface to GTS | 1h | May 18, 2026 10:00 | May 18, 2026 11:00 |  | 6
952 | Yes | Auto Scheduled | Post Load Validation | 1h | May 18, 2026 11:00 | May 18, 2026 12:00 | 951 | 6 | 4/17 99% complete ran in to some erros with defect 934
953 | Yes | Auto Scheduled | GTS - Vendors initial load from S4 (Run Interface) | 0.25d | May 19, 2026 9:00 | May 19, 2026 11:00 |  | 5
954 | Yes | Auto Scheduled | Run material interface to GTS | 1h | May 19, 2026 9:00 | May 19, 2026 10:00 | 759 | 6 | 4/16- Have 3 records with issues
955 | Yes | Auto Scheduled | Post Load Validation | 1h | May 19, 2026 10:00 | May 19, 2026 11:00 | 954 | 6
956 | Yes | Auto Scheduled | GTS - ECCN - Create | 1.13d | May 18, 2026 10:00 | May 19, 2026 11:00 |  | 5
957 | Yes | Auto Scheduled | Load Descartes XML File | 1h | May 18, 2026 10:00 | May 18, 2026 11:00 |  | 6
958 | Yes | Auto Scheduled | Post Load Validation | 1h | May 19, 2026 10:00 | May 19, 2026 11:00 | 954 | 6
959 | Yes | Auto Scheduled | GTS - ECCN - Assign | 0.25d | May 25, 2026 3:30 | May 26, 2026 8:30 |  | 5
960 | Yes | Auto Scheduled | Load Descartes XML File | 1h | May 25, 2026 3:30 | May 25, 2026 4:30 | 949 | 6
961 | Yes | Auto Scheduled | Post Load Validation | 1h | May 25, 2026 4:30 | May 26, 2026 8:30 | 960 | 6
962 | Yes | Auto Scheduled | GTS - HTS - Create | 0.25d | May 18, 2026 10:00 | May 18, 2026 12:00 |  | 5
963 | Yes | Auto Scheduled | Load Descartes XML File | 1h | May 18, 2026 10:00 | May 18, 2026 11:00 |  | 6
964 | Yes | Auto Scheduled | Post Load Validation | 1h | May 18, 2026 11:00 | May 18, 2026 12:00 | 963 | 6
965 | Yes | Auto Scheduled | GTS - HTS - Assign | 0.25d | May 26, 2026 8:30 | May 26, 2026 10:30 |  | 5
966 | Yes | Auto Scheduled | Load Descartes XML File | 1h | May 26, 2026 8:30 | May 26, 2026 9:30 | 961 | 6
967 | Yes | Auto Scheduled | Post Load Validation | 1h | May 26, 2026 9:30 | May 26, 2026 10:30 | 966 | 6
968 | Yes | Auto Scheduled | GTS - License - Create | 0.25d | May 26, 2026 11:30 | May 26, 2026 2:30 |  | 5
969 | Yes | Auto Scheduled | Load Descartes XML File | 1h | May 26, 2026 11:30 | May 26, 2026 1:30 | 966,982 | 6 | 4/13 - Need to update dep.
970 | Yes | Auto Scheduled | Post Load Validation | 1h | May 26, 2026 1:30 | May 26, 2026 2:30 | 969 | 6
971 | Yes | Auto Scheduled | Commodity Code/Tarif | 2.78d | May 26, 2026 10:30 | May 29, 2026 8:45 |  | 5
972 | Yes | Auto Scheduled | Load | 21.25h | May 26, 2026 10:30 | May 28, 2026 4:45 | 967 | 6 | 4/17- wants to use the old load program
973 | Yes | Auto Scheduled | Post Load Validation | 1h | May 28, 2026 4:45 | May 29, 2026 8:45 | 972 | 6
974 | Yes | Auto Scheduled | SPL Master File | 0.25d | May 26, 2026 9:30 | May 26, 2026 11:30 |  | 5
975 | Yes | Auto Scheduled | Load | 1h | May 26, 2026 9:30 | May 26, 2026 10:30 | 966 | 6
976 | Yes | Auto Scheduled | Post Load Validation | 1h | May 26, 2026 10:30 | May 26, 2026 11:30 | 975 | 6
977 | Yes | Auto Scheduled | Initialize Embargo situation | 0.38d | May 19, 2026 11:00 | May 19, 2026 3:00 |  | 5
978 | Yes | Auto Scheduled | Run report /SAPSLL/EMB_CNTRY_INIT | 1h | May 19, 2026 11:00 | May 19, 2026 12:00 | 958 | 6
979 | Yes | Auto Scheduled | Set Embargo situations | 1h | May 19, 2026 1:00 | May 19, 2026 2:00 | 978 | 6 | 4/17 - Needs access
980 | Yes | Auto Scheduled | Post Load Validation | 1h | May 19, 2026 2:00 | May 19, 2026 3:00 | 979 | 6
981 | Yes | Auto Scheduled | GTS - SPL (Sanctioned party list) | 0.25d | May 26, 2026 10:30 | May 26, 2026 1:30 |  | 5
982 | Yes | Auto Scheduled | Load Descartes XML File | 1h | May 26, 2026 10:30 | May 26, 2026 11:30 | 967 | 6
983 | Yes | Auto Scheduled | Post Load Validation | 1h | May 26, 2026 11:30 | May 26, 2026 1:30 | 982 | 6
984 | Yes | Auto Scheduled | RTR_CM17_Project Definition / Builder | 1.13d | May 18, 2026 10:30 | May 19, 2026 11:30 |  | 5 | 4/20 - Will have files to load in the morning
985 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 18, 2026 10:30 | May 18, 2026 11:00 | 930 | 6
986 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 18, 2026 11:00 | May 18, 2026 11:30 | 985 | 6
987 | Yes | Auto Scheduled | Simulate Load | 1h | May 18, 2026 11:30 | May 18, 2026 1:30 | 986 | 6
988 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 18, 2026 1:30 | May 18, 2026 3:30 | 987 | 6
989 | Yes | Auto Scheduled | Load | 2h | May 18, 2026 3:30 | May 19, 2026 8:30 | 988 | 6
990 | Yes | Auto Scheduled | Post Load Validation | 3h | May 19, 2026 8:30 | May 19, 2026 11:30 | 989 | 6
991 | Yes | Auto Scheduled | RTR_CM18_WBS Element | 1.13d | May 18, 2026 11:00 | May 19, 2026 12:00 |  | 5
992 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | May 18, 2026 11:00 | May 18, 2026 11:30 | 985 | 6
993 | Yes | Auto Scheduled | Pre Load Validation | 30m | May 18, 2026 11:30 | May 18, 2026 12:00 | 992 | 6
994 | Yes | Auto Scheduled | Simulate Load | 1h | May 18, 2026 1:00 | May 18, 2026 2:00 | 993 | 6
995 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | May 18, 2026 2:00 | May 18, 2026 4:00 | 994 | 6
996 | Yes | Auto Scheduled | Load | 2h | May 18, 2026 4:00 | May 19, 2026 9:00 | 995 | 6
997 | Yes | Auto Scheduled | Post Load Validation | 3h | May 19, 2026 9:00 | May 19, 2026 12:00 | 996 | 6
998 | Yes | Auto Scheduled | ITC2 Master Data Loads Complete | 0m | May 29, 2026 4:00 | May 29, 2026 4:00 | 631 | 4
999 | Yes | Auto Scheduled | Mock Transactional Data | 2d | October 8, 2026 2:00 | October 12, 2026 2:00 | 998,1759,2140 | 4
1000 | Yes | Auto Scheduled | Inventory | 4h | October 8, 2026 2:00 | October 9, 2026 9:00 | 998SS,1759SS,2140SS | 5
1001 | Yes | Auto Scheduled | Open AR | 4h | October 9, 2026 9:00 | October 9, 2026 2:00 | 1000 | 5
1002 | Yes | Auto Scheduled | Open AP | 4h | October 9, 2026 2:00 | October 12, 2026 9:00 | 1001 | 5
1003 | Yes | Auto Scheduled | Bank and Cash | 4h | October 12, 2026 9:00 | October 12, 2026 2:00 | 1002 | 5
1004 | Yes | Auto Scheduled | Open Purchase Orders(Manual) | 1d | October 9, 2026 9:00 | October 12, 2026 9:00 | 1000 | 5
1005 | Yes | Auto Scheduled | Open Sales Orders(Manual) | 1d | October 9, 2026 9:00 | October 12, 2026 9:00 | 1000 | 5
1006 | Yes | Auto Scheduled | Service Orders(Manual) | 0.5d | October 9, 2026 9:00 | October 9, 2026 2:00 | 1000 | 5
1007 | Yes | Auto Scheduled | Open Production Orders(Manual) | 1d | October 9, 2026 9:00 | October 12, 2026 9:00 | 1000 | 5
1008 | Yes | Auto Scheduled | ITC2 Mock Data Loads Complete | 0m | October 12, 2026 2:00 | October 12, 2026 2:00 | 999 | 4
1009 | Yes | Auto Scheduled | ITC3 Data Load Tasks QS5 | 11.88d | June 8, 2026 8:00 | June 23, 2026 4:00 |  | 3
1010 | Yes | Auto Scheduled | PMO Authorization to Start Data Loads | 2h | June 8, 2026 8:00 | June 8, 2026 10:00 | 72 | 4
1011 | Yes | Auto Scheduled | Master Data Loads | 9.63d | June 8, 2026 10:00 | June 19, 2026 4:00 | 1010 | 4
1012 | Yes | Auto Scheduled | RTR_CM02_Profit Center Hierarchy | 0.75d | June 8, 2026 10:00 | June 8, 2026 5:00 |  | 5
1013 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | June 8, 2026 10:00 | June 8, 2026 11:00 |  | 6
1014 | Yes | Auto Scheduled | Load | 2h | June 8, 2026 11:00 | June 8, 2026 2:00 | 1013 | 6
1015 | Yes | Auto Scheduled | Post Load Validation | 3h | June 8, 2026 2:00 | June 8, 2026 5:00 | 1014 | 6
1016 | Yes | Auto Scheduled | RTR_CM03_Cost Center Hierarchy | 0.75d | June 9, 2026 8:00 | June 9, 2026 3:00 |  | 5
1017 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | June 9, 2026 8:00 | June 9, 2026 9:00 | 1015 | 6
1018 | Yes | Auto Scheduled | Load | 2h | June 9, 2026 9:00 | June 9, 2026 11:00 | 1017 | 6
1019 | Yes | Auto Scheduled | Post Load Validation | 3h | June 9, 2026 11:00 | June 9, 2026 3:00 | 1018 | 6
1020 | Yes | Auto Scheduled | RTR_CM01_GL_Account_Master to CC 1000 | 2.44d | June 9, 2026 3:00 | June 12, 2026 9:30 |  | 5
1021 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | June 9, 2026 3:00 | June 9, 2026 4:00 | 1019 | 6
1022 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 9, 2026 4:00 | June 10, 2026 9:00 | 1021 | 6
1023 | Yes | Auto Scheduled | Simulate Load | 6h | June 10, 2026 9:00 | June 10, 2026 4:00 | 1022 | 6
1024 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 10, 2026 4:00 | June 11, 2026 10:30 | 1023 | 6
1025 | Yes | Auto Scheduled | Load | 1h | June 11, 2026 10:30 | June 11, 2026 11:30 | 1024 | 6
1026 | Yes | Auto Scheduled | Post Load Validation | 2h | June 11, 2026 11:30 | June 11, 2026 2:30 | 1025 | 6
1027 | Yes | Auto Scheduled | Extend GL to all Company Codes | 2h | June 11, 2026 2:30 | June 11, 2026 4:30 | 1026 | 6
1028 | Yes | Auto Scheduled | Post GL Extention Validation | 2h | June 11, 2026 4:30 | June 12, 2026 9:30 | 1027 | 6
1029 | Yes | Auto Scheduled | RTR_CM05_Profit_Center | 1.13d | June 9, 2026 8:00 | June 10, 2026 9:00 |  | 5
1030 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | June 9, 2026 8:00 | June 9, 2026 9:00 | 1015 | 6
1031 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 9, 2026 9:00 | June 9, 2026 11:00 | 1030 | 6
1032 | Yes | Auto Scheduled | Simulate Load | 1h | June 9, 2026 11:00 | June 9, 2026 12:00 | 1031 | 6
1033 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 9, 2026 1:00 | June 9, 2026 3:00 | 1032 | 6
1034 | Yes | Auto Scheduled | Load | 1h | June 9, 2026 3:00 | June 9, 2026 4:00 | 1033 | 6
1035 | Yes | Auto Scheduled | Post Load Validation | 2h | June 9, 2026 4:00 | June 10, 2026 9:00 | 1034 | 6
1036 | Yes | Auto Scheduled | RTR_CM04_Cost_Center | 1.13d | June 10, 2026 9:00 | June 11, 2026 10:00 |  | 5
1037 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | June 10, 2026 9:00 | June 10, 2026 10:00 | 1035 | 6
1038 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 10, 2026 10:00 | June 10, 2026 12:00 | 1037 | 6
1039 | Yes | Auto Scheduled | Simulate Load | 1h | June 10, 2026 1:00 | June 10, 2026 2:00 | 1038 | 6
1040 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 10, 2026 2:00 | June 10, 2026 4:00 | 1039 | 6
1041 | Yes | Auto Scheduled | Load | 1h | June 10, 2026 4:00 | June 10, 2026 5:00 | 1040 | 6
1042 | Yes | Auto Scheduled | Post Load Validation | 2h | June 11, 2026 8:00 | June 11, 2026 10:00 | 1041 | 6
1043 | Yes | Auto Scheduled | Manual Configuration Activities in QS5 | 5.94d | June 11, 2026 10:00 | June 19, 2026 9:30 | 1036 | 5
1044 | Yes | Auto Scheduled | Open Client | 30m | June 11, 2026 10:00 | June 11, 2026 10:30 |  | 6
1045 | Yes | Auto Scheduled | Service Enterprise Setup | 5d | June 12, 2026 9:30 | June 19, 2026 9:30 | 1012,1016,1020 | 6
1046 | Yes | Auto Scheduled | Close Client | 30m | June 11, 2026 10:00 | June 11, 2026 10:30 |  | 6
1047 | Yes | Auto Scheduled | Intercompany Business Partner Setup | 2h | June 12, 2026 9:30 | June 12, 2026 11:30 | 1012,1016,1028 | 6
1048 | Yes | Auto Scheduled | RTR_CM09_Activity_Type | 1.38d | June 11, 2026 2:30 | June 15, 2026 8:30 |  | 5
1049 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | June 11, 2026 2:30 | June 11, 2026 4:45 | 1026 | 6
1050 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 11, 2026 4:45 | June 12, 2026 10:30 | 1049 | 6
1051 | Yes | Auto Scheduled | Simulate Load | 1h | June 12, 2026 10:30 | June 12, 2026 11:30 | 1050 | 6
1052 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 12, 2026 11:30 | June 12, 2026 2:30 | 1051 | 6
1053 | Yes | Auto Scheduled | Load | 1h | June 12, 2026 2:30 | June 12, 2026 3:30 | 1052 | 6
1054 | Yes | Auto Scheduled | Post Load Validation | 2h | June 12, 2026 3:30 | June 15, 2026 8:30 | 1053 | 6
1055 | Yes | Auto Scheduled | RTR_CM12_Activity Rates | 1.13d | June 9, 2026 3:00 | June 10, 2026 4:00 |  | 5
1056 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | June 9, 2026 3:00 | June 9, 2026 4:00 | 1019 | 6
1057 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 9, 2026 4:00 | June 10, 2026 9:00 | 1056 | 6
1058 | Yes | Auto Scheduled | Simulate Load | 1h | June 10, 2026 9:00 | June 10, 2026 10:00 | 1057 | 6
1059 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 10, 2026 10:00 | June 10, 2026 12:00 | 1058 | 6
1060 | Yes | Auto Scheduled | Load | 1h | June 10, 2026 1:00 | June 10, 2026 2:00 | 1059 | 6
1061 | Yes | Auto Scheduled | Post Load Validation | 2h | June 10, 2026 2:00 | June 10, 2026 4:00 | 1060 | 6
1062 | Yes | Auto Scheduled | RTR_CM06_Bank_master | 3.81d | June 8, 2026 10:00 | June 12, 2026 8:30 |  | 5
1063 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | June 11, 2026 2:30 | June 11, 2026 3:30 | 1026 | 6
1064 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 11, 2026 3:30 | June 12, 2026 8:30 | 1063 | 6
1065 | Yes | Auto Scheduled | Simulate Load | 1h | June 8, 2026 10:00 | June 8, 2026 11:00 |  | 6
1066 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 8, 2026 11:00 | June 8, 2026 2:00 | 1065 | 6
1067 | Yes | Auto Scheduled | Load | 5h | June 8, 2026 2:00 | June 9, 2026 10:00 | 1066 | 6
1068 | Yes | Auto Scheduled | Post Load Validation | 2h | June 9, 2026 10:00 | June 9, 2026 4:30 | 1067 | 6
1069 | Yes | Auto Scheduled | RTR_CM08_Exchange_Rates | 1.13d | June 9, 2026 10:00 | June 10, 2026 11:00 |  | 5
1070 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | June 9, 2026 10:00 | June 9, 2026 11:00 | 1067 | 6
1071 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 9, 2026 11:00 | June 9, 2026 2:00 | 1070 | 6
1072 | Yes | Auto Scheduled | Simulate Load | 1h | June 9, 2026 2:00 | June 9, 2026 3:00 | 1071 | 6
1073 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 9, 2026 3:00 | June 9, 2026 5:00 | 1072 | 6
1074 | Yes | Auto Scheduled | Load | 1h | June 10, 2026 8:00 | June 10, 2026 9:00 | 1073 | 6
1075 | Yes | Auto Scheduled | Post Load Validation | 2h | June 10, 2026 9:00 | June 10, 2026 11:00 | 1074 | 6
1076 | Yes | Auto Scheduled | RTR_CM14_Cost Element_Group | 1.44d | June 11, 2026 2:30 | June 15, 2026 9:00 |  | 5
1077 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | June 11, 2026 2:30 | June 11, 2026 3:00 | 1026 | 6
1078 | Yes | Auto Scheduled | Load | 8h | June 11, 2026 3:00 | June 12, 2026 3:00 | 1077 | 6
1079 | Yes | Auto Scheduled | Post Load Validation | 3h | June 12, 2026 3:00 | June 15, 2026 9:00 | 1078 | 6
1080 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Bill-To | 2h | June 8, 2026 10:00 | June 8, 2026 12:00 |  | 5 | 4/20 Per OTC this is not needed for ITC1
1081 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Ship-To | 1.5d | June 11, 2026 2:30 | June 15, 2026 9:30 |  | 5
1082 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 11, 2026 2:30 | June 11, 2026 3:00 | 1026 | 6
1083 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 11, 2026 3:00 | June 11, 2026 3:30 | 1082 | 6
1084 | Yes | Auto Scheduled | Open client for BP number range update | 30m | June 11, 2026 3:30 | June 11, 2026 4:00 | 1083 | 6
1085 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 30m | June 11, 2026 4:00 | June 11, 2026 4:30 | 1084 | 6
1086 | Yes | Auto Scheduled | Close Client | 15m | June 11, 2026 4:30 | June 11, 2026 4:45 | 1085 | 6
1087 | Yes | Auto Scheduled | Simulate Load | 1h | June 11, 2026 3:30 | June 11, 2026 4:30 | 1083 | 6
1088 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | June 11, 2026 4:30 | June 12, 2026 11:30 | 1087 | 6
1089 | Yes | Auto Scheduled | Load | 3h | June 12, 2026 11:30 | June 12, 2026 3:30 | 1088 | 6
1090 | Yes | Auto Scheduled | Post Load Validation | 3h | June 12, 2026 3:30 | June 15, 2026 9:30 | 1089 | 6
1091 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Sold-To | 1.63d | June 11, 2026 3:30 | June 15, 2026 11:30 |  | 5
1092 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 11, 2026 3:30 | June 11, 2026 4:00 | 1083 | 6
1093 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 11, 2026 4:00 | June 11, 2026 4:30 | 1092 | 6
1094 | Yes | Auto Scheduled | Simulate Load | 1h | June 12, 2026 9:30 | June 12, 2026 10:30 | 1028,1087 | 6
1095 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | June 12, 2026 10:30 | June 12, 2026 2:30 | 1094 | 6
1096 | Yes | Auto Scheduled | Load | 3h | June 12, 2026 2:30 | June 15, 2026 8:30 | 1095 | 6
1097 | Yes | Auto Scheduled | Post Load Validation | 3h | June 15, 2026 8:30 | June 15, 2026 11:30 | 1096 | 6
1098 | Yes | Auto Scheduled | Open client for BP number range update | 15m | June 11, 2026 4:30 | June 11, 2026 4:45 | 1087 | 6
1099 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 15m | June 11, 2026 4:45 | June 11, 2026 5:00 | 1098 | 6
1100 | Yes | Auto Scheduled | Close Client | 15m | June 12, 2026 8:00 | June 12, 2026 8:15 | 1099 | 6
1101 | Yes | Auto Scheduled | PTP_CM27_Vendor Master as Customer - FLCU01 | 4.81d | June 15, 2026 8:30 | June 19, 2026 4:00 |  | 5
1102 | Yes | Auto Scheduled | Extract File | 1h | June 15, 2026 8:30 | June 15, 2026 9:30 | 1096 | 6
1103 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 15, 2026 9:30 | June 15, 2026 11:30 | 1102 | 6
1104 | Yes | Auto Scheduled | Simulate Load | 11.25h | June 15, 2026 11:30 | June 16, 2026 3:45 | 1068,1103 | 6
1105 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 16, 2026 3:45 | June 18, 2026 10:30 | 1104 | 6
1106 | Yes | Auto Scheduled | Load | 1h | June 18, 2026 10:30 | June 19, 2026 2:00 | 1105 | 6
1107 | Yes | Auto Scheduled | Post Load Validation | 2h | June 19, 2026 2:00 | June 19, 2026 4:00 | 1106 | 6
1108 | Yes | Auto Scheduled | OTC_CM23_Customer_Hierarchy | 0.69d | June 15, 2026 8:30 | June 15, 2026 3:00 |  | 5
1109 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | June 15, 2026 8:30 | June 15, 2026 9:00 | 1096 | 6
1110 | Yes | Auto Scheduled | Load | 2h | June 15, 2026 9:00 | June 15, 2026 11:00 | 1109 | 6
1111 | Yes | Auto Scheduled | Post Load Validation | 3h | June 15, 2026 11:00 | June 15, 2026 3:00 | 1110 | 6
1112 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Z001 - External Sales Rep | 3.38d | June 15, 2026 8:30 | June 18, 2026 11:30 |  | 5
1113 | Yes | Auto Scheduled | Extract File | 1h | June 15, 2026 8:30 | June 15, 2026 9:30 | 1096 | 6
1114 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 15, 2026 9:30 | June 15, 2026 11:30 | 1113 | 6
1115 | Yes | Auto Scheduled | Simulate Load | 1h | June 15, 2026 11:30 | June 15, 2026 1:30 | 1068,1114 | 6
1116 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 15, 2026 1:30 | June 15, 2026 3:30 | 1115 | 6
1117 | Yes | Auto Scheduled | Load | 1h | June 15, 2026 3:30 | June 18, 2026 9:30 | 1116 | 6
1118 | Yes | Auto Scheduled | Post Load Validation | 2h | June 18, 2026 9:30 | June 18, 2026 11:30 | 1117 | 6
1119 | Yes | Auto Scheduled | RTR_CM10_Credit_Management_Role | 1.84d | June 15, 2026 8:30 | June 16, 2026 4:15 |  | 5
1120 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 15, 2026 8:30 | June 15, 2026 9:00 | 1096 | 6
1121 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 15, 2026 9:00 | June 15, 2026 9:30 | 1120 | 6
1122 | Yes | Auto Scheduled | Simulate Load | 1h | June 15, 2026 9:30 | June 15, 2026 10:30 | 1121 | 6 | 4/16 - Asked to reload per Brian
1123 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 15, 2026 10:30 | June 15, 2026 2:00 | 1122 | 6
1124 | Yes | Auto Scheduled | Load | 2h | June 15, 2026 2:00 | June 16, 2026 9:00 | 1123 | 6
1125 | Yes | Auto Scheduled | Post Load Validation | 3h | June 16, 2026 9:00 | June 16, 2026 4:15 | 1124 | 6 | 4/17 - Error on load,resolution identifed, Def899,Will manually change customer for IT1
1126 | Yes | Auto Scheduled | PTP_CM27_Vendor Master | 6.28d | June 8, 2026 10:00 | June 16, 2026 1:15 |  | 5
1127 | Yes | Auto Scheduled | Extract File | 1h | June 15, 2026 9:30 | June 15, 2026 10:30 | 1113 | 6
1128 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 15, 2026 10:30 | June 15, 2026 1:30 | 1127 | 6
1129 | Yes | Auto Scheduled | Simulate Load | 2.25h | June 15, 2026 1:30 | June 15, 2026 3:45 | 1128 | 6 | First time simulation on 4/13
1130 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 15, 2026 3:45 | June 16, 2026 1:15 | 1129 | 6 | 4/14 - Ran into more errors and Manoj will follow up ib 2hrs....
1131 | Yes | Auto Scheduled | Load | 1h | June 8, 2026 10:00 | June 8, 2026 11:00 |  | 6
1132 | Yes | Auto Scheduled | Post Load Validation | 2h | June 8, 2026 11:00 | June 8, 2026 2:00 | 1131 | 6 | 4/14 PTP Is complete
1133 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | 0.88d | June 8, 2026 10:00 | June 9, 2026 9:00 |  | 5
1134 | Yes | Auto Scheduled | Extract File(Will Extract from LFA1) | 1h | June 8, 2026 10:00 | June 8, 2026 11:00 |  | 6
1135 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 8, 2026 11:00 | June 8, 2026 2:00 | 1134 | 6
1136 | Yes | Auto Scheduled | Simulate Load/ Not Needed | 1h | June 8, 2026 2:00 | June 8, 2026 3:00 | 1135 | 6
1137 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 8, 2026 3:00 | June 8, 2026 5:00 | 1136 | 6 | 4/16 - Defect created no impact to ITC1
1138 | Yes | Auto Scheduled | Load | 1h | June 8, 2026 3:00 | June 8, 2026 4:00 | 1136 | 6
1139 | Yes | Auto Scheduled | Post Load Validation | 2h | June 8, 2026 4:00 | June 9, 2026 9:00 | 1138 | 6
1140 | Yes | Auto Scheduled | RTR_****_Credit Hierarchy | 1.91d | June 15, 2026 2:00 | June 17, 2026 1:15 |  | 5
1141 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | June 15, 2026 2:00 | June 15, 2026 2:30 | 1123 | 6 | 4/16 -Completed
1142 | Yes | Auto Scheduled | Load | 2h | June 16, 2026 4:15 | June 17, 2026 9:15 | 1125 | 6
1143 | Yes | Auto Scheduled | Post Load Validation | 3h | June 17, 2026 9:15 | June 17, 2026 1:15 | 1142 | 6
1144 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Supplier | 1.13d | June 8, 2026 2:00 | June 9, 2026 3:00 |  | 5
1145 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 8, 2026 2:00 | June 8, 2026 2:30 | 1132 | 6
1146 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 8, 2026 2:30 | June 8, 2026 3:00 | 1145 | 6
1147 | Yes | Auto Scheduled | Simulate Load | 1h | June 8, 2026 3:00 | June 8, 2026 4:00 | 1146 | 6
1148 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 8, 2026 4:00 | June 9, 2026 9:00 | 1147 | 6
1149 | Yes | Auto Scheduled | Load | 2h | June 9, 2026 9:00 | June 9, 2026 11:00 | 1148 | 6
1150 | Yes | Auto Scheduled | Post Load Validation | 3h | June 9, 2026 11:00 | June 9, 2026 3:00 | 1149 | 6
1151 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Customer | 1.06d | June 8, 2026 10:00 | June 9, 2026 10:30 |  | 5
1152 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 8, 2026 10:00 | June 8, 2026 10:30 |  | 6
1153 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 8, 2026 10:00 | June 8, 2026 10:30 |  | 6
1154 | Yes | Auto Scheduled | Simulate Load | 1h | June 8, 2026 10:30 | June 8, 2026 11:30 | 1153 | 6
1155 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 8, 2026 11:30 | June 8, 2026 2:30 | 1154 | 6
1156 | Yes | Auto Scheduled | Load | 2h | June 8, 2026 2:30 | June 8, 2026 4:30 | 1155 | 6
1157 | Yes | Auto Scheduled | Post Load Validation | 3h | June 8, 2026 4:30 | June 9, 2026 10:30 | 1156 | 6
1158 | Yes | Auto Scheduled | PTP_CM26_Material_Master - All Types | 2.28d | June 8, 2026 11:00 | June 10, 2026 2:15 |  | 5
1159 | Yes | Auto Scheduled | Extract File | 5h | June 8, 2026 11:00 | June 9, 2026 9:45 | 1134 | 6
1160 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 8, 2026 2:00 | June 9, 2026 11:15 | 1132 | 6
1161 | Yes | Auto Scheduled | Simulate Load | 1h | June 9, 2026 11:15 | June 9, 2026 1:15 | 1160 | 6
1162 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | June 9, 2026 1:15 | June 10, 2026 8:15 | 1161 | 6
1163 | Yes | Auto Scheduled | Load | 3h | June 10, 2026 8:15 | June 10, 2026 11:15 | 1162 | 6
1164 | Yes | Auto Scheduled | Post Load Validation | 2h | June 10, 2026 11:15 | June 10, 2026 2:15 | 1163 | 6
1165 | Yes | Auto Scheduled | PTP_CM26_Material_Master - SERV - Service Materials | 1.34d | June 10, 2026 9:00 | June 11, 2026 11:45 |  | 5
1166 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 10, 2026 9:00 | June 10, 2026 9:30 | 1035 | 6
1167 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 10, 2026 11:15 | June 10, 2026 11:45 | 1163 | 6
1168 | Yes | Auto Scheduled | Simulate Load | 1h | June 10, 2026 11:45 | June 10, 2026 1:45 | 1167 | 6
1169 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 10, 2026 1:45 | June 10, 2026 3:45 | 1168 | 6
1170 | Yes | Auto Scheduled | Load | 2h | June 10, 2026 3:45 | June 11, 2026 8:45 | 1169 | 6
1171 | Yes | Auto Scheduled | Post Load Validation | 3h | June 11, 2026 8:45 | June 11, 2026 11:45 | 1170 | 6
1172 | Yes | Auto Scheduled | PTP_CM26_Material_Master - KMAT - Configurable Materials | 1.34d | June 10, 2026 9:00 | June 11, 2026 11:45 |  | 5
1173 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 10, 2026 9:00 | June 10, 2026 9:30 | 1035 | 6
1174 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 10, 2026 11:15 | June 10, 2026 11:45 | 1163 | 6
1175 | Yes | Auto Scheduled | Simulate Load | 1h | June 10, 2026 11:45 | June 10, 2026 1:45 | 1174 | 6
1176 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 10, 2026 1:45 | June 10, 2026 3:45 | 1175 | 6
1177 | Yes | Auto Scheduled | Load | 2h | June 10, 2026 3:45 | June 11, 2026 8:45 | 1176 | 6
1178 | Yes | Auto Scheduled | Post Load Validation | 3h | June 11, 2026 8:45 | June 11, 2026 11:45 | 1177 | 6
1179 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Records | 3.59d | June 8, 2026 2:00 | June 12, 2026 9:45 |  | 5
1180 | Yes | Auto Scheduled | Extract File | 1h | June 11, 2026 11:45 | June 11, 2026 1:45 | 1164,1178 | 6 | 4/16 - Started extract
1181 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 11, 2026 1:45 | June 11, 2026 3:45 | 1180 | 6
1182 | Yes | Auto Scheduled | Simulate Load | 1h | June 11, 2026 3:45 | June 11, 2026 4:45 | 1181 | 6
1183 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 11, 2026 4:45 | June 12, 2026 9:45 | 1182 | 6
1184 | Yes | Auto Scheduled | Load | 1h | June 8, 2026 2:00 | June 8, 2026 3:00 | 1132 | 6
1185 | Yes | Auto Scheduled | Post Load Validation | 2h | June 8, 2026 3:00 | June 8, 2026 5:00 | 1184 | 6
1186 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record External Processing | 1.13d | June 11, 2026 11:45 | June 12, 2026 1:45 |  | 5
1187 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 11, 2026 11:45 | June 11, 2026 1:15 | 1164,1178 | 6
1188 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 11, 2026 1:15 | June 11, 2026 1:45 | 1187 | 6
1189 | Yes | Auto Scheduled | Simulate Load | 1h | June 11, 2026 1:45 | June 11, 2026 2:45 | 1188 | 6
1190 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 11, 2026 2:45 | June 11, 2026 4:45 | 1189 | 6
1191 | Yes | Auto Scheduled | Load | 2h | June 11, 2026 4:45 | June 12, 2026 9:45 | 1190 | 6
1192 | Yes | Auto Scheduled | Post Load Validation | 3h | June 12, 2026 9:45 | June 12, 2026 1:45 | 1191 | 6
1193 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | 1.13d | June 11, 2026 11:45 | June 12, 2026 1:45 |  | 5
1194 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 11, 2026 11:45 | June 11, 2026 1:15 | 1164,1178 | 6
1195 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 11, 2026 1:15 | June 11, 2026 1:45 | 1194 | 6
1196 | Yes | Auto Scheduled | Simulate Load | 1h | June 11, 2026 1:45 | June 11, 2026 2:45 | 1195 | 6 | 4/16 - Eror
1197 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 11, 2026 2:45 | June 11, 2026 4:45 | 1196 | 6
1198 | Yes | Auto Scheduled | Load | 2h | June 11, 2026 4:45 | June 12, 2026 9:45 | 1197 | 6
1199 | Yes | Auto Scheduled | Post Load Validation | 3h | June 12, 2026 9:45 | June 12, 2026 1:45 | 1198 | 6
1200 | Yes | Auto Scheduled | PTM_CM31_BOM Conversion | 2.48d | June 11, 2026 1:45 | June 16, 2026 8:38 |  | 5
1201 | Yes | Auto Scheduled | Extract File | 1h | June 11, 2026 1:45 | June 11, 2026 2:45 | 1180 | 6
1202 | Yes | Auto Scheduled | Pre Load Validation | 0.5h | June 11, 2026 2:45 | June 11, 2026 3:15 | 1201 | 6
1203 | Yes | Auto Scheduled | Simulate Load | 15.5h | June 11, 2026 3:15 | June 15, 2026 3:15 | 1202 | 6
1204 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | June 15, 2026 3:15 | June 15, 2026 3:45 | 1203 | 6
1205 | Yes | Auto Scheduled | Load | 1h | June 15, 2026 3:45 | June 15, 2026 5:00 | 1204 | 6 | 4/17- Bom issues and not moving to routings...
1206 | Yes | Auto Scheduled | Post Load Validation | 0.5h | June 16, 2026 8:00 | June 16, 2026 8:38 | 1205 | 6 | 4/16 - updated to post load...
1207 | Yes | Auto Scheduled | PTM_CM40_Work Center Conversion | 3.08d | June 11, 2026 2:45 | June 16, 2026 3:23 |  | 5
1208 | Yes | Auto Scheduled | Extract File | 1h | June 11, 2026 2:45 | June 11, 2026 3:45 | 1201 | 6
1209 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 16, 2026 8:38 | June 16, 2026 10:38 | 1206 | 6
1210 | Yes | Auto Scheduled | Simulate Load | 0.25h | June 16, 2026 10:38 | June 16, 2026 10:53 | 1209 | 6
1211 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | June 16, 2026 10:53 | June 16, 2026 11:23 | 1210 | 6 | 4/16- Defect created
1212 | Yes | Auto Scheduled | Load | 1h | June 16, 2026 11:23 | June 16, 2026 1:23 | 1211 | 6
1213 | Yes | Auto Scheduled | Post Load Validation | 2h | June 16, 2026 1:23 | June 16, 2026 3:23 | 1212 | 6
1214 | Yes | Auto Scheduled | PTM_CM38_Routing Conversion | 4.27d | June 11, 2026 3:45 | June 18, 2026 8:53 |  | 5
1215 | Yes | Auto Scheduled | Extract File | 1h | June 11, 2026 3:45 | June 11, 2026 4:45 | 1208 | 6
1216 | Yes | Auto Scheduled | Pre Load Validation | 2h | June 16, 2026 3:23 | June 17, 2026 10:53 | 1213 | 6
1217 | Yes | Auto Scheduled | Simulate Load | 2h | June 17, 2026 10:53 | June 17, 2026 1:53 | 1216 | 6 | 4/20 Cost element has been resolved and now ready to run simulation again. Need to decide if we need to load all routings or load what we have that will load
1218 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | June 17, 2026 10:53 | June 17, 2026 2:53 | 1217SS | 6
1219 | Yes | Auto Scheduled | Load | 1h | June 17, 2026 2:53 | June 17, 2026 3:53 | 1218 | 6
1220 | Yes | Auto Scheduled | Post Load Validation | 2h | June 17, 2026 3:53 | June 18, 2026 8:53 | 1219 | 6
1221 | Yes | Auto Scheduled | PTM_CM36_Production Version Conversion | 1.13d | June 11, 2026 4:45 | June 15, 2026 8:45 |  | 5
1222 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 11, 2026 4:45 | June 12, 2026 8:15 | 1215 | 6
1223 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 12, 2026 8:15 | June 12, 2026 8:45 | 1222 | 6
1224 | Yes | Auto Scheduled | Simulate Load | 1h | June 12, 2026 8:45 | June 12, 2026 9:45 | 1223 | 6
1225 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 12, 2026 9:45 | June 12, 2026 11:45 | 1224 | 6
1226 | Yes | Auto Scheduled | Load | 2h | June 12, 2026 11:45 | June 12, 2026 2:45 | 1225 | 6
1227 | Yes | Auto Scheduled | Post Load Validation | 3h | June 12, 2026 2:45 | June 15, 2026 8:45 | 1226 | 6
1228 | Yes | Auto Scheduled | PTM_CM35_Inspection Plan | 1.13d | June 15, 2026 8:45 | June 16, 2026 9:45 |  | 5 | 4/17 - will manually load IP for ITC1
1229 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 15, 2026 8:45 | June 15, 2026 9:15 | 1227 | 6 | 4/20- Per Brad they will load manaually for ITC1
1230 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 15, 2026 9:15 | June 15, 2026 9:45 | 1229 | 6
1231 | Yes | Auto Scheduled | Simulate Load | 1h | June 15, 2026 9:45 | June 15, 2026 10:45 | 1230 | 6
1232 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 15, 2026 10:45 | June 15, 2026 1:45 | 1231 | 6
1233 | Yes | Auto Scheduled | Load | 2h | June 15, 2026 1:45 | June 15, 2026 3:45 | 1232 | 6
1234 | Yes | Auto Scheduled | Post Load Validation | 3h | June 15, 2026 3:45 | June 16, 2026 9:45 | 1233 | 6
1235 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Serial Numbers | 1.13d | June 15, 2026 9:15 | June 16, 2026 10:15 |  | 5 | 4/17- will cherry pick equiments for testing ITC1/Smoke
1236 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 15, 2026 9:15 | June 15, 2026 9:45 | 1229 | 6
1237 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 15, 2026 9:45 | June 15, 2026 10:15 | 1236 | 6
1238 | Yes | Auto Scheduled | Simulate Load | 1h | June 15, 2026 10:15 | June 15, 2026 11:15 | 1237 | 6
1239 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 15, 2026 11:15 | June 15, 2026 2:15 | 1238 | 6
1240 | Yes | Auto Scheduled | Load | 2h | June 15, 2026 2:15 | June 15, 2026 4:15 | 1239 | 6
1241 | Yes | Auto Scheduled | Post Load Validation | 3h | June 15, 2026 4:15 | June 16, 2026 10:15 | 1240 | 6
1242 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Service | 6.78d | June 8, 2026 10:00 | June 17, 2026 8:15 |  | 5 | 4/17- will cherry pick equiments for testing ITC1/Smoke
1243 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 16, 2026 10:15 | June 16, 2026 10:45 | 1241 | 6
1244 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 16, 2026 10:45 | June 16, 2026 11:15 | 1243 | 6
1245 | Yes | Auto Scheduled | Simulate Load | 1h | June 16, 2026 11:15 | June 16, 2026 1:15 | 1244 | 6
1246 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 16, 2026 1:15 | June 16, 2026 3:15 | 1245 | 6
1247 | Yes | Auto Scheduled | Load | 2h | June 16, 2026 3:15 | June 17, 2026 8:15 | 1246 | 6
1248 | Yes | Auto Scheduled | Post Load Validation | 3h | June 8, 2026 10:00 | June 8, 2026 2:00 |  | 6
1249 | Yes | Auto Scheduled | VC_Object Dependencies | 0.63d | June 8, 2026 10:00 | June 8, 2026 4:00 |  | 5
1250 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | June 8, 2026 10:00 | June 8, 2026 12:00 |  | 6
1251 | Yes | Auto Scheduled | Post Load Validation | 3h | June 8, 2026 1:00 | June 8, 2026 4:00 | 1250 | 6
1252 | Yes | Auto Scheduled | VC_Characteristics | 0.63d | June 8, 2026 4:00 | June 9, 2026 12:00 |  | 5
1253 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | June 8, 2026 4:00 | June 9, 2026 9:00 | 1251 | 6
1254 | Yes | Auto Scheduled | Post Load Validation | 3h | June 9, 2026 9:00 | June 9, 2026 12:00 | 1253 | 6
1255 | Yes | Auto Scheduled | VC_Classes | 0.63d | June 9, 2026 1:00 | June 10, 2026 9:00 |  | 5
1256 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | June 9, 2026 1:00 | June 9, 2026 3:00 | 1254 | 6
1257 | Yes | Auto Scheduled | Post Load Validation | 3h | June 9, 2026 3:00 | June 10, 2026 9:00 | 1256 | 6
1258 | Yes | Auto Scheduled | VC_Classification (Class Type 200) | 0.63d | June 11, 2026 11:45 | June 12, 2026 8:45 |  | 5
1259 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | June 11, 2026 11:45 | June 11, 2026 2:45 | 1178 | 6
1260 | Yes | Auto Scheduled | Post Load Validation | 3h | June 11, 2026 2:45 | June 12, 2026 8:45 | 1259 | 6
1261 | Yes | Auto Scheduled | VC_Dependency Nets | 0.63d | June 11, 2026 11:45 | June 12, 2026 8:45 |  | 5
1262 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | June 11, 2026 11:45 | June 11, 2026 2:45 | 1172,1257 | 6
1263 | Yes | Auto Scheduled | Post Load Validation | 3h | June 11, 2026 2:45 | June 12, 2026 8:45 | 1262 | 6
1264 | Yes | Auto Scheduled | VC_Configuration Profiles | 0.63d | June 11, 2026 11:45 | June 12, 2026 8:45 |  | 5
1265 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | June 11, 2026 11:45 | June 11, 2026 2:45 | 1172 | 6
1266 | Yes | Auto Scheduled | Post Load Validation | 3h | June 11, 2026 2:45 | June 12, 2026 8:45 | 1265 | 6
1267 | Yes | Auto Scheduled | VC_Variant Tables | 0.63d | June 12, 2026 8:45 | June 12, 2026 2:45 |  | 5
1268 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | June 12, 2026 8:45 | June 12, 2026 10:45 | 1266 | 6
1269 | Yes | Auto Scheduled | Post Load Validation | 3h | June 12, 2026 10:45 | June 12, 2026 2:45 | 1268 | 6
1270 | Yes | Auto Scheduled | VC_Variant Tables Content | 0.63d | June 12, 2026 2:45 | June 15, 2026 10:45 |  | 5
1271 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | June 12, 2026 2:45 | June 12, 2026 4:45 | 1269 | 6
1272 | Yes | Auto Scheduled | Post Load Validation | 3h | June 12, 2026 4:45 | June 15, 2026 10:45 | 1271 | 6
1273 | Yes | Auto Scheduled | VC_Characteristic Groups | 1.97d | June 12, 2026 8:45 | June 16, 2026 8:30 |  | 5 | 4/20- Defect - 963
1274 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 12.75h | June 12, 2026 8:45 | June 15, 2026 2:30 | 1266 | 6 | 4/17 - Authorization error/loaded but getting in app is issue. 4/20 Defect recorded and still open
1275 | Yes | Auto Scheduled | Post Load Validation | 3h | June 15, 2026 2:30 | June 16, 2026 8:30 | 1274 | 6
1276 | Yes | Auto Scheduled | PTM_CM52_Super_BOM | 2d | June 11, 2026 11:45 | June 15, 2026 11:45 |  | 5 | 4/21- Pittsburg was loaded and working on remaining sites 4/20 - Working through errors with materials
1277 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 11, 2026 11:45 | June 11, 2026 1:15 | 1178 | 6
1278 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 11, 2026 1:15 | June 11, 2026 1:45 | 1277 | 6
1279 | Yes | Auto Scheduled | Simulate Load | 8h | June 11, 2026 1:45 | June 12, 2026 1:45 | 1278 | 6 | 4/17 - Have issues and Manoj to work with Chip
1280 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 12, 2026 1:45 | June 12, 2026 3:45 | 1279 | 6 | 4/16- Reviewing some errors , 4/17- Still running into errors
1281 | Yes | Auto Scheduled | Load | 2h | June 12, 2026 3:45 | June 15, 2026 8:45 | 1280 | 6
1282 | Yes | Auto Scheduled | Post Load Validation | 3h | June 15, 2026 8:45 | June 15, 2026 11:45 | 1281 | 6
1283 | Yes | Auto Scheduled | PTM_CM53_Super_Routing | 2.13d | June 15, 2026 11:45 | June 17, 2026 1:45 |  | 5
1284 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 15, 2026 11:45 | June 15, 2026 1:15 | 1282 | 6
1285 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 15, 2026 1:15 | June 15, 2026 1:45 | 1284 | 6
1286 | Yes | Auto Scheduled | Simulate Load | 1h | June 15, 2026 1:45 | June 16, 2026 2:45 | 1285 | 6
1287 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 16, 2026 2:45 | June 16, 2026 4:45 | 1286 | 6
1288 | Yes | Auto Scheduled | Load | 2h | June 16, 2026 4:45 | June 17, 2026 9:45 | 1287 | 6
1289 | Yes | Auto Scheduled | Post Load Validation | 3h | June 17, 2026 9:45 | June 17, 2026 1:45 | 1288 | 6 | 4/22 -Loaded for Pittsburg
1290 | Yes | Auto Scheduled | VC_VK30 Pricing Variant | 0.69d | June 17, 2026 9:45 | June 17, 2026 4:15 |  | 5
1291 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | June 17, 2026 9:45 | June 17, 2026 10:15 | 1288 | 6
1292 | Yes | Auto Scheduled | Load | 2h | June 17, 2026 10:15 | June 17, 2026 1:15 | 1291 | 6
1293 | Yes | Auto Scheduled | Post Load Validation | 3h | June 17, 2026 1:15 | June 17, 2026 4:15 | 1292 | 6
1294 | Yes | Auto Scheduled | OTC_CM22_Pricing_Condition | 0.69d | June 17, 2026 4:15 | June 18, 2026 1:45 |  | 5
1295 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | June 17, 2026 4:15 | June 17, 2026 4:45 | 1293 | 6
1296 | Yes | Auto Scheduled | Load | 2h | June 17, 2026 4:45 | June 18, 2026 9:45 | 1295 | 6
1297 | Yes | Auto Scheduled | Post Load Validation | 3h | June 18, 2026 9:45 | June 18, 2026 1:45 | 1296 | 6 | 4/16 - Service to load
1298 | Yes | Auto Scheduled | OTC_CM21_CMIR | 0.5d | June 18, 2026 9:45 | June 18, 2026 2:45 |  | 5
1299 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 18, 2026 9:45 | June 18, 2026 10:15 | 1296,1307 | 6
1300 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 18, 2026 10:15 | June 18, 2026 10:45 | 1299 | 6
1301 | Yes | Auto Scheduled | Simulate Load | 0h | June 18, 2026 10:45 | June 18, 2026 10:45 | 1300 | 6
1302 | Yes | Auto Scheduled | Error and Defect Mitigation | 0h | June 18, 2026 10:45 | June 18, 2026 10:45 | 1301 | 6
1303 | Yes | Auto Scheduled | Load | 0h | June 18, 2026 10:45 | June 18, 2026 10:45 | 1302 | 6 | 4/16 - Load done
1304 | Yes | Auto Scheduled | Post Load Validation | 3h | June 18, 2026 10:45 | June 18, 2026 2:45 | 1303 | 6
1305 | Yes | Auto Scheduled | PTP_CM29_Source_List | 6.16d | June 9, 2026 11:00 | June 17, 2026 1:15 |  | 5
1306 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | June 9, 2026 11:00 | June 9, 2026 11:30 | 1149,1156 | 6 | 4/16 -
1307 | Yes | Auto Scheduled | Load | 2h | June 16, 2026 4:15 | June 17, 2026 9:15 | 1125 | 6
1308 | Yes | Auto Scheduled | Post Load Validation | 3h | June 17, 2026 9:15 | June 17, 2026 1:15 | 1307 | 6
1309 | Yes | Auto Scheduled | RTR_CM11_Asset_Master | 3.75d | June 8, 2026 10:00 | June 11, 2026 5:00 |  | 5 | 4/20- Move to ITC2
1310 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 8, 2026 10:00 | June 8, 2026 10:30 |  | 6
1311 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 8, 2026 10:30 | June 8, 2026 11:00 | 1310 | 6
1312 | Yes | Auto Scheduled | Simulate Load | 8h | June 8, 2026 11:00 | June 9, 2026 11:00 | 1311 | 6 | 4/17 - Going back and forth
1313 | Yes | Auto Scheduled | Error and Defect Mitigation | 16h | June 9, 2026 11:00 | June 11, 2026 11:00 | 1312 | 6
1314 | Yes | Auto Scheduled | Load | 2h | June 11, 2026 11:00 | June 11, 2026 2:00 | 1313 | 6
1315 | Yes | Auto Scheduled | Post Load Validation | 3h | June 11, 2026 2:00 | June 11, 2026 5:00 | 1314 | 6
1316 | Yes | Auto Scheduled | PTM_CM50_Material Class | 2.13d | June 12, 2026 8:15 | June 16, 2026 9:15 |  | 5
1317 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | June 12, 2026 8:15 | June 12, 2026 8:45 | 1222 | 6
1318 | Yes | Auto Scheduled | Load | 30m | June 12, 2026 8:45 | June 12, 2026 9:15 | 1317 | 6 | 4/17 -Manually loaded
1319 | Yes | Auto Scheduled | Post Load Validation | 16h | June 12, 2026 9:15 | June 16, 2026 9:15 | 1318 | 6 | 4/16 - Will load manually
1320 | Yes | Auto Scheduled | PTM_CM55_Class assignment to materials | 1.13d | June 12, 2026 8:45 | June 15, 2026 9:45 |  | 5 | 4/16 - Is not being loaded part of ITC1
1321 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 12, 2026 8:45 | June 12, 2026 9:15 | 1317 | 6
1322 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 12, 2026 9:15 | June 12, 2026 9:45 | 1321 | 6
1323 | Yes | Auto Scheduled | Simulate Load | 1h | June 12, 2026 9:45 | June 12, 2026 10:45 | 1322 | 6
1324 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 12, 2026 10:45 | June 12, 2026 1:45 | 1323 | 6
1325 | Yes | Auto Scheduled | Load | 2h | June 12, 2026 1:45 | June 12, 2026 3:45 | 1324 | 6
1326 | Yes | Auto Scheduled | Post Load Validation | 3h | June 12, 2026 3:45 | June 15, 2026 9:45 | 1325 | 6
1327 | Yes | Auto Scheduled | GTS - Material initial load from S4 (Run Interface) | 2.09d | June 11, 2026 2:45 | June 15, 2026 3:30 |  | 5
1328 | Yes | Auto Scheduled | Run material interface to GTS | 15.75h | June 11, 2026 2:45 | June 15, 2026 2:30 | 1196 | 6
1329 | Yes | Auto Scheduled | Post Load Validation | 1h | June 15, 2026 2:30 | June 15, 2026 3:30 | 1328 | 6
1330 | Yes | Auto Scheduled | GTS - Customers initial load from S4 (Run Interface) | 0.25d | June 8, 2026 10:00 | June 8, 2026 12:00 |  | 5
1331 | Yes | Auto Scheduled | Run material interface to GTS | 1h | June 8, 2026 10:00 | June 8, 2026 11:00 |  | 6
1332 | Yes | Auto Scheduled | Post Load Validation | 1h | June 8, 2026 11:00 | June 8, 2026 12:00 | 1331 | 6 | 4/17 99% complete ran in to some erros with defect 934
1333 | Yes | Auto Scheduled | GTS - Vendors initial load from S4 (Run Interface) | 0.25d | June 9, 2026 9:00 | June 9, 2026 11:00 |  | 5
1334 | Yes | Auto Scheduled | Run material interface to GTS | 1h | June 9, 2026 9:00 | June 9, 2026 10:00 | 1139 | 6 | 4/16- Have 3 records with issues
1335 | Yes | Auto Scheduled | Post Load Validation | 1h | June 9, 2026 10:00 | June 9, 2026 11:00 | 1334 | 6
1336 | Yes | Auto Scheduled | GTS - ECCN - Create | 1.13d | June 8, 2026 10:00 | June 9, 2026 11:00 |  | 5
1337 | Yes | Auto Scheduled | Load Descartes XML File | 1h | June 8, 2026 10:00 | June 8, 2026 11:00 |  | 6
1338 | Yes | Auto Scheduled | Post Load Validation | 1h | June 9, 2026 10:00 | June 9, 2026 11:00 | 1334 | 6
1339 | Yes | Auto Scheduled | GTS - ECCN - Assign | 0.25d | June 15, 2026 3:30 | June 16, 2026 8:30 |  | 5
1340 | Yes | Auto Scheduled | Load Descartes XML File | 1h | June 15, 2026 3:30 | June 15, 2026 4:30 | 1329 | 6
1341 | Yes | Auto Scheduled | Post Load Validation | 1h | June 15, 2026 4:30 | June 16, 2026 8:30 | 1340 | 6
1342 | Yes | Auto Scheduled | GTS - HTS - Create | 0.25d | June 8, 2026 10:00 | June 8, 2026 12:00 |  | 5
1343 | Yes | Auto Scheduled | Load Descartes XML File | 1h | June 8, 2026 10:00 | June 8, 2026 11:00 |  | 6
1344 | Yes | Auto Scheduled | Post Load Validation | 1h | June 8, 2026 11:00 | June 8, 2026 12:00 | 1343 | 6
1345 | Yes | Auto Scheduled | GTS - HTS - Assign | 0.25d | June 16, 2026 8:30 | June 16, 2026 10:30 |  | 5
1346 | Yes | Auto Scheduled | Load Descartes XML File | 1h | June 16, 2026 8:30 | June 16, 2026 9:30 | 1341 | 6
1347 | Yes | Auto Scheduled | Post Load Validation | 1h | June 16, 2026 9:30 | June 16, 2026 10:30 | 1346 | 6
1348 | Yes | Auto Scheduled | GTS - License - Create | 0.25d | June 16, 2026 11:30 | June 16, 2026 2:30 |  | 5
1349 | Yes | Auto Scheduled | Load Descartes XML File | 1h | June 16, 2026 11:30 | June 16, 2026 1:30 | 1346,1362 | 6 | 4/13 - Need to update dep.
1350 | Yes | Auto Scheduled | Post Load Validation | 1h | June 16, 2026 1:30 | June 16, 2026 2:30 | 1349 | 6
1351 | Yes | Auto Scheduled | Commodity Code/Tarif | 2.78d | June 16, 2026 10:30 | June 19, 2026 8:45 |  | 5
1352 | Yes | Auto Scheduled | Load | 21.25h | June 16, 2026 10:30 | June 18, 2026 4:45 | 1347 | 6 | 4/17- wants to use the old load program
1353 | Yes | Auto Scheduled | Post Load Validation | 1h | June 18, 2026 4:45 | June 19, 2026 8:45 | 1352 | 6
1354 | Yes | Auto Scheduled | SPL Master File | 0.25d | June 16, 2026 9:30 | June 16, 2026 11:30 |  | 5
1355 | Yes | Auto Scheduled | Load | 1h | June 16, 2026 9:30 | June 16, 2026 10:30 | 1346 | 6
1356 | Yes | Auto Scheduled | Post Load Validation | 1h | June 16, 2026 10:30 | June 16, 2026 11:30 | 1355 | 6
1357 | Yes | Auto Scheduled | Initialize Embargo situation | 0.38d | June 9, 2026 11:00 | June 9, 2026 3:00 |  | 5
1358 | Yes | Auto Scheduled | Run report /SAPSLL/EMB_CNTRY_INIT | 1h | June 9, 2026 11:00 | June 9, 2026 12:00 | 1338 | 6
1359 | Yes | Auto Scheduled | Set Embargo situations | 1h | June 9, 2026 1:00 | June 9, 2026 2:00 | 1358 | 6 | 4/17 - Needs access
1360 | Yes | Auto Scheduled | Post Load Validation | 1h | June 9, 2026 2:00 | June 9, 2026 3:00 | 1359 | 6
1361 | Yes | Auto Scheduled | GTS - SPL (Sanctioned party list) | 0.25d | June 16, 2026 10:30 | June 16, 2026 1:30 |  | 5
1362 | Yes | Auto Scheduled | Load Descartes XML File | 1h | June 16, 2026 10:30 | June 16, 2026 11:30 | 1347 | 6
1363 | Yes | Auto Scheduled | Post Load Validation | 1h | June 16, 2026 11:30 | June 16, 2026 1:30 | 1362 | 6
1364 | Yes | Auto Scheduled | RTR_CM17_Project Definition / Builder | 1.13d | June 8, 2026 10:30 | June 9, 2026 11:30 |  | 5 | 4/20 - Will have files to load in the morning
1365 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 8, 2026 10:30 | June 8, 2026 11:00 | 1310 | 6
1366 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 8, 2026 11:00 | June 8, 2026 11:30 | 1365 | 6
1367 | Yes | Auto Scheduled | Simulate Load | 1h | June 8, 2026 11:30 | June 8, 2026 1:30 | 1366 | 6
1368 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 8, 2026 1:30 | June 8, 2026 3:30 | 1367 | 6
1369 | Yes | Auto Scheduled | Load | 2h | June 8, 2026 3:30 | June 9, 2026 8:30 | 1368 | 6
1370 | Yes | Auto Scheduled | Post Load Validation | 3h | June 9, 2026 8:30 | June 9, 2026 11:30 | 1369 | 6
1371 | Yes | Auto Scheduled | RTR_CM18_WBS Element | 1.13d | June 8, 2026 11:00 | June 9, 2026 12:00 |  | 5
1372 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | June 8, 2026 11:00 | June 8, 2026 11:30 | 1365 | 6
1373 | Yes | Auto Scheduled | Pre Load Validation | 30m | June 8, 2026 11:30 | June 8, 2026 12:00 | 1372 | 6
1374 | Yes | Auto Scheduled | Simulate Load | 1h | June 8, 2026 1:00 | June 8, 2026 2:00 | 1373 | 6
1375 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | June 8, 2026 2:00 | June 8, 2026 4:00 | 1374 | 6
1376 | Yes | Auto Scheduled | Load | 2h | June 8, 2026 4:00 | June 9, 2026 9:00 | 1375 | 6
1377 | Yes | Auto Scheduled | Post Load Validation | 3h | June 9, 2026 9:00 | June 9, 2026 12:00 | 1376 | 6
1378 | Yes | Auto Scheduled | ITC3 Master Data Loads Complete | 0m | June 19, 2026 4:00 | June 19, 2026 4:00 | 1011 | 4
1379 | Yes | Auto Scheduled | Mock Transactional Data | 2d | June 19, 2026 4:00 | June 23, 2026 4:00 | 1378 | 4
1380 | Yes | Auto Scheduled | Inventory | 4h | June 19, 2026 4:00 | June 22, 2026 11:00 | 998SS | 5
1381 | Yes | Auto Scheduled | Open AR | 4h | June 22, 2026 11:00 | June 22, 2026 4:00 | 1380 | 5
1382 | Yes | Auto Scheduled | Open AP | 4h | June 22, 2026 4:00 | June 23, 2026 11:00 | 1381 | 5
1383 | Yes | Auto Scheduled | Bank and Cash | 4h | June 23, 2026 11:00 | June 23, 2026 4:00 | 1382 | 5
1384 | Yes | Auto Scheduled | Open Purchase Orders(Manual) | 1d | June 22, 2026 11:00 | June 23, 2026 11:00 | 1380 | 5
1385 | Yes | Auto Scheduled | Open Sales Orders(Manual) | 1d | June 22, 2026 11:00 | June 23, 2026 11:00 | 1380 | 5
1386 | Yes | Auto Scheduled | Service Orders(Manual) | 0.5d | June 22, 2026 11:00 | June 22, 2026 4:00 | 1380 | 5
1387 | Yes | Auto Scheduled | Open Production Orders(Manual) | 1d | June 22, 2026 11:00 | June 23, 2026 11:00 | 1380 | 5
1388 | Yes | Auto Scheduled | ITC3 Mock Data Loads Complete | 0m | June 23, 2026 4:00 | June 23, 2026 4:00 | 1379 | 4
1389 | Yes | Auto Scheduled | UAT Data Load Tasks QS4 | 80.66d | June 22, 2026 8:00 | October 12, 2026 2:15 | 1009,103,134 | 3
1390 | Yes | Auto Scheduled | PMO Authorization to Start Data Loads | 1m | June 22, 2026 8:00 | June 22, 2026 8:01 | 103,134 | 4
1391 | Yes | Auto Scheduled | Master Data Loads | 10.56d | September 24, 2026 8:30 | October 8, 2026 2:00 | 1390 | 4
1392 | Yes | Auto Scheduled | RTR_CM02_Profit Center Hierarchy | 0.75d | September 24, 2026 8:30 | September 24, 2026 3:30 |  | 5
1393 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | September 24, 2026 8:30 | September 24, 2026 9:30 | 1390 | 6
1394 | Yes | Auto Scheduled | Load | 2h | September 24, 2026 9:30 | September 24, 2026 11:30 | 1393 | 6
1395 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 11:30 | September 24, 2026 3:30 | 1394 | 6
1396 | Yes | Auto Scheduled | RTR_CM03_Cost Center Hierarchy | 0.75d | September 24, 2026 3:30 | September 25, 2026 1:30 |  | 5
1397 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | September 24, 2026 3:30 | September 24, 2026 4:30 | 1395 | 6
1398 | Yes | Auto Scheduled | Load | 2h | September 24, 2026 4:30 | September 25, 2026 9:30 | 1397 | 6
1399 | Yes | Auto Scheduled | Post Load Validation | 3h | September 25, 2026 9:30 | September 25, 2026 1:30 | 1398 | 6
1400 | Yes | Auto Scheduled | RTR_CM01_GL_Account_Master to CC 1000 | 2.44d | September 25, 2026 1:30 | September 29, 2026 5:00 |  | 5
1401 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 25, 2026 1:30 | September 25, 2026 2:30 | 1399 | 6
1402 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 25, 2026 2:30 | September 25, 2026 4:30 | 1401 | 6
1403 | Yes | Auto Scheduled | Simulate Load | 6h | September 25, 2026 4:30 | September 28, 2026 2:30 | 1402 | 6
1404 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 28, 2026 2:30 | September 29, 2026 9:00 | 1403 | 6
1405 | Yes | Auto Scheduled | Load | 1h | September 29, 2026 9:00 | September 29, 2026 10:00 | 1404 | 6
1406 | Yes | Auto Scheduled | Post Load Validation | 2h | September 29, 2026 10:00 | September 29, 2026 12:00 | 1405 | 6
1407 | Yes | Auto Scheduled | Extend GL to all Company Codes | 2h | September 29, 2026 1:00 | September 29, 2026 3:00 | 1406 | 6
1408 | Yes | Auto Scheduled | Post GL Extention Validation | 2h | September 29, 2026 3:00 | September 29, 2026 5:00 | 1407 | 6
1409 | Yes | Auto Scheduled | RTR_CM05_Profit_Center | 1.13d | September 24, 2026 3:30 | September 25, 2026 4:30 |  | 5
1410 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 24, 2026 3:30 | September 24, 2026 4:30 | 1395 | 6
1411 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 24, 2026 4:30 | September 25, 2026 9:30 | 1410 | 6
1412 | Yes | Auto Scheduled | Simulate Load | 1h | September 25, 2026 9:30 | September 25, 2026 10:30 | 1411 | 6
1413 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 25, 2026 10:30 | September 25, 2026 1:30 | 1412 | 6
1414 | Yes | Auto Scheduled | Load | 1h | September 25, 2026 1:30 | September 25, 2026 2:30 | 1413 | 6
1415 | Yes | Auto Scheduled | Post Load Validation | 2h | September 25, 2026 2:30 | September 25, 2026 4:30 | 1414 | 6
1416 | Yes | Auto Scheduled | RTR_CM04_Cost_Center | 1.13d | September 25, 2026 4:30 | September 29, 2026 8:30 |  | 5
1417 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 25, 2026 4:30 | September 28, 2026 8:30 | 1415 | 6
1418 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 28, 2026 8:30 | September 28, 2026 10:30 | 1417 | 6
1419 | Yes | Auto Scheduled | Simulate Load | 1h | September 28, 2026 10:30 | September 28, 2026 11:30 | 1418 | 6
1420 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 28, 2026 11:30 | September 28, 2026 2:30 | 1419 | 6
1421 | Yes | Auto Scheduled | Load | 1h | September 28, 2026 2:30 | September 28, 2026 3:30 | 1420 | 6
1422 | Yes | Auto Scheduled | Post Load Validation | 2h | September 28, 2026 3:30 | September 29, 2026 8:30 | 1421 | 6
1423 | Yes | Auto Scheduled | Manual Configuration Activities in QS5 | 8.94d | September 24, 2026 8:30 | October 6, 2026 5:00 | 40 | 5
1424 | Yes | Auto Scheduled | Open Client | 30m | September 24, 2026 8:30 | September 24, 2026 9:00 |  | 6
1425 | Yes | Auto Scheduled | Service Enterprise Setup | 5d | September 30, 2026 8:00 | October 6, 2026 5:00 | 1392,1396,1400 | 6
1426 | Yes | Auto Scheduled | Close Client | 30m | September 24, 2026 8:30 | September 24, 2026 9:00 |  | 6
1427 | Yes | Auto Scheduled | Intercompany Business Partner Setup | 2h | September 30, 2026 8:00 | September 30, 2026 10:00 | 1392,1396,1408 | 6
1428 | Yes | Auto Scheduled | RTR_CM09_Activity_Type | 1.38d | September 29, 2026 1:00 | September 30, 2026 4:00 |  | 5
1429 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 29, 2026 1:00 | September 29, 2026 3:15 | 1406 | 6
1430 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 29, 2026 3:15 | September 30, 2026 9:00 | 1429 | 6
1431 | Yes | Auto Scheduled | Simulate Load | 1h | September 30, 2026 9:00 | September 30, 2026 10:00 | 1430 | 6
1432 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 30, 2026 10:00 | September 30, 2026 12:00 | 1431 | 6
1433 | Yes | Auto Scheduled | Load | 1h | September 30, 2026 1:00 | September 30, 2026 2:00 | 1432 | 6
1434 | Yes | Auto Scheduled | Post Load Validation | 2h | September 30, 2026 2:00 | September 30, 2026 4:00 | 1433 | 6
1435 | Yes | Auto Scheduled | RTR_CM12_Activity Rates | 1.13d | September 25, 2026 1:30 | September 28, 2026 2:30 |  | 5
1436 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 25, 2026 1:30 | September 25, 2026 2:30 | 1399 | 6
1437 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 25, 2026 2:30 | September 25, 2026 4:30 | 1436 | 6
1438 | Yes | Auto Scheduled | Simulate Load | 1h | September 25, 2026 4:30 | September 28, 2026 8:30 | 1437 | 6
1439 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 28, 2026 8:30 | September 28, 2026 10:30 | 1438 | 6
1440 | Yes | Auto Scheduled | Load | 1h | September 28, 2026 10:30 | September 28, 2026 11:30 | 1439 | 6
1441 | Yes | Auto Scheduled | Post Load Validation | 2h | September 28, 2026 11:30 | September 28, 2026 2:30 | 1440 | 6
1442 | Yes | Auto Scheduled | RTR_CM06_Bank_master | 3.81d | September 24, 2026 8:30 | September 29, 2026 4:00 |  | 5
1443 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 29, 2026 1:00 | September 29, 2026 2:00 | 1406 | 6
1444 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 29, 2026 2:00 | September 29, 2026 4:00 | 1443 | 6
1445 | Yes | Auto Scheduled | Simulate Load | 1h | September 24, 2026 8:30 | September 24, 2026 9:30 |  | 6
1446 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 24, 2026 9:30 | September 24, 2026 11:30 | 1445 | 6
1447 | Yes | Auto Scheduled | Load | 5h | September 24, 2026 11:30 | September 25, 2026 8:30 | 1446 | 6
1448 | Yes | Auto Scheduled | Post Load Validation | 2h | September 25, 2026 8:30 | September 25, 2026 3:00 | 1447 | 6
1449 | Yes | Auto Scheduled | RTR_CM08_Exchange_Rates | 1.13d | September 25, 2026 8:30 | September 28, 2026 9:30 |  | 5
1450 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 25, 2026 8:30 | September 25, 2026 9:30 | 1447 | 6
1451 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 25, 2026 9:30 | September 25, 2026 11:30 | 1450 | 6
1452 | Yes | Auto Scheduled | Simulate Load | 1h | September 25, 2026 11:30 | September 25, 2026 1:30 | 1451 | 6
1453 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 25, 2026 1:30 | September 25, 2026 3:30 | 1452 | 6
1454 | Yes | Auto Scheduled | Load | 1h | September 25, 2026 3:30 | September 25, 2026 4:30 | 1453 | 6
1455 | Yes | Auto Scheduled | Post Load Validation | 2h | September 25, 2026 4:30 | September 28, 2026 9:30 | 1454 | 6
1456 | Yes | Auto Scheduled | RTR_CM14_Cost Element_Group | 4.44d | September 29, 2026 1:00 | October 5, 2026 4:30 |  | 5
1457 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | September 29, 2026 1:00 | September 29, 2026 1:30 | 1406 | 6
1458 | Yes | Auto Scheduled | Load | 32h | September 29, 2026 1:30 | October 5, 2026 1:30 | 1457 | 6
1459 | Yes | Auto Scheduled | Post Load Validation | 3h | October 5, 2026 1:30 | October 5, 2026 4:30 | 1458 | 6
1460 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Bill-To | 2h | September 24, 2026 8:30 | September 24, 2026 10:30 |  | 5 | 4/20 Per OTC this is not needed for ITC1
1461 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Ship-To | 1.5d | September 29, 2026 1:00 | September 30, 2026 5:00 |  | 5
1462 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 1:00 | September 29, 2026 1:30 | 1406 | 6
1463 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 1:30 | September 29, 2026 2:00 | 1462 | 6
1464 | Yes | Auto Scheduled | Open client for BP number range update | 30m | September 29, 2026 2:00 | September 29, 2026 2:30 | 1463 | 6
1465 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 30m | September 29, 2026 2:30 | September 29, 2026 3:00 | 1464 | 6
1466 | Yes | Auto Scheduled | Close Client | 15m | September 29, 2026 3:00 | September 29, 2026 3:15 | 1465 | 6
1467 | Yes | Auto Scheduled | Simulate Load | 1h | September 29, 2026 2:00 | September 29, 2026 3:00 | 1463 | 6
1468 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | September 29, 2026 3:00 | September 30, 2026 10:00 | 1467 | 6
1469 | Yes | Auto Scheduled | Load | 3h | September 30, 2026 10:00 | September 30, 2026 2:00 | 1468 | 6
1470 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 2:00 | September 30, 2026 5:00 | 1469 | 6
1471 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Sold-To | 1.63d | September 29, 2026 2:00 | October 1, 2026 10:00 |  | 5
1472 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 2:00 | September 29, 2026 2:30 | 1463 | 6
1473 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 2:30 | September 29, 2026 3:00 | 1472 | 6
1474 | Yes | Auto Scheduled | Simulate Load | 1h | September 30, 2026 8:00 | September 30, 2026 9:00 | 1408,1467 | 6
1475 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | September 30, 2026 9:00 | September 30, 2026 12:00 | 1474 | 6
1476 | Yes | Auto Scheduled | Load | 3h | September 30, 2026 1:00 | September 30, 2026 4:00 | 1475 | 6
1477 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 4:00 | October 1, 2026 10:00 | 1476 | 6
1478 | Yes | Auto Scheduled | Open client for BP number range update | 15m | September 29, 2026 3:00 | September 29, 2026 3:15 | 1467 | 6
1479 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 15m | September 29, 2026 3:15 | September 29, 2026 3:30 | 1478 | 6
1480 | Yes | Auto Scheduled | Close Client | 15m | September 29, 2026 3:30 | September 29, 2026 3:45 | 1479 | 6
1481 | Yes | Auto Scheduled | PTP_CM27_Vendor Master as Customer - FLCU01 | 4.81d | September 30, 2026 4:00 | October 7, 2026 2:30 |  | 5
1482 | Yes | Auto Scheduled | Extract File | 1h | September 30, 2026 4:00 | September 30, 2026 5:00 | 1476 | 6
1483 | Yes | Auto Scheduled | Pre Load Validation | 2h | October 1, 2026 8:00 | October 1, 2026 10:00 | 1482 | 6
1484 | Yes | Auto Scheduled | Simulate Load | 11.25h | October 1, 2026 10:00 | October 2, 2026 2:15 | 1448,1483 | 6
1485 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 2, 2026 2:15 | October 6, 2026 9:00 | 1484 | 6
1486 | Yes | Auto Scheduled | Load | 1h | October 6, 2026 9:00 | October 7, 2026 11:30 | 1485 | 6
1487 | Yes | Auto Scheduled | Post Load Validation | 2h | October 7, 2026 11:30 | October 7, 2026 2:30 | 1486 | 6
1488 | Yes | Auto Scheduled | OTC_CM23_Customer_Hierarchy | 0.69d | September 30, 2026 4:00 | October 1, 2026 1:30 |  | 5
1489 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | September 30, 2026 4:00 | September 30, 2026 4:30 | 1476 | 6
1490 | Yes | Auto Scheduled | Load | 2h | September 30, 2026 4:30 | October 1, 2026 9:30 | 1489 | 6
1491 | Yes | Auto Scheduled | Post Load Validation | 3h | October 1, 2026 9:30 | October 1, 2026 1:30 | 1490 | 6
1492 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Z001 - External Sales Rep | 3.38d | September 30, 2026 4:00 | October 6, 2026 10:00 |  | 5
1493 | Yes | Auto Scheduled | Extract File | 1h | September 30, 2026 4:00 | September 30, 2026 5:00 | 1476 | 6
1494 | Yes | Auto Scheduled | Pre Load Validation | 2h | October 1, 2026 8:00 | October 1, 2026 10:00 | 1493 | 6
1495 | Yes | Auto Scheduled | Simulate Load | 1h | October 1, 2026 10:00 | October 1, 2026 11:00 | 1448,1494 | 6
1496 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 1, 2026 11:00 | October 1, 2026 2:00 | 1495 | 6
1497 | Yes | Auto Scheduled | Load | 1h | October 1, 2026 2:00 | October 5, 2026 5:00 | 1496 | 6
1498 | Yes | Auto Scheduled | Post Load Validation | 2h | October 6, 2026 8:00 | October 6, 2026 10:00 | 1497 | 6
1499 | Yes | Auto Scheduled | RTR_CM10_Credit_Management_Role | 1.84d | September 30, 2026 4:00 | October 2, 2026 2:45 |  | 5
1500 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 30, 2026 4:00 | September 30, 2026 4:30 | 1476 | 6
1501 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 30, 2026 4:30 | September 30, 2026 5:00 | 1500 | 6
1502 | Yes | Auto Scheduled | Simulate Load | 1h | October 1, 2026 8:00 | October 1, 2026 9:00 | 1501 | 6 | 4/16 - Asked to reload per Brian
1503 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 1, 2026 9:00 | October 1, 2026 11:30 | 1502 | 6
1504 | Yes | Auto Scheduled | Load | 2h | October 1, 2026 11:30 | October 1, 2026 4:30 | 1503 | 6
1505 | Yes | Auto Scheduled | Post Load Validation | 3h | October 1, 2026 4:30 | October 2, 2026 2:45 | 1504 | 6 | 4/17 - Error on load,resolution identifed, Def899,Will manually change customer for IT1
1506 | Yes | Auto Scheduled | PTP_CM27_Vendor Master | 6.28d | September 24, 2026 8:30 | October 2, 2026 10:45 |  | 5
1507 | Yes | Auto Scheduled | Extract File | 1h | October 1, 2026 8:00 | October 1, 2026 9:00 | 1493 | 6
1508 | Yes | Auto Scheduled | Pre Load Validation | 2h | October 1, 2026 9:00 | October 1, 2026 11:00 | 1507 | 6
1509 | Yes | Auto Scheduled | Simulate Load | 2.25h | October 1, 2026 11:00 | October 1, 2026 2:15 | 1508 | 6 | First time simulation on 4/13
1510 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 1, 2026 2:15 | October 2, 2026 10:45 | 1509 | 6 | 4/14 - Ran into more errors and Manoj will follow up ib 2hrs....
1511 | Yes | Auto Scheduled | Load | 1h | September 24, 2026 8:30 | September 24, 2026 9:30 |  | 6
1512 | Yes | Auto Scheduled | Post Load Validation | 2h | September 24, 2026 9:30 | September 24, 2026 11:30 | 1511 | 6 | 4/14 PTP Is complete
1513 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | 0.88d | September 24, 2026 8:30 | September 24, 2026 4:30 |  | 5
1514 | Yes | Auto Scheduled | Extract File(Will Extract from LFA1) | 1h | September 24, 2026 8:30 | September 24, 2026 9:30 |  | 6
1515 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 24, 2026 9:30 | September 24, 2026 11:30 | 1514 | 6
1516 | Yes | Auto Scheduled | Simulate Load/ Not Needed | 1h | September 24, 2026 11:30 | September 24, 2026 1:30 | 1515 | 6
1517 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 24, 2026 1:30 | September 24, 2026 3:30 | 1516 | 6 | 4/16 - Defect created no impact to ITC1
1518 | Yes | Auto Scheduled | Load | 1h | September 24, 2026 1:30 | September 24, 2026 2:30 | 1516 | 6
1519 | Yes | Auto Scheduled | Post Load Validation | 2h | September 24, 2026 2:30 | September 24, 2026 4:30 | 1518 | 6
1520 | Yes | Auto Scheduled | RTR_****_Credit Hierarchy | 1.91d | October 1, 2026 11:30 | October 5, 2026 10:45 |  | 5
1521 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | October 1, 2026 11:30 | October 1, 2026 12:00 | 1503 | 6 | 4/16 -Completed
1522 | Yes | Auto Scheduled | Load | 2h | October 2, 2026 2:45 | October 2, 2026 4:45 | 1505 | 6
1523 | Yes | Auto Scheduled | Post Load Validation | 3h | October 2, 2026 4:45 | October 5, 2026 10:45 | 1522 | 6
1524 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Supplier | 1.13d | September 24, 2026 11:30 | September 25, 2026 1:30 |  | 5
1525 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 24, 2026 11:30 | September 24, 2026 12:00 | 1512 | 6
1526 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 24, 2026 1:00 | September 24, 2026 1:30 | 1525 | 6
1527 | Yes | Auto Scheduled | Simulate Load | 1h | September 24, 2026 1:30 | September 24, 2026 2:30 | 1526 | 6
1528 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 24, 2026 2:30 | September 24, 2026 4:30 | 1527 | 6
1529 | Yes | Auto Scheduled | Load | 2h | September 24, 2026 4:30 | September 25, 2026 9:30 | 1528 | 6
1530 | Yes | Auto Scheduled | Post Load Validation | 3h | September 25, 2026 9:30 | September 25, 2026 1:30 | 1529 | 6
1531 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Customer | 1.06d | September 24, 2026 8:30 | September 25, 2026 9:00 |  | 5
1532 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 24, 2026 8:30 | September 24, 2026 9:00 |  | 6
1533 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 24, 2026 8:30 | September 24, 2026 9:00 |  | 6
1534 | Yes | Auto Scheduled | Simulate Load | 1h | September 24, 2026 9:00 | September 24, 2026 10:00 | 1533 | 6
1535 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 24, 2026 10:00 | September 24, 2026 12:00 | 1534 | 6
1536 | Yes | Auto Scheduled | Load | 2h | September 24, 2026 1:00 | September 24, 2026 3:00 | 1535 | 6
1537 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 3:00 | September 25, 2026 9:00 | 1536 | 6
1538 | Yes | Auto Scheduled | PTP_CM26_Material_Master - All Types | 2.28d | September 24, 2026 9:30 | September 28, 2026 11:45 |  | 5
1539 | Yes | Auto Scheduled | Extract File | 5h | September 24, 2026 9:30 | September 25, 2026 8:15 | 1514 | 6
1540 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 24, 2026 11:30 | September 25, 2026 9:45 | 1512 | 6
1541 | Yes | Auto Scheduled | Simulate Load | 1h | September 25, 2026 9:45 | September 25, 2026 10:45 | 1540 | 6
1542 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | September 25, 2026 10:45 | September 25, 2026 3:45 | 1541 | 6
1543 | Yes | Auto Scheduled | Load | 3h | September 25, 2026 3:45 | September 28, 2026 9:45 | 1542 | 6
1544 | Yes | Auto Scheduled | Post Load Validation | 2h | September 28, 2026 9:45 | September 28, 2026 11:45 | 1543 | 6
1545 | Yes | Auto Scheduled | PTP_CM26_Material_Master - SERV - Service Materials | 1.34d | September 25, 2026 4:30 | September 29, 2026 10:15 |  | 5
1546 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 25, 2026 4:30 | September 25, 2026 5:00 | 1415 | 6
1547 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 28, 2026 9:45 | September 28, 2026 10:15 | 1543 | 6
1548 | Yes | Auto Scheduled | Simulate Load | 1h | September 28, 2026 10:15 | September 28, 2026 11:15 | 1547 | 6
1549 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 28, 2026 11:15 | September 28, 2026 2:15 | 1548 | 6
1550 | Yes | Auto Scheduled | Load | 2h | September 28, 2026 2:15 | September 28, 2026 4:15 | 1549 | 6
1551 | Yes | Auto Scheduled | Post Load Validation | 3h | September 28, 2026 4:15 | September 29, 2026 10:15 | 1550 | 6
1552 | Yes | Auto Scheduled | PTP_CM26_Material_Master - KMAT - Configurable Materials | 1.34d | September 25, 2026 4:30 | September 29, 2026 10:15 |  | 5
1553 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 25, 2026 4:30 | September 25, 2026 5:00 | 1415 | 6
1554 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 28, 2026 9:45 | September 28, 2026 10:15 | 1543 | 6
1555 | Yes | Auto Scheduled | Simulate Load | 1h | September 28, 2026 10:15 | September 28, 2026 11:15 | 1554 | 6
1556 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 28, 2026 11:15 | September 28, 2026 2:15 | 1555 | 6
1557 | Yes | Auto Scheduled | Load | 2h | September 28, 2026 2:15 | September 28, 2026 4:15 | 1556 | 6
1558 | Yes | Auto Scheduled | Post Load Validation | 3h | September 28, 2026 4:15 | September 29, 2026 10:15 | 1557 | 6
1559 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Records | 3.59d | September 24, 2026 11:30 | September 30, 2026 8:15 |  | 5
1560 | Yes | Auto Scheduled | Extract File | 1h | September 29, 2026 10:15 | September 29, 2026 11:15 | 1544,1558 | 6 | 4/16 - Started extract
1561 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 29, 2026 11:15 | September 29, 2026 2:15 | 1560 | 6
1562 | Yes | Auto Scheduled | Simulate Load | 1h | September 29, 2026 2:15 | September 29, 2026 3:15 | 1561 | 6
1563 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 29, 2026 3:15 | September 30, 2026 8:15 | 1562 | 6
1564 | Yes | Auto Scheduled | Load | 1h | September 24, 2026 11:30 | September 24, 2026 1:30 | 1512 | 6
1565 | Yes | Auto Scheduled | Post Load Validation | 2h | September 24, 2026 1:30 | September 24, 2026 3:30 | 1564 | 6
1566 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record External Processing | 1.13d | September 29, 2026 10:15 | September 30, 2026 11:15 |  | 5
1567 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 10:15 | September 29, 2026 10:45 | 1544,1558 | 6
1568 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 10:45 | September 29, 2026 11:15 | 1567 | 6
1569 | Yes | Auto Scheduled | Simulate Load | 1h | September 29, 2026 11:15 | September 29, 2026 1:15 | 1568 | 6
1570 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 29, 2026 1:15 | September 29, 2026 3:15 | 1569 | 6
1571 | Yes | Auto Scheduled | Load | 2h | September 29, 2026 3:15 | September 30, 2026 8:15 | 1570 | 6
1572 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 8:15 | September 30, 2026 11:15 | 1571 | 6
1573 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | 1.13d | September 29, 2026 10:15 | September 30, 2026 11:15 |  | 5
1574 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 10:15 | September 29, 2026 10:45 | 1544,1558 | 6
1575 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 10:45 | September 29, 2026 11:15 | 1574 | 6
1576 | Yes | Auto Scheduled | Simulate Load | 1h | September 29, 2026 11:15 | September 29, 2026 1:15 | 1575 | 6 | 4/16 - Eror
1577 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 29, 2026 1:15 | September 29, 2026 3:15 | 1576 | 6
1578 | Yes | Auto Scheduled | Load | 2h | September 29, 2026 3:15 | September 30, 2026 8:15 | 1577 | 6
1579 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 8:15 | September 30, 2026 11:15 | 1578 | 6
1580 | Yes | Auto Scheduled | PTM_CM31_BOM Conversion | 2.48d | September 29, 2026 11:15 | October 1, 2026 4:08 |  | 5
1581 | Yes | Auto Scheduled | Extract File | 1h | September 29, 2026 11:15 | September 29, 2026 1:15 | 1560 | 6
1582 | Yes | Auto Scheduled | Pre Load Validation | 0.5h | September 29, 2026 1:15 | September 29, 2026 1:45 | 1581 | 6
1583 | Yes | Auto Scheduled | Simulate Load | 15.5h | September 29, 2026 1:45 | October 1, 2026 1:45 | 1582 | 6
1584 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | October 1, 2026 1:45 | October 1, 2026 2:15 | 1583 | 6
1585 | Yes | Auto Scheduled | Load | 1h | October 1, 2026 2:15 | October 1, 2026 3:30 | 1584 | 6 | 4/17- Bom issues and not moving to routings...
1586 | Yes | Auto Scheduled | Post Load Validation | 0.5h | October 1, 2026 3:30 | October 1, 2026 4:08 | 1585 | 6 | 4/16 - updated to post load...
1587 | Yes | Auto Scheduled | PTM_CM40_Work Center Conversion | 3.08d | September 29, 2026 1:15 | October 2, 2026 1:53 |  | 5
1588 | Yes | Auto Scheduled | Extract File | 1h | September 29, 2026 1:15 | September 29, 2026 2:15 | 1581 | 6
1589 | Yes | Auto Scheduled | Pre Load Validation | 2h | October 1, 2026 4:08 | October 2, 2026 9:08 | 1586 | 6
1590 | Yes | Auto Scheduled | Simulate Load | 0.25h | October 2, 2026 9:08 | October 2, 2026 9:23 | 1589 | 6
1591 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | October 2, 2026 9:23 | October 2, 2026 9:53 | 1590 | 6 | 4/16- Defect created
1592 | Yes | Auto Scheduled | Load | 1h | October 2, 2026 9:53 | October 2, 2026 10:53 | 1591 | 6
1593 | Yes | Auto Scheduled | Post Load Validation | 2h | October 2, 2026 10:53 | October 2, 2026 1:53 | 1592 | 6
1594 | Yes | Auto Scheduled | PTM_CM38_Routing Conversion | 4.27d | September 29, 2026 2:15 | October 5, 2026 4:23 |  | 5
1595 | Yes | Auto Scheduled | Extract File | 1h | September 29, 2026 2:15 | September 29, 2026 3:15 | 1588 | 6
1596 | Yes | Auto Scheduled | Pre Load Validation | 2h | October 2, 2026 1:53 | October 5, 2026 9:23 | 1593 | 6
1597 | Yes | Auto Scheduled | Simulate Load | 2h | October 5, 2026 9:23 | October 5, 2026 11:23 | 1596 | 6 | 4/20 Cost element has been resolved and now ready to run simulation again. Need to decide if we need to load all routings or load what we have that will load
1598 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | October 5, 2026 9:23 | October 5, 2026 1:23 | 1597SS | 6
1599 | Yes | Auto Scheduled | Load | 1h | October 5, 2026 1:23 | October 5, 2026 2:23 | 1598 | 6
1600 | Yes | Auto Scheduled | Post Load Validation | 2h | October 5, 2026 2:23 | October 5, 2026 4:23 | 1599 | 6
1601 | Yes | Auto Scheduled | PTM_CM36_Production Version Conversion | 1.13d | September 29, 2026 3:15 | September 30, 2026 4:15 |  | 5
1602 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 3:15 | September 29, 2026 3:45 | 1595 | 6
1603 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 3:45 | September 29, 2026 4:15 | 1602 | 6
1604 | Yes | Auto Scheduled | Simulate Load | 1h | September 29, 2026 4:15 | September 30, 2026 8:15 | 1603 | 6
1605 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 30, 2026 8:15 | September 30, 2026 10:15 | 1604 | 6
1606 | Yes | Auto Scheduled | Load | 2h | September 30, 2026 10:15 | September 30, 2026 1:15 | 1605 | 6
1607 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 1:15 | September 30, 2026 4:15 | 1606 | 6
1608 | Yes | Auto Scheduled | PTM_CM35_Inspection Plan | 1.13d | September 30, 2026 4:15 | October 2, 2026 8:15 |  | 5 | 4/17 - will manually load IP for ITC1
1609 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 30, 2026 4:15 | September 30, 2026 4:45 | 1607 | 6 | 4/20- Per Brad they will load manaually for ITC1
1610 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 30, 2026 4:45 | October 1, 2026 8:15 | 1609 | 6
1611 | Yes | Auto Scheduled | Simulate Load | 1h | October 1, 2026 8:15 | October 1, 2026 9:15 | 1610 | 6
1612 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 1, 2026 9:15 | October 1, 2026 11:15 | 1611 | 6
1613 | Yes | Auto Scheduled | Load | 2h | October 1, 2026 11:15 | October 1, 2026 2:15 | 1612 | 6
1614 | Yes | Auto Scheduled | Post Load Validation | 3h | October 1, 2026 2:15 | October 2, 2026 8:15 | 1613 | 6
1615 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Serial Numbers | 1.13d | September 30, 2026 4:45 | October 2, 2026 8:45 |  | 5 | 4/17- will cherry pick equiments for testing ITC1/Smoke
1616 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 30, 2026 4:45 | October 1, 2026 8:15 | 1609 | 6
1617 | Yes | Auto Scheduled | Pre Load Validation | 30m | October 1, 2026 8:15 | October 1, 2026 8:45 | 1616 | 6
1618 | Yes | Auto Scheduled | Simulate Load | 1h | October 1, 2026 8:45 | October 1, 2026 9:45 | 1617 | 6
1619 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 1, 2026 9:45 | October 1, 2026 11:45 | 1618 | 6
1620 | Yes | Auto Scheduled | Load | 2h | October 1, 2026 11:45 | October 1, 2026 2:45 | 1619 | 6
1621 | Yes | Auto Scheduled | Post Load Validation | 3h | October 1, 2026 2:45 | October 2, 2026 8:45 | 1620 | 6
1622 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Service | 6.78d | September 24, 2026 8:30 | October 2, 2026 3:45 |  | 5 | 4/17- will cherry pick equiments for testing ITC1/Smoke
1623 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | October 2, 2026 8:45 | October 2, 2026 9:15 | 1621 | 6
1624 | Yes | Auto Scheduled | Pre Load Validation | 30m | October 2, 2026 9:15 | October 2, 2026 9:45 | 1623 | 6
1625 | Yes | Auto Scheduled | Simulate Load | 1h | October 2, 2026 9:45 | October 2, 2026 10:45 | 1624 | 6
1626 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 2, 2026 10:45 | October 2, 2026 1:45 | 1625 | 6
1627 | Yes | Auto Scheduled | Load | 2h | October 2, 2026 1:45 | October 2, 2026 3:45 | 1626 | 6
1628 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 8:30 | September 24, 2026 11:30 |  | 6
1629 | Yes | Auto Scheduled | VC_Object Dependencies | 0.63d | September 24, 2026 8:30 | September 24, 2026 2:30 |  | 5
1630 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 24, 2026 8:30 | September 24, 2026 10:30 | 1390 | 6
1631 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 10:30 | September 24, 2026 2:30 | 1630 | 6
1632 | Yes | Auto Scheduled | VC_Characteristics | 0.63d | September 24, 2026 2:30 | September 25, 2026 10:30 |  | 5
1633 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 24, 2026 2:30 | September 24, 2026 4:30 | 1631 | 6
1634 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 4:30 | September 25, 2026 10:30 | 1633 | 6
1635 | Yes | Auto Scheduled | VC_Classes | 0.63d | September 25, 2026 10:30 | September 25, 2026 4:30 |  | 5
1636 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 25, 2026 10:30 | September 25, 2026 1:30 | 1634 | 6
1637 | Yes | Auto Scheduled | Post Load Validation | 3h | September 25, 2026 1:30 | September 25, 2026 4:30 | 1636 | 6
1638 | Yes | Auto Scheduled | VC_Classification (Class Type 200) | 0.63d | September 29, 2026 10:15 | September 29, 2026 4:15 |  | 5
1639 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 29, 2026 10:15 | September 29, 2026 1:15 | 1558 | 6
1640 | Yes | Auto Scheduled | Post Load Validation | 3h | September 29, 2026 1:15 | September 29, 2026 4:15 | 1639 | 6
1641 | Yes | Auto Scheduled | VC_Dependency Nets | 0.63d | September 29, 2026 10:15 | September 29, 2026 4:15 |  | 5
1642 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 29, 2026 10:15 | September 29, 2026 1:15 | 1552,1637 | 6
1643 | Yes | Auto Scheduled | Post Load Validation | 3h | September 29, 2026 1:15 | September 29, 2026 4:15 | 1642 | 6
1644 | Yes | Auto Scheduled | VC_Configuration Profiles | 0.63d | September 29, 2026 10:15 | September 29, 2026 4:15 |  | 5
1645 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 29, 2026 10:15 | September 29, 2026 1:15 | 1552 | 6
1646 | Yes | Auto Scheduled | Post Load Validation | 3h | September 29, 2026 1:15 | September 29, 2026 4:15 | 1645 | 6
1647 | Yes | Auto Scheduled | VC_Variant Tables | 0.63d | September 29, 2026 4:15 | September 30, 2026 1:15 |  | 5
1648 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 29, 2026 4:15 | September 30, 2026 9:15 | 1646 | 6
1649 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 9:15 | September 30, 2026 1:15 | 1648 | 6
1650 | Yes | Auto Scheduled | VC_Variant Tables Content | 0.63d | September 30, 2026 1:15 | October 1, 2026 9:15 |  | 5
1651 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 30, 2026 1:15 | September 30, 2026 3:15 | 1649 | 6
1652 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 3:15 | October 1, 2026 9:15 | 1651 | 6
1653 | Yes | Auto Scheduled | VC_Characteristic Groups | 1.97d | September 29, 2026 4:15 | October 1, 2026 4:00 |  | 5 | 4/20- Defect - 963
1654 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 12.75h | September 29, 2026 4:15 | October 1, 2026 12:00 | 1646 | 6 | 4/17 - Authorization error/loaded but getting in app is issue. 4/20 Defect recorded and still open
1655 | Yes | Auto Scheduled | Post Load Validation | 3h | October 1, 2026 1:00 | October 1, 2026 4:00 | 1654 | 6
1656 | Yes | Auto Scheduled | PTM_CM52_Super_BOM | 4.09d | September 29, 2026 10:15 | October 5, 2026 11:00 |  | 5 | 4/21- Pittsburg was loaded and working on remaining sites 4/20 - Working through errors with materials
1657 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 10:15 | September 29, 2026 10:45 | 1558 | 6
1658 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 10:45 | September 29, 2026 11:15 | 1657 | 6
1659 | Yes | Auto Scheduled | Simulate Load | 24.75h | September 29, 2026 11:15 | October 2, 2026 12:00 | 1658 | 6 | 4/17 - Have issues and Manoj to work with Chip
1660 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 2, 2026 1:00 | October 2, 2026 3:00 | 1659 | 6 | 4/16- Reviewing some errors , 4/17- Still running into errors
1661 | Yes | Auto Scheduled | Load | 2h | October 2, 2026 3:00 | October 2, 2026 5:00 | 1660 | 6
1662 | Yes | Auto Scheduled | Post Load Validation | 3h | October 5, 2026 8:00 | October 5, 2026 11:00 | 1661 | 6
1663 | Yes | Auto Scheduled | PTM_CM53_Super_Routing | 2.13d | October 5, 2026 11:00 | October 7, 2026 12:00 |  | 5
1664 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | October 5, 2026 11:00 | October 5, 2026 11:30 | 1662 | 6
1665 | Yes | Auto Scheduled | Pre Load Validation | 30m | October 5, 2026 11:30 | October 5, 2026 12:00 | 1664 | 6
1666 | Yes | Auto Scheduled | Simulate Load | 1h | October 5, 2026 1:00 | October 6, 2026 2:00 | 1665 | 6
1667 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 6, 2026 2:00 | October 6, 2026 4:00 | 1666 | 6
1668 | Yes | Auto Scheduled | Load | 2h | October 6, 2026 4:00 | October 7, 2026 9:00 | 1667 | 6
1669 | Yes | Auto Scheduled | Post Load Validation | 3h | October 7, 2026 9:00 | October 7, 2026 12:00 | 1668 | 6 | 4/22 -Loaded for Pittsburg
1670 | Yes | Auto Scheduled | VC_VK30 Pricing Variant | 0.69d | October 7, 2026 9:00 | October 7, 2026 3:30 |  | 5
1671 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | October 7, 2026 9:00 | October 7, 2026 9:30 | 1668 | 6
1672 | Yes | Auto Scheduled | Load | 2h | October 7, 2026 9:30 | October 7, 2026 11:30 | 1671 | 6
1673 | Yes | Auto Scheduled | Post Load Validation | 3h | October 7, 2026 11:30 | October 7, 2026 3:30 | 1672 | 6
1674 | Yes | Auto Scheduled | OTC_CM22_Pricing_Condition | 0.69d | October 7, 2026 3:30 | October 8, 2026 12:00 |  | 5
1675 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | October 7, 2026 3:30 | October 7, 2026 4:00 | 1673 | 6
1676 | Yes | Auto Scheduled | Load | 2h | October 7, 2026 4:00 | October 8, 2026 9:00 | 1675 | 6
1677 | Yes | Auto Scheduled | Post Load Validation | 3h | October 8, 2026 9:00 | October 8, 2026 12:00 | 1676 | 6 | 4/16 - Service to load
1678 | Yes | Auto Scheduled | OTC_CM21_CMIR | 0.5d | October 8, 2026 9:00 | October 8, 2026 2:00 |  | 5
1679 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | October 8, 2026 9:00 | October 8, 2026 9:30 | 1676,1687 | 6
1680 | Yes | Auto Scheduled | Pre Load Validation | 30m | October 8, 2026 9:30 | October 8, 2026 10:00 | 1679 | 6
1681 | Yes | Auto Scheduled | Simulate Load | 0h | October 8, 2026 10:00 | October 8, 2026 10:00 | 1680 | 6
1682 | Yes | Auto Scheduled | Error and Defect Mitigation | 0h | October 8, 2026 10:00 | October 8, 2026 10:00 | 1681 | 6
1683 | Yes | Auto Scheduled | Load | 0h | October 8, 2026 10:00 | October 8, 2026 10:00 | 1682 | 6 | 4/16 - Load done
1684 | Yes | Auto Scheduled | Post Load Validation | 3h | October 8, 2026 10:00 | October 8, 2026 2:00 | 1683 | 6
1685 | Yes | Auto Scheduled | PTP_CM29_Source_List | 6.16d | September 25, 2026 9:30 | October 5, 2026 10:45 |  | 5
1686 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | September 25, 2026 9:30 | September 25, 2026 10:00 | 1529,1536 | 6 | 4/16 -
1687 | Yes | Auto Scheduled | Load | 2h | October 2, 2026 2:45 | October 2, 2026 4:45 | 1505 | 6
1688 | Yes | Auto Scheduled | Post Load Validation | 3h | October 2, 2026 4:45 | October 5, 2026 10:45 | 1687 | 6
1689 | Yes | Auto Scheduled | RTR_CM11_Asset_Master | 6.63d | September 24, 2026 8:30 | October 2, 2026 2:30 |  | 5 | 4/20- Move to ITC2
1690 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 24, 2026 8:30 | September 24, 2026 9:00 |  | 6
1691 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 24, 2026 9:00 | September 24, 2026 9:30 | 1690 | 6
1692 | Yes | Auto Scheduled | Simulate Load | 31h | September 24, 2026 9:30 | September 30, 2026 8:30 | 1691 | 6 | 4/17 - Going back and forth
1693 | Yes | Auto Scheduled | Error and Defect Mitigation | 16h | September 30, 2026 8:30 | October 2, 2026 8:30 | 1692 | 6
1694 | Yes | Auto Scheduled | Load | 2h | October 2, 2026 8:30 | October 2, 2026 10:30 | 1693 | 6
1695 | Yes | Auto Scheduled | Post Load Validation | 3h | October 2, 2026 10:30 | October 2, 2026 2:30 | 1694 | 6
1696 | Yes | Auto Scheduled | PTM_CM50_Material Class | 2.13d | September 29, 2026 3:45 | October 1, 2026 4:45 |  | 5
1697 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | September 29, 2026 3:45 | September 29, 2026 4:15 | 1602 | 6
1698 | Yes | Auto Scheduled | Load | 30m | September 29, 2026 4:15 | September 29, 2026 4:45 | 1697 | 6 | 4/17 -Manually loaded
1699 | Yes | Auto Scheduled | Post Load Validation | 16h | September 29, 2026 4:45 | October 1, 2026 4:45 | 1698 | 6 | 4/16 - Will load manually
1700 | Yes | Auto Scheduled | PTM_CM55_Class assignment to materials | 1.13d | September 29, 2026 4:15 | October 1, 2026 8:15 |  | 5 | 4/16 - Is not being loaded part of ITC1
1701 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 4:15 | September 29, 2026 4:45 | 1697 | 6
1702 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 4:45 | September 30, 2026 8:15 | 1701 | 6
1703 | Yes | Auto Scheduled | Simulate Load | 1h | September 30, 2026 8:15 | September 30, 2026 9:15 | 1702 | 6
1704 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 30, 2026 9:15 | September 30, 2026 11:15 | 1703 | 6
1705 | Yes | Auto Scheduled | Load | 2h | September 30, 2026 11:15 | September 30, 2026 2:15 | 1704 | 6
1706 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 2:15 | October 1, 2026 8:15 | 1705 | 6
1707 | Yes | Auto Scheduled | GTS - Material initial load from S4 (Run Interface) | 2.09d | September 29, 2026 1:15 | October 1, 2026 2:00 |  | 5
1708 | Yes | Auto Scheduled | Run material interface to GTS | 15.75h | September 29, 2026 1:15 | October 1, 2026 12:00 | 1576 | 6
1709 | Yes | Auto Scheduled | Post Load Validation | 1h | October 1, 2026 1:00 | October 1, 2026 2:00 | 1708 | 6
1710 | Yes | Auto Scheduled | GTS - Customers initial load from S4 (Run Interface) | 0.25d | September 24, 2026 8:30 | September 24, 2026 10:30 |  | 5
1711 | Yes | Auto Scheduled | Run material interface to GTS | 1h | September 24, 2026 8:30 | September 24, 2026 9:30 |  | 6
1712 | Yes | Auto Scheduled | Post Load Validation | 1h | September 24, 2026 9:30 | September 24, 2026 10:30 | 1711 | 6 | 4/17 99% complete ran in to some erros with defect 934
1713 | Yes | Auto Scheduled | GTS - Vendors initial load from S4 (Run Interface) | 0.25d | September 24, 2026 4:30 | September 25, 2026 9:30 |  | 5
1714 | Yes | Auto Scheduled | Run material interface to GTS | 1h | September 24, 2026 4:30 | September 25, 2026 8:30 | 1519 | 6 | 4/16- Have 3 records with issues
1715 | Yes | Auto Scheduled | Post Load Validation | 1h | September 25, 2026 8:30 | September 25, 2026 9:30 | 1714 | 6
1716 | Yes | Auto Scheduled | GTS - ECCN - Create | 1.13d | September 24, 2026 8:30 | September 25, 2026 9:30 |  | 5
1717 | Yes | Auto Scheduled | Load Descartes XML File | 1h | September 24, 2026 8:30 | September 24, 2026 9:30 | 1390 | 6
1718 | Yes | Auto Scheduled | Post Load Validation | 1h | September 25, 2026 8:30 | September 25, 2026 9:30 | 1714 | 6
1719 | Yes | Auto Scheduled | GTS - ECCN - Assign | 0.25d | October 1, 2026 2:00 | October 1, 2026 4:00 |  | 5
1720 | Yes | Auto Scheduled | Load Descartes XML File | 1h | October 1, 2026 2:00 | October 1, 2026 3:00 | 1709 | 6
1721 | Yes | Auto Scheduled | Post Load Validation | 1h | October 1, 2026 3:00 | October 1, 2026 4:00 | 1720 | 6
1722 | Yes | Auto Scheduled | GTS - HTS - Create | 0.25d | September 24, 2026 8:30 | September 24, 2026 10:30 |  | 5
1723 | Yes | Auto Scheduled | Load Descartes XML File | 1h | September 24, 2026 8:30 | September 24, 2026 9:30 | 1390 | 6
1724 | Yes | Auto Scheduled | Post Load Validation | 1h | September 24, 2026 9:30 | September 24, 2026 10:30 | 1723 | 6
1725 | Yes | Auto Scheduled | GTS - HTS - Assign | 0.25d | October 1, 2026 4:00 | October 2, 2026 9:00 |  | 5
1726 | Yes | Auto Scheduled | Load Descartes XML File | 1h | October 1, 2026 4:00 | October 1, 2026 5:00 | 1721 | 6
1727 | Yes | Auto Scheduled | Post Load Validation | 1h | October 2, 2026 8:00 | October 2, 2026 9:00 | 1726 | 6
1728 | Yes | Auto Scheduled | GTS - License - Create | 0.25d | October 2, 2026 10:00 | October 2, 2026 12:00 |  | 5
1729 | Yes | Auto Scheduled | Load Descartes XML File | 1h | October 2, 2026 10:00 | October 2, 2026 11:00 | 1726,1742 | 6 | 4/13 - Need to update dep.
1730 | Yes | Auto Scheduled | Post Load Validation | 1h | October 2, 2026 11:00 | October 2, 2026 12:00 | 1729 | 6
1731 | Yes | Auto Scheduled | Commodity Code/Tarif | 2.78d | October 2, 2026 9:00 | October 6, 2026 4:15 |  | 5
1732 | Yes | Auto Scheduled | Load | 21.25h | October 2, 2026 9:00 | October 6, 2026 3:15 | 1727 | 6 | 4/17- wants to use the old load program
1733 | Yes | Auto Scheduled | Post Load Validation | 1h | October 6, 2026 3:15 | October 6, 2026 4:15 | 1732 | 6
1734 | Yes | Auto Scheduled | SPL Master File | 0.25d | October 2, 2026 8:00 | October 2, 2026 10:00 |  | 5
1735 | Yes | Auto Scheduled | Load | 1h | October 2, 2026 8:00 | October 2, 2026 9:00 | 1726 | 6
1736 | Yes | Auto Scheduled | Post Load Validation | 1h | October 2, 2026 9:00 | October 2, 2026 10:00 | 1735 | 6
1737 | Yes | Auto Scheduled | Initialize Embargo situation | 0.38d | September 25, 2026 9:30 | September 25, 2026 1:30 |  | 5
1738 | Yes | Auto Scheduled | Run report /SAPSLL/EMB_CNTRY_INIT | 1h | September 25, 2026 9:30 | September 25, 2026 10:30 | 1718 | 6
1739 | Yes | Auto Scheduled | Set Embargo situations | 1h | September 25, 2026 10:30 | September 25, 2026 11:30 | 1738 | 6 | 4/17 - Needs access
1740 | Yes | Auto Scheduled | Post Load Validation | 1h | September 25, 2026 11:30 | September 25, 2026 1:30 | 1739 | 6
1741 | Yes | Auto Scheduled | GTS - SPL (Sanctioned party list) | 0.25d | October 2, 2026 9:00 | October 2, 2026 11:00 |  | 5
1742 | Yes | Auto Scheduled | Load Descartes XML File | 1h | October 2, 2026 9:00 | October 2, 2026 10:00 | 1727 | 6
1743 | Yes | Auto Scheduled | Post Load Validation | 1h | October 2, 2026 10:00 | October 2, 2026 11:00 | 1742 | 6
1744 | Yes | Auto Scheduled | RTR_CM17_Project Definition / Builder | 1.13d | September 24, 2026 9:00 | September 25, 2026 10:00 |  | 5 | 4/20 - Will have files to load in the morning
1745 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 24, 2026 9:00 | September 24, 2026 9:30 | 1690 | 6
1746 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 24, 2026 9:30 | September 24, 2026 10:00 | 1745 | 6
1747 | Yes | Auto Scheduled | Simulate Load | 1h | September 24, 2026 10:00 | September 24, 2026 11:00 | 1746 | 6
1748 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 24, 2026 11:00 | September 24, 2026 2:00 | 1747 | 6
1749 | Yes | Auto Scheduled | Load | 2h | September 24, 2026 2:00 | September 24, 2026 4:00 | 1748 | 6
1750 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 4:00 | September 25, 2026 10:00 | 1749 | 6
1751 | Yes | Auto Scheduled | RTR_CM18_WBS Element | 1.25d | September 24, 2026 8:30 | September 25, 2026 10:30 |  | 5
1752 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 24, 2026 9:30 | September 24, 2026 10:00 | 1745 | 6
1753 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 24, 2026 10:00 | September 24, 2026 10:30 | 1752 | 6
1754 | Yes | Auto Scheduled | Simulate Load | 1h | September 24, 2026 10:30 | September 24, 2026 11:30 | 1753 | 6
1755 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 24, 2026 11:30 | September 24, 2026 2:30 | 1754 | 6
1756 | Yes | Auto Scheduled | Load | 2h | September 24, 2026 2:30 | September 24, 2026 4:30 | 1755 | 6
1757 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 4:30 | September 25, 2026 10:30 | 1756 | 6
1758 | Yes | Auto Scheduled | UAT Mock Data Loads Complete | 15m | September 24, 2026 8:30 | September 24, 2026 8:45 |  | 6
1759 | Yes | Auto Scheduled | UAT Master Data Loads Complete | 0m | October 8, 2026 2:00 | October 8, 2026 2:00 | 1391 | 4
1760 | Yes | Auto Scheduled | Mock Transactional Data | 2d | October 8, 2026 2:00 | October 12, 2026 2:00 | 1759 | 4
1761 | Yes | Auto Scheduled | Inventory | 4h | October 8, 2026 2:00 | October 9, 2026 9:00 | 998SS,1759SS | 5
1762 | Yes | Auto Scheduled | Open AR | 4h | October 9, 2026 9:00 | October 9, 2026 2:00 | 1761 | 5
1763 | Yes | Auto Scheduled | Open AP | 4h | October 9, 2026 2:00 | October 12, 2026 9:00 | 1762 | 5
1764 | Yes | Auto Scheduled | Bank and Cash | 4h | October 12, 2026 9:00 | October 12, 2026 2:00 | 1763 | 5
1765 | Yes | Auto Scheduled | Open Purchase Orders(Manual) | 1d | October 9, 2026 9:00 | October 12, 2026 9:00 | 1761 | 5
1766 | Yes | Auto Scheduled | Open Sales Orders(Manual) | 1d | October 9, 2026 9:00 | October 12, 2026 9:00 | 1761 | 5
1767 | Yes | Auto Scheduled | Service Orders(Manual) | 0.5d | October 9, 2026 9:00 | October 9, 2026 2:00 | 1761 | 5
1768 | Yes | Auto Scheduled | Open Production Orders(Manual) | 1d | October 9, 2026 9:00 | October 12, 2026 9:00 | 1761 | 5
1769 | Yes | Auto Scheduled | UAT Mock Data Loads Complete | 15m | October 12, 2026 2:00 | October 12, 2026 2:15 | 1760 | 4
1770 | Yes | Auto Scheduled | PROD Data Load Tasks P? | 10.56d | September 24, 2026 8:30 | October 8, 2026 2:01 | 134 | 3
1771 | Yes | Auto Scheduled | PMO Authorization to Start Data Loads | 1m | September 24, 2026 8:30 | September 24, 2026 8:31 | 134 | 4
1772 | Yes | Manually Scheduled | Master Data Loads | 5d | September 24, 2026 8:31 | October 1, 2026 8:31 | 1771 | 4
1773 | Yes | Auto Scheduled | RTR_CM02_Profit Center Hierarchy | 0.75d | September 24, 2026 8:31 | September 24, 2026 3:31 |  | 5
1774 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | September 24, 2026 8:31 | September 24, 2026 9:31 | 1771 | 6
1775 | Yes | Auto Scheduled | Load | 2h | September 24, 2026 9:31 | September 24, 2026 11:31 | 1774 | 6
1776 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 11:31 | September 24, 2026 3:31 | 1775 | 6
1777 | Yes | Auto Scheduled | RTR_CM03_Cost Center Hierarchy | 0.75d | September 24, 2026 3:31 | September 25, 2026 1:31 |  | 5
1778 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 1h | September 24, 2026 3:31 | September 24, 2026 4:31 | 1776 | 6
1779 | Yes | Auto Scheduled | Load | 2h | September 24, 2026 4:31 | September 25, 2026 9:31 | 1778 | 6
1780 | Yes | Auto Scheduled | Post Load Validation | 3h | September 25, 2026 9:31 | September 25, 2026 1:31 | 1779 | 6
1781 | Yes | Auto Scheduled | RTR_CM01_GL_Account_Master to CC 1000 | 2.44d | September 25, 2026 1:31 | September 30, 2026 8:01 |  | 5
1782 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 25, 2026 1:31 | September 25, 2026 2:31 | 1780 | 6
1783 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 25, 2026 2:31 | September 25, 2026 4:31 | 1782 | 6
1784 | Yes | Auto Scheduled | Simulate Load | 6h | September 25, 2026 4:31 | September 28, 2026 2:31 | 1783 | 6
1785 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 28, 2026 2:31 | September 29, 2026 9:01 | 1784 | 6
1786 | Yes | Auto Scheduled | Load | 1h | September 29, 2026 9:01 | September 29, 2026 10:01 | 1785 | 6
1787 | Yes | Auto Scheduled | Post Load Validation | 2h | September 29, 2026 10:01 | September 29, 2026 1:01 | 1786 | 6
1788 | Yes | Auto Scheduled | Extend GL to all Company Codes | 2h | September 29, 2026 1:01 | September 29, 2026 3:01 | 1787 | 6
1789 | Yes | Auto Scheduled | Post GL Extention Validation | 2h | September 29, 2026 3:01 | September 30, 2026 8:01 | 1788 | 6
1790 | Yes | Auto Scheduled | RTR_CM05_Profit_Center | 1.13d | September 24, 2026 3:31 | September 25, 2026 4:31 |  | 5
1791 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 24, 2026 3:31 | September 24, 2026 4:31 | 1776 | 6
1792 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 24, 2026 4:31 | September 25, 2026 9:31 | 1791 | 6
1793 | Yes | Auto Scheduled | Simulate Load | 1h | September 25, 2026 9:31 | September 25, 2026 10:31 | 1792 | 6
1794 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 25, 2026 10:31 | September 25, 2026 1:31 | 1793 | 6
1795 | Yes | Auto Scheduled | Load | 1h | September 25, 2026 1:31 | September 25, 2026 2:31 | 1794 | 6
1796 | Yes | Auto Scheduled | Post Load Validation | 2h | September 25, 2026 2:31 | September 25, 2026 4:31 | 1795 | 6
1797 | Yes | Auto Scheduled | RTR_CM04_Cost_Center | 1.13d | September 25, 2026 4:31 | September 29, 2026 8:31 |  | 5
1798 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 25, 2026 4:31 | September 28, 2026 8:31 | 1796 | 6
1799 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 28, 2026 8:31 | September 28, 2026 10:31 | 1798 | 6
1800 | Yes | Auto Scheduled | Simulate Load | 1h | September 28, 2026 10:31 | September 28, 2026 11:31 | 1799 | 6
1801 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 28, 2026 11:31 | September 28, 2026 2:31 | 1800 | 6
1802 | Yes | Auto Scheduled | Load | 1h | September 28, 2026 2:31 | September 28, 2026 3:31 | 1801 | 6
1803 | Yes | Auto Scheduled | Post Load Validation | 2h | September 28, 2026 3:31 | September 29, 2026 8:31 | 1802 | 6
1804 | Yes | Auto Scheduled | Manual Configuration Activities in QS5 | 8.94d | September 24, 2026 8:31 | October 7, 2026 8:01 | 40 | 5
1805 | Yes | Auto Scheduled | Open Client | 30m | September 24, 2026 8:31 | September 24, 2026 9:01 |  | 6
1806 | Yes | Auto Scheduled | Service Enterprise Setup | 5d | September 30, 2026 8:01 | October 7, 2026 8:01 | 1773,1777,1781 | 6
1807 | Yes | Auto Scheduled | Close Client | 30m | September 24, 2026 8:31 | September 24, 2026 9:01 |  | 6
1808 | Yes | Auto Scheduled | Intercompany Business Partner Setup | 2h | September 30, 2026 8:01 | September 30, 2026 10:01 | 1773,1777,1789 | 6
1809 | Yes | Auto Scheduled | RTR_CM09_Activity_Type | 1.38d | September 29, 2026 1:01 | September 30, 2026 4:01 |  | 5
1810 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 29, 2026 1:01 | September 29, 2026 3:16 | 1787 | 6
1811 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 29, 2026 3:16 | September 30, 2026 9:01 | 1810 | 6
1812 | Yes | Auto Scheduled | Simulate Load | 1h | September 30, 2026 9:01 | September 30, 2026 10:01 | 1811 | 6
1813 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 30, 2026 10:01 | September 30, 2026 1:01 | 1812 | 6
1814 | Yes | Auto Scheduled | Load | 1h | September 30, 2026 1:01 | September 30, 2026 2:01 | 1813 | 6
1815 | Yes | Auto Scheduled | Post Load Validation | 2h | September 30, 2026 2:01 | September 30, 2026 4:01 | 1814 | 6
1816 | Yes | Auto Scheduled | RTR_CM12_Activity Rates | 1.13d | September 25, 2026 1:31 | September 28, 2026 2:31 |  | 5
1817 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 25, 2026 1:31 | September 25, 2026 2:31 | 1780 | 6
1818 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 25, 2026 2:31 | September 25, 2026 4:31 | 1817 | 6
1819 | Yes | Auto Scheduled | Simulate Load | 1h | September 25, 2026 4:31 | September 28, 2026 8:31 | 1818 | 6
1820 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 28, 2026 8:31 | September 28, 2026 10:31 | 1819 | 6
1821 | Yes | Auto Scheduled | Load | 1h | September 28, 2026 10:31 | September 28, 2026 11:31 | 1820 | 6
1822 | Yes | Auto Scheduled | Post Load Validation | 2h | September 28, 2026 11:31 | September 28, 2026 2:31 | 1821 | 6
1823 | Yes | Auto Scheduled | RTR_CM06_Bank_master | 3.81d | September 24, 2026 8:31 | September 29, 2026 4:01 |  | 5
1824 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 29, 2026 1:01 | September 29, 2026 2:01 | 1787 | 6
1825 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 29, 2026 2:01 | September 29, 2026 4:01 | 1824 | 6
1826 | Yes | Auto Scheduled | Simulate Load | 1h | September 24, 2026 8:31 | September 24, 2026 9:31 |  | 6
1827 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 24, 2026 9:31 | September 24, 2026 11:31 | 1826 | 6
1828 | Yes | Auto Scheduled | Load | 5h | September 24, 2026 11:31 | September 25, 2026 8:31 | 1827 | 6
1829 | Yes | Auto Scheduled | Post Load Validation | 2h | September 25, 2026 8:31 | September 25, 2026 3:01 | 1828 | 6
1830 | Yes | Auto Scheduled | RTR_CM08_Exchange_Rates | 1.13d | September 25, 2026 8:31 | September 28, 2026 9:31 |  | 5
1831 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 1h | September 25, 2026 8:31 | September 25, 2026 9:31 | 1828 | 6
1832 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 25, 2026 9:31 | September 25, 2026 11:31 | 1831 | 6
1833 | Yes | Auto Scheduled | Simulate Load | 1h | September 25, 2026 11:31 | September 25, 2026 1:31 | 1832 | 6
1834 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 25, 2026 1:31 | September 25, 2026 3:31 | 1833 | 6
1835 | Yes | Auto Scheduled | Load | 1h | September 25, 2026 3:31 | September 25, 2026 4:31 | 1834 | 6
1836 | Yes | Auto Scheduled | Post Load Validation | 2h | September 25, 2026 4:31 | September 28, 2026 9:31 | 1835 | 6
1837 | Yes | Auto Scheduled | RTR_CM14_Cost Element_Group | 4.44d | September 29, 2026 1:01 | October 5, 2026 4:31 |  | 5
1838 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | September 29, 2026 1:01 | September 29, 2026 1:31 | 1787 | 6
1839 | Yes | Auto Scheduled | Load | 32h | September 29, 2026 1:31 | October 5, 2026 1:31 | 1838 | 6
1840 | Yes | Auto Scheduled | Post Load Validation | 3h | October 5, 2026 1:31 | October 5, 2026 4:31 | 1839 | 6
1841 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Bill-To | 2h | September 24, 2026 8:31 | September 24, 2026 10:31 |  | 5 | 4/20 Per OTC this is not needed for ITC1
1842 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Ship-To | 1.5d | September 29, 2026 1:01 | October 1, 2026 8:01 |  | 5
1843 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 1:01 | September 29, 2026 1:31 | 1787 | 6
1844 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 1:31 | September 29, 2026 2:01 | 1843 | 6
1845 | Yes | Auto Scheduled | Open client for BP number range update | 30m | September 29, 2026 2:01 | September 29, 2026 2:31 | 1844 | 6
1846 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 30m | September 29, 2026 2:31 | September 29, 2026 3:01 | 1845 | 6
1847 | Yes | Auto Scheduled | Close Client | 15m | September 29, 2026 3:01 | September 29, 2026 3:16 | 1846 | 6
1848 | Yes | Auto Scheduled | Simulate Load | 1h | September 29, 2026 2:01 | September 29, 2026 3:01 | 1844 | 6
1849 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | September 29, 2026 3:01 | September 30, 2026 10:01 | 1848 | 6
1850 | Yes | Auto Scheduled | Load | 3h | September 30, 2026 10:01 | September 30, 2026 2:01 | 1849 | 6
1851 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 2:01 | October 1, 2026 8:01 | 1850 | 6
1852 | Yes | Auto Scheduled | OTC_CM19_Customer_Master - Sold-To | 1.63d | September 29, 2026 2:01 | October 1, 2026 10:01 |  | 5
1853 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 2:01 | September 29, 2026 2:31 | 1844 | 6
1854 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 2:31 | September 29, 2026 3:01 | 1853 | 6
1855 | Yes | Auto Scheduled | Simulate Load | 1h | September 30, 2026 8:01 | September 30, 2026 9:01 | 1789,1848 | 6
1856 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | September 30, 2026 9:01 | September 30, 2026 1:01 | 1855 | 6
1857 | Yes | Auto Scheduled | Load | 3h | September 30, 2026 1:01 | September 30, 2026 4:01 | 1856 | 6
1858 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 4:01 | October 1, 2026 10:01 | 1857 | 6
1859 | Yes | Auto Scheduled | Open client for BP number range update | 15m | September 29, 2026 3:01 | September 29, 2026 3:16 | 1848 | 6
1860 | Yes | Auto Scheduled | Update number range BP02 from Internal to External | 15m | September 29, 2026 3:16 | September 29, 2026 3:31 | 1859 | 6
1861 | Yes | Auto Scheduled | Close Client | 15m | September 29, 2026 3:31 | September 29, 2026 3:46 | 1860 | 6
1862 | Yes | Auto Scheduled | PTP_CM27_Vendor Master as Customer - FLCU01 | 4.81d | September 30, 2026 4:01 | October 7, 2026 2:31 |  | 5
1863 | Yes | Auto Scheduled | Extract File | 1h | September 30, 2026 4:01 | October 1, 2026 8:01 | 1857 | 6
1864 | Yes | Auto Scheduled | Pre Load Validation | 2h | October 1, 2026 8:01 | October 1, 2026 10:01 | 1863 | 6
1865 | Yes | Auto Scheduled | Simulate Load | 11.25h | October 1, 2026 10:01 | October 2, 2026 2:16 | 1829,1864 | 6
1866 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 2, 2026 2:16 | October 6, 2026 9:01 | 1865 | 6
1867 | Yes | Auto Scheduled | Load | 1h | October 6, 2026 9:01 | October 7, 2026 11:31 | 1866 | 6
1868 | Yes | Auto Scheduled | Post Load Validation | 2h | October 7, 2026 11:31 | October 7, 2026 2:31 | 1867 | 6
1869 | Yes | Auto Scheduled | OTC_CM23_Customer_Hierarchy | 0.69d | September 30, 2026 4:01 | October 1, 2026 1:31 |  | 5
1870 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | September 30, 2026 4:01 | September 30, 2026 4:31 | 1857 | 6
1871 | Yes | Auto Scheduled | Load | 2h | September 30, 2026 4:31 | October 1, 2026 9:31 | 1870 | 6
1872 | Yes | Auto Scheduled | Post Load Validation | 3h | October 1, 2026 9:31 | October 1, 2026 1:31 | 1871 | 6
1873 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Z001 - External Sales Rep | 3.38d | September 30, 2026 4:01 | October 6, 2026 10:01 |  | 5
1874 | Yes | Auto Scheduled | Extract File | 1h | September 30, 2026 4:01 | October 1, 2026 8:01 | 1857 | 6
1875 | Yes | Auto Scheduled | Pre Load Validation | 2h | October 1, 2026 8:01 | October 1, 2026 10:01 | 1874 | 6
1876 | Yes | Auto Scheduled | Simulate Load | 1h | October 1, 2026 10:01 | October 1, 2026 11:01 | 1829,1875 | 6
1877 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 1, 2026 11:01 | October 1, 2026 2:01 | 1876 | 6
1878 | Yes | Auto Scheduled | Load | 1h | October 1, 2026 2:01 | October 6, 2026 8:01 | 1877 | 6
1879 | Yes | Auto Scheduled | Post Load Validation | 2h | October 6, 2026 8:01 | October 6, 2026 10:01 | 1878 | 6
1880 | Yes | Auto Scheduled | RTR_CM10_Credit_Management_Role | 1.84d | September 30, 2026 4:01 | October 2, 2026 2:46 |  | 5
1881 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 30, 2026 4:01 | September 30, 2026 4:31 | 1857 | 6
1882 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 30, 2026 4:31 | October 1, 2026 8:01 | 1881 | 6
1883 | Yes | Auto Scheduled | Simulate Load | 1h | October 1, 2026 8:01 | October 1, 2026 9:01 | 1882 | 6 | 4/16 - Asked to reload per Brian
1884 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 1, 2026 9:01 | October 1, 2026 11:31 | 1883 | 6
1885 | Yes | Auto Scheduled | Load | 2h | October 1, 2026 11:31 | October 1, 2026 4:31 | 1884 | 6
1886 | Yes | Auto Scheduled | Post Load Validation | 3h | October 1, 2026 4:31 | October 2, 2026 2:46 | 1885 | 6 | 4/17 - Error on load,resolution identifed, Def899,Will manually change customer for IT1
1887 | Yes | Auto Scheduled | PTP_CM27_Vendor Master | 6.28d | September 24, 2026 8:31 | October 2, 2026 10:46 |  | 5
1888 | Yes | Auto Scheduled | Extract File | 1h | October 1, 2026 8:01 | October 1, 2026 9:01 | 1874 | 6
1889 | Yes | Auto Scheduled | Pre Load Validation | 2h | October 1, 2026 9:01 | October 1, 2026 11:01 | 1888 | 6
1890 | Yes | Auto Scheduled | Simulate Load | 2.25h | October 1, 2026 11:01 | October 1, 2026 2:16 | 1889 | 6 | First time simulation on 4/13
1891 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 1, 2026 2:16 | October 2, 2026 10:46 | 1890 | 6 | 4/14 - Ran into more errors and Manoj will follow up ib 2hrs....
1892 | Yes | Auto Scheduled | Load | 1h | September 24, 2026 8:31 | September 24, 2026 9:31 |  | 6
1893 | Yes | Auto Scheduled | Post Load Validation | 2h | September 24, 2026 9:31 | September 24, 2026 11:31 | 1892 | 6 | 4/14 PTP Is complete
1894 | Yes | Auto Scheduled | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | 0.88d | September 24, 2026 8:31 | September 24, 2026 4:31 |  | 5
1895 | Yes | Auto Scheduled | Extract File(Will Extract from LFA1) | 1h | September 24, 2026 8:31 | September 24, 2026 9:31 |  | 6
1896 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 24, 2026 9:31 | September 24, 2026 11:31 | 1895 | 6
1897 | Yes | Auto Scheduled | Simulate Load/ Not Needed | 1h | September 24, 2026 11:31 | September 24, 2026 1:31 | 1896 | 6
1898 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 24, 2026 1:31 | September 24, 2026 3:31 | 1897 | 6 | 4/16 - Defect created no impact to ITC1
1899 | Yes | Auto Scheduled | Load | 1h | September 24, 2026 1:31 | September 24, 2026 2:31 | 1897 | 6
1900 | Yes | Auto Scheduled | Post Load Validation | 2h | September 24, 2026 2:31 | September 24, 2026 4:31 | 1899 | 6
1901 | Yes | Auto Scheduled | RTR_****_Credit Hierarchy | 1.91d | October 1, 2026 11:31 | October 5, 2026 10:46 |  | 5
1902 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | October 1, 2026 11:31 | October 1, 2026 1:01 | 1884 | 6 | 4/16 -Completed
1903 | Yes | Auto Scheduled | Load | 2h | October 2, 2026 2:46 | October 2, 2026 4:46 | 1886 | 6
1904 | Yes | Auto Scheduled | Post Load Validation | 3h | October 2, 2026 4:46 | October 5, 2026 10:46 | 1903 | 6
1905 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Supplier | 1.13d | September 24, 2026 11:31 | September 25, 2026 1:31 |  | 5
1906 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 24, 2026 11:31 | September 24, 2026 1:01 | 1893 | 6
1907 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 24, 2026 1:01 | September 24, 2026 1:31 | 1906 | 6
1908 | Yes | Auto Scheduled | Simulate Load | 1h | September 24, 2026 1:31 | September 24, 2026 2:31 | 1907 | 6
1909 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 24, 2026 2:31 | September 24, 2026 4:31 | 1908 | 6
1910 | Yes | Auto Scheduled | Load | 2h | September 24, 2026 4:31 | September 25, 2026 9:31 | 1909 | 6
1911 | Yes | Auto Scheduled | Post Load Validation | 3h | September 25, 2026 9:31 | September 25, 2026 1:31 | 1910 | 6
1912 | Yes | Auto Scheduled | PTP_CM27_BP_Intercompany Customer | 1.06d | September 24, 2026 8:31 | September 25, 2026 9:01 |  | 5
1913 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 24, 2026 8:31 | September 24, 2026 9:01 |  | 6
1914 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 24, 2026 8:31 | September 24, 2026 9:01 |  | 6
1915 | Yes | Auto Scheduled | Simulate Load | 1h | September 24, 2026 9:01 | September 24, 2026 10:01 | 1914 | 6
1916 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 24, 2026 10:01 | September 24, 2026 1:01 | 1915 | 6
1917 | Yes | Auto Scheduled | Load | 2h | September 24, 2026 1:01 | September 24, 2026 3:01 | 1916 | 6
1918 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 3:01 | September 25, 2026 9:01 | 1917 | 6
1919 | Yes | Auto Scheduled | PTP_CM26_Material_Master - All Types | 2.28d | September 24, 2026 9:31 | September 28, 2026 11:46 |  | 5
1920 | Yes | Auto Scheduled | Extract File | 5h | September 24, 2026 9:31 | September 25, 2026 8:16 | 1895 | 6
1921 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 24, 2026 11:31 | September 25, 2026 9:46 | 1893 | 6
1922 | Yes | Auto Scheduled | Simulate Load | 1h | September 25, 2026 9:46 | September 25, 2026 10:46 | 1921 | 6
1923 | Yes | Auto Scheduled | Error and Defect Mitigation | 4h | September 25, 2026 10:46 | September 25, 2026 3:46 | 1922 | 6
1924 | Yes | Auto Scheduled | Load | 3h | September 25, 2026 3:46 | September 28, 2026 9:46 | 1923 | 6
1925 | Yes | Auto Scheduled | Post Load Validation | 2h | September 28, 2026 9:46 | September 28, 2026 11:46 | 1924 | 6
1926 | Yes | Auto Scheduled | PTP_CM26_Material_Master - SERV - Service Materials | 1.34d | September 25, 2026 4:31 | September 29, 2026 10:16 |  | 5
1927 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 25, 2026 4:31 | September 28, 2026 8:01 | 1796 | 6
1928 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 28, 2026 9:46 | September 28, 2026 10:16 | 1924 | 6
1929 | Yes | Auto Scheduled | Simulate Load | 1h | September 28, 2026 10:16 | September 28, 2026 11:16 | 1928 | 6
1930 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 28, 2026 11:16 | September 28, 2026 2:16 | 1929 | 6
1931 | Yes | Auto Scheduled | Load | 2h | September 28, 2026 2:16 | September 28, 2026 4:16 | 1930 | 6
1932 | Yes | Auto Scheduled | Post Load Validation | 3h | September 28, 2026 4:16 | September 29, 2026 10:16 | 1931 | 6
1933 | Yes | Auto Scheduled | PTP_CM26_Material_Master - KMAT - Configurable Materials | 1.34d | September 25, 2026 4:31 | September 29, 2026 10:16 |  | 5
1934 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 25, 2026 4:31 | September 28, 2026 8:01 | 1796 | 6
1935 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 28, 2026 9:46 | September 28, 2026 10:16 | 1924 | 6
1936 | Yes | Auto Scheduled | Simulate Load | 1h | September 28, 2026 10:16 | September 28, 2026 11:16 | 1935 | 6
1937 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 28, 2026 11:16 | September 28, 2026 2:16 | 1936 | 6
1938 | Yes | Auto Scheduled | Load | 2h | September 28, 2026 2:16 | September 28, 2026 4:16 | 1937 | 6
1939 | Yes | Auto Scheduled | Post Load Validation | 3h | September 28, 2026 4:16 | September 29, 2026 10:16 | 1938 | 6
1940 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Records | 3.59d | September 24, 2026 11:31 | September 30, 2026 8:16 |  | 5
1941 | Yes | Auto Scheduled | Extract File | 1h | September 29, 2026 10:16 | September 29, 2026 11:16 | 1925,1939 | 6 | 4/16 - Started extract
1942 | Yes | Auto Scheduled | Pre Load Validation | 2h | September 29, 2026 11:16 | September 29, 2026 2:16 | 1941 | 6
1943 | Yes | Auto Scheduled | Simulate Load | 1h | September 29, 2026 2:16 | September 29, 2026 3:16 | 1942 | 6
1944 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 29, 2026 3:16 | September 30, 2026 8:16 | 1943 | 6
1945 | Yes | Auto Scheduled | Load | 1h | September 24, 2026 11:31 | September 24, 2026 1:31 | 1893 | 6
1946 | Yes | Auto Scheduled | Post Load Validation | 2h | September 24, 2026 1:31 | September 24, 2026 3:31 | 1945 | 6
1947 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record External Processing | 1.13d | September 29, 2026 10:16 | September 30, 2026 11:16 |  | 5
1948 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 10:16 | September 29, 2026 10:46 | 1925,1939 | 6
1949 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 10:46 | September 29, 2026 11:16 | 1948 | 6
1950 | Yes | Auto Scheduled | Simulate Load | 1h | September 29, 2026 11:16 | September 29, 2026 1:16 | 1949 | 6
1951 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 29, 2026 1:16 | September 29, 2026 3:16 | 1950 | 6
1952 | Yes | Auto Scheduled | Load | 2h | September 29, 2026 3:16 | September 30, 2026 8:16 | 1951 | 6
1953 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 8:16 | September 30, 2026 11:16 | 1952 | 6
1954 | Yes | Auto Scheduled | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | 1.13d | September 29, 2026 10:16 | September 30, 2026 11:16 |  | 5
1955 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 10:16 | September 29, 2026 10:46 | 1925,1939 | 6
1956 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 10:46 | September 29, 2026 11:16 | 1955 | 6
1957 | Yes | Auto Scheduled | Simulate Load | 1h | September 29, 2026 11:16 | September 29, 2026 1:16 | 1956 | 6 | 4/16 - Eror
1958 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 29, 2026 1:16 | September 29, 2026 3:16 | 1957 | 6
1959 | Yes | Auto Scheduled | Load | 2h | September 29, 2026 3:16 | September 30, 2026 8:16 | 1958 | 6
1960 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 8:16 | September 30, 2026 11:16 | 1959 | 6
1961 | Yes | Auto Scheduled | PTM_CM31_BOM Conversion | 2.48d | September 29, 2026 11:16 | October 1, 2026 4:09 |  | 5
1962 | Yes | Auto Scheduled | Extract File | 1h | September 29, 2026 11:16 | September 29, 2026 1:16 | 1941 | 6
1963 | Yes | Auto Scheduled | Pre Load Validation | 0.5h | September 29, 2026 1:16 | September 29, 2026 1:46 | 1962 | 6
1964 | Yes | Auto Scheduled | Simulate Load | 15.5h | September 29, 2026 1:46 | October 1, 2026 1:46 | 1963 | 6
1965 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | October 1, 2026 1:46 | October 1, 2026 2:16 | 1964 | 6
1966 | Yes | Auto Scheduled | Load | 1h | October 1, 2026 2:16 | October 1, 2026 3:31 | 1965 | 6 | 4/17- Bom issues and not moving to routings...
1967 | Yes | Auto Scheduled | Post Load Validation | 0.5h | October 1, 2026 3:31 | October 1, 2026 4:09 | 1966 | 6 | 4/16 - updated to post load...
1968 | Yes | Auto Scheduled | PTM_CM40_Work Center Conversion | 3.08d | September 29, 2026 1:16 | October 2, 2026 1:54 |  | 5
1969 | Yes | Auto Scheduled | Extract File | 1h | September 29, 2026 1:16 | September 29, 2026 2:16 | 1962 | 6
1970 | Yes | Auto Scheduled | Pre Load Validation | 2h | October 1, 2026 4:09 | October 2, 2026 9:09 | 1967 | 6
1971 | Yes | Auto Scheduled | Simulate Load | 0.25h | October 2, 2026 9:09 | October 2, 2026 9:24 | 1970 | 6
1972 | Yes | Auto Scheduled | Error and Defect Mitigation | 0.5h | October 2, 2026 9:24 | October 2, 2026 9:54 | 1971 | 6 | 4/16- Defect created
1973 | Yes | Auto Scheduled | Load | 1h | October 2, 2026 9:54 | October 2, 2026 10:54 | 1972 | 6
1974 | Yes | Auto Scheduled | Post Load Validation | 2h | October 2, 2026 10:54 | October 2, 2026 1:54 | 1973 | 6
1975 | Yes | Auto Scheduled | PTM_CM38_Routing Conversion | 4.27d | September 29, 2026 2:16 | October 5, 2026 4:24 |  | 5
1976 | Yes | Auto Scheduled | Extract File | 1h | September 29, 2026 2:16 | September 29, 2026 3:16 | 1969 | 6
1977 | Yes | Auto Scheduled | Pre Load Validation | 2h | October 2, 2026 1:54 | October 5, 2026 9:24 | 1974 | 6
1978 | Yes | Auto Scheduled | Simulate Load | 2h | October 5, 2026 9:24 | October 5, 2026 11:24 | 1977 | 6 | 4/20 Cost element has been resolved and now ready to run simulation again. Need to decide if we need to load all routings or load what we have that will load
1979 | Yes | Auto Scheduled | Error and Defect Mitigation | 3h | October 5, 2026 9:24 | October 5, 2026 1:24 | 1978SS | 6
1980 | Yes | Auto Scheduled | Load | 1h | October 5, 2026 1:24 | October 5, 2026 2:24 | 1979 | 6
1981 | Yes | Auto Scheduled | Post Load Validation | 2h | October 5, 2026 2:24 | October 5, 2026 4:24 | 1980 | 6
1982 | Yes | Auto Scheduled | PTM_CM36_Production Version Conversion | 1.13d | September 29, 2026 3:16 | September 30, 2026 4:16 |  | 5
1983 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 3:16 | September 29, 2026 3:46 | 1976 | 6
1984 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 3:46 | September 29, 2026 4:16 | 1983 | 6
1985 | Yes | Auto Scheduled | Simulate Load | 1h | September 29, 2026 4:16 | September 30, 2026 8:16 | 1984 | 6
1986 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 30, 2026 8:16 | September 30, 2026 10:16 | 1985 | 6
1987 | Yes | Auto Scheduled | Load | 2h | September 30, 2026 10:16 | September 30, 2026 1:16 | 1986 | 6
1988 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 1:16 | September 30, 2026 4:16 | 1987 | 6
1989 | Yes | Auto Scheduled | PTM_CM35_Inspection Plan | 1.13d | September 30, 2026 4:16 | October 2, 2026 8:16 |  | 5 | 4/17 - will manually load IP for ITC1
1990 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 30, 2026 4:16 | September 30, 2026 4:46 | 1988 | 6 | 4/20- Per Brad they will load manaually for ITC1
1991 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 30, 2026 4:46 | October 1, 2026 8:16 | 1990 | 6
1992 | Yes | Auto Scheduled | Simulate Load | 1h | October 1, 2026 8:16 | October 1, 2026 9:16 | 1991 | 6
1993 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 1, 2026 9:16 | October 1, 2026 11:16 | 1992 | 6
1994 | Yes | Auto Scheduled | Load | 2h | October 1, 2026 11:16 | October 1, 2026 2:16 | 1993 | 6
1995 | Yes | Auto Scheduled | Post Load Validation | 3h | October 1, 2026 2:16 | October 2, 2026 8:16 | 1994 | 6
1996 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Serial Numbers | 1.13d | September 30, 2026 4:46 | October 2, 2026 8:46 |  | 5 | 4/17- will cherry pick equiments for testing ITC1/Smoke
1997 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 30, 2026 4:46 | October 1, 2026 8:16 | 1990 | 6
1998 | Yes | Auto Scheduled | Pre Load Validation | 30m | October 1, 2026 8:16 | October 1, 2026 8:46 | 1997 | 6
1999 | Yes | Auto Scheduled | Simulate Load | 1h | October 1, 2026 8:46 | October 1, 2026 9:46 | 1998 | 6
2000 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 1, 2026 9:46 | October 1, 2026 11:46 | 1999 | 6
2001 | Yes | Auto Scheduled | Load | 2h | October 1, 2026 11:46 | October 1, 2026 2:46 | 2000 | 6
2002 | Yes | Auto Scheduled | Post Load Validation | 3h | October 1, 2026 2:46 | October 2, 2026 8:46 | 2001 | 6
2003 | Yes | Auto Scheduled | PTM_CM48_Equipment_Master_Service | 6.78d | September 24, 2026 8:31 | October 2, 2026 3:46 |  | 5 | 4/17- will cherry pick equiments for testing ITC1/Smoke
2004 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | October 2, 2026 8:46 | October 2, 2026 9:16 | 2002 | 6
2005 | Yes | Auto Scheduled | Pre Load Validation | 30m | October 2, 2026 9:16 | October 2, 2026 9:46 | 2004 | 6
2006 | Yes | Auto Scheduled | Simulate Load | 1h | October 2, 2026 9:46 | October 2, 2026 10:46 | 2005 | 6
2007 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 2, 2026 10:46 | October 2, 2026 1:46 | 2006 | 6
2008 | Yes | Auto Scheduled | Load | 2h | October 2, 2026 1:46 | October 2, 2026 3:46 | 2007 | 6
2009 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 8:31 | September 24, 2026 11:31 |  | 6
2010 | Yes | Auto Scheduled | VC_Object Dependencies | 0.63d | September 24, 2026 8:31 | September 24, 2026 2:31 |  | 5
2011 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 24, 2026 8:31 | September 24, 2026 10:31 | 1771 | 6
2012 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 10:31 | September 24, 2026 2:31 | 2011 | 6
2013 | Yes | Auto Scheduled | VC_Characteristics | 0.63d | September 24, 2026 2:31 | September 25, 2026 10:31 |  | 5
2014 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 24, 2026 2:31 | September 24, 2026 4:31 | 2012 | 6
2015 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 4:31 | September 25, 2026 10:31 | 2014 | 6
2016 | Yes | Auto Scheduled | VC_Classes | 0.63d | September 25, 2026 10:31 | September 25, 2026 4:31 |  | 5
2017 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 25, 2026 10:31 | September 25, 2026 1:31 | 2015 | 6
2018 | Yes | Auto Scheduled | Post Load Validation | 3h | September 25, 2026 1:31 | September 25, 2026 4:31 | 2017 | 6
2019 | Yes | Auto Scheduled | VC_Classification (Class Type 200) | 0.63d | September 29, 2026 10:16 | September 29, 2026 4:16 |  | 5
2020 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 29, 2026 10:16 | September 29, 2026 1:16 | 1939 | 6
2021 | Yes | Auto Scheduled | Post Load Validation | 3h | September 29, 2026 1:16 | September 29, 2026 4:16 | 2020 | 6
2022 | Yes | Auto Scheduled | VC_Dependency Nets | 0.63d | September 29, 2026 10:16 | September 29, 2026 4:16 |  | 5
2023 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 29, 2026 10:16 | September 29, 2026 1:16 | 1933,2018 | 6
2024 | Yes | Auto Scheduled | Post Load Validation | 3h | September 29, 2026 1:16 | September 29, 2026 4:16 | 2023 | 6
2025 | Yes | Auto Scheduled | VC_Configuration Profiles | 0.63d | September 29, 2026 10:16 | September 29, 2026 4:16 |  | 5
2026 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 29, 2026 10:16 | September 29, 2026 1:16 | 1933 | 6
2027 | Yes | Auto Scheduled | Post Load Validation | 3h | September 29, 2026 1:16 | September 29, 2026 4:16 | 2026 | 6
2028 | Yes | Auto Scheduled | VC_Variant Tables | 0.63d | September 29, 2026 4:16 | September 30, 2026 1:16 |  | 5
2029 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 29, 2026 4:16 | September 30, 2026 9:16 | 2027 | 6
2030 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 9:16 | September 30, 2026 1:16 | 2029 | 6
2031 | Yes | Auto Scheduled | VC_Variant Tables Content | 0.63d | September 30, 2026 1:16 | October 1, 2026 9:16 |  | 5
2032 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 2h | September 30, 2026 1:16 | September 30, 2026 3:16 | 2030 | 6
2033 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 3:16 | October 1, 2026 9:16 | 2032 | 6
2034 | Yes | Auto Scheduled | VC_Characteristic Groups | 1.97d | September 29, 2026 4:16 | October 1, 2026 4:01 |  | 5 | 4/20- Defect - 963
2035 | Yes | Auto Scheduled | Run ALE Transaction to QS5 from DS4 130 | 12.75h | September 29, 2026 4:16 | October 1, 2026 1:01 | 2027 | 6 | 4/17 - Authorization error/loaded but getting in app is issue. 4/20 Defect recorded and still open
2036 | Yes | Auto Scheduled | Post Load Validation | 3h | October 1, 2026 1:01 | October 1, 2026 4:01 | 2035 | 6
2037 | Yes | Auto Scheduled | PTM_CM52_Super_BOM | 4.09d | September 29, 2026 10:16 | October 5, 2026 11:01 |  | 5 | 4/21- Pittsburg was loaded and working on remaining sites 4/20 - Working through errors with materials
2038 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 10:16 | September 29, 2026 10:46 | 1939 | 6
2039 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 10:46 | September 29, 2026 11:16 | 2038 | 6
2040 | Yes | Auto Scheduled | Simulate Load | 24.75h | September 29, 2026 11:16 | October 2, 2026 1:01 | 2039 | 6 | 4/17 - Have issues and Manoj to work with Chip
2041 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 2, 2026 1:01 | October 2, 2026 3:01 | 2040 | 6 | 4/16- Reviewing some errors , 4/17- Still running into errors
2042 | Yes | Auto Scheduled | Load | 2h | October 2, 2026 3:01 | October 5, 2026 8:01 | 2041 | 6
2043 | Yes | Auto Scheduled | Post Load Validation | 3h | October 5, 2026 8:01 | October 5, 2026 11:01 | 2042 | 6
2044 | Yes | Auto Scheduled | PTM_CM53_Super_Routing | 2.13d | October 5, 2026 11:01 | October 7, 2026 1:01 |  | 5
2045 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | October 5, 2026 11:01 | October 5, 2026 11:31 | 2043 | 6
2046 | Yes | Auto Scheduled | Pre Load Validation | 30m | October 5, 2026 11:31 | October 5, 2026 1:01 | 2045 | 6
2047 | Yes | Auto Scheduled | Simulate Load | 1h | October 5, 2026 1:01 | October 6, 2026 2:01 | 2046 | 6
2048 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | October 6, 2026 2:01 | October 6, 2026 4:01 | 2047 | 6
2049 | Yes | Auto Scheduled | Load | 2h | October 6, 2026 4:01 | October 7, 2026 9:01 | 2048 | 6
2050 | Yes | Auto Scheduled | Post Load Validation | 3h | October 7, 2026 9:01 | October 7, 2026 1:01 | 2049 | 6 | 4/22 -Loaded for Pittsburg
2051 | Yes | Auto Scheduled | VC_VK30 Pricing Variant | 0.69d | October 7, 2026 9:01 | October 7, 2026 3:31 |  | 5
2052 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | October 7, 2026 9:01 | October 7, 2026 9:31 | 2049 | 6
2053 | Yes | Auto Scheduled | Load | 2h | October 7, 2026 9:31 | October 7, 2026 11:31 | 2052 | 6
2054 | Yes | Auto Scheduled | Post Load Validation | 3h | October 7, 2026 11:31 | October 7, 2026 3:31 | 2053 | 6
2055 | Yes | Auto Scheduled | OTC_CM22_Pricing_Condition | 0.69d | October 7, 2026 3:31 | October 8, 2026 1:01 |  | 5
2056 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | October 7, 2026 3:31 | October 7, 2026 4:01 | 2054 | 6
2057 | Yes | Auto Scheduled | Load | 2h | October 7, 2026 4:01 | October 8, 2026 9:01 | 2056 | 6
2058 | Yes | Auto Scheduled | Post Load Validation | 3h | October 8, 2026 9:01 | October 8, 2026 1:01 | 2057 | 6 | 4/16 - Service to load
2059 | Yes | Auto Scheduled | OTC_CM21_CMIR | 0.5d | October 8, 2026 9:01 | October 8, 2026 2:01 |  | 5
2060 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | October 8, 2026 9:01 | October 8, 2026 9:31 | 2057,2068 | 6
2061 | Yes | Auto Scheduled | Pre Load Validation | 30m | October 8, 2026 9:31 | October 8, 2026 10:01 | 2060 | 6
2062 | Yes | Auto Scheduled | Simulate Load | 0h | October 8, 2026 10:01 | October 8, 2026 10:01 | 2061 | 6
2063 | Yes | Auto Scheduled | Error and Defect Mitigation | 0h | October 8, 2026 10:01 | October 8, 2026 10:01 | 2062 | 6
2064 | Yes | Auto Scheduled | Load | 0h | October 8, 2026 10:01 | October 8, 2026 10:01 | 2063 | 6 | 4/16 - Load done
2065 | Yes | Auto Scheduled | Post Load Validation | 3h | October 8, 2026 10:01 | October 8, 2026 2:01 | 2064 | 6
2066 | Yes | Auto Scheduled | PTP_CM29_Source_List | 6.16d | September 25, 2026 9:31 | October 5, 2026 10:46 |  | 5
2067 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | September 25, 2026 9:31 | September 25, 2026 10:01 | 1910,1917 | 6 | 4/16 -
2068 | Yes | Auto Scheduled | Load | 2h | October 2, 2026 2:46 | October 2, 2026 4:46 | 1886 | 6
2069 | Yes | Auto Scheduled | Post Load Validation | 3h | October 2, 2026 4:46 | October 5, 2026 10:46 | 2068 | 6
2070 | Yes | Auto Scheduled | RTR_CM11_Asset_Master | 6.63d | September 24, 2026 8:31 | October 2, 2026 2:31 |  | 5 | 4/20- Move to ITC2
2071 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 24, 2026 8:31 | September 24, 2026 9:01 |  | 6
2072 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 24, 2026 9:01 | September 24, 2026 9:31 | 2071 | 6
2073 | Yes | Auto Scheduled | Simulate Load | 31h | September 24, 2026 9:31 | September 30, 2026 8:31 | 2072 | 6 | 4/17 - Going back and forth
2074 | Yes | Auto Scheduled | Error and Defect Mitigation | 16h | September 30, 2026 8:31 | October 2, 2026 8:31 | 2073 | 6
2075 | Yes | Auto Scheduled | Load | 2h | October 2, 2026 8:31 | October 2, 2026 10:31 | 2074 | 6
2076 | Yes | Auto Scheduled | Post Load Validation | 3h | October 2, 2026 10:31 | October 2, 2026 2:31 | 2075 | 6
2077 | Yes | Auto Scheduled | PTM_CM50_Material Class | 2.13d | September 29, 2026 3:46 | October 1, 2026 4:46 |  | 5
2078 | Yes | Auto Scheduled | Manual File Staged and Posted "Ready" | 30m | September 29, 2026 3:46 | September 29, 2026 4:16 | 1983 | 6
2079 | Yes | Auto Scheduled | Load | 30m | September 29, 2026 4:16 | September 29, 2026 4:46 | 2078 | 6 | 4/17 -Manually loaded
2080 | Yes | Auto Scheduled | Post Load Validation | 16h | September 29, 2026 4:46 | October 1, 2026 4:46 | 2079 | 6 | 4/16 - Will load manually
2081 | Yes | Auto Scheduled | PTM_CM55_Class assignment to materials | 1.13d | September 29, 2026 4:16 | October 1, 2026 8:16 |  | 5 | 4/16 - Is not being loaded part of ITC1
2082 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 29, 2026 4:16 | September 29, 2026 4:46 | 2078 | 6
2083 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 29, 2026 4:46 | September 30, 2026 8:16 | 2082 | 6
2084 | Yes | Auto Scheduled | Simulate Load | 1h | September 30, 2026 8:16 | September 30, 2026 9:16 | 2083 | 6
2085 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 30, 2026 9:16 | September 30, 2026 11:16 | 2084 | 6
2086 | Yes | Auto Scheduled | Load | 2h | September 30, 2026 11:16 | September 30, 2026 2:16 | 2085 | 6
2087 | Yes | Auto Scheduled | Post Load Validation | 3h | September 30, 2026 2:16 | October 1, 2026 8:16 | 2086 | 6
2088 | Yes | Auto Scheduled | GTS - Material initial load from S4 (Run Interface) | 2.09d | September 29, 2026 1:16 | October 1, 2026 2:01 |  | 5
2089 | Yes | Auto Scheduled | Run material interface to GTS | 15.75h | September 29, 2026 1:16 | October 1, 2026 1:01 | 1957 | 6
2090 | Yes | Auto Scheduled | Post Load Validation | 1h | October 1, 2026 1:01 | October 1, 2026 2:01 | 2089 | 6
2091 | Yes | Auto Scheduled | GTS - Customers initial load from S4 (Run Interface) | 0.25d | September 24, 2026 8:31 | September 24, 2026 10:31 |  | 5
2092 | Yes | Auto Scheduled | Run material interface to GTS | 1h | September 24, 2026 8:31 | September 24, 2026 9:31 |  | 6
2093 | Yes | Auto Scheduled | Post Load Validation | 1h | September 24, 2026 9:31 | September 24, 2026 10:31 | 2092 | 6 | 4/17 99% complete ran in to some erros with defect 934
2094 | Yes | Auto Scheduled | GTS - Vendors initial load from S4 (Run Interface) | 0.25d | September 24, 2026 4:31 | September 25, 2026 9:31 |  | 5
2095 | Yes | Auto Scheduled | Run material interface to GTS | 1h | September 24, 2026 4:31 | September 25, 2026 8:31 | 1900 | 6 | 4/16- Have 3 records with issues
2096 | Yes | Auto Scheduled | Post Load Validation | 1h | September 25, 2026 8:31 | September 25, 2026 9:31 | 2095 | 6
2097 | Yes | Auto Scheduled | GTS - ECCN - Create | 1.13d | September 24, 2026 8:31 | September 25, 2026 9:31 |  | 5
2098 | Yes | Auto Scheduled | Load Descartes XML File | 1h | September 24, 2026 8:31 | September 24, 2026 9:31 | 1771 | 6
2099 | Yes | Auto Scheduled | Post Load Validation | 1h | September 25, 2026 8:31 | September 25, 2026 9:31 | 2095 | 6
2100 | Yes | Auto Scheduled | GTS - ECCN - Assign | 0.25d | October 1, 2026 2:01 | October 1, 2026 4:01 |  | 5
2101 | Yes | Auto Scheduled | Load Descartes XML File | 1h | October 1, 2026 2:01 | October 1, 2026 3:01 | 2090 | 6
2102 | Yes | Auto Scheduled | Post Load Validation | 1h | October 1, 2026 3:01 | October 1, 2026 4:01 | 2101 | 6
2103 | Yes | Auto Scheduled | GTS - HTS - Create | 0.25d | September 24, 2026 8:31 | September 24, 2026 10:31 |  | 5
2104 | Yes | Auto Scheduled | Load Descartes XML File | 1h | September 24, 2026 8:31 | September 24, 2026 9:31 | 1771 | 6
2105 | Yes | Auto Scheduled | Post Load Validation | 1h | September 24, 2026 9:31 | September 24, 2026 10:31 | 2104 | 6
2106 | Yes | Auto Scheduled | GTS - HTS - Assign | 0.25d | October 1, 2026 4:01 | October 2, 2026 9:01 |  | 5
2107 | Yes | Auto Scheduled | Load Descartes XML File | 1h | October 1, 2026 4:01 | October 2, 2026 8:01 | 2102 | 6
2108 | Yes | Auto Scheduled | Post Load Validation | 1h | October 2, 2026 8:01 | October 2, 2026 9:01 | 2107 | 6
2109 | Yes | Auto Scheduled | GTS - License - Create | 0.25d | October 2, 2026 10:01 | October 2, 2026 1:01 |  | 5
2110 | Yes | Auto Scheduled | Load Descartes XML File | 1h | October 2, 2026 10:01 | October 2, 2026 11:01 | 2107,2123 | 6 | 4/13 - Need to update dep.
2111 | Yes | Auto Scheduled | Post Load Validation | 1h | October 2, 2026 11:01 | October 2, 2026 1:01 | 2110 | 6
2112 | Yes | Auto Scheduled | Commodity Code/Tarif | 2.78d | October 2, 2026 9:01 | October 6, 2026 4:16 |  | 5
2113 | Yes | Auto Scheduled | Load | 21.25h | October 2, 2026 9:01 | October 6, 2026 3:16 | 2108 | 6 | 4/17- wants to use the old load program
2114 | Yes | Auto Scheduled | Post Load Validation | 1h | October 6, 2026 3:16 | October 6, 2026 4:16 | 2113 | 6
2115 | Yes | Auto Scheduled | SPL Master File | 0.25d | October 2, 2026 8:01 | October 2, 2026 10:01 |  | 5
2116 | Yes | Auto Scheduled | Load | 1h | October 2, 2026 8:01 | October 2, 2026 9:01 | 2107 | 6
2117 | Yes | Auto Scheduled | Post Load Validation | 1h | October 2, 2026 9:01 | October 2, 2026 10:01 | 2116 | 6
2118 | Yes | Auto Scheduled | Initialize Embargo situation | 0.38d | September 25, 2026 9:31 | September 25, 2026 1:31 |  | 5
2119 | Yes | Auto Scheduled | Run report /SAPSLL/EMB_CNTRY_INIT | 1h | September 25, 2026 9:31 | September 25, 2026 10:31 | 2099 | 6
2120 | Yes | Auto Scheduled | Set Embargo situations | 1h | September 25, 2026 10:31 | September 25, 2026 11:31 | 2119 | 6 | 4/17 - Needs access
2121 | Yes | Auto Scheduled | Post Load Validation | 1h | September 25, 2026 11:31 | September 25, 2026 1:31 | 2120 | 6
2122 | Yes | Auto Scheduled | GTS - SPL (Sanctioned party list) | 0.25d | October 2, 2026 9:01 | October 2, 2026 11:01 |  | 5
2123 | Yes | Auto Scheduled | Load Descartes XML File | 1h | October 2, 2026 9:01 | October 2, 2026 10:01 | 2108 | 6
2124 | Yes | Auto Scheduled | Post Load Validation | 1h | October 2, 2026 10:01 | October 2, 2026 11:01 | 2123 | 6
2125 | Yes | Auto Scheduled | RTR_CM17_Project Definition / Builder | 1.13d | September 24, 2026 9:01 | September 25, 2026 10:01 |  | 5 | 4/20 - Will have files to load in the morning
2126 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 24, 2026 9:01 | September 24, 2026 9:31 | 2071 | 6
2127 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 24, 2026 9:31 | September 24, 2026 10:01 | 2126 | 6
2128 | Yes | Auto Scheduled | Simulate Load | 1h | September 24, 2026 10:01 | September 24, 2026 11:01 | 2127 | 6
2129 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 24, 2026 11:01 | September 24, 2026 2:01 | 2128 | 6
2130 | Yes | Auto Scheduled | Load | 2h | September 24, 2026 2:01 | September 24, 2026 4:01 | 2129 | 6
2131 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 4:01 | September 25, 2026 10:01 | 2130 | 6
2132 | Yes | Auto Scheduled | RTR_CM18_WBS Element | 1.25d | September 24, 2026 8:31 | September 25, 2026 10:31 |  | 5
2133 | Yes | Auto Scheduled | Load File Staged and Posted "Ready" | 30m | September 24, 2026 9:31 | September 24, 2026 10:01 | 2126 | 6
2134 | Yes | Auto Scheduled | Pre Load Validation | 30m | September 24, 2026 10:01 | September 24, 2026 10:31 | 2133 | 6
2135 | Yes | Auto Scheduled | Simulate Load | 1h | September 24, 2026 10:31 | September 24, 2026 11:31 | 2134 | 6
2136 | Yes | Auto Scheduled | Error and Defect Mitigation | 2h | September 24, 2026 11:31 | September 24, 2026 2:31 | 2135 | 6
2137 | Yes | Auto Scheduled | Load | 2h | September 24, 2026 2:31 | September 24, 2026 4:31 | 2136 | 6
2138 | Yes | Auto Scheduled | Post Load Validation | 3h | September 24, 2026 4:31 | September 25, 2026 10:31 | 2137 | 6
2139 | Yes | Auto Scheduled | UAT Mock Data Loads Complete | 15m | September 24, 2026 8:31 | September 24, 2026 8:46 |  | 6
2140 | Yes | Auto Scheduled | PROD Master Data Loads Complete | 0m | October 1, 2026 8:31 | October 1, 2026 8:31 | 1772 | 4
2141 | Yes | Auto Scheduled | Mock Transactional Data | 2d | October 1, 2026 8:31 | October 5, 2026 8:31 | 2140 | 4
2142 | Yes | Auto Scheduled | Inventory | 4h | October 1, 2026 8:31 | October 1, 2026 1:31 | 2140SS,998SS | 5
2143 | Yes | Auto Scheduled | Open AR | 4h | October 1, 2026 1:31 | October 2, 2026 8:31 | 2142 | 5
2144 | Yes | Auto Scheduled | Open AP | 4h | October 2, 2026 8:31 | October 2, 2026 1:31 | 2143 | 5
2145 | Yes | Auto Scheduled | Bank and Cash | 4h | October 2, 2026 1:31 | October 5, 2026 8:31 | 2144 | 5
2146 | Yes | Auto Scheduled | Open Purchase Orders(Manual) | 1d | October 1, 2026 1:31 | October 2, 2026 1:31 | 2142 | 5
2147 | Yes | Auto Scheduled | Open Sales Orders(Manual) | 1d | October 1, 2026 1:31 | October 2, 2026 1:31 | 2142 | 5
2148 | Yes | Auto Scheduled | Service Orders(Manual) | 0.5d | October 1, 2026 1:31 | October 2, 2026 8:31 | 2142 | 5
2149 | Yes | Auto Scheduled | Open Production Orders(Manual) | 1d | October 1, 2026 1:31 | October 2, 2026 1:31 | 2142 | 5
2150 | Yes | Auto Scheduled | PRO Data Loads Complete | 15m | October 5, 2026 8:31 | October 5, 2026 8:46 | 2141 | 4
2151 | Yes | Auto Scheduled | Solution Readniess | 131.5d | April 16, 2026 8:00 | October 16, 2026 12:00 |  | 2
2152 | Yes | Auto Scheduled | Business Process Design Documentation | 20d | May 4, 2026 8:00 | May 29, 2026 5:00 |  | 3
2153 | Yes | Auto Scheduled | FICO | 20d | May 4, 2026 8:00 | May 29, 2026 5:00 |  | 4
2154 | Yes | Auto Scheduled | Order to Cash | 20d | May 4, 2026 8:00 | May 29, 2026 5:00 |  | 4
2155 | Yes | Auto Scheduled | Procure to Pay | 20d | May 4, 2026 8:00 | May 29, 2026 5:00 |  | 4
2156 | Yes | Auto Scheduled | Plan to Make | 20d | May 4, 2026 8:00 | May 29, 2026 5:00 |  | 4
2157 | Yes | Auto Scheduled | Development RICEFW | 75d | May 4, 2026 8:00 | August 14, 2026 5:00 |  | 3
2158 | Yes | Auto Scheduled | Reports | 75d | May 4, 2026 8:00 | August 14, 2026 5:00 |  | 4
2159 | Yes | Auto Scheduled | Interfaces | 75d | May 4, 2026 8:00 | August 14, 2026 5:00 |  | 4
2160 | Yes | Auto Scheduled | Enhanchments | 61d | May 4, 2026 8:00 | August 14, 2026 5:00 |  | 4
2161 | Yes | Auto Scheduled | Workflow | 75d | May 4, 2026 8:00 | August 14, 2026 5:00 |  | 4
2162 | Yes | Auto Scheduled | Forms | 0d | August 14, 2026 5:00 | August 14, 2026 5:00 |  | 4
2163 | Yes | Auto Scheduled | Testing Cycles | 131.5d | April 16, 2026 8:00 | October 16, 2026 12:00 |  | 3
2164 | Yes | Auto Scheduled | Test Readiness Review (TRR) - ITC 1 | 1h | April 16, 2026 8:00 | May 1, 2026 8:45 | 628 | 4
2165 | Yes | Auto Scheduled | Test Readiness Review (TRR) - ITC 2 | 1h | October 12, 2026 2:00 | October 12, 2026 3:00 | 1008,2180 | 4
2166 | Yes | Auto Scheduled | Test Readiness Review (TRR) - ITC 3 | 1h | June 30, 2026 11:00 | June 30, 2026 12:00 | 2190,1388 | 4
2167 | Yes | Auto Scheduled | Test Readiness Review (TRR) - UAT | 1h | October 16, 2026 11:00 | October 16, 2026 12:00 | 1769,2199,2150 | 4
2168 | Yes | Auto Scheduled | ITC-1 | 23.88d | April 16, 2026 9:00 | May 19, 2026 5:00 | 2164 | 4
2169 | Yes | Auto Scheduled | Testing expectations | 1h | April 16, 2026 9:00 | April 16, 2026 10:00 | 2164 | 5
2170 | Yes | Auto Scheduled | Functional Smoke Testing | 5d | April 20, 2026 8:00 | April 29, 2026 12:00 | 2169 | 5
2171 | Yes | Auto Scheduled | Assign Tester ID's | 2h | April 16, 2026 9:00 | April 23, 2026 4:30 | 2164 | 5
2172 | Yes | Auto Scheduled | ITC-1 Team Testing | 15d | April 27, 2026 8:00 | May 18, 2026 10:45 | 2171 | 5
2173 | Yes | Auto Scheduled | ITC-1 Defect Correction / Retesting / Mitigation / Close | 10d | May 6, 2026 8:00 | May 19, 2026 5:00 | 2172SS+4d | 5
2174 | Yes | Auto Scheduled | ITC-1 Gate Review | 8h | May 15, 2026 8:00 | May 15, 2026 5:00 | 2173FS-3d | 5
2175 | Yes | Auto Scheduled | ITC-2 | 15.13d | May 29, 2026 4:00 | June 19, 2026 5:00 |  | 4
2176 | Yes | Auto Scheduled | Assign Resources to Depolyment 1 locations | 2h | May 29, 2026 4:00 | June 1, 2026 9:00 | 998 | 5
2177 | Yes | Auto Scheduled | Assign Tester ID's | 2h | May 29, 2026 4:00 | June 1, 2026 9:00 | 2176SS | 5
2178 | Yes | Auto Scheduled | Identify Data and Processes for ITC | 1d | May 29, 2026 4:00 | June 1, 2026 4:00 | 2177SS | 5
2179 | Yes | Auto Scheduled | Run Costing for Data Identified(or ALL) | 4h | June 1, 2026 4:00 | June 2, 2026 11:00 | 2178 | 5
2180 | Yes | Auto Scheduled | Functional Smoke Testing | 5d | June 2, 2026 11:00 | June 9, 2026 11:00 | 2179 | 5
2181 | Yes | Auto Scheduled | Test Kickoff | 1h | June 8, 2026 8:00 | June 8, 2026 9:00 | 2165 | 5
2182 | Yes | Auto Scheduled | Team Testing | 10d | June 8, 2026 8:00 | June 19, 2026 5:00 | 2181SS | 5
2183 | Yes | Auto Scheduled | Defect Correction / Retesting / Mitigation / Close | 5d | June 11, 2026 8:00 | June 17, 2026 5:00 | 2182SS+3d | 5
2184 | Yes | Auto Scheduled | Gate Review | 1h | June 17, 2026 8:00 | June 17, 2026 9:00 | 2183SS+4d | 5
2185 | Yes | Auto Scheduled | ITC-3 | 25.13d | June 19, 2026 4:00 | July 24, 2026 5:00 |  | 4
2186 | Yes | Auto Scheduled | Assign Resources to Depolyment 1 locations | 2h | June 19, 2026 4:00 | June 22, 2026 9:00 | 1378 | 5
2187 | Yes | Auto Scheduled | Assign Tester ID's | 2h | June 19, 2026 4:00 | June 22, 2026 9:00 | 2186SS | 5
2188 | Yes | Auto Scheduled | Identify Data and Processes for ITC | 1d | June 19, 2026 4:00 | June 22, 2026 4:00 | 2187SS | 5
2189 | Yes | Auto Scheduled | Run Costing for Data Identified | 4h | June 22, 2026 4:00 | June 23, 2026 11:00 | 2188 | 5
2190 | Yes | Auto Scheduled | Functional Smoke Testing | 5d | June 23, 2026 11:00 | June 30, 2026 11:00 | 2189 | 5
2191 | Yes | Auto Scheduled | Test Kickoff | 1h | July 13, 2026 8:00 | July 13, 2026 9:00 | 2166 | 5
2192 | Yes | Auto Scheduled | Team Testing | 10d | July 13, 2026 8:00 | July 24, 2026 5:00 | 2191SS | 5
2193 | Yes | Auto Scheduled | Defect Correction / Retesting / Mitigation / Close | 5d | July 16, 2026 8:00 | July 22, 2026 5:00 | 2192SS+3d | 5
2194 | Yes | Auto Scheduled | Gate Review | 0h | July 21, 2026 5:00 | July 21, 2026 5:00 | 2193SS+4d | 5
2195 | Yes | Auto Scheduled | UAT (DR) | 44.38d | August 17, 2026 8:00 | October 16, 2026 11:00 |  | 4
2196 | Yes | Auto Scheduled | Assign Resources to Depolyment 1 locations | 2h | October 8, 2026 2:00 | October 8, 2026 4:00 | 1759,2140 | 5
2197 | Yes | Auto Scheduled | Assign Tester ID's | 2h | October 8, 2026 4:00 | October 9, 2026 9:00 | 2196 | 5
2198 | Yes | Auto Scheduled | Run Costing for Data Identified | 4h | October 8, 2026 4:00 | October 9, 2026 11:00 | 2197SS | 5
2199 | Yes | Auto Scheduled | Functional Smoke Testing | 5d | October 9, 2026 11:00 | October 16, 2026 11:00 | 2198 | 5
2200 | Yes | Auto Scheduled | Test Kickoff | 1h | August 17, 2026 8:00 | August 17, 2026 9:00 | 2167 | 5
2201 | Yes | Auto Scheduled | Team Testing | 10d | August 17, 2026 8:00 | August 28, 2026 5:00 | 2200SS | 5
2202 | Yes | Auto Scheduled | Defect Correction / Retesting / Mitigation / Close | 0d | August 19, 2026 5:00 | August 19, 2026 5:00 | 2201SS+3d | 5
2203 | Yes | Auto Scheduled | Gate Review | 0h | August 25, 2026 5:00 | August 25, 2026 5:00 | 2202SS+4d | 5
2204 | Yes | Auto Scheduled | Business Readniess | 191d | February 16, 2026 8:00 | November 9, 2026 5:00 |  | 2
2205 | Yes | Auto Scheduled | Training Readiness | 191d | February 16, 2026 8:00 | November 9, 2026 5:00 |  | 3
2206 | Yes | Auto Scheduled | Content Development | 191d | February 16, 2026 8:00 | November 9, 2026 5:00 |  | 4
2207 | Yes | Auto Scheduled | Verify Role Mapping Complete | 66d | May 1, 2026 8:00 | July 31, 2026 5:00 |  | 5
2208 | Yes | Auto Scheduled | Develop Curriculum | 66d | May 1, 2026 8:00 | July 31, 2026 5:00 | 2207SS | 5
2209 | Yes | Auto Scheduled | Develop Course ppts | 86d | May 1, 2026 8:00 | August 28, 2026 5:00 | 2208SS | 5
2210 | Yes | Auto Scheduled | Develop Work Instructions | 86d | May 1, 2026 8:00 | August 28, 2026 5:00 | 2209SS | 5
2211 | Yes | Auto Scheduled | Develop Training Data Sheets (Testing/Training) | 71d | August 3, 2026 8:00 | November 9, 2026 5:00 | 2208 | 5
2212 | Yes | Auto Scheduled | Develop Train the Trainer | 120d | February 16, 2026 8:00 | July 31, 2026 5:00 | 2207SS | 5
2213 | Yes | Auto Scheduled | Publish Training Materials to SP/LMS | 6d | August 31, 2026 8:00 | September 7, 2026 5:00 | 2209 | 5
2214 | Yes | Auto Scheduled | Talent LMS Application Setup | 1d | August 31, 2026 8:00 | August 31, 2026 5:00 | 2209 | 4
2215 | Yes | Auto Scheduled | Train the Trainer | 20d | August 3, 2026 8:00 | August 28, 2026 5:00 |  | 4
2216 | Yes | Auto Scheduled | Deliver Train the Trainer (BPL->SME) | 20d | August 3, 2026 8:00 | August 28, 2026 5:00 | 2212 | 5
2217 | Yes | Auto Scheduled | End User Training Exeuction | 71d | July 10, 2026 8:00 | October 16, 2026 5:00 |  | 4
2218 | Yes | Auto Scheduled | User Training Plan and Schedule | 136h | July 10, 2026 8:00 | August 3, 2026 5:00 |  | 5
2219 | Yes | Auto Scheduled | Deliver End User Training | 35d | August 31, 2026 8:00 | October 16, 2026 5:00 | 2216 | 5

## Sheet1
#VALUE!

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Renee | R | Work |  |  |  |  | 100% | 0.00/h | 0
2 | Basis | B | Work |  |  |  |  | 100% | 0.00/h | 0
3 | Security | S | Work |  |  |  |  | 100% | 0.00/h | 0
4 | Functional Leads | F | Work |  |  |  |  | 100% | 0.00/h | 0
5 | PMO | P | Work |  |  |  |  | 100% | 0.00/h | 0
6 | Training | T | Work |  |  |  |  | 100% | 0.00/h | 0
7 | Data | D | Work |  |  |  |  | 100% | 0.00/h | 0
8 | Controlling Team | C | Work |  |  |  |  | 100% | 0.00/h | 0
9 | DCT-DMC | D | Work |  |  |  |  | 100% | 0.00/h | 0
10 | Kasey Hughes | K | Work |  |  |  |  | 100% | 0.00/h | 0
11 | Femi Oguntala | F | Work |  |  |  |  | 100% | 0.00/h | 0
12 | Brian | B | Work |  |  |  |  | 100% | 0.00/h | 0
13 | Jared | J | Work |  |  |  |  | 100% | 0.00/h | 0
14 | Ade | A | Work |  |  |  |  | 100% | 0.00/h | 0
15 | Brian Wagner | B | Work |  |  |  |  | 100% | 0.00/h | 0
16 | Ade John | A | Work |  |  |  |  | 100% | 0.00/h | 0
17 | Jared Allen | J | Work |  |  |  |  | 100% | 0.00/h | 0
18 | Kim Kolesar | K | Work |  |  |  |  | 100% | 0.00/h | 0
19 | Ric Haraida | R | Work |  |  |  |  | 100% | 0.00/h | 0
20 | Denis Dubrovin | D | Work |  |  |  |  | 100% | 0.00/h | 0
21 | Nevin Varkkey | N | Work |  |  |  |  | 100% | 0.00/h | 0
22 | Kim Kolesar; Dave Duda | K | Work |  |  |  |  | 100% | 0.00/h | 0
23 | Matt Palastro | M | Work |  |  |  |  | 100% | 0.00/h | 0
24 | Kim Kolesar; Dave Duda; Matt Palastro | K | Work |  |  |  |  | 100% | 0.00/h | 0
25 | Nevin Varkey | N | Work |  |  |  |  | 100% | 0.00/h | 0
26 | Dev Team | D | Work |  |  |  |  | 100% | 0.00/h | 0
27 | Data Migration Team | D | Work |  |  |  |  | 100% | 0.00/h | 0
28 | NS2 | N | Work |  |  |  |  | 100% | 0.00/h | 0
29 | OTC | O | Work |  |  |  |  | 100% | 0.00/h | 0
30 | Mark George | M | Work |  |  |  |  | 100% | 0.00/h | 0
31 | Brad | B | Work |  |  |  |  | 100% | 0.00/h | 0
32 | Eric Heiler | E | Work |  |  |  |  | 100% | 0.00/h | 0
33 | Eric Heisler | E | Work |  |  |  |  | 100% | 0.00/h | 0
34 | Brad Meseck | B | Work |  |  |  |  | 100% | 0.00/h | 0
35 | James | J | Work |  |  |  |  | 100% | 0.00/h | 0
36 | James Van Riper | J | Work |  |  |  |  | 100% | 0.00/h | 0
37 | Keith Riley | K | Work |  |  |  |  | 100% | 0.00/h | 0
38 | Sam | S | Work |  |  |  |  | 100% | 0.00/h | 0
39 | Nwe | N | Work |  |  |  |  | 100% | 0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Change Request to NS2 | Basis | 1 | 1h | 100%
Dev Environment Release from SAP | NS2 | 1 | 0h | 100%
Release Setup ID's and Access | Security | 1 | 1h | 100%
Client Config / Validation | Basis | 1 | 8h | 100%
Technical Transports / BP Setup | Basis | 1 | 8h | 100%
Best Practice / Country Validation | Basis | 1 | 8h | 100%
Connect Systems and Validate | Basis | 1 | 8h | 100%
Validate Syniti Connections to QS5 | Data | 1 | 8h | 100%
Security Transports | Security | 1 | 4h | 100%
Security Manual Tasks | Security | 1 | 8h | 100%
Manual Technical Tasks | Basis | 1 | 8h | 100%
Validate Fiori | Basis | 1 | 4h | 100%
Fiori App Activation | Dev Team | 1 | 6h | 100%
Download Transport List | Basis | 1 | 1h | 100%
Business Functions Validation | Basis | 1 | 8h | 100%
Functional Leads Validation of Transport List | Functional Leads | 1 | 1h | 100%
Release Security roles to Functional Team | Security | 1 | 1h | 100%
Import Group 1 - Ent Structure | Functional Leads | 1 | 2h | 100%
Manual activities group 1 | Functional Leads | 1 | 20h | 100%
Import Group 2 - Core Transports | Functional Leads | 1 | 2h | 100%
Manual activities group 2 | Functional Leads | 1 | 8h | 100%
Import Group 3 - prior to transactions | Functional Leads | 1 | 2h | 100%
Manual Activities Group 3 | Functional Leads | 1 | 8h | 100%
Import Group 4 - workbench / dev work | Dev Team | 1 | 2h | 100%
Import Group 5 - Config to support dev workbench | Dev Team | 1 | 2h | 100%
Create Migration Data Project in DMC | Data Migration Team | 1 | 8h | 100%
Environment Ready for Build | PMO | 1 | 0h | 100%
Dev Refresh Basis(Workinig with NS2) | Basis | 1 | 16h | 100%
Client Config / Validation | Basis | 1 | 8h | 100%
Technical Transports / BP Setup | Basis | 1 | 8h | 100%
Best Practice / Country Validation | Basis | 1 | 8h | 100%
Connect Systems and Validate | Basis | 1 | 8h | 100%
Validate Syniti Connections to QS5 | Data | 1 | 8h | 100%
Security Transports | Security | 1 | 4h | 100%
Security Manual Tasks | Security | 1 | 8h | 100%
Manual Technical Tasks | Basis | 1 | 8h | 100%
Validate Fiori | Basis | 0.25 | 8h | 100%
Fiori App Activation | Dev Team | 0.25 | 8h | 100%
Download Transport List | Basis | 0.25 | 1h | 100%
Business Functions Validation | Basis | 0.25 | 8h | 100%
Functional Leads Validation of Transport List | Functional Leads | 0 | 1h | 100%
Release Security roles to Functional Team | Security | 0 | 1h | 100%
Import Group 1 - Ent Structure | Functional Leads | 0 | 2h | 100%
Manual activities group 1 | Functional Leads | 0 | 20h | 100%
Import Group 2 - Core Transports | Functional Leads | 0 | 2h | 100%
Manual activities group 2 | Functional Leads | 0 | 8h | 100%
Import Group 3 - prior to transactions | Functional Leads | 0 | 2h | 100%
Manual Activities Group 3 | Functional Leads | 0 | 8h | 100%
Import Group 4 - workbench / dev work | Dev Team | 0 | 2h | 100%
Import Group 5 - Config to support dev workbench | Dev Team | 0 | 8.5h | 100%
Open Client | Basis | 0 | 0.25h | 100%
Create Migration Data Project in DMC | Data Migration Team | 0 | 4h | 100%
Close Client | Basis | 0 | 0.25h | 100%
Environment Ready for Test | PMO | 0 | 0h | 100%
System Refresh Basis(Workinig with NS2) | Basis | 0 | 24h | 100%
Client Config / Validation | Basis | 0 | 8h | 100%
Technical Transports / BP Setup | Basis | 0 | 8h | 100%
Best Practice / Country Validation | Basis | 0 | 8h | 100%
Connect Systems and Validate | Basis | 0 | 8h | 100%
Validate Syniti Connections to QS5 | Data | 0 | 8h | 100%
Security Transports | Security | 0 | 4h | 100%
Security Manual Tasks | Security | 0 | 8h | 100%
Manual Technical Tasks | Basis | 0 | 8h | 100%
Validate Fiori | Basis | 0 | 4h | 100%
Fiori App Activation | Dev Team | 0 | 6h | 100%
Download Transport List | Basis | 0 | 1h | 100%
Business Functions Validation | Basis | 0 | 8h | 100%
Functional Leads Validation of Transport | Functional Leads | 0 | 1h | 100%
Release Security roles to Functional Team | Security | 0 | 1h | 100%
Import Group 1 - Ent Structure | Functional Leads | 0 | 2h | 100%
Manual activities group 1 | Functional Leads | 0 | 20h | 100%
Import Group 2 - Core Transports | Functional Leads | 0 | 2h | 100%
Manual activities group 2 | Functional Leads | 0 | 8h | 100%
Import Group 3 - prior to transactions | Functional Leads | 0 | 2h | 100%
Manual Activities Group 3 | Functional Leads | 0 | 8h | 100%
Import Group 4 - workbench / dev work | Dev Team | 0 | 2h | 100%
Import Group 5 - Config to support dev workbench | Dev Team | 0 | 8.5h | 100%
Open Client | Basis | 0 | 0.25h | 100%
Create Migration Data Project in DMC | Data Migration Team | 0 | 4h | 100%
Close Client | Basis | 0 | 0.25h | 100%
Environment Ready for Test | PMO | 0 | 0h | 100%
System Refresh Basis(Workinig with NS2) | Basis | 0 | 16h | 100%
Client Config / Validation | Basis | 0 | 16h | 100%
Technical Transports / BP Setup | Basis | 0 | 8h | 100%
Best Practice / Country Validation | Basis | 0 | 8h | 100%
Connect Systems and Validate | Basis | 0 | 16h | 100%
Validate Syniti Connections to QS5 | Data | 0 | 8h | 100%
Security Transports | Security | 0 | 8h | 100%
Security Manual Tasks | Security | 0 | 8h | 100%
Manual Technical Tasks | Basis | 0 | 8h | 100%
Validate Fiori | Basis | 0 | 8h | 100%
Fiori App Activation | Dev Team | 0 | 8h | 100%
Download Transport List | Basis | 0 | 1h | 100%
Business Functions Validation | Basis | 0 | 8h | 100%
Functional Leads Validation of Transport List | Functional Leads | 0 | 8h | 100%
Release Security roles to Functional Team | Security | 0 | 1h | 100%
Import Group 1 - Ent Structure | Functional Leads | 0 | 2h | 100%
Manual activities group 1 | Functional Leads | 0 | 20h | 100%
Import Group 2 - Core Transports | Functional Leads | 0 | 2h | 100%
Manual activities group 2 | Functional Leads | 0 | 8h | 100%
Import Group 3 - prior to transactions | Functional Leads | 0 | 2h | 100%
Manual Activities Group 3 | Functional Leads | 0 | 8h | 100%
Import Group 4 - workbench / dev work | Dev Team | 0 | 2h | 100%
Import Group 5 - Config to support dev workbench | Dev Team | 0 | 2h | 100%
Open Client | Basis | 0 | 0.25h | 100%
Create Migration Data Project in DMC | Data Migration Team | 0 | 4h | 100%
Close Client | Basis | 0 | 0.25h | 100%
Environment Ready for Build | PMO | 0 | 0h | 100%
System Refresh Basis(Workinig with NS2) | Basis | 0 | 16h | 100%
Client Config / Validation | Basis | 0 | 16h | 100%
Technical Transports / BP Setup | Basis | 0 | 8h | 100%
Best Practice / Country Validation | Basis | 0 | 8h | 100%
Connect Systems and Validate | Basis | 0 | 16h | 100%
Validate Syniti Connections to QS5 | Data | 0 | 8h | 100%
Security Transports | Security | 0 | 8h | 100%
Security Manual Tasks | Security | 0 | 8h | 100%
Manual Technical Tasks | Basis | 0 | 8h | 100%
Validate Fiori | Basis | 0 | 8h | 100%
Fiori App Activation | Dev Team | 0 | 8h | 100%
Download Transport List | Basis | 0 | 1h | 100%
Business Functions Validation | Basis | 0 | 8h | 100%
Functional Leads Validation of Transport List | Functional Leads | 0 | 8h | 100%
Release Security roles to Functional Team | Security | 0 | 1h | 100%
Import Group 1 - Ent Structure | Functional Leads | 0 | 2h | 100%
Manual activities group 1 | Functional Leads | 0 | 20h | 100%
Import Group 2 - Core Transports | Functional Leads | 0 | 2h | 100%
Manual activities group 2 | Functional Leads | 0 | 8h | 100%
Import Group 3 - prior to transactions | Functional Leads | 0 | 2h | 100%
Manual Activities Group 3 | Functional Leads | 0 | 8h | 100%
Import Group 4 - workbench / dev work | Dev Team | 0 | 2h | 100%
Import Group 5 - Config to support dev workbench | Dev Team | 0 | 2h | 100%
Open Client | Basis | 0 | 0.25h | 100%
Create Migration Data Project in DMC | Data Migration Team | 0 | 4h | 100%
Close Client | Basis | 0 | 0.25h | 100%
Environment Ready for Build | PMO | 0 | 0h | 100%
RCM Development | Controlling Team | 1 | 8h | 100%
PMO Authorization to Start Data Loads | Mark George | 1 | 0.25h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 1 | 1h | 100%
Load | Kasey Hughes | 1 | 2h | 100%
Post Load Validation | Kasey Hughes | 1 | 3h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 1 | 1h | 100%
Load | Kasey Hughes | 1 | 2h | 100%
Post Load Validation | Kasey Hughes | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 1 | 1h | 100%
Pre Load Validation | Kasey Hughes | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 6h | 100%
Error and Defect Mitigation | Kasey Hughes | 1 | 2h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Kasey Hughes | 1 | 2h | 100%
Extend GL to all Company Codes | Kasey Hughes | 1 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 1 | 1h | 100%
Pre Load Validation | Kasey Hughes | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 1 | 2h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Kasey Hughes | 1 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 1 | 1h | 100%
Pre Load Validation | Kasey Hughes | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 1 | 2h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Kasey Hughes | 1 | 2h | 100%
Open Client | Basis | 1 | 0.5h | 100%
Service Enterprise Setup | Keith Riley | 1 | 40h | 100%
Close Client | Basis | 1 | 0.5h | 100%
Intercompany Business Partner Setup | Functional Leads | 1 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 1 | 1h | 100%
Pre Load Validation | Kasey Hughes | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 1 | 2h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Kasey Hughes | 1 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 1 | 1h | 100%
Pre Load Validation | Kasey Hughes | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 1 | 2h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Kasey Hughes | 1 | 2h | 100%
Load File Staged and Posted "Ready" | Data Migration Team | 1 | 1h | 100%
Pre Load Validation | Kasey Hughes | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 1 | 2h | 100%
Load | Data Migration Team | 1 | 5h | 100%
Post Load Validation | Kasey Hughes | 1 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 1 | 1h | 100%
Pre Load Validation | Kasey Hughes | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 1 | 2h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Kasey Hughes | 1 | 2h | 100%
RTR_CM14_Cost Element_Group | Kasey Hughes | 1 | 43h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 1 | 0.5h | 100%
Load | Kasey Hughes | 1 | 32h | 100%
Post Load Validation | Kasey Hughes | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 1 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 1 | 0.5h | 100%
Open client for BP number range update | Basis | 1 | 0.5h | 100%
Update number range BP02 from Internal to External | Ric Haraida | 1 | 0.5h | 100%
Close Client | Basis | 1 | 0.25h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Ric Haraida | 1 | 4h | 100%
Load | Data Migration Team | 1 | 3h | 100%
Post Load Validation | Ric Haraida | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 1 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Ric Haraida | 1 | 3h | 100%
Load | Data Migration Team | 1 | 3h | 100%
Post Load Validation | Ric Haraida | 1 | 3h | 100%
Open client for BP number range update | Basis | 1 | 0.25h | 100%
Update number range BP02 from Internal to External | Ric Haraida | 1 | 0.25h | 100%
Close Client | Basis | 1 | 0.25h | 100%
Extract File | Data Migration Team | 1 | 1h | 100%
Pre Load Validation | Nevin Varkey | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 11.25h | 100%
Error and Defect Mitigation | Nevin Varkey | 1 | 2h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Nevin Varkey | 1 | 2h | 100%
Manual File Staged and Posted "Ready" | Ric Haraida | 1 | 0.5h | 100%
Load | Ric Haraida | 1 | 2h | 100%
Post Load Validation | Ric Haraida | 1 | 3h | 100%
Extract File | Data Migration Team | 1 | 1h | 100%
Pre Load Validation | Nevin Varkey | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 1 | 2h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Nevin Varkey | 1 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 1 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Kasey Hughes | 1 | 3h | 100%
Extract File | Data Migration Team | 1 | 1h | 100%
Pre Load Validation | Nevin Varkey | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 2.25h | 100%
Error and Defect Mitigation | Nevin Varkey | 1 | 2h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Nevin Varkey | 1 | 2h | 100%
Extract File(Will Extract from LFA1) | Nevin Varkey | 1 | 1h | 100%
Pre Load Validation | Nevin Varkey | 1 | 2h | 100%
Simulate Load/ Not Needed | Nevin Varkey | 1 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 1 | 2h | 100%
Load | Nevin Varkkey | 1 | 1h | 100%
Post Load Validation | Nevin Varkey | 1 | 2h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 1 | 0.5h | 100%
Load | Kasey Hughes | 1 | 2h | 100%
Post Load Validation | Kasey Hughes | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 1 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 1 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 1 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 1 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Nevin Varkey | 1 | 3h | 100%
Post Load Validation | Ric Haraida | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 1 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 1 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 1 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 1 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Nevin Varkey | 1 | 3h | 100%
Post Load Validation | Ric Haraida | 1 | 3h | 100%
Extract File | Data Migration Team | 1 | 5h | 100%
Pre Load Validation | Nevin Varkey | 1 | 2h | 100%
Pre Load Validation | Ric Haraida | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 1 | 4h | 100%
Load | Data Migration Team | 1 | 3h | 100%
Post Load Validation | Nevin Varkey | 1 | 2h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 1 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 1 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 1 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 1 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Nevin Varkey | 1 | 3h | 100%
Post Load Validation | Ric Haraida | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 1 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Eric Heisler | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Extract File | Data Migration Team | 1 | 1h | 100%
Pre Load Validation | Nevin Varkey | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 1 | 2h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Nevin Varkey | 1 | 2h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 1 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Nevin Varkey | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 1 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Nevin Varkey | 1 | 3h | 100%
Extract File | Data Migration Team | 1 | 1h | 100%
Pre Load Validation | Brad Meseck | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 15.5h | 100%
Error and Defect Mitigation | Brad Meseck | 1 | 0.5h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Brad Meseck | 1 | 0.5h | 100%
Extract File | Data Migration Team | 1 | 1h | 100%
Pre Load Validation | Brad Meseck | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 0.25h | 100%
Error and Defect Mitigation | Brad Meseck | 1 | 0.5h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Brad Meseck | 1 | 2h | 100%
Extract File | Data Migration Team | 1 | 1h | 100%
Pre Load Validation | Brad Meseck | 1 | 2h | 100%
Simulate Load | Data Migration Team | 1 | 2h | 100%
Error and Defect Mitigation | Brad Meseck | 1 | 3h | 100%
Load | Data Migration Team | 1 | 1h | 100%
Post Load Validation | Brad Meseck | 1 | 2h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 1 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Brad Meseck | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 1 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Brad Meseck | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 1 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Brad Meseck | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 1 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Brad Meseck | 1 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 1 | 2h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 1 | 2h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 1 | 2h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 1 | 2h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 1 | 2h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 1 | 2h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 1 | 2h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 1 | 2h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 1 | 12.75h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 1 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 24.75h | 100%
Error and Defect Mitigation | Eric Heisler | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 1 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Eric Heisler | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Manual File Staged and Posted "Ready" | Eric Heisler | 1 | 0.5h | 100%
Load | Eric Heisler | 1 | 2h | 100%
Post Load Validation | Eric Heisler | 1 | 3h | 100%
Manual File Staged and Posted "Ready" | Ric Haraida | 1 | 0.5h | 100%
Load | Ric Haraida | 1 | 2h | 100%
Post Load Validation | Ric Haraida | 1 | 3h | 100%
Post Load Validation | Kim Kolesar | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 1 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 0h | 100%
Error and Defect Mitigation | Ric Haraida | 1 | 0h | 100%
Load | Data Migration Team | 1 | 0h | 100%
Post Load Validation | Ric Haraida | 1 | 3h | 100%
Manual File Staged and Posted "Ready" | Nevin Varkey | 1 | 0.5h | 100%
Load | Nevin Varkey | 1 | 2h | 100%
Post Load Validation | Nevin Varkey | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 1 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 1 | 0.5h | 100%
Pre Load Validation | Femi Oguntala | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 31h | 100%
Error and Defect Mitigation | Kasey Hughes | 1 | 16h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Kasey Hughes | 1 | 3h | 100%
Manual File Staged and Posted "Ready" | Sam | 1 | 0.5h | 100%
Load | Brad Meseck | 1 | 0.5h | 100%
Post Load Validation | Brad | 1 | 16h | 100%
Load File Staged and Posted "Ready" | Sam | 1 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Brad Meseck | 1 | 3h | 100%
Run material interface to GTS | James Van Riper | 1 | 15.75h | 100%
Post Load Validation | James Van Riper | 1 | 1h | 100%
Run material interface to GTS | James Van Riper | 1 | 1h | 100%
Post Load Validation | James Van Riper | 1 | 1h | 100%
Run material interface to GTS | James Van Riper | 1 | 1h | 100%
Post Load Validation | James Van Riper | 1 | 1h | 100%
Load Descartes XML File | James Van Riper | 1 | 1h | 100%
Post Load Validation | James Van Riper | 1 | 1h | 100%
Load Descartes XML File | James Van Riper | 1 | 1h | 100%
Post Load Validation | James Van Riper | 1 | 1h | 100%
Load Descartes XML File | James Van Riper | 1 | 1h | 100%
Post Load Validation | James Van Riper | 1 | 1h | 100%
Load Descartes XML File | James Van Riper | 1 | 1h | 100%
Post Load Validation | James Van Riper | 1 | 1h | 100%
Load Descartes XML File | James Van Riper | 1 | 1h | 100%
Post Load Validation | James Van Riper | 1 | 1h | 100%
Load | James Van Riper | 1 | 21.25h | 100%
Post Load Validation | James Van Riper | 1 | 1h | 100%
Load | James Van Riper | 1 | 1h | 100%
Post Load Validation | James Van Riper | 1 | 1h | 100%
Run report /SAPSLL/EMB_CNTRY_INIT | James Van Riper | 1 | 1h | 100%
Set Embargo situations | James Van Riper | 1 | 1h | 100%
Post Load Validation | James Van Riper | 1 | 1h | 100%
Load Descartes XML File | James Van Riper | 1 | 1h | 100%
Post Load Validation | James Van Riper | 1 | 1h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 1 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Kasey Hughes | 1 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 1 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 1 | 0.5h | 100%
Simulate Load | Data Migration Team | 1 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 1 | 2h | 100%
Load | Data Migration Team | 1 | 2h | 100%
Post Load Validation | Kasey Hughes | 1 | 3h | 100%
ITC1 Mock Data Loads Complete | Mark George | 1 | 0.25h | 100%
PMO Authorization to Start Data Loads | Mark George | 0 | 2h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Load | Kasey Hughes | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Load | Kasey Hughes | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 6h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Extend GL to all Company Codes | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Open Client | Basis | 0 | 0.5h | 100%
Service Enterprise Setup | Keith Riley | 0 | 40h | 100%
Close Client | Basis | 0 | 0.5h | 100%
Intercompany Business Partner Setup | Functional Leads | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 5h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
RTR_CM14_Cost Element_Group | Kasey Hughes | 0 | 11h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Load | Kasey Hughes | 0 | 8h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Open client for BP number range update | Basis | 0 | 0.5h | 100%
Update number range BP02 from Internal to External | Ric Haraida | 0 | 0.5h | 100%
Close Client | Basis | 0 | 0.25h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 4h | 100%
Load | Data Migration Team | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 3h | 100%
Load | Data Migration Team | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Open client for BP number range update | Basis | 0 | 0.25h | 100%
Update number range BP02 from Internal to External | Ric Haraida | 0 | 0.25h | 100%
Close Client | Basis | 0 | 0.25h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 11.25h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Manual File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Load | Ric Haraida | 0 | 2h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 2.25h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Extract File(Will Extract from LFA1) | Nevin Varkey | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load/ Not Needed | Nevin Varkey | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Nevin Varkkey | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Load | Kasey Hughes | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Pre Load Validation | Ric Haraida | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 4h | 100%
Load | Data Migration Team | 0 | 3h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Eric Heisler | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 15.5h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 0.5h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Brad Meseck | 0 | 0.5h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Brad Meseck | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 0.25h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 0.5h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Brad Meseck | 0 | 2h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Brad Meseck | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 2h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 3h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Brad Meseck | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 12.75h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 8h | 100%
Error and Defect Mitigation | Eric Heisler | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Eric Heisler | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Load | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Load | Ric Haraida | 0 | 2h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Post Load Validation | Kim Kolesar | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 0h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 0h | 100%
Load | Data Migration Team | 0 | 0h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load | Nevin Varkey | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Femi Oguntala | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 8h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 16h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Sam | 0 | 0.5h | 100%
Load | Brad Meseck | 0 | 0.5h | 100%
Post Load Validation | Brad | 0 | 16h | 100%
Load File Staged and Posted "Ready" | Sam | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Run material interface to GTS | James Van Riper | 0 | 15.75h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Run material interface to GTS | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Run material interface to GTS | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load | James Van Riper | 0 | 21.25h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Run report /SAPSLL/EMB_CNTRY_INIT | James Van Riper | 0 | 1h | 100%
Set Embargo situations | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
ITC2 Mock Data Loads Complete | Mark George | 0 | 0h | 100%
PMO Authorization to Start Data Loads | Mark George | 0 | 2h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Load | Kasey Hughes | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Load | Kasey Hughes | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 6h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Extend GL to all Company Codes | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Open Client | Basis | 0 | 0.5h | 100%
Service Enterprise Setup | Keith Riley | 0 | 40h | 100%
Close Client | Basis | 0 | 0.5h | 100%
Intercompany Business Partner Setup | Functional Leads | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 5h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
RTR_CM14_Cost Element_Group | Kasey Hughes | 0 | 11h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Load | Kasey Hughes | 0 | 8h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Open client for BP number range update | Basis | 0 | 0.5h | 100%
Update number range BP02 from Internal to External | Ric Haraida | 0 | 0.5h | 100%
Close Client | Basis | 0 | 0.25h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 4h | 100%
Load | Data Migration Team | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 3h | 100%
Load | Data Migration Team | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Open client for BP number range update | Basis | 0 | 0.25h | 100%
Update number range BP02 from Internal to External | Ric Haraida | 0 | 0.25h | 100%
Close Client | Basis | 0 | 0.25h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 11.25h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Manual File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Load | Ric Haraida | 0 | 2h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 2.25h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Extract File(Will Extract from LFA1) | Nevin Varkey | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load/ Not Needed | Nevin Varkey | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Nevin Varkkey | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Load | Kasey Hughes | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Pre Load Validation | Ric Haraida | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 4h | 100%
Load | Data Migration Team | 0 | 3h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Eric Heisler | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 15.5h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 0.5h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Brad Meseck | 0 | 0.5h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Brad Meseck | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 0.25h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 0.5h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Brad Meseck | 0 | 2h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Brad Meseck | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 2h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 3h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Brad Meseck | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 12.75h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 8h | 100%
Error and Defect Mitigation | Eric Heisler | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Eric Heisler | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Load | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Load | Ric Haraida | 0 | 2h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Post Load Validation | Kim Kolesar | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 0h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 0h | 100%
Load | Data Migration Team | 0 | 0h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load | Nevin Varkey | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Femi Oguntala | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 8h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 16h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Sam | 0 | 0.5h | 100%
Load | Brad Meseck | 0 | 0.5h | 100%
Post Load Validation | Brad | 0 | 16h | 100%
Load File Staged and Posted "Ready" | Sam | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Run material interface to GTS | James Van Riper | 0 | 15.75h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Run material interface to GTS | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Run material interface to GTS | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load | James Van Riper | 0 | 21.25h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Run report /SAPSLL/EMB_CNTRY_INIT | James Van Riper | 0 | 1h | 100%
Set Embargo situations | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
ITC3 Mock Data Loads Complete | Mark George | 0 | 0h | 100%
PMO Authorization to Start Data Loads | Mark George | 0 | 0.02h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Load | Kasey Hughes | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Load | Kasey Hughes | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 6h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Extend GL to all Company Codes | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Open Client | Basis | 0 | 0.5h | 100%
Service Enterprise Setup | Keith Riley | 0 | 40h | 100%
Close Client | Basis | 0 | 0.5h | 100%
Intercompany Business Partner Setup | Functional Leads | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 5h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
RTR_CM14_Cost Element_Group | Kasey Hughes | 0 | 0h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Load | Kasey Hughes | 0 | 32h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Open client for BP number range update | Basis | 0 | 0.5h | 100%
Update number range BP02 from Internal to External | Ric Haraida | 0 | 0.5h | 100%
Close Client | Basis | 0 | 0.25h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 4h | 100%
Load | Data Migration Team | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 3h | 100%
Load | Data Migration Team | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Open client for BP number range update | Basis | 0 | 0.25h | 100%
Update number range BP02 from Internal to External | Ric Haraida | 0 | 0.25h | 100%
Close Client | Basis | 0 | 0.25h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 11.25h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Manual File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Load | Ric Haraida | 0 | 2h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 2.25h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Extract File(Will Extract from LFA1) | Nevin Varkey | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load/ Not Needed | Nevin Varkey | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Nevin Varkkey | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Load | Kasey Hughes | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Pre Load Validation | Ric Haraida | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 4h | 100%
Load | Data Migration Team | 0 | 3h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Eric Heisler | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 15.5h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 0.5h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Brad Meseck | 0 | 0.5h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Brad Meseck | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 0.25h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 0.5h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Brad Meseck | 0 | 2h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Brad Meseck | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 2h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 3h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Brad Meseck | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 12.75h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 24.75h | 100%
Error and Defect Mitigation | Eric Heisler | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Eric Heisler | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Load | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Load | Ric Haraida | 0 | 2h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Post Load Validation | Kim Kolesar | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 0h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 0h | 100%
Load | Data Migration Team | 0 | 0h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load | Nevin Varkey | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Femi Oguntala | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 31h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 16h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Sam | 0 | 0.5h | 100%
Load | Brad Meseck | 0 | 0.5h | 100%
Post Load Validation | Brad | 0 | 16h | 100%
Load File Staged and Posted "Ready" | Sam | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Run material interface to GTS | James Van Riper | 0 | 15.75h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Run material interface to GTS | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Run material interface to GTS | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load | James Van Riper | 0 | 21.25h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Run report /SAPSLL/EMB_CNTRY_INIT | James Van Riper | 0 | 1h | 100%
Set Embargo situations | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
UAT Mock Data Loads Complete | Mark George | 0 | 0.25h | 100%
UAT Mock Data Loads Complete | Mark George | 0 | 0.25h | 100%
PMO Authorization to Start Data Loads | Mark George | 0 | 0.02h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Load | Kasey Hughes | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Load | Kasey Hughes | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 6h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Extend GL to all Company Codes | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Open Client | Basis | 0 | 0.5h | 100%
Service Enterprise Setup | Keith Riley | 0 | 40h | 100%
Close Client | Basis | 0 | 0.5h | 100%
Intercompany Business Partner Setup | Functional Leads | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 5h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 1h | 100%
Pre Load Validation | Kasey Hughes | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Kasey Hughes | 0 | 2h | 100%
RTR_CM14_Cost Element_Group | Kasey Hughes | 0 | 0h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Load | Kasey Hughes | 0 | 32h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Open client for BP number range update | Basis | 0 | 0.5h | 100%
Update number range BP02 from Internal to External | Ric Haraida | 0 | 0.5h | 100%
Close Client | Basis | 0 | 0.25h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 4h | 100%
Load | Data Migration Team | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 3h | 100%
Load | Data Migration Team | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Open client for BP number range update | Basis | 0 | 0.25h | 100%
Update number range BP02 from Internal to External | Ric Haraida | 0 | 0.25h | 100%
Close Client | Basis | 0 | 0.25h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 11.25h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Manual File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Load | Ric Haraida | 0 | 2h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 2.25h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Extract File(Will Extract from LFA1) | Nevin Varkey | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load/ Not Needed | Nevin Varkey | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Nevin Varkkey | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Manual File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Load | Kasey Hughes | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Pre Load Validation | Ric Haraida | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 4h | 100%
Load | Data Migration Team | 0 | 3h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Eric Heisler | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Nevin Varkey | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Nevin Varkey | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Pre Load Validation | Nevin Varkey | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Nevin Varkey | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 15.5h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 0.5h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Brad Meseck | 0 | 0.5h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Brad Meseck | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 0.25h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 0.5h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Brad Meseck | 0 | 2h | 100%
Extract File | Data Migration Team | 0 | 1h | 100%
Pre Load Validation | Brad Meseck | 0 | 2h | 100%
Simulate Load | Data Migration Team | 0 | 2h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 3h | 100%
Load | Data Migration Team | 0 | 1h | 100%
Post Load Validation | Brad Meseck | 0 | 2h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Brad Meseck | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Run ALE Transaction to QS5 from DS4 130 | Eric Heisler | 0 | 12.75h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 24.75h | 100%
Error and Defect Mitigation | Eric Heisler | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Pre Load Validation | Eric Heisler | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Eric Heisler | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Eric Heisler | 0 | 0.5h | 100%
Load | Eric Heisler | 0 | 2h | 100%
Post Load Validation | Eric Heisler | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Load | Ric Haraida | 0 | 2h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Post Load Validation | Kim Kolesar | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Ric Haraida | 0 | 0.5h | 100%
Pre Load Validation | Ric Haraida | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 0h | 100%
Error and Defect Mitigation | Ric Haraida | 0 | 0h | 100%
Load | Data Migration Team | 0 | 0h | 100%
Post Load Validation | Ric Haraida | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Nevin Varkey | 0 | 0.5h | 100%
Load | Nevin Varkey | 0 | 2h | 100%
Post Load Validation | Nevin Varkey | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Femi Oguntala | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 31h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 16h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Manual File Staged and Posted "Ready" | Sam | 0 | 0.5h | 100%
Load | Brad Meseck | 0 | 0.5h | 100%
Post Load Validation | Brad | 0 | 16h | 100%
Load File Staged and Posted "Ready" | Sam | 0 | 0.5h | 100%
Pre Load Validation | Brad Meseck | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Brad Meseck | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Brad Meseck | 0 | 3h | 100%
Run material interface to GTS | James Van Riper | 0 | 15.75h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Run material interface to GTS | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Run material interface to GTS | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load | James Van Riper | 0 | 21.25h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Run report /SAPSLL/EMB_CNTRY_INIT | James Van Riper | 0 | 1h | 100%
Set Embargo situations | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load Descartes XML File | James Van Riper | 0 | 1h | 100%
Post Load Validation | James Van Riper | 0 | 1h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
Load File Staged and Posted "Ready" | Kasey Hughes | 0 | 0.5h | 100%
Pre Load Validation | Kasey Hughes | 0 | 0.5h | 100%
Simulate Load | Data Migration Team | 0 | 1h | 100%
Error and Defect Mitigation | Kasey Hughes | 0 | 2h | 100%
Load | Data Migration Team | 0 | 2h | 100%
Post Load Validation | Kasey Hughes | 0 | 3h | 100%
UAT Mock Data Loads Complete | Mark George | 0 | 0.25h | 100%
PRO Data Loads Complete | Mark George | 0 | 0.25h | 100%
Testing expectations | PMO | 1 | 1h | 100%
Assign Resources to Depolyment 1 locations | Renee | 0 | 2h | 100%
Assign Tester ID's | Security | 0 | 2h | 100%
Functional Smoke Testing | Functional Leads | 0 | 40h | 100%
Test Kickoff | Renee | 0 | 1h | 100%
Assign Resources to Depolyment 1 locations | Renee | 0 | 2h | 100%
Assign Tester ID's | Security | 0 | 2h | 100%
Functional Smoke Testing | Functional Leads | 0 | 40h | 100%
Test Kickoff | Renee | 0 | 1h | 100%
Assign Resources to Depolyment 1 locations | Renee | 0 | 2h | 100%
Assign Tester ID's | Security | 0 | 2h | 100%
Functional Smoke Testing | Functional Leads | 0 | 40h | 100%
Test Kickoff | Renee | 0 | 1h | 100%
Verify Role Mapping Complete | Training | 0.46000000000000002 | 528h | 100%
Develop Curriculum | Training | 0.29999999999999999 | 528h | 100%
Develop Course ppts | Training | 0.34999999999999998 | 688h | 100%
Develop Work Instructions | Training | 0.20999999999999999 | 688h | 100%
Develop Training Data Sheets (Testing/Training) | Training | 0 | 568h | 100%
Develop Train the Trainer | Training | 1 | 960h | 100%
Publish Training Materials to SP/LMS | Training | 0 | 48h | 100%
Deliver Train the Trainer (BPL->SME) | Training | 0 | 160h | 100%
User Training Plan and Schedule | Training | 0 | 136h | 100%
Deliver End User Training | Training | 0 | 280h | 100%