I've cleaned up the ITC_Details sheet by removing the legend and RAID summary. Here's the updated layout:

## ✅ ITC_Details — Cleaned Up

### Current Structure

| Section | Rows | Content |
| --- | --- | --- |
| Header | 1 | "DAILY STATUS REPORT — MILESTONE TRACKER" + Date |
| Overall Project Status | 3-5 | 8 KPI values with labels below (all formula-driven) |
| ▼ ITC1 | 7-15 | Summary tile + 6 feeders table + Testing/Defects row |
| ▼ ITC2 | 17-25 | Summary tile + 6 feeders table + Testing/Defects row |
| ▶ ITC3 (FUTURE) | 27-28 | Compact summary + feeders on one line |
| Footer | 30 | Last Refreshed date |

### Removed

- Legend row (was row 6)

- RAID Summary table (was rows 31-37)

- Note about workstreams (was row 38)

## 📋 Canvas/Page for New Session

Here's a complete summary you can paste into a new session to recreate this framework:

### PMO DASHBOARD FRAMEWORK — CANVAS

#### 1. Workbook Structure

| Sheet | Purpose |
| --- | --- |
| Metrics | Source data — tbl_Metrics (Domain, Metric, Value) + tbl_AnalyticsCatalogue |
| PMO_Report | Summary view with ITC milestones, RAID, Long-Lead Items |
| PMO_Meeting_Review | Raw numbers for Project Plan, Testing, Defects, RAID |
| ITC_Details | Daily Status Report — Milestone Tracker with feeders |
| QA_Details | (Empty — reserved for QA) |

#### 2. ITC_Details Layout

1 Row 1: DAILY STATUS REPORT — MILESTONE TRACKER [Date: =TODAY()] 2 3 Row 3: OVERALL PROJECT STATUS 4 Row 4: [22.5%] [2219] [489] [3] [1] [13] [37] [82.8] 5 Row 5: Progress Tasks Complete On Sched Late Past Due Miles. Avg Slip 6 (All formula-driven from Metrics! sheet) 7 8 Row 7: ▼ ITC1 │ Progress: 85% │ Target: 30-May-26 │ Tasks: 23/27 │ Tests: 150 │ Defects: 8 │ RAID: 14R 23I 12D 9 Row 8: [Header] Feeder ¦ Status ¦ % Done ¦ Open ¦ Blocked ¦ Notes ¦ Workstreams 10 Row 9: ├─ System Readiness ¦ ● Complete ¦ 100% ¦ 0 ¦ 0 ¦ QA Refresh complete ¦ 11 Row 10: ├─ Security ¦ ● Complete ¦ 100% ¦ 0 ¦ 0 ¦ Security validated ¦ 12 Row 11: ├─ Data Migration ¦ ● Complete ¦ 100% ¦ 0 ¦ 0 ¦ Data load & master data complete ¦ 13 Row 12: ├─ Testing ¦ ◐ In Progress ¦ 45% ¦ 8 ¦ 2 ¦ Test execution active ¦ PTM(3) ● FIN(2) ● IT(1) 14 Row 13: ├─ Training ┈┈┈┈► ITC1 ¦ ◐ In Progress ¦ 60% ¦ 3 ¦ 0 ¦ Materials development ¦ HR(2) ● OPS(1) 15 Row 14: └─ RICEFW ¦ ● Complete ¦ 100% ¦ 0 ¦ 0 ¦ Custom dev complete ¦ 16 Row 15: Testing/Defects: ¦ 0 Tests ¦ 0 Pass ¦ 0 Fail ¦ 0 Defects ¦ 0 Critical 17 18 Row 17: ▼ ITC2 │ Progress: 0% │ Target: 15-Jun-26 │ Tasks: 0/36 │ Tests: 0 │ Defects: 0 │ RAID: 5R 4I 2D 19 Row 18: [Header] Feeder ¦ Status ¦ % Done ¦ Open ¦ Blocked ¦ Notes ¦ Workstreams 20 Row 19: ├─ System Readiness ¦ ○ Not Started ¦ 0% ¦ 0 ¦ 0 ¦ ⚠ QA Refresh pending ¦ 21 Row 20: ├─ Security ¦ ○ Not Started ¦ 0% ¦ 0 ¦ 0 ¦ ⚠ Blocked - long lead ¦ SEC(5) 22 Row 21: ├─ Data Migration ¦ ○ Not Started ¦ 0% ¦ 0 ¦ 0 ¦ ⚠ Awaiting ITC1 completion ¦ DM(8) ● MDM(3) 23 Row 22: ├─ Testing ¦ ○ Not Started ¦ 0% ¦ 0 ¦ 0 ¦ Pending all feeders ¦ 24 Row 23: ├─ Training ┈┈┈┈► ITC2 ¦ ○ Not Started ¦ 0% ¦ 0 ¦ 0 ¦ ⚠ Long-lead - plan early ¦ HR(4) ● OPS(2) 25 Row 24: └─ RICEFW ¦ ○ Not Started ¦ 0% ¦ 0 ¦ 0 ¦ Pending ITC1 learnings ¦ DEV(2) 26 Row 25: Testing/Defects: ¦ 0 Tests ¦ 0 Pass ¦ 0 Fail ¦ 0 Defects ¦ 0 Critical 27 28 Row 27: ▶ ITC3 (FUTURE) │ Progress: 0% │ Target: TBD │ Tasks: 0/0 │ Tests: 0 │ Defects: 0 │ RAID: 0R 0I 0D 29 Row 28: ○ Sys Ready │ ○ Security │ ○ Data Migration │ ○ Testing │ ○ Training ┈┈► ITC3 │ ○ RICEFW 30 31 Row 30: Last Refreshed: [=TODAY()]

#### 3. Feeders (6 per ITC)

| Order | Feeder | Description |
| --- | --- | --- |
| 1 | System Readiness | QA Refresh |
| 2 | Security | Security validation |
| 3 | Data Migration | Data + Master Data combined |
| 4 | Testing | Test execution |
| 5 | Training | Training materials & delivery (long-lead) |
| 6 | RICEFW | Custom development |

#### 4. Status Indicators

| Symbol | Meaning | Color |
| --- | --- | --- |
| ● | Complete | Green (#00B050) |
| ◐ | In Progress | Blue (#4F81BD) |
| ○ | Not Started | Gray (#888888) |
| ⚠ | At Risk / Warning | Amber (#FFC000) |
| ┈┈► | Dependency arrow | Gray dotted |

#### 5. Workstreams Column Format

Shows open tasks by workstream abbreviation:

1 PTM(3) ● FIN(2) ● IT(1)

- Bold abbreviation + count in parentheses

- Black bullet ● separates workstreams

#### 6. Key Formulas (from Metrics! sheet)

| Metric | Formula |
| --- | --- |
| Progress | =SUMIFS(Metrics!C:C,Metrics!A:A,"Project Plan",Metrics!B:B,"Avg % Complete")&"%" |
| Tasks | =SUMIFS(Metrics!C:C,Metrics!A:A,"Project Plan",Metrics!B:B,"Total Tasks") |
| Complete | =SUMIFS(Metrics!C:C,Metrics!A:A,"Project Plan",Metrics!B:B,"Complete") |
| On Sched | =SUMIFS(Metrics!C:C,Metrics!A:A,"Project Plan",Metrics!B:B,"On Schedule") |
| Late | =SUMIFS(Metrics!C:C,Metrics!A:A,"Project Plan",Metrics!B:B,"Late") |
| Past Due | =SUMIFS(Metrics!C:C,Metrics!A:A,"Project Plan",Metrics!B:B,"Past Due") |
| Milestones | =SUMIFS(Metrics!C:C,Metrics!A:A,"Project Plan",Metrics!B:B,"Milestones") |
| Avg Slip | =SUMIFS(Metrics!C:C,Metrics!A:A,"Project Plan",Metrics!B:B,"Avg Schedule Slip (Days)") |
| Open Risks | =SUMIFS(Metrics!C:C,Metrics!A:A,"Risks",Metrics!B:B,"Open") |
| Open Issues | =SUMIFS(Metrics!C:C,Metrics!A:A,"Issues",Metrics!B:B,"Open / Escalated") |
| Open Decisions | =SUMIFS(Metrics!C:C,Metrics!A:A,"Decisions",Metrics!B:B,"Open") |
| Overdue Actions | =SUMIFS(Metrics!C:C,Metrics!A:A,"Actions",Metrics!B:B,"Overdue") |
| Tests | =SUMIFS(Metrics!C:C,Metrics!A:A,"Testing",Metrics!B:B,"Total Tests") |
| Defects | =SUMIFS(Metrics!C:C,Metrics!A:A,"Defects",Metrics!B:B,"Open") |

#### 7. Design Specs

| Element | Spec |
| --- | --- |
| Colors | AMETEK Navy (#003366), Steel Blue (#4F81BD), Gray (#58595B), Amber (#FFC000) |
| Fonts | Values: 16pt bold navy, Labels: 8pt gray |
| Borders | Thin gray (#D0D0D0), subtle |
| Gridlines | Hidden |
| In-progress shading | Light amber (#FFF8E1) |

#### 8. What's Still Placeholder (Needs Data Linkage)

| Item | Status | What's Needed |
| --- | --- | --- |
| Feeder % Done | Hard-coded | Workstream/Phase field in Project Plan |
| Feeder Open/Blocked counts | Hard-coded | Task filtering by feeder type |
| Workstreams column | Hard-coded | Task counts by workstream abbreviation |
| Testing/Defects | Shows 0 | Real data source connection |
| ITC-specific RAID | Hard-coded | Workstream field in RAID sources |

Copy this canvas to your new session and I'll help you wire up the live data connections once your updated file is ready!