## metrics_summary
metric | value
Plan rows | 2219
Plan open tasks | 1735
Plan complete % | 21.68
Late vs baseline | 1606
Critical tasks | 1658
Milestones | 37
Due next 14 days | 264
Workstreams represented | 1
Run generated at | 2026-05-08T07:34:52

## change_summary
source | entity_type | source_path | row_count | added | removed | changed | unchanged | sample_added | sample_removed | sample_changed
project_plan | project_plan | C:\Users\jsw73\OneDrive\Ametek Project Plan Risks\imports\staging\AMETEK SAP XXL Project Plan Replan MSP Task.csv | 2219 | 2219 | 0 | 0 | 0 | 1, 100, 1000, 1001, 1002

## source_profile
entity_type | canonical_column | source_column | status
project_plan | record_id | Unique ID | mapped
project_plan | task_id |  | missing
project_plan | task_name | Task Name | mapped
project_plan | workstream |  | missing
project_plan | owner | Resource Names | mapped
project_plan | start_date | Start | mapped
project_plan | finish_date | Finish | mapped
project_plan | baseline_finish | Baseline Finish | mapped
project_plan | percent_complete | % Complete | mapped
project_plan | status | Status | mapped
project_plan | predecessor_ids | Unique ID Predecessors | mapped
project_plan | critical_flag | Critical | mapped
project_plan | milestone_flag | Milestone | mapped
project_plan | __source_path__ | C:\Users\jsw73\OneDrive\Ametek Project Plan Risks\imports\staging\AMETEK SAP XXL Project Plan Replan MSP Task.csv | loaded
project_plan | __warning__ | Source 'project_plan' missing useful data for: task_id, workstream | warning

## relationship_links
info
No data available

## relationship_rollup
workstream | project_plan | testing | defects | raid | has_all_sources
(Unassigned) | 2219 | 0 | 0 | 0 | FALSE

## raw_project_plan
entity_type | source_name | source_row_number | record_id | task_id | task_name | workstream | owner | start_date | finish_date | baseline_finish | percent_complete | status | predecessor_ids | critical_flag | milestone_flag | record_key | row_hash
project_plan | project_plan | 2 | 1 |  | AMETEK Release-1, 3-Deployment Plan |  |  | Mon 2/17/25 | Mon 11/9/26 | Fri 10/16/26 | 50% | On Schedule |  | Yes | No | 1 | 32a49d72fe1fc18567d26304c2e6c51c4d09226f70f36cc77248d3ba998bde03
project_plan | project_plan | 3 | 2 |  | System Readiness |  |  | Mon 2/17/25 | Thu 10/22/26 | Thu 7/16/26 | 82% | Late |  | No | No | 2 | b15c7b57c53dd28fe05b2f4546011fa458ebe7dfa86f31bfb3eeb8052cd7d7e7
project_plan | project_plan | 4 | 5 |  | Environment Schedule |  |  | Thu 3/13/25 | Tue 9/29/26 | Thu 7/16/26 | 21% | Late |  | No | No | 5 | caff958e2d10c169c5f7f94810f93d88b542267a626033ebe13b0c2321ca7ad3
project_plan | project_plan | 5 | 85 |  | DS4-100 Config / Development Client |  |  | Wed 5/7/25 | Wed 5/7/25 | Wed 5/7/25 | 100% | Complete |  | No | No | 85 | 18d82058206235a77a119a8950fb16f06e17515dad4ba93d77f63537d7f3208b
project_plan | project_plan | 6 | 100 |  | Copy DS4-100 to DS4-110 Dev |  |  | Wed 5/7/25 | Wed 5/7/25 | Wed 5/7/25 | 100% | Complete |  | No | No | 100 | 21d3ba86982747ee2e159fc6e2825579682554be970e828af6f5ea2f4bd4c62e
project_plan | project_plan | 7 | 86 |  | DS4-110 Unit Test Client |  |  | Thu 5/8/25 | Thu 5/8/25 | Thu 5/8/25 | 100% | Complete |  | No | No | 86 | 0cbea90d6a845226b6ad6ef634411fc5d2bdaf8cd3a8c09e6041f8541f64246c
project_plan | project_plan | 8 | 106 |  | List of functional users |  |  | Thu 5/8/25 | Thu 5/8/25 | Thu 5/8/25 | 100% | Complete | 100 | No | No | 106 | 3cf586af3f9ee641cb29b0135c49b1b7f716ce4a26cca3542479875261408845
project_plan | project_plan | 9 | 101 |  | Security Role for Functional Team |  |  | Thu 5/8/25 | Thu 5/8/25 | Thu 5/8/25 | 100% | Complete | 106 | No | No | 101 | 09ba502fe5257505b7b3e65fed479bec298072ae566148c477d452c661cb76c3
project_plan | project_plan | 10 | 87 |  | DS4-120 Data Dev Client |  |  | Thu 5/8/25 | Thu 5/8/25 | Thu 5/8/25 | 100% | Complete |  | No | No | 87 | 90d390cc49dedc1c115fdd78bf73b87eedd582f6abddc285ca739d6c1f0feed2
project_plan | project_plan | 11 | 107 |  | List of functional users |  |  | Thu 5/8/25 | Thu 5/8/25 | Thu 5/8/25 | 100% | Complete | 100 | No | No | 107 | eed04865e71a4c3f6503a18b0ee12db69281734e0a6747296d790ce93bd7a58d
project_plan | project_plan | 12 | 104 |  | Security Role for Data Team |  |  | Thu 5/8/25 | Thu 5/8/25 | Thu 5/8/25 | 100% | Complete | 107 | No | No | 104 | 2dc94f8cf26aa33e7def276a625c59acd2c519faf4913cdfe182726fb886aa06
project_plan | project_plan | 13 | 88 |  | QS5 ITC-1 Refresh |  |  | Thu 3/13/25 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete |  | No | No | 88 | 5abf7818366dd4b8e28e8dc438dc90470ac720be8339c4a969135c7486cd62ae
project_plan | project_plan | 14 | 830 |  | Change Request to NS2 |  | Basis | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 830 | 102bd14b7b8ec944b46ccb0e9638b84a97d18392e36d02a165f2e341a212d17b
project_plan | project_plan | 15 | 669 |  | Dev Environment Release from SAP |  | NS2 | Thu 1/8/26 | Thu 1/8/26 | Thu 1/8/26 | 100% | Complete |  | No | Yes | 669 | fdea147a484265324c5ef4c97fb3f895f447c5c6128555dd1d2c513257755bf6
project_plan | project_plan | 16 | 670 |  | Release Setup ID's and Access |  | Security | Thu 1/8/26 | Thu 1/8/26 | Thu 1/8/26 | 100% | Complete | 669 | No | No | 670 | 439e3d2a875d7395bd8bc42af0dbc377a8bd30dbf473dfda6b4a67c44e6b38f8
project_plan | project_plan | 17 | 654 |  | Client Config / Validation |  | Basis | Mon 2/2/26 | Mon 2/2/26 | Mon 2/2/26 | 100% | Complete | 670 | No | No | 654 | 935f12707ac48ec5f7f022647215c71cdf9cd43ae90ddd0fb8ea845129b372e8
project_plan | project_plan | 18 | 640 |  | Technical Transports / BP Setup |  | Basis | Wed 2/4/26 | Wed 2/4/26 | Wed 2/4/26 | 100% | Complete |  | No | No | 640 | b7196e85732bd89580afc30c66240dc9d50b8eed859a22b9e6e622dc7eb437c0
project_plan | project_plan | 19 | 655 |  | Best Practice / Country Validation |  | Basis | Tue 2/3/26 | Tue 2/3/26 | Tue 2/3/26 | 100% | Complete | 654 | No | No | 655 | 5f0e64d6a6ee4a55314da06ac8eb450d13caf48e62f992607d36008f04aa3aaf
project_plan | project_plan | 20 | 641 |  | Connect Systems and Validate |  | Basis | Thu 2/5/26 | Thu 2/5/26 | Thu 2/5/26 | 100% | Complete | 640 | No | No | 641 | 868d0ac4648fe3d329480b6ccc0a4d12c7d88b7770f30addd7665be47796339e
project_plan | project_plan | 21 | 674 |  | Validate Syniti Connections to QS5 |  | Data | Thu 2/5/26 | Thu 2/5/26 | Thu 2/5/26 | 100% | Complete | 640 | No | No | 674 | 6ab32c941925e0583db8b8e21ca1271e30982592fdad4c43a3d5ac42f30405f5
project_plan | project_plan | 22 | 642 |  | Security Transports |  | Security | Thu 2/5/26 | Thu 2/5/26 | Thu 2/5/26 | 100% | Complete | 640 | No | No | 642 | b380d41c13dc2c85ea471c511e982006b78fcc69584ffcc7c48b5949f59ccd49
project_plan | project_plan | 23 | 671 |  | Security Manual Tasks |  | Security | Thu 2/5/26 | Fri 2/6/26 | Fri 2/6/26 | 100% | Complete | 642 | No | No | 671 | 09c9e02afff0061d87c536f2f66c1c28b782c39225c03d8652a078f0195f5134
project_plan | project_plan | 24 | 643 |  | Manual Technical Tasks |  | Basis | Thu 2/5/26 | Fri 2/6/26 | Fri 2/6/26 | 100% | Complete | 642 | No | No | 643 | 31dce6396cca8240b56a9432538834600c5aeb5d63c9289803517e18b511b2e9
project_plan | project_plan | 25 | 644 |  | Validate Fiori |  | Basis | Fri 2/6/26 | Fri 2/6/26 | Fri 2/6/26 | 100% | Complete | 643 | No | No | 644 | b7e11baceea3b9505b28bf972856cfd84c273e57a4d485028042e7a4abc2c0c8
project_plan | project_plan | 26 | 672 |  | Fiori App Activation |  | Dev Team | Mon 2/9/26 | Mon 2/9/26 | Mon 2/9/26 | 100% | Complete | 644 | No | No | 672 | ba1f5a61a07571c3c9a2c2a44440735ae07a9e7b0ed9a922c0d05dfd50f70052
project_plan | project_plan | 27 | 645 |  | Download Transport List |  | Basis | Mon 2/9/26 | Mon 2/9/26 | Mon 2/9/26 | 100% | Complete | 644 | No | No | 645 | 8b640a0a6d67d0064299b929bb78b8bbb4f48ed84ecbbbb7802e02ee094ff408
project_plan | project_plan | 28 | 653 |  | Business Functions Validation |  | Basis | Mon 2/9/26 | Mon 2/9/26 | Mon 2/9/26 | 100% | Complete | 644 | No | No | 653 | cc8871044c28623771b566faa6f108c3e376cb06d38ec445e3f769f8b3fdd4a6
project_plan | project_plan | 29 | 646 |  | Functional Leads Validation of Transport List |  | Functional Leads | Mon 2/9/26 | Mon 2/9/26 | Mon 2/9/26 | 100% | Complete | 645 | No | No | 646 | 2a5dd81c888cea3fa7f293bf393bdbf424ea2d41c30c32318c09a22d64feee05
project_plan | project_plan | 30 | 673 |  | Release Security roles to Functional Team |  | Security | Mon 2/9/26 | Mon 2/9/26 | Mon 2/9/26 | 100% | Complete | 646 | No | No | 673 | 44b3bbcd7d4086f11e0c041aff1f2faac802626a4e99ca0569126415d09579d6
project_plan | project_plan | 31 | 647 |  | Release Transports to Client |  |  | Mon 2/9/26 | Wed 3/25/26 | Wed 3/25/26 | 100% | Complete |  | No | No | 647 | 77b53ad320b1d016a82d6564a7f09ca5c675ff014549bd256308483f5e8b9c2c
project_plan | project_plan | 32 | 657 |  | Import Group 1 - Ent Structure |  | Functional Leads | Mon 2/9/26 | Mon 2/9/26 | Mon 2/9/26 | 100% | Complete | 646 | No | No | 657 | bdc2aba63a0999e145d008098e00924a1ca05866d068f8500e9e122ed212171b
project_plan | project_plan | 33 | 658 |  | Manual activities group 1 |  | Functional Leads | Thu 3/19/26 | Mon 3/23/26 | Mon 3/23/26 | 100% | Complete | 657 | No | No | 658 | 71873b576a07800546f19ee3de6d8d025f1da02537e81aeed64cbb764af8ae8f
project_plan | project_plan | 34 | 659 |  | Import Group 2 - Core Transports |  | Functional Leads | Mon 3/23/26 | Mon 3/23/26 | Mon 3/23/26 | 100% | Complete | 658 | No | No | 659 | 7b2c8946a75459eeb7eaa807ffd9a35b9580415fa1525630351ec3b652cc398f
project_plan | project_plan | 35 | 660 |  | Manual activities group 2 |  | Functional Leads | Mon 3/23/26 | Tue 3/24/26 | Tue 3/24/26 | 100% | Complete | 659 | No | No | 660 | d29008946434c8f7efb501b4adc3ffaaf6069c9e4d73ca08f9d3f1511727367f
project_plan | project_plan | 36 | 661 |  | Import Group 3 - prior to transactions |  | Functional Leads | Tue 3/24/26 | Tue 3/24/26 | Tue 3/24/26 | 100% | Complete | 660 | No | No | 661 | 871a18d6369a87854fca58e4498a2d2c15353a9bc1c6f5e8fb4263bb46f94720
project_plan | project_plan | 37 | 831 |  | Manual Activities Group 3 |  | Functional Leads | Wed 3/25/26 | Wed 3/25/26 | Wed 3/25/26 | 100% | Complete | 661 | No | No | 831 | 4a27fd5cf967f88835828626f5f0aff4015519cbaf78276526ec41ebfc840d11
project_plan | project_plan | 38 | 662 |  | Import Group 4 - workbench / dev work |  | Dev Team | Fri 4/3/26 | Fri 4/3/26 | Fri 4/3/26 | 100% | Complete |  | No | No | 662 | 59eb96a453a71f3a1618d93972097dc324b4b7ef48f4d0988aaa5709bd0f2819
project_plan | project_plan | 39 | 663 |  | Import Group 5 - Config to support dev workbench |  | Dev Team | Fri 4/3/26 | Fri 4/3/26 | Fri 4/3/26 | 100% | Complete | 662 | No | No | 663 | 57504fa1a6e02051ba3e21fd620b5ebb9ca4d04184938ffb26c8cefd57ab5020
project_plan | project_plan | 40 | 833 |  | Create Migration Data Project in DMC |  | Data Migration Team | Fri 4/3/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 663 | No | No | 833 | 089ab24ea96cf2768ec27cc29a6c87d1c3aeee88a118f62ff7699f0ae3c8d827
project_plan | project_plan | 41 | 652 |  | Environment Ready for Build |  | PMO | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 833 | No | Yes | 652 | d9a9b08cd289fc78d4129af95bc3b5d761a66ad26811b451148fb25c28dc279b
project_plan | project_plan | 42 | 849 |  | QS4 ITC-2 Refresh |  |  | Mon 4/27/26 | Thu 5/14/26 | Thu 7/16/26 | 31% | Late |  | Yes | No | 849 | ad26651a202606afdc2dcaa08f17312b4c0f8f185c1968e70c3236288b5b6f08
project_plan | project_plan | 43 | 3340 |  | System Setup |  |  | Mon 4/27/26 | Tue 5/5/26 |  | 49% | Late | 652 | Yes | No | 3340 | d78cb108dbe2e1afd533fb6b54fd449af17461c82e525cf1ad5ff5b257248b82
project_plan | project_plan | 44 | 850 |  | Dev Refresh Basis(Workinig with NS2) |  | Basis | Mon 4/27/26 | Tue 4/28/26 | Fri 5/1/26 | 100% | Complete |  | No | No | 850 | e21204592772aa72c30e9bde6302bd19d462d83cecca812012d12ab4aa80dcea
project_plan | project_plan | 45 | 853 |  | Client Config / Validation |  | Basis | Mon 4/27/26 | Mon 4/27/26 | Mon 5/11/26 | 100% | Complete | 652 | No | No | 853 | a7cd26d852bf88b159d90e1f88380465ae4e455f2084e080fdf3e75afc859eb6
project_plan | project_plan | 46 | 854 |  | Technical Transports / BP Setup |  | Basis | Tue 4/28/26 | Tue 4/28/26 | Tue 5/12/26 | 100% | Complete | 853 | No | No | 854 | 69d03f62f49e9c568ae3c3f85428e05f6fb2492a165abf4c371909cc919e786f
project_plan | project_plan | 47 | 855 |  | Best Practice / Country Validation |  | Basis | Wed 4/29/26 | Wed 4/29/26 | Wed 5/13/26 | 100% | Complete | 854 | No | No | 855 | bb086f1436df259a85fd4781c7097e3bc7b054a76fe6a3402dabfdf07d78e210
project_plan | project_plan | 48 | 856 |  | Connect Systems and Validate |  | Basis | Thu 4/30/26 | Thu 4/30/26 | Thu 5/14/26 | 100% | Complete | 855 | No | No | 856 | a563b546937f32367300f840cd1259f8f524c8128aca51b1ddc12d9857381713
project_plan | project_plan | 49 | 857 |  | Validate Syniti Connections to QS5 |  | Data | Fri 5/1/26 | Fri 5/1/26 | Fri 5/15/26 | 0% | Late | 856 | Yes | No | 857 | 8466e07de91b0eaecfad13977534b0a535ff185cc6649a8459714804e37eea88
project_plan | project_plan | 50 | 858 |  | Security Transports |  | Security | Mon 5/4/26 | Mon 5/4/26 | Fri 5/15/26 | 0% | On Schedule | 857 | Yes | No | 858 | 47c06b8d755da0ada0e284d539c15e78c4393cee414912f4d8a07e6ceb7f63d5
project_plan | project_plan | 51 | 859 |  | Security Manual Tasks |  | Security | Mon 5/4/26 | Mon 5/4/26 | Mon 5/18/26 | 0% | On Schedule | 858SS | Yes | No | 859 | 4c7b5ed80bfdab6dd6e49d583b4dd95754b28a372a7e9e80147abcb9c66d3d21
project_plan | project_plan | 52 | 860 |  | Manual Technical Tasks |  | Basis | Mon 5/4/26 | Mon 5/4/26 | Mon 5/18/26 | 0% | On Schedule | 858SS | Yes | No | 860 | f30c9e4b96479366b8bf9db04b6983cb22052dd8abc724d526ab0bf22ee08df2
project_plan | project_plan | 53 | 861 |  | Validate Fiori |  | Basis | Tue 5/5/26 | Tue 5/5/26 | Tue 5/19/26 | 0% | Future Task | 860 | Yes | No | 861 | 4b20eb365cb525922d7352902fad24c4aa1de4747550aae6e0ffd1c72f3b864a
project_plan | project_plan | 54 | 862 |  | Fiori App Activation |  | Dev Team | Tue 5/5/26 | Tue 5/5/26 | Tue 5/19/26 | 0% | Future Task | 861SS | Yes | No | 862 | 1764431561d56706fc129020a2f99776bbcb4cd3b78bfb282201cda7d48d10fa
project_plan | project_plan | 55 | 863 |  | Download Transport List |  | Basis | Tue 5/5/26 | Tue 5/5/26 | Tue 5/19/26 | 0% | Future Task | 861 | Yes | No | 863 | f8a810e285159fe3b9d1e6ebef032e25537b28e2eaef457314c2b176b898c574
project_plan | project_plan | 56 | 864 |  | Business Functions Validation |  | Basis | Tue 5/5/26 | Tue 5/5/26 | Wed 5/20/26 | 0% | Future Task | 861SS | Yes | No | 864 | d6d6f6ff3525847787de09ec7d59cd66aee14146bb1f6f2166d46c1dd989e851
project_plan | project_plan | 57 | 865 |  | Functional Leads Validation of Transport List |  | Functional Leads | Tue 5/5/26 | Tue 5/5/26 | Tue 5/19/26 | 0% | Future Task | 863 | Yes | No | 865 | 2e2b485ad77e21a766b755ff17b25484a0d14bd9323a5b23a480b688bd286e5b
project_plan | project_plan | 58 | 866 |  | Release Security roles to Functional Team |  | Security | Tue 5/5/26 | Tue 5/5/26 | Tue 5/19/26 | 0% | Future Task | 865 | Yes | No | 866 | fe6e32b0201965908411a18d8fb23daf5b97dd408cb8d05b4eed6a51e480ff3b
project_plan | project_plan | 59 | 867 |  | Release Transports to Client |  |  | Wed 5/6/26 | Thu 5/14/26 | Tue 5/26/26 | 0% | Future Task | 3340 | Yes | No | 867 | 0217dbb9f0a9834d60403c4c7fc4d07866a98bc04c4837cfc6decf681c759d39
project_plan | project_plan | 60 | 868 |  | Import Group 1 - Ent Structure |  | Functional Leads | Wed 5/6/26 | Wed 5/6/26 | Tue 5/19/26 | 0% | Future Task | 865 | Yes | No | 868 | e1db095c16fd204563a8de37fe589aaa2a9eec2a413703ba77720a658b00ce5f
project_plan | project_plan | 61 | 869 |  | Manual activities group 1 |  | Functional Leads | Wed 5/6/26 | Fri 5/8/26 | Fri 5/22/26 | 0% | Future Task | 868 | Yes | No | 869 | d09d39272e35594ed62ee91e5d9c16591186c4c7ba49378fc4e41cfb0b6aa8e7
project_plan | project_plan | 62 | 870 |  | Import Group 2 - Core Transports |  | Functional Leads | Fri 5/8/26 | Fri 5/8/26 | Fri 5/22/26 | 0% | Future Task | 869 | Yes | No | 870 | a8cfe770cbf0919c6eaa06d8f7d5cda536e803a8b2c55afc5b57e152f45f4771
project_plan | project_plan | 63 | 871 |  | Manual activities group 2 |  | Functional Leads | Mon 5/11/26 | Mon 5/11/26 | Mon 5/25/26 | 0% | Future Task | 870 | Yes | No | 871 | dccd907ea8d9524ec71ca43b4202792e0a8b8b04540e04d03f2b6f85d7dca5ae
project_plan | project_plan | 64 | 872 |  | Import Group 3 - prior to transactions |  | Functional Leads | Tue 5/12/26 | Tue 5/12/26 | Mon 5/25/26 | 0% | Future Task | 871 | Yes | No | 872 | 8b84eb12e1a3d1b24015abdf57df9410bedec4f70fc9c4327cc227dc106c3397
project_plan | project_plan | 65 | 873 |  | Manual Activities Group 3 |  | Functional Leads | Tue 5/12/26 | Wed 5/13/26 | Tue 5/26/26 | 0% | Future Task | 872 | Yes | No | 873 | 2dda975f9720d8cf79746ff4113c21310d055dc8f16c21a05b9fc28e4ec467da
project_plan | project_plan | 66 | 874 |  | Import Group 4 - workbench / dev work |  | Dev Team | Wed 5/13/26 | Wed 5/13/26 | Tue 5/26/26 | 0% | Future Task | 873 | Yes | No | 874 | d2245471283845fd0d911a6157e3a32d00efbb07a76c7e3dc24f422c6f2cb582
project_plan | project_plan | 67 | 875 |  | Import Group 5 - Config to support dev workbench |  | Dev Team | Wed 5/13/26 | Thu 5/14/26 | Thu 5/28/26 | 0% | Future Task | 874SS | Yes | No | 875 | 24a48c429fb6c793c3ea86bc3a9b42789500dd927b9fb2072370046e4ef31c37
project_plan | project_plan | 68 | 1226 |  | Data Project Create |  |  | Thu 5/14/26 | Thu 5/14/26 | Thu 5/28/26 | 0% | Future Task |  | Yes | No | 1226 | 5f8e1fd45b3630825ecf328c95a9b2b87a30abc78f5aceb433aaf2053697c28b
project_plan | project_plan | 69 | 1221 |  | Open Client |  | Basis | Thu 5/14/26 | Thu 5/14/26 | Wed 5/27/26 | 0% | Future Task | 875 | Yes | No | 1221 | ccae56c85fa526413859151586a7ab334ef532dd7182930519f1e77f9c81751d
project_plan | project_plan | 70 | 876 |  | Create Migration Data Project in DMC |  | Data Migration Team | Thu 5/14/26 | Thu 5/14/26 | Thu 5/28/26 | 0% | Future Task | 1221 | Yes | No | 876 | 7dd7aec5bf011e74c8c3faa72f823f3db0eb74715860dc7f2e8527d3d06ea173
project_plan | project_plan | 71 | 1222 |  | Close Client |  | Basis | Thu 5/14/26 | Thu 5/14/26 | Thu 5/28/26 | 0% | Future Task | 876 | Yes | No | 1222 | 32d5941b3180690a049ecc4c4a2a6e33ed0ee10b443425909e954c977b446341
project_plan | project_plan | 72 | 877 |  | Environment Ready for Test |  | PMO | Thu 5/14/26 | Thu 5/14/26 | Thu 7/16/26 | 0% | Future Task | 1222 | Yes | Yes | 877 | dfb8bb1184f704a46571710169b70b27615d94b40e2abbca42ab798d962db71c
project_plan | project_plan | 73 | 1284 |  | QS5 ITC-3 Refresh |  |  | Mon 5/18/26 | Mon 6/1/26 | Thu 7/16/26 | 0% | Future Task |  | Yes | No | 1284 | 0501cc6898355b5365bb77873ad4d4b74faf250d20a26d4b3ad91215b3b92b90
project_plan | project_plan | 74 | 3339 |  | System Setup |  |  | Mon 5/18/26 | Wed 5/27/26 |  | 0% | Future Task | 867 | Yes | No | 3339 | d94fb9e3e2aca94c577571c04487aa580421ce7a772d36d7fc15d41f00f2bfd2
project_plan | project_plan | 75 | 1285 |  | System Refresh Basis(Workinig with NS2) |  | Basis | Mon 5/18/26 | Wed 5/20/26 | Fri 5/1/26 | 0% | Future Task |  | Yes | No | 1285 | a768095d1c5b7317083dcd952606617486a83c6fb2ba1b9ca2c520297b4c796e
project_plan | project_plan | 76 | 1288 |  | Client Config / Validation |  | Basis | Thu 5/21/26 | Thu 5/21/26 | Mon 5/11/26 | 0% | Future Task | 1285 | Yes | No | 1288 | c51526191e001a2dcdb2880f1789c0460a0c21ade2d78cd9017857dc2bed6cee
project_plan | project_plan | 77 | 1289 |  | Technical Transports / BP Setup |  | Basis | Fri 5/22/26 | Fri 5/22/26 | Tue 5/12/26 | 0% | Future Task | 1288 | No | No | 1289 | 999f6c894a982407c7216972c09af8dad094e5e35d1b342b40280367af841de3
project_plan | project_plan | 78 | 1290 |  | Best Practice / Country Validation |  | Basis | Mon 5/25/26 | Mon 5/25/26 | Wed 5/13/26 | 0% | Future Task | 1289 | No | No | 1290 | 643acd7a22ca62699270cf3987961bcbb618a3740c3de53d4a390a3c95d2d702
project_plan | project_plan | 79 | 1291 |  | Connect Systems and Validate |  | Basis | Tue 5/26/26 | Tue 5/26/26 | Thu 5/14/26 | 0% | Future Task | 1290 | No | No | 1291 | 747309df27753e352e2bc75dbfd5ee5243600aa89f682a9d31a48e0321b22961
project_plan | project_plan | 80 | 1292 |  | Validate Syniti Connections to QS5 |  | Data | Wed 5/27/26 | Wed 5/27/26 | Fri 5/15/26 | 0% | Future Task | 1291 | No | No | 1292 | 6dea50083e2759b44bf3acb47732b69807a1718d0710917101fde676a89dbe1c
project_plan | project_plan | 81 | 1293 |  | Security Transports |  | Security | Thu 5/21/26 | Thu 5/21/26 | Fri 5/15/26 | 0% | Future Task | 1288SS | Yes | No | 1293 | 89a99a164f0e3e8957d5dd6dbf8e349e173cda3cf8fc19198a8aa48e40b7b27b
project_plan | project_plan | 82 | 1294 |  | Security Manual Tasks |  | Security | Thu 5/21/26 | Fri 5/22/26 | Mon 5/18/26 | 0% | Future Task | 1293 | No | No | 1294 | 7e79b9bca947a79489131fad8929c5c75123e6295cc82b5eb28a7127d8fd95e3
project_plan | project_plan | 83 | 1295 |  | Manual Technical Tasks |  | Basis | Thu 5/21/26 | Thu 5/21/26 | Mon 5/18/26 | 0% | Future Task | 1293SS | Yes | No | 1295 | 7da4b2b75f634b31822d6b9ef0e1928f281ff6de3995da724ed3e576209e1031
project_plan | project_plan | 84 | 1296 |  | Validate Fiori |  | Basis | Fri 5/22/26 | Fri 5/22/26 | Tue 5/19/26 | 0% | Future Task | 1295 | Yes | No | 1296 | 81a4d36d97ec66ea9f323e435699e3aeb8039683ff8aa6725419e460dc37f1eb
project_plan | project_plan | 85 | 1297 |  | Fiori App Activation |  | Dev Team | Fri 5/22/26 | Fri 5/22/26 | Tue 5/19/26 | 0% | Future Task | 1296SS | Yes | No | 1297 | 65c0ab9ece5e01b407556fc8f5cb4bb9de6d4d124114170a05e167ecb2c1d250
project_plan | project_plan | 86 | 1298 |  | Download Transport List |  | Basis | Fri 5/22/26 | Fri 5/22/26 | Tue 5/19/26 | 0% | Future Task | 1297SS | Yes | No | 1298 | f2a7861c823176b213e45ffe2559c9b6698c9bbe6915e61831e434ea98141523
project_plan | project_plan | 87 | 1299 |  | Business Functions Validation |  | Basis | Fri 5/22/26 | Fri 5/22/26 | Wed 5/20/26 | 0% | Future Task | 1298SS | No | No | 1299 | 5e0290c103243c6f60a6b8a6beccc2da1f72b409ebef89c2fc37b97426c0c8fa
project_plan | project_plan | 88 | 1300 |  | Functional Leads Validation of Transport |  | Functional Leads | Fri 5/22/26 | Fri 5/22/26 | Tue 5/19/26 | 0% | Future Task | 1298SS | Yes | No | 1300 | 3d1339ef40c37b0a97102aaf45b5e626fb1da77a4dd4963439b1e71f8d0759fb
project_plan | project_plan | 89 | 1301 |  | Release Security roles to Functional Team |  | Security | Mon 5/25/26 | Mon 5/25/26 | Tue 5/19/26 | 0% | Future Task | 1299 | No | No | 1301 | 0394ae68a4e278398ead46662961f46fa3741011daea4ca8ae4800e8f3df0ffe
project_plan | project_plan | 90 | 1302 |  | Release Transports to Client |  |  | Fri 5/22/26 | Mon 6/1/26 | Tue 5/26/26 | 0% | Future Task | 1300 | Yes | No | 1302 | 52a06bc753ea98828a1adb76fc58f258538bc10ab0e1baab033a7588352919dc
project_plan | project_plan | 91 | 1303 |  | Import Group 1 - Ent Structure |  | Functional Leads | Fri 5/22/26 | Fri 5/22/26 | Tue 5/19/26 | 0% | Future Task | 1300 | Yes | No | 1303 | f0e3569a5608f0bf5f01e56bb6e6d822f18af0eb2c22a3774d254e2ed2b2984d
project_plan | project_plan | 92 | 1304 |  | Manual activities group 1 |  | Functional Leads | Fri 5/22/26 | Tue 5/26/26 | Fri 5/22/26 | 0% | Future Task | 1303 | Yes | No | 1304 | 9866102c2490eb4914c75395e96632e2cdeac62684ab06b3a5723552b47ecaff
project_plan | project_plan | 93 | 1305 |  | Import Group 2 - Core Transports |  | Functional Leads | Tue 5/26/26 | Wed 5/27/26 | Fri 5/22/26 | 0% | Future Task | 1304 | Yes | No | 1305 | 7519249ed2070ef4a36893784a84bec03d37290923989215ca60fa5cb6c1f2e4
project_plan | project_plan | 94 | 1306 |  | Manual activities group 2 |  | Functional Leads | Wed 5/27/26 | Thu 5/28/26 | Mon 5/25/26 | 0% | Future Task | 1305 | Yes | No | 1306 | 6397d4cf5c36a8acd9240c11f809d170fe205666a3f6722b5f4854b33ceab39f
project_plan | project_plan | 95 | 1307 |  | Import Group 3 - prior to transactions |  | Functional Leads | Thu 5/28/26 | Thu 5/28/26 | Mon 5/25/26 | 0% | Future Task | 1306 | Yes | No | 1307 | 13c9db02dae6722e8a394014752ea10d4b428b7f4220b5f2198e300300f5e3fd
project_plan | project_plan | 96 | 1308 |  | Manual Activities Group 3 |  | Functional Leads | Thu 5/28/26 | Fri 5/29/26 | Tue 5/26/26 | 0% | Future Task | 1307 | Yes | No | 1308 | 547f87d7553f0f0f7adfbd901ba0c98fe5418299585e1f14a8150fcec3abe080
project_plan | project_plan | 97 | 1309 |  | Import Group 4 - workbench / dev work |  | Dev Team | Fri 5/29/26 | Fri 5/29/26 | Tue 5/26/26 | 0% | Future Task | 1308 | No | No | 1309 | 87b6791111c55b167fdc23edd85f36b5cc6f7eacd4765f2f8df9beecef8c915c
project_plan | project_plan | 98 | 1310 |  | Import Group 5 - Config to support dev workbench |  | Dev Team | Fri 5/29/26 | Mon 6/1/26 | Thu 5/28/26 | 0% | Future Task | 1309SS | No | No | 1310 | cafe34e3090f665e6d53445fffe7fadef0cc888705e961e33c12d8a59f552050
project_plan | project_plan | 99 | 1311 |  | Data Project Create |  |  | Fri 5/29/26 | Fri 5/29/26 | Thu 5/28/26 | 0% | Future Task | 1308 | Yes | No | 1311 | b7188bc967dca58869816394d26c0f92a24570b4a97b80a7b8adb31933eb9952
project_plan | project_plan | 100 | 1312 |  | Open Client |  | Basis | Fri 5/29/26 | Fri 5/29/26 | Wed 5/27/26 | 0% | Future Task | 1308 | Yes | No | 1312 | acda4324fbc51cc07a4447cdc2cd967daab80861edb765e845d2395a9a40fb28
project_plan | project_plan | 101 | 1313 |  | Create Migration Data Project in DMC |  | Data Migration Team | Fri 5/29/26 | Fri 5/29/26 | Thu 5/28/26 | 0% | Future Task | 1312 | Yes | No | 1313 | 9ee8b574ad4ecdb1c1e0107dfdce148f7ad7d7294344ba604383ab8a7ef780b5
project_plan | project_plan | 102 | 1314 |  | Close Client |  | Basis | Fri 5/29/26 | Fri 5/29/26 | Thu 5/28/26 | 0% | Future Task | 1313 | Yes | No | 1314 | f085f33331e2b8b8add46281416e6fa1d0a578582d55fb4ea1ab854289b77866
project_plan | project_plan | 103 | 1315 |  | Environment Ready for Test |  | PMO | Fri 5/29/26 | Fri 5/29/26 | Thu 7/16/26 | 0% | Future Task | 1314 | Yes | Yes | 1315 | 9d8ab60c6832148cb0263c1e615793dacbf655c9d315a4cf44529fa58b1eea11
project_plan | project_plan | 104 | 884 |  | QS4 UAT Refresh |  |  | Mon 6/8/26 | Fri 6/26/26 | Thu 7/16/26 | 0% | Future Task |  | Yes | No | 884 | a4127c341177f048ab987d382128f81f6a5301ff5de2a94dc67791a8c22db84b
project_plan | project_plan | 105 | 3338 |  | System Setup |  |  | Mon 6/8/26 | Wed 6/17/26 |  | 0% | Future Task | 1315 | Yes | No | 3338 | 737a889354664065459a5ad6fff91ba077a3f266a60c6f0c389687556b85d17d
project_plan | project_plan | 106 | 885 |  | System Refresh Basis(Workinig with NS2) |  | Basis | Mon 6/8/26 | Tue 6/9/26 | Fri 6/19/26 | 0% | Future Task |  | Yes | No | 885 | 0512ec1130bc381c510760f867a363f063fed291e6311acf4f1e15a9972484fb
project_plan | project_plan | 107 | 888 |  | Client Config / Validation |  | Basis | Wed 6/10/26 | Thu 6/11/26 | Mon 6/29/26 | 0% | Future Task | 885 | Yes | No | 888 | b0854caa84561f808088c2387c7e8f738e30b252d3da38372ea0fb9c179a3574
project_plan | project_plan | 108 | 889 |  | Technical Transports / BP Setup |  | Basis | Fri 6/12/26 | Fri 6/12/26 | Tue 6/30/26 | 0% | Future Task | 888 | Yes | No | 889 | 3a1ca1e5dcfae42add28e5e5ae5d896933b88d21e4ecaa152e814e8c134a4941
project_plan | project_plan | 109 | 890 |  | Best Practice / Country Validation |  | Basis | Fri 6/12/26 | Fri 6/12/26 | Wed 7/1/26 | 0% | Future Task | 888 | Yes | No | 890 | b22ef844e025f0338ddb22f36f112095e4c8cd6dd081a48b16a3233ac00dd9e0
project_plan | project_plan | 110 | 891 |  | Connect Systems and Validate |  | Basis | Mon 6/15/26 | Tue 6/16/26 | Thu 7/2/26 | 0% | Future Task | 890 | Yes | No | 891 | 30e3b1f51037106d17f3d5bd2c12e5e1fa1a79a1e00f14fcbf93422667a42b75
project_plan | project_plan | 111 | 892 |  | Validate Syniti Connections to QS5 |  | Data | Wed 6/17/26 | Wed 6/17/26 | Fri 7/3/26 | 0% | Future Task | 891 | Yes | No | 892 | f7558d3e9dcf747c0240a7dc6bbb59191bd6d668896878c3071b96a264691669
project_plan | project_plan | 112 | 893 |  | Security Transports |  | Security | Mon 6/15/26 | Mon 6/15/26 | Fri 7/3/26 | 0% | Future Task | 890,889 | Yes | No | 893 | c539fa9b4142db413aa5e720a66214924b8600f97d8d8f2a8212d6faa3bd0232
project_plan | project_plan | 113 | 894 |  | Security Manual Tasks |  | Security | Tue 6/16/26 | Tue 6/16/26 | Mon 7/6/26 | 0% | Future Task | 893 | Yes | No | 894 | e69a7d96ff89c6000ff171588d2f9a76c10be4db6a4da352105b8cc4bf1bafdf
project_plan | project_plan | 114 | 895 |  | Manual Technical Tasks |  | Basis | Mon 6/15/26 | Mon 6/15/26 | Mon 7/6/26 | 0% | Future Task | 893SS | Yes | No | 895 | 503329c8539f34d2f7043dfc892e613826bf32981a2e18a28693fc7de2d1b22d
project_plan | project_plan | 115 | 896 |  | Validate Fiori |  | Basis | Tue 6/16/26 | Tue 6/16/26 | Tue 7/7/26 | 0% | Future Task | 895 | Yes | No | 896 | a498dedc98281d627bd95a8073fa1e96f72c16e95a7b6715d980e154d95d3e08
project_plan | project_plan | 116 | 897 |  | Fiori App Activation |  | Dev Team | Tue 6/16/26 | Tue 6/16/26 | Tue 7/7/26 | 0% | Future Task | 896SS | Yes | No | 897 | 83aea180353ca183ef7f0e92fc8a246574cf9617d9b62fc802cb86c219defc7c
project_plan | project_plan | 117 | 898 |  | Download Transport List |  | Basis | Wed 6/17/26 | Wed 6/17/26 | Tue 7/7/26 | 0% | Future Task | 896 | Yes | No | 898 | 491e2c47c40d6d7fe788a715b1d4951f051495ce884eaced67841a52b39b01d7
project_plan | project_plan | 118 | 899 |  | Business Functions Validation |  | Basis | Tue 6/16/26 | Tue 6/16/26 | Wed 7/8/26 | 0% | Future Task | 896SS | Yes | No | 899 | f95a21c9465449472fccfa19b4e526d78b43eb3d3399a956aad47c66af02cbfd
project_plan | project_plan | 119 | 900 |  | Functional Leads Validation of Transport List |  | Functional Leads | Tue 6/16/26 | Tue 6/16/26 | Tue 7/7/26 | 0% | Future Task | 896SS | Yes | No | 900 | 0e674ac71431ab08ca00523e4934ae2c55f36e0605d863fc91731a40bac264b2
project_plan | project_plan | 120 | 901 |  | Release Security roles to Functional Team |  | Security | Wed 6/17/26 | Wed 6/17/26 | Tue 7/7/26 | 0% | Future Task | 900 | Yes | No | 901 | e80417d527e2208dd8ff87b465d3f4696212912e13adae1b27dccc55368bdc35
project_plan | project_plan | 121 | 902 |  | Release Transports to Client |  |  | Thu 6/18/26 | Thu 6/25/26 | Tue 7/14/26 | 0% | Future Task | 3338 | Yes | No | 902 | 83e765c760126b1c142e00f4e97cb6c5df76e9e15ecadca9dbe1076e73133b43
project_plan | project_plan | 122 | 903 |  | Import Group 1 - Ent Structure |  | Functional Leads | Thu 6/18/26 | Thu 6/18/26 | Tue 7/7/26 | 0% | Future Task | 900 | Yes | No | 903 | dddd052be86f85fbd8ca955a338eaa3a382126bf8b6df4763c8f412488e0e2c8
project_plan | project_plan | 123 | 904 |  | Manual activities group 1 |  | Functional Leads | Thu 6/18/26 | Mon 6/22/26 | Fri 7/10/26 | 0% | Future Task | 903 | Yes | No | 904 | 58b00b07a4de48b6f5f7d51d233cc0c63fc4d6938e8326f33165169798b77b82
project_plan | project_plan | 124 | 905 |  | Import Group 2 - Core Transports |  | Functional Leads | Mon 6/22/26 | Mon 6/22/26 | Fri 7/10/26 | 0% | Future Task | 904 | Yes | No | 905 | 9b482d171caa8365082f409719c2f4d07a7d3b5e33906ca68d5e607da779f6d5
project_plan | project_plan | 125 | 906 |  | Manual activities group 2 |  | Functional Leads | Tue 6/23/26 | Tue 6/23/26 | Mon 7/13/26 | 0% | Future Task | 905 | Yes | No | 906 | b9a41c1dcc7458fe55d445e6017b6e8f85f2eb3c676d0963cc839ad832ffe769
project_plan | project_plan | 126 | 907 |  | Import Group 3 - prior to transactions |  | Functional Leads | Wed 6/24/26 | Wed 6/24/26 | Mon 7/13/26 | 0% | Future Task | 906 | Yes | No | 907 | b55f3a0a202334804a513082220d132b13332a9dcbea0d82bfbfe86959ab39c5
project_plan | project_plan | 127 | 908 |  | Manual Activities Group 3 |  | Functional Leads | Wed 6/24/26 | Thu 6/25/26 | Tue 7/14/26 | 0% | Future Task | 907 | Yes | No | 908 | 2eb4cd1f2f1ee854f5134d697eb1574f4e6645077b963a68cbfb033afe9f1c38
project_plan | project_plan | 128 | 909 |  | Import Group 4 - workbench / dev work |  | Dev Team | Thu 6/25/26 | Thu 6/25/26 | Tue 7/14/26 | 0% | Future Task | 908 | Yes | No | 909 | 30a034a5f54fcee0ff334f2782b39b9773d31f9b80c9039936844a7e3687acfe
project_plan | project_plan | 129 | 910 |  | Import Group 5 - Config to support dev workbench |  | Dev Team | Thu 6/25/26 | Thu 6/25/26 | Wed 7/15/26 | 0% | Future Task | 909SS | Yes | No | 910 | 05862b83a686de4f679ef0c292995b7e267ef5867bd39c662ace5cd965ef31f7
project_plan | project_plan | 130 | 1227 |  | Data Project Create |  |  | Thu 6/25/26 | Fri 6/26/26 | Thu 7/16/26 | 0% | Future Task |  | Yes | No | 1227 | 4e3ed3ace5ec42d8737b80c32a70073c9b02f5d3bf0f33f0b1c86d6a91e331f8
project_plan | project_plan | 131 | 1228 |  | Open Client |  | Basis | Thu 6/25/26 | Thu 6/25/26 | Wed 7/15/26 | 0% | Future Task | 910 | Yes | No | 1228 | aeed26aca8582d189ab2445bb5a76a1a77191ee39d83cf3e2f22e2b36f4bfd54
project_plan | project_plan | 132 | 1229 |  | Create Migration Data Project in DMC |  | Data Migration Team | Thu 6/25/26 | Fri 6/26/26 | Thu 7/16/26 | 0% | Future Task | 1228 | Yes | No | 1229 | 8eb1a8a030dee00b53c81a661b5f67eddfc8ac41035fe56c6ec39d5b005a4024
project_plan | project_plan | 133 | 1230 |  | Close Client |  | Basis | Fri 6/26/26 | Fri 6/26/26 | Thu 7/16/26 | 0% | Future Task | 1229 | Yes | No | 1230 | 413cc28821affc8e3277d922a157123b294d5aabde65d022de565e6d88d6da88
project_plan | project_plan | 134 | 912 |  | Environment Ready for Build |  | PMO | Fri 6/26/26 | Fri 6/26/26 | Thu 3/13/25 | 0% | Future Task | 1230 | Yes | Yes | 912 | 360b2bc461f02cbf44f6cf0a73422a62b1b441880c35c0693f4c580722a0ab94
project_plan | project_plan | 135 | 3367 |  | P? Production System |  |  | Mon 9/7/26 | Thu 9/24/26 | Thu 7/16/26 | 0% | Future Task |  | Yes | No | 3367 | f04cb44007bba63b5b21bfb064fe97876b9c41003ca31528d94f33b1b959e37a
project_plan | project_plan | 136 | 3368 |  | System Setup |  |  | Mon 9/7/26 | Wed 9/16/26 |  | 0% | Future Task | 902 | Yes | No | 3368 | b5049c009319f48551dec71b972240dbb0210995d503a218e4eeaff3cd215416
project_plan | project_plan | 137 | 3369 |  | System Refresh Basis(Workinig with NS2) |  | Basis | Mon 9/7/26 | Tue 9/8/26 | Fri 6/19/26 | 0% | Future Task |  | Yes | No | 3369 | 69abcca3679be7dbb3175ffa6bfe8d9c05721f6b2fbbf05dfc982d34e89dc413
project_plan | project_plan | 138 | 3370 |  | Client Config / Validation |  | Basis | Wed 9/9/26 | Thu 9/10/26 | Mon 6/29/26 | 0% | Future Task | 3369 | Yes | No | 3370 | c46d3c545162d8e51c54b975846a79306d2b11f352f43f82131d72e7779304b8
project_plan | project_plan | 139 | 3371 |  | Technical Transports / BP Setup |  | Basis | Fri 9/11/26 | Fri 9/11/26 | Tue 6/30/26 | 0% | Future Task | 3370 | Yes | No | 3371 | 2e924973e73c9ae02a85dacac3f264e1bc8bafa5a6e10617edf02fae84007972
project_plan | project_plan | 140 | 3372 |  | Best Practice / Country Validation |  | Basis | Fri 9/11/26 | Fri 9/11/26 | Wed 7/1/26 | 0% | Future Task | 3370 | Yes | No | 3372 | 57022cef685c2bd8fcb6e76ed4a9f12189ffb98311c27a170b533397c569fe94
project_plan | project_plan | 141 | 3373 |  | Connect Systems and Validate |  | Basis | Mon 9/14/26 | Tue 9/15/26 | Thu 7/2/26 | 0% | Future Task | 3372 | Yes | No | 3373 | eede7720b80802226129c244683ce5e7ed18342d27705190489a146047b79e4c
project_plan | project_plan | 142 | 3374 |  | Validate Syniti Connections to QS5 |  | Data | Wed 9/16/26 | Wed 9/16/26 | Fri 7/3/26 | 0% | Future Task | 3373 | Yes | No | 3374 | 65ebb86926f2a9ec20fa1b17504e66fce2a8ccb49448ab2b262934d5aa2dee59
project_plan | project_plan | 143 | 3375 |  | Security Transports |  | Security | Mon 9/14/26 | Mon 9/14/26 | Fri 7/3/26 | 0% | Future Task | 33,713,372 | Yes | No | 3375 | 1723761c01c9bb021c604888d010e65d92ec282e83157b92306bca0119aa9ad8
project_plan | project_plan | 144 | 3376 |  | Security Manual Tasks |  | Security | Tue 9/15/26 | Tue 9/15/26 | Mon 7/6/26 | 0% | Future Task | 3375 | Yes | No | 3376 | af2b9d8b6623e9b4d36960bd21a6b55bb6c8f62b8b203c1af868af2cdee74ce5
project_plan | project_plan | 145 | 3377 |  | Manual Technical Tasks |  | Basis | Mon 9/14/26 | Mon 9/14/26 | Mon 7/6/26 | 0% | Future Task | 3375SS | Yes | No | 3377 | a513e57d8672876e9a5a1afc0f634c6a7a32e327dff57752cf345dcf160516d2
project_plan | project_plan | 146 | 3378 |  | Validate Fiori |  | Basis | Tue 9/15/26 | Tue 9/15/26 | Tue 7/7/26 | 0% | Future Task | 3377 | Yes | No | 3378 | 4898cb7beea46086ec77ce191bf0be0ccc7cdc2af1373d5a7e7be06d3334e62e
project_plan | project_plan | 147 | 3379 |  | Fiori App Activation |  | Dev Team | Tue 9/15/26 | Tue 9/15/26 | Tue 7/7/26 | 0% | Future Task | 3378SS | Yes | No | 3379 | 32adf6b16f49fa69b653662837be2a50a751829c3b2116403a1faf6bc7769173
project_plan | project_plan | 148 | 3380 |  | Download Transport List |  | Basis | Wed 9/16/26 | Wed 9/16/26 | Tue 7/7/26 | 0% | Future Task | 3378 | Yes | No | 3380 | eb5c0d1a1fc0496f79610092e2df036b204eba70694a31843f3403edf615d769
project_plan | project_plan | 149 | 3381 |  | Business Functions Validation |  | Basis | Tue 9/15/26 | Tue 9/15/26 | Wed 7/8/26 | 0% | Future Task | 3378SS | Yes | No | 3381 | be3f1e347fc2a7f66cd23677546582cb2be5bbecc1829354fc00575cdc611127
project_plan | project_plan | 150 | 3382 |  | Functional Leads Validation of Transport List |  | Functional Leads | Tue 9/15/26 | Tue 9/15/26 | Tue 7/7/26 | 0% | Future Task | 3378SS | Yes | No | 3382 | a7da82c3d144084173f3101073b0349a233eed3654e71a6502f20ba649641730
project_plan | project_plan | 151 | 3383 |  | Release Security roles to Functional Team |  | Security | Wed 9/16/26 | Wed 9/16/26 | Tue 7/7/26 | 0% | Future Task | 3382 | Yes | No | 3383 | 3924f8c51606bec6c3b5fa9e45c5b84c308afd9155cbf6f7eff3f1c9b28313e5
project_plan | project_plan | 152 | 3384 |  | Release Transports to Client |  |  | Wed 9/16/26 | Wed 9/23/26 | Tue 7/14/26 | 0% | Future Task | 3382 | Yes | No | 3384 | a5320ea6ba0b17045a510c07eff3abc66c4e225058a7f6fbd47bdecfac16cac0
project_plan | project_plan | 153 | 3385 |  | Import Group 1 - Ent Structure |  | Functional Leads | Wed 9/16/26 | Wed 9/16/26 | Tue 7/7/26 | 0% | Future Task | 3382 | Yes | No | 3385 | 9361e880bbfa55b1b61d100c25ec9c31cfa6d93e8a7af610c37a9e72cee4d9c9
project_plan | project_plan | 154 | 3386 |  | Manual activities group 1 |  | Functional Leads | Wed 9/16/26 | Fri 9/18/26 | Fri 7/10/26 | 0% | Future Task | 3385 | Yes | No | 3386 | a9cba37f08a33707766f5a50794700535817104c127a89b23dcb4bf8e0ef82e7
project_plan | project_plan | 155 | 3387 |  | Import Group 2 - Core Transports |  | Functional Leads | Fri 9/18/26 | Fri 9/18/26 | Fri 7/10/26 | 0% | Future Task | 3386 | Yes | No | 3387 | 4f8d9940abfe0416c4e4c1739ad5ccbd965a877f8a574c4cdee1593efa7d27c5
project_plan | project_plan | 156 | 3388 |  | Manual activities group 2 |  | Functional Leads | Mon 9/21/26 | Mon 9/21/26 | Mon 7/13/26 | 0% | Future Task | 3387 | Yes | No | 3388 | a3b117917d525a186f340f8545de2c04217610ff39912877d18f33cb70bffc83
project_plan | project_plan | 157 | 3389 |  | Import Group 3 - prior to transactions |  | Functional Leads | Tue 9/22/26 | Tue 9/22/26 | Mon 7/13/26 | 0% | Future Task | 3388 | Yes | No | 3389 | 76fb0ce72b9856117426270012bb47f8974071f913e34e827ee052c1254c64dc
project_plan | project_plan | 158 | 3390 |  | Manual Activities Group 3 |  | Functional Leads | Tue 9/22/26 | Wed 9/23/26 | Tue 7/14/26 | 0% | Future Task | 3389 | Yes | No | 3390 | 3d1a0957215753b8dbf33b284282fbea31a3119bd3c2617d9fe86a08dac05ca4
project_plan | project_plan | 159 | 3391 |  | Import Group 4 - workbench / dev work |  | Dev Team | Wed 9/23/26 | Wed 9/23/26 | Tue 7/14/26 | 0% | Future Task | 3390 | Yes | No | 3391 | e749258b4d2787305f0d580af54ac351e7876bce91f7fb91d5db3a0efca2975e
project_plan | project_plan | 160 | 3392 |  | Import Group 5 - Config to support dev workbench |  | Dev Team | Wed 9/23/26 | Wed 9/23/26 | Wed 7/15/26 | 0% | Future Task | 3391SS | Yes | No | 3392 | eae6abefb538ca4849596d4bcb24d7beaa36cf3192f807dbf8fe3df488bdb84e
project_plan | project_plan | 161 | 3393 |  | Data Project Create |  |  | Wed 9/23/26 | Thu 9/24/26 | Thu 7/16/26 | 0% | Future Task |  | Yes | No | 3393 | a20c5fd9b57f704f71cceb5869a18e99a86ace8cac8843c051c3a509d42d59a2
project_plan | project_plan | 162 | 3394 |  | Open Client |  | Basis | Wed 9/23/26 | Wed 9/23/26 | Wed 7/15/26 | 0% | Future Task | 3392 | Yes | No | 3394 | 67ea979254b0afff73d2a5dcd38774f99dee311011ff35a8b2912813e118acd2
project_plan | project_plan | 163 | 3395 |  | Create Migration Data Project in DMC |  | Data Migration Team | Wed 9/23/26 | Thu 9/24/26 | Thu 7/16/26 | 0% | Future Task | 3394 | Yes | No | 3395 | 5606221c2dd085ae7396f901ffc851ff935ee122476f5b5ff0615d131857ea8f
project_plan | project_plan | 164 | 3396 |  | Close Client |  | Basis | Thu 9/24/26 | Thu 9/24/26 | Thu 7/16/26 | 0% | Future Task | 3395 | Yes | No | 3396 | c862ac92b13fc3ab2bab80be32ad30fe4e1d9bd09d91cd626cc4668ab312cecd
project_plan | project_plan | 165 | 3397 |  | Environment Ready for Build |  | PMO | Thu 9/24/26 | Thu 9/24/26 | Thu 3/13/25 | 0% | Future Task | 3393 | Yes | Yes | 3397 | b56f8741582bf1ab204b98550b032ed88761cc73c0c648d22a719f59562fb928
project_plan | project_plan | 166 | 201 |  | Prod (PS4) Setup |  |  | Mon 9/7/26 | Tue 9/29/26 | Mon 4/7/25 | 0% | Future Task |  | No | No | 201 | d20ee17682289da8e0ae6181cb329783cd623d3e5cc5c48d12445be338c99b44
project_plan | project_plan | 167 | 248 |  | GRC Security Utility |  |  | Mon 2/17/25 | Thu 10/22/26 | Mon 4/6/26 | 88% | Complete |  | No | No | 248 | 17cc363f609bf6b95a409e3a72d99a336206e1ea5142bff2face988e4cfe52cd
project_plan | project_plan | 168 | 299 |  | Initiation & Planning |  |  | Mon 2/17/25 | Tue 2/17/26 | Tue 2/17/26 | 100% | Complete |  | No | No | 299 | e027714f75130a400e0ddfc3cb5436fcbc834eb346745bf95abdc8df4d38b91e
project_plan | project_plan | 169 | 249 |  | Project kickoff |  |  | Wed 7/16/25 | Wed 7/16/25 | Wed 7/16/25 | 100% | Complete |  | No | No | 249 | dfd6bf5c43b25ea58690818207659a536de2666808f8bd4ad91c8f7e156283d2
project_plan | project_plan | 170 | 250 |  | Requirement gathering |  |  | Mon 2/17/25 | Fri 8/15/25 | Fri 8/15/25 | 100% | Complete |  | No | No | 250 | 2d6522fc2ad2c80e16d6421f5468d39ed9bbb15af63bd8fd8eb424dd0b89a354
project_plan | project_plan | 171 | 251 |  | Landscape design |  |  | Mon 8/18/25 | Tue 8/19/25 | Tue 8/19/25 | 100% | Complete | 250 | No | No | 251 | a702e0cbcb42a6f9d03a6583ae48fc676b163a92f895cba78d13e9961947ca35
project_plan | project_plan | 172 | 252 |  | Project plan finalization |  |  | Mon 2/16/26 | Tue 2/17/26 | Tue 2/17/26 | 100% | Complete |  | No | No | 252 | 40a0c8ca2f1041704bd0650e75c72104bf3fe6e6a177eb0bef8eac06cff0646f
project_plan | project_plan | 173 | 253 |  | System Setup & Connectivity |  |  | Mon 7/28/25 | Mon 3/23/26 | Mon 3/23/26 | 100% | Complete |  | No | No | 253 | b35f9ba15eb666fd82587d84348a65bc470c8049879b1157d9a23e4bc7bc3e23
project_plan | project_plan | 174 | 254 |  | Install GRC AC components |  |  | Mon 7/28/25 | Fri 8/1/25 | Fri 8/1/25 | 100% | Complete |  | No | No | 254 | 6293d19ddb0d73bcba419b872baa3879a5c3e90ed3a87522c8e0ab16edf6a547
project_plan | project_plan | 175 | 258 |  | Install plug-ins on target systems |  |  | Wed 2/18/26 | Tue 2/24/26 | Tue 2/24/26 | 100% | Complete | 252 | No | No | 258 | f264443eeeffc140b33aee266893cfee506081228874b6f4f14a97e365b5d403
project_plan | project_plan | 176 | 259 |  | Post installation Steps |  |  | Wed 2/25/26 | Tue 3/3/26 | Tue 3/3/26 | 100% | Complete | 258 | No | No | 259 | cc1c372b8eae54e1e7ae038efc821cb7d9648ba87ab3fe15ba612c005d8b7b53
project_plan | project_plan | 177 | 260 |  | Activate BC Sets |  |  | Wed 3/4/26 | Thu 3/5/26 | Thu 3/5/26 | 100% | Complete | 259 | No | No | 260 | 84ea9a3a4ebb3382c641d2cdf64f91de7a2ddce3684f859f780f6dda39c8b116
project_plan | project_plan | 178 | 261 |  | Connector configuration (S4 / LDAP Connector) |  |  | Fri 3/6/26 | Thu 3/12/26 | Thu 3/12/26 | 100% | Complete | 260 | No | No | 261 | fc67e7a76e1cafa72b18f8db6f8a4e295687a035e9c9b68a02518562b6191d94
project_plan | project_plan | 179 | 262 |  | Initial configuration [GRC Parameter/Business Process/Sub Process and system Configuration] |  |  | Fri 3/13/26 | Fri 3/20/26 | Fri 3/20/26 | 100% | Complete | 261 | No | No | 262 | 9d3d144f78f18746ae3c0ef46ff29e92fc51f1c420798a88709ee1a592fe77f1
project_plan | project_plan | 180 | 263 |  | Transport setup |  |  | Mon 3/23/26 | Mon 3/23/26 | Mon 3/23/26 | 100% | Complete | 262 | No | No | 263 | 5ce60066dd2cd8c2ddaf8119d0efb2ad463d9dc23ce8d22eae3623c1079fde6c
project_plan | project_plan | 181 | 264 |  | Workflow setup |  |  | Tue 3/24/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete |  | No | No | 264 | f7adff457cfacda2a3b156f9280bdd42f03be23eff569bb5775178a067c72345
project_plan | project_plan | 182 | 265 |  | MSMP workflow configuration |  |  | Tue 3/24/26 | Mon 3/30/26 | Mon 3/30/26 | 100% | Complete | 263 | No | No | 265 | 05f091f13ebc03fa0effd2822438da0ec66f0501a618135c19b646757c9bd253
project_plan | project_plan | 183 | 266 |  | BRF+ decision tables |  |  | Tue 3/31/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 265 | No | No | 266 | 7ec7425572acd1191106d2039c4d7abebbf67820d80b9e8329fefb3ba2e32107
project_plan | project_plan | 184 | 267 |  | Rule Set & Role Design |  |  | Thu 3/13/25 | Thu 5/21/26 | Wed 12/10/25 | 77% | Complete |  | No | No | 267 | b2e83a7158bb2e044dba9320fde283d2f8c117617d12a869e117be4ebaeb8912
project_plan | project_plan | 185 | 268 |  | Extract the default Global Ruleset from SAP |  |  | Tue 9/2/25 | Fri 9/5/25 | Fri 9/5/25 | 100% | Complete |  | No | No | 268 | 39630720f93b0716be703a9503beaccbfaa0c8f70b6bfa48eec9c37d77dcac38
project_plan | project_plan | 186 | 269 |  | Extract SU24 Details of transactions from global ruleset and Custom Transactions |  |  | Mon 9/8/25 | Tue 9/16/25 | Tue 9/16/25 | 100% | Complete | 268 | No | No | 269 | a91af0715200fb5c30f21fe439d05d73f268fb93287a38647ddbc67b4bdce316
project_plan | project_plan | 187 | 281 |  | Prepare/Share the Ruleset Draft with all the functional leads for inputs |  |  | Wed 9/17/25 | Wed 9/24/25 | Wed 9/24/25 | 100% | Complete | 269 | No | No | 281 | a2a67769c5a991838f83ca586120b4272078dcebbf76c608588fdbc2edd4bc94
project_plan | project_plan | 188 | 282 |  | Schedule workshops to collect complete details of ruleset module wise and close the gaps |  |  | Thu 9/25/25 | Thu 10/30/25 | Thu 10/30/25 | 100% | Complete | 281 | No | No | 282 | 6d829b161bd19dd38bf0b860dcf6f81eeec70083b1f60a964abb07ed8815c419
project_plan | project_plan | 189 | 283 |  | Final Review Rule Set and update the recommendations |  |  | Fri 10/31/25 | Mon 5/4/26 | Wed 11/5/25 | 60% | Late | 282 | No | No | 283 | fde2aac8fe3bfef7a93832400762e98e643afa30bfc63c84f03cb22c8696926b
project_plan | project_plan | 190 | 284 |  | Import rulesets into system |  |  | Thu 11/6/25 | Tue 11/11/25 | Tue 11/11/25 | 100% | Complete | 283 | No | No | 284 | 0b38aee1c6ac58302c3d108ef5b2f6775872c54de4d1941633b55a880a520bae
project_plan | project_plan | 191 | 303 |  | RCM Development |  | Controlling Team | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 303 | 9cb8835b6b4241dc8725f28f4440bad6f2b824c9f85b26c226de44901d0c17b7
project_plan | project_plan | 192 | 285 |  | Setup Mitigation controls |  |  | Wed 11/12/25 | Wed 11/19/25 | Wed 11/19/25 | 100% | Complete | 284 | No | No | 285 | a26d9c4825b1e439949aa207c79ddc9c9d2b1cbd0f1dce9417f87976325c2533
project_plan | project_plan | 193 | 286 |  | Risk analysis on existing roles |  |  | Fri 5/1/26 | Thu 5/7/26 | Wed 11/26/25 | 0% | Late | 285 | No | No | 286 | eb8aaf80b0cb7284d28a8ff25f35254f22a96421d7796b925debfbb87a3ddfbb
project_plan | project_plan | 194 | 270 |  | Role remediation planning - Can impact role design & Possible of retesting. |  |  | Fri 5/8/26 | Thu 5/21/26 | Wed 12/10/25 | 0% | Future Task | 286 | No | No | 270 | 764451724d357c11d5151abe7fd67f09b8afa20429e6fd494751dfcf0261e320
project_plan | project_plan | 195 | 271 |  | Business Role Management |  |  | Fri 5/8/26 | Thu 5/21/26 | Wed 12/10/25 | 0% | Future Task |  | No | No | 271 | 92d425e48a30efa7ad38bd0cb255eabe1fa0c1cd2765658ccfb9fc3fbd084cdf
project_plan | project_plan | 196 | 272 |  | Role Mapping with Business Process and Sub-Process /Functional Area |  |  | Fri 5/8/26 | Thu 5/14/26 | Wed 12/3/25 | 0% | Future Task | 286 | No | No | 272 | 135598375ba0f1e706812475e35567265422167b6937f8cd5d930daa6b74798f
project_plan | project_plan | 197 | 273 |  | Role Upload to SAP GRC |  |  | Fri 5/15/26 | Thu 5/21/26 | Wed 12/10/25 | 0% | Future Task | 272 | No | No | 273 | e8128f999b58e89592ec22a78f9d949a1abacb3e862f6f94a4156f82694270b4
project_plan | project_plan | 198 | 274 |  | Firefighter Configuration |  |  | Fri 5/1/26 | Thu 5/21/26 | Fri 11/7/25 | 0% | Late |  | No | No | 274 | c233d0ecf7f216e54b2ff3edae8e0118f00f4882000b6c16b8e1d8a82fbdbb0e
project_plan | project_plan | 199 | 275 |  | Firefighter ID setup |  |  | Fri 5/1/26 | Thu 5/7/26 | Fri 10/24/25 | 0% | Late |  | No | No | 275 | b4524b600b8c6b9668234498ae9a1900758765d03b296e74514b5cea7f102c48
project_plan | project_plan | 200 | 276 |  | Firefighter log settings |  |  | Fri 5/8/26 | Thu 5/14/26 | Fri 10/31/25 | 0% | Future Task | 275 | No | No | 276 | 774cbb73bc27defb8d4c6ddca26d5c9a273f5359818528caa569bc35dc76e56c
project_plan | project_plan | 201 | 277 |  | Functional validation |  |  | Fri 5/15/26 | Thu 5/21/26 | Fri 11/7/25 | 0% | Future Task | 276 | No | No | 277 | 8c2b3681ddf9b3f95b3704026e372e38d399ced57143afcac9b7cd7486b179d5
project_plan | project_plan | 202 | 278 |  | Testing & Training |  |  | Fri 5/1/26 | Wed 8/5/26 | Thu 2/12/26 | 0% | Late |  | No | No | 278 | 24d5e5ae8b5554b0a223871ce0e0329239075e27fcf8a85940e40de31b87dca9
project_plan | project_plan | 203 | 279 |  | Unit testing |  |  | Fri 5/1/26 | Wed 5/13/26 | Thu 11/20/25 | 0% | Late |  | No | No | 279 | d13d4b8d971ad330e60529d632c23fba316f446fa3eadfbacc85a711a47f48f5
project_plan | project_plan | 204 | 280 |  | Changes moved to Test System |  |  | Thu 5/14/26 | Mon 5/18/26 | Tue 11/25/25 | 0% | Future Task | 279 | No | No | 280 | 242c555d244289bbadad33d4260e42760290e42923aaab584cff519baee62f16
project_plan | project_plan | 205 | 287 |  | Connector configuration (S4 / LDAP Connector) |  |  | Tue 5/19/26 | Thu 5/21/26 | Fri 11/28/25 | 0% | Future Task | 280 | No | No | 287 | 824d3e33613a27fa6d274dc978572c9e30fd76b1ba1cf797e2147196692425e5
project_plan | project_plan | 206 | 288 |  | Workflow Activation / Data load in Test System |  |  | Fri 5/22/26 | Thu 5/28/26 | Fri 12/5/25 | 0% | Future Task | 287 | No | No | 288 | e9567842db46d9449c3fd2ba26d24fc956dde72c830b32d31d44774110c68ece
project_plan | project_plan | 207 | 289 |  | Integration testing - Smoke Test |  |  | Fri 5/29/26 | Wed 6/10/26 | Thu 12/18/25 | 0% | Future Task | 288 | No | No | 289 | 69e650c0e5391e134ac3967f084162715eff0059de17856f73123fc6c9394144
project_plan | project_plan | 208 | 290 |  | UAT (User Acceptance Testing) - ITC-3 - with roles |  |  | Thu 6/11/26 | Thu 7/2/26 | Fri 1/9/26 | 0% | Future Task | 289 | No | No | 290 | affa41ba4ef108970f461f3cd3da2edc58a25009cc176362409e5f91cccc186a
project_plan | project_plan | 209 | 291 |  | Issue resolution |  |  | Fri 7/3/26 | Thu 7/16/26 | Fri 1/23/26 | 0% | Future Task | 290 | No | No | 291 | 9a0b2aa86624f8f870ff03008e0269b589c21d07563842efc38d37f09841915a
project_plan | project_plan | 210 | 292 |  | End-user training |  |  | Fri 7/17/26 | Fri 7/24/26 | Mon 2/2/26 | 0% | Future Task | 291 | No | No | 292 | 7896252b03579150e31abad9bf9752490a8e48f529347e4e67ac52ac7ff845b9
project_plan | project_plan | 211 | 293 |  | Initiate Preparation of Cutover Plans |  |  | Mon 7/27/26 | Wed 8/5/26 | Thu 2/12/26 | 0% | Future Task | 292 | No | No | 293 | 28d7e805d30cdcf08861bb37a340f6bf7a6c798ea761449519ab3fc9cc578a65
project_plan | project_plan | 212 | 294 |  | Go-Live |  |  | Thu 10/1/26 | Thu 10/22/26 | Thu 1/22/26 | 0% | Future Task |  | Yes | No | 294 | 57a2aa68eccc0f39c6ad7f414317930e70c4e1d4fa9a00d28786181b6be2259b
project_plan | project_plan | 213 | 297 |  | Production deployment |  |  | Thu 10/1/26 | Fri 10/9/26 | Fri 1/9/26 | 0% | Future Task | 3367 | Yes | No | 297 | eb196534f50945f7edcb0a4c456791c89acb21e2e0aed721be9b906bc9a0d325
project_plan | project_plan | 214 | 295 |  | Execution of Cutover Plan(Business and Technical) |  |  | Thu 10/1/26 | Fri 10/9/26 | Fri 1/9/26 | 0% | Future Task | 297SS | No | No | 295 | dc3ae04b8a61068c18d77d0a6819c0056a351a562e24e7a44ab0c847e8a79d5a
project_plan | project_plan | 215 | 296 |  | Final risk analysis |  |  | Mon 10/12/26 | Tue 10/20/26 | Tue 1/20/26 | 0% | Future Task | 295 | No | No | 296 | fc4da3d3adad2e921482fcf168242f046eea32e597e8958db0326a7ef40fa828
project_plan | project_plan | 216 | 298 |  | Go-live (Technical) |  |  | Wed 10/21/26 | Thu 10/22/26 | Thu 1/22/26 | 0% | Future Task | 296 | No | No | 298 | 7a0e24ebe0e11e98745bf0ad1e5c5dd98636c065bb71b890b0d0c355cd26e92e
project_plan | project_plan | 217 | 24 |  | Functional Build Tasks |  |  | Mon 4/7/25 | Thu 9/18/25 | Thu 9/18/25 | 100% | Complete |  | No | No | 24 | 1bc7437848d3e986e48e483c5d837032694767a8dd4a0343053775c0fd0920c6
project_plan | project_plan | 218 | 25 |  | BPD Development / Configuration Specs |  |  | Mon 4/7/25 | Thu 9/18/25 | Thu 9/18/25 | 100% | Complete |  | No | No | 25 | 1b2b960e7ae54200813d7fc29ab9ca0e2536c150a3bf0849da0344eab7598a67
project_plan | project_plan | 219 | 56 |  | Master Data |  |  | Mon 6/16/25 | Thu 9/4/25 | Thu 9/4/25 | 100% | Complete |  | No | No | 56 | eddfe9fe2487172d5f144490fa032c78b41dc74a6c2b0271ac54d8d1f0295f41
project_plan | project_plan | 220 | 57 |  | In Draft |  |  | Mon 6/16/25 | Tue 7/15/25 | Tue 7/15/25 | 100% | Complete |  | No | No | 57 | 3e01cfafaa36e9350f20025ff4d940c8bce37b76b8b4bff2470b66b1efd3ee31
project_plan | project_plan | 221 | 58 |  | Complete - Ready for Security Review |  |  | Mon 7/7/25 | Fri 8/15/25 | Fri 8/15/25 | 100% | Complete |  | No | No | 58 | 7d97cd3875e1c125c60df990b9db976174d186623588612b131b10fe9f5e3c7f
project_plan | project_plan | 222 | 133 |  | Complete - Audit and Controls Review |  |  | Mon 8/18/25 | Thu 9/4/25 | Thu 9/4/25 | 100% | Complete | 58 | No | No | 133 | a72f677bd7a706d6c11a813024ef57424fb9de8d392c337f277555e881ea04f3
project_plan | project_plan | 223 | 26 |  | Finance |  |  | Mon 4/7/25 | Thu 8/28/25 | Thu 8/28/25 | 100% | Complete |  | No | No | 26 | ab705aa174242502f03b7355e75d6f9e7a6089dd0276ad14ae48c45d2486327e
project_plan | project_plan | 224 | 31 |  | In Draft |  |  | Mon 4/7/25 | Fri 6/27/25 | Fri 6/27/25 | 100% | Complete |  | No | No | 31 | 7282a14cc38cd1d9ff857cb54173c2aadbc1cac4b20b3aa272f901667ed16737
project_plan | project_plan | 225 | 32 |  | Complete - Ready for Security Review |  |  | Mon 4/21/25 | Fri 8/8/25 | Fri 8/8/25 | 100% | Complete |  | No | No | 32 | 8519e5fbbcf9c3d95f5392c4d205e5ef9187d120e14d82c11510723e373e0080
project_plan | project_plan | 226 | 134 |  | Complete - Ready for Audit and Controls Review |  |  | Mon 8/11/25 | Thu 8/28/25 | Thu 8/28/25 | 100% | Complete | 32 | No | No | 134 | 3047dc6dea2f27b21811e3e08dd8754ce346cafaf31446d12c046dec0a6501c9
project_plan | project_plan | 227 | 27 |  | Plan to Make |  |  | Tue 4/8/25 | Thu 9/4/25 | Thu 9/4/25 | 100% | Complete |  | No | No | 27 | 295ca0fed74cd24fd6fc6cde6d7ab7975d5f6d380a0779552b43562e966d07e5
project_plan | project_plan | 228 | 33 |  | In Draft |  |  | Tue 4/8/25 | Mon 7/21/25 | Mon 7/21/25 | 100% | Complete |  | No | No | 33 | 5fcccb42fb9cf9d78659b33b2fe7ae1996e08c02e267fffcfd12b55bdcbf4857
project_plan | project_plan | 229 | 34 |  | Complete - Ready for Security Review |  |  | Mon 4/21/25 | Fri 8/15/25 | Fri 8/15/25 | 100% | Complete |  | No | No | 34 | 3bfd0577fa2f6a2504793a21ad0de72cd247139fb8cdd0a4a5d47f8870416c63
project_plan | project_plan | 230 | 135 |  | Complete - Ready for Audit and Controls Review |  |  | Mon 8/18/25 | Thu 9/4/25 | Thu 9/4/25 | 100% | Complete | 34 | No | No | 135 | a12fd163688598796a8713e6f56975882ded222e150795266d42d6a2bebae203
project_plan | project_plan | 231 | 28 |  | Procure to Pay |  |  | Mon 4/7/25 | Thu 9/18/25 | Thu 9/18/25 | 100% | Complete |  | No | No | 28 | dfa4b1d425fcbcad98eecb554f31ba2ffe4f51bdf78cbbe91e9dba060eda5bd9
project_plan | project_plan | 232 | 35 |  | In Draft |  |  | Mon 4/7/25 | Mon 8/18/25 | Mon 8/18/25 | 100% | Complete |  | No | No | 35 | 128a26bc611c6a5c6d1e151110f71a1e0d7b7d9d947d7012b012c8a46cab2821
project_plan | project_plan | 233 | 36 |  | Complete - Ready for Security Review |  |  | Mon 4/21/25 | Fri 8/29/25 | Fri 8/29/25 | 100% | Complete |  | No | No | 36 | 3f101861af3f944cdcb927e48bba7de32a83ad50816310ae703a89ce270e6621
project_plan | project_plan | 234 | 136 |  | Complete - Ready for Audit and Controls Review |  |  | Mon 9/1/25 | Thu 9/18/25 | Thu 9/18/25 | 100% | Complete | 36 | No | No | 136 | 6d29249b5c6ddd47d4bfe8d434a664e81b81118a287e799c52cc6b3574b89970
project_plan | project_plan | 235 | 29 |  | Order to Cash |  |  | Mon 4/7/25 | Thu 8/21/25 | Thu 8/21/25 | 100% | Complete |  | No | No | 29 | 3e1281c7c7fc29a567f095c62c7e36476a119431af0e25ca54d59c90c5ebcbbf
project_plan | project_plan | 236 | 37 |  | In Draft |  |  | Mon 4/7/25 | Mon 7/21/25 | Mon 7/21/25 | 100% | Complete |  | No | No | 37 | 8b06164107b401d6ae33b422e4a1e8e8516e053a3df0a413df05bb9c00b98379
project_plan | project_plan | 237 | 38 |  | Complete - Ready for Security Review |  |  | Mon 4/21/25 | Fri 8/1/25 | Fri 8/1/25 | 100% | Complete |  | No | No | 38 | 1f95764f96da29094742021a5f5a6fea8481fc64a1cdc5a291a453e5d8561e71
project_plan | project_plan | 238 | 137 |  | Complete - Ready for Audit and Controls Review |  |  | Mon 8/4/25 | Thu 8/21/25 | Thu 8/21/25 | 100% | Complete | 38 | No | No | 137 | d9137d2196e397a844de602fddd146ab8458ad0e6200a59b55fd4edc544f1f02
project_plan | project_plan | 239 | 55 |  | RICEFW Development Tasks (RICEFW Tracker) |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 55 | bc67e33b488ed44dbac045601c634a442db7880dfb89cd1750f3491bad923e4b
project_plan | project_plan | 240 | 59 |  | Finance and Controlling |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 59 | 1e7b1022cbfcf9bdb5c92b7f1241ea5f7e0676cd8ac4d868ad127d75ebeb6613
project_plan | project_plan | 241 | 60 |  | Specs Completed |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 60 | c352d444ceffc3d4df1fde894dfbb943b985c7e5391c1c918a0ee3eb1dc688f9
project_plan | project_plan | 242 | 61 |  | Specs Assigned to Developer |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 61 | c0291e78b1eb7bcf6bbd7df83afe098e21079572e4b3cc47266e0830a208fafb
project_plan | project_plan | 243 | 71 |  | Testing Complete |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 71 | 95b200add4b2a66bff75eb28711aa33536f43eec9eee12beda02d8126db4db99
project_plan | project_plan | 244 | 72 |  | Assigned to Testing Cycle |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 72 | ab466c185bd4fa1ba69ae7fa8f3e5600fdf25961a0aece00d56f1a2e9822723f
project_plan | project_plan | 245 | 62 |  | Plan to Make |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 62 | 7d5162fb4207e9a0de17ea44652d2d0e53d4cf6794a4e8984d0640dd009f16c2
project_plan | project_plan | 246 | 73 |  | Specs Completed |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 73 | 899174154b6ee643f06779856fececccd2dc9a314b0802210d3644907f3c236d
project_plan | project_plan | 247 | 74 |  | Specs Assigned to Developer |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 74 | cfdc4000423bff2cd5d554278606b5946a6106496000b66c941e2a58e8d2917e
project_plan | project_plan | 248 | 75 |  | Testing Complete |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 75 | 54ec00dfbb31813bed7da4d300e11e76dc2e1faf3d871c9fdf7946a8daba039a
project_plan | project_plan | 249 | 76 |  | Assigned to Testing Cycle |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 76 | 1eb6c3dfcdba7684431deaf3c623a0693630a80f46ac6cac675c5fd250480139
project_plan | project_plan | 250 | 65 |  | Procure to Pay |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 65 | 826955e2eba13cb73784327f0e5c21eda4d925304f34175c5f3455ff06b1ad7d
project_plan | project_plan | 251 | 77 |  | Specs Completed |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 77 | 3cef37954a79ee70a4511aa88d74722dcfb0051c43b313ddc0de9585130df44d
project_plan | project_plan | 252 | 78 |  | Specs Assigned to Developer |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 78 | 09e5d02956d66a1f9dc62bca28d1d0a47df11096b9f624d5dbfa3d60bf932907
project_plan | project_plan | 253 | 79 |  | Testing Complete |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 79 | 808b56b91a959611d46566e2e22ff7597dcd4bc7b2396c89fddd4483f5d8b4ae
project_plan | project_plan | 254 | 80 |  | Assigned to Testing Cycle |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 80 | c7c1845635eaf070f3b2a7f662d5ba4633d9521f61e9e6555b2993b71bdaeb65
project_plan | project_plan | 255 | 68 |  | Order to Cash |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 68 | 273c7787a0bcae1cff81952eeff82bb5d0358627d124e67ceaacdddf490705df
project_plan | project_plan | 256 | 81 |  | Specs Completed |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 81 | 137c05d90ad7c48aa1c6e806824f23bfdbb5dd8c350f43a8a107f0d03dd89c59
project_plan | project_plan | 257 | 82 |  | Specs Assigned to Developer |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 82 | a6503b3c15093b60fa0c5de2abe0f41aeb3166ff171b68d71cfc99c08ea6f14c
project_plan | project_plan | 258 | 83 |  | Testing Complete |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 83 | 27b4477970bcb7e94fad69152b1ef8ef4713bd10fd741629382ce7bcfe7775e1
project_plan | project_plan | 259 | 84 |  | Assigned to Testing Cycle |  |  | Thu 3/13/25 | Thu 3/13/25 | Thu 3/13/25 | 100% | Complete |  | No | No | 84 | 3d2d8f2a6f07e97f2c553ea238315351272bb18da758934243019b111a2da525
project_plan | project_plan | 260 | 682 |  | Data Readiness |  |  | Mon 4/6/26 | Mon 10/12/26 | Tue 4/21/26 | 20% | On Schedule |  | Yes | No | 682 | 5a6269e31113a35664a61ef5d503cd8a6c96bc2e65d03ba353dda95cbfee9c64
project_plan | project_plan | 261 | 425 |  | ITC1 Data Load Tasks QS5 |  |  | Mon 4/6/26 | Thu 4/23/26 | Tue 4/21/26 | 100% | Complete |  | No | No | 425 | b8a4a3311835f768819ab05ac97f5be2a21f51450d5eab89354c4be31fedb470
project_plan | project_plan | 262 | 956 |  | PMO Authorization to Start Data Loads |  | Mark George | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete |  | No | No | 956 | 0c363a7a11b8590bc83482bf33cf8016ecf0ed4c402a716f0f6c95b9993cb2de
project_plan | project_plan | 263 | 755 |  | RTR_CM02_Profit Center Hierarchy |  |  | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete |  | No | No | 755 | 3420ba9690d0d0c82466b1b2e79d46f8281cfb95c4a3ba3e3d2807b36903f61a
project_plan | project_plan | 264 | 777 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 956 | No | No | 777 | d0f1bfdacfe803280c4e988dc416c34adcf02f2df66bf6b308825d8f67fc4d5c
project_plan | project_plan | 265 | 780 |  | Load |  | Kasey Hughes | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 777 | No | No | 780 | ac8a9ec13a7ea72783b94afa9955a43ce192d3f3979b8730849f92c440ee78ac
project_plan | project_plan | 266 | 781 |  | Post Load Validation |  | Kasey Hughes | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 780 | No | No | 781 | 162399dfa8e6f2f932d70eca2f5c1f53b722887d54f965729b4b7e9c55ba200a
project_plan | project_plan | 267 | 756 |  | RTR_CM03_Cost Center Hierarchy |  |  | Mon 4/6/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 755 | No | No | 756 | 353fe81c62c79160ca3835e7c944d981bad8d37ad4b8e87a6bbc538bbc440b2c
project_plan | project_plan | 268 | 783 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 781 | No | No | 783 | 0589031505c04120adf3369b75c7c5e55bc92ce73bd2fd88685805b8fcf30f14
project_plan | project_plan | 269 | 786 |  | Load |  | Kasey Hughes | Mon 4/6/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 783 | No | No | 786 | c1780d12045d00ffef3da046013c8ad8f83314623b2786a657427dfb6ce6c355
project_plan | project_plan | 270 | 787 |  | Post Load Validation |  | Kasey Hughes | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 786 | No | No | 787 | b85ab99d04aa0aac20eaa02b8f1ff1d28fedaa9b61b20a7a54f9a7c1f9026e4c
project_plan | project_plan | 271 | 740 |  | RTR_CM01_GL_Account_Master to CC 1000 |  |  | Tue 4/7/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 756 | No | No | 740 | 8c1584bd75a44aa66a463e322d933886b74aed7dff06185ab409ef097ea7c461
project_plan | project_plan | 272 | 958 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 787 | No | No | 958 | 022255998b5deb3be64b290920b0bee7cb2d4288bd12c8da2a5363d774a2d87a
project_plan | project_plan | 273 | 773 |  | Pre Load Validation |  | Kasey Hughes | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 958 | No | No | 773 | e38a0fbcbadba44aaba7393cf1d1429baa3365db6191c51df12c2e85af785317
project_plan | project_plan | 274 | 774 |  | Simulate Load |  | Data Migration Team | Tue 4/7/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 773 | No | No | 774 | 196b5cf74e8c52982c67ac3ebb33f09fb75db6e0692ab5abc049fb1475370b5a
project_plan | project_plan | 275 | 775 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 774 | No | No | 775 | 94efccba71880d4a32f3aadd7ace521225f0277f28ee0f29777607c03a75e05e
project_plan | project_plan | 276 | 795 |  | Load |  | Data Migration Team | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 775 | No | No | 795 | 60f603ffd2995cbb14d1ec4a26b94fd54d978fd75394accf88de9b6a77dedf17
project_plan | project_plan | 277 | 776 |  | Post Load Validation |  | Kasey Hughes | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 795 | No | No | 776 | 3d5688ad0e8b6ae63555900169b89af30df5b5b76c7c4710e2634fc00c64c499
project_plan | project_plan | 278 | 1243 |  | Extend GL to all Company Codes |  | Kasey Hughes | Wed 4/8/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 776 | No | No | 1243 | 202e7cb19d1f9499dd08f169868f10a336e08c86204b8b070a7b6175a7f7d52e
project_plan | project_plan | 279 | 1244 |  | Post GL Extention Validation |  |  | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 1243 | No | No | 1244 | 13d7566d35c7d937573fb851413c2e36969774278a11b1aaf866a2aa39906f76
project_plan | project_plan | 280 | 759 |  | RTR_CM05_Profit_Center |  |  | Mon 4/6/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 740 | No | No | 759 | a3f3939fab9a81073321bb79e6567846ae2a0bf583d4352b9e5a01d8f20ff03f
project_plan | project_plan | 281 | 802 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 781 | No | No | 802 | 7159e193a36e1c4cfd5272f4137519d27761ebde1d38520dd44501ec4b7b6d8b
project_plan | project_plan | 282 | 803 |  | Pre Load Validation |  | Kasey Hughes | Mon 4/6/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 802 | No | No | 803 | a7e565b0828792f7fd39f04ba9623774631f79020502bcdc5f58221692333d77
project_plan | project_plan | 283 | 804 |  | Simulate Load |  | Data Migration Team | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 803 | No | No | 804 | 04ff30ad259d49b36094f00e8d72b90fbc31baef7e4a5192f980472b2c6778a8
project_plan | project_plan | 284 | 805 |  | Error and Defect Mitigation |  | Kasey Hughes | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 804 | No | No | 805 | 57a715a89c7fd2a226842c29c035e2cbc84f6569b0798123ca4a1542963ec27e
project_plan | project_plan | 285 | 806 |  | Load |  | Data Migration Team | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 805 | No | No | 806 | c0f3ff5cd2384733808b1545c42980a8b1ea369be71aaf6b7b81a9afb39283d3
project_plan | project_plan | 286 | 807 |  | Post Load Validation |  | Kasey Hughes | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 806 | No | No | 807 | f6c56d64c0632055fdd7ca36b32b2940e924275a62f282fcb76124e8c8c90d55
project_plan | project_plan | 287 | 767 |  | RTR_CM04_Cost_Center |  |  | Tue 4/7/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 759 | No | No | 767 | 3e15d5bc6dbfbdc19cc902a9db10bca5d18db0123e0ef71dc93b6376862e24a1
project_plan | project_plan | 288 | 959 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 4/7/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 807 | No | No | 959 | 8b3fb0f015266716050b27c1b70f464200a8c659e00bdb1f9d5215ce153f99cb
project_plan | project_plan | 289 | 960 |  | Pre Load Validation |  | Kasey Hughes | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 959 | No | No | 960 | 9d7ecfc2f13ebb25d91643d7b5153079f9f36d615e8afdc5d1a6c1e8bde1a1af
project_plan | project_plan | 290 | 961 |  | Simulate Load |  | Data Migration Team | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 960 | No | No | 961 | c4c03c47a31959d3f4604dbc708c901befe7460e3a7c9be09e90cff388755705
project_plan | project_plan | 291 | 962 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 961 | No | No | 962 | 2936eaeb4881da5752d7eb9ea69658b9c46ee8fd054746c284e80de8534b868e
project_plan | project_plan | 292 | 963 |  | Load |  | Data Migration Team | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 962 | No | No | 963 | 7a497c988ca841daacef49d6e7d0699b9b79659385f9fac3d5c4afbc1a044155
project_plan | project_plan | 293 | 964 |  | Post Load Validation |  | Kasey Hughes | Wed 4/8/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 963 | No | No | 964 | aea4a4a45448f47ed218da0bef7e99b357e9dcdc0aef05f33772779930b68e18
project_plan | project_plan | 294 | 881 |  | Manual Configuration Activities in QS5 |  |  | Mon 4/6/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 767 | No | No | 881 | 50d45981eaa0f2357d9d7fcadc22ac738fb8ce187c6cfb430111415eeb32d6f6
project_plan | project_plan | 295 | 1219 |  | Open Client |  | Basis | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete |  | No | No | 1219 | 6e6d4e9528ae85b2277f0497a9c5984d36ec3fe59e6fd376e04916ba39100869
project_plan | project_plan | 296 | 882 |  | Service Enterprise Setup |  | Keith Riley | Wed 4/8/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 740,755,756 | No | No | 882 | 0751d9ae790542647be886c57203b3e4a475991c295b1885e1a8b8bbd3524b2e
project_plan | project_plan | 297 | 1220 |  | Close Client |  | Basis | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete |  | No | No | 1220 | fd54d03045288639e1b1a23f61a685bbe9bb9a1086ee181b7c0669efe6bc1b93
project_plan | project_plan | 298 | 883 |  | Intercompany Business Partner Setup |  | Functional Leads | Wed 4/8/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 7,557,561,244 | No | No | 883 | f099e9ca22f095261c1e8b99a805aae558527d1af4bb029e8c260f8e73b192d4
project_plan | project_plan | 299 | 760 |  | RTR_CM09_Activity_Type |  |  | Wed 4/8/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 767 | No | No | 760 | 569260daca5c068a463dfa18ae83e249d1cf184f7a3c2a5bf03931066d8983c3
project_plan | project_plan | 300 | 808 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 776 | No | No | 808 | 146ff3057af3451d65f02f15745b69304767a16c810d8e56212a7adbe732cc66
project_plan | project_plan | 301 | 809 |  | Pre Load Validation |  | Kasey Hughes | Wed 4/8/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 808 | No | No | 809 | 42733b69d1876dd08e8d63e35b0c217090b56b3bd8456e744e3cfad6d89435e4
project_plan | project_plan | 302 | 810 |  | Simulate Load |  | Data Migration Team | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 809 | No | No | 810 | 54c3c8d5b0e2a1c76bf95d049fa86ce80584287ccfce169260cdcf4084c3ca97
project_plan | project_plan | 303 | 811 |  | Error and Defect Mitigation |  | Kasey Hughes | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 810 | No | No | 811 | 5664e3618e81653dd165c2d03feb53efeb5898c75f78b215ffce0f909946426a
project_plan | project_plan | 304 | 812 |  | Load |  | Data Migration Team | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 811 | No | No | 812 | 0362b8eeb4a114ffb32f21ab11688820df87ab71532270749edb104b03d24d9a
project_plan | project_plan | 305 | 813 |  | Post Load Validation |  | Kasey Hughes | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 812 | No | No | 813 | 089f68786559fd237e11ebd7ba2a33a86dc5e3f5af0d5b7eccb5787da9de0636
project_plan | project_plan | 306 | 753 |  | RTR_CM12_Activity Rates |  |  | Tue 4/7/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 760 | No | No | 753 | f40db22a3ef710d3c0e31194320ed39abf2bedce9d03e87f788ac5e4589e122e
project_plan | project_plan | 307 | 965 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 787 | No | No | 965 | 8e7e44cc0aaa381fc147405c4e71adf717eb1fa7457c819e94efae8cd2a4b116
project_plan | project_plan | 308 | 966 |  | Pre Load Validation |  | Kasey Hughes | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 965 | No | No | 966 | 8fadd11da87bdb5efdbb00bf51866fa19ba13b9da04a24d28e36816ced214129
project_plan | project_plan | 309 | 967 |  | Simulate Load |  | Data Migration Team | Tue 4/7/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 966 | No | No | 967 | 79558bb680054bfd77ad75f7b09ce9ec841e8ecded422e2574b018acb1fc982d
project_plan | project_plan | 310 | 968 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 967 | No | No | 968 | 75ae5e35f93b1bac10600cbfbac03864dd4dc5e0354e8be44e95d0f35f61166f
project_plan | project_plan | 311 | 969 |  | Load |  | Data Migration Team | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 968 | No | No | 969 | 3aac91ada09922a775aa60f63fc1095a5fe823eb2b40beac72170cd84bf7687a
project_plan | project_plan | 312 | 970 |  | Post Load Validation |  | Kasey Hughes | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 969 | No | No | 970 | cc65ceb8999eb408ebc1a5105d9dd783d3ce2ebec43fd2416636d6338c0778e7
project_plan | project_plan | 313 | 757 |  | RTR_CM06_Bank_master |  |  | Tue 4/14/26 | Thu 4/16/26 | Thu 4/9/26 | 100% | Complete | 753 | No | No | 757 | 6148a34e9c0f42e84387936bb1dbf7b7c0a83b7b93442f2353aaea8f7e70086a
project_plan | project_plan | 314 | 789 |  | Load File Staged and Posted "Ready" |  | Data Migration Team | Tue 4/14/26 | Tue 4/14/26 | Wed 4/8/26 | 100% | Complete | 776 | No | No | 789 | 4655513878ba250cf288105377df7013839b1dc5564bad35dc64af5dcca01b9f
project_plan | project_plan | 315 | 790 |  | Pre Load Validation |  | Kasey Hughes | Tue 4/14/26 | Tue 4/14/26 | Thu 4/9/26 | 100% | Complete | 789 | No | No | 790 | fb927310ba31da1d1e551cdcaa4c3fb276657fafcd63793f86d76aac95a74b31
project_plan | project_plan | 316 | 791 |  | Simulate Load |  | Data Migration Team | Wed 4/15/26 | Wed 4/15/26 | Thu 4/9/26 | 100% | Complete |  | No | No | 791 | a5bf59872d38387b375a6d28df7b674da894e3170432ae5d6b7597cab1b96ddf
project_plan | project_plan | 317 | 792 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 4/15/26 | Wed 4/15/26 | Thu 4/9/26 | 100% | Complete | 791 | No | No | 792 | c2c50d82fe777f1cf7bc95ce839a6c5c32fcbc6317e23c9c3f48e6d640cbeff6
project_plan | project_plan | 318 | 793 |  | Load |  | Data Migration Team | Wed 4/15/26 | Wed 4/15/26 | Thu 4/9/26 | 100% | Complete | 792 | No | No | 793 | 5ae4ed31fd33f2e5294cb254d90e2cf4549832d8ba27d73fc9ee49b2f3f7ca62
project_plan | project_plan | 319 | 794 |  | Post Load Validation |  | Kasey Hughes | Wed 4/15/26 | Thu 4/16/26 | Thu 4/9/26 | 100% | Complete | 793 | No | No | 794 | e7f8451e000822b1917b9e960ab77aa753680ff10addac0fa420e3656db94dd3
project_plan | project_plan | 320 | 758 |  | RTR_CM08_Exchange_Rates |  |  | Thu 4/9/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 757 | No | No | 758 | ea3ba44a3822bee83b3c6ce8dd5a00a7034afeadf8f53201fdbb1a4f84b7939e
project_plan | project_plan | 321 | 796 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 793 | No | No | 796 | a176da7a5a9287bdc904b04aed3ee8f1c935e4079d65896cb4468be87c953ae1
project_plan | project_plan | 322 | 797 |  | Pre Load Validation |  | Kasey Hughes | Thu 4/9/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 796 | No | No | 797 | 76dac9e2cad108ac450c14852b83094ec7a6ae15a0280bf02c5e0fc8a5274ae5
project_plan | project_plan | 323 | 798 |  | Simulate Load |  | Data Migration Team | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 797 | No | No | 798 | 6000defcd6150cd914d21aaaa6979fb5bae67cd9434fc646a45b0b9aab487cae
project_plan | project_plan | 324 | 799 |  | Error and Defect Mitigation |  | Kasey Hughes | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 798 | No | No | 799 | 1b201307dd8d6c53f8382fa3b66e023754bb727d202826a1838731ca2fabe44c
project_plan | project_plan | 325 | 800 |  | Load |  | Data Migration Team | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 799 | No | No | 800 | d839af8da91129f964153779c7a09bfdef7f5c24d376b5fb8df29670af31db61
project_plan | project_plan | 326 | 801 |  | Post Load Validation |  | Kasey Hughes | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 800 | No | No | 801 | a0b05e3badf3d205523faefb369dd0c0a2ad066d80a4ad1582e481db50afdd44
project_plan | project_plan | 327 | 761 |  | RTR_CM14_Cost Element_Group |  | Kasey Hughes | Wed 4/15/26 | Wed 4/22/26 | Wed 4/15/26 | 100% | Complete | 758 | No | No | 761 | 8c03c891aceb1aac5f47586e73b8dc6b25faee6fd3178814f876a0b7851561bc
project_plan | project_plan | 328 | 814 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Wed 4/15/26 | Wed 4/15/26 | Tue 4/14/26 | 100% | Complete | 776 | No | No | 814 | d1d40243daecc22847006244ae24f9da14846383c49fbed11a1a9c1c45372c87
project_plan | project_plan | 329 | 815 |  | Load |  | Kasey Hughes | Thu 4/16/26 | Tue 4/21/26 | Wed 4/15/26 | 100% | Complete | 814 | No | No | 815 | 76973e8db0e28aea7e9e72bdeeb2bb885b5c89e82b59294fa7bf8def41337db2
project_plan | project_plan | 330 | 816 |  | Post Load Validation |  | Kasey Hughes | Wed 4/22/26 | Wed 4/22/26 | Wed 4/15/26 | 100% | Complete | 815 | No | No | 816 | 119dd694a611b492e975ed1649189ff044266cfd6ff7f66eb85b2aa68be580a8
project_plan | project_plan | 331 | 764 |  | OTC_CM19_Customer_Master - Bill-To |  |  | Thu 4/16/26 | Thu 4/16/26 | Wed 4/16/25 | 100% | Complete | 761 | No | No | 764 | 451041822330fca51def9a4b2c51e074671fb7acb97b6684bac76346ff923909
project_plan | project_plan | 332 | 763 |  | OTC_CM19_Customer_Master - Ship-To |  |  | Wed 4/8/26 | Fri 4/10/26 | Mon 4/13/26 | 100% | Complete | 764 | No | No | 763 | c4aa699df13586360d8f86215078bd80eea5fb938a3df0fa68deb295c8ed450c
project_plan | project_plan | 333 | 823 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 776 | No | No | 823 | 5e804697d00c1b61fb0fe1b827a1fa5aa9d545476a6c3961bfcdcff45484094d
project_plan | project_plan | 334 | 824 |  | Pre Load Validation |  | Ric Haraida | Wed 4/8/26 | Wed 4/8/26 | Wed 4/8/26 | 100% | Complete | 823 | No | No | 824 | bc850066f7b69255b8caf368cc0be4c5e259befedf5102230cc0e4f679967d3e
project_plan | project_plan | 335 | 1231 |  | Open client for BP number range update |  | Basis | Wed 4/8/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 824 | No | No | 1231 | 2aab5fdc4cb686d6748b9549adbc089a3c856fb36377edf9fee8cb730a115703
project_plan | project_plan | 336 | 1232 |  | Update number range BP02 from Internal to External |  | Ric Haraida | Thu 4/9/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 1231 | No | No | 1232 | 058d0505314f72f1503c34e5260f72962c23f7fabfe9ca18e40dfaddf6e7ca08
project_plan | project_plan | 337 | 1233 |  | Close Client |  | Basis | Fri 4/10/26 | Fri 4/10/26 | Mon 4/13/26 | 100% | Complete | 1232 | No | No | 1233 | 154c26b62f3fd1b0d0d0c93079c82b1f8f65bd8ebd1ddb83c4d3b940d9de0dad
project_plan | project_plan | 338 | 825 |  | Simulate Load |  | Data Migration Team | Wed 4/8/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 824 | No | No | 825 | 644b9a592d38e4ece70e8eb6514ab241f469445d0dde609b0f4195a5cb964ad6
project_plan | project_plan | 339 | 826 |  | Error and Defect Mitigation |  | Ric Haraida | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 825 | No | No | 826 | ea79303f7afba47a08de85f05f6a60779ad618740faf46a9e07f2f853a42aa38
project_plan | project_plan | 340 | 827 |  | Load |  | Data Migration Team | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 826 | No | No | 827 | 04a530cca0e443f1c98e942b47cb0a890f05c78f810108b8650359a22644b308
project_plan | project_plan | 341 | 828 |  | Post Load Validation |  | Ric Haraida | Thu 4/9/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 827 | No | No | 828 | 578b65a56b6c645fb7667a330bebed3be3b4e71c10e803bc76a78bc7efa1bcf8
project_plan | project_plan | 342 | 762 |  | OTC_CM19_Customer_Master - Sold-To |  |  | Wed 4/8/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 763 | No | No | 762 | 227906c9c30f5c6d8381802ee8bbe86078d5fe97ddd3a63f007bea4b5f6b5111
project_plan | project_plan | 343 | 817 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Wed 4/8/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 824 | No | No | 817 | 6a982d9c844e5d7cd8eca7efe16b8b05e280cf82ec85982dc0ffccdd1f286940
project_plan | project_plan | 344 | 818 |  | Pre Load Validation |  | Ric Haraida | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 817 | No | No | 818 | 2db2c00267605af06d3c62da950eb3d6df0348c8ec6d4b3c002492c656ff6d3c
project_plan | project_plan | 345 | 819 |  | Simulate Load |  | Data Migration Team | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 8,251,244 | No | No | 819 | d64bb272fddc53d511b9ab6b23c53a10eb1abbd861e0890f4587fbfc403c7102
project_plan | project_plan | 346 | 820 |  | Error and Defect Mitigation |  | Ric Haraida | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 819 | No | No | 820 | 022865ee7d6ab5dd4747358aa76b655bc00e917302687c6cbe675e3465988a7c
project_plan | project_plan | 347 | 821 |  | Load |  | Data Migration Team | Thu 4/9/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 820 | No | No | 821 | 941b6debc0c2e634a043b78e965f303f8ae80e723fd39cdfcfb4eed0d43b52a1
project_plan | project_plan | 348 | 822 |  | Post Load Validation |  | Ric Haraida | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 821 | No | No | 822 | 05b8d797dcf9369154ecc27e329938cb295876f4dac1badf7dfeced4294a3ec2
project_plan | project_plan | 349 | 1240 |  | Open client for BP number range update |  | Basis | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 825 | No | No | 1240 | 535de8cb7b04f2098d37bfb3597438db58aebe4ef86ebc7fc90952564276bf96
project_plan | project_plan | 350 | 1241 |  | Update number range BP02 from Internal to External |  | Ric Haraida | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 1240 | No | No | 1241 | 3ffff9fa542a7c7c2b8176541c28505953df53feed9d4626e078415420901c94
project_plan | project_plan | 351 | 1242 |  | Close Client |  | Basis | Thu 4/9/26 | Thu 4/9/26 | Thu 4/9/26 | 100% | Complete | 1241 | No | No | 1242 | 02177d19e1ebd53a12a66f8d74c0d55e3dc03e0b0760e50c628ae14ecf54603f
project_plan | project_plan | 352 | 765 |  | PTP_CM27_Vendor Master as Customer - FLCU01 |  |  | Fri 4/10/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 762 | No | No | 765 | 3c65fcd6d6aa07e80f163b9e329c4d46da6da2b7ed4a9d5ab614df11e07cd5ac
project_plan | project_plan | 353 | 972 |  | Extract File |  | Data Migration Team | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 821 | No | No | 972 | f843d457353ebe8e66209206155a10d2f4aa9b6d539a4ff1ed3dc79c6fa53c73
project_plan | project_plan | 354 | 973 |  | Pre Load Validation |  | Nevin Varkey | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 972 | No | No | 973 | 73070af184cd11b1d1fa0d82c0ec6d8befbd19299bd6cb2e477fe9a0170fc332
project_plan | project_plan | 355 | 974 |  | Simulate Load |  | Data Migration Team | Fri 4/10/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete | 973,794 | No | No | 974 | c3b3a285ff15e0684644d72283f6c2eaf59bd1e325c2bb98b6a0a1ee7a23ce64
project_plan | project_plan | 356 | 975 |  | Error and Defect Mitigation |  | Nevin Varkey | Fri 4/10/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 974 | No | No | 975 | e5eb30fa0570eff65b911f09c7993aad1c64ad5995a44cda447324cda332219e
project_plan | project_plan | 357 | 976 |  | Load |  | Data Migration Team | Fri 4/10/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 975 | No | No | 976 | 41c6993463abfced500f5a94dc6db0d539ab340ffead280704ea20e593c6be69
project_plan | project_plan | 358 | 977 |  | Post Load Validation |  | Nevin Varkey | Tue 4/14/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 976 | No | No | 977 | 2dce9a26a18b3a7e35b3351ab079b1a4cf22ccc85d009b9380a92c4670aa6af4
project_plan | project_plan | 359 | 771 |  | OTC_CM23_Customer_Hierarchy |  |  | Fri 4/10/26 | Wed 4/15/26 | Fri 4/10/26 | 100% | Complete | 765 | No | No | 771 | e626ef59a6454a6401da005367f62e6acf8178b9f6e918afbdf451c06ec04a90
project_plan | project_plan | 360 | 984 |  | Manual File Staged and Posted "Ready" |  | Ric Haraida | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 821 | No | No | 984 | 90e144f9a0d04e30d93e39f3064addc3e8e96d3ea5bc3b978601aef379557d2e
project_plan | project_plan | 361 | 985 |  | Load |  | Ric Haraida | Wed 4/15/26 | Wed 4/15/26 | Fri 4/10/26 | 100% | Complete | 984 | No | No | 985 | 231d0830a637ff550601dd995ceb0ca04f96df8c75bdb0b352565ea02b4e9d3d
project_plan | project_plan | 362 | 986 |  | Post Load Validation |  | Ric Haraida | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 985 | No | No | 986 | 87797fe38082abee2791ad23d75b78c349924e75b09058992c1aca5d95e6bf47
project_plan | project_plan | 363 | 766 |  | PTP_CM27_Vendor Master - Z001 - External Sales Rep |  |  | Fri 4/10/26 | Wed 4/15/26 | Mon 4/13/26 | 100% | Complete | 771 | No | No | 766 | 62afde2c0d9d5e406a232400315b94aa12cc63e120bf033d44aba2d690824d37
project_plan | project_plan | 364 | 987 |  | Extract File |  | Data Migration Team | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 821 | No | No | 987 | 729f8863aa13f8bd68cda9f227ae8da526c5bf73b021b4418e6710415cce4aaf
project_plan | project_plan | 365 | 988 |  | Pre Load Validation |  | Nevin Varkey | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 987 | No | No | 988 | 043158852ec80c797f4176dfdc11151f3d6888c2e0edbc5bee12a8790c357c9f
project_plan | project_plan | 366 | 989 |  | Simulate Load |  | Data Migration Team | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 988,794 | No | No | 989 | 077e23a23a7e3b3c80ff99bc17072d80ec99d48622afb73dc9d7989b962292e8
project_plan | project_plan | 367 | 990 |  | Error and Defect Mitigation |  | Nevin Varkey | Wed 4/15/26 | Wed 4/15/26 | Fri 4/10/26 | 100% | Complete | 989 | No | No | 990 | f17851676610eff451c96500a292819abed77afdf3a7e313cb214bd8e4c0bd65
project_plan | project_plan | 368 | 991 |  | Load |  | Data Migration Team | Fri 4/10/26 | Wed 4/15/26 | Mon 4/13/26 | 100% | Complete | 990 | No | No | 991 | 11571381164a693b15590f981f3244339a3ff338202bcd5b2d04bd0af6e5375f
project_plan | project_plan | 369 | 992 |  | Post Load Validation |  | Nevin Varkey | Wed 4/15/26 | Wed 4/15/26 | Mon 4/13/26 | 100% | Complete | 991 | No | No | 992 | 4b99e5eac207190f91166a0f2a64a7bb8bccd937c01040e759ffa30ae4d9b53c
project_plan | project_plan | 370 | 768 |  | RTR_CM10_Credit_Management_Role |  |  | Fri 4/10/26 | Fri 4/17/26 | Mon 4/13/26 | 100% | Complete | 766 | No | No | 768 | ceb35e326d787bb97f5e63e5a738b195e3f5c4d905f243f34b7056fadc0f79fd
project_plan | project_plan | 371 | 993 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 821 | No | No | 993 | 21a585e35074df1491ec84819c402eb00bdffc2334a2d15d659d0c8ca27f2655
project_plan | project_plan | 372 | 994 |  | Pre Load Validation |  | Kasey Hughes | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 993 | No | No | 994 | 9e0c905e16682bf43fefea21a4056e6d243afdff1c247fd99234a96b80f6c636
project_plan | project_plan | 373 | 995 |  | Simulate Load |  | Data Migration Team | Fri 4/17/26 | Fri 4/17/26 | Fri 4/10/26 | 100% | Complete | 994 | No | No | 995 | 0006d0e8ad47ff14c4e888b89cfeecf1530fee26b51e591827c476921fc487b7
project_plan | project_plan | 374 | 996 |  | Error and Defect Mitigation |  | Kasey Hughes | Fri 4/17/26 | Fri 4/17/26 | Fri 4/10/26 | 100% | Complete | 995 | No | No | 996 | 45a343be39a56bda9abbe4eed4a04a8d9177c60fbd0b4b0c7a1c5cfd728cb41f
project_plan | project_plan | 375 | 997 |  | Load |  | Data Migration Team | Fri 4/17/26 | Fri 4/17/26 | Fri 4/10/26 | 100% | Complete | 996 | No | No | 997 | 5cd5ad41fa5d379627bb42ce62606c3ca041067b6fd3d359ccb399a610319b76
project_plan | project_plan | 376 | 998 |  | Post Load Validation |  | Kasey Hughes | Fri 4/17/26 | Fri 4/17/26 | Mon 4/13/26 | 100% | Complete | 997 | No | No | 998 | 48efa2139faac161f342c0b92c4062ef8c54ddde7ffc70cfcebddf4a81dc480c
project_plan | project_plan | 377 | 752 |  | PTP_CM27_Vendor Master |  |  | Fri 4/10/26 | Thu 4/16/26 | Wed 4/15/26 | 100% | Complete | 768 | No | No | 752 | fa94210e8c5694742df1c5b26cb20dac3c80fedf119911c8afcf039980516136
project_plan | project_plan | 378 | 999 |  | Extract File |  | Data Migration Team | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 987 | No | No | 999 | 78615f27b4e9f37f3490aebdadc8a200aa4edc701e0252023a55a1b454e6702e
project_plan | project_plan | 379 | 1000 |  | Pre Load Validation |  | Nevin Varkey | Fri 4/10/26 | Fri 4/10/26 | Fri 4/10/26 | 100% | Complete | 999 | No | No | 1000 | 8852cb6fe3c5fb9f4668d66b19de02a640a8bc427171ddf34331b9b728f6f25a
project_plan | project_plan | 380 | 1001 |  | Simulate Load |  | Data Migration Team | Fri 4/10/26 | Fri 4/10/26 | Tue 4/14/26 | 100% | Complete | 1000 | No | No | 1001 | f93a72e46da8997d1e4e3e20763c18ad5b523bccad9f7781da72cc0f1ee0f8a8
project_plan | project_plan | 381 | 1002 |  | Error and Defect Mitigation |  | Nevin Varkey | Mon 4/13/26 | Mon 4/13/26 | Tue 4/14/26 | 100% | Complete | 1001 | No | No | 1002 | 0841fa1982bb3196cf99c11a2b49c87683a9842e4d9cf43edbe043d692720e49
project_plan | project_plan | 382 | 1003 |  | Load |  | Data Migration Team | Wed 4/15/26 | Wed 4/15/26 | Tue 4/14/26 | 100% | Complete |  | No | No | 1003 | d816199e1bd1d5418519b2aaa6d0eebdbf99cfddf11de91587b399cc8fb32c7e
project_plan | project_plan | 383 | 1004 |  | Post Load Validation |  | Nevin Varkey | Wed 4/15/26 | Thu 4/16/26 | Wed 4/15/26 | 100% | Complete | 1003 | No | No | 1004 | 7b59d9bd3c1f9e32193736b5dc7ce2d66fd3915165d8d506b75a68474f34da56
project_plan | project_plan | 384 | 692 |  | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR |  |  | Thu 4/16/26 | Thu 4/16/26 | Wed 4/15/26 | 100% | Complete | 752 | No | No | 692 | 353cec42dec64c1ee414c31d02ac4f383ff7e05331dfa5818cbdfac7c97a052b
project_plan | project_plan | 385 | 1005 |  | Extract File(Will Extract from LFA1) |  | Nevin Varkey | Thu 4/16/26 | Thu 4/16/26 | Fri 4/10/26 | 100% | Complete |  | No | No | 1005 | d991ef1045c39699fa322988855ff9483cc38e26c5d14806d18731a3a646ee46
project_plan | project_plan | 386 | 1006 |  | Pre Load Validation |  | Nevin Varkey | Thu 4/16/26 | Thu 4/16/26 | Fri 4/10/26 | 100% | Complete | 1005 | No | No | 1006 | dc03ded82a880531ba59fb99a6c2f903e03746452d64ad898216413a7d525c30
project_plan | project_plan | 387 | 1007 |  | Simulate Load/ Not Needed |  | Nevin Varkey | Thu 4/16/26 | Thu 4/16/26 | Fri 4/10/26 | 100% | Complete | 1006 | No | No | 1007 | aa8eacf06c42be358bfd85c851e8c9b1a345e400d67dd837aa9a262168aa3b43
project_plan | project_plan | 388 | 1008 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 4/16/26 | Thu 4/16/26 | Mon 4/13/26 | 100% | Complete | 1007 | No | No | 1008 | 6fd54fbb2037efd91692caaa19cce7ecb4fce3142e0318eee50b6b90ef183699
project_plan | project_plan | 389 | 1009 |  | Load |  | Nevin Varkkey | Thu 4/16/26 | Thu 4/16/26 | Wed 4/15/26 | 100% | Complete | 1007 | No | No | 1009 | f4797efbfe5c6ee1285840e4592be5b9d8a5ef52e259ef04a0c24438b67a95be
project_plan | project_plan | 390 | 1010 |  | Post Load Validation |  | Nevin Varkey | Thu 4/16/26 | Thu 4/16/26 | Wed 4/15/26 | 100% | Complete | 1009 | No | No | 1010 | b5f7a23b297386ca30e4b59342b8d6b417e0222f567c2313b1a0f9accfc1cabb
project_plan | project_plan | 391 | 935 |  | RTR_****_Credit Hierarchy |  |  | Wed 4/15/26 | Thu 4/16/26 | Mon 4/13/26 | 100% | Complete | 692 | No | No | 935 | c3f4c4851b842228a26323841f057857014c5fe6487338198edf16862dd2885a
project_plan | project_plan | 392 | 1011 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Wed 4/15/26 | Wed 4/15/26 | Fri 4/10/26 | 100% | Complete | 996 | No | No | 1011 | 20108bf589b4f72a8e21c40aadaa2c95259c8448744f6f4efc606657f1d5af8a
project_plan | project_plan | 393 | 1012 |  | Load |  | Kasey Hughes | Wed 4/15/26 | Wed 4/15/26 | Mon 4/13/26 | 100% | Complete | 998 | No | No | 1012 | a303405e8816578c45e0c9da29c546e228248ef92d7aa3de639e01fafebae778
project_plan | project_plan | 394 | 1013 |  | Post Load Validation |  | Kasey Hughes | Thu 4/16/26 | Thu 4/16/26 | Mon 4/13/26 | 100% | Complete | 1012 | No | No | 1013 | cffdc8afa31efe3f13e93c365496b9b23fde33e86b78a783748ff41c101723e4
project_plan | project_plan | 395 | 693 |  | PTP_CM27_BP_Intercompany Supplier |  |  | Mon 4/13/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 935 | No | No | 693 | 0e8dd96c6cd1c20141e7863f4a66a57daef883b29353c2b9c4d57beb86ece63e
project_plan | project_plan | 396 | 1014 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Mon 4/13/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete | 1004 | No | No | 1014 | e8883af83ca0fee87023d17640adc4a0d42500d1f641769e74f5eeaa8b028698
project_plan | project_plan | 397 | 1015 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Mon 4/13/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete | 1014 | No | No | 1015 | 436233e1f23e28a0bdb0658d8fd985662ccfccdde162e687a68fd62f5a7eb3c0
project_plan | project_plan | 398 | 1016 |  | Simulate Load |  | Data Migration Team | Mon 4/13/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete | 1015 | No | No | 1016 | f19be4374b748c504de9024a741548dbf66d3e2e3cff7ddf2d9c8b5ad0855787
project_plan | project_plan | 399 | 1017 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Mon 4/13/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete | 1016 | No | No | 1017 | ddd12a6ce3bc35ae2088165d6ad921bcbe939e209778250cc30490d78b8f038d
project_plan | project_plan | 400 | 1018 |  | Load |  | Data Migration Team | Mon 4/13/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 1017 | No | No | 1018 | 0429ae4fb97e67a88b83e85e2f8d2bfc4d8942f56b6df0988e5dcf226ce0c395
project_plan | project_plan | 401 | 1019 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Tue 4/14/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 1018 | No | No | 1019 | f9e6828bdb4f63d86fcc1c7c2073a9c431bd16c5092cbba157bd6a594aa88e28
project_plan | project_plan | 402 | 1245 |  | PTP_CM27_BP_Intercompany Customer |  |  | Mon 4/13/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 693 | No | No | 1245 | 20afebe3b7558a672548db18529ab55f4312e7a50ba8255b746cc1474e1ac44d
project_plan | project_plan | 403 | 1246 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Mon 4/13/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete |  | No | No | 1246 | 7cef1793b23448c299bf3e20265cc2df8d2b77bd5115a6208f3751c599fa408a
project_plan | project_plan | 404 | 1247 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Mon 4/13/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete |  | No | No | 1247 | 95443df2e12f5afd8bb3bc69cdad33795dc29fe2aed3c87b7a59fa94fb125118
project_plan | project_plan | 405 | 1248 |  | Simulate Load |  | Data Migration Team | Mon 4/13/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete | 1247 | No | No | 1248 | b37376ca0fe073b0b2bdee3288efd69b290104cb5b401c8bc7bdc6691b3d6e6f
project_plan | project_plan | 406 | 1249 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Mon 4/13/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete | 1248 | No | No | 1249 | 3a3819b8d40bdd607d7a385e7852d277d36055a38aff05c8236dbb0ea14857fc
project_plan | project_plan | 407 | 1250 |  | Load |  | Data Migration Team | Mon 4/13/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 1249 | No | No | 1250 | 923126f89a6f39c659dda3308d99ecc9856ce3403ac47b3531e263327ff46f14
project_plan | project_plan | 408 | 1251 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Tue 4/14/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 1250 | No | No | 1251 | ffa7a8f8295730c4c5529eaffcd8d06910bb34b299b4ab7b4e21548c573188ae
project_plan | project_plan | 409 | 741 |  | PTP_CM26_Material_Master - All Types |  |  | Fri 4/10/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1245 | No | No | 741 | 3c7e540f69ef85c3eab3f262517f12c14f92d694d2ec59b8abc7e4017b5b00ad
project_plan | project_plan | 410 | 1020 |  | Extract File |  | Data Migration Team | Fri 4/10/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete | 1005 | No | No | 1020 | c498666dbfc66cd75f696de70b3b0408baf74173f04777e6bc16c195ce13cf71
project_plan | project_plan | 411 | 1021 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Mon 4/13/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 1004 | No | No | 1021 | 32d7892e112e168bd51e415c1e899f6631bea87a162dae0d9ff4024beb822352
project_plan | project_plan | 412 | 1022 |  | Simulate Load |  | Data Migration Team | Tue 4/14/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 1021 | No | No | 1022 | 094abddcb09b1544bf5d17634d528e7ef98d20ed71413dc65c439f2af72e9cce
project_plan | project_plan | 413 | 1023 |  | Error and Defect Mitigation |  | Nevin Varkey | Tue 4/14/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 1022 | No | No | 1023 | c0c5962c759fab704e32373ec03d8fdb0360976923d7a768d3ab26f36b9fd47f
project_plan | project_plan | 414 | 1024 |  | Load |  | Data Migration Team | Tue 4/14/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1023 | No | No | 1024 | fb8a3a67f71bd11b07426f01b844dfa1104df4b1b2a09ed8063faf771bacbbe8
project_plan | project_plan | 415 | 1025 |  | Post Load Validation |  | Nevin Varkey | Wed 4/15/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1024 | No | No | 1025 | 74b7aef0b7f01d1342bf058557a78fa795a2529ab87a6c6343aefbdcf276fa6d
project_plan | project_plan | 416 | 748 |  | PTP_CM26_Material_Master - SERV - Service Materials |  |  | Tue 4/7/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 741 | No | No | 748 | 5eb22718731fe62a32c50cd9ac6334f8cebdb680e10034e7a50f0cf8deff3873
project_plan | project_plan | 417 | 1026 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 807 | No | No | 1026 | e664ea065d93d9612c6cca749eb21c6d33cd0d750fb6d55b8e5bc7ab94d76908
project_plan | project_plan | 418 | 1027 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Tue 4/14/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 1024 | No | No | 1027 | e9dc0baf34a96c258b87cc889ec25c6f845bfb6b5cd899682598e24762e6c2d9
project_plan | project_plan | 419 | 1028 |  | Simulate Load |  | Data Migration Team | Tue 4/14/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 1027 | No | No | 1028 | 0d5c8fd3a739c8b364d7ea366ebcb583b9386cf56a2875eced63b4eefa01897e
project_plan | project_plan | 420 | 1029 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Tue 4/14/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1028 | No | No | 1029 | e61ab669a52d61bbe1c75294d8c3d2440e276592460cb68b843371d5227245e3
project_plan | project_plan | 421 | 1030 |  | Load |  | Data Migration Team | Wed 4/15/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1029 | No | No | 1030 | 12faf50da7377a22852c2227dbe05cc10eecd28e61080c0dcd8a6679c4d7c347
project_plan | project_plan | 422 | 1031 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Wed 4/15/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1030 | No | No | 1031 | f60a0e44ff3f525f996422a7b5cb883324af6ab3af160e658b694ced820ef25c
project_plan | project_plan | 423 | 749 |  | PTP_CM26_Material_Master - KMAT - Configurable Materials |  |  | Tue 4/7/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 748 | No | No | 749 | 4bd2f46c9184480d43bbbd77cd12de46e74d13e75e5d3572154e81689ebf0cd6
project_plan | project_plan | 424 | 1032 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 807 | No | No | 1032 | 14455e26b8ed6bc2fc84c15256e102a9977e1e69ce33c2c89b89e7f14c078645
project_plan | project_plan | 425 | 1033 |  | Pre Load Validation |  | Eric Heisler | Tue 4/14/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 1024 | No | No | 1033 | 34a3bf9baff0d8b6cb811b43ccad4c68557f5aee9b623c7d03ab58978363589a
project_plan | project_plan | 426 | 1034 |  | Simulate Load |  | Data Migration Team | Tue 4/14/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 1033 | No | No | 1034 | ae7060eea98a837145f74ba72468d407eed917a7604df55617c8aa4396a7d72d
project_plan | project_plan | 427 | 1035 |  | Error and Defect Mitigation |  | Eric Heisler | Tue 4/14/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1034 | No | No | 1035 | caf27edfbbdac19c2a2a2fd50ca71767926b2d45eabd6a2236cab911773338ed
project_plan | project_plan | 428 | 1036 |  | Load |  | Data Migration Team | Wed 4/15/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1035 | No | No | 1036 | 607733ed97d319f10e715a65294df27d556bb7fef33b91340f4e7ebd1ddeb35e
project_plan | project_plan | 429 | 1037 |  | Post Load Validation |  | Eric Heisler | Wed 4/15/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1036 | No | No | 1037 | 6534cba90c055540729579c7436534c64d687b74bff2c65b3a124f9bd4ec6c3b
project_plan | project_plan | 430 | 703 |  | PTP_CM28_Purchase_Info_Records |  |  | Wed 4/15/26 | Fri 4/17/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 703 | a9aed7eb266eea25c89a54c161f62627a2571028a663044f8ced6e3ec790f17a
project_plan | project_plan | 431 | 1038 |  | Extract File |  | Data Migration Team | Wed 4/15/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 10,251,037 | No | No | 1038 | d6b6f5696c4f9b06adb7f30c665463115e94f35fae646b609442d51006187786
project_plan | project_plan | 432 | 1039 |  | Pre Load Validation |  | Nevin Varkey | Wed 4/15/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1038 | No | No | 1039 | 4fa5285e2ab950be91eeaf82bc6c4d2ef189cfa78d6d0e7a1c78a69c88fbcf27
project_plan | project_plan | 433 | 1040 |  | Simulate Load |  | Data Migration Team | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1039 | No | No | 1040 | 2838d9c26a64499a269bc2b653d99eb24aa9295dc40e462afb4b2e587564aa12
project_plan | project_plan | 434 | 1041 |  | Error and Defect Mitigation |  | Nevin Varkey | Fri 4/17/26 | Fri 4/17/26 | Thu 4/16/26 | 100% | Complete | 1040 | No | No | 1041 | 9cd3c13b2f1ce1b8821915c2c09b4141a363a83a90881d3e76b03e6a6253e1f3
project_plan | project_plan | 435 | 1042 |  | Load |  | Data Migration Team | Fri 4/17/26 | Fri 4/17/26 | Wed 4/15/26 | 100% | Complete | 1004 | No | No | 1042 | 935d38ab6ba20b1e4ce8a93edfc3133e5098e66542093dd3513050e799ba8f9f
project_plan | project_plan | 436 | 1043 |  | Post Load Validation |  | Nevin Varkey | Fri 4/17/26 | Fri 4/17/26 | Wed 4/15/26 | 100% | Complete | 1042 | No | No | 1043 | dd3757eb89e79fc2584615d2b226f6ee39d30fc9b568412f079ecdefaec75a8b
project_plan | project_plan | 437 | 936 |  | PTP_CM28_Purchase_Info_Record External Processing |  |  | Wed 4/15/26 | Fri 4/17/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 936 | abbc97c650391c0ac9076b2bdad91d713efbc2c26534574cd1b139ec23ebf5c9
project_plan | project_plan | 438 | 1044 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey | Wed 4/15/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 10,251,037 | No | No | 1044 | 219ef5c8bc071478ede3a1273daaf158ad16122298b55920adc58db3650d1112
project_plan | project_plan | 439 | 1045 |  | Pre Load Validation |  | Nevin Varkey | Wed 4/15/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1044 | No | No | 1045 | 7157de82667119ec75cef0c8bcd48f4e8114d6f74b22d0bb8a4f9f3509a2903e
project_plan | project_plan | 440 | 1046 |  | Simulate Load |  | Data Migration Team | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1045 | No | No | 1046 | c1eeeeedf73291d0a6e8af47519df9e3955054f28854137b626b6d429b46e5a3
project_plan | project_plan | 441 | 1047 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1046 | No | No | 1047 | 0b777a6ab5b57cad90c9125d9ebb1106def6644f27fe851584fa52e9e2e81af9
project_plan | project_plan | 442 | 1048 |  | Load |  | Data Migration Team | Fri 4/17/26 | Fri 4/17/26 | Thu 4/16/26 | 100% | Complete | 1047 | No | No | 1048 | 639c76425a4bb15dddffcba69a52c0a4e71cbbd47aa06ab325c4b5fb2856e6c7
project_plan | project_plan | 443 | 1049 |  | Post Load Validation |  | Nevin Varkey | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1048 | No | No | 1049 | f0f53ca123ee4f9185f72439fbbd43003f4d0c01143068cdce9318ca4707fb48
project_plan | project_plan | 444 | 937 |  | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment |  |  | Wed 4/15/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 937 | 105575929e1eba949ae30c7ae1de00e733736dbded5b90b370010e48e3dca70a
project_plan | project_plan | 445 | 1050 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey | Wed 4/15/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 10,251,037 | No | No | 1050 | 995609fedef42a9e0d57aed9997a033ca1d7a635376ec81d79e049177a324456
project_plan | project_plan | 446 | 1051 |  | Pre Load Validation |  | Nevin Varkey | Wed 4/15/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1050 | No | No | 1051 | 8d5fe4d2e0a4d9012b9b4c0ec7e6cde2c1732c625956dd8ceaf8eb1f0a574cfe
project_plan | project_plan | 447 | 1052 |  | Simulate Load |  | Data Migration Team | Wed 4/15/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1051 | No | No | 1052 | 9395ab54e7e3bdf8025def73512d948bfeb33e1d9156fc30498b3e3b5f375343
project_plan | project_plan | 448 | 1053 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1052 | No | No | 1053 | 695d71359858a419f1a2bbdb653265d7db773a1dc8579791db463a4bdbda3de5
project_plan | project_plan | 449 | 1054 |  | Load |  | Data Migration Team | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1053 | No | No | 1054 | b6d9de36440e63fd5af7d2cea582d743cfcd6d701bbf276cecaa200d5e3d9923
project_plan | project_plan | 450 | 1055 |  | Post Load Validation |  | Nevin Varkey | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1054 | No | No | 1055 | ff4df6d14bb0526152216fa1c8e19bfc7788e2961c24b1ff0b9707e7545ab3fd
project_plan | project_plan | 451 | 694 |  | PTM_CM31_BOM Conversion |  |  | Wed 4/15/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete |  | No | No | 694 | 702184fbd8dff39b9749df99f8a9dc8395b6fbd9db41a0c9d8dda99f484d57f4
project_plan | project_plan | 452 | 1056 |  | Extract File |  | Data Migration Team | Wed 4/15/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1038 | No | No | 1056 | 4c1022ad5fb1355e5f47670821dfa9dda6e5a3843fbd65ad07b3031aea4af901
project_plan | project_plan | 453 | 1057 |  | Pre Load Validation |  | Brad Meseck | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1056 | No | No | 1057 | eed29ee9c1d901bd5c020b2f712a07ac5daaec45d5e2770a803783b072da57fe
project_plan | project_plan | 454 | 1058 |  | Simulate Load |  | Data Migration Team | Thu 4/16/26 | Fri 4/17/26 | Thu 4/16/26 | 100% | Complete | 1057 | No | No | 1058 | 8e3cce072d6dc58d07c186208c2c76d9b767b1c289aea36f1a32c2778ba0cad1
project_plan | project_plan | 455 | 1059 |  | Error and Defect Mitigation |  | Brad Meseck | Fri 4/17/26 | Fri 4/17/26 | Thu 4/16/26 | 100% | Complete | 1058 | No | No | 1059 | 5fd8cd8c28d4ac1c81ab38ceb8002cc13a1c6c7baaef79413bb54667db40eecc
project_plan | project_plan | 456 | 1060 |  | Load |  | Data Migration Team | Fri 4/17/26 | Fri 4/17/26 | Thu 4/16/26 | 100% | Complete | 1059 | No | No | 1060 | 807c8e700a9c3c0e42439bf69214f8afb3715fcd13be142ebb4a1e969db887ea
project_plan | project_plan | 457 | 1061 |  | Post Load Validation |  | Brad Meseck | Fri 4/17/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete | 1060 | No | No | 1061 | db90a364cdd1134f9444c1bc0cf95d527dd333ce3a2e89dcfa27a86a17902896
project_plan | project_plan | 458 | 695 |  | PTM_CM40_Work Center Conversion |  |  | Thu 4/16/26 | Thu 4/16/26 | Mon 4/20/26 | 100% | Complete |  | No | No | 695 | 662ece00d75b6207d7d7f8e96e091fd9216992e480b9d4ac5d611c22562096e0
project_plan | project_plan | 459 | 1062 |  | Extract File |  | Data Migration Team | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1056 | No | No | 1062 | 981056fcba670e4288ac3b745d0026a9543b25d1ca67fdbab95d174f1091e313
project_plan | project_plan | 460 | 1063 |  | Pre Load Validation |  | Brad Meseck | Thu 4/16/26 | Thu 4/16/26 | Fri 4/17/26 | 100% | Complete | 1061 | No | No | 1063 | 2dcd30b7e9889c3a9eb0db46903d2bc0cb41ff782df6b5b8a54357c10785bcb5
project_plan | project_plan | 461 | 1064 |  | Simulate Load |  | Data Migration Team | Thu 4/16/26 | Thu 4/16/26 | Fri 4/17/26 | 100% | Complete | 1063 | No | No | 1064 | 1667c374fa991dc16489c2592eb69652d35d259115087f1053b4c4a383f3aeac
project_plan | project_plan | 462 | 1065 |  | Error and Defect Mitigation |  | Brad Meseck | Thu 4/16/26 | Thu 4/16/26 | Fri 4/17/26 | 100% | Complete | 1064 | No | No | 1065 | 289e1f0d51512a356ce522df5825884951f6c05f3b5f9519f6d3b3a65318920f
project_plan | project_plan | 463 | 1066 |  | Load |  | Data Migration Team | Thu 4/16/26 | Thu 4/16/26 | Fri 4/17/26 | 100% | Complete | 1065 | No | No | 1066 | 9ba2e2fec024f2c56885d3678002331b79b35bbd279d7fa27ece77a239b9fd97
project_plan | project_plan | 464 | 1067 |  | Post Load Validation |  | Brad Meseck | Thu 4/16/26 | Thu 4/16/26 | Mon 4/20/26 | 100% | Complete | 1066 | No | No | 1067 | 0d8a872a03067b356acd969c955ebcbc38bd0435a277287226051a46bce065ff
project_plan | project_plan | 465 | 707 |  | PTM_CM38_Routing Conversion |  |  | Thu 4/16/26 | Mon 4/20/26 | Tue 4/21/26 | 100% | Complete |  | No | No | 707 | 0195c581d4caca202ebb2d1dfb1ea270d5da8329ea9d0a9a53e02d5f995f2ee8
project_plan | project_plan | 466 | 1075 |  | Extract File |  | Data Migration Team | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1062 | No | No | 1075 | 52cda8787fed4783d600344144897bd77408f3b38ba57a3a9b6c0fb42c894442
project_plan | project_plan | 467 | 1076 |  | Pre Load Validation |  | Brad Meseck | Thu 4/16/26 | Thu 4/16/26 | Mon 4/20/26 | 100% | Complete | 1067 | No | No | 1076 | fa17401a8c2b65a164f4c1091dc106a759f9bbc75f56963878af813b601a3429
project_plan | project_plan | 468 | 1077 |  | Simulate Load |  | Data Migration Team | Mon 4/20/26 | Mon 4/20/26 | Mon 4/20/26 | 100% | Complete | 1076 | No | No | 1077 | ea470719a768e3af80416e1b36f377662e80d2bde578979ecde19d34db84905f
project_plan | project_plan | 469 | 1078 |  | Error and Defect Mitigation |  | Brad Meseck | Mon 4/20/26 | Mon 4/20/26 | Mon 4/20/26 | 100% | Complete | 1077SS | No | No | 1078 | 2439f6a582bc33994c5a572c7ce699fd406f3125aa940c53d0880d6a72fb80e9
project_plan | project_plan | 470 | 1079 |  | Load |  | Data Migration Team | Mon 4/20/26 | Mon 4/20/26 | Mon 4/20/26 | 100% | Complete | 1078 | No | No | 1079 | eff109d073578c558665b194e71006ef2a302702c1966dd0f978310addee00c3
project_plan | project_plan | 471 | 1080 |  | Post Load Validation |  | Brad Meseck | Mon 4/20/26 | Mon 4/20/26 | Tue 4/21/26 | 100% | Complete | 1079 | No | No | 1080 | 8f24241492284149076a22a706b1cdee15370fc854982b06cb86cec51520b904
project_plan | project_plan | 472 | 709 |  | PTM_CM36_Production Version Conversion |  |  | Mon 4/20/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete |  | No | No | 709 | 162d57cdde17f78d11c2cd6027211c2457b99eaffdf8d6edc3cded0a92cf69b6
project_plan | project_plan | 473 | 1081 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Mon 4/20/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete | 1075 | No | No | 1081 | 186364c589adfbd47f943457bafe36dfdf0bba791147cd9099316e25d4624bdd
project_plan | project_plan | 474 | 1082 |  | Pre Load Validation |  | Brad Meseck | Mon 4/20/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete | 1081 | No | No | 1082 | 5bc0f649440a0d6e58a7080d8e37b4bef5962aa7915a00a3723a93b7d6dcd567
project_plan | project_plan | 475 | 1083 |  | Simulate Load |  | Data Migration Team | Mon 4/20/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete | 1082 | No | No | 1083 | 407128c8f4de1bda6178b71adc03071700b949a094df4f1cd53dbe360abfcbd1
project_plan | project_plan | 476 | 1084 |  | Error and Defect Mitigation |  | Brad Meseck | Mon 4/20/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete | 1083 | No | No | 1084 | 834c763d6b9e71953c246fd4837ab301eeaa697a87a627ab0b973d6fd5077e87
project_plan | project_plan | 477 | 1085 |  | Load |  | Data Migration Team | Mon 4/20/26 | Mon 4/20/26 | Fri 4/17/26 | 100% | Complete | 1084 | No | No | 1085 | 5ceca73aa08e20ba60d2428ab59b58cb2f1de6a18b27d203d3e12a5738060da0
project_plan | project_plan | 478 | 1086 |  | Post Load Validation |  | Brad Meseck | Mon 4/20/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete | 1085 | No | No | 1086 | fee64e16d6e02c652bbe87e8b7f7ce6e0dedb6963f27cdccbec07680c04a8bfe
project_plan | project_plan | 479 | 710 |  | PTM_CM35_Inspection Plan |  |  | Tue 4/21/26 | Wed 4/22/26 | Mon 4/20/26 | 100% | Complete |  | No | No | 710 | c9df0fa884d3d2430a566ca846c0a8a970d1c9a869414d4dacc1fe6cebb33255
project_plan | project_plan | 480 | 1088 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Tue 4/21/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete | 1086 | No | No | 1088 | a6581727e2905b6e7864fc46368487c542f299ef301bca72cf389c967ec616c1
project_plan | project_plan | 481 | 1089 |  | Pre Load Validation |  | Brad Meseck | Tue 4/21/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete | 1088 | No | No | 1089 | b1ddbf43db092495164e3e12c092a6114380f83dd647d8416cc6421f4ec026b2
project_plan | project_plan | 482 | 1090 |  | Simulate Load |  | Data Migration Team | Tue 4/21/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete | 1089 | No | No | 1090 | 191c1d8c1a675b21359edad9354db37cf8e7685bb3c7fca99b25ac65e5239724
project_plan | project_plan | 483 | 1091 |  | Error and Defect Mitigation |  | Brad Meseck | Tue 4/21/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete | 1090 | No | No | 1091 | dd47ee760d023747ec00379f3f97c97cf5cdfa746a2c640772b2fd29c13ed533
project_plan | project_plan | 484 | 1092 |  | Load |  | Data Migration Team | Tue 4/21/26 | Tue 4/21/26 | Mon 4/20/26 | 100% | Complete | 1091 | No | No | 1092 | 2d3d29074e350c4bf0c1a68e95c10777aa2978f71cede8a0c23dd963236fb2e6
project_plan | project_plan | 485 | 1093 |  | Post Load Validation |  | Brad Meseck | Tue 4/21/26 | Wed 4/22/26 | Mon 4/20/26 | 100% | Complete | 1092 | No | No | 1093 | 1c7e9ba6c1ddf5dfc6a4258f28200b5bcdf690e652e8e0cf0eaa32864aab2b65
project_plan | project_plan | 486 | 1194 |  | PTM_CM48_Equipment_Master_Serial Numbers |  |  | Tue 4/21/26 | Wed 4/22/26 | Mon 4/20/26 | 100% | Complete |  | No | No | 1194 | c5e96458df3b5b2dd24ecf39b87b8d5e16098681c37cc2c4ad2b5c12eaceb883
project_plan | project_plan | 487 | 1196 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Tue 4/21/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete | 1088 | No | No | 1196 | 2eb6371b76daffaadb9613d3ac821152c69a6d3f4bf80cdd610f1e5f6e3f2ce0
project_plan | project_plan | 488 | 1197 |  | Pre Load Validation |  | Brad Meseck | Tue 4/21/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete | 1196 | No | No | 1197 | 8c32c0faf742b37234f71b77da91e801f3493ae0d8b3b0cbfc16e0b775420aff
project_plan | project_plan | 489 | 1198 |  | Simulate Load |  | Data Migration Team | Tue 4/21/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete | 1197 | No | No | 1198 | 1a0257720263470faf78834b39546d2de616ca50ebc066401836fc7395a397a1
project_plan | project_plan | 490 | 1199 |  | Error and Defect Mitigation |  | Brad Meseck | Tue 4/21/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete | 1198 | No | No | 1199 | e124d3f9822fb5b9dd34092f938628bedd7b761cdd3957d670b263f4c5188445
project_plan | project_plan | 491 | 1200 |  | Load |  | Data Migration Team | Tue 4/21/26 | Tue 4/21/26 | Mon 4/20/26 | 100% | Complete | 1199 | No | No | 1200 | cc5f010bfd3a1df8ccb362f71bb653dcf243e6431b431e740422f50d6e5c4d6a
project_plan | project_plan | 492 | 1201 |  | Post Load Validation |  | Brad Meseck | Tue 4/21/26 | Wed 4/22/26 | Mon 4/20/26 | 100% | Complete | 1200 | No | No | 1201 | 9a24170b28320b8e283a2b12d70e5d5802ec39f4bcc9af06cde459afe5417cd5
project_plan | project_plan | 493 | 1195 |  | PTM_CM48_Equipment_Master_Service |  |  | Tue 4/21/26 | Thu 4/23/26 | Tue 4/21/26 | 100% | Complete |  | No | No | 1195 | 9e91d2e7d2bbf85e8185c622565a704058680528e25767679ec7bbde64904857
project_plan | project_plan | 494 | 1202 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Wed 4/22/26 | Wed 4/22/26 | Mon 4/20/26 | 100% | Complete | 1201 | No | No | 1202 | 221df490318200ecd68d10a6fa8a30447a5fcce53e2331d8cf57126a1cf80e02
project_plan | project_plan | 495 | 1203 |  | Pre Load Validation |  | Brad Meseck | Wed 4/22/26 | Wed 4/22/26 | Mon 4/20/26 | 100% | Complete | 1202 | No | No | 1203 | 5196aeb59fa1c81102ba4e17c8c3c97dd736a4cbcacb99e3a80b27bbc5d20661
project_plan | project_plan | 496 | 1204 |  | Simulate Load |  | Data Migration Team | Wed 4/22/26 | Wed 4/22/26 | Mon 4/20/26 | 100% | Complete | 1203 | No | No | 1204 | d9bc463f964bfd1fab3133814b73eb7aec617b36c7a2a755de9cf913842acb5f
project_plan | project_plan | 497 | 1205 |  | Error and Defect Mitigation |  | Brad Meseck | Wed 4/22/26 | Wed 4/22/26 | Tue 4/21/26 | 100% | Complete | 1204 | No | No | 1205 | 4adad7f0adcef216c2f69c4ae82dc13cfe2ce94270dc2bbfd0f011dff138b05e
project_plan | project_plan | 498 | 1206 |  | Load |  | Data Migration Team | Wed 4/22/26 | Thu 4/23/26 | Tue 4/21/26 | 100% | Complete | 1205 | No | No | 1206 | 47c8d1a899283e63a166d5b79432f9f1416db09339e8309a3716b98b2ed5ce6c
project_plan | project_plan | 499 | 1207 |  | Post Load Validation |  | Brad Meseck | Tue 4/21/26 | Tue 4/21/26 | Tue 4/21/26 | 100% | Complete |  | No | No | 1207 | de3036f0797ae413c2fd17279c63906be2f726fd13fe8e8a3a27f2a2a3965f4a
project_plan | project_plan | 500 | 938 |  | VC_Object Dependencies |  |  | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete |  | No | No | 938 | 71b234dcaef56d6f5d88ada9842557e58d9b5289c92352eb39f319105ea0707e
project_plan | project_plan | 501 | 1151 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 956 | No | No | 1151 | 996ea0a88f0f23daa000ec4e6d6e13e29545762e527fd1debecc2d2984f11d92
project_plan | project_plan | 502 | 1153 |  | Post Load Validation |  | Eric Heisler | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 1151 | No | No | 1153 | 37789b13419d9b056329fdb3ffa01d4ceafd35c943f7d35074e1ecde09ea7c37
project_plan | project_plan | 503 | 939 |  | VC_Characteristics |  |  | Mon 4/6/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete |  | No | No | 939 | 787ee899ac2c641c43e944fcf86bbfbef2f9a6ec549cd6f18bc6569afe848243
project_plan | project_plan | 504 | 1154 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 1153 | No | No | 1154 | 3ec5bfd51d5601863804dc42f62d94ea3db102594bb49e87e3e1a7c972de2e48
project_plan | project_plan | 505 | 1155 |  | Post Load Validation |  | Eric Heisler | Mon 4/6/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 1154 | No | No | 1155 | ce9c93532ad4fa556a340e4b47dc5a11cd811ced87e8f3cd5f0ae1cf521ed727
project_plan | project_plan | 506 | 940 |  | VC_Classes |  |  | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete |  | No | No | 940 | fe202204d1a489f290e276814840dc2540d64ce8fca546133beb6952479c164c
project_plan | project_plan | 507 | 1156 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 1155 | No | No | 1156 | 45f478293ed788a97d33b8122bc222cce5c67d060e470e9463134e58323917d9
project_plan | project_plan | 508 | 1157 |  | Post Load Validation |  | Eric Heisler | Tue 4/7/26 | Tue 4/7/26 | Tue 4/7/26 | 100% | Complete | 1156 | No | No | 1157 | cbf3a92e9cf79346a93d2adabb126348377ffbbc1b34b18eb56eebcab6fc99b4
project_plan | project_plan | 509 | 941 |  | VC_Classification (Class Type 200) |  |  | Wed 4/15/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 941 | 725bde328d3a5b372c259d9a895f0364209067e40c4f44fbb409c077d46f39ca
project_plan | project_plan | 510 | 1158 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Wed 4/15/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1037 | No | No | 1158 | 5b7364e26c3050f705d7950a1bfcd464843168ddb9729fd8edf3780c9d932079
project_plan | project_plan | 511 | 1159 |  | Post Load Validation |  | Eric Heisler | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1158 | No | No | 1159 | 5a9c7fc3ba96cc44b140beecc6e912329a59f94f3c6cc13412a88601f0fd633e
project_plan | project_plan | 512 | 942 |  | VC_Dependency Nets |  |  | Wed 4/15/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 942 | 9aecdb583d29271c0dc82d27400c72f88bf9d5a863bea05ae4c2f4e8c44a727b
project_plan | project_plan | 513 | 1160 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Wed 4/15/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1,157,749 | No | No | 1160 | 679d6990dd0d58d8f3e73046391e3c338cffa206421e7534958187072edd819f
project_plan | project_plan | 514 | 1161 |  | Post Load Validation |  | Eric Heisler | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1160 | No | No | 1161 | 475c38eb02ee43942fef1038186f2093f8c84e8436070ea72cb07dc7e891a4cd
project_plan | project_plan | 515 | 943 |  | VC_Configuration Profiles |  |  | Wed 4/15/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 943 | ce7c2a24822eb1960ce380a1dcdf1a0fb662dc2e43d6568031778cc8cd70ea57
project_plan | project_plan | 516 | 1162 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Wed 4/15/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 749 | No | No | 1162 | 997d9fd427d15fa97c2b0601994e1260e53abfb5ecd77ba6d87c5da409727b47
project_plan | project_plan | 517 | 1163 |  | Post Load Validation |  | Eric Heisler | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1162 | No | No | 1163 | 5a588e151f26ed78db28c980bc09d750ee7cc378260f1e6c5544c52ccb0f642e
project_plan | project_plan | 518 | 944 |  | VC_Variant Tables |  |  | Thu 4/16/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete |  | No | No | 944 | 45e6073475c47c7ce8f83c333b15ffc69b6db15f372fa2e6c924efebe57bdd8c
project_plan | project_plan | 519 | 1164 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1163 | No | No | 1164 | eaa3018d493eb69ccf939d43b62d33f51aad82f76a634043b19d8e143e891946
project_plan | project_plan | 520 | 1165 |  | Post Load Validation |  | Eric Heisler | Thu 4/16/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete | 1164 | No | No | 1165 | 1f30857a9fed58833a277ca3d0f723235ddd0abc4c65b9f3d82045ea4a8e5184
project_plan | project_plan | 521 | 945 |  | VC_Variant Tables Content |  |  | Fri 4/17/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete |  | No | No | 945 | a3fe65856f4564aceffac4be2453778e557f3b6d57953b6da57af9a36032ec56
project_plan | project_plan | 522 | 1166 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Fri 4/17/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete | 1165 | No | No | 1166 | 2ea027844c39504b9bfe46604c6db8044689ad3c689d2db6bb25686b9f0ebbbd
project_plan | project_plan | 523 | 1167 |  | Post Load Validation |  | Eric Heisler | Fri 4/17/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete | 1166 | No | No | 1167 | a0e6e1e85d912c045d3758ba8a5b683d8eca5ce28de0f8751ab41b414de9d591
project_plan | project_plan | 524 | 946 |  | VC_Characteristic Groups |  |  | Fri 4/17/26 | Mon 4/20/26 | Fri 4/17/26 | 100% | Complete |  | No | No | 946 | 74b4d5a777c2955296f9a72e727a37900f81fe0f549e9e1eed1eae8735af101e
project_plan | project_plan | 525 | 1168 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Fri 4/17/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete | 1163 | No | No | 1168 | 686272fe519c8df08da9d029e5103dbaa4d24b029c725cdd6ec12e5bd10ebd7c
project_plan | project_plan | 526 | 1169 |  | Post Load Validation |  | Eric Heisler | Mon 4/20/26 | Mon 4/20/26 | Fri 4/17/26 | 100% | Complete | 1168 | No | No | 1169 | c6bc24cc891f62f9c7d48602f136cfb251a67c1e832485ed0d960a2f63a2c71c
project_plan | project_plan | 527 | 713 |  | PTM_CM52_Super_BOM |  |  | Wed 4/15/26 | Tue 4/21/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 713 | 21a3b7dd48f9d17a764994551abeb0f9b54bec3ae9587534d609f6b58e465ec4
project_plan | project_plan | 528 | 1094 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Wed 4/15/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1037 | No | No | 1094 | 131d5f31518ab817fdd07fe2ddae1361bc3907902eba7f6c0a8ef968c97e28f0
project_plan | project_plan | 529 | 1095 |  | Pre Load Validation |  | Eric Heisler | Wed 4/15/26 | Wed 4/15/26 | Wed 4/15/26 | 100% | Complete | 1094 | No | No | 1095 | 423fbf5912946c3dc8d86a3daed7734a456b4370bd46846a78a3dc4992f1baa9
project_plan | project_plan | 530 | 1096 |  | Simulate Load |  | Data Migration Team | Wed 4/15/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete | 1095 | No | No | 1096 | 428b4f59d061d8b7d6b8f96d6b59df6822ef4157ec0a07e41d0baf22003ac6b1
project_plan | project_plan | 531 | 1097 |  | Error and Defect Mitigation |  | Eric Heisler | Tue 4/21/26 | Tue 4/21/26 | Thu 4/16/26 | 100% | Complete | 1096 | No | No | 1097 | 25dcf814a3f2fdafe0b2b550a2dc1db53a44bd6e7e7e622665b48402e249ca8c
project_plan | project_plan | 532 | 1098 |  | Load |  | Data Migration Team | Tue 4/21/26 | Tue 4/21/26 | Thu 4/16/26 | 100% | Complete | 1097 | No | No | 1098 | 2d6de688ad6ab92307ae4ab907491d6dbde7d8033ef86c4d6648c3d3ba997feb
project_plan | project_plan | 533 | 1099 |  | Post Load Validation |  | Eric Heisler | Tue 4/21/26 | Tue 4/21/26 | Thu 4/16/26 | 100% | Complete | 1098 | No | No | 1099 | 79ea12bfc2fbf55194984a5fcfcc2e4e4c0a320ffadcf1d8a0bbd8943bb26751
project_plan | project_plan | 534 | 714 |  | PTM_CM53_Super_Routing |  |  | Thu 4/16/26 | Fri 4/17/26 | Mon 4/20/26 | 100% | Complete |  | No | No | 714 | aae30ccd919032028bed0fe44ab9a6bcd15c5e67fe6d73fe3dfee4251e725182
project_plan | project_plan | 535 | 1100 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1099 | No | No | 1100 | 1f1b6231646fb99e917f50613ada12700c95ddd5eef6aa593e8097b519e915ac
project_plan | project_plan | 536 | 1101 |  | Pre Load Validation |  | Eric Heisler | Thu 4/16/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete | 1100 | No | No | 1101 | e7d0560b44e6b12581926faacdeb92366bc56fb4a526e265d50ced6d6b874a46
project_plan | project_plan | 537 | 1102 |  | Simulate Load |  | Data Migration Team | Thu 4/16/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete | 1101 | No | No | 1102 | b24cc7841f9383f32ce15294db2aad0daa26d392b7bd5c839a62177bfa3b5488
project_plan | project_plan | 538 | 1103 |  | Error and Defect Mitigation |  | Eric Heisler | Fri 4/17/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete | 1102 | No | No | 1103 | 4db0e09460a8c8c98c9fa92df2eec60d123c1892a6e3f0859f9dcbc613c7656e
project_plan | project_plan | 539 | 1104 |  | Load |  | Data Migration Team | Fri 4/17/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete | 1103 | No | No | 1104 | df3c31c5b0eabea1fb911140fb60683606371d4aa3b9cd9dd922efd1be1493fc
project_plan | project_plan | 540 | 1105 |  | Post Load Validation |  | Eric Heisler | Fri 4/17/26 | Fri 4/17/26 | Mon 4/20/26 | 100% | Complete | 1104 | No | No | 1105 | 801eedf201bfff99570d40b5cd0b4fb29337d6daf2e4c1c29e5e70e404de20e5
project_plan | project_plan | 541 | 949 |  | VC_VK30 Pricing Variant |  |  | Thu 4/16/26 | Thu 4/16/26 | Mon 4/20/26 | 100% | Complete |  | No | No | 949 | b20ed9f1efbc47b67c8431b00c92c3d69ed978f9a3ec2390af560bc5acca0dbd
project_plan | project_plan | 542 | 1106 |  | Manual File Staged and Posted "Ready" |  | Eric Heisler | Thu 4/16/26 | Thu 4/16/26 | Fri 4/17/26 | 100% | Complete | 1104 | No | No | 1106 | 5e7e04de693974938888d45a0533b7a589b75c61fae0410d88031cb18cc107ca
project_plan | project_plan | 543 | 1107 |  | Load |  | Eric Heisler | Thu 4/16/26 | Thu 4/16/26 | Fri 4/17/26 | 100% | Complete | 1106 | No | No | 1107 | 062fe60f10f3f134948f04c3f9d2a093eef3c8169f3824ec5a273a340dec4000
project_plan | project_plan | 544 | 1108 |  | Post Load Validation |  | Eric Heisler | Thu 4/16/26 | Thu 4/16/26 | Mon 4/20/26 | 100% | Complete | 1107 | No | No | 1108 | 0dce627aa4b8263b6bad261612b9287cad93320e36627500d344ea0b96669fde
project_plan | project_plan | 545 | 951 |  | OTC_CM22_Pricing_Condition |  |  | Wed 4/15/26 | Thu 4/16/26 | Tue 4/21/26 | 100% | Complete |  | No | No | 951 | f733e363070880e9d737c0ea35c58856bda40d270d76f545f966c49603cc9af5
project_plan | project_plan | 546 | 1109 |  | Manual File Staged and Posted "Ready" |  | Ric Haraida | Wed 4/15/26 | Wed 4/15/26 | Mon 4/20/26 | 100% | Complete | 1108 | No | No | 1109 | db749d43da4c80f751880665c98681c314b5b42de8f83d0d616f8566f0075d32
project_plan | project_plan | 547 | 1110 |  | Load |  | Ric Haraida | Wed 4/15/26 | Wed 4/15/26 | Mon 4/20/26 | 100% | Complete | 1109 | No | No | 1110 | 503991f58a92cf9d7134b470da8a9345ca544c668aca34aaf125d449406cebfe
project_plan | project_plan | 548 | 1111 |  | Post Load Validation |  | Ric Haraida,Kim Kolesar | Thu 4/16/26 | Thu 4/16/26 | Tue 4/21/26 | 100% | Complete | 1110 | No | No | 1111 | 1077b1ed05a2c507d6da9d4f6905099671566a4e13803e5b3f5944fcf89d4717
project_plan | project_plan | 549 | 691 |  | OTC_CM21_CMIR |  |  | Thu 4/16/26 | Mon 4/20/26 | Tue 4/21/26 | 100% | Complete |  | No | No | 691 | cadc57759e0a86239ee4b2a4b506c43f24ace65a8ceec240767627c362770750
project_plan | project_plan | 550 | 1112 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Mon 4/20/26 | Mon 4/20/26 | Mon 4/20/26 | 100% | Complete | 11,101,119 | No | No | 1112 | d76fd71787fc13c1072594a763c8ec1143a1c9a6b2f86a088f88a72f1a894e14
project_plan | project_plan | 551 | 1113 |  | Pre Load Validation |  | Ric Haraida | Thu 4/16/26 | Thu 4/16/26 | Mon 4/20/26 | 100% | Complete | 1112 | No | No | 1113 | 4c3ce15d568e4c5514f78214b1565be017888e276a321e7cb67877a22e73fef2
project_plan | project_plan | 552 | 1114 |  | Simulate Load |  | Data Migration Team | Thu 4/16/26 | Thu 4/16/26 | Mon 4/20/26 | 100% | Complete | 1113 | No | Yes | 1114 | 84f1385d0b7b451a7df5659ef12cb9287a7ccd8860b47ccff8d1f97c74d35f3d
project_plan | project_plan | 553 | 1115 |  | Error and Defect Mitigation |  | Ric Haraida | Thu 4/16/26 | Thu 4/16/26 | Tue 4/21/26 | 100% | Complete | 1114 | No | Yes | 1115 | 3303f23abf8c8337b748be2c46df6b533e13fb9c87c97b1ea3a6392d5d01bbb2
project_plan | project_plan | 554 | 1116 |  | Load |  | Data Migration Team | Thu 4/16/26 | Thu 4/16/26 | Tue 4/21/26 | 100% | Complete | 1115 | No | Yes | 1116 | 91e2ee3c19af7c0b277143ef08aa786f74a6650a1b573c20e9d7da207c6d3302
project_plan | project_plan | 555 | 1117 |  | Post Load Validation |  | Ric Haraida | Thu 4/16/26 | Thu 4/16/26 | Tue 4/21/26 | 100% | Complete | 1116 | No | No | 1117 | 6a0f109249d0983134a0fd85f44bf6f2e86fda810e015fa46d73fe1b21a2efe8
project_plan | project_plan | 556 | 704 |  | PTP_CM29_Source_List |  |  | Fri 4/17/26 | Mon 4/20/26 | Tue 4/14/26 | 100% | Complete |  | No | No | 704 | a55b38829c50cf182bf171b954a2392a3de81828ee47e4212e8f42b5dadc5de0
project_plan | project_plan | 557 | 1118 |  | Manual File Staged and Posted "Ready" |  | Nevin Varkey | Fri 4/17/26 | Fri 4/17/26 | Tue 4/14/26 | 100% | Complete | 10,181,250 | No | No | 1118 | 676489f447abb6acef21bc5926544839bc8ae87ab47022f089fcde8c449d5776
project_plan | project_plan | 558 | 1119 |  | Load |  | Nevin Varkey | Fri 4/17/26 | Mon 4/20/26 | Mon 4/13/26 | 100% | Complete | 998 | No | No | 1119 | e40317e5dd523c5f1ea074576bd8f7c53dc09f6eff8559a9c74171e9a2c44250
project_plan | project_plan | 559 | 1120 |  | Post Load Validation |  | Nevin Varkey | Mon 4/20/26 | Mon 4/20/26 | Mon 4/13/26 | 100% | Complete | 1119 | No | No | 1120 | 4f59a6184345ce31626128f0d739ac84bea47dd971a17603a015873576865a88
project_plan | project_plan | 560 | 702 |  | RTR_CM11_Asset_Master |  |  | Wed 4/15/26 | Thu 4/23/26 | Mon 4/13/26 | 100% | Complete |  | No | No | 702 | 59c023cd93e24d9eb29678a8c887ec369a2ad83ea10cdaae5c38797ff3b232ec
project_plan | project_plan | 561 | 1121 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Wed 4/15/26 | Wed 4/15/26 | Fri 4/10/26 | 100% | Complete |  | No | No | 1121 | 4976b7a91d35d1fa33cc77ab1af1bbfc714cc51e23007b5303c6a74604e645da
project_plan | project_plan | 562 | 1122 |  | Pre Load Validation |  | Kasey Hughes,Femi Oguntala | Wed 4/15/26 | Wed 4/15/26 | Fri 4/10/26 | 100% | Complete | 1121 | No | No | 1122 | 20775f1abd3188c2025f5bc86cc1b47df9b79adbf728d2e8e998af3707913647
project_plan | project_plan | 563 | 1123 |  | Simulate Load |  | Data Migration Team | Wed 4/15/26 | Mon 4/20/26 | Fri 4/10/26 | 100% | Complete | 1122 | No | No | 1123 | 888749b17177069fe77913af3f1be3e1510cb9e3725a0c9d57109d1431e4e36e
project_plan | project_plan | 564 | 1124 |  | Error and Defect Mitigation |  | Kasey Hughes | Tue 4/21/26 | Wed 4/22/26 | Fri 4/10/26 | 100% | Complete | 1123 | No | No | 1124 | 40ad52d04f5e471bb4b25a6373a84adb2d61dde0b403e8078d355cf63b49f703
project_plan | project_plan | 565 | 1125 |  | Load |  | Data Migration Team | Thu 4/23/26 | Thu 4/23/26 | Fri 4/10/26 | 100% | Complete | 1124 | No | No | 1125 | 3d53f6e98689f204b6ab1320a21762e29b82a0bd23069502088d0949673ac029
project_plan | project_plan | 566 | 1126 |  | Post Load Validation |  | Kasey Hughes | Thu 4/23/26 | Thu 4/23/26 | Mon 4/13/26 | 100% | Complete | 1125 | No | No | 1126 | 3bbe60c00a847c281fb3f784e50fad407fa733c481d0c5ecb0b190033e2da06d
project_plan | project_plan | 567 | 712 |  | PTM_CM50_Material Class |  |  | Thu 4/16/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 712 | 24bbfd93d4170c9e766a308f796e741d5a544d670e095d9ff95ba564d16a8935
project_plan | project_plan | 568 | 1127 |  | Manual File Staged and Posted "Ready" |  | Sam | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1081 | No | No | 1127 | 0c5b98ced744510911d4df4ce3680da73cdb51b1a93efbdc41a3a4882f0b0b25
project_plan | project_plan | 569 | 1128 |  | Load |  | Brad Meseck | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1127 | No | No | 1128 | 959ba86d3db491c6899a8cc273e84f9bcdae86fc975cd10abe201a50b6c8570a
project_plan | project_plan | 570 | 1129 |  | Post Load Validation |  | Brad | Fri 4/17/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete | 1128 | No | No | 1129 | 695f4eb2e05ccaa204aaeea69d03b4ab3f265d184c8d53e23ddd85552ce7293c
project_plan | project_plan | 571 | 715 |  | PTM_CM55_Class assignment to materials |  |  | Thu 4/16/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete |  | No | No | 715 | c3d105da03fba37e68552ad4dc6dc8ecc37eca7cdcbebef3e549ba6007501443
project_plan | project_plan | 572 | 1133 |  | Load File Staged and Posted "Ready" |  | Sam | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1127 | No | No | 1133 | 0f7e4218643630a04f48e67f37cff749a844e2565e5763710882a01ba56d6b2a
project_plan | project_plan | 573 | 1134 |  | Pre Load Validation |  | Brad Meseck | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1133 | No | No | 1134 | f2aba775f0396b99c504175db9c00fd23fa8eb122cd111e79775f6d1d334d7de
project_plan | project_plan | 574 | 1135 |  | Simulate Load |  | Data Migration Team | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1134 | No | No | 1135 | b1bf037efb4143337e3a426e2c8c31c9ced01669e7a941ed4379fb759f048f2b
project_plan | project_plan | 575 | 1136 |  | Error and Defect Mitigation |  | Brad Meseck | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1135 | No | No | 1136 | 7d39cec9eddeaf88a73c9b2213202283d748c52b6a8447b5657f7652f3ad74b9
project_plan | project_plan | 576 | 1137 |  | Load |  | Data Migration Team | Thu 4/16/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete | 1136 | No | No | 1137 | 7029b2fe6e8c731be9aa4a210483d333b4cf784c3887e66d0180b06ef5feea66
project_plan | project_plan | 577 | 1138 |  | Post Load Validation |  | Brad Meseck | Fri 4/17/26 | Fri 4/17/26 | Fri 4/17/26 | 100% | Complete | 1137 | No | No | 1138 | ba8159bd43c7132a39b5cd045fea25766923725c8b74287745e8e47225d36874
project_plan | project_plan | 578 | 952 |  | GTS - Material initial load from S4 (Run Interface) |  |  | Thu 4/16/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 952 | fd661c11efc27cc4ab22e78644d8eb748c1de0003c9b56118c66cf865015dea9
project_plan | project_plan | 579 | 1171 |  | Run material interface to GTS |  | James Van Riper | Thu 4/16/26 | Fri 4/17/26 | Thu 4/16/26 | 100% | Complete | 1052 | No | No | 1171 | dd1e50eeccce553ecd926237421806f4b02fc33f207f00b2d12034b6e742aacd
project_plan | project_plan | 580 | 1173 |  | Post Load Validation |  | James Van Riper | Mon 4/20/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete | 1171 | No | No | 1173 | c597fc6c9122abf8e76cc1fec4be7af83595315986d43a9171e79d8a07076332
project_plan | project_plan | 581 | 953 |  | GTS - Customers initial load from S4 (Run Interface) |  |  | Wed 4/15/26 | Mon 4/20/26 | Fri 4/10/26 | 100% | Complete |  | No | No | 953 | 19e6af168f19266d3e365545adeb3db994e3d04a938b59a20dd7f2153186d6ce
project_plan | project_plan | 582 | 1174 |  | Run material interface to GTS |  | James Van Riper | Wed 4/15/26 | Wed 4/15/26 | Fri 4/10/26 | 100% | Complete |  | No | No | 1174 | 8c9e7a2dd8fcb58e34a89c564b3288adb16c7e2776db24c7325f0e59cb7e840c
project_plan | project_plan | 583 | 1175 |  | Post Load Validation |  | James Van Riper | Mon 4/20/26 | Mon 4/20/26 | Fri 4/10/26 | 100% | Complete | 1174 | No | No | 1175 | 6bc964a90f43844e914c06cbcce9255c868645d16c872f1ebc5f1fb27ef88214
project_plan | project_plan | 584 | 954 |  | GTS - Vendors initial load from S4 (Run Interface) |  |  | Thu 4/16/26 | Fri 4/17/26 | Wed 4/15/26 | 100% | Complete |  | No | No | 954 | d8061d1014227adc1aeb2037e52cbb1df213db2090d3e8135cff300d6eb94b25
project_plan | project_plan | 585 | 1176 |  | Run material interface to GTS |  | James Van Riper | Thu 4/16/26 | Thu 4/16/26 | Wed 4/15/26 | 100% | Complete | 1010 | No | No | 1176 | f417bf416517bca7f11b99d63dabe690ca553d1a7fe672d1840ab135a530cb5c
project_plan | project_plan | 586 | 1177 |  | Post Load Validation |  | James Van Riper | Fri 4/17/26 | Fri 4/17/26 | Wed 4/15/26 | 100% | Complete | 1176 | No | No | 1177 | 04272a51af3fe0e5d6f6752b537ba90948aff78166e87fb1ed54d544727dd52a
project_plan | project_plan | 587 | 698 |  | GTS - ECCN - Create |  |  | Mon 4/6/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete |  | No | No | 698 | c7e85dbe7cf17d200bf5f22cff30a20c2edbb50630c03b6031a85e4914fc5db9
project_plan | project_plan | 588 | 1178 |  | Load Descartes XML File |  | James Van Riper | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 956 | No | No | 1178 | eac1be176416d146cccfc5668688c77e8854c53d21313964344ec83b64d83682
project_plan | project_plan | 589 | 1179 |  | Post Load Validation |  | James Van Riper | Mon 4/13/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete | 1176 | No | No | 1179 | d76ec6f5cc8711d6c84f04563d79d0d288a554881f01f38c2d582da6d16f32ba
project_plan | project_plan | 590 | 699 |  | GTS - ECCN - Assign |  |  | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 699 | 75618f846ad2c3d971c31597723e67a8dc7a94429c1fa86844b9e80251228038
project_plan | project_plan | 591 | 1180 |  | Load Descartes XML File |  | James Van Riper | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1173 | No | No | 1180 | 9d1c0d12f39c483830d42f36dfd87b4d87e6afe414b2b6b633e4ed66f174d524
project_plan | project_plan | 592 | 1181 |  | Post Load Validation |  | James Van Riper | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1180 | No | No | 1181 | e26e8ac1eebd8fe317a6981c5bcc5583d70170334fedb2b1a560d46deb147c14
project_plan | project_plan | 593 | 700 |  | GTS - HTS - Create |  |  | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete |  | No | No | 700 | ea3c925219c8db947cb23a0514885583a2a877d1b0677cc4117d98f3c011e85a
project_plan | project_plan | 594 | 1182 |  | Load Descartes XML File |  | James Van Riper | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 956 | No | No | 1182 | d70389baba1b504b4073152ded31a7c89040ef01d32125437172d946e59f0792
project_plan | project_plan | 595 | 1183 |  | Post Load Validation |  | James Van Riper | Mon 4/6/26 | Mon 4/6/26 | Mon 4/6/26 | 100% | Complete | 1182 | No | No | 1183 | a18da12ef17ed4d9e15880740781ddc4d0a77c3c2308752439263eeebb374233
project_plan | project_plan | 596 | 701 |  | GTS - HTS - Assign |  |  | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 701 | 89d3ee3924249100ca37e1678e7a6736b9f3b84a6c6f70c5299cc40bd370be13
project_plan | project_plan | 597 | 1184 |  | Load Descartes XML File |  | James Van Riper | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1181 | No | No | 1184 | 0bf88a6a0cf226bc3077c40502de5d329c52c81bf7d58a75ed8329470973a43a
project_plan | project_plan | 598 | 1185 |  | Post Load Validation |  | James Van Riper | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1184 | No | No | 1185 | 25047a81a8fb6d00e978ed6c2e072d73fdda7d3196992186963848c268b4a5ea
project_plan | project_plan | 599 | 706 |  | GTS - License - Create |  |  | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 706 | ab757330b032bc122687a425b91e9f95b69d4171a036d3e7f4c10f09a9b4e1b8
project_plan | project_plan | 600 | 1186 |  | Load Descartes XML File |  | James Van Riper | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 11,841,188 | No | No | 1186 | 0d1412a248abcbec63a90456e627893d34d0a2dd076335e15e005b9d5b7f9ae1
project_plan | project_plan | 601 | 1187 |  | Post Load Validation |  | James Van Riper | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1186 | No | No | 1187 | b2ed4ec6fffa2218b4f7a49f22d0f9ecc14064e8452132b78bb5f8f9ca9fc541
project_plan | project_plan | 602 | 1213 |  | Commodity Code/Tarif |  |  | Thu 4/16/26 | Tue 4/21/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 1213 | dfe217bee9aa32e6159f975352b759bb9c6dfa7e5ce1e5b2d3d0452a2e3f7108
project_plan | project_plan | 603 | 1214 |  | Load |  | James Van Riper | Thu 4/16/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete | 1185 | No | No | 1214 | 4367a0730ca8f88a037874322b57a3ea571bbeab2497a65570cdaee2786cff9e
project_plan | project_plan | 604 | 1215 |  | Post Load Validation |  | James Van Riper | Tue 4/21/26 | Tue 4/21/26 | Thu 4/16/26 | 100% | Complete | 1214 | No | No | 1215 | 18898208727d5ecd5b84a104885ef1a905325a736a95eef5510d2a2f84504bb5
project_plan | project_plan | 605 | 1216 |  | SPL Master File |  |  | Wed 4/15/26 | Thu 4/16/26 | Thu 3/13/25 | 100% | Complete |  | No | No | 1216 | 877e648490ec9b12e76e24de65db0832dc259e66bf93d7cf5028f036cf5ed759
project_plan | project_plan | 606 | 1217 |  | Load |  | James Van Riper | Thu 4/16/26 | Thu 4/16/26 | Thu 3/13/25 | 100% | Complete | 1184 | No | No | 1217 | f5ad70891f03fa5f7fc59cad79336121f74aebbd947c519f5586e1bd4cd73d27
project_plan | project_plan | 607 | 1218 |  | Post Load Validation |  | James Van Riper | Wed 4/15/26 | Wed 4/15/26 | Thu 3/13/25 | 100% | Complete | 1217 | No | No | 1218 | 828c5b9fec63e2d0da24beaf25cb77318035fef47250fea621f6b750ac4dd5c2
project_plan | project_plan | 608 | 1209 |  | Initialize Embargo situation |  |  | Mon 4/13/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete |  | No | No | 1209 | 63a8ff251b54cbd83c7d5ad5a43285c4fd9d2c4788b078e27ac60e0de9720607
project_plan | project_plan | 609 | 1210 |  | Run report /SAPSLL/EMB_CNTRY_INIT |  | James Van Riper | Mon 4/13/26 | Mon 4/13/26 | Mon 4/13/26 | 100% | Complete | 1179 | No | No | 1210 | 1d3bf3808114afb6999b0c9f4fe81b6cb91a08db001bb7591ea6b3ce13707457
project_plan | project_plan | 610 | 1211 |  | Set Embargo situations |  | James Van Riper | Tue 4/14/26 | Tue 4/14/26 | Mon 4/13/26 | 100% | Complete | 1210 | No | No | 1211 | f0c3817c46b440964fc30e4bcd5198e4440dec5ec8c9bd5f6483944539bd2792
project_plan | project_plan | 611 | 1212 |  | Post Load Validation |  | James Van Riper | Tue 4/14/26 | Tue 4/14/26 | Tue 4/14/26 | 100% | Complete | 1211 | No | No | 1212 | 9551cfcb958ef171356679d9e65d476ce98215364c80478105234850989b854d
project_plan | project_plan | 612 | 955 |  | GTS - SPL (Sanctioned party list) |  |  | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete |  | No | No | 955 | eaebb499e1479c7dca1c5ebf5c26a668158360003e6831d1f6d6c28332bfd981
project_plan | project_plan | 613 | 1188 |  | Load Descartes XML File |  | James Van Riper | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1185 | No | No | 1188 | 1aeb6661c15c6477e3393cec87e957319cf06b1dc41453f592f2288d3500e37d
project_plan | project_plan | 614 | 1189 |  | Post Load Validation |  | James Van Riper | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 1188 | No | No | 1189 | efab234992dbf31571a61d62723256637b92865bf72c91078257f060f2d23357
project_plan | project_plan | 615 | 950 |  | RTR_CM17_Project Definition / Builder |  |  | Mon 4/20/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete |  | No | No | 950 | 27e3112a7f5f5e9861792c832e0d8be36fdb6a5af9d254a73b53c39910a57547
project_plan | project_plan | 616 | 1139 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Mon 4/20/26 | Mon 4/20/26 | Fri 4/10/26 | 100% | Complete | 1121 | No | No | 1139 | 89d3384d6f12f154e605f1e7513aba2185bd269c663f98446f1fd90d586ded52
project_plan | project_plan | 617 | 1140 |  | Pre Load Validation |  | Kasey Hughes | Mon 4/20/26 | Mon 4/20/26 | Fri 4/10/26 | 100% | Complete | 1139 | No | No | 1140 | 0f07ece47d9f68c5c4d39495ddbfd937aed0a672c039d2308eb10b0cb82ef5ee
project_plan | project_plan | 618 | 1141 |  | Simulate Load |  | Data Migration Team | Mon 4/20/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete | 1140 | No | No | 1141 | 0ffc3ebcb3baacd90645637b1b007efc1b020c23f02258702cb704eec9aa3be0
project_plan | project_plan | 619 | 1142 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 4/20/26 | Mon 4/20/26 | Fri 4/17/26 | 100% | Complete | 1141 | No | No | 1142 | 2b070960e4e74e38e9b7bbf223f0aebe472a31d1bf658f291121f65a543875e5
project_plan | project_plan | 620 | 1143 |  | Load |  | Data Migration Team | Mon 4/20/26 | Mon 4/20/26 | Fri 4/17/26 | 100% | Complete | 1142 | No | No | 1143 | 8ed8f7f6ba9c987ee2548be762db1ead6ea9acf3dadf029a573f869770e3eb8c
project_plan | project_plan | 621 | 1144 |  | Post Load Validation |  | Kasey Hughes | Mon 4/20/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete | 1143 | No | No | 1144 | bdf681edc29f388512c9e1fb9f64f5821a7832b429eb0ef79a3ead268c5eb31d
project_plan | project_plan | 622 | 754 |  | RTR_CM18_WBS Element |  |  | Mon 4/20/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete |  | No | No | 754 | 130208310107f39a8ac5ac02d647265a2556e896d453afc61c50baebf72b731b
project_plan | project_plan | 623 | 1145 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Mon 4/20/26 | Mon 4/20/26 | Fri 4/10/26 | 100% | Complete | 1139 | No | No | 1145 | 9529756038fa41f49a617e479f3d3401ed3245555577ce8091593e5a6fd48761
project_plan | project_plan | 624 | 1146 |  | Pre Load Validation |  | Kasey Hughes | Mon 4/20/26 | Mon 4/20/26 | Fri 4/10/26 | 100% | Complete | 1145 | No | No | 1146 | b8fbd83f758a4a7ef68acc4f5d85919476c56cb474a056073c814f03c717bba5
project_plan | project_plan | 625 | 1147 |  | Simulate Load |  | Data Migration Team | Mon 4/20/26 | Mon 4/20/26 | Thu 4/16/26 | 100% | Complete | 1146 | No | No | 1147 | 5e4df2863b82c8f7f59c09d225ece8857569d96b99cf42e94c1d2dbc320b4b28
project_plan | project_plan | 626 | 1148 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 4/20/26 | Mon 4/20/26 | Fri 4/17/26 | 100% | Complete | 1147 | No | No | 1148 | f58ea30e0fea5cd0d666d4bd7ad64e1efe20f3fb3b3900351fb78916109037d4
project_plan | project_plan | 627 | 1149 |  | Load |  | Data Migration Team | Mon 4/20/26 | Mon 4/20/26 | Fri 4/17/26 | 100% | Complete | 1148 | No | No | 1149 | 05fb14d1b3df93bd0c3059ffbcf1d597426c7999f50d10348073ad6f7539df35
project_plan | project_plan | 628 | 1150 |  | Post Load Validation |  | Kasey Hughes | Mon 4/20/26 | Tue 4/21/26 | Fri 4/17/26 | 100% | Complete | 1149 | No | No | 1150 | 8f51047634940f5988e6bb624a7ce946fc965d60d7aa6aa329a08a8226212341
project_plan | project_plan | 629 | 1170 |  | ITC1 Mock Data Loads Complete |  | Mark George | Thu 4/23/26 | Thu 4/23/26 | Tue 4/21/26 | 100% | Complete |  | No | Yes | 1170 | 8ea39818913fa56f1a6cc8d375e40464d7992119bf95b6a1e96e1d917feed437
project_plan | project_plan | 630 | 2809 |  | ITC2 Data Load Tasks QS4 |  |  | Mon 5/18/26 | Mon 10/12/26 |  | 0% | Future Task | 425,849 | Yes | No | 2809 | 3ca155b34cb9a537ac10bfe1b823fbb79d195f9680f6d80ceb02d434ee4ffecb
project_plan | project_plan | 631 | 1685 |  | PMO Authorization to Start Data Loads |  | Mark George | Mon 5/18/26 | Mon 5/18/26 | Mon 4/6/26 | 0% | Future Task | 849 | Yes | No | 1685 | 7a68264d55b79a4ebab07defd61c0740911e77f98c713c4fd720dba5c45ec001
project_plan | project_plan | 632 | 2800 |  | Master Data Loads |  |  | Mon 5/18/26 | Fri 5/29/26 |  | 0% | Future Task | 1685 | Yes | No | 2800 | 4c27331aec101c4b16a687f7a116b0291ef48d7204eac486e11edefa34d000e9
project_plan | project_plan | 633 | 1686 |  | RTR_CM02_Profit Center Hierarchy |  |  | Mon 5/18/26 | Mon 5/18/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 1686 | 75e8de66ac444c7fa508d15c0e547d0e0d4c60177b768be007bb9f969ee6fa3b
project_plan | project_plan | 634 | 1687 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Mon 5/18/26 | Mon 5/18/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 1687 | f056b214565196adbf5f1589912910d9b93135e399836f28bc0dc1cc115884b6
project_plan | project_plan | 635 | 1688 |  | Load |  | Kasey Hughes | Mon 5/18/26 | Mon 5/18/26 | Mon 4/6/26 | 0% | Future Task | 1687 | Yes | No | 1688 | 62d1037761d5c4657deaf4277e6b67fc6170f9b33a68530e4b67cc83b2198796
project_plan | project_plan | 636 | 1689 |  | Post Load Validation |  | Kasey Hughes | Mon 5/18/26 | Mon 5/18/26 | Mon 4/6/26 | 0% | Future Task | 1688 | Yes | No | 1689 | 30c0cee3cc7040916bf526eda3e3f242c14691d891284e25b63f22207ec41a80
project_plan | project_plan | 637 | 1690 |  | RTR_CM03_Cost Center Hierarchy |  |  | Tue 5/19/26 | Tue 5/19/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 1690 | de1e1ffd66f1c39d4d82e94c18b94912f11f466f1066aa40e59eb65985fa5ea6
project_plan | project_plan | 638 | 1691 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Mon 4/6/26 | 0% | Future Task | 1689 | Yes | No | 1691 | a38b7fea7c0748f7488a3bc2c6c4606c854ce8c07892398728ce2a437130a790
project_plan | project_plan | 639 | 1692 |  | Load |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Tue 4/7/26 | 0% | Future Task | 1691 | Yes | No | 1692 | 3fc6051d226c2e176aa490c7d468bbef4f65dd17481464fee3f80c69a521f1d5
project_plan | project_plan | 640 | 1693 |  | Post Load Validation |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Tue 4/7/26 | 0% | Future Task | 1692 | Yes | No | 1693 | bce28efe7228dfa4aa41f9490077354b49dc017ff91d98f5bb14beeacc714cbc
project_plan | project_plan | 641 | 1694 |  | RTR_CM01_GL_Account_Master to CC 1000 |  |  | Tue 5/19/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 1694 | 4998c0b743e602014baaf0c647478075120c8da896cb12ea40c44e63ba83bf81
project_plan | project_plan | 642 | 1695 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Tue 4/7/26 | 0% | Future Task | 1693 | Yes | No | 1695 | b5fd414f8209930d2d020cd02ae7e75207edf837c057d36a3fb2ea078d90d7e6
project_plan | project_plan | 643 | 1696 |  | Pre Load Validation |  | Kasey Hughes | Tue 5/19/26 | Wed 5/20/26 | Tue 4/7/26 | 0% | Future Task | 1695 | Yes | No | 1696 | 4997a3416ef46c6074b5019fe330de44b7e1d13852815ea4d294ea2e775718e8
project_plan | project_plan | 644 | 1697 |  | Simulate Load |  | Data Migration Team | Wed 5/20/26 | Wed 5/20/26 | Wed 4/8/26 | 0% | Future Task | 1696 | Yes | No | 1697 | 477bbf5b5edbc63a3fbba9986076a5e05ff2f2e1c0d971ae5b4b18b536461f04
project_plan | project_plan | 645 | 1698 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 5/20/26 | Thu 5/21/26 | Wed 4/8/26 | 0% | Future Task | 1697 | Yes | No | 1698 | 417014422e5fe3a1febf7141a9b50ab3f266ebcfae9ad9e1766c1a1509d25eba
project_plan | project_plan | 646 | 1699 |  | Load |  | Data Migration Team | Thu 5/21/26 | Thu 5/21/26 | Wed 4/8/26 | 0% | Future Task | 1698 | Yes | No | 1699 | b3f3e4521e8f57877a201b6c48f78d340229abd9214a56469aeb680595cdaee6
project_plan | project_plan | 647 | 1700 |  | Post Load Validation |  | Kasey Hughes | Thu 5/21/26 | Thu 5/21/26 | Wed 4/8/26 | 0% | Future Task | 1699 | Yes | No | 1700 | e6c9fe93ed37b8b2ca72a244f63feb51f8126ef48a88d119b0c683c286678b8d
project_plan | project_plan | 648 | 1701 |  | Extend GL to all Company Codes |  | Kasey Hughes | Thu 5/21/26 | Thu 5/21/26 | Thu 4/9/26 | 0% | Future Task | 1700 | Yes | No | 1701 | 50ad1631ad47d04c7134f2b9572dd9301e458a79b372a6312df9d856606aee07
project_plan | project_plan | 649 | 1702 |  | Post GL Extention Validation |  |  | Thu 5/21/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task | 1701 | Yes | No | 1702 | 13f3edbef2b81e61830738b381403196f594817df7efe6dc523ba0c0b88b3f42
project_plan | project_plan | 650 | 1703 |  | RTR_CM05_Profit_Center |  |  | Tue 5/19/26 | Wed 5/20/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 1703 | 6930f4f0bdd541ffbb63f0b7f1ff343871d54d424aca490c32a5a5678fdbb360
project_plan | project_plan | 651 | 1704 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Mon 4/6/26 | 0% | Future Task | 1689 | Yes | No | 1704 | 043380cc7b2a6dc439f1f2c76941dfe7994626dba7b6ccbfbbf4b9b76446fa16
project_plan | project_plan | 652 | 1705 |  | Pre Load Validation |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Tue 4/7/26 | 0% | Future Task | 1704 | Yes | No | 1705 | 12f791d59574c2661422b60b82450b46b5bdebf7fddb0b8534d4f0b640a5c2af
project_plan | project_plan | 653 | 1706 |  | Simulate Load |  | Data Migration Team | Tue 5/19/26 | Tue 5/19/26 | Tue 4/7/26 | 0% | Future Task | 1705 | Yes | No | 1706 | 3b53818853309b2315fc7edb248fbf3f157b91e730479625dd67721317400a27
project_plan | project_plan | 654 | 1707 |  | Error and Defect Mitigation |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Tue 4/7/26 | 0% | Future Task | 1706 | Yes | No | 1707 | 4446b14e972c484503800ff0744c3826d63b1cd791bb85aea648bc832db2bfd5
project_plan | project_plan | 655 | 1708 |  | Load |  | Data Migration Team | Tue 5/19/26 | Tue 5/19/26 | Tue 4/7/26 | 0% | Future Task | 1707 | Yes | No | 1708 | 97a9524ce782249067c28e3df13118e35e20696a443dfde849f945b6c333c026
project_plan | project_plan | 656 | 1709 |  | Post Load Validation |  | Kasey Hughes | Tue 5/19/26 | Wed 5/20/26 | Tue 4/7/26 | 0% | Future Task | 1708 | Yes | No | 1709 | b2b68840b944757999c5bbd20233511ca1b615728336cc537ef0307e4998204a
project_plan | project_plan | 657 | 1710 |  | RTR_CM04_Cost_Center |  |  | Wed 5/20/26 | Thu 5/21/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 1710 | d976aa8bd2304a8f34da850b7921132593805a053dc56ebdb3ea146df656e130
project_plan | project_plan | 658 | 1711 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Wed 5/20/26 | Wed 5/20/26 | Wed 4/8/26 | 0% | Future Task | 1709 | Yes | No | 1711 | 060305fcb35d7180988c2efb4eafbd552ff7c4f75c39941f674dfcfe76918e2d
project_plan | project_plan | 659 | 1712 |  | Pre Load Validation |  | Kasey Hughes | Wed 5/20/26 | Wed 5/20/26 | Wed 4/8/26 | 0% | Future Task | 1711 | Yes | No | 1712 | 0a99b70015acd7c6d0431e3b83898720f3723e5ea5709151f33f1f997ba38211
project_plan | project_plan | 660 | 1713 |  | Simulate Load |  | Data Migration Team | Wed 5/20/26 | Wed 5/20/26 | Wed 4/8/26 | 0% | Future Task | 1712 | Yes | No | 1713 | 2fd0d89d4fd966a023d1771f48398ce5c7286283178a15d7232f53c7d6e2e6b6
project_plan | project_plan | 661 | 1714 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 5/20/26 | Wed 5/20/26 | Wed 4/8/26 | 0% | Future Task | 1713 | Yes | No | 1714 | ff3bee2c6fd97f59129bc13eae62973e53638da1991a93cd6f9d60cdc5626d7d
project_plan | project_plan | 662 | 1715 |  | Load |  | Data Migration Team | Wed 5/20/26 | Wed 5/20/26 | Wed 4/8/26 | 0% | Future Task | 1714 | Yes | No | 1715 | e320fcef6277ce23aa4f282156f642d0bf1f817250260591a8541703fee62a2f
project_plan | project_plan | 663 | 1716 |  | Post Load Validation |  | Kasey Hughes | Thu 5/21/26 | Thu 5/21/26 | Thu 4/9/26 | 0% | Future Task | 1715 | Yes | No | 1716 | deb450fb54d03e64da760020907d5a1a58f7d877a13f353129be630fe101b76b
project_plan | project_plan | 664 | 1717 |  | Manual Configuration Activities in QS5 |  |  | Thu 5/21/26 | Fri 5/29/26 | Wed 4/15/26 | 0% | Future Task | 1710 | Yes | No | 1717 | 8c75d991b91602cc95a114edb50541a29c9eeb489d61dc7de6733d0464fe389f
project_plan | project_plan | 665 | 1718 |  | Open Client |  | Basis | Thu 5/21/26 | Thu 5/21/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 1718 | ec659a8c1c17e2b3ba9b842c5d9b3694ea1fa96e993cc8bd9a9d760a0be60b80
project_plan | project_plan | 666 | 1719 |  | Service Enterprise Setup |  | Keith Riley | Fri 5/22/26 | Fri 5/29/26 | Wed 4/15/26 | 0% | Future Task | 168,616,901,694 | Yes | No | 1719 | 4a0f4b28c6c48906395ec6a154344f1662879fd48efcf803da34ec0e18b16ce2
project_plan | project_plan | 667 | 1720 |  | Close Client |  | Basis | Thu 5/21/26 | Thu 5/21/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 1720 | 2b3b5504362cc1ab614fc61dbffde5f2be2d5adb5c46fb0060e63904d2275bf7
project_plan | project_plan | 668 | 1721 |  | Intercompany Business Partner Setup |  | Functional Leads | Fri 5/22/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task | 168,616,901,702 | Yes | No | 1721 | 961db38846570d9eb91b8356de15fe1f4c419bdbd3559ae90573b6e313a4b249
project_plan | project_plan | 669 | 1722 |  | RTR_CM09_Activity_Type |  |  | Thu 5/21/26 | Mon 5/25/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 1722 | 67f77a21ee6a23115404ca6159b351faf3d5a6ef1ef880b9d72ba55993565fa0
project_plan | project_plan | 670 | 1723 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Thu 5/21/26 | Thu 5/21/26 | Wed 4/8/26 | 0% | Future Task | 1700 | Yes | No | 1723 | 7528cf01ef380064941fb634843e7858745e32058c48b1589ed3d7d4a1a11ae1
project_plan | project_plan | 671 | 1724 |  | Pre Load Validation |  | Kasey Hughes | Thu 5/21/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task | 1723 | Yes | No | 1724 | 742be8d27ac7918370baee0324dab52bb9b450ffe19727f4a15f2c00103654f1
project_plan | project_plan | 672 | 1725 |  | Simulate Load |  | Data Migration Team | Fri 5/22/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task | 1724 | Yes | No | 1725 | 900250f53849e841e93d0d561c8bd92fb625fbde2af9b335870a19964be6404c
project_plan | project_plan | 673 | 1726 |  | Error and Defect Mitigation |  | Kasey Hughes | Fri 5/22/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task | 1725 | Yes | No | 1726 | c95b9895ac875ede567b8a2de11f30c70a132063f2e173feacd8a4b5afb6d90f
project_plan | project_plan | 674 | 1727 |  | Load |  | Data Migration Team | Fri 5/22/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task | 1726 | Yes | No | 1727 | cb6851730565fa829f59c51264829e7f091b79a42312abcbbe26cc88ebc59b49
project_plan | project_plan | 675 | 1728 |  | Post Load Validation |  | Kasey Hughes | Fri 5/22/26 | Mon 5/25/26 | Thu 4/9/26 | 0% | Future Task | 1727 | Yes | No | 1728 | 7ef27dc217488abc8e6f4511a1fc76946712f402e3e64b334af5f83b40d95ddb
project_plan | project_plan | 676 | 1729 |  | RTR_CM12_Activity Rates |  |  | Tue 5/19/26 | Wed 5/20/26 | Wed 4/8/26 | 0% | Future Task |  | Yes | No | 1729 | c6ea502ef8449f2f8451336098304e414e4fd7fae6f8df7514fb8a7abebbd2ac
project_plan | project_plan | 677 | 1730 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Tue 4/7/26 | 0% | Future Task | 1693 | Yes | No | 1730 | 9421a00fb605e65f4efddc461040abfbf6981711d2364394ffca8fd6892d4b3b
project_plan | project_plan | 678 | 1731 |  | Pre Load Validation |  | Kasey Hughes | Tue 5/19/26 | Wed 5/20/26 | Tue 4/7/26 | 0% | Future Task | 1730 | Yes | No | 1731 | 056025b9080f6805409eb49651c1d0ed606af4c89514801bce9a7e9f6fab1173
project_plan | project_plan | 679 | 1732 |  | Simulate Load |  | Data Migration Team | Wed 5/20/26 | Wed 5/20/26 | Wed 4/8/26 | 0% | Future Task | 1731 | Yes | No | 1732 | 3e7129f368b1f1bdc0e06a191754c5f73cf43bc558732356ced151a8f087131b
project_plan | project_plan | 680 | 1733 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 5/20/26 | Wed 5/20/26 | Wed 4/8/26 | 0% | Future Task | 1732 | Yes | No | 1733 | 5dbc2a948cbce89bf1723f04930b80a9796f3c16badb9e37a6c24372e73413ee
project_plan | project_plan | 681 | 1734 |  | Load |  | Data Migration Team | Wed 5/20/26 | Wed 5/20/26 | Wed 4/8/26 | 0% | Future Task | 1733 | Yes | No | 1734 | 6b2084c750ea1b83884373254eb0badf91815db8914e739846483110bac675a7
project_plan | project_plan | 682 | 1735 |  | Post Load Validation |  | Kasey Hughes | Wed 5/20/26 | Wed 5/20/26 | Wed 4/8/26 | 0% | Future Task | 1734 | Yes | No | 1735 | 09de2dd334994eea0f72735a4487badb61b7d7151a81fe91780b0f37df391f6d
project_plan | project_plan | 683 | 1736 |  | RTR_CM06_Bank_master |  |  | Mon 5/18/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 1736 | 34fa77669e4dc79f581b12b4bb945c6cec864ad6ad8fe96721a1b6eb3af8b3a9
project_plan | project_plan | 684 | 1737 |  | Load File Staged and Posted "Ready" |  | Data Migration Team | Thu 5/21/26 | Thu 5/21/26 | Wed 4/8/26 | 0% | Future Task | 1700 | Yes | No | 1737 | 4b7e8c3ab7071e545433ba70ea7ac661376db93b9eaf00635061dfccb360db59
project_plan | project_plan | 685 | 1738 |  | Pre Load Validation |  | Kasey Hughes | Thu 5/21/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task | 1737 | Yes | No | 1738 | a6310469248f5f273dd8ccb4856a7e0fd135676001b05f143dcf0716de938454
project_plan | project_plan | 686 | 1739 |  | Simulate Load |  | Data Migration Team | Mon 5/18/26 | Mon 5/18/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 1739 | 850d8500b448a77ffd13b43de423150aa0882db334c28bacadc3a553ef43e4d4
project_plan | project_plan | 687 | 1740 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 5/18/26 | Mon 5/18/26 | Thu 4/9/26 | 0% | Future Task | 1739 | Yes | No | 1740 | 5461360134f9b753472ed81d42e4baeff8821cc7af72c1bd3f8570d08c090380
project_plan | project_plan | 688 | 1741 |  | Load |  | Data Migration Team | Mon 5/18/26 | Tue 5/19/26 | Thu 4/9/26 | 0% | Future Task | 1740 | Yes | No | 1741 | 64acfc41a65a3beb7e52023167f6028c6e65568de96d7794023452f5a9d56254
project_plan | project_plan | 689 | 1742 |  | Post Load Validation |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Thu 4/9/26 | 0% | Future Task | 1741 | Yes | No | 1742 | 2bf0e93d376f8a11fe4f2182f53840cf67d8e4c45650726e5fb9a68ae98c2f4c
project_plan | project_plan | 690 | 1743 |  | RTR_CM08_Exchange_Rates |  |  | Tue 5/19/26 | Wed 5/20/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 1743 | 54783c621c60633030bd341b9bdab4157149b3cd79de0b71b4d7bf4085340385
project_plan | project_plan | 691 | 1744 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Thu 4/9/26 | 0% | Future Task | 1741 | Yes | No | 1744 | 4edcc57845f48b884795fc734a782a2f8aa9b905ae8e69bc28f01cb2e313d450
project_plan | project_plan | 692 | 1745 |  | Pre Load Validation |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Fri 4/10/26 | 0% | Future Task | 1744 | Yes | No | 1745 | d3124d4a9a9110e0dc27ab34e018d3a13f602a0900c04a4b4f8521151be5c226
project_plan | project_plan | 693 | 1746 |  | Simulate Load |  | Data Migration Team | Tue 5/19/26 | Tue 5/19/26 | Fri 4/10/26 | 0% | Future Task | 1745 | Yes | No | 1746 | f4962cf010245b136e500f87ab33e55faba36631b5bbe50d3e4daf67810a3213
project_plan | project_plan | 694 | 1747 |  | Error and Defect Mitigation |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Fri 4/10/26 | 0% | Future Task | 1746 | Yes | No | 1747 | cf3dc9e9d2a545d78166240e16db50ba943380fc30fac6dbb1e9a222db57afb5
project_plan | project_plan | 695 | 1748 |  | Load |  | Data Migration Team | Wed 5/20/26 | Wed 5/20/26 | Fri 4/10/26 | 0% | Future Task | 1747 | Yes | No | 1748 | 67b794520f171a83862729f01321deac0451cdac7d21d0bc718eea0549028f26
project_plan | project_plan | 696 | 1749 |  | Post Load Validation |  | Kasey Hughes | Wed 5/20/26 | Wed 5/20/26 | Fri 4/10/26 | 0% | Future Task | 1748 | Yes | No | 1749 | 9e031956a74978bbfe2178ef4afafaf9b27569d312566f0a716e5b8b5b62af3a
project_plan | project_plan | 697 | 1750 |  | RTR_CM14_Cost Element_Group |  | Kasey Hughes | Thu 5/21/26 | Mon 5/25/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 1750 | 72f0f9d467c5d639168c6dd3be3eb1c1d22844e76d2523e8e0159058e99dc70e
project_plan | project_plan | 698 | 1751 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Thu 5/21/26 | Thu 5/21/26 | Tue 4/14/26 | 0% | Future Task | 1700 | Yes | No | 1751 | c1a7b892c875598bd820e825f8fb91f7f776e880469ffc83404de17190766a59
project_plan | project_plan | 699 | 1752 |  | Load |  | Kasey Hughes | Thu 5/21/26 | Fri 5/22/26 | Wed 4/15/26 | 0% | Future Task | 1751 | Yes | No | 1752 | 167285c6b266f9caa6308d4c850b7d4679955116783269c872cb0239e9889011
project_plan | project_plan | 700 | 1753 |  | Post Load Validation |  | Kasey Hughes | Fri 5/22/26 | Mon 5/25/26 | Wed 4/15/26 | 0% | Future Task | 1752 | Yes | No | 1753 | 1132c21af1995034052e3eb27136cc8d63daf02f6f4d94f2e74e16ee4a3f15e7
project_plan | project_plan | 701 | 1754 |  | OTC_CM19_Customer_Master - Bill-To |  |  | Mon 5/18/26 | Mon 5/18/26 | Wed 4/16/25 | 0% | Future Task |  | Yes | No | 1754 | 76da2f623dfb5c3e2553dc99ba053dc177f3879a43c7dd69835611b2d8a25204
project_plan | project_plan | 702 | 1755 |  | OTC_CM19_Customer_Master - Ship-To |  |  | Thu 5/21/26 | Mon 5/25/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 1755 | 16f03b0a48a58fc98eddc6e6c8b5e2f8f5dd24a9c710fdfaecacbf2bcbf56655
project_plan | project_plan | 703 | 1756 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Thu 5/21/26 | Thu 5/21/26 | Wed 4/8/26 | 0% | Future Task | 1700 | Yes | No | 1756 | 144c56b3f5bc00a8d4c9dc8ed0acd83c4250eb140e72a2c7fff3d541b1515e1a
project_plan | project_plan | 704 | 1757 |  | Pre Load Validation |  | Ric Haraida | Thu 5/21/26 | Thu 5/21/26 | Wed 4/8/26 | 0% | Future Task | 1756 | Yes | No | 1757 | 85e90e50acacd24a1e96bed451d231b0f8762166c293fe0abb387319da1a9ea8
project_plan | project_plan | 705 | 1758 |  | Open client for BP number range update |  | Basis | Thu 5/21/26 | Thu 5/21/26 | Thu 4/9/26 | 0% | Future Task | 1757 | Yes | No | 1758 | 43e0bbbc0847e89bdf44b06b4d31ed13bb60f40157dd68c78e1af10f3b2ec6e3
project_plan | project_plan | 706 | 1759 |  | Update number range BP02 from Internal to External |  | Ric Haraida | Thu 5/21/26 | Thu 5/21/26 | Fri 4/10/26 | 0% | Future Task | 1758 | Yes | No | 1759 | 04d8efd7ecbc1b2799cfbc66fd060febad46ed857b58e1c58532fba42d017ce0
project_plan | project_plan | 707 | 1760 |  | Close Client |  | Basis | Thu 5/21/26 | Thu 5/21/26 | Mon 4/13/26 | 0% | Future Task | 1759 | Yes | No | 1760 | 372e1f0363a21748bb735ac81caa027a8755debff0071a3c9fa4435a18451eff
project_plan | project_plan | 708 | 1761 |  | Simulate Load |  | Data Migration Team | Thu 5/21/26 | Thu 5/21/26 | Thu 4/9/26 | 0% | Future Task | 1757 | Yes | No | 1761 | 55517c6dfaabfe750ccfca4c398b9aab545a462ffc78aa2ab254d9a373f6e88a
project_plan | project_plan | 709 | 1762 |  | Error and Defect Mitigation |  | Ric Haraida | Thu 5/21/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task | 1761 | Yes | No | 1762 | 603863c3946fbc970123dc22fa4c8fb03e15ac7cd63954ca32599111ba6cfdad
project_plan | project_plan | 710 | 1763 |  | Load |  | Data Migration Team | Fri 5/22/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task | 1762 | Yes | No | 1763 | 0e962f890e6a495fd12101533c81f0efe10d9a13beefb3342efeb9e4a4331e45
project_plan | project_plan | 711 | 1764 |  | Post Load Validation |  | Ric Haraida | Fri 5/22/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1763 | Yes | No | 1764 | cf46657ef09923af4f94e24d1e1781f05cf90b332dc74be425f8b2c4a8ddf3bc
project_plan | project_plan | 712 | 1765 |  | OTC_CM19_Customer_Master - Sold-To |  |  | Thu 5/21/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 1765 | 54c0560c79970c0cf82d098af9b40eb96ae4e1f6aa7cbe9da5beecaba8478560
project_plan | project_plan | 713 | 1766 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Thu 5/21/26 | Thu 5/21/26 | Thu 4/9/26 | 0% | Future Task | 1757 | Yes | No | 1766 | 9cedbb34162c769677d12274560e8c5ecce7ad56c2b910abd083c492bfbf598c
project_plan | project_plan | 714 | 1767 |  | Pre Load Validation |  | Ric Haraida | Thu 5/21/26 | Thu 5/21/26 | Thu 4/9/26 | 0% | Future Task | 1766 | Yes | No | 1767 | 3b088a3397b61a0b56858d1b81fb1b3060300b67f3f14beb9617837a53b282fa
project_plan | project_plan | 715 | 1768 |  | Simulate Load |  | Data Migration Team | Fri 5/22/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task | 17,021,761 | Yes | No | 1768 | 85fe5623ededc1fe2e25fb0fef3bd9b4db8f87c5b197cb7553e553d610de0b64
project_plan | project_plan | 716 | 1769 |  | Error and Defect Mitigation |  | Ric Haraida | Fri 5/22/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task | 1768 | Yes | No | 1769 | 6fc667891c8407824a367293e8137c673589cd0e8203b65cb08fcc2f7a60e26c
project_plan | project_plan | 717 | 1770 |  | Load |  | Data Migration Team | Fri 5/22/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1769 | Yes | No | 1770 | 04215f510a9e95ded2767d2aed0b045eaedfb87d57553ffebcf298fde29b73ba
project_plan | project_plan | 718 | 1771 |  | Post Load Validation |  | Ric Haraida | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1770 | Yes | No | 1771 | be4f311681b73b4bd34e942657e9701d67a20a8b221c2a19a18b7ce50b006437
project_plan | project_plan | 719 | 1772 |  | Open client for BP number range update |  | Basis | Thu 5/21/26 | Thu 5/21/26 | Thu 4/9/26 | 0% | Future Task | 1761 | Yes | No | 1772 | 22ef436cbc11fe9d13efa2e26d534bcc58a02aa1864c7ea365ee85247c527b5b
project_plan | project_plan | 720 | 1773 |  | Update number range BP02 from Internal to External |  | Ric Haraida | Thu 5/21/26 | Thu 5/21/26 | Thu 4/9/26 | 0% | Future Task | 1772 | Yes | No | 1773 | 4ead1845b20fcc6f3a7540d340deb1f2f14765e6644146dec1e40f55f01b1e46
project_plan | project_plan | 721 | 1774 |  | Close Client |  | Basis | Fri 5/22/26 | Fri 5/22/26 | Thu 4/9/26 | 0% | Future Task | 1773 | Yes | No | 1774 | 5163a67f6245e9655e07bdb09ab5ad987a45ef860e04a725193a5f8a9f355357
project_plan | project_plan | 722 | 1775 |  | PTP_CM27_Vendor Master as Customer - FLCU01 |  |  | Mon 5/25/26 | Fri 5/29/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 1775 | 2b9aa0c6a98c7429c835c91d589721c5167c44284b034da700ed975787dec9b5
project_plan | project_plan | 723 | 1776 |  | Extract File |  | Data Migration Team | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1770 | Yes | No | 1776 | d8f7d433735408634aa05d15f8ba89c5272ac0b4beef689e2a6158c2bb4096c5
project_plan | project_plan | 724 | 1777 |  | Pre Load Validation |  | Nevin Varkey | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1776 | Yes | No | 1777 | 4fb57cc5e1679d1c9f640c6011d35fd054a868ee381fbf882e978a4eb3b76e4c
project_plan | project_plan | 725 | 1778 |  | Simulate Load |  | Data Migration Team | Mon 5/25/26 | Tue 5/26/26 | Mon 4/13/26 | 0% | Future Task | 17,421,777 | Yes | No | 1778 | d9ede0c977163bf5f38037e73012f445e6b856f7fa860db36bc85091518b1bfd
project_plan | project_plan | 726 | 1779 |  | Error and Defect Mitigation |  | Nevin Varkey | Tue 5/26/26 | Thu 5/28/26 | Tue 4/14/26 | 0% | Future Task | 1778 | Yes | No | 1779 | 8383852385b151ffc01c5baca4e359ae7e915b9046f92e99c5558b4e18163b91
project_plan | project_plan | 727 | 1780 |  | Load |  | Data Migration Team | Thu 5/28/26 | Fri 5/29/26 | Tue 4/14/26 | 0% | Future Task | 1779 | Yes | No | 1780 | 2b692de56ebaa58bedd92d4143eeb913b0b6121618a608c460b1ab85291428d6
project_plan | project_plan | 728 | 1781 |  | Post Load Validation |  | Nevin Varkey | Fri 5/29/26 | Fri 5/29/26 | Tue 4/14/26 | 0% | Future Task | 1780 | Yes | No | 1781 | e2e927b8bf4cd977110aa94970cb0d467aaa881784245851336393e03be64a15
project_plan | project_plan | 729 | 1782 |  | OTC_CM23_Customer_Hierarchy |  |  | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 1782 | 8877319309c21442478b1682555dec32b1e93c42a358235efcec3377615a93ff
project_plan | project_plan | 730 | 1783 |  | Manual File Staged and Posted "Ready" |  | Ric Haraida | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1770 | Yes | No | 1783 | 9448e3f119f39d40e9ba96987d21306b1c56d60ae1ecde6e6691fca30a921841
project_plan | project_plan | 731 | 1784 |  | Load |  | Ric Haraida | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1783 | Yes | No | 1784 | 77e77817e333c0a534c0dde1d02dd24dac44e33ee670bd55c1ef93a49f69988d
project_plan | project_plan | 732 | 1785 |  | Post Load Validation |  | Ric Haraida | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1784 | Yes | No | 1785 | 59b1ab6f8ef8e6773b09f0d5639d0ffaef34fb4a6eeeff7310149ad0fcb29c50
project_plan | project_plan | 733 | 1786 |  | PTP_CM27_Vendor Master - Z001 - External Sales Rep |  |  | Mon 5/25/26 | Thu 5/28/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 1786 | 62f0aad81e2783a7f4032ada3047d3547e22cdea52d960d9ca8a32893dde8a17
project_plan | project_plan | 734 | 1787 |  | Extract File |  | Data Migration Team | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1770 | Yes | No | 1787 | 99b189ae6341ee3b1345ad7f0c8286cc1271350256a0199ed79635ec5d4b4ea7
project_plan | project_plan | 735 | 1788 |  | Pre Load Validation |  | Nevin Varkey | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1787 | Yes | No | 1788 | c5d403f0398c7411fa1955a1387e17ceb8196d60184540d8b62b103132a26a0f
project_plan | project_plan | 736 | 1789 |  | Simulate Load |  | Data Migration Team | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 17,421,788 | Yes | No | 1789 | 2bc5e23ee938c1f9289917f31ee689d7a0a6fcfba0b257404c70ed477d0e83e0
project_plan | project_plan | 737 | 1790 |  | Error and Defect Mitigation |  | Nevin Varkey | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1789 | Yes | No | 1790 | 6962608e2fc6ef8154fde9d1bed91c4e3d20efc9e1b3d5a520a3abf5929bb35a
project_plan | project_plan | 738 | 1791 |  | Load |  | Data Migration Team | Mon 5/25/26 | Thu 5/28/26 | Mon 4/13/26 | 0% | Future Task | 1790 | Yes | No | 1791 | 30b89a73f11ccb78059e6bf94aa11aeb527a726a9115672036796f0761ae7f9b
project_plan | project_plan | 739 | 1792 |  | Post Load Validation |  | Nevin Varkey | Thu 5/28/26 | Thu 5/28/26 | Mon 4/13/26 | 0% | Future Task | 1791 | Yes | No | 1792 | 38d53136552354628172f4643869aa64c26c41d97ab8ed5e42d64b6000abc5ea
project_plan | project_plan | 740 | 1793 |  | RTR_CM10_Credit_Management_Role |  |  | Mon 5/25/26 | Tue 5/26/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 1793 | dd8bf54863cf23a753f1df35f1021ee80cbf509725647938e8ff753910f44b93
project_plan | project_plan | 741 | 1794 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1770 | Yes | No | 1794 | 8110256b0c9fff97e5456088f4006655fa05048740ff9f1257ad892e357e7aaa
project_plan | project_plan | 742 | 1795 |  | Pre Load Validation |  | Kasey Hughes | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1794 | Yes | No | 1795 | f2adc613c3b2bd88942945002addfdea7204667967f94fa516dd85bfb1756376
project_plan | project_plan | 743 | 1796 |  | Simulate Load |  | Data Migration Team | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1795 | Yes | No | 1796 | 4eddb400309e93ffc0209dcf061fd356f11cdae86ca14ef95684901eebd627c7
project_plan | project_plan | 744 | 1797 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1796 | Yes | No | 1797 | 9a45564de6776c9da232da34de2b88525d370805b2315d17686d74f5e66eb260
project_plan | project_plan | 745 | 1798 |  | Load |  | Data Migration Team | Mon 5/25/26 | Tue 5/26/26 | Fri 4/10/26 | 0% | Future Task | 1797 | Yes | No | 1798 | ac88c015cc570ce8246c1465fcac16f1e5d49449bc5640051b165cced9edf0ba
project_plan | project_plan | 746 | 1799 |  | Post Load Validation |  | Kasey Hughes | Tue 5/26/26 | Tue 5/26/26 | Mon 4/13/26 | 0% | Future Task | 1798 | Yes | No | 1799 | d0a5c280f1446abccef0b29fdeaf76c4580b8efa9d4a57ddf2e5d2b37ed29743
project_plan | project_plan | 747 | 1800 |  | PTP_CM27_Vendor Master |  |  | Mon 5/18/26 | Tue 5/26/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 1800 | e5a776572d37a285e5089442134adfc75677f2716737454ab1f8c48573e0cde2
project_plan | project_plan | 748 | 1801 |  | Extract File |  | Data Migration Team | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1787 | Yes | No | 1801 | 57e1c8d8119f57333d5da2cd17267f73741f8bfb70f37d4e8ddfa4b94cd6b6cf
project_plan | project_plan | 749 | 1802 |  | Pre Load Validation |  | Nevin Varkey | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1801 | Yes | No | 1802 | caf07aab561fcaff650e1a0091e36272dd01ddccc4d38dafc4e2da92ca4bd399
project_plan | project_plan | 750 | 1803 |  | Simulate Load |  | Data Migration Team | Mon 5/25/26 | Mon 5/25/26 | Tue 4/14/26 | 0% | Future Task | 1802 | Yes | No | 1803 | 81964e10d6dceb73ca5fbf5c8fa60a3cb94be143971a33a017f2df7fa23ea6f6
project_plan | project_plan | 751 | 1804 |  | Error and Defect Mitigation |  | Nevin Varkey | Mon 5/25/26 | Tue 5/26/26 | Tue 4/14/26 | 0% | Future Task | 1803 | Yes | No | 1804 | d0e1b59f9845e58a019f6975d5357530571a04218af585fb1033f5cd880cce85
project_plan | project_plan | 752 | 1805 |  | Load |  | Data Migration Team | Mon 5/18/26 | Mon 5/18/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 1805 | b2f2042c3d0725fc014a2b3e121db2a1aea60135ebdb41b6137985117ca38f0f
project_plan | project_plan | 753 | 1806 |  | Post Load Validation |  | Nevin Varkey | Mon 5/18/26 | Mon 5/18/26 | Wed 4/15/26 | 0% | Future Task | 1805 | Yes | No | 1806 | aa7b7adb4bb990c2c13f26e147e07f59bdbe8e775dbcd0ca44682a26fae24cc0
project_plan | project_plan | 754 | 1807 |  | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR |  |  | Mon 5/18/26 | Tue 5/19/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 1807 | d98a65441838c55eb6bf3c3181ed2d1cfb1d0e002e1c6e2c7990ec64eaab96ba
project_plan | project_plan | 755 | 1808 |  | Extract File(Will Extract from LFA1) |  | Nevin Varkey | Mon 5/18/26 | Mon 5/18/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 1808 | e926682e791ab74f1a206044ad1381a2035f092aae338e7fc2399359d0e6ddf7
project_plan | project_plan | 756 | 1809 |  | Pre Load Validation |  | Nevin Varkey | Mon 5/18/26 | Mon 5/18/26 | Fri 4/10/26 | 0% | Future Task | 1808 | Yes | No | 1809 | 92776cc842344248a74b5f5d6203593dc3369034d68be67fe01e8e5d197feec5
project_plan | project_plan | 757 | 1810 |  | Simulate Load/ Not Needed |  | Nevin Varkey | Mon 5/18/26 | Mon 5/18/26 | Fri 4/10/26 | 0% | Future Task | 1809 | Yes | No | 1810 | 766aebed5c1e09c5d38f1006247ece4e39a30f1e6242fd75258543cb04f5ae6f
project_plan | project_plan | 758 | 1811 |  | Error and Defect Mitigation |  | Nevin Varkey | Mon 5/18/26 | Mon 5/18/26 | Mon 4/13/26 | 0% | Future Task | 1810 | Yes | No | 1811 | 8bfa2aa6496387dc9615cd9fdf5a52cb1081738ecff2eaa67e9fb0de9bf16342
project_plan | project_plan | 759 | 1812 |  | Load |  | Nevin Varkkey | Mon 5/18/26 | Mon 5/18/26 | Wed 4/15/26 | 0% | Future Task | 1810 | Yes | No | 1812 | 522d8f2976dcfe4bbb1fce1848913c311736db674ad82221283a1a1105ae62f8
project_plan | project_plan | 760 | 1813 |  | Post Load Validation |  | Nevin Varkey | Mon 5/18/26 | Tue 5/19/26 | Wed 4/15/26 | 0% | Future Task | 1812 | Yes | No | 1813 | f29fcf2d83ad0eac08599a83a3d6f5215d3b3d41b9021cabfd308a482c09083d
project_plan | project_plan | 761 | 1814 |  | RTR_****_Credit Hierarchy |  |  | Mon 5/25/26 | Wed 5/27/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 1814 | 160d39dad7dc90ea31514e40f7abd66a9f958a3ca18b20d462f5989744197575
project_plan | project_plan | 762 | 1815 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Mon 5/25/26 | Mon 5/25/26 | Fri 4/10/26 | 0% | Future Task | 1797 | Yes | No | 1815 | 0141470671a3b12a7fd0800c44ab4f2ae4583ae1897f7c546156a2a73783db8a
project_plan | project_plan | 763 | 1816 |  | Load |  | Kasey Hughes | Tue 5/26/26 | Wed 5/27/26 | Mon 4/13/26 | 0% | Future Task | 1799 | Yes | No | 1816 | ae5ea1d95efdda14a83555700329e11f44032c17aad55e4d5b95c48366ce9f71
project_plan | project_plan | 764 | 1817 |  | Post Load Validation |  | Kasey Hughes | Wed 5/27/26 | Wed 5/27/26 | Mon 4/13/26 | 0% | Future Task | 1816 | Yes | No | 1817 | 161333f410f83786b8c80de030897d23381c81a9f43d6e29726b6f6c29d99d4f
project_plan | project_plan | 765 | 1818 |  | PTP_CM27_BP_Intercompany Supplier |  |  | Mon 5/18/26 | Tue 5/19/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 1818 | 553a5cacc22a72ad624d0c04626e0a657227c7969029555b55708c46321fd6dc
project_plan | project_plan | 766 | 1819 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Mon 5/18/26 | Mon 5/18/26 | Mon 4/13/26 | 0% | Future Task | 1806 | Yes | No | 1819 | b56cbd3fe8776f5b44a59d0c5518d93565d14a1237f928e32dfb758d497f5768
project_plan | project_plan | 767 | 1820 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Mon 5/18/26 | Mon 5/18/26 | Mon 4/13/26 | 0% | Future Task | 1819 | Yes | No | 1820 | 67dd4ecd0fa7c60d5719e4967dc68ff6e60634f8102ad3feecee14f6f8582c44
project_plan | project_plan | 768 | 1821 |  | Simulate Load |  | Data Migration Team | Mon 5/18/26 | Mon 5/18/26 | Mon 4/13/26 | 0% | Future Task | 1820 | Yes | No | 1821 | 7dbbabd53ddb639eef00f1cdc3d4c08825d570e94b9a3446e38e1a8c475cddfe
project_plan | project_plan | 769 | 1822 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Mon 5/18/26 | Tue 5/19/26 | Mon 4/13/26 | 0% | Future Task | 1821 | Yes | No | 1822 | 89aa75df1832f118cb6036a5b8bbfdfd0f07d964188d7f5e2f097c034c836a36
project_plan | project_plan | 770 | 1823 |  | Load |  | Data Migration Team | Tue 5/19/26 | Tue 5/19/26 | Tue 4/14/26 | 0% | Future Task | 1822 | Yes | No | 1823 | 66c48d95b88b19755c4d2711b08784dc2697a13b86621f3029d226ec6b01b08f
project_plan | project_plan | 771 | 1824 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Tue 5/19/26 | Tue 5/19/26 | Tue 4/14/26 | 0% | Future Task | 1823 | Yes | No | 1824 | ef63fc732e5b312cab069eb580b6645279b68e34d21f6396658cb33dda1bef85
project_plan | project_plan | 772 | 1825 |  | PTP_CM27_BP_Intercompany Customer |  |  | Mon 5/18/26 | Tue 5/19/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 1825 | 05643d03e7a2911b2cd22ef88c124879168ddb147252603e4fb694f1ac902860
project_plan | project_plan | 773 | 1826 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Mon 5/18/26 | Mon 5/18/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 1826 | adc1b8e6e0123ce0422b172a56d3ba1886f455dc485754b67b6550490101a786
project_plan | project_plan | 774 | 1827 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Mon 5/18/26 | Mon 5/18/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 1827 | 15e23e5ce59a128fd2ec9befdc34ad58f175a9626238f877fcbabce400943253
project_plan | project_plan | 775 | 1828 |  | Simulate Load |  | Data Migration Team | Mon 5/18/26 | Mon 5/18/26 | Mon 4/13/26 | 0% | Future Task | 1827 | Yes | No | 1828 | 1496bb312bf6bfc8da187107ea7cf5781052f23f89e74fc73d085d32511336ad
project_plan | project_plan | 776 | 1829 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Mon 5/18/26 | Mon 5/18/26 | Mon 4/13/26 | 0% | Future Task | 1828 | Yes | No | 1829 | a8a072a08988354ccb84feddb50dfbcb53cd4ad1251965234890870b52edbead
project_plan | project_plan | 777 | 1830 |  | Load |  | Data Migration Team | Mon 5/18/26 | Mon 5/18/26 | Tue 4/14/26 | 0% | Future Task | 1829 | Yes | No | 1830 | 7be16b1cb9ddc30d7bf8ff23393869e8137b1a50a4a57923696d777de994f2f9
project_plan | project_plan | 778 | 1831 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Mon 5/18/26 | Tue 5/19/26 | Tue 4/14/26 | 0% | Future Task | 1830 | Yes | No | 1831 | 923ce0fcd2f7e26a81b391380477953d5f7ae66aeb538a56b05b8031c62567dc
project_plan | project_plan | 779 | 1832 |  | PTP_CM26_Material_Master - All Types |  |  | Mon 5/18/26 | Wed 5/20/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 1832 | 902a26cefd6fee5dfd260b289fbb8965cf25dd2ac85ae5e4cc9338a4a00a9bb1
project_plan | project_plan | 780 | 1833 |  | Extract File |  | Data Migration Team | Mon 5/18/26 | Tue 5/19/26 | Mon 4/13/26 | 0% | Future Task | 1808 | Yes | No | 1833 | a45fc76ecf54c867d9f2f44680fff8406e6f77c8248e1bc6b8f5b025a8bd6382
project_plan | project_plan | 781 | 1834 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Mon 5/18/26 | Tue 5/19/26 | Tue 4/14/26 | 0% | Future Task | 1806 | Yes | No | 1834 | 1d384389a021344671acf2b337dd300d710a1f4efc8338fe154584f0bf055632
project_plan | project_plan | 782 | 1835 |  | Simulate Load |  | Data Migration Team | Tue 5/19/26 | Tue 5/19/26 | Tue 4/14/26 | 0% | Future Task | 1834 | Yes | No | 1835 | 05696b87f08bde3b69913b999a2da26fbd6f34cd87ee531979f8007e6406e7d8
project_plan | project_plan | 783 | 1836 |  | Error and Defect Mitigation |  | Nevin Varkey | Tue 5/19/26 | Wed 5/20/26 | Tue 4/14/26 | 0% | Future Task | 1835 | Yes | No | 1836 | bd392b97f31f16a6c9f791fbe84c81c13f2bb77cf86bfc1dbf834798ba192aa9
project_plan | project_plan | 784 | 1837 |  | Load |  | Data Migration Team | Wed 5/20/26 | Wed 5/20/26 | Wed 4/15/26 | 0% | Future Task | 1836 | Yes | No | 1837 | 6daac97ee83fe3722fd3803a5ad67cd4a4858d7274b1e884bf93adc2e7c09c52
project_plan | project_plan | 785 | 1838 |  | Post Load Validation |  | Nevin Varkey | Wed 5/20/26 | Wed 5/20/26 | Wed 4/15/26 | 0% | Future Task | 1837 | Yes | No | 1838 | b0d3b2f9e6a8d154f1e90517a26ebfbc308b034fc61d8a6ed85b856fcd44337e
project_plan | project_plan | 786 | 1839 |  | PTP_CM26_Material_Master - SERV - Service Materials |  |  | Wed 5/20/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 1839 | b2ab6bf38334fbe8369e71c45b73909315666e93dec1e38ee3610c62961d8761
project_plan | project_plan | 787 | 1840 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Wed 5/20/26 | Wed 5/20/26 | Tue 4/7/26 | 0% | Future Task | 1709 | Yes | No | 1840 | 0223cbaefd7c6d4a68a984e25c7624a1d73f5a62c82791dc76141502d16e9458
project_plan | project_plan | 788 | 1841 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Wed 5/20/26 | Wed 5/20/26 | Tue 4/14/26 | 0% | Future Task | 1837 | Yes | No | 1841 | 9921c54375165e04546611ac3ba4dfb399ed267371e8398ab31ef7c7d8e40d1f
project_plan | project_plan | 789 | 1842 |  | Simulate Load |  | Data Migration Team | Wed 5/20/26 | Wed 5/20/26 | Tue 4/14/26 | 0% | Future Task | 1841 | Yes | No | 1842 | 3014898d959a2a030a54100b82a4f44847917cd4f73e7f74f9cfd4b159961540
project_plan | project_plan | 790 | 1843 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Wed 5/20/26 | Wed 5/20/26 | Wed 4/15/26 | 0% | Future Task | 1842 | Yes | No | 1843 | e1164575bd81700cb933ac5420d8bc92e49e89c1ac60a6132faa7a966b9f4802
project_plan | project_plan | 791 | 1844 |  | Load |  | Data Migration Team | Wed 5/20/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task | 1843 | Yes | No | 1844 | 8605a651e2d57c00ccdc3e9aced3a3079db0d78ff5d256e974d80099187a15ae
project_plan | project_plan | 792 | 1845 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Thu 5/21/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task | 1844 | Yes | No | 1845 | bef5c0277e0e63c7ff849c70a3901adc38b451e6738dda74f06df4869adc93db
project_plan | project_plan | 793 | 1846 |  | PTP_CM26_Material_Master - KMAT - Configurable Materials |  |  | Wed 5/20/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 1846 | fb484c253402a090ee339e454450c7df5beb6acd25f491e4c7a6e8ae51b0c58d
project_plan | project_plan | 794 | 1847 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Wed 5/20/26 | Wed 5/20/26 | Tue 4/7/26 | 0% | Future Task | 1709 | Yes | No | 1847 | 7eb4a03b19bdb933201221f54ae3f7501049e56e615663c527ac2f565e4c03cb
project_plan | project_plan | 795 | 1848 |  | Pre Load Validation |  | Eric Heisler | Wed 5/20/26 | Wed 5/20/26 | Tue 4/14/26 | 0% | Future Task | 1837 | Yes | No | 1848 | c5e764e3e2da571da11b3b88a97d2fed7af2dbfe220dfa803a08e8b5bf489edd
project_plan | project_plan | 796 | 1849 |  | Simulate Load |  | Data Migration Team | Wed 5/20/26 | Wed 5/20/26 | Tue 4/14/26 | 0% | Future Task | 1848 | Yes | No | 1849 | 63693597dad15ad0e1a4bc2c9de50affd9f14ed2de943be982cde182bdc61f95
project_plan | project_plan | 797 | 1850 |  | Error and Defect Mitigation |  | Eric Heisler | Wed 5/20/26 | Wed 5/20/26 | Wed 4/15/26 | 0% | Future Task | 1849 | Yes | No | 1850 | 0d47bd66cd98813f6f2c8648e6af500c740c790a1a82c1642fb2e81161bda33b
project_plan | project_plan | 798 | 1851 |  | Load |  | Data Migration Team | Wed 5/20/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task | 1850 | Yes | No | 1851 | 8be788acaf12ae94768ce54af39ca10cee8245da94cc940c74a241362c033f05
project_plan | project_plan | 799 | 1852 |  | Post Load Validation |  | Eric Heisler | Thu 5/21/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task | 1851 | Yes | No | 1852 | dba86de752cdcf4f2350c129470b4ce1b06f4cd8d48ec29cfd2a68e0fa8d49b3
project_plan | project_plan | 800 | 1853 |  | PTP_CM28_Purchase_Info_Records |  |  | Mon 5/18/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 1853 | 0ed006f79c38e4dc692afde985b033460e725ed7478ab8a5b86ad2eb42d092bb
project_plan | project_plan | 801 | 1854 |  | Extract File |  | Data Migration Team | Thu 5/21/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task | 18,381,852 | Yes | No | 1854 | 7a1e411b1c2745f64bc26464a4bff72dcff9cc15da64c8fd7e83f55efad3f8eb
project_plan | project_plan | 802 | 1855 |  | Pre Load Validation |  | Nevin Varkey | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 1854 | Yes | No | 1855 | 3253ec251569f0791aee00c816695d8f60ee65a3a0b4a32c0e6cdc48d4ca8893
project_plan | project_plan | 803 | 1856 |  | Simulate Load |  | Data Migration Team | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 1855 | Yes | No | 1856 | cfe60465afdf76f8ac3f96cc955c1fb0a6c6d39d2d7efc31e149c0c3f62faecc
project_plan | project_plan | 804 | 1857 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1856 | Yes | No | 1857 | cbbacdae3ee542aff0bd577d655a231cd8ebd3670afe95d3c73163e8549f8088
project_plan | project_plan | 805 | 1858 |  | Load |  | Data Migration Team | Mon 5/18/26 | Mon 5/18/26 | Wed 4/15/26 | 0% | Future Task | 1806 | Yes | No | 1858 | 2105726a541b104397fa14c8df3dd571950e345dda2a5614bbb26b4fee123b27
project_plan | project_plan | 806 | 1859 |  | Post Load Validation |  | Nevin Varkey | Mon 5/18/26 | Mon 5/18/26 | Wed 4/15/26 | 0% | Future Task | 1858 | Yes | No | 1859 | 39c70c67112885b8977c579b215719677edb286396f1549131ba08b7026bba00
project_plan | project_plan | 807 | 1860 |  | PTP_CM28_Purchase_Info_Record External Processing |  |  | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 1860 | e9632fb05b63ebd4e95b331da5fb9817de23c2adea2e81b1cb6cc43902df50e8
project_plan | project_plan | 808 | 1861 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey | Thu 5/21/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task | 18,381,852 | Yes | No | 1861 | b6f3369f3a304d7a160084948a18d7f55efbf238b30a684edac6da00335a6257
project_plan | project_plan | 809 | 1862 |  | Pre Load Validation |  | Nevin Varkey | Thu 5/21/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task | 1861 | Yes | No | 1862 | 946e281266369f9315c5926e9ec470c0a0ee1937a1d941f3816b1022f5a3b86e
project_plan | project_plan | 810 | 1863 |  | Simulate Load |  | Data Migration Team | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 1862 | Yes | No | 1863 | 6b1b8f114880a9466c869868ba27c99fba36ad70fe4ec8063d1411b9c5153217
project_plan | project_plan | 811 | 1864 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 1863 | Yes | No | 1864 | 292e61416469985e5f45bd67845f29736343aadc027569e5ce68b349e8c40fb5
project_plan | project_plan | 812 | 1865 |  | Load |  | Data Migration Team | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1864 | Yes | No | 1865 | 04b0790d4d0eb05837ee575d2684cd55c66c8d9c75a894fb90d05420fb73b906
project_plan | project_plan | 813 | 1866 |  | Post Load Validation |  | Nevin Varkey | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1865 | Yes | No | 1866 | fe5ff16dd25a62957e717b3407db2840b2f0cea70e77965137266a4a3334b0c4
project_plan | project_plan | 814 | 1867 |  | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment |  |  | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 1867 | 054017aba573270881d74c52dcfd7029fd9a29179e3accc21fa15354d9d2582e
project_plan | project_plan | 815 | 1868 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey | Thu 5/21/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task | 18,381,852 | Yes | No | 1868 | 5e6a4c1ca7acf062941883099cb4186a35a1618e231f83ac03211b900681e4d5
project_plan | project_plan | 816 | 1869 |  | Pre Load Validation |  | Nevin Varkey | Thu 5/21/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task | 1868 | Yes | No | 1869 | ae40c55c5982b4f92c523f0582824452104e72ccdd02ca5eee5a50bbe58da22b
project_plan | project_plan | 817 | 1870 |  | Simulate Load |  | Data Migration Team | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 1869 | Yes | No | 1870 | 212a29d4c2b7b8f04f9a2ccc0f9256aff8cd04032611ccfd2f754c36e725f91c
project_plan | project_plan | 818 | 1871 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 1870 | Yes | No | 1871 | f09ac9b5af913cf680103042613ead4069967c56e9d0e7694f8ab1d1cb95c307
project_plan | project_plan | 819 | 1872 |  | Load |  | Data Migration Team | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1871 | Yes | No | 1872 | 3a3cb15380f7d73898c94445c4674fead34ca1936b1dd618993124305a82affd
project_plan | project_plan | 820 | 1873 |  | Post Load Validation |  | Nevin Varkey | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1872 | Yes | No | 1873 | 3400ac1ebb0f3d8110eeee7d8a5d0b85a16198378eb5221341071289bddfd9f3
project_plan | project_plan | 821 | 1874 |  | PTM_CM31_BOM Conversion |  |  | Thu 5/21/26 | Tue 5/26/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 1874 | 1bcbf26fad22be13320a8b0a952fa4b982bd8945d8538e20edcb3fdfe0b93167
project_plan | project_plan | 822 | 1875 |  | Extract File |  | Data Migration Team | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 1854 | Yes | No | 1875 | 796f5b07b6a8f1406b2570433499563c528b70f4256d751edd76a343f6a989a0
project_plan | project_plan | 823 | 1876 |  | Pre Load Validation |  | Brad Meseck | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 1875 | Yes | No | 1876 | 658c5da03881f6a57929ca1fc4232bb2f82649801f7127c1e91288b92cebab71
project_plan | project_plan | 824 | 1877 |  | Simulate Load |  | Data Migration Team | Thu 5/21/26 | Mon 5/25/26 | Thu 4/16/26 | 0% | Future Task | 1876 | Yes | No | 1877 | 041dd0ff952727286e182e21ceded1e32cda0458c14317a635f56f7e0b446653
project_plan | project_plan | 825 | 1878 |  | Error and Defect Mitigation |  | Brad Meseck | Mon 5/25/26 | Mon 5/25/26 | Thu 4/16/26 | 0% | Future Task | 1877 | Yes | No | 1878 | ab0ca7c8baec58f9064b916c0d2dca535f155fcbc03c0b0e6eebdf01479b46e3
project_plan | project_plan | 826 | 1879 |  | Load |  | Data Migration Team | Mon 5/25/26 | Mon 5/25/26 | Thu 4/16/26 | 0% | Future Task | 1878 | Yes | No | 1879 | 3f0a3c273b598e4d3ae5817b67d8af30c1c20c4642cf6834607893f45f47cc90
project_plan | project_plan | 827 | 1880 |  | Post Load Validation |  | Brad Meseck | Tue 5/26/26 | Tue 5/26/26 | Fri 4/17/26 | 0% | Future Task | 1879 | Yes | No | 1880 | b795bc46d8dbd02ef0d7de75f3410576a08edf1b67ab950a36c042e75369c5b6
project_plan | project_plan | 828 | 1881 |  | PTM_CM40_Work Center Conversion |  |  | Thu 5/21/26 | Tue 5/26/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 1881 | a2ba35a22e64349d4cde974ba9beb028f857f038cf2d57da1885b25ec435fa80
project_plan | project_plan | 829 | 1882 |  | Extract File |  | Data Migration Team | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 1875 | Yes | No | 1882 | 5ff1cc734843365a8a1927f0ca77dd91677e06151ed1c7713ea335add1746fd7
project_plan | project_plan | 830 | 1883 |  | Pre Load Validation |  | Brad Meseck | Tue 5/26/26 | Tue 5/26/26 | Fri 4/17/26 | 0% | Future Task | 1880 | Yes | No | 1883 | cc8e0ac64d79f7a97316aac46580a68512a6ce67ba0f00649837adf32b29f0dd
project_plan | project_plan | 831 | 1884 |  | Simulate Load |  | Data Migration Team | Tue 5/26/26 | Tue 5/26/26 | Fri 4/17/26 | 0% | Future Task | 1883 | Yes | No | 1884 | 197e932be8647f0c5425d2069b2557c09a65eda0649b98704857e24e63ce3c6c
project_plan | project_plan | 832 | 1885 |  | Error and Defect Mitigation |  | Brad Meseck | Tue 5/26/26 | Tue 5/26/26 | Fri 4/17/26 | 0% | Future Task | 1884 | Yes | No | 1885 | 41c0311349ccea899a4b09802daae6ec6b1747899d1666a77a3e430ed522b8a1
project_plan | project_plan | 833 | 1886 |  | Load |  | Data Migration Team | Tue 5/26/26 | Tue 5/26/26 | Fri 4/17/26 | 0% | Future Task | 1885 | Yes | No | 1886 | 3d830d74fedc6642901ddb1ef850800c9735c9ee9232785d65482f3471b3a584
project_plan | project_plan | 834 | 1887 |  | Post Load Validation |  | Brad Meseck | Tue 5/26/26 | Tue 5/26/26 | Mon 4/20/26 | 0% | Future Task | 1886 | Yes | No | 1887 | aa867ad34f9e6a04a5595ba75428121b3240580a63476b647bcf0a89a1ee7910
project_plan | project_plan | 835 | 1888 |  | PTM_CM38_Routing Conversion |  |  | Thu 5/21/26 | Thu 5/28/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 1888 | 12d68cf27697a4698b2bf98cea841529f76480c7702e501ae8ebb5981de68fba
project_plan | project_plan | 836 | 1889 |  | Extract File |  | Data Migration Team | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 1882 | Yes | No | 1889 | 1b4b33a8ada75c08f47da7fe5885de8f801cf2cd6360c7747962973f8131ae3d
project_plan | project_plan | 837 | 1890 |  | Pre Load Validation |  | Brad Meseck | Tue 5/26/26 | Wed 5/27/26 | Mon 4/20/26 | 0% | Future Task | 1887 | Yes | No | 1890 | 0a5781fb002f5b6331553bd95d3a22c47345b9f871c6caf949edec4daaae06c7
project_plan | project_plan | 838 | 1891 |  | Simulate Load |  | Data Migration Team | Wed 5/27/26 | Wed 5/27/26 | Mon 4/20/26 | 0% | Future Task | 1890 | Yes | No | 1891 | 858a6b242f3883abfc18f92706793404faa5372f6f2f010666364c431608d2a9
project_plan | project_plan | 839 | 1892 |  | Error and Defect Mitigation |  | Brad Meseck | Wed 5/27/26 | Wed 5/27/26 | Mon 4/20/26 | 0% | Future Task | 1891SS | Yes | No | 1892 | 5d6d58c0c6366f195a877487d40f2bffd26253bcf9199bd61db49029729b4ab1
project_plan | project_plan | 840 | 1893 |  | Load |  | Data Migration Team | Wed 5/27/26 | Wed 5/27/26 | Mon 4/20/26 | 0% | Future Task | 1892 | Yes | No | 1893 | e1dcb7891755ed02ff27f96e989c8942cd4bb0c9b813a15537326e38d1659380
project_plan | project_plan | 841 | 1894 |  | Post Load Validation |  | Brad Meseck | Wed 5/27/26 | Thu 5/28/26 | Tue 4/21/26 | 0% | Future Task | 1893 | Yes | No | 1894 | 10e3b10d03adf82ab44548c9d5f46ed2533b33dbee2439d456c9c4419969a560
project_plan | project_plan | 842 | 1895 |  | PTM_CM36_Production Version Conversion |  |  | Thu 5/21/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 1895 | 50194ac06228dabbc9acc927ad30f9c8e8d42787f5228ef8a4b5b050a04c205d
project_plan | project_plan | 843 | 1896 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1889 | Yes | No | 1896 | b8f5a7d9041226bb1ab708f3b2d7cdfe661661f28f860e0fe707a077b1d4919b
project_plan | project_plan | 844 | 1897 |  | Pre Load Validation |  | Brad Meseck | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1896 | Yes | No | 1897 | d3095a885eb8367eb833ef5ccac0c16fecf11a6b2ce1adc84c9afd1385bd41bc
project_plan | project_plan | 845 | 1898 |  | Simulate Load |  | Data Migration Team | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1897 | Yes | No | 1898 | 5c808884ef6f0c70cd30bb6ac4eabe988e648c18d46c2006f1f534693353c957
project_plan | project_plan | 846 | 1899 |  | Error and Defect Mitigation |  | Brad Meseck | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1898 | Yes | No | 1899 | f531e18b4da9f83cd32ffc95695a8bee8c744452616a61baa124310e872fc2af
project_plan | project_plan | 847 | 1900 |  | Load |  | Data Migration Team | Fri 5/22/26 | Fri 5/22/26 | Fri 4/17/26 | 0% | Future Task | 1899 | Yes | No | 1900 | 26b12afbb9607ca93edcaa5bc376e6aa2a2567229f9d599e06c3670f2a213369
project_plan | project_plan | 848 | 1901 |  | Post Load Validation |  | Brad Meseck | Fri 5/22/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task | 1900 | Yes | No | 1901 | e9795004de36b5552172cdc70ec41ded791870516ffd603f6a4f21ca13f1f2cb
project_plan | project_plan | 849 | 1902 |  | PTM_CM35_Inspection Plan |  |  | Mon 5/25/26 | Tue 5/26/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 1902 | 19a77bd9f07096f0bdd8f1c03292116b09c1a7ce21c01924a8905c79c239e63d
project_plan | project_plan | 850 | 1903 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Mon 5/25/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task | 1901 | Yes | No | 1903 | eb28c74c0f1a01cfa4c6349e74cab7164a055ca31c1bc455cf350c042e925dbf
project_plan | project_plan | 851 | 1904 |  | Pre Load Validation |  | Brad Meseck | Mon 5/25/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task | 1903 | Yes | No | 1904 | b4b176993dc726958dd88197a0e32be9d9f2e8d5fc2d56c5ffe1cc58e6aff4c1
project_plan | project_plan | 852 | 1905 |  | Simulate Load |  | Data Migration Team | Mon 5/25/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task | 1904 | Yes | No | 1905 | b6e9eb7049b36d17906b9ebbd061ce0700f530917ba26bf4c17f6158af3bdc24
project_plan | project_plan | 853 | 1906 |  | Error and Defect Mitigation |  | Brad Meseck | Mon 5/25/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task | 1905 | Yes | No | 1906 | 3e29e9f8933672bd0f9731f5205fe5c0e069d288b438fa5109791d57ad3e995f
project_plan | project_plan | 854 | 1907 |  | Load |  | Data Migration Team | Mon 5/25/26 | Mon 5/25/26 | Mon 4/20/26 | 0% | Future Task | 1906 | Yes | No | 1907 | c5594445f0d23a40e38bb2bde4810028b508863afadcd43fd49ca1b1383332ee
project_plan | project_plan | 855 | 1908 |  | Post Load Validation |  | Brad Meseck | Mon 5/25/26 | Tue 5/26/26 | Mon 4/20/26 | 0% | Future Task | 1907 | Yes | No | 1908 | 1e825afbfe17ec87d87f3942f485d987e96998a84672289d92b0bcb80af02ac8
project_plan | project_plan | 856 | 1909 |  | PTM_CM48_Equipment_Master_Serial Numbers |  |  | Mon 5/25/26 | Tue 5/26/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 1909 | 953a34a91c99ceb6644f7080bfe05d853d0d6fff0d3ebf6b133107a74c00a0b2
project_plan | project_plan | 857 | 1910 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Mon 5/25/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task | 1903 | Yes | No | 1910 | 76b6e7af8a47b595537b53b61dbcc73f4c4b81ab73eded88e814dc999c293438
project_plan | project_plan | 858 | 1911 |  | Pre Load Validation |  | Brad Meseck | Mon 5/25/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task | 1910 | Yes | No | 1911 | e2252b8f653b2a46a99eac87a61769cec3647cf7bf02f44344c63fa18356f955
project_plan | project_plan | 859 | 1912 |  | Simulate Load |  | Data Migration Team | Mon 5/25/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task | 1911 | Yes | No | 1912 | 65ec6c88c9835df3e1b84e65328dcfc9426f242462d1172a1959065d90dc53b4
project_plan | project_plan | 860 | 1913 |  | Error and Defect Mitigation |  | Brad Meseck | Mon 5/25/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task | 1912 | Yes | No | 1913 | dfc11ca92507810418adc92f4fff40a0935408c4f4faa56cc4ae6b4c634dd837
project_plan | project_plan | 861 | 1914 |  | Load |  | Data Migration Team | Mon 5/25/26 | Mon 5/25/26 | Mon 4/20/26 | 0% | Future Task | 1913 | Yes | No | 1914 | 735c2b781a88f91fc3602736aa3823f1cfee9d52748cd45be4ae83c1e3a7c91a
project_plan | project_plan | 862 | 1915 |  | Post Load Validation |  | Brad Meseck | Mon 5/25/26 | Tue 5/26/26 | Mon 4/20/26 | 0% | Future Task | 1914 | Yes | No | 1915 | c77938ab21e8897028a87e3c082a80511415eb7db1f7f1b63b967bdc8dc593c7
project_plan | project_plan | 863 | 1916 |  | PTM_CM48_Equipment_Master_Service |  |  | Mon 5/18/26 | Wed 5/27/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 1916 | 8e31dd4119acec98f5640be083ca577bd065a08dea8b0c62ccf4302c8dc48bb0
project_plan | project_plan | 864 | 1917 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Tue 5/26/26 | Tue 5/26/26 | Mon 4/20/26 | 0% | Future Task | 1915 | Yes | No | 1917 | bb6aff741b0535b466441edcd86f03f422f59c44932b809dd92a62f3c2715485
project_plan | project_plan | 865 | 1918 |  | Pre Load Validation |  | Brad Meseck | Tue 5/26/26 | Tue 5/26/26 | Mon 4/20/26 | 0% | Future Task | 1917 | Yes | No | 1918 | 6f0e771b8163e9fe9ac22d044b762524f2ef3d5209170db0d520e3b593e7b013
project_plan | project_plan | 866 | 1919 |  | Simulate Load |  | Data Migration Team | Tue 5/26/26 | Tue 5/26/26 | Mon 4/20/26 | 0% | Future Task | 1918 | Yes | No | 1919 | 578e483714f2957c54a5bb75c9da22d01c2c5a22102a8c2a0fc203ca5564aa56
project_plan | project_plan | 867 | 1920 |  | Error and Defect Mitigation |  | Brad Meseck | Tue 5/26/26 | Tue 5/26/26 | Tue 4/21/26 | 0% | Future Task | 1919 | Yes | No | 1920 | 0c501460c087d95a462e12c3c46db56b6f3e9301a22b1ecbd6cffda2e5a1576b
project_plan | project_plan | 868 | 1921 |  | Load |  | Data Migration Team | Tue 5/26/26 | Wed 5/27/26 | Tue 4/21/26 | 0% | Future Task | 1920 | Yes | No | 1921 | 14491510be63ab5db324e720ef0350e95772fd636ee66165e3f9cc24188ccc25
project_plan | project_plan | 869 | 1922 |  | Post Load Validation |  | Brad Meseck | Mon 5/18/26 | Mon 5/18/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 1922 | 4b8e702a3d1457ae1af0ff5b781edaae0da6f980a687d99d27a609eddb223be5
project_plan | project_plan | 870 | 1923 |  | VC_Object Dependencies |  |  | Mon 5/18/26 | Mon 5/18/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 1923 | 5ab512ab770684371627816fbfa6584af71164db2b592831a29f0ea082dd389a
project_plan | project_plan | 871 | 1924 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Mon 5/18/26 | Mon 5/18/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 1924 | c9045c7d03522055e24f6ac1d1e7cd6fd86cb33817a88641a74e14dbaf5e6d43
project_plan | project_plan | 872 | 1925 |  | Post Load Validation |  | Eric Heisler | Mon 5/18/26 | Mon 5/18/26 | Mon 4/6/26 | 0% | Future Task | 1924 | Yes | No | 1925 | 093fda21cbf64877292479c122c90c5c3cb5c6679d8b779ed456ee6b1a44cd9b
project_plan | project_plan | 873 | 1926 |  | VC_Characteristics |  |  | Mon 5/18/26 | Tue 5/19/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 1926 | 3691d0e2f50dba7e5e57b04a27b943c6adf98d0425007e048beaf929ed475ea4
project_plan | project_plan | 874 | 1927 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Mon 5/18/26 | Tue 5/19/26 | Mon 4/6/26 | 0% | Future Task | 1925 | Yes | No | 1927 | 46f1436f7e026947a2e99a50d1ee8a793b126628a5635222d1da02d5eb8cb840
project_plan | project_plan | 875 | 1928 |  | Post Load Validation |  | Eric Heisler | Tue 5/19/26 | Tue 5/19/26 | Tue 4/7/26 | 0% | Future Task | 1927 | Yes | No | 1928 | 3a8b2f0d29123fbfcc96387f2280d0a32a95a4f42db7d83943fc15db4339a3e2
project_plan | project_plan | 876 | 1929 |  | VC_Classes |  |  | Tue 5/19/26 | Wed 5/20/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 1929 | 219b449ec0940ca82d814cabe90ff0c474f6edd49614d2349986a85383a14956
project_plan | project_plan | 877 | 1930 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 5/19/26 | Tue 5/19/26 | Tue 4/7/26 | 0% | Future Task | 1928 | Yes | No | 1930 | 5a0f2d7961c2af93c206fc95ee4037aac2d1b2f073aa9fc9234ea214893cab59
project_plan | project_plan | 878 | 1931 |  | Post Load Validation |  | Eric Heisler | Tue 5/19/26 | Wed 5/20/26 | Tue 4/7/26 | 0% | Future Task | 1930 | Yes | No | 1931 | 8b23376a846fa475749dc0d5c829b6e6c18f9f7e5cc6c48d15b65d001c9d6e47
project_plan | project_plan | 879 | 1932 |  | VC_Classification (Class Type 200) |  |  | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 1932 | 2c9ed20c283348067ad1c7fde9421cc527f73df0341c7732ac345b1c9fc02a0e
project_plan | project_plan | 880 | 1933 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 1852 | Yes | No | 1933 | 05ef239ade54553f3b5653505698e9d48fdb3a2b6e4b7300a1b0f6b2c6875306
project_plan | project_plan | 881 | 1934 |  | Post Load Validation |  | Eric Heisler | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1933 | Yes | No | 1934 | b451f9424f91c48ab136c6f0604d390b625da1f9e4a764f2c93751cc46c9837f
project_plan | project_plan | 882 | 1935 |  | VC_Dependency Nets |  |  | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 1935 | 837f66d39af2806cc357e621edab6b314e47110043da466b6c316b76eaed758a
project_plan | project_plan | 883 | 1936 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 18,461,931 | Yes | No | 1936 | 6e2179db4ac5356e2783f395d35346459d5e114084bf3045f2896ace72e9cbed
project_plan | project_plan | 884 | 1937 |  | Post Load Validation |  | Eric Heisler | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1936 | Yes | No | 1937 | 8ba8188d7ca8169367c662d7bb8b937f2846d37b8a8bb90c6bebfda75c423c35
project_plan | project_plan | 885 | 1938 |  | VC_Configuration Profiles |  |  | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 1938 | f115589525204ec0dad4fbb89e696a1a664c3617564a5e22de81a65716ad206d
project_plan | project_plan | 886 | 1939 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Thu 5/21/26 | Thu 5/21/26 | Thu 4/16/26 | 0% | Future Task | 1846 | Yes | No | 1939 | 3fc59ce49d8b05f928efe4f0a4d2e11987b72534c8e0956bae7420c41152cd57
project_plan | project_plan | 887 | 1940 |  | Post Load Validation |  | Eric Heisler | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1939 | Yes | No | 1940 | 4db9bef6a6c3708a9b2139c714b16d754efe8dd3328c7141d1f23f4cb3671e33
project_plan | project_plan | 888 | 1941 |  | VC_Variant Tables |  |  | Fri 5/22/26 | Fri 5/22/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 1941 | 5681d33fe58e85338d673a7f67f7b8e02113d976b3fb4a4fdaa9e92d63c53897
project_plan | project_plan | 889 | 1942 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1940 | Yes | No | 1942 | 99ddab63d72448ccf24cecad8133338c69104d1bde1072393bfb2f3e0d1be0fd
project_plan | project_plan | 890 | 1943 |  | Post Load Validation |  | Eric Heisler | Fri 5/22/26 | Fri 5/22/26 | Fri 4/17/26 | 0% | Future Task | 1942 | Yes | No | 1943 | 6ae04796de5d23e06941e47bb807d39ea184699cf0aaef6328f7865f4a6c41fe
project_plan | project_plan | 891 | 1944 |  | VC_Variant Tables Content |  |  | Fri 5/22/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 1944 | e304d97f080be1c60b4ef041c07d72298593eb9b9637c4363f4e21ae462fd9ff
project_plan | project_plan | 892 | 1945 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Fri 5/22/26 | Fri 5/22/26 | Fri 4/17/26 | 0% | Future Task | 1943 | Yes | No | 1945 | 26fccffc63c632a0a6554bc4d3cfeb698c1fb0fc90d16e95c67cdfb8f7e0243d
project_plan | project_plan | 893 | 1946 |  | Post Load Validation |  | Eric Heisler | Fri 5/22/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task | 1945 | Yes | No | 1946 | 5fa1bbc7d1be9cbc6291c353c7e529f76d7b4abb2825e52873dee4f229232006
project_plan | project_plan | 894 | 1947 |  | VC_Characteristic Groups |  |  | Fri 5/22/26 | Tue 5/26/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 1947 | d61aeeb38c6e838c95dd9d6aa1bd6a4f3ff6b8090755d83342f5f02c61f88e37
project_plan | project_plan | 895 | 1948 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Fri 5/22/26 | Mon 5/25/26 | Thu 4/16/26 | 0% | Future Task | 1940 | Yes | No | 1948 | 01f509f5fa9667c8b9f556b3770add3add91e732919deb1ea7973b99792714be
project_plan | project_plan | 896 | 1949 |  | Post Load Validation |  | Eric Heisler | Mon 5/25/26 | Tue 5/26/26 | Fri 4/17/26 | 0% | Future Task | 1948 | Yes | No | 1949 | 56c7567545355e98e2ae6342faee60706b4b240e599e4c8e6a7bb3ba0c9b09f0
project_plan | project_plan | 897 | 1950 |  | PTM_CM52_Super_BOM |  |  | Thu 5/21/26 | Mon 5/25/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 1950 | 0e99a85988ee5af84cb96cc1e62d629f1974a29e45e468f5865b1597e07e894f
project_plan | project_plan | 898 | 1951 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Thu 5/21/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task | 1852 | Yes | No | 1951 | 456038a337a3a8c0094213d92f679d05cc65fc9ba5878de0f975ed1a0317248f
project_plan | project_plan | 899 | 1952 |  | Pre Load Validation |  | Eric Heisler | Thu 5/21/26 | Thu 5/21/26 | Wed 4/15/26 | 0% | Future Task | 1951 | Yes | No | 1952 | b9e57a7c0caac54f1fe97e1e9370d8be0c2995bdd47c58dcc994fcf59f8aa58e
project_plan | project_plan | 900 | 1953 |  | Simulate Load |  | Data Migration Team | Thu 5/21/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1952 | Yes | No | 1953 | 18308ac386193b1c72fd7801e1971e7ea4c29d22c82eec75909e1c95a82188bd
project_plan | project_plan | 901 | 1954 |  | Error and Defect Mitigation |  | Eric Heisler | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1953 | Yes | No | 1954 | dc5d21db7d33bb3cf4bd0b8748e86e015263937008da9c8d727a63d62af412a1
project_plan | project_plan | 902 | 1955 |  | Load |  | Data Migration Team | Fri 5/22/26 | Mon 5/25/26 | Thu 4/16/26 | 0% | Future Task | 1954 | Yes | No | 1955 | 93de2a94f63cfc0a517c7efa9c62dba2c6ecd767ac1f42ff82200b0bb088e308
project_plan | project_plan | 903 | 1956 |  | Post Load Validation |  | Eric Heisler | Mon 5/25/26 | Mon 5/25/26 | Thu 4/16/26 | 0% | Future Task | 1955 | Yes | No | 1956 | 1bb0d05e631525cc432998d7c2aa35279bfd2807efdbf56f4d418eadd90e42d5
project_plan | project_plan | 904 | 1957 |  | PTM_CM53_Super_Routing |  |  | Mon 5/25/26 | Wed 5/27/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 1957 | 330f9507857007cb7b973b3522dd794e9c6305db1921e77b1973ef8eaf42be25
project_plan | project_plan | 905 | 1958 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Mon 5/25/26 | Mon 5/25/26 | Thu 4/16/26 | 0% | Future Task | 1956 | Yes | No | 1958 | 85dd360c4e7264c0c0c7883b5fa8ca675a1ca8275171bf47f1322c7fd4e84f40
project_plan | project_plan | 906 | 1959 |  | Pre Load Validation |  | Eric Heisler | Mon 5/25/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task | 1958 | Yes | No | 1959 | c8ad5dd23092d74c8c5fea01034388f29beb35805f94071311543a1fc5104338
project_plan | project_plan | 907 | 1960 |  | Simulate Load |  | Data Migration Team | Mon 5/25/26 | Tue 5/26/26 | Fri 4/17/26 | 0% | Future Task | 1959 | Yes | No | 1960 | 51fca3d73022627a3c281f6c36df307cf28133abddcdf8db8b5b1fbdd304399f
project_plan | project_plan | 908 | 1961 |  | Error and Defect Mitigation |  | Eric Heisler | Tue 5/26/26 | Tue 5/26/26 | Fri 4/17/26 | 0% | Future Task | 1960 | Yes | No | 1961 | 8556863ed2aeb69663d0605d14f813d0e8d04fa2f84026c684778f614ac6619d
project_plan | project_plan | 909 | 1962 |  | Load |  | Data Migration Team | Tue 5/26/26 | Wed 5/27/26 | Fri 4/17/26 | 0% | Future Task | 1961 | Yes | No | 1962 | fae81747be8fb2b08f9df02bfdc362eb4cba0d758e15bafd2cfbfabfdef45925
project_plan | project_plan | 910 | 1963 |  | Post Load Validation |  | Eric Heisler | Wed 5/27/26 | Wed 5/27/26 | Mon 4/20/26 | 0% | Future Task | 1962 | Yes | No | 1963 | b20765fb0b0a6fb8a96ff91e33316701cfaaf4870927b3482a74f7198cdc980a
project_plan | project_plan | 911 | 1964 |  | VC_VK30 Pricing Variant |  |  | Wed 5/27/26 | Wed 5/27/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 1964 | 5bc4435cc5616921ac7d34cb37785e1789c6b90d3c29ed0a1729ce162c7cfa84
project_plan | project_plan | 912 | 1965 |  | Manual File Staged and Posted "Ready" |  | Eric Heisler | Wed 5/27/26 | Wed 5/27/26 | Fri 4/17/26 | 0% | Future Task | 1962 | Yes | No | 1965 | 179a42f905bf588280edd66104cc34986c37220f58b5b8e416ad5a012fa39a20
project_plan | project_plan | 913 | 1966 |  | Load |  | Eric Heisler | Wed 5/27/26 | Wed 5/27/26 | Fri 4/17/26 | 0% | Future Task | 1965 | Yes | No | 1966 | b5f80778755791dc78bb078f455bd51d46e23d15d939af5a52421092c17f8232
project_plan | project_plan | 914 | 1967 |  | Post Load Validation |  | Eric Heisler | Wed 5/27/26 | Wed 5/27/26 | Mon 4/20/26 | 0% | Future Task | 1966 | Yes | No | 1967 | 73b776d8ff548162e04db11ec283314f97e3632954888beffedc6831d3cd05b2
project_plan | project_plan | 915 | 1968 |  | OTC_CM22_Pricing_Condition |  |  | Wed 5/27/26 | Thu 5/28/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 1968 | d73244baf24a81ad121eea2b0fd5670ef74cf63eea74bc354f969e36bb6cfe11
project_plan | project_plan | 916 | 1969 |  | Manual File Staged and Posted "Ready" |  | Ric Haraida | Wed 5/27/26 | Wed 5/27/26 | Mon 4/20/26 | 0% | Future Task | 1967 | Yes | No | 1969 | d1f36500e46a1a80acd34202121c2f374bf61113d96736b89b3197123811bcd9
project_plan | project_plan | 917 | 1970 |  | Load |  | Ric Haraida | Wed 5/27/26 | Thu 5/28/26 | Mon 4/20/26 | 0% | Future Task | 1969 | Yes | No | 1970 | a03b84245ea9622f0534e5ad957c387386a40cb5e586e7e78855144940e0e9cc
project_plan | project_plan | 918 | 1971 |  | Post Load Validation |  | Ric Haraida,Kim Kolesar | Thu 5/28/26 | Thu 5/28/26 | Tue 4/21/26 | 0% | Future Task | 1970 | Yes | No | 1971 | 4b2357dff30b1e7ee45669286a5b041cecd468b354e461153fa9ff73e64e9a60
project_plan | project_plan | 919 | 1972 |  | OTC_CM21_CMIR |  |  | Thu 5/28/26 | Thu 5/28/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 1972 | 495f456d8d8a4394b5a4b1d643b3763140e8e21a4212b110aba6cbfb496f32e6
project_plan | project_plan | 920 | 1973 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Thu 5/28/26 | Thu 5/28/26 | Mon 4/20/26 | 0% | Future Task | 19,701,981 | Yes | No | 1973 | ef49601cbc7020acb74b151d6e28e1cda6e31d022d96118b1362ee111d50e7ec
project_plan | project_plan | 921 | 1974 |  | Pre Load Validation |  | Ric Haraida | Thu 5/28/26 | Thu 5/28/26 | Mon 4/20/26 | 0% | Future Task | 1973 | Yes | No | 1974 | 387d4030a79f52e211b6be3546cd026fb3549b672ce905652cd2369bb2fcfc28
project_plan | project_plan | 922 | 1975 |  | Simulate Load |  | Data Migration Team | Thu 5/28/26 | Thu 5/28/26 | Mon 4/20/26 | 0% | Future Task | 1974 | Yes | Yes | 1975 | e70a0cc795fab29200963637465b77e497cf01ddaf71f4962ed82fee1d4066a7
project_plan | project_plan | 923 | 1976 |  | Error and Defect Mitigation |  | Ric Haraida | Thu 5/28/26 | Thu 5/28/26 | Tue 4/21/26 | 0% | Future Task | 1975 | Yes | Yes | 1976 | d3db50a36de2b00451211565b6fc93dde20368369a8a8785809154e8f3d85bf0
project_plan | project_plan | 924 | 1977 |  | Load |  | Data Migration Team | Thu 5/28/26 | Thu 5/28/26 | Tue 4/21/26 | 0% | Future Task | 1976 | Yes | Yes | 1977 | ed54ed0b6226827b63c2100b481882b3abb17bbd9db9a887f7bfd21a8377e6d4
project_plan | project_plan | 925 | 1978 |  | Post Load Validation |  | Ric Haraida | Thu 5/28/26 | Thu 5/28/26 | Tue 4/21/26 | 0% | Future Task | 1977 | Yes | No | 1978 | 9b02b869e4b58aef870d72a7b7faaaceff5f806acf73920fe32be9f7f16947cb
project_plan | project_plan | 926 | 1979 |  | PTP_CM29_Source_List |  |  | Tue 5/19/26 | Wed 5/27/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 1979 | 59a5fe14eedb6ada8795f02be335dfd943f53761d00373128b46f9bd6099f0bb
project_plan | project_plan | 927 | 1980 |  | Manual File Staged and Posted "Ready" |  | Nevin Varkey | Tue 5/19/26 | Tue 5/19/26 | Tue 4/14/26 | 0% | Future Task | 18,231,830 | Yes | No | 1980 | e63d318cf21188c13011ab17a9d1c67734c47ed4c8c5bc7725d4d903696be9ba
project_plan | project_plan | 928 | 1981 |  | Load |  | Nevin Varkey | Tue 5/26/26 | Wed 5/27/26 | Mon 4/13/26 | 0% | Future Task | 1799 | Yes | No | 1981 | fee04615ab04f95788906eacba5241ab20495d76069b0496fcda178efb755554
project_plan | project_plan | 929 | 1982 |  | Post Load Validation |  | Nevin Varkey | Wed 5/27/26 | Wed 5/27/26 | Mon 4/13/26 | 0% | Future Task | 1981 | Yes | No | 1982 | 7dbc41fdb15698dc1128aa4833d134c6ec5194bfe352363c4d7ecd1917c92072
project_plan | project_plan | 930 | 1983 |  | RTR_CM11_Asset_Master |  |  | Mon 5/18/26 | Thu 5/21/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 1983 | 68983fa0a57a65337c2e4208e390982d8e22520b7b9b7f12fabb6d7401f18ba3
project_plan | project_plan | 931 | 1984 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Mon 5/18/26 | Mon 5/18/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 1984 | a203abcb62e3418e92c55a44befc3b423c640d65340b0dc32463e88b78a6650b
project_plan | project_plan | 932 | 1985 |  | Pre Load Validation |  | Kasey Hughes,Femi Oguntala | Mon 5/18/26 | Mon 5/18/26 | Fri 4/10/26 | 0% | Future Task | 1984 | Yes | No | 1985 | e616b0948670f824d9deef008e3046f77f1563991a57c45d1b2b9c100e39fb4d
project_plan | project_plan | 933 | 1986 |  | Simulate Load |  | Data Migration Team | Mon 5/18/26 | Tue 5/19/26 | Fri 4/10/26 | 0% | Future Task | 1985 | Yes | No | 1986 | 2fadaec9037e8e385a058395092d8cadff4f43225f0c19fca1e42dc7de36d035
project_plan | project_plan | 934 | 1987 |  | Error and Defect Mitigation |  | Kasey Hughes | Tue 5/19/26 | Thu 5/21/26 | Fri 4/10/26 | 0% | Future Task | 1986 | Yes | No | 1987 | f0df700f7f47121619289ad4b0df21d404e19fab500c8d0ce3dc3be0236a1f4c
project_plan | project_plan | 935 | 1988 |  | Load |  | Data Migration Team | Thu 5/21/26 | Thu 5/21/26 | Fri 4/10/26 | 0% | Future Task | 1987 | Yes | No | 1988 | f636a66ceffb2bfe3b8aa118401e6e44695c6b1bc5e88535881a18ecb619cd66
project_plan | project_plan | 936 | 1989 |  | Post Load Validation |  | Kasey Hughes | Thu 5/21/26 | Thu 5/21/26 | Mon 4/13/26 | 0% | Future Task | 1988 | Yes | No | 1989 | b6bc36b6031625e32cf78c71aeb685f765654faf545370ddaf74c5b8643d2f73
project_plan | project_plan | 937 | 1990 |  | PTM_CM50_Material Class |  |  | Fri 5/22/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 1990 | 93e9b72cb3a9bcce6e68bbb15744fb7244e6269acfa630a2afa3ce388519e3ef
project_plan | project_plan | 938 | 1991 |  | Manual File Staged and Posted "Ready" |  | Sam | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1896 | Yes | No | 1991 | 7b527bfc1adfd9ce0ceea8d5008d81d2aacb43576702a9f3b7a50245743171f7
project_plan | project_plan | 939 | 1992 |  | Load |  | Brad Meseck | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1991 | Yes | No | 1992 | af1db1aedf08db863dccaccc610fcb76c87544a6f19500e32956a2ae6a889464
project_plan | project_plan | 940 | 1993 |  | Post Load Validation |  | Brad | Fri 5/22/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task | 1992 | Yes | No | 1993 | a6ad7d9af30de4e607dfb1591ec562b63268bd4f7f7ebf3ef7660d61eff83c69
project_plan | project_plan | 941 | 1994 |  | PTM_CM55_Class assignment to materials |  |  | Fri 5/22/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 1994 | bb924d311a591d5883b93ccf3fce64923056f2080f42f25b9b9f10ea112ace52
project_plan | project_plan | 942 | 1995 |  | Load File Staged and Posted "Ready" |  | Sam | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1991 | Yes | No | 1995 | 8c52ca03d85090852d8fb01ea343e5962d23e0e6e0a64889d52c7f39ebec4ea2
project_plan | project_plan | 943 | 1996 |  | Pre Load Validation |  | Brad Meseck | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1995 | Yes | No | 1996 | d9fea04cc28c625e6eb84166aca1134772602600d3c005037483e1cabc52371a
project_plan | project_plan | 944 | 1997 |  | Simulate Load |  | Data Migration Team | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1996 | Yes | No | 1997 | 9436d9e8a2f479e58e143e9a3a70b20c148f26f38bd6650db72994d75327c542
project_plan | project_plan | 945 | 1998 |  | Error and Defect Mitigation |  | Brad Meseck | Fri 5/22/26 | Fri 5/22/26 | Thu 4/16/26 | 0% | Future Task | 1997 | Yes | No | 1998 | 5ebf87f8c018e3cbc29c81acd7b877bf65e4002ddb3625cfad569a0b108155ed
project_plan | project_plan | 946 | 1999 |  | Load |  | Data Migration Team | Fri 5/22/26 | Fri 5/22/26 | Fri 4/17/26 | 0% | Future Task | 1998 | Yes | No | 1999 | b93a33bc69d8c5788835358afccdc50dae21e66360f4b1f6303b7f3effeafb6e
project_plan | project_plan | 947 | 2000 |  | Post Load Validation |  | Brad Meseck | Fri 5/22/26 | Mon 5/25/26 | Fri 4/17/26 | 0% | Future Task | 1999 | Yes | No | 2000 | 15b4e66f22a8647556b3b27ad349c6a3568bccbad7e3f83380204820054e750a
project_plan | project_plan | 948 | 2001 |  | GTS - Material initial load from S4 (Run Interface) |  |  | Thu 5/21/26 | Mon 5/25/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2001 | 723da506a9dd946bb6ec12405218fe221117077d4a0089e934784a3e79ea2e82
project_plan | project_plan | 949 | 2002 |  | Run material interface to GTS |  | James Van Riper | Thu 5/21/26 | Mon 5/25/26 | Thu 4/16/26 | 0% | Future Task | 1870 | Yes | No | 2002 | b95a0e0b29e124a13715c6b73c24891f1d48f6ddadde2c17977b0df3f2edb67c
project_plan | project_plan | 950 | 2003 |  | Post Load Validation |  | James Van Riper | Mon 5/25/26 | Mon 5/25/26 | Thu 4/16/26 | 0% | Future Task | 2002 | Yes | No | 2003 | f39cd2d3b577d6c47abf6416b992bcb69eac10b48e903382f940bbf823273272
project_plan | project_plan | 951 | 2004 |  | GTS - Customers initial load from S4 (Run Interface) |  |  | Mon 5/18/26 | Mon 5/18/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 2004 | 55a6628bb3c2724f4d36f82ceac51d46bfd3272f4242be2a57808cf202036468
project_plan | project_plan | 952 | 2005 |  | Run material interface to GTS |  | James Van Riper | Mon 5/18/26 | Mon 5/18/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 2005 | b68a8d779a9537b3bcfe0a4d162ab90eabf78d2ca5d8d0f304a991237b201200
project_plan | project_plan | 953 | 2006 |  | Post Load Validation |  | James Van Riper | Mon 5/18/26 | Mon 5/18/26 | Fri 4/10/26 | 0% | Future Task | 2005 | Yes | No | 2006 | 2128a486b0070039bd357e8d3c3edfae33c417a8a7d902b3d725eb5501c8ab9b
project_plan | project_plan | 954 | 2007 |  | GTS - Vendors initial load from S4 (Run Interface) |  |  | Tue 5/19/26 | Tue 5/19/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 2007 | 5f9dc1dcdbb31b70c324421859bee7ec3426372a5dfd31ab0ed9929726684d25
project_plan | project_plan | 955 | 2008 |  | Run material interface to GTS |  | James Van Riper | Tue 5/19/26 | Tue 5/19/26 | Wed 4/15/26 | 0% | Future Task | 1813 | Yes | No | 2008 | 0bd6be7dcb4d6a5ac3ce94aa991b9239553acadc4e0b724990a3e24b8f0825da
project_plan | project_plan | 956 | 2009 |  | Post Load Validation |  | James Van Riper | Tue 5/19/26 | Tue 5/19/26 | Wed 4/15/26 | 0% | Future Task | 2008 | Yes | No | 2009 | 958a83f00f051d3edcbe93fe466a6ebb4e12ed5c072b272ba4e8de1f442c59b1
project_plan | project_plan | 957 | 2010 |  | GTS - ECCN - Create |  |  | Mon 5/18/26 | Tue 5/19/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 2010 | ef99c28d452238c5c1041711bcaa941f32a0ff3034ee9e1ed07e279325598696
project_plan | project_plan | 958 | 2011 |  | Load Descartes XML File |  | James Van Riper | Mon 5/18/26 | Mon 5/18/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 2011 | f58050a105c2c3284199aedd8b4be1ea32572b41e30efb2d53b0f20298097231
project_plan | project_plan | 959 | 2012 |  | Post Load Validation |  | James Van Riper | Tue 5/19/26 | Tue 5/19/26 | Mon 4/13/26 | 0% | Future Task | 2008 | Yes | No | 2012 | c2b5ef3eb6f0e8aa2e1a0b4fade2a2e7ccaf2435b256677925c236242870e7ef
project_plan | project_plan | 960 | 2013 |  | GTS - ECCN - Assign |  |  | Mon 5/25/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2013 | e45364d0b566797d1788a747481bb78bcbddf2d2b51861b30f88ba9414f46f62
project_plan | project_plan | 961 | 2014 |  | Load Descartes XML File |  | James Van Riper | Mon 5/25/26 | Mon 5/25/26 | Thu 4/16/26 | 0% | Future Task | 2003 | Yes | No | 2014 | c6b29685b09d172165d712cb5207fec3f1b09bfb21d8732f3dac933b218619ea
project_plan | project_plan | 962 | 2015 |  | Post Load Validation |  | James Van Riper | Mon 5/25/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task | 2014 | Yes | No | 2015 | 3f5e42445e5b565634deafa9aa6cbe82d2796d1b2b43d96cd0f8942e41764d75
project_plan | project_plan | 963 | 2016 |  | GTS - HTS - Create |  |  | Mon 5/18/26 | Mon 5/18/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 2016 | 41b7044aed4b3a433b5fbce11cc3d1febcb5a8e097a076f27e5ce455f5bfecd4
project_plan | project_plan | 964 | 2017 |  | Load Descartes XML File |  | James Van Riper | Mon 5/18/26 | Mon 5/18/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 2017 | a09228e2db3bcce12b7addbee60ad19551680fe2f39497a4b32e0e8646d8ee2e
project_plan | project_plan | 965 | 2018 |  | Post Load Validation |  | James Van Riper | Mon 5/18/26 | Mon 5/18/26 | Mon 4/6/26 | 0% | Future Task | 2017 | Yes | No | 2018 | 47255e8ffa3fbd70bf6e8936448b90a134fe7437b1e432e490df320d02d429da
project_plan | project_plan | 966 | 2019 |  | GTS - HTS - Assign |  |  | Tue 5/26/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2019 | f101c5567c73bb9cb38934d83e92f2e4f0ff6e319952c25bf66302b8966ea3bd
project_plan | project_plan | 967 | 2020 |  | Load Descartes XML File |  | James Van Riper | Tue 5/26/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task | 2015 | Yes | No | 2020 | a75d4e946ca531e6c483ba96078a455010f58a23b9050ab65fae3eb51ff92454
project_plan | project_plan | 968 | 2021 |  | Post Load Validation |  | James Van Riper | Tue 5/26/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task | 2020 | Yes | No | 2021 | 90a502df43fd195170bcebc00382d176865bf4702044ef5681b8c1b2f84fc738
project_plan | project_plan | 969 | 2022 |  | GTS - License - Create |  |  | Tue 5/26/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2022 | 403e6e25965bf9a775a10c56e260956b91e02f5cd79104dd91ea110a58149e30
project_plan | project_plan | 970 | 2023 |  | Load Descartes XML File |  | James Van Riper | Tue 5/26/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task | 20,202,036 | Yes | No | 2023 | 15fca24b45d09e415444891cafea75bcd37d44b4cb058c0a54dcfa9bb7485da1
project_plan | project_plan | 971 | 2024 |  | Post Load Validation |  | James Van Riper | Tue 5/26/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task | 2023 | Yes | No | 2024 | 8f86002b215a1590648db36482c88a58037615ccc7c8e5dad366bc3f8e43bc5a
project_plan | project_plan | 972 | 2025 |  | Commodity Code/Tarif |  |  | Tue 5/26/26 | Fri 5/29/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2025 | 5cd4f26da3384518a5c68ce6b4044086977aeffa22d5239c7ecdf78af2b8c39c
project_plan | project_plan | 973 | 2026 |  | Load |  | James Van Riper | Tue 5/26/26 | Thu 5/28/26 | Thu 4/16/26 | 0% | Future Task | 2021 | Yes | No | 2026 | 2385ba3316d732160b2dac30b2cdce6f626c74340647f69bb69945f08c991e68
project_plan | project_plan | 974 | 2027 |  | Post Load Validation |  | James Van Riper | Thu 5/28/26 | Fri 5/29/26 | Thu 4/16/26 | 0% | Future Task | 2026 | Yes | No | 2027 | f25f4991a0e28c194c832386dd1225ab33823167686b67ef58d9602b1878fd96
project_plan | project_plan | 975 | 2028 |  | SPL Master File |  |  | Tue 5/26/26 | Tue 5/26/26 | Thu 3/13/25 | 0% | Future Task |  | Yes | No | 2028 | d58ed6fb483f71e6f3fd7fde0dbc0f7f6121ca9f7bda247b785ccf55e14ffd0d
project_plan | project_plan | 976 | 2029 |  | Load |  | James Van Riper | Tue 5/26/26 | Tue 5/26/26 | Thu 3/13/25 | 0% | Future Task | 2020 | Yes | No | 2029 | b570004d012ea174dc5b86462f2687795bf16f3a6108dd03b86b76a60bbd68d5
project_plan | project_plan | 977 | 2030 |  | Post Load Validation |  | James Van Riper | Tue 5/26/26 | Tue 5/26/26 | Thu 3/13/25 | 0% | Future Task | 2029 | Yes | No | 2030 | bd4082f13520eca4fc4a3c9e0bd1b9cad9734438352808bb1cdf0ee53148c3d0
project_plan | project_plan | 978 | 2031 |  | Initialize Embargo situation |  |  | Tue 5/19/26 | Tue 5/19/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 2031 | 8cfc9301d4fef3710dcde52e5b34430d5d7179d6ff5cae2822a59fe37924313d
project_plan | project_plan | 979 | 2032 |  | Run report /SAPSLL/EMB_CNTRY_INIT |  | James Van Riper | Tue 5/19/26 | Tue 5/19/26 | Mon 4/13/26 | 0% | Future Task | 2012 | Yes | No | 2032 | 34acd7de601de7753c3c2e92965db0ca602212fa912647cd2c3a508cf3b10685
project_plan | project_plan | 980 | 2033 |  | Set Embargo situations |  | James Van Riper | Tue 5/19/26 | Tue 5/19/26 | Mon 4/13/26 | 0% | Future Task | 2032 | Yes | No | 2033 | 1f9a7feaefa93779db6bb244ce93b8c138573df6e770f13a0c3e8bd830fd6422
project_plan | project_plan | 981 | 2034 |  | Post Load Validation |  | James Van Riper | Tue 5/19/26 | Tue 5/19/26 | Tue 4/14/26 | 0% | Future Task | 2033 | Yes | No | 2034 | 6e4973777f5b032d04717c279359878eaab81c6c573b4239214e883de78535d6
project_plan | project_plan | 982 | 2035 |  | GTS - SPL (Sanctioned party list) |  |  | Tue 5/26/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2035 | 576517220672db0efca580044e9ed547da77f7c582452f5a89dd695e14d01b35
project_plan | project_plan | 983 | 2036 |  | Load Descartes XML File |  | James Van Riper | Tue 5/26/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task | 2021 | Yes | No | 2036 | d2f4fcfe2c01334a498f7c63d05ed05c0d685bda7671417867b9b7918b146c2b
project_plan | project_plan | 984 | 2037 |  | Post Load Validation |  | James Van Riper | Tue 5/26/26 | Tue 5/26/26 | Thu 4/16/26 | 0% | Future Task | 2036 | Yes | No | 2037 | 6b92d37840d2d312291a314099ad7cbad39cba8a35005fc21e824a54db165ab1
project_plan | project_plan | 985 | 2038 |  | RTR_CM17_Project Definition / Builder |  |  | Mon 5/18/26 | Tue 5/19/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 2038 | 882ae4c382056beefcc947887c2ef6e6108e1ffd94eb68a1c094162e1de40235
project_plan | project_plan | 986 | 2039 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Mon 5/18/26 | Mon 5/18/26 | Fri 4/10/26 | 0% | Future Task | 1984 | Yes | No | 2039 | 3cac330f543e5a28c2dcdd3644af89d04fbd5ac2f2387009489a917d6c66170d
project_plan | project_plan | 987 | 2040 |  | Pre Load Validation |  | Kasey Hughes | Mon 5/18/26 | Mon 5/18/26 | Fri 4/10/26 | 0% | Future Task | 2039 | Yes | No | 2040 | ad6c944b2f864df27a83f14a83816f183895393fe4ac9a8f9f7b099cc75f752f
project_plan | project_plan | 988 | 2041 |  | Simulate Load |  | Data Migration Team | Mon 5/18/26 | Mon 5/18/26 | Thu 4/16/26 | 0% | Future Task | 2040 | Yes | No | 2041 | 67440e8415ea4c6d27a682fe30fdfbc2fc811d95f0f418eadfdfd9cbc6508ac2
project_plan | project_plan | 989 | 2042 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 5/18/26 | Mon 5/18/26 | Fri 4/17/26 | 0% | Future Task | 2041 | Yes | No | 2042 | 151a712e352670e76a0055173b8e1d5cb73489baeb6b675f4d9656dad914b1ab
project_plan | project_plan | 990 | 2043 |  | Load |  | Data Migration Team | Mon 5/18/26 | Tue 5/19/26 | Fri 4/17/26 | 0% | Future Task | 2042 | Yes | No | 2043 | 35aa2a811f255eea7cb7163a99394bc23965fdbd3a6a8da60fc51ca7498620fe
project_plan | project_plan | 991 | 2044 |  | Post Load Validation |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Fri 4/17/26 | 0% | Future Task | 2043 | Yes | No | 2044 | 59f76ebe93a16eeb3cb4b92f85cd02416a0f345f6adece6fa87a63f9793ce3d4
project_plan | project_plan | 992 | 2045 |  | RTR_CM18_WBS Element |  |  | Mon 5/18/26 | Tue 5/19/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 2045 | 59d2cb74eb0b5868a8f0ec9b42043e8808bc8691572b2fa36b1ffdba77bc88c9
project_plan | project_plan | 993 | 2046 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Mon 5/18/26 | Mon 5/18/26 | Fri 4/10/26 | 0% | Future Task | 2039 | Yes | No | 2046 | ebcbb969e13d87f43923306b00967064fe0f43c5a49868734eafed73d0da61b9
project_plan | project_plan | 994 | 2047 |  | Pre Load Validation |  | Kasey Hughes | Mon 5/18/26 | Mon 5/18/26 | Fri 4/10/26 | 0% | Future Task | 2046 | Yes | No | 2047 | 8d22a88de891ec9085a3b2d3cb6247d923f8f61eff0fe3b32b814b568f0e0b57
project_plan | project_plan | 995 | 2048 |  | Simulate Load |  | Data Migration Team | Mon 5/18/26 | Mon 5/18/26 | Thu 4/16/26 | 0% | Future Task | 2047 | Yes | No | 2048 | ff5bb35e84f1f1048af252a6ebeadca19a3974e44d387b090e6ea2ce5b5c64c1
project_plan | project_plan | 996 | 2049 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 5/18/26 | Mon 5/18/26 | Fri 4/17/26 | 0% | Future Task | 2048 | Yes | No | 2049 | bfa0070e13caa6a367b20e5ad32d9ea09c2a529235c9c65edae39297336be7eb
project_plan | project_plan | 997 | 2050 |  | Load |  | Data Migration Team | Mon 5/18/26 | Tue 5/19/26 | Fri 4/17/26 | 0% | Future Task | 2049 | Yes | No | 2050 | adb45d819171eb5269cce394561d63007eb2ba49bf6fdc21fe6ba037d82c0c94
project_plan | project_plan | 998 | 2051 |  | Post Load Validation |  | Kasey Hughes | Tue 5/19/26 | Tue 5/19/26 | Fri 4/17/26 | 0% | Future Task | 2050 | Yes | No | 2051 | de776f962aa3a2700d5e102c8b56e3e20b20bee031f612aba13b976555d8ef8b
project_plan | project_plan | 999 | 2947 |  | ITC2 Master Data Loads Complete |  |  | Fri 5/29/26 | Fri 5/29/26 |  | 0% | Future Task | 2800 | Yes | Yes | 2947 | 09f1efc4c944d9293e8b664897d88349c786c7371b3cde7e9fe606efeace865c
project_plan | project_plan | 1000 | 2801 |  | Mock Transactional Data |  |  | Thu 10/8/26 | Mon 10/12/26 |  | 0% | Future Task | 294,733,604,530 | Yes | No | 2801 | 7c7a5a53038415c5c1be1683b08b4ab47a4dc591ab43cab69d01e3fce43058a2
project_plan | project_plan | 1001 | 2945 |  | Inventory |  |  | Thu 10/8/26 | Fri 10/9/26 |  | 0% | Future Task | 2947SS,3360SS,4530SS | Yes | No | 2945 | 230434a14037a66033316b7d2c636e0d9b99630f307ca051254c3d7836775dfe
project_plan | project_plan | 1002 | 2829 |  | Open AR |  |  | Fri 10/9/26 | Fri 10/9/26 |  | 0% | Future Task | 2945 | Yes | No | 2829 | 4fe065474129a0c0356b126b3ab8ce11761bcac2491775a32116daa27cadd2d1
project_plan | project_plan | 1003 | 2824 |  | Open AP |  |  | Fri 10/9/26 | Mon 10/12/26 |  | 0% | Future Task | 2829 | Yes | No | 2824 | 27efe2f145d6ca0d7435f56a7d824c15bb2e4a847dbd468680d778f7d6e857b3
project_plan | project_plan | 1004 | 2821 |  | Bank and Cash |  |  | Mon 10/12/26 | Mon 10/12/26 |  | 0% | Future Task | 2824 | Yes | No | 2821 | 4d33be73ce11afa059c34f0669fe16f9319de91f8bab395edd3b3452b54e72d8
project_plan | project_plan | 1005 | 2944 |  | Open Purchase Orders(Manual) |  |  | Fri 10/9/26 | Mon 10/12/26 |  | 0% | Future Task | 2945 | Yes | No | 2944 | e85c2cafc9ebe55f3ab0555ae2da95be2a5dfe3182011ae0cf74dbf654cd9082
project_plan | project_plan | 1006 | 2838 |  | Open Sales Orders(Manual) |  |  | Fri 10/9/26 | Mon 10/12/26 |  | 0% | Future Task | 2945 | Yes | No | 2838 | 6385c6af829ae012895430f0f946dca00f7a18a3b0481a138415394aad7e03ed
project_plan | project_plan | 1007 | 2860 |  | Service Orders(Manual) |  |  | Fri 10/9/26 | Fri 10/9/26 |  | 0% | Future Task | 2945 | Yes | No | 2860 | 796a44936d4cfc624bacceb49a485b979bf91ec66fe359d7a220278571b312c9
project_plan | project_plan | 1008 | 2858 |  | Open Production Orders(Manual) |  |  | Fri 10/9/26 | Mon 10/12/26 |  | 0% | Future Task | 2945 | Yes | No | 2858 | 3e3cc83342aca53d9e6f35ed6a815ab1d81ce317365b75529e46cbac496f577d
project_plan | project_plan | 1009 | 2052 |  | ITC2 Mock Data Loads Complete |  | Mark George | Mon 10/12/26 | Mon 10/12/26 | Tue 4/21/26 | 0% | Future Task | 2801 | Yes | Yes | 2052 | 6355d36f991f91fab04fc70a7ec3932805f3d17e85e3e62da6cdf6a086eefcd6
project_plan | project_plan | 1010 | 2053 |  | ITC3 Data Load Tasks QS5 |  |  | Mon 6/8/26 | Tue 6/23/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 2053 | 6eefed26cc2b16a7377691b7810f3812047223f1c025b371d973b42a1013a95f
project_plan | project_plan | 1011 | 2054 |  | PMO Authorization to Start Data Loads |  | Mark George | Mon 6/8/26 | Mon 6/8/26 | Mon 4/6/26 | 0% | Future Task | 1284 | Yes | No | 2054 | 585c025410d39357793342b4e3f77683d42511501c6778b822d0f8a432d2271a
project_plan | project_plan | 1012 | 2959 |  | Master Data Loads |  |  | Mon 6/8/26 | Fri 6/19/26 |  | 0% | Future Task | 2054 | Yes | No | 2959 | 5befd19086545eb15418de898fcbc2072bcf69dc4d40247e469ee7a201797e9c
project_plan | project_plan | 1013 | 2960 |  | RTR_CM02_Profit Center Hierarchy |  |  | Mon 6/8/26 | Mon 6/8/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 2960 | 83bd684495e6656a6ec466e299e3e5af507844f48412408a881264deedc5bb5a
project_plan | project_plan | 1014 | 2961 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Mon 6/8/26 | Mon 6/8/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 2961 | 0f244a13be6de5778b166f68a7765aada16c63526be29adda2dd39eb9404f548
project_plan | project_plan | 1015 | 2962 |  | Load |  | Kasey Hughes | Mon 6/8/26 | Mon 6/8/26 | Mon 4/6/26 | 0% | Future Task | 2961 | Yes | No | 2962 | 5c673f4e93f5620e47de2af82542f8fa814f28746010e20460a424387b4b6024
project_plan | project_plan | 1016 | 2963 |  | Post Load Validation |  | Kasey Hughes | Mon 6/8/26 | Mon 6/8/26 | Mon 4/6/26 | 0% | Future Task | 2962 | Yes | No | 2963 | 27accf0bfe0659e22e9e2ed64d090c2133aa3657c257487095008a35e2f5c733
project_plan | project_plan | 1017 | 2964 |  | RTR_CM03_Cost Center Hierarchy |  |  | Tue 6/9/26 | Tue 6/9/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 2964 | f409704355af1045566ae767ddbdd6c7a6c49fa31d481439b7260ccf079e7473
project_plan | project_plan | 1018 | 2965 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Mon 4/6/26 | 0% | Future Task | 2963 | Yes | No | 2965 | 8b60065b6d988f9330148739808d262b7ad2f40f0117a6569c995d1a47af8b61
project_plan | project_plan | 1019 | 2966 |  | Load |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Tue 4/7/26 | 0% | Future Task | 2965 | Yes | No | 2966 | 027481cdff252cf41e291193bf19e9ef73af0165bdc34c47f45eaced5244e9dc
project_plan | project_plan | 1020 | 2967 |  | Post Load Validation |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Tue 4/7/26 | 0% | Future Task | 2966 | Yes | No | 2967 | 620b469a3e9a088c3543a8436dc8682102f0da54638b99eb97f40b5548f313b6
project_plan | project_plan | 1021 | 2968 |  | RTR_CM01_GL_Account_Master to CC 1000 |  |  | Tue 6/9/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 2968 | f3c5b4774b69f008d737ad89d3a01f91734a9feae4fc3503b01a3be9e965dc0b
project_plan | project_plan | 1022 | 2969 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Tue 4/7/26 | 0% | Future Task | 2967 | Yes | No | 2969 | f1d53c1095f0bd1047001cf10b4a94566d058b481e6f6b3ed3ba661910e6136a
project_plan | project_plan | 1023 | 2970 |  | Pre Load Validation |  | Kasey Hughes | Tue 6/9/26 | Wed 6/10/26 | Tue 4/7/26 | 0% | Future Task | 2969 | Yes | No | 2970 | 696ed9c24f9accd25ffdfd4b723afc096aeb95feeddbb86334b937b8cbbaf203
project_plan | project_plan | 1024 | 2971 |  | Simulate Load |  | Data Migration Team | Wed 6/10/26 | Wed 6/10/26 | Wed 4/8/26 | 0% | Future Task | 2970 | Yes | No | 2971 | 9382938085d12d36ff4d69fe8e2a782cf76da5589bca056703e6def954bf0da2
project_plan | project_plan | 1025 | 2972 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 6/10/26 | Thu 6/11/26 | Wed 4/8/26 | 0% | Future Task | 2971 | Yes | No | 2972 | 32d71f4b27a5c62ce90bf96a890e949c9e9392b0986e663163ebdbc121c02687
project_plan | project_plan | 1026 | 2973 |  | Load |  | Data Migration Team | Thu 6/11/26 | Thu 6/11/26 | Wed 4/8/26 | 0% | Future Task | 2972 | Yes | No | 2973 | 1c40b7d2a3c24a6b603bb5cc29672dd22492f9f96ba76cc8e60306a5090a7fe8
project_plan | project_plan | 1027 | 2974 |  | Post Load Validation |  | Kasey Hughes | Thu 6/11/26 | Thu 6/11/26 | Wed 4/8/26 | 0% | Future Task | 2973 | Yes | No | 2974 | dfa17952ad877e16fb7d2fbb0565159e696867b6132d6e82051664f937513b0d
project_plan | project_plan | 1028 | 2975 |  | Extend GL to all Company Codes |  | Kasey Hughes | Thu 6/11/26 | Thu 6/11/26 | Thu 4/9/26 | 0% | Future Task | 2974 | Yes | No | 2975 | 3f8ff10ed2fbdec03aebdb27bdeaccb8f69b1e2986335ed2a7a58f793dcf97aa
project_plan | project_plan | 1029 | 2976 |  | Post GL Extention Validation |  |  | Thu 6/11/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task | 2975 | Yes | No | 2976 | 443cab4bcf979e9e7bf45f156f682a0ad2ef92d44c4b96a83385583b4063d875
project_plan | project_plan | 1030 | 2977 |  | RTR_CM05_Profit_Center |  |  | Tue 6/9/26 | Wed 6/10/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 2977 | 21832d42042f7cbb9fbd575c5c443ce3b762628ff1aeca4f45ab02ae10378f63
project_plan | project_plan | 1031 | 2978 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Mon 4/6/26 | 0% | Future Task | 2963 | Yes | No | 2978 | a9f5a6543367c3ef026014483cf6d6ffcc299a07ba23a8600e11f755dc90228a
project_plan | project_plan | 1032 | 2979 |  | Pre Load Validation |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Tue 4/7/26 | 0% | Future Task | 2978 | Yes | No | 2979 | 814e370b9fa582d5bdd0bbf0a7562cae050155cb0ef52c2711094c673db912b2
project_plan | project_plan | 1033 | 2980 |  | Simulate Load |  | Data Migration Team | Tue 6/9/26 | Tue 6/9/26 | Tue 4/7/26 | 0% | Future Task | 2979 | Yes | No | 2980 | 32d15e298baaa918f4e4b22388bf75aa36dc42e07a0cf512069e3980cbbdf30b
project_plan | project_plan | 1034 | 2981 |  | Error and Defect Mitigation |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Tue 4/7/26 | 0% | Future Task | 2980 | Yes | No | 2981 | ddfe8af1476b17e4eba6390602edecf5bf6ea20efcbc43f7274adef680b311bb
project_plan | project_plan | 1035 | 2982 |  | Load |  | Data Migration Team | Tue 6/9/26 | Tue 6/9/26 | Tue 4/7/26 | 0% | Future Task | 2981 | Yes | No | 2982 | 2ee37396acd80fb6247abd0c5908157f947ae03d9a5b6997292bf41630be5688
project_plan | project_plan | 1036 | 2983 |  | Post Load Validation |  | Kasey Hughes | Tue 6/9/26 | Wed 6/10/26 | Tue 4/7/26 | 0% | Future Task | 2982 | Yes | No | 2983 | f3bcd1875b44585a2b21df20e365d6ee4af54dcde828dc44e02fbc6f9030de8f
project_plan | project_plan | 1037 | 2984 |  | RTR_CM04_Cost_Center |  |  | Wed 6/10/26 | Thu 6/11/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 2984 | aee6219dd12dd7a1f1fe92b823bca4ff962035e39dfb381dc520a11ceef4793e
project_plan | project_plan | 1038 | 2985 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Wed 6/10/26 | Wed 6/10/26 | Wed 4/8/26 | 0% | Future Task | 2983 | Yes | No | 2985 | 6f76608a484805db78aac277054cb1079be1bd9d7e3a87d16cbfa1558ccc4df9
project_plan | project_plan | 1039 | 2986 |  | Pre Load Validation |  | Kasey Hughes | Wed 6/10/26 | Wed 6/10/26 | Wed 4/8/26 | 0% | Future Task | 2985 | Yes | No | 2986 | f861f850aa22693b13032921f65d54ffd42b6600327157a93e44737574ed4522
project_plan | project_plan | 1040 | 2987 |  | Simulate Load |  | Data Migration Team | Wed 6/10/26 | Wed 6/10/26 | Wed 4/8/26 | 0% | Future Task | 2986 | Yes | No | 2987 | f44cb1cdf123cd3015a7b903e9d0eb8b844cae47fcf7a5b80d394aefc73e8965
project_plan | project_plan | 1041 | 2988 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 6/10/26 | Wed 6/10/26 | Wed 4/8/26 | 0% | Future Task | 2987 | Yes | No | 2988 | 1cfa87efdd934e7ceeb40b2edc9213e4ae938cd7dee135ab2fdd40c5d161f331
project_plan | project_plan | 1042 | 2989 |  | Load |  | Data Migration Team | Wed 6/10/26 | Wed 6/10/26 | Wed 4/8/26 | 0% | Future Task | 2988 | Yes | No | 2989 | e48b42bfdcc98c32455d113f6dca7efea952e72a7d36f3912dcd2d27c38cf0a4
project_plan | project_plan | 1043 | 2990 |  | Post Load Validation |  | Kasey Hughes | Thu 6/11/26 | Thu 6/11/26 | Thu 4/9/26 | 0% | Future Task | 2989 | Yes | No | 2990 | 6e41cf6e4f2383696f21252027522c68ff7a4dc25c7286c01bb73d2c7e37a349
project_plan | project_plan | 1044 | 2991 |  | Manual Configuration Activities in QS5 |  |  | Thu 6/11/26 | Fri 6/19/26 | Wed 4/15/26 | 0% | Future Task | 2984 | Yes | No | 2991 | 131b27e81925479f1315ff469192007c26379ce115e1a2fcf0ee3010ecd65dc8
project_plan | project_plan | 1045 | 2992 |  | Open Client |  | Basis | Thu 6/11/26 | Thu 6/11/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 2992 | 3bf86c5b1829b9fb024015d51ebef8f4e55cff97aa1cbcea537a8c52c88cc432
project_plan | project_plan | 1046 | 2993 |  | Service Enterprise Setup |  | Keith Riley | Fri 6/12/26 | Fri 6/19/26 | Wed 4/15/26 | 0% | Future Task | 296,029,642,968 | Yes | No | 2993 | 133eed2e02144edde4f7fc85fd099edeb1e8a7a449258d154285172cef1a10ac
project_plan | project_plan | 1047 | 2994 |  | Close Client |  | Basis | Thu 6/11/26 | Thu 6/11/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 2994 | 9fbd225871d8166499c5050c8364bd4764932b861e07bb3ad2b6fca704da8bbe
project_plan | project_plan | 1048 | 2995 |  | Intercompany Business Partner Setup |  | Functional Leads | Fri 6/12/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task | 296,029,642,976 | Yes | No | 2995 | e38691d2ae24731eef520801cbdd04d90104f1aec8e323a170229cb57234e0a8
project_plan | project_plan | 1049 | 2996 |  | RTR_CM09_Activity_Type |  |  | Thu 6/11/26 | Mon 6/15/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 2996 | ddff182554abca3c7f0a4c016f907b8d73a8dcf2b697633fe22e7bf22735fd05
project_plan | project_plan | 1050 | 2997 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Thu 6/11/26 | Thu 6/11/26 | Wed 4/8/26 | 0% | Future Task | 2974 | Yes | No | 2997 | ccd0e8caefec036caa1e1a9ded996c86ccb550a31fd2c7bbddca1abc55bf7882
project_plan | project_plan | 1051 | 2998 |  | Pre Load Validation |  | Kasey Hughes | Thu 6/11/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task | 2997 | Yes | No | 2998 | e7a228f14872f5b11d0b8bbc55032fb75a3d02cdb86d0fd77686b90bab3e0995
project_plan | project_plan | 1052 | 2999 |  | Simulate Load |  | Data Migration Team | Fri 6/12/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task | 2998 | Yes | No | 2999 | b2fb82bd17c2a1d4840dc634e7b0b4c5841bca13969f8177c2029988b30eb8eb
project_plan | project_plan | 1053 | 3000 |  | Error and Defect Mitigation |  | Kasey Hughes | Fri 6/12/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task | 2999 | Yes | No | 3000 | 11f74cddc3f4aff17d47e278f8051fcc725e11ca20303f4b715fa1d280226d1a
project_plan | project_plan | 1054 | 3001 |  | Load |  | Data Migration Team | Fri 6/12/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task | 3000 | Yes | No | 3001 | 817a9c033e50f7dc2aa2766a115352f28fbe0c9558764754b7aec5debb2d4676
project_plan | project_plan | 1055 | 3002 |  | Post Load Validation |  | Kasey Hughes | Fri 6/12/26 | Mon 6/15/26 | Thu 4/9/26 | 0% | Future Task | 3001 | Yes | No | 3002 | 7038474cd9a60a98d577da1efc445677940409f69d6d1154a7a4739ec97058ed
project_plan | project_plan | 1056 | 3003 |  | RTR_CM12_Activity Rates |  |  | Tue 6/9/26 | Wed 6/10/26 | Wed 4/8/26 | 0% | Future Task |  | Yes | No | 3003 | 411830708a43799ea8a705b05fb576ad92d35703f11c3a6703e1902219bee33e
project_plan | project_plan | 1057 | 3004 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Tue 4/7/26 | 0% | Future Task | 2967 | Yes | No | 3004 | 3eec0e38982f2accecdb495970d58a23c8b45096935c89860a0fd4c6f590dddd
project_plan | project_plan | 1058 | 3005 |  | Pre Load Validation |  | Kasey Hughes | Tue 6/9/26 | Wed 6/10/26 | Tue 4/7/26 | 0% | Future Task | 3004 | Yes | No | 3005 | b92123bde3681e4c3e2976dfc53e15d751cbadbc25d5792f1be523a9657598de
project_plan | project_plan | 1059 | 3006 |  | Simulate Load |  | Data Migration Team | Wed 6/10/26 | Wed 6/10/26 | Wed 4/8/26 | 0% | Future Task | 3005 | Yes | No | 3006 | c90d1a5b1a501f1c32d8944ec94fded6dbc5163845a140ceba954799936d6972
project_plan | project_plan | 1060 | 3007 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 6/10/26 | Wed 6/10/26 | Wed 4/8/26 | 0% | Future Task | 3006 | Yes | No | 3007 | ba3de23a2532c52c19b5c4bfc1adcf1626824cb41c8b840d72bc78619d540594
project_plan | project_plan | 1061 | 3008 |  | Load |  | Data Migration Team | Wed 6/10/26 | Wed 6/10/26 | Wed 4/8/26 | 0% | Future Task | 3007 | Yes | No | 3008 | 2dc1696242ea1a488b9a8c9d9f844f818b055bbaa7a827ffb051d975afc907a7
project_plan | project_plan | 1062 | 3009 |  | Post Load Validation |  | Kasey Hughes | Wed 6/10/26 | Wed 6/10/26 | Wed 4/8/26 | 0% | Future Task | 3008 | Yes | No | 3009 | 8a96ec9d48d1ebc2aab4c33522cd34663d3172a464a500b8f226da1db6d7b6b4
project_plan | project_plan | 1063 | 3010 |  | RTR_CM06_Bank_master |  |  | Mon 6/8/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 3010 | 4debae57ffd3f9749641c53e65147ff8531bd01a932da857b2692e40f8844a70
project_plan | project_plan | 1064 | 3011 |  | Load File Staged and Posted "Ready" |  | Data Migration Team | Thu 6/11/26 | Thu 6/11/26 | Wed 4/8/26 | 0% | Future Task | 2974 | Yes | No | 3011 | 2b041a104069f08cd8122f9083c236075c9c78ebc44b3b9fc57cecb1fa63d82a
project_plan | project_plan | 1065 | 3012 |  | Pre Load Validation |  | Kasey Hughes | Thu 6/11/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task | 3011 | Yes | No | 3012 | afabd816eacde4adc01cc51e08cc3acf2f60d2c2d2141b4565cb50e21eb4de12
project_plan | project_plan | 1066 | 3013 |  | Simulate Load |  | Data Migration Team | Mon 6/8/26 | Mon 6/8/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 3013 | 73670e9c4564deb6f7c468262cd6923b9b2c467751f9fdaaa6a30e9df1162289
project_plan | project_plan | 1067 | 3014 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 6/8/26 | Mon 6/8/26 | Thu 4/9/26 | 0% | Future Task | 3013 | Yes | No | 3014 | 5d99eccb5812d68965cdda733eac037def72b26857531d5534bc13dac4acada2
project_plan | project_plan | 1068 | 3015 |  | Load |  | Data Migration Team | Mon 6/8/26 | Tue 6/9/26 | Thu 4/9/26 | 0% | Future Task | 3014 | Yes | No | 3015 | 2617993f38bb159a7052ff0d70cb2bed0e96758a30450069f717e9e06bf5953f
project_plan | project_plan | 1069 | 3016 |  | Post Load Validation |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Thu 4/9/26 | 0% | Future Task | 3015 | Yes | No | 3016 | 955ff2412e296e50710bc8bfe4e258d53b75b9f5038caf1984b1aadb6ad2bb8d
project_plan | project_plan | 1070 | 3017 |  | RTR_CM08_Exchange_Rates |  |  | Tue 6/9/26 | Wed 6/10/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 3017 | 0ba08ec0d3860cc1f1b1d5f6edf8f4932660401ee1423f4acb32a8dde6e7712a
project_plan | project_plan | 1071 | 3018 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Thu 4/9/26 | 0% | Future Task | 3015 | Yes | No | 3018 | 89ff61db023266c6b57ec9f9869ba99aaf52fc481c47771b7c0ae9ff5f928b46
project_plan | project_plan | 1072 | 3019 |  | Pre Load Validation |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Fri 4/10/26 | 0% | Future Task | 3018 | Yes | No | 3019 | 9bcb0da479a04339074c519b62989969ecd78c6444bae4a395b50711b7fe3b4f
project_plan | project_plan | 1073 | 3020 |  | Simulate Load |  | Data Migration Team | Tue 6/9/26 | Tue 6/9/26 | Fri 4/10/26 | 0% | Future Task | 3019 | Yes | No | 3020 | f8cef6f7ec918b83051c34611d4e2ac0041a2f6b4d19662e90c05aa4c1ce7315
project_plan | project_plan | 1074 | 3021 |  | Error and Defect Mitigation |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Fri 4/10/26 | 0% | Future Task | 3020 | Yes | No | 3021 | 8f7866a7f23fbac72a751c3a5bcb3e8f26a60ab8217bc9528b899b7a1951150c
project_plan | project_plan | 1075 | 3022 |  | Load |  | Data Migration Team | Wed 6/10/26 | Wed 6/10/26 | Fri 4/10/26 | 0% | Future Task | 3021 | Yes | No | 3022 | f76dbe7a75abedd01fd7d31612f0f8177f48235a0b6e1dbcdeaac75477cb182d
project_plan | project_plan | 1076 | 3023 |  | Post Load Validation |  | Kasey Hughes | Wed 6/10/26 | Wed 6/10/26 | Fri 4/10/26 | 0% | Future Task | 3022 | Yes | No | 3023 | 99e67009bfc9fb96715371c3e3eca1ed7eb780d1a02298e45153dea3f7d960ea
project_plan | project_plan | 1077 | 3024 |  | RTR_CM14_Cost Element_Group |  | Kasey Hughes | Thu 6/11/26 | Mon 6/15/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 3024 | ddd054016b6d4ba187858718cc9c774cb8b4df884353ba93daa196f9d3f0b324
project_plan | project_plan | 1078 | 3025 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Thu 6/11/26 | Thu 6/11/26 | Tue 4/14/26 | 0% | Future Task | 2974 | Yes | No | 3025 | 541778b9b845445ef06a8d0ab5a397f4b6504ebad9810133ca00ac29d1a1c209
project_plan | project_plan | 1079 | 3026 |  | Load |  | Kasey Hughes | Thu 6/11/26 | Fri 6/12/26 | Wed 4/15/26 | 0% | Future Task | 3025 | Yes | No | 3026 | 2be508a670dec6e5244c9427140fa7c46f627598309992edf4d44fd415aa476e
project_plan | project_plan | 1080 | 3027 |  | Post Load Validation |  | Kasey Hughes | Fri 6/12/26 | Mon 6/15/26 | Wed 4/15/26 | 0% | Future Task | 3026 | Yes | No | 3027 | 066aa303763c409c0011e217e6f0a36d7928baa224d4ccd920b4ff7947c40954
project_plan | project_plan | 1081 | 3028 |  | OTC_CM19_Customer_Master - Bill-To |  |  | Mon 6/8/26 | Mon 6/8/26 | Wed 4/16/25 | 0% | Future Task |  | Yes | No | 3028 | 4dcabdda1037f9c7eb92fe5f8b7f15d4c74f927ab48b6476c792367996f4a193
project_plan | project_plan | 1082 | 3029 |  | OTC_CM19_Customer_Master - Ship-To |  |  | Thu 6/11/26 | Mon 6/15/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 3029 | 58ce9ca4c47dfb2c3f123fa7ca9e3b479553d938398dfeb29c9ff88e749b584b
project_plan | project_plan | 1083 | 3030 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Thu 6/11/26 | Thu 6/11/26 | Wed 4/8/26 | 0% | Future Task | 2974 | Yes | No | 3030 | e9562cd443d8761f35b35674f1cdee211879f527e0fefe13bedb9c420b2853dc
project_plan | project_plan | 1084 | 3031 |  | Pre Load Validation |  | Ric Haraida | Thu 6/11/26 | Thu 6/11/26 | Wed 4/8/26 | 0% | Future Task | 3030 | Yes | No | 3031 | b201f81dc6ec11757c3c891b80eb11c210355675399e69096027f2737ba3c14b
project_plan | project_plan | 1085 | 3032 |  | Open client for BP number range update |  | Basis | Thu 6/11/26 | Thu 6/11/26 | Thu 4/9/26 | 0% | Future Task | 3031 | Yes | No | 3032 | 939fb464070748ed1f970a0ace765f2dd0202907c548c28e44b66423cb3c7d55
project_plan | project_plan | 1086 | 3033 |  | Update number range BP02 from Internal to External |  | Ric Haraida | Thu 6/11/26 | Thu 6/11/26 | Fri 4/10/26 | 0% | Future Task | 3032 | Yes | No | 3033 | 7c762b22adac629bc7b5eea180dc5aac3e3cfa927031cb1bd68b9b22f4000c64
project_plan | project_plan | 1087 | 3034 |  | Close Client |  | Basis | Thu 6/11/26 | Thu 6/11/26 | Mon 4/13/26 | 0% | Future Task | 3033 | Yes | No | 3034 | f7002c1c304016dd5c26a30fbcb00a55cd345c677bccec6d28b69a70712998a6
project_plan | project_plan | 1088 | 3035 |  | Simulate Load |  | Data Migration Team | Thu 6/11/26 | Thu 6/11/26 | Thu 4/9/26 | 0% | Future Task | 3031 | Yes | No | 3035 | 4ac16476f394ab7b0e53889570bde6da9367c4911f9a6697d5b171cde4fba9b8
project_plan | project_plan | 1089 | 3036 |  | Error and Defect Mitigation |  | Ric Haraida | Thu 6/11/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task | 3035 | Yes | No | 3036 | 038260550cee686f31b1921dd99e2e765b915aa4a12670ee80301528e82a8b88
project_plan | project_plan | 1090 | 3037 |  | Load |  | Data Migration Team | Fri 6/12/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task | 3036 | Yes | No | 3037 | 1b766e66e4ba79811eac16c09619b36cf1bae50c7088884a0f3ce86af52e9e1c
project_plan | project_plan | 1091 | 3038 |  | Post Load Validation |  | Ric Haraida | Fri 6/12/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3037 | Yes | No | 3038 | 2605278452b284ec803b435e300e07863f5d82629af166c8429900523888fdae
project_plan | project_plan | 1092 | 3039 |  | OTC_CM19_Customer_Master - Sold-To |  |  | Thu 6/11/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 3039 | 592927b4db064c4a50f437d61ee8f64ee912d16e5c1f0087dea037f3cce0e1cf
project_plan | project_plan | 1093 | 3040 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Thu 6/11/26 | Thu 6/11/26 | Thu 4/9/26 | 0% | Future Task | 3031 | Yes | No | 3040 | 111bd4b540cc6bcc658d3bcf41e348d390e20622e3fa1a4b9ba7a69cec0c68c2
project_plan | project_plan | 1094 | 3041 |  | Pre Load Validation |  | Ric Haraida | Thu 6/11/26 | Thu 6/11/26 | Thu 4/9/26 | 0% | Future Task | 3040 | Yes | No | 3041 | 10ed4e15399f094026dbfaa6e0a6b7d65c2f32d8cc0ec4a36c4aa89824b82c16
project_plan | project_plan | 1095 | 3042 |  | Simulate Load |  | Data Migration Team | Fri 6/12/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task | 29,763,035 | Yes | No | 3042 | 0992e315b9bb2406ebc512afd8b2d2bca0ab9893d75dd0908304f4d9bd23d2aa
project_plan | project_plan | 1096 | 3043 |  | Error and Defect Mitigation |  | Ric Haraida | Fri 6/12/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task | 3042 | Yes | No | 3043 | 2c2206aebe24c8f6a5ecc797b8883a4461cd72e8f11fb00f9aef5ba618f66029
project_plan | project_plan | 1097 | 3044 |  | Load |  | Data Migration Team | Fri 6/12/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3043 | Yes | No | 3044 | 5c0cbc7d6c8f9a58780e5bd2da0ada0988ad5d9c36b1a706cb989213b20dcf8d
project_plan | project_plan | 1098 | 3045 |  | Post Load Validation |  | Ric Haraida | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3044 | Yes | No | 3045 | 102169f3806fda73edbe5c2b5cd04912a4a6fee4383d0696ad0d4a1b25b5e9e0
project_plan | project_plan | 1099 | 3046 |  | Open client for BP number range update |  | Basis | Thu 6/11/26 | Thu 6/11/26 | Thu 4/9/26 | 0% | Future Task | 3035 | Yes | No | 3046 | 05c8de8e76fedefed6b38f9a96cab5813a8c4be05bb088f7d08d6a2e23e6c0d0
project_plan | project_plan | 1100 | 3047 |  | Update number range BP02 from Internal to External |  | Ric Haraida | Thu 6/11/26 | Thu 6/11/26 | Thu 4/9/26 | 0% | Future Task | 3046 | Yes | No | 3047 | f5de9b56bae80e1c72b3c7305c2d8bb034d1b66ad84f7266af478cc00c362e47
project_plan | project_plan | 1101 | 3048 |  | Close Client |  | Basis | Fri 6/12/26 | Fri 6/12/26 | Thu 4/9/26 | 0% | Future Task | 3047 | Yes | No | 3048 | ac009553fe5259348f039dfb381da274216a304ce58333a21d169b8bc2fd319c
project_plan | project_plan | 1102 | 3049 |  | PTP_CM27_Vendor Master as Customer - FLCU01 |  |  | Mon 6/15/26 | Fri 6/19/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 3049 | 80944f1ed3e47abc3404cefa63d2f074564f2eda9b899c82866d25d4c691b5c3
project_plan | project_plan | 1103 | 3050 |  | Extract File |  | Data Migration Team | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3044 | Yes | No | 3050 | a71659071b8d2886b7e43f7f3b1e4dae3b03c3bc0bf7a859bbd4c5ad100d054a
project_plan | project_plan | 1104 | 3051 |  | Pre Load Validation |  | Nevin Varkey | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3050 | Yes | No | 3051 | d88e2f936177e26377f27b3a101efca6e6be723a4056489c72dbb1d970a90585
project_plan | project_plan | 1105 | 3052 |  | Simulate Load |  | Data Migration Team | Mon 6/15/26 | Tue 6/16/26 | Mon 4/13/26 | 0% | Future Task | 30,163,051 | Yes | No | 3052 | 9372805d376967f9daf5ab00873e75eb2f0513551939775d069fe66d327511c8
project_plan | project_plan | 1106 | 3053 |  | Error and Defect Mitigation |  | Nevin Varkey | Tue 6/16/26 | Thu 6/18/26 | Tue 4/14/26 | 0% | Future Task | 3052 | Yes | No | 3053 | 0dfec9a99951e43133d8497f6568aac28b4cec697de91aaa2f93961e95775210
project_plan | project_plan | 1107 | 3054 |  | Load |  | Data Migration Team | Thu 6/18/26 | Fri 6/19/26 | Tue 4/14/26 | 0% | Future Task | 3053 | Yes | No | 3054 | 4cc438c7d859b0612669e2d22e865e6bbbc36ef4385f172c80124510af9e7f5a
project_plan | project_plan | 1108 | 3055 |  | Post Load Validation |  | Nevin Varkey | Fri 6/19/26 | Fri 6/19/26 | Tue 4/14/26 | 0% | Future Task | 3054 | Yes | No | 3055 | f0d2c791b37b45b571e4f348e5f814d2eed4457544d3159f14712197f7ab4c02
project_plan | project_plan | 1109 | 3056 |  | OTC_CM23_Customer_Hierarchy |  |  | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 3056 | e20ceb75cc664d7e808caca9980e210944f0c8b145808ac4065439b8dd5f96d9
project_plan | project_plan | 1110 | 3057 |  | Manual File Staged and Posted "Ready" |  | Ric Haraida | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3044 | Yes | No | 3057 | 885263d35fb753eea0db2d6903abe9bbcb91f11a450fcff70ed1e022eb78ac30
project_plan | project_plan | 1111 | 3058 |  | Load |  | Ric Haraida | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3057 | Yes | No | 3058 | 9dc972ac223c1da4555a32ff9ba5792d3c3fdbeff3e4a07c768b24b154b8034d
project_plan | project_plan | 1112 | 3059 |  | Post Load Validation |  | Ric Haraida | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3058 | Yes | No | 3059 | 1d7e30c0f1270a7f01ca046bf40e54653ef200169d53a615b7e2050b0ee9daa8
project_plan | project_plan | 1113 | 3060 |  | PTP_CM27_Vendor Master - Z001 - External Sales Rep |  |  | Mon 6/15/26 | Thu 6/18/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 3060 | a1d17e84062c1cc68f91c183b3e67a850f07e986336b3d8266dde969dd3f764b
project_plan | project_plan | 1114 | 3061 |  | Extract File |  | Data Migration Team | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3044 | Yes | No | 3061 | c3e1424a1c763c86b0753e7a6dcafa68017fdd1bd6bd6203f11079c7ce90b026
project_plan | project_plan | 1115 | 3062 |  | Pre Load Validation |  | Nevin Varkey | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3061 | Yes | No | 3062 | cb0b56575350198fda9c29df7d28c25b26523b7034443e9bd69bab51fa23d0dd
project_plan | project_plan | 1116 | 3063 |  | Simulate Load |  | Data Migration Team | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 30,163,062 | Yes | No | 3063 | ea7fdde2fb8e9091e5ed918b808645097f8bff59af439e59fb66f40df9404413
project_plan | project_plan | 1117 | 3064 |  | Error and Defect Mitigation |  | Nevin Varkey | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3063 | Yes | No | 3064 | 99aa32819cbd7440832c4b59312eadcdce879b0b41c9fbef971245845ef8ab51
project_plan | project_plan | 1118 | 3065 |  | Load |  | Data Migration Team | Mon 6/15/26 | Thu 6/18/26 | Mon 4/13/26 | 0% | Future Task | 3064 | Yes | No | 3065 | 8ca94ba6df571b5574967ab5afa002a8347d2c91af9f85a1103d4f9a997b7e9a
project_plan | project_plan | 1119 | 3066 |  | Post Load Validation |  | Nevin Varkey | Thu 6/18/26 | Thu 6/18/26 | Mon 4/13/26 | 0% | Future Task | 3065 | Yes | No | 3066 | 1b5270eec98a65f8ade5144928be501590fdf1e05988eda988076947dc7827f8
project_plan | project_plan | 1120 | 3067 |  | RTR_CM10_Credit_Management_Role |  |  | Mon 6/15/26 | Tue 6/16/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 3067 | 3f14a35b9c17bbb51a349eb34ad507c3fc6694aa99faa045c570caf8af1e41b5
project_plan | project_plan | 1121 | 3068 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3044 | Yes | No | 3068 | c9ddd75a59c2cee07af6e83260fb082f80c41a8ea9314b7a9b8e9f30df41980f
project_plan | project_plan | 1122 | 3069 |  | Pre Load Validation |  | Kasey Hughes | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3068 | Yes | No | 3069 | b8fedf47d09f7e4f51dd76ca2d4b00c72b431405376dda7543265a885368148a
project_plan | project_plan | 1123 | 3070 |  | Simulate Load |  | Data Migration Team | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3069 | Yes | No | 3070 | 39a35ef3b9a2c431c56a354545c87c1275045a0a1158703d44de02e9b1dad376
project_plan | project_plan | 1124 | 3071 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3070 | Yes | No | 3071 | c777abbb5af35e65b5fb8fb20fc91d7c8c3f160b80b33fd6005e232ef15cba0f
project_plan | project_plan | 1125 | 3072 |  | Load |  | Data Migration Team | Mon 6/15/26 | Tue 6/16/26 | Fri 4/10/26 | 0% | Future Task | 3071 | Yes | No | 3072 | 74271f438ab9c9afae8afa3bf3e4e3eed16644b139497f7d7ad7c5c0d24f4598
project_plan | project_plan | 1126 | 3073 |  | Post Load Validation |  | Kasey Hughes | Tue 6/16/26 | Tue 6/16/26 | Mon 4/13/26 | 0% | Future Task | 3072 | Yes | No | 3073 | 3452b41f07d465be82b414b6639cc13fdebbf4ae6b200db57f7217c398326826
project_plan | project_plan | 1127 | 3074 |  | PTP_CM27_Vendor Master |  |  | Mon 6/8/26 | Tue 6/16/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 3074 | ee6598a379971dd65e33462836dc3eaf4293ee1b35ea7c3ee74faa2f85b57eae
project_plan | project_plan | 1128 | 3075 |  | Extract File |  | Data Migration Team | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3061 | Yes | No | 3075 | bf0c054d3e7ae0190bbb5830c0a679527bd93a228e563871d2ebd576ddd0f4b0
project_plan | project_plan | 1129 | 3076 |  | Pre Load Validation |  | Nevin Varkey | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3075 | Yes | No | 3076 | 90e435e5737ed49160a08af2d5f3c38ef7bf22417c355c37898887468e52cb9c
project_plan | project_plan | 1130 | 3077 |  | Simulate Load |  | Data Migration Team | Mon 6/15/26 | Mon 6/15/26 | Tue 4/14/26 | 0% | Future Task | 3076 | Yes | No | 3077 | a82bc1971cf7bae342a83a960c7a45774e02727a0a52551b4c27db4c177832ba
project_plan | project_plan | 1131 | 3078 |  | Error and Defect Mitigation |  | Nevin Varkey | Mon 6/15/26 | Tue 6/16/26 | Tue 4/14/26 | 0% | Future Task | 3077 | Yes | No | 3078 | 2ae9508bc4a73f9d28df6ceae683f6f029c87c7c64daa49d90f0d19e742170a4
project_plan | project_plan | 1132 | 3079 |  | Load |  | Data Migration Team | Mon 6/8/26 | Mon 6/8/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 3079 | 35e419ec2c8142eccf783784a9d9faf663caa3490f8aa2aa5ae8fcb03872c07a
project_plan | project_plan | 1133 | 3080 |  | Post Load Validation |  | Nevin Varkey | Mon 6/8/26 | Mon 6/8/26 | Wed 4/15/26 | 0% | Future Task | 3079 | Yes | No | 3080 | f80ad73e313ecfd5f0b0fd1d15a0e25e1d03f6d86313f235ba93de982b9913b2
project_plan | project_plan | 1134 | 3081 |  | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR |  |  | Mon 6/8/26 | Tue 6/9/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 3081 | 0721165924a89f1611d786efe2c07206108d3fb72140cbbf7ef07759d8bc384a
project_plan | project_plan | 1135 | 3082 |  | Extract File(Will Extract from LFA1) |  | Nevin Varkey | Mon 6/8/26 | Mon 6/8/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 3082 | f78ab21edb78e98f5e61e6480c0520f84a3529968fd2b550450784b43109ec20
project_plan | project_plan | 1136 | 3083 |  | Pre Load Validation |  | Nevin Varkey | Mon 6/8/26 | Mon 6/8/26 | Fri 4/10/26 | 0% | Future Task | 3082 | Yes | No | 3083 | f63ff1e04424d73ceb2b9d1829652622081f1850d25e7dddef8e604451017b10
project_plan | project_plan | 1137 | 3084 |  | Simulate Load/ Not Needed |  | Nevin Varkey | Mon 6/8/26 | Mon 6/8/26 | Fri 4/10/26 | 0% | Future Task | 3083 | Yes | No | 3084 | 9cf88cdde67375d9a9ba2a69a30a22d86d2f65af1886885766bc9be5b638d7b0
project_plan | project_plan | 1138 | 3085 |  | Error and Defect Mitigation |  | Nevin Varkey | Mon 6/8/26 | Mon 6/8/26 | Mon 4/13/26 | 0% | Future Task | 3084 | Yes | No | 3085 | b3d0d9befbc4a3f9080acc741d61ce87cf8c0a3beeaa0bfb01f74fc2a0093ac0
project_plan | project_plan | 1139 | 3086 |  | Load |  | Nevin Varkkey | Mon 6/8/26 | Mon 6/8/26 | Wed 4/15/26 | 0% | Future Task | 3084 | Yes | No | 3086 | 527ee3eea2af120077ae66e502c1ec6a426c46c6ee65b48322f6303e6be2f62d
project_plan | project_plan | 1140 | 3087 |  | Post Load Validation |  | Nevin Varkey | Mon 6/8/26 | Tue 6/9/26 | Wed 4/15/26 | 0% | Future Task | 3086 | Yes | No | 3087 | adba5da75d9dd4b878f4bba4b60ac7c7065013b6f545cc2cb6c3916f456f0321
project_plan | project_plan | 1141 | 3088 |  | RTR_****_Credit Hierarchy |  |  | Mon 6/15/26 | Wed 6/17/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 3088 | 0c0cafe2921339d5ccf81bc3fa025dfcb0d8b1d7dd9a7f1efcd48cde3863df37
project_plan | project_plan | 1142 | 3089 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Mon 6/15/26 | Mon 6/15/26 | Fri 4/10/26 | 0% | Future Task | 3071 | Yes | No | 3089 | effd5f201315ecee54dc59774d0bb54890486f8cf38992a8fd8edfdbee426ff5
project_plan | project_plan | 1143 | 3090 |  | Load |  | Kasey Hughes | Tue 6/16/26 | Wed 6/17/26 | Mon 4/13/26 | 0% | Future Task | 3073 | Yes | No | 3090 | ff1bcf39877468e420f52cc5d9e769912dd1ab3cfcdb49505bf484e569130d60
project_plan | project_plan | 1144 | 3091 |  | Post Load Validation |  | Kasey Hughes | Wed 6/17/26 | Wed 6/17/26 | Mon 4/13/26 | 0% | Future Task | 3090 | Yes | No | 3091 | b6fb0756cc02c81544a7d539debb948a4e18e39fb60af9e3be47fa2e92fb93fb
project_plan | project_plan | 1145 | 3092 |  | PTP_CM27_BP_Intercompany Supplier |  |  | Mon 6/8/26 | Tue 6/9/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 3092 | 9eae16713f28276234ba84764a69c8311e12581653af9778172fd6b5ad30e908
project_plan | project_plan | 1146 | 3093 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Mon 6/8/26 | Mon 6/8/26 | Mon 4/13/26 | 0% | Future Task | 3080 | Yes | No | 3093 | 317c34239d09d98abc5e946e43318e4dddfb4f438317dd0d5837d24985dd5f0c
project_plan | project_plan | 1147 | 3094 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Mon 6/8/26 | Mon 6/8/26 | Mon 4/13/26 | 0% | Future Task | 3093 | Yes | No | 3094 | 9066338325f05103b625f81dc87dcc79441b2c7fa5a150c4b5d6bcb2600fdd9b
project_plan | project_plan | 1148 | 3095 |  | Simulate Load |  | Data Migration Team | Mon 6/8/26 | Mon 6/8/26 | Mon 4/13/26 | 0% | Future Task | 3094 | Yes | No | 3095 | ea8167351d2063fdbf21704b4f319008a1159e445b991e884073d14fe65cda82
project_plan | project_plan | 1149 | 3096 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Mon 6/8/26 | Tue 6/9/26 | Mon 4/13/26 | 0% | Future Task | 3095 | Yes | No | 3096 | a96d7020c03715a49b8f15b4658fedd57d4beda0f9b78d310d8e43e3d18dbedf
project_plan | project_plan | 1150 | 3097 |  | Load |  | Data Migration Team | Tue 6/9/26 | Tue 6/9/26 | Tue 4/14/26 | 0% | Future Task | 3096 | Yes | No | 3097 | d7d373ce4e5aab17c2f68bcaa72940fe7a818ed6ed8f081e7d2a0993478a2bf7
project_plan | project_plan | 1151 | 3098 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Tue 6/9/26 | Tue 6/9/26 | Tue 4/14/26 | 0% | Future Task | 3097 | Yes | No | 3098 | 0de34289c55207ea5badd4b8bbcb91ea351261e371e0f86152efd63287d185e2
project_plan | project_plan | 1152 | 3099 |  | PTP_CM27_BP_Intercompany Customer |  |  | Mon 6/8/26 | Tue 6/9/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 3099 | cd1afcec243851222b5997b36322c687144a84cea006fa6bc6cd4c7068a4286f
project_plan | project_plan | 1153 | 3100 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Mon 6/8/26 | Mon 6/8/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 3100 | aa137e422481500f30b0233bcd4ded0e40b1d840ef9df89d06a12312b72929ae
project_plan | project_plan | 1154 | 3101 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Mon 6/8/26 | Mon 6/8/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 3101 | 7803c8931b976337cbfe029bf26b8f0d457420bb9a12269cfe211074eb8dd47d
project_plan | project_plan | 1155 | 3102 |  | Simulate Load |  | Data Migration Team | Mon 6/8/26 | Mon 6/8/26 | Mon 4/13/26 | 0% | Future Task | 3101 | Yes | No | 3102 | e06e0000808ed3ccbeb10c1f97caf49e412cdebc2bf316d1e0b3b6da1dd1046c
project_plan | project_plan | 1156 | 3103 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Mon 6/8/26 | Mon 6/8/26 | Mon 4/13/26 | 0% | Future Task | 3102 | Yes | No | 3103 | 27caff6c5f5439cccf2677e81975cdf2a4444c00c1a73e0d3e540c61a81d6c27
project_plan | project_plan | 1157 | 3104 |  | Load |  | Data Migration Team | Mon 6/8/26 | Mon 6/8/26 | Tue 4/14/26 | 0% | Future Task | 3103 | Yes | No | 3104 | dafe643635e2a588fcd921f904b6520cd9be9f42df93b4052bd18bd46a8f6b7e
project_plan | project_plan | 1158 | 3105 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Mon 6/8/26 | Tue 6/9/26 | Tue 4/14/26 | 0% | Future Task | 3104 | Yes | No | 3105 | ed17c496a9a09e79f8604a00173dd6ff5333f1a4a312ec694a2c0776c403b111
project_plan | project_plan | 1159 | 3106 |  | PTP_CM26_Material_Master - All Types |  |  | Mon 6/8/26 | Wed 6/10/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 3106 | 410cd4e6df608990a62d69fd0651291e246bbd008bc5af3e7f3941260fc98eb9
project_plan | project_plan | 1160 | 3107 |  | Extract File |  | Data Migration Team | Mon 6/8/26 | Tue 6/9/26 | Mon 4/13/26 | 0% | Future Task | 3082 | Yes | No | 3107 | cdbe9ef256787ad04a2e3fd9f294715d10501a3234298af88a07699e444d10ec
project_plan | project_plan | 1161 | 3108 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Mon 6/8/26 | Tue 6/9/26 | Tue 4/14/26 | 0% | Future Task | 3080 | Yes | No | 3108 | 4bd1d536209ac414ba4f45523824b72dfb30a5f9c568d9ceff1309d055e79158
project_plan | project_plan | 1162 | 3109 |  | Simulate Load |  | Data Migration Team | Tue 6/9/26 | Tue 6/9/26 | Tue 4/14/26 | 0% | Future Task | 3108 | Yes | No | 3109 | f7bc2daf9497424d92c488972150fb0215cfcf78b0984a3c4b59f4aaee25ba61
project_plan | project_plan | 1163 | 3110 |  | Error and Defect Mitigation |  | Nevin Varkey | Tue 6/9/26 | Wed 6/10/26 | Tue 4/14/26 | 0% | Future Task | 3109 | Yes | No | 3110 | b8c1d66cbbaa8bb80243e2406fa85b2006a5216a379b8c70f4a480ceffc1a0cc
project_plan | project_plan | 1164 | 3111 |  | Load |  | Data Migration Team | Wed 6/10/26 | Wed 6/10/26 | Wed 4/15/26 | 0% | Future Task | 3110 | Yes | No | 3111 | 4973386f2b7670c99fda0a6637f7286137ce46561008f8123c77679eb40fb7d9
project_plan | project_plan | 1165 | 3112 |  | Post Load Validation |  | Nevin Varkey | Wed 6/10/26 | Wed 6/10/26 | Wed 4/15/26 | 0% | Future Task | 3111 | Yes | No | 3112 | b844607f989ab3c3b2e64ba7f0cf8a7d402c33aa9b4e7a76583ffe49d8358378
project_plan | project_plan | 1166 | 3113 |  | PTP_CM26_Material_Master - SERV - Service Materials |  |  | Wed 6/10/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 3113 | 125bbbe651a6effb5974a4f1a0cdccd0ebd93bb3863a89f1b590e1a78b8fd8df
project_plan | project_plan | 1167 | 3114 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Wed 6/10/26 | Wed 6/10/26 | Tue 4/7/26 | 0% | Future Task | 2983 | Yes | No | 3114 | b89e77e4d1d210314c35847b7215966bf881175a3519af0e660902aa29dd6196
project_plan | project_plan | 1168 | 3115 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Wed 6/10/26 | Wed 6/10/26 | Tue 4/14/26 | 0% | Future Task | 3111 | Yes | No | 3115 | 86b285f0c12d2490607a598645da351748f6d30803a4b749cd344b6865369271
project_plan | project_plan | 1169 | 3116 |  | Simulate Load |  | Data Migration Team | Wed 6/10/26 | Wed 6/10/26 | Tue 4/14/26 | 0% | Future Task | 3115 | Yes | No | 3116 | 816612285b99a3eb6b4c2584d33a94aadf2f8dc43704daa56809744cc1f6c93e
project_plan | project_plan | 1170 | 3117 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Wed 6/10/26 | Wed 6/10/26 | Wed 4/15/26 | 0% | Future Task | 3116 | Yes | No | 3117 | 21bb78ce0e14f3b4e43789ce567302be911637f9bf1a2d0337d185a7f2403fd1
project_plan | project_plan | 1171 | 3118 |  | Load |  | Data Migration Team | Wed 6/10/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task | 3117 | Yes | No | 3118 | e4d3a85e692f0f3f39bcacf12f1fc7d460ebe0cd5e0982dd2c031ab505bb2998
project_plan | project_plan | 1172 | 3119 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Thu 6/11/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task | 3118 | Yes | No | 3119 | bf0b65c04a55cea6f2c969c06868e1537c3292dc11cfe19217b4033417831da4
project_plan | project_plan | 1173 | 3120 |  | PTP_CM26_Material_Master - KMAT - Configurable Materials |  |  | Wed 6/10/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 3120 | 448bd49bd3f8d1303a7ce361146c3f6ae205c65d28a58daf71f16d4e2bca9be4
project_plan | project_plan | 1174 | 3121 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Wed 6/10/26 | Wed 6/10/26 | Tue 4/7/26 | 0% | Future Task | 2983 | Yes | No | 3121 | 34c0520256296bcd0a2cf0b45b6d8e2c96f1c0b4c10436e1d69ba3bb2bafebf1
project_plan | project_plan | 1175 | 3122 |  | Pre Load Validation |  | Eric Heisler | Wed 6/10/26 | Wed 6/10/26 | Tue 4/14/26 | 0% | Future Task | 3111 | Yes | No | 3122 | d62f9bcf8e818986b524bdf825f07a61141468881c606654e5ecc3702ee089f2
project_plan | project_plan | 1176 | 3123 |  | Simulate Load |  | Data Migration Team | Wed 6/10/26 | Wed 6/10/26 | Tue 4/14/26 | 0% | Future Task | 3122 | Yes | No | 3123 | 546d703dd44a160649a5e8262eff9dc29f02954a42464290943197465f654141
project_plan | project_plan | 1177 | 3124 |  | Error and Defect Mitigation |  | Eric Heisler | Wed 6/10/26 | Wed 6/10/26 | Wed 4/15/26 | 0% | Future Task | 3123 | Yes | No | 3124 | fcb03144bf476f7720eaa7ea14302885f4ce3526450b1e86a5d2e0858e1151ab
project_plan | project_plan | 1178 | 3125 |  | Load |  | Data Migration Team | Wed 6/10/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task | 3124 | Yes | No | 3125 | 9455b40a793bafe8a9afde8b522d084cffccb146244e6345c167d478edae9dae
project_plan | project_plan | 1179 | 3126 |  | Post Load Validation |  | Eric Heisler | Thu 6/11/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task | 3125 | Yes | No | 3126 | d9aacd24c7c20ba5c02015fd3680eb664cea08504e0a87fe6601bdc977dfa0bd
project_plan | project_plan | 1180 | 3127 |  | PTP_CM28_Purchase_Info_Records |  |  | Mon 6/8/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3127 | 883a3a08270cf353c75276bb8fb76b913b04803d2f4bcbc1093d87847935abf3
project_plan | project_plan | 1181 | 3128 |  | Extract File |  | Data Migration Team | Thu 6/11/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task | 31,123,126 | Yes | No | 3128 | df907a451c98502d33d7e268074512a090d938633c2cd9e128d9b709d5291312
project_plan | project_plan | 1182 | 3129 |  | Pre Load Validation |  | Nevin Varkey | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 3128 | Yes | No | 3129 | c961582a568a154590cbcab119f1fee5a461c593ed9338d1126c7c2313dbb7c3
project_plan | project_plan | 1183 | 3130 |  | Simulate Load |  | Data Migration Team | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 3129 | Yes | No | 3130 | 0b2d0a162ad0e91d08f3b4509873382b892418f0cf43934576bfae63f970d3d8
project_plan | project_plan | 1184 | 3131 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3130 | Yes | No | 3131 | 9f3fd9f783d58d60ac358541bd0d1a68e9f623a98ab7951969e127df03059fde
project_plan | project_plan | 1185 | 3132 |  | Load |  | Data Migration Team | Mon 6/8/26 | Mon 6/8/26 | Wed 4/15/26 | 0% | Future Task | 3080 | Yes | No | 3132 | 590d8120899e8cd60e7a205e6b3d752a6a9af58135c366fa4a8ae58879994d96
project_plan | project_plan | 1186 | 3133 |  | Post Load Validation |  | Nevin Varkey | Mon 6/8/26 | Mon 6/8/26 | Wed 4/15/26 | 0% | Future Task | 3132 | Yes | No | 3133 | 128991d9b4565f91eed235a99f7ea46f1d768b60fb020252466b5b0684dd65f3
project_plan | project_plan | 1187 | 3134 |  | PTP_CM28_Purchase_Info_Record External Processing |  |  | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3134 | 9ce370df8c4cb4e7a4da27b511cca9842dbaa8490f3897168363f7d3b884c651
project_plan | project_plan | 1188 | 3135 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey | Thu 6/11/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task | 31,123,126 | Yes | No | 3135 | 04e3e2d1b0308c8a29fa7cd6071d55f07608fe4e6427e9f6e88a2019df874efc
project_plan | project_plan | 1189 | 3136 |  | Pre Load Validation |  | Nevin Varkey | Thu 6/11/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task | 3135 | Yes | No | 3136 | dca5fd760970b34bbe3e929fccc14b2c5d8dd566093703d8697016a2ae6839b3
project_plan | project_plan | 1190 | 3137 |  | Simulate Load |  | Data Migration Team | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 3136 | Yes | No | 3137 | 08266efe4bd6937a6e32a69d6de47a307837822a0f640a2ff45430b1e92df4d0
project_plan | project_plan | 1191 | 3138 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 3137 | Yes | No | 3138 | c18ec7eba0d37bf0e2947aa010259761b0a0dc8759388457a57a1819013fe6f4
project_plan | project_plan | 1192 | 3139 |  | Load |  | Data Migration Team | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3138 | Yes | No | 3139 | b9acebd30f8a3327c92e7f9716731034868aa08e9d8a45119297ff04921c22bf
project_plan | project_plan | 1193 | 3140 |  | Post Load Validation |  | Nevin Varkey | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3139 | Yes | No | 3140 | 90a74d40f6ffa3f20ff8537e8be35ac2a8f045f232acbbf53ce81803a3268d5a
project_plan | project_plan | 1194 | 3141 |  | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment |  |  | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3141 | d339d10a9f4f0fa249926a213941323fe962e0e30ee46eb29490d698e22b11b3
project_plan | project_plan | 1195 | 3142 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey | Thu 6/11/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task | 31,123,126 | Yes | No | 3142 | 7f565c33c72ad136db2ebb389531aa20e57ec460bc7da514b2202756206dc719
project_plan | project_plan | 1196 | 3143 |  | Pre Load Validation |  | Nevin Varkey | Thu 6/11/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task | 3142 | Yes | No | 3143 | 749558b60e65537699d494422606b351cdd62ffe13c3b6e0eb1c9936a1685e91
project_plan | project_plan | 1197 | 3144 |  | Simulate Load |  | Data Migration Team | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 3143 | Yes | No | 3144 | c8e7203a816b253472053d85e14cce773d537f87f2e6c5401dadae7fe931d227
project_plan | project_plan | 1198 | 3145 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 3144 | Yes | No | 3145 | 4d999bb9ffb980b71e148c6fdf17bf59022a388233f394afaaaa015204fd12e9
project_plan | project_plan | 1199 | 3146 |  | Load |  | Data Migration Team | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3145 | Yes | No | 3146 | a3e44ba802eecfb53ef9a926e62519e4a1998545651c2ff9caae1c4be8e29e67
project_plan | project_plan | 1200 | 3147 |  | Post Load Validation |  | Nevin Varkey | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3146 | Yes | No | 3147 | 7fbd559bd8f44841f21656ddf5072a29e892eb0f3bae5227405ccefb0eaedd61
project_plan | project_plan | 1201 | 3148 |  | PTM_CM31_BOM Conversion |  |  | Thu 6/11/26 | Tue 6/16/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 3148 | 583b5c27db370896fbbddb0387b5cda155e1bde6f5a6f37d71826dfeb767681e
project_plan | project_plan | 1202 | 3149 |  | Extract File |  | Data Migration Team | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 3128 | Yes | No | 3149 | e5b25f7126ade0c88df09dcbc82bcc1f9b6b9c5d443d562a2342bf522be800a6
project_plan | project_plan | 1203 | 3150 |  | Pre Load Validation |  | Brad Meseck | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 3149 | Yes | No | 3150 | bbe2624788d8ea617f82b5ae2afbc40d8117639a3fbdb278b856b5be2afeae66
project_plan | project_plan | 1204 | 3151 |  | Simulate Load |  | Data Migration Team | Thu 6/11/26 | Mon 6/15/26 | Thu 4/16/26 | 0% | Future Task | 3150 | Yes | No | 3151 | 1aadb5247a042bd581e0f0cea7efbf706498983c34a3cc33bb04bd6d06ffa5b8
project_plan | project_plan | 1205 | 3152 |  | Error and Defect Mitigation |  | Brad Meseck | Mon 6/15/26 | Mon 6/15/26 | Thu 4/16/26 | 0% | Future Task | 3151 | Yes | No | 3152 | d56878e5e4f2220c32aacd8aac908c9a7ce8ebf5d4eaebdb2b411a76ec0274e7
project_plan | project_plan | 1206 | 3153 |  | Load |  | Data Migration Team | Mon 6/15/26 | Mon 6/15/26 | Thu 4/16/26 | 0% | Future Task | 3152 | Yes | No | 3153 | 3304d994b405587b5c7f6a64fc11c93a8f51cab878f41785479bc13e10f7b2d3
project_plan | project_plan | 1207 | 3154 |  | Post Load Validation |  | Brad Meseck | Tue 6/16/26 | Tue 6/16/26 | Fri 4/17/26 | 0% | Future Task | 3153 | Yes | No | 3154 | a36d884bd2c0f2b473ff062e22641ba7f9cb428e49803d75306705e1737ad744
project_plan | project_plan | 1208 | 3155 |  | PTM_CM40_Work Center Conversion |  |  | Thu 6/11/26 | Tue 6/16/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 3155 | 9dc67d2f8e0b387d5a89c47c6933edf7eaf7e55583faf32fc3f166bca938beee
project_plan | project_plan | 1209 | 3156 |  | Extract File |  | Data Migration Team | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 3149 | Yes | No | 3156 | 1c64c4a259a538bab15665dfbdcd97912d58cdabb12dc9d0450827f61862c1f7
project_plan | project_plan | 1210 | 3157 |  | Pre Load Validation |  | Brad Meseck | Tue 6/16/26 | Tue 6/16/26 | Fri 4/17/26 | 0% | Future Task | 3154 | Yes | No | 3157 | fdc6f76e4024a9505e21a1c4f01683ac31d9c80875a3b81653f4eacdc90ae920
project_plan | project_plan | 1211 | 3158 |  | Simulate Load |  | Data Migration Team | Tue 6/16/26 | Tue 6/16/26 | Fri 4/17/26 | 0% | Future Task | 3157 | Yes | No | 3158 | c4f5dcf6928fdd68ce505ad4a6dc34e44f478bfec28c4965e4467c8217cf0b97
project_plan | project_plan | 1212 | 3159 |  | Error and Defect Mitigation |  | Brad Meseck | Tue 6/16/26 | Tue 6/16/26 | Fri 4/17/26 | 0% | Future Task | 3158 | Yes | No | 3159 | 2a13aafcda1393fa9299299a82218fb910edc98ce142fae45dee6b9dc28be79b
project_plan | project_plan | 1213 | 3160 |  | Load |  | Data Migration Team | Tue 6/16/26 | Tue 6/16/26 | Fri 4/17/26 | 0% | Future Task | 3159 | Yes | No | 3160 | 89dc8cd220bd140cec69cdada6b37cc93142331b8c3dff04bd021a250e55c913
project_plan | project_plan | 1214 | 3161 |  | Post Load Validation |  | Brad Meseck | Tue 6/16/26 | Tue 6/16/26 | Mon 4/20/26 | 0% | Future Task | 3160 | Yes | No | 3161 | 0fce26d33dc0374ef0aa5e99072892acd941d5efd81e61473a6b7cd75a916f8f
project_plan | project_plan | 1215 | 3162 |  | PTM_CM38_Routing Conversion |  |  | Thu 6/11/26 | Thu 6/18/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 3162 | f2efe70ce5fdaa8a55bbe62a67a715efd128ab7452e309ef00e8fbec63038637
project_plan | project_plan | 1216 | 3163 |  | Extract File |  | Data Migration Team | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 3156 | Yes | No | 3163 | a2d1171e118282c129d54a175e5a624b130bb510c65a12cc3f6c09071e225a2b
project_plan | project_plan | 1217 | 3164 |  | Pre Load Validation |  | Brad Meseck | Tue 6/16/26 | Wed 6/17/26 | Mon 4/20/26 | 0% | Future Task | 3161 | Yes | No | 3164 | 5e07b5117099d6df57509d82f7a7c8b0a540d923b9d21d69e4dd150530b8551a
project_plan | project_plan | 1218 | 3165 |  | Simulate Load |  | Data Migration Team | Wed 6/17/26 | Wed 6/17/26 | Mon 4/20/26 | 0% | Future Task | 3164 | Yes | No | 3165 | ac15ad26a4b2fabd722e59525549ed4f743f00f0c3c582fc23e30dddf23deee3
project_plan | project_plan | 1219 | 3166 |  | Error and Defect Mitigation |  | Brad Meseck | Wed 6/17/26 | Wed 6/17/26 | Mon 4/20/26 | 0% | Future Task | 3165SS | Yes | No | 3166 | 17c13129e7c50b7bb662bb720ffe00cc658e08888fbfbcae4569733c1c283b52
project_plan | project_plan | 1220 | 3167 |  | Load |  | Data Migration Team | Wed 6/17/26 | Wed 6/17/26 | Mon 4/20/26 | 0% | Future Task | 3166 | Yes | No | 3167 | 81b20150573f66f0b038bd56d0c66bf944239fa2416981bfa68ecb5fb63778e8
project_plan | project_plan | 1221 | 3168 |  | Post Load Validation |  | Brad Meseck | Wed 6/17/26 | Thu 6/18/26 | Tue 4/21/26 | 0% | Future Task | 3167 | Yes | No | 3168 | fe24edda8e92df23e48893944c737d968dbaff548649a07b3c8625c11dfbb452
project_plan | project_plan | 1222 | 3169 |  | PTM_CM36_Production Version Conversion |  |  | Thu 6/11/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 3169 | 40a408b925f87204603b6c83b19c1ff6f0907a7640197dc3884b8935e381b550
project_plan | project_plan | 1223 | 3170 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3163 | Yes | No | 3170 | d4b23af1d50de15c704da746b933f78675ee700a11dfce53613cbd42d5ff2dd4
project_plan | project_plan | 1224 | 3171 |  | Pre Load Validation |  | Brad Meseck | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3170 | Yes | No | 3171 | 9da015a3e9394665441f8df5d00aa446e0a92a52ba4b1e7ee89db57ae17867a4
project_plan | project_plan | 1225 | 3172 |  | Simulate Load |  | Data Migration Team | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3171 | Yes | No | 3172 | 1953ea3d8c90188ecc22b373b67399c944e07db335dab3b4a0f1b9bd867ec9d4
project_plan | project_plan | 1226 | 3173 |  | Error and Defect Mitigation |  | Brad Meseck | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3172 | Yes | No | 3173 | 397b2cb1ea315651a5f232dc2e287a9080c0f9974a1542fbaaea660581ae1c68
project_plan | project_plan | 1227 | 3174 |  | Load |  | Data Migration Team | Fri 6/12/26 | Fri 6/12/26 | Fri 4/17/26 | 0% | Future Task | 3173 | Yes | No | 3174 | c1fbc3371b1ed8669da2fe9aeb156a7c748e88f2d4b5fb2cf06169dc64a8387e
project_plan | project_plan | 1228 | 3175 |  | Post Load Validation |  | Brad Meseck | Fri 6/12/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task | 3174 | Yes | No | 3175 | 76100ac6d39979bb4f5a9626a192a014a5ac012f358100a3a1a209ae67dc36e4
project_plan | project_plan | 1229 | 3176 |  | PTM_CM35_Inspection Plan |  |  | Mon 6/15/26 | Tue 6/16/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 3176 | 698047c1bc9a6898ea273837acff99479459907f8afa731907758b67c262f782
project_plan | project_plan | 1230 | 3177 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Mon 6/15/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task | 3175 | Yes | No | 3177 | 17fa2146fdf601c206802b4571ca45c3b46534d8f0f69a17dc0a091c909b21ae
project_plan | project_plan | 1231 | 3178 |  | Pre Load Validation |  | Brad Meseck | Mon 6/15/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task | 3177 | Yes | No | 3178 | eebfb6df796c631a5afba12cbfcbde0ba023131545e91d608f36d91ecb7716ae
project_plan | project_plan | 1232 | 3179 |  | Simulate Load |  | Data Migration Team | Mon 6/15/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task | 3178 | Yes | No | 3179 | 82f1fc8347b67eae7a0d69424f7a9c410481f62f4ebfa3e9c2f47c834e93b33e
project_plan | project_plan | 1233 | 3180 |  | Error and Defect Mitigation |  | Brad Meseck | Mon 6/15/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task | 3179 | Yes | No | 3180 | ec0fb422faff01d853bbf5c417a6924e302903ebfe74e5a5a667bee35361210a
project_plan | project_plan | 1234 | 3181 |  | Load |  | Data Migration Team | Mon 6/15/26 | Mon 6/15/26 | Mon 4/20/26 | 0% | Future Task | 3180 | Yes | No | 3181 | 8ea1d8f23bad0f73f625a965d4f6a0b1d028123d53d1719b43bf3a715058fd97
project_plan | project_plan | 1235 | 3182 |  | Post Load Validation |  | Brad Meseck | Mon 6/15/26 | Tue 6/16/26 | Mon 4/20/26 | 0% | Future Task | 3181 | Yes | No | 3182 | b18bc00a2ca3ecf2011e480a3428a2e4b80498e52b14c932488b832e73b9b148
project_plan | project_plan | 1236 | 3183 |  | PTM_CM48_Equipment_Master_Serial Numbers |  |  | Mon 6/15/26 | Tue 6/16/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 3183 | 65f4669e6de7f2c60c7aa0efdd05e4a9afbbbff15723874bcaae0dbbf87096d6
project_plan | project_plan | 1237 | 3184 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Mon 6/15/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task | 3177 | Yes | No | 3184 | c3b9db54f49b4592cfb075e407430aa330c1f1310fbf7ad14b4cd9e7fa59d8e3
project_plan | project_plan | 1238 | 3185 |  | Pre Load Validation |  | Brad Meseck | Mon 6/15/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task | 3184 | Yes | No | 3185 | e6dfa192e9a07cf4fee8e903f7b2b3806a25ac6e1c7a414011b945250df8b72c
project_plan | project_plan | 1239 | 3186 |  | Simulate Load |  | Data Migration Team | Mon 6/15/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task | 3185 | Yes | No | 3186 | 9e5957e55a618104ea4a21859d1138f9332f53f3a31c4911a23ab0b55ac890ae
project_plan | project_plan | 1240 | 3187 |  | Error and Defect Mitigation |  | Brad Meseck | Mon 6/15/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task | 3186 | Yes | No | 3187 | e85f5a883a96da190ac0f56210f2151fb7c57aa4546e019f0206c40a59411780
project_plan | project_plan | 1241 | 3188 |  | Load |  | Data Migration Team | Mon 6/15/26 | Mon 6/15/26 | Mon 4/20/26 | 0% | Future Task | 3187 | Yes | No | 3188 | 934d3341bd5711786e49d54a0a33cbe08ea76ceb71250ab2fb47a523ed3e6e73
project_plan | project_plan | 1242 | 3189 |  | Post Load Validation |  | Brad Meseck | Mon 6/15/26 | Tue 6/16/26 | Mon 4/20/26 | 0% | Future Task | 3188 | Yes | No | 3189 | a80145df4538c6696cac1e1021fd4702aab315d0f66992500a08042948bffc64
project_plan | project_plan | 1243 | 3190 |  | PTM_CM48_Equipment_Master_Service |  |  | Mon 6/8/26 | Wed 6/17/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 3190 | 7b4cb53e5b643bd959ca0d1c379a3171b910487852467cf3ebf9f3622ba10831
project_plan | project_plan | 1244 | 3191 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Tue 6/16/26 | Tue 6/16/26 | Mon 4/20/26 | 0% | Future Task | 3189 | Yes | No | 3191 | 4735961d0c9a98c6d4f94c068bdbb443fdb5a31433f61afc2da8997c4553a97f
project_plan | project_plan | 1245 | 3192 |  | Pre Load Validation |  | Brad Meseck | Tue 6/16/26 | Tue 6/16/26 | Mon 4/20/26 | 0% | Future Task | 3191 | Yes | No | 3192 | 3b8bbc054b1d8b071a971db65290c1ca4a86e12801b3edc300967add34db4789
project_plan | project_plan | 1246 | 3193 |  | Simulate Load |  | Data Migration Team | Tue 6/16/26 | Tue 6/16/26 | Mon 4/20/26 | 0% | Future Task | 3192 | Yes | No | 3193 | 7a81e086fe084778bcb9f43e7e851d287f627d5e9dbbca41f918c5bd68411d7b
project_plan | project_plan | 1247 | 3194 |  | Error and Defect Mitigation |  | Brad Meseck | Tue 6/16/26 | Tue 6/16/26 | Tue 4/21/26 | 0% | Future Task | 3193 | Yes | No | 3194 | 0bdd903af07956565fe13a052d52a0644976b92e6808a841b1d9c1848d775f40
project_plan | project_plan | 1248 | 3195 |  | Load |  | Data Migration Team | Tue 6/16/26 | Wed 6/17/26 | Tue 4/21/26 | 0% | Future Task | 3194 | Yes | No | 3195 | d111d67ec1d82d9794ca4944f63446e502d3892a9859152c2891f4c4aff0b4af
project_plan | project_plan | 1249 | 3196 |  | Post Load Validation |  | Brad Meseck | Mon 6/8/26 | Mon 6/8/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 3196 | 75d23a62b9f63011b85604169a03cad44c77bb74de368e3db7bd990aa2441dde
project_plan | project_plan | 1250 | 3197 |  | VC_Object Dependencies |  |  | Mon 6/8/26 | Mon 6/8/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 3197 | 45d8fb55666ba5bd15e9ed45e7e4b5266ef60d08e6a6a31a31680123d381f658
project_plan | project_plan | 1251 | 3198 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Mon 6/8/26 | Mon 6/8/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 3198 | e341ea96b71f178f3d9c0fb40564f2378c42105542ca8f537d16375a5d90d996
project_plan | project_plan | 1252 | 3199 |  | Post Load Validation |  | Eric Heisler | Mon 6/8/26 | Mon 6/8/26 | Mon 4/6/26 | 0% | Future Task | 3198 | Yes | No | 3199 | 41300bfbf6b3f15f780ed592b2f3e902b7014fd487b324950a677617491dce7d
project_plan | project_plan | 1253 | 3200 |  | VC_Characteristics |  |  | Mon 6/8/26 | Tue 6/9/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 3200 | 6d0aee846ea04a53dadb6f62d959bb5da8677831b573e8def40913af6e45d757
project_plan | project_plan | 1254 | 3201 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Mon 6/8/26 | Tue 6/9/26 | Mon 4/6/26 | 0% | Future Task | 3199 | Yes | No | 3201 | dd6d13d82706aeb8bc73a907c70244168476a86ff802dd66fee646e4bb0f63d2
project_plan | project_plan | 1255 | 3202 |  | Post Load Validation |  | Eric Heisler | Tue 6/9/26 | Tue 6/9/26 | Tue 4/7/26 | 0% | Future Task | 3201 | Yes | No | 3202 | 2f7812981ea78eff643925aebaf7986c7f4980b93523e0dad6ef56839b5653cb
project_plan | project_plan | 1256 | 3203 |  | VC_Classes |  |  | Tue 6/9/26 | Wed 6/10/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 3203 | 00fc67ab732dd35ba07c095bb8aa78685530a915b93b41ed28af0c8ef5bd8bb3
project_plan | project_plan | 1257 | 3204 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 6/9/26 | Tue 6/9/26 | Tue 4/7/26 | 0% | Future Task | 3202 | Yes | No | 3204 | ea38e5d0c4bb93c3239f69b2c57adf8983db45dfd5c4907229f5cf6ab1f4b2c0
project_plan | project_plan | 1258 | 3205 |  | Post Load Validation |  | Eric Heisler | Tue 6/9/26 | Wed 6/10/26 | Tue 4/7/26 | 0% | Future Task | 3204 | Yes | No | 3205 | a9317fbbce5fb259985e5269c8193f481cfa956e50c40cbf6e48f534fa29b6d1
project_plan | project_plan | 1259 | 3206 |  | VC_Classification (Class Type 200) |  |  | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3206 | 20053d299efdfc481689228753cd583197f87feb9926d46ad6eeef17f2fcd8db
project_plan | project_plan | 1260 | 3207 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 3126 | Yes | No | 3207 | bf422d8fa81656388ed6c88cfc877e353e80976b5a6f57c2e30bf6a5bbf47a0f
project_plan | project_plan | 1261 | 3208 |  | Post Load Validation |  | Eric Heisler | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3207 | Yes | No | 3208 | 84262973d123de5f05107664b1d1f536c092b5cc8e591561dda9eba88e085bc7
project_plan | project_plan | 1262 | 3209 |  | VC_Dependency Nets |  |  | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3209 | af56e4c2fa2a8fba1b508017bcf028afabbb619300431163d1cabccbf5457d8a
project_plan | project_plan | 1263 | 3210 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 31,203,205 | Yes | No | 3210 | d9f001941436346284f9a63c685883fb60d69035f8a03b951a58172fdfa539de
project_plan | project_plan | 1264 | 3211 |  | Post Load Validation |  | Eric Heisler | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3210 | Yes | No | 3211 | a2e05fec8d1aaa40d764c3462d0f33edaf2dc04b3a7f6b7187113d65784952e3
project_plan | project_plan | 1265 | 3212 |  | VC_Configuration Profiles |  |  | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3212 | 77c91f47f8649961ddce24163dee4df2f60ac0f308c6aeae9d3e5e082ddd469c
project_plan | project_plan | 1266 | 3213 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Thu 6/11/26 | Thu 6/11/26 | Thu 4/16/26 | 0% | Future Task | 3120 | Yes | No | 3213 | fb609a7b524d7d65cf80b3122ab3aa3abd834734f4c68ba0cfd0a4ef9c1a26cb
project_plan | project_plan | 1267 | 3214 |  | Post Load Validation |  | Eric Heisler | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3213 | Yes | No | 3214 | 7b0ba0d986c6f14b690a7aeb59ae951e49abb650cd5ea8ac57cc135f6f5bc3ba
project_plan | project_plan | 1268 | 3215 |  | VC_Variant Tables |  |  | Fri 6/12/26 | Fri 6/12/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 3215 | 6ae5ac66cc8aba211301cbc4c1e49bbc7d720ba858e7791996484ee6573ca2be
project_plan | project_plan | 1269 | 3216 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3214 | Yes | No | 3216 | 8ad982b3f8962461cc2ef1bf4bdae7ec42a51584482e6bc59941b58c66f90f59
project_plan | project_plan | 1270 | 3217 |  | Post Load Validation |  | Eric Heisler | Fri 6/12/26 | Fri 6/12/26 | Fri 4/17/26 | 0% | Future Task | 3216 | Yes | No | 3217 | b51fc6fe1ed4efa75b7b69d46173bc362c5fa3e7b81eb04ce97f3f947ad79bc1
project_plan | project_plan | 1271 | 3218 |  | VC_Variant Tables Content |  |  | Fri 6/12/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 3218 | 64ff63dce66175b86bd759a5640053d402a3b83b7d7777f842a84029d078fa89
project_plan | project_plan | 1272 | 3219 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Fri 6/12/26 | Fri 6/12/26 | Fri 4/17/26 | 0% | Future Task | 3217 | Yes | No | 3219 | 17eec8265a9e19e8f69844fa68d375ec3d88f8598343a806e57c7524d9a64cdc
project_plan | project_plan | 1273 | 3220 |  | Post Load Validation |  | Eric Heisler | Fri 6/12/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task | 3219 | Yes | No | 3220 | b29af2e364baf2d5f10a76fde5aef7d1dd929f81836177b3a75dbee4cd8535dc
project_plan | project_plan | 1274 | 3221 |  | VC_Characteristic Groups |  |  | Fri 6/12/26 | Tue 6/16/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 3221 | d6cd78db366e55e004112f2a667cad54cc394d67d11307dbf644cb5b426b66fc
project_plan | project_plan | 1275 | 3222 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Fri 6/12/26 | Mon 6/15/26 | Thu 4/16/26 | 0% | Future Task | 3214 | Yes | No | 3222 | c29f94b5bc89e1ecd6532e593e263762327d0c5084020b103892b8b228d8414b
project_plan | project_plan | 1276 | 3223 |  | Post Load Validation |  | Eric Heisler | Mon 6/15/26 | Tue 6/16/26 | Fri 4/17/26 | 0% | Future Task | 3222 | Yes | No | 3223 | dae740385fdf12c5b9ae24645270bc0b759891535684316fbf3bcf09ed906a81
project_plan | project_plan | 1277 | 3224 |  | PTM_CM52_Super_BOM |  |  | Thu 6/11/26 | Mon 6/15/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3224 | 996366950c3ce3ae6da2f1fe925fe967360d8043fe75a14b2bd14775d85b71fc
project_plan | project_plan | 1278 | 3225 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Thu 6/11/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task | 3126 | Yes | No | 3225 | 77e7336beaf6aafa82592747f3ad96ca4a034c305c7261bc5486543b74c98ec6
project_plan | project_plan | 1279 | 3226 |  | Pre Load Validation |  | Eric Heisler | Thu 6/11/26 | Thu 6/11/26 | Wed 4/15/26 | 0% | Future Task | 3225 | Yes | No | 3226 | 042f477238d9f367b99318b61ce88c79f2d519943f597233ef28c487dfa3c65c
project_plan | project_plan | 1280 | 3227 |  | Simulate Load |  | Data Migration Team | Thu 6/11/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3226 | Yes | No | 3227 | 5dc3653130fce4a6f006ea9db325b0ad13d068deceb04d0dcf3df7fc6b8d466d
project_plan | project_plan | 1281 | 3228 |  | Error and Defect Mitigation |  | Eric Heisler | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3227 | Yes | No | 3228 | 1dac61f86e3741ab934ead7f12137b29fece2acfab58336b44af6c54a42cb18d
project_plan | project_plan | 1282 | 3229 |  | Load |  | Data Migration Team | Fri 6/12/26 | Mon 6/15/26 | Thu 4/16/26 | 0% | Future Task | 3228 | Yes | No | 3229 | 7b5d364f4e4339c06ced59c93b79193ca6372c188f4fd51b82fa1ad40474a439
project_plan | project_plan | 1283 | 3230 |  | Post Load Validation |  | Eric Heisler | Mon 6/15/26 | Mon 6/15/26 | Thu 4/16/26 | 0% | Future Task | 3229 | Yes | No | 3230 | 154177f7512d72bfabb78416757eeb6555386ea95dd5b5e2e8dca186962fd01b
project_plan | project_plan | 1284 | 3231 |  | PTM_CM53_Super_Routing |  |  | Mon 6/15/26 | Wed 6/17/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 3231 | b9b70f2eca15407805cbafb42fb62826b772acc2c9031778f7a038c419ef5e9a
project_plan | project_plan | 1285 | 3232 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Mon 6/15/26 | Mon 6/15/26 | Thu 4/16/26 | 0% | Future Task | 3230 | Yes | No | 3232 | eae48cfd58771bb40913b8119c1c42fd5b5e7bb7e126cee3d61c5387a9bf87bf
project_plan | project_plan | 1286 | 3233 |  | Pre Load Validation |  | Eric Heisler | Mon 6/15/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task | 3232 | Yes | No | 3233 | fb4bd9907582c17c9417b895415e531bfae88ba99aaf9487527d7fd26ce69e3d
project_plan | project_plan | 1287 | 3234 |  | Simulate Load |  | Data Migration Team | Mon 6/15/26 | Tue 6/16/26 | Fri 4/17/26 | 0% | Future Task | 3233 | Yes | No | 3234 | 5a2d1f7fd125d0f25e8808ac3f21c721e27d096aeb48fb65c03786dbb43308c5
project_plan | project_plan | 1288 | 3235 |  | Error and Defect Mitigation |  | Eric Heisler | Tue 6/16/26 | Tue 6/16/26 | Fri 4/17/26 | 0% | Future Task | 3234 | Yes | No | 3235 | 4f98ce6fd0caec48359dc0c8a3205966959f80dbdb7715c7dc03b7ab859fa500
project_plan | project_plan | 1289 | 3236 |  | Load |  | Data Migration Team | Tue 6/16/26 | Wed 6/17/26 | Fri 4/17/26 | 0% | Future Task | 3235 | Yes | No | 3236 | 83c85e095ca4345c9d5a2f3062f23436c1f25e91634d7b153e2ff35636feb644
project_plan | project_plan | 1290 | 3237 |  | Post Load Validation |  | Eric Heisler | Wed 6/17/26 | Wed 6/17/26 | Mon 4/20/26 | 0% | Future Task | 3236 | Yes | No | 3237 | 3e2fbfb6509fa479e6a6f7ac2de06f4a2b9a8eef657f094a9581b897f8c3233e
project_plan | project_plan | 1291 | 3238 |  | VC_VK30 Pricing Variant |  |  | Wed 6/17/26 | Wed 6/17/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 3238 | 10b4bf8c534376b3b1155b2c2c2aa8f8b8238e076f4061a7e31adafcc1b09c81
project_plan | project_plan | 1292 | 3239 |  | Manual File Staged and Posted "Ready" |  | Eric Heisler | Wed 6/17/26 | Wed 6/17/26 | Fri 4/17/26 | 0% | Future Task | 3236 | Yes | No | 3239 | 12b0bd9239181072744bfa60d91af6eaae17adc8846ab7127dcfa0255a5dec06
project_plan | project_plan | 1293 | 3240 |  | Load |  | Eric Heisler | Wed 6/17/26 | Wed 6/17/26 | Fri 4/17/26 | 0% | Future Task | 3239 | Yes | No | 3240 | 27a6681f8028ed270958d5126e77ba038a829ea6335596dee70855e8fdf2efd9
project_plan | project_plan | 1294 | 3241 |  | Post Load Validation |  | Eric Heisler | Wed 6/17/26 | Wed 6/17/26 | Mon 4/20/26 | 0% | Future Task | 3240 | Yes | No | 3241 | c20799fd2900276a72fc22d303ff751fa8971bac74932cee4bf8b0717f96cbce
project_plan | project_plan | 1295 | 3242 |  | OTC_CM22_Pricing_Condition |  |  | Wed 6/17/26 | Thu 6/18/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 3242 | e142792f8e6884b081947d32da773f289a6d28b87875eef38949242eeee03765
project_plan | project_plan | 1296 | 3243 |  | Manual File Staged and Posted "Ready" |  | Ric Haraida | Wed 6/17/26 | Wed 6/17/26 | Mon 4/20/26 | 0% | Future Task | 3241 | Yes | No | 3243 | a69ff39473614fa5463a34136caacf97f82b62fe540bafd44e33091850b77a80
project_plan | project_plan | 1297 | 3244 |  | Load |  | Ric Haraida | Wed 6/17/26 | Thu 6/18/26 | Mon 4/20/26 | 0% | Future Task | 3243 | Yes | No | 3244 | 3c13c17eda219a15832d1a9c031b26c71aeda60784983b7bf446bdb1eba90a7d
project_plan | project_plan | 1298 | 3245 |  | Post Load Validation |  | Ric Haraida,Kim Kolesar | Thu 6/18/26 | Thu 6/18/26 | Tue 4/21/26 | 0% | Future Task | 3244 | Yes | No | 3245 | c1c88f43e295f925db428d1dbb4dec61e0f3141736090a5227770baebad5ef04
project_plan | project_plan | 1299 | 3246 |  | OTC_CM21_CMIR |  |  | Thu 6/18/26 | Thu 6/18/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 3246 | e99923318a641f5823cfe081bfd27e537128494d39d64e4af74806e57b336ba4
project_plan | project_plan | 1300 | 3247 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Thu 6/18/26 | Thu 6/18/26 | Mon 4/20/26 | 0% | Future Task | 32,443,255 | Yes | No | 3247 | 01f2e345875c54bf186735ae44bfb85a22345eb7ce8d372d3b6c15fb9d9f018d
project_plan | project_plan | 1301 | 3248 |  | Pre Load Validation |  | Ric Haraida | Thu 6/18/26 | Thu 6/18/26 | Mon 4/20/26 | 0% | Future Task | 3247 | Yes | No | 3248 | 44d4bf88d23590ca745158b4584a660a43ba7d572bb5d7b74fc5c7858c0b5e0f
project_plan | project_plan | 1302 | 3249 |  | Simulate Load |  | Data Migration Team | Thu 6/18/26 | Thu 6/18/26 | Mon 4/20/26 | 0% | Future Task | 3248 | Yes | Yes | 3249 | ca134c4f5f1638fe6c4ba652cae7adbd948a751372f5eac257ef59873bb48b54
project_plan | project_plan | 1303 | 3250 |  | Error and Defect Mitigation |  | Ric Haraida | Thu 6/18/26 | Thu 6/18/26 | Tue 4/21/26 | 0% | Future Task | 3249 | Yes | Yes | 3250 | 9e2e98578b0d37b71ba142f610cc475fda1e21aa71755dd3bc76a4121a3f2978
project_plan | project_plan | 1304 | 3251 |  | Load |  | Data Migration Team | Thu 6/18/26 | Thu 6/18/26 | Tue 4/21/26 | 0% | Future Task | 3250 | Yes | Yes | 3251 | 96318797238d3439fcba8045bed42c0e6068f675eb4b0497da81665de92f35cc
project_plan | project_plan | 1305 | 3252 |  | Post Load Validation |  | Ric Haraida | Thu 6/18/26 | Thu 6/18/26 | Tue 4/21/26 | 0% | Future Task | 3251 | Yes | No | 3252 | cbf31d5ec6f482aa246753be933fded9fd68d6467a7ec11e304943847a2b3df1
project_plan | project_plan | 1306 | 3253 |  | PTP_CM29_Source_List |  |  | Tue 6/9/26 | Wed 6/17/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 3253 | c059314cfac64086b4e661221d29119e18c5daf4c743fe44eeee6fcb2a92b0a2
project_plan | project_plan | 1307 | 3254 |  | Manual File Staged and Posted "Ready" |  | Nevin Varkey | Tue 6/9/26 | Tue 6/9/26 | Tue 4/14/26 | 0% | Future Task | 30,973,104 | Yes | No | 3254 | aa0bf21ce1f183918aff8151e8cabdec0bc4db923461c1f2fb3aecdc9aae7f1f
project_plan | project_plan | 1308 | 3255 |  | Load |  | Nevin Varkey | Tue 6/16/26 | Wed 6/17/26 | Mon 4/13/26 | 0% | Future Task | 3073 | Yes | No | 3255 | 0453c9334ae672b1a1e9ba6e54ea9830afe7c7345216ff767c09e91a4fdc4237
project_plan | project_plan | 1309 | 3256 |  | Post Load Validation |  | Nevin Varkey | Wed 6/17/26 | Wed 6/17/26 | Mon 4/13/26 | 0% | Future Task | 3255 | Yes | No | 3256 | 35f2823a586ea30653e7e084e6f3ebfcee37c76cc514580bd2f4d57fabc889ea
project_plan | project_plan | 1310 | 3257 |  | RTR_CM11_Asset_Master |  |  | Mon 6/8/26 | Thu 6/11/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 3257 | 780c7e378622122ff1f75db58cc3c5fec2d2cf234ff9feb8e2a513a0a90cd951
project_plan | project_plan | 1311 | 3258 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Mon 6/8/26 | Mon 6/8/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 3258 | 37a921a6e5cf1af237b4640f964546e1e9d91a2154ac05d4a17029e013e321e0
project_plan | project_plan | 1312 | 3259 |  | Pre Load Validation |  | Kasey Hughes,Femi Oguntala | Mon 6/8/26 | Mon 6/8/26 | Fri 4/10/26 | 0% | Future Task | 3258 | Yes | No | 3259 | e3fb311c8a0c52bf863ba7d464a89fb5b3c88d0e038755eaf99d044f95c63b87
project_plan | project_plan | 1313 | 3260 |  | Simulate Load |  | Data Migration Team | Mon 6/8/26 | Tue 6/9/26 | Fri 4/10/26 | 0% | Future Task | 3259 | Yes | No | 3260 | 6bbab2fd95d6a65e82dcf555958bff22e88640de550c44850ba1f971c87b355f
project_plan | project_plan | 1314 | 3261 |  | Error and Defect Mitigation |  | Kasey Hughes | Tue 6/9/26 | Thu 6/11/26 | Fri 4/10/26 | 0% | Future Task | 3260 | Yes | No | 3261 | 7fbfe1ac487f3da4a43395331654316cdaa44ab4b6f9fe5b45c442d3e35fe055
project_plan | project_plan | 1315 | 3262 |  | Load |  | Data Migration Team | Thu 6/11/26 | Thu 6/11/26 | Fri 4/10/26 | 0% | Future Task | 3261 | Yes | No | 3262 | aecd08dad529283fffb60ad9347f31969fd75ffb634bbbf86e91ff22fa645919
project_plan | project_plan | 1316 | 3263 |  | Post Load Validation |  | Kasey Hughes | Thu 6/11/26 | Thu 6/11/26 | Mon 4/13/26 | 0% | Future Task | 3262 | Yes | No | 3263 | 1c18b5acf56671186ee5c80fc9eb64f179145560b4435a7a391e3e691a40a69a
project_plan | project_plan | 1317 | 3264 |  | PTM_CM50_Material Class |  |  | Fri 6/12/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3264 | 648313204fd370424743df76c0c2cbc9de67c8c8cf0a91968cd643eccbd076cf
project_plan | project_plan | 1318 | 3265 |  | Manual File Staged and Posted "Ready" |  | Sam | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3170 | Yes | No | 3265 | e5cf715dd59c4ecd487b5c64e16fc9832bd7ba09a0f70bce34601c24efbee4f7
project_plan | project_plan | 1319 | 3266 |  | Load |  | Brad Meseck | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3265 | Yes | No | 3266 | 261aa87333c6b748636c6b437286a79acf924c6d144c810819057ea162562d26
project_plan | project_plan | 1320 | 3267 |  | Post Load Validation |  | Brad | Fri 6/12/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task | 3266 | Yes | No | 3267 | a31e194cb395d4626e67f063ea6d7366a8d63b331511123fb2a885457aaf1bff
project_plan | project_plan | 1321 | 3268 |  | PTM_CM55_Class assignment to materials |  |  | Fri 6/12/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 3268 | 670a075d91f83537a1145f7f7309e36c243d1588d5bb7e029b86bcb11a5545d8
project_plan | project_plan | 1322 | 3269 |  | Load File Staged and Posted "Ready" |  | Sam | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3265 | Yes | No | 3269 | 7036cda0b0ff681830a09c5809ecfaccbab269881980476e5859876d0cf78db9
project_plan | project_plan | 1323 | 3270 |  | Pre Load Validation |  | Brad Meseck | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3269 | Yes | No | 3270 | 00451f2c9d2524d1df9770a8551c5bbc75d6f869a7f3aef97d716f1f93e30ce4
project_plan | project_plan | 1324 | 3271 |  | Simulate Load |  | Data Migration Team | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3270 | Yes | No | 3271 | 41ee318e4d302409ad895dc4a7b3d7c4c359d0136f823264b0c6ffc99f5f306c
project_plan | project_plan | 1325 | 3272 |  | Error and Defect Mitigation |  | Brad Meseck | Fri 6/12/26 | Fri 6/12/26 | Thu 4/16/26 | 0% | Future Task | 3271 | Yes | No | 3272 | aef8f087698f0830d5155c3c0d1691f849387b4c3b8d0983586dc8b8a00cbf12
project_plan | project_plan | 1326 | 3273 |  | Load |  | Data Migration Team | Fri 6/12/26 | Fri 6/12/26 | Fri 4/17/26 | 0% | Future Task | 3272 | Yes | No | 3273 | 81658380bafa253d3c5bb41758e56e2c3b39af28f99dd729e8cf89faf51aa969
project_plan | project_plan | 1327 | 3274 |  | Post Load Validation |  | Brad Meseck | Fri 6/12/26 | Mon 6/15/26 | Fri 4/17/26 | 0% | Future Task | 3273 | Yes | No | 3274 | 4a8d7b4bd7479694728c1b5419699df60f9f32d0f2eb05f6b60b5bc5d761d2bf
project_plan | project_plan | 1328 | 3275 |  | GTS - Material initial load from S4 (Run Interface) |  |  | Thu 6/11/26 | Mon 6/15/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3275 | 8e2b80befafde614f85e2bd35984f228fb63d834e59c8f8c8d925352f50e16e0
project_plan | project_plan | 1329 | 3276 |  | Run material interface to GTS |  | James Van Riper | Thu 6/11/26 | Mon 6/15/26 | Thu 4/16/26 | 0% | Future Task | 3144 | Yes | No | 3276 | 340bb26bdaea30e24611189d9f80af8c727a98e530d3ac6dba9d6bea2b2995cb
project_plan | project_plan | 1330 | 3277 |  | Post Load Validation |  | James Van Riper | Mon 6/15/26 | Mon 6/15/26 | Thu 4/16/26 | 0% | Future Task | 3276 | Yes | No | 3277 | 69c64a6a0341dc2b466bedb59084d013c0912369c4c01a101a8366123e8ffe78
project_plan | project_plan | 1331 | 3278 |  | GTS - Customers initial load from S4 (Run Interface) |  |  | Mon 6/8/26 | Mon 6/8/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 3278 | e015f1722aa8a9b4e026d059a18d64322ec8ce30871ceaabcae8d9714508628f
project_plan | project_plan | 1332 | 3279 |  | Run material interface to GTS |  | James Van Riper | Mon 6/8/26 | Mon 6/8/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 3279 | 6b8e32760073c63e74a006ce59ef5c331d1283e227d2be6914fd10f4b514fd94
project_plan | project_plan | 1333 | 3280 |  | Post Load Validation |  | James Van Riper | Mon 6/8/26 | Mon 6/8/26 | Fri 4/10/26 | 0% | Future Task | 3279 | Yes | No | 3280 | f31b4ca971255b57b00f49ac855abc882dd915b8bc4f801e5fe42f6da0dee137
project_plan | project_plan | 1334 | 3281 |  | GTS - Vendors initial load from S4 (Run Interface) |  |  | Tue 6/9/26 | Tue 6/9/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 3281 | 5f4da9bae8040da3e83abf528c68728d1259afe4e0c6a252edc906eafda13821
project_plan | project_plan | 1335 | 3282 |  | Run material interface to GTS |  | James Van Riper | Tue 6/9/26 | Tue 6/9/26 | Wed 4/15/26 | 0% | Future Task | 3087 | Yes | No | 3282 | 9c8a3334af846c902bd04d2f3d830c93d7f3921d80de42188599aa63d12665f9
project_plan | project_plan | 1336 | 3283 |  | Post Load Validation |  | James Van Riper | Tue 6/9/26 | Tue 6/9/26 | Wed 4/15/26 | 0% | Future Task | 3282 | Yes | No | 3283 | 95f58105548409881253a2b8b114fc22304a8983522247bf767ab9f3e616cba9
project_plan | project_plan | 1337 | 3284 |  | GTS - ECCN - Create |  |  | Mon 6/8/26 | Tue 6/9/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 3284 | 3429c98eb6eb3884fdf154ce1997ad6b9eed621ad64283af558f9ec0a12c3dfe
project_plan | project_plan | 1338 | 3285 |  | Load Descartes XML File |  | James Van Riper | Mon 6/8/26 | Mon 6/8/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 3285 | e8a462b2efe27f13c0a94fae1658cb3c8f43609700b349f8e59f0255558bc7fd
project_plan | project_plan | 1339 | 3286 |  | Post Load Validation |  | James Van Riper | Tue 6/9/26 | Tue 6/9/26 | Mon 4/13/26 | 0% | Future Task | 3282 | Yes | No | 3286 | 9c063b73979fe1af74c07bf62dd21755759bc49d13df1183bed1f9dba715a43f
project_plan | project_plan | 1340 | 3287 |  | GTS - ECCN - Assign |  |  | Mon 6/15/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3287 | 1ee46d71abca1020cebedaa1b84f12dace461483d1aebd057139406132881ca4
project_plan | project_plan | 1341 | 3288 |  | Load Descartes XML File |  | James Van Riper | Mon 6/15/26 | Mon 6/15/26 | Thu 4/16/26 | 0% | Future Task | 3277 | Yes | No | 3288 | 107a0c4b50f62ed9eb5ba3dd5fd07dcf0e324aadf205258066fba14095af2b17
project_plan | project_plan | 1342 | 3289 |  | Post Load Validation |  | James Van Riper | Mon 6/15/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task | 3288 | Yes | No | 3289 | 6a01708e41fbf6557ca1ba30f6b18045dbe94c7ce43cc777afc3d2dbaaefdbac
project_plan | project_plan | 1343 | 3290 |  | GTS - HTS - Create |  |  | Mon 6/8/26 | Mon 6/8/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 3290 | 1ce52224800964eb9215b0e71ddeeb8c6bb30776575fd2a9e7171b755fbdf025
project_plan | project_plan | 1344 | 3291 |  | Load Descartes XML File |  | James Van Riper | Mon 6/8/26 | Mon 6/8/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 3291 | d53e623e7c8fe5016b3f32d04227c9c157e73ae61993ce0b9240874410afa0b7
project_plan | project_plan | 1345 | 3292 |  | Post Load Validation |  | James Van Riper | Mon 6/8/26 | Mon 6/8/26 | Mon 4/6/26 | 0% | Future Task | 3291 | Yes | No | 3292 | 688f5f9c1e53da4669a9ba5151dcb70df86dd3029114570149941cd8d3df2776
project_plan | project_plan | 1346 | 3293 |  | GTS - HTS - Assign |  |  | Tue 6/16/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3293 | b8059c4bb16070b467ff7508ec100e9bdbc341175ecdc2e2eb92a5e57aa450e5
project_plan | project_plan | 1347 | 3294 |  | Load Descartes XML File |  | James Van Riper | Tue 6/16/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task | 3289 | Yes | No | 3294 | c960d73e5d8a724d54a9acec6537b11776d2612335955620756cb7afc22af53c
project_plan | project_plan | 1348 | 3295 |  | Post Load Validation |  | James Van Riper | Tue 6/16/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task | 3294 | Yes | No | 3295 | 4986a550f5b2284c83a1cff5b4e870e6ad1c11035521a418f0f4597dfe2a3411
project_plan | project_plan | 1349 | 3296 |  | GTS - License - Create |  |  | Tue 6/16/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3296 | 0ea4fb3f96a73f0f2ccfc98d93e3ac611abb74c21f774f62845e36adb3c75e79
project_plan | project_plan | 1350 | 3297 |  | Load Descartes XML File |  | James Van Riper | Tue 6/16/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task | 32,943,310 | Yes | No | 3297 | cd51ccb19a86d5c01b612c61e63d13608dd53aa6f111136316d6cc5644b7c5db
project_plan | project_plan | 1351 | 3298 |  | Post Load Validation |  | James Van Riper | Tue 6/16/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task | 3297 | Yes | No | 3298 | 0b7ab5b22c7a71201aeb3040207026dd07be4d675dfd6608017ae3873528da2c
project_plan | project_plan | 1352 | 3299 |  | Commodity Code/Tarif |  |  | Tue 6/16/26 | Fri 6/19/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3299 | 485f9f8d2a77d2bb39cf65e4ad87df67be579241811eae434ecf9b7debc6f77a
project_plan | project_plan | 1353 | 3300 |  | Load |  | James Van Riper | Tue 6/16/26 | Thu 6/18/26 | Thu 4/16/26 | 0% | Future Task | 3295 | Yes | No | 3300 | a757779c0330efe230d4dcf695699ba65300bd67f842f0d52143c2841d491119
project_plan | project_plan | 1354 | 3301 |  | Post Load Validation |  | James Van Riper | Thu 6/18/26 | Fri 6/19/26 | Thu 4/16/26 | 0% | Future Task | 3300 | Yes | No | 3301 | 158a25e31b24c87c01ea2550b6197df506fdc0cd3f6a00a9b4fb66f81690300d
project_plan | project_plan | 1355 | 3302 |  | SPL Master File |  |  | Tue 6/16/26 | Tue 6/16/26 | Thu 3/13/25 | 0% | Future Task |  | Yes | No | 3302 | 5999bb30ec55fa729918e6aa742bff7293ae78c30906a168817cd61f827b24b1
project_plan | project_plan | 1356 | 3303 |  | Load |  | James Van Riper | Tue 6/16/26 | Tue 6/16/26 | Thu 3/13/25 | 0% | Future Task | 3294 | Yes | No | 3303 | 6ac9c0242410898aa4081c2f29f5c410cd60e9a5c346963217ce94df852bad5a
project_plan | project_plan | 1357 | 3304 |  | Post Load Validation |  | James Van Riper | Tue 6/16/26 | Tue 6/16/26 | Thu 3/13/25 | 0% | Future Task | 3303 | Yes | No | 3304 | c4ee0c5434f895cd803728a047ef774ff3533422f89fe0239600fa7556ec14b9
project_plan | project_plan | 1358 | 3305 |  | Initialize Embargo situation |  |  | Tue 6/9/26 | Tue 6/9/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 3305 | ea8e71a8c4a40f7d3b840ef76dcd032127ce6fa5d499db3a3f983e48b19e42bd
project_plan | project_plan | 1359 | 3306 |  | Run report /SAPSLL/EMB_CNTRY_INIT |  | James Van Riper | Tue 6/9/26 | Tue 6/9/26 | Mon 4/13/26 | 0% | Future Task | 3286 | Yes | No | 3306 | 3012e8fdb462618427e83a34e6b23d6709c3fc243d912cf66e17fc1d4de36941
project_plan | project_plan | 1360 | 3307 |  | Set Embargo situations |  | James Van Riper | Tue 6/9/26 | Tue 6/9/26 | Mon 4/13/26 | 0% | Future Task | 3306 | Yes | No | 3307 | f90d4978af2afe5ac0c0a162cb6bfdccc38201d76a24f3517ce2cc02bc5ffec8
project_plan | project_plan | 1361 | 3308 |  | Post Load Validation |  | James Van Riper | Tue 6/9/26 | Tue 6/9/26 | Tue 4/14/26 | 0% | Future Task | 3307 | Yes | No | 3308 | 0606e6c2db39c475eacbcfc2024aa819d695c6086f867a92221159939a0aa335
project_plan | project_plan | 1362 | 3309 |  | GTS - SPL (Sanctioned party list) |  |  | Tue 6/16/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 3309 | 96b996c2cbb7f84db69293f332c59862efa9c919d25549099b03a8ce8060118a
project_plan | project_plan | 1363 | 3310 |  | Load Descartes XML File |  | James Van Riper | Tue 6/16/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task | 3295 | Yes | No | 3310 | 7248f94832eb08f4529646e519a8f77b0c60b08197353886cc63e6fbdfe15598
project_plan | project_plan | 1364 | 3311 |  | Post Load Validation |  | James Van Riper | Tue 6/16/26 | Tue 6/16/26 | Thu 4/16/26 | 0% | Future Task | 3310 | Yes | No | 3311 | eb5dc1e148e6e015754d7f8f4ec15b0401e39cf1b4439874f014f86283235c7b
project_plan | project_plan | 1365 | 3312 |  | RTR_CM17_Project Definition / Builder |  |  | Mon 6/8/26 | Tue 6/9/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 3312 | 809f52a7b49c05a86c0472d473954c6501d76b99920923d9f3f95949b0537f7f
project_plan | project_plan | 1366 | 3313 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Mon 6/8/26 | Mon 6/8/26 | Fri 4/10/26 | 0% | Future Task | 3258 | Yes | No | 3313 | 6ba9adc72c2ee191de952ec7023b6af945698f55518849dac7a7ac2448c8e044
project_plan | project_plan | 1367 | 3314 |  | Pre Load Validation |  | Kasey Hughes | Mon 6/8/26 | Mon 6/8/26 | Fri 4/10/26 | 0% | Future Task | 3313 | Yes | No | 3314 | f315978c402569649114f47e20297cdc2202008b7a70be72a8541c2f8edbb531
project_plan | project_plan | 1368 | 3315 |  | Simulate Load |  | Data Migration Team | Mon 6/8/26 | Mon 6/8/26 | Thu 4/16/26 | 0% | Future Task | 3314 | Yes | No | 3315 | 057c1455d26a06246109321199658e6b62e626cd8ff0e23b31a85438d00a77e6
project_plan | project_plan | 1369 | 3316 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 6/8/26 | Mon 6/8/26 | Fri 4/17/26 | 0% | Future Task | 3315 | Yes | No | 3316 | 6dc9e5b208faffbf01d1c1585e4d76a9c8d467f261e7660413aad7e76d23fed8
project_plan | project_plan | 1370 | 3317 |  | Load |  | Data Migration Team | Mon 6/8/26 | Tue 6/9/26 | Fri 4/17/26 | 0% | Future Task | 3316 | Yes | No | 3317 | 227292354227af66a74580199fd2f630d92ae725c8994c10583d0de8970abdcb
project_plan | project_plan | 1371 | 3318 |  | Post Load Validation |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Fri 4/17/26 | 0% | Future Task | 3317 | Yes | No | 3318 | 8e105be48f7ea9429f335ab7b9abcd8130c414150949c5be33206a9c76f03e80
project_plan | project_plan | 1372 | 3319 |  | RTR_CM18_WBS Element |  |  | Mon 6/8/26 | Tue 6/9/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 3319 | b5b2696d1deaa732d2343e02b525d78c2d8dc854e7b88cd41f3cca58fd439ffd
project_plan | project_plan | 1373 | 3320 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Mon 6/8/26 | Mon 6/8/26 | Fri 4/10/26 | 0% | Future Task | 3313 | Yes | No | 3320 | 098d57b7c85e510474e06d55345ec36c3af694165d9b292de2f20f40a6fff26a
project_plan | project_plan | 1374 | 3321 |  | Pre Load Validation |  | Kasey Hughes | Mon 6/8/26 | Mon 6/8/26 | Fri 4/10/26 | 0% | Future Task | 3320 | Yes | No | 3321 | 34d4cbe4167e6cec6f28b3a278001f9e5f6f0a0463e65464cbba5499ea854673
project_plan | project_plan | 1375 | 3322 |  | Simulate Load |  | Data Migration Team | Mon 6/8/26 | Mon 6/8/26 | Thu 4/16/26 | 0% | Future Task | 3321 | Yes | No | 3322 | d6fe2c48724183de5cd66d81765fc181fde3abc9e021d0e084f744026bb89195
project_plan | project_plan | 1376 | 3323 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 6/8/26 | Mon 6/8/26 | Fri 4/17/26 | 0% | Future Task | 3322 | Yes | No | 3323 | 9ed49b1424c25bda5d2988857f315919bc70c34a15573771485926f2e0f99433
project_plan | project_plan | 1377 | 3324 |  | Load |  | Data Migration Team | Mon 6/8/26 | Tue 6/9/26 | Fri 4/17/26 | 0% | Future Task | 3323 | Yes | No | 3324 | a10d2a9e836b5a0ae27b410a1d544d4cb20438782880cd6b37d142f67a126d11
project_plan | project_plan | 1378 | 3325 |  | Post Load Validation |  | Kasey Hughes | Tue 6/9/26 | Tue 6/9/26 | Fri 4/17/26 | 0% | Future Task | 3324 | Yes | No | 3325 | 9f35b608b0cbcab3c4bd38977c2b48b27ef3c045d17edcfc271c0f5844636b71
project_plan | project_plan | 1379 | 2958 |  | ITC3 Master Data Loads Complete |  |  | Fri 6/19/26 | Fri 6/19/26 |  | 0% | Future Task | 2959 | Yes | Yes | 2958 | 162c27fce25b2cf3a868031884a211dfe65503ffad56b19cf51266193efa5400
project_plan | project_plan | 1380 | 3326 |  | Mock Transactional Data |  |  | Fri 6/19/26 | Tue 6/23/26 |  | 0% | Future Task | 2958 | Yes | No | 3326 | c62c7c271ecf682b7a248ffbb6d7bea56a9dd3bd8a110da858f5072e6b1c3a50
project_plan | project_plan | 1381 | 3330 |  | Inventory |  |  | Fri 6/19/26 | Mon 6/22/26 |  | 0% | Future Task | 2947SS | Yes | No | 3330 | 7c255860f43ceaf6569dd77788c5f6641000bd82661f64c1cfff7986d7f71d28
project_plan | project_plan | 1382 | 3331 |  | Open AR |  |  | Mon 6/22/26 | Mon 6/22/26 |  | 0% | Future Task | 3330 | Yes | No | 3331 | acacbbe10ae761504cd0f608170ef45196cd349bb895adc14f27094017dd809d
project_plan | project_plan | 1383 | 3332 |  | Open AP |  |  | Mon 6/22/26 | Tue 6/23/26 |  | 0% | Future Task | 3331 | Yes | No | 3332 | d32e4aff0b53f0096a2add41bb7df2d14f8698f2fc4a9d8f46153f955ff9d169
project_plan | project_plan | 1384 | 3333 |  | Bank and Cash |  |  | Tue 6/23/26 | Tue 6/23/26 |  | 0% | Future Task | 3332 | Yes | No | 3333 | 49d0c9dda32f6223bacccf1cdb672a147bbacebdb4a9da2b54c21b2cbc8e9892
project_plan | project_plan | 1385 | 3334 |  | Open Purchase Orders(Manual) |  |  | Mon 6/22/26 | Tue 6/23/26 |  | 0% | Future Task | 3330 | Yes | No | 3334 | b66acc90812c3aff9d6ed8208b582a51d551f8c172fb94b2f97e0aa4bdc990ba
project_plan | project_plan | 1386 | 3335 |  | Open Sales Orders(Manual) |  |  | Mon 6/22/26 | Tue 6/23/26 |  | 0% | Future Task | 3330 | Yes | No | 3335 | 7b65e3a8bd691054f290387c4592ed1f160942aaf7edf2936065867cd16ee0fa
project_plan | project_plan | 1387 | 3336 |  | Service Orders(Manual) |  |  | Mon 6/22/26 | Mon 6/22/26 |  | 0% | Future Task | 3330 | Yes | No | 3336 | 4ea973c8fe0403e55d8dccb97afb920e737bc235385f89eb3de338812ae85c81
project_plan | project_plan | 1388 | 3337 |  | Open Production Orders(Manual) |  |  | Mon 6/22/26 | Tue 6/23/26 |  | 0% | Future Task | 3330 | Yes | No | 3337 | 5a0de16a889fa5fda235b6686e4ca37bd24a0ea8882efb2b69bd687d7d86ff66
project_plan | project_plan | 1389 | 2421 |  | ITC3 Mock Data Loads Complete |  | Mark George | Tue 6/23/26 | Tue 6/23/26 | Tue 4/21/26 | 0% | Future Task | 3326 | Yes | Yes | 2421 | 3f40e56398594b1d0caf394d2194ae76c099c5c7adb0846893baf65e5860055f
project_plan | project_plan | 1390 | 2422 |  | UAT Data Load Tasks QS4 |  |  | Mon 6/22/26 | Mon 10/12/26 | Tue 4/21/26 | 0% | Future Task | 20,538,843,367 | Yes | No | 2422 | 51bd8f773990f33e4fc0eced6d3db4ea1e62cf8981ce981f3d441f22463b3fc3
project_plan | project_plan | 1391 | 2423 |  | PMO Authorization to Start Data Loads |  | Mark George | Mon 6/22/26 | Mon 6/22/26 | Mon 4/6/26 | 0% | Future Task | 8,843,367 | Yes | No | 2423 | 3cbacff20b51f427c8c30bfa6d88664f1068ee4bea0d4744d53df16d9512bcd2
project_plan | project_plan | 1392 | 2898 |  | Master Data Loads |  |  | Thu 9/24/26 | Thu 10/8/26 |  | 0% | Future Task | 2423 | Yes | No | 2898 | d8f4b692bf4be4c62966cf707224edf27996142759067cd1d0cda9cd9acac204
project_plan | project_plan | 1393 | 2424 |  | RTR_CM02_Profit Center Hierarchy |  |  | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 2424 | 30e2102d24d1e3c106b04319fcb6faee35b27ea175d96a79340c6542c3e9e857
project_plan | project_plan | 1394 | 2425 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 2423 | Yes | No | 2425 | 9499e007a20075f6da916673c7f0537faf0b98ab8a564ff4868a0165a8554e1a
project_plan | project_plan | 1395 | 2426 |  | Load |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 2425 | Yes | No | 2426 | 6e99f18146f5c27f43f968625a3b511407c8ecb66a242d265faa166e57c4b6d3
project_plan | project_plan | 1396 | 2427 |  | Post Load Validation |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 2426 | Yes | No | 2427 | 1066518c07a89858f1cae9aa6499d83d019299f8a36cdd54f681fc353505ce65
project_plan | project_plan | 1397 | 2428 |  | RTR_CM03_Cost Center Hierarchy |  |  | Thu 9/24/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 2428 | 19281670c9ecfaaca89b4d3651ff6bbb34b864c1f8d9b8dde16b12299f0b5e99
project_plan | project_plan | 1398 | 2429 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 2427 | Yes | No | 2429 | 720bcbf034a5d4681e17abfb9760435b73d5cd70c0291676fd4d41d216d46202
project_plan | project_plan | 1399 | 2430 |  | Load |  | Kasey Hughes | Thu 9/24/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2429 | Yes | No | 2430 | e89008cd19e305dd9ff2fca378f86eba76fbe7616e38857b437972395c32ab80
project_plan | project_plan | 1400 | 2431 |  | Post Load Validation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2430 | Yes | No | 2431 | 0342f2ca933a5a2c3672a433284bb70ead3d160336f9178987c87ac5646633f3
project_plan | project_plan | 1401 | 2432 |  | RTR_CM01_GL_Account_Master to CC 1000 |  |  | Fri 9/25/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 2432 | 1351a9cf7b51fa478de539d3230c7a7a61227f308c98e0c78e564d1bd644ea95
project_plan | project_plan | 1402 | 2433 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2431 | Yes | No | 2433 | fafbb12b52eb6c03fe4da26c40b697507110ba359d6639ea748972ba20a098bf
project_plan | project_plan | 1403 | 2434 |  | Pre Load Validation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2433 | Yes | No | 2434 | ccb3f867654a0b80ceac514e8b07a2bc98f94dcce54f87b76dcb9dbb8fb6bab6
project_plan | project_plan | 1404 | 2435 |  | Simulate Load |  | Data Migration Team | Fri 9/25/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 2434 | Yes | No | 2435 | ffe2587d8a88e19e9d30679277b3e287a49a2bf9dfea342a826e9f57929749ef
project_plan | project_plan | 1405 | 2436 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 9/28/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 2435 | Yes | No | 2436 | 93e79a624edc3780fbc18f7327ab7c4db1439d7e0431c79bcb84f3663878b653
project_plan | project_plan | 1406 | 2437 |  | Load |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 2436 | Yes | No | 2437 | c26a913bdd7cae317438fa0e21536a936e9eda0d939f23f5cba35e70aab7452d
project_plan | project_plan | 1407 | 2438 |  | Post Load Validation |  | Kasey Hughes | Tue 9/29/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 2437 | Yes | No | 2438 | 6c6c8106bd1deb62b5d9ec532f7e3971c8d643e8f717468c93406745977c9d56
project_plan | project_plan | 1408 | 2439 |  | Extend GL to all Company Codes |  | Kasey Hughes | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 2438 | Yes | No | 2439 | b1a79b4cb0611a4616b370796181d3143d82f11eaea20f9302149a2e4c1903d1
project_plan | project_plan | 1409 | 2440 |  | Post GL Extention Validation |  |  | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 2439 | Yes | No | 2440 | b1fa4ed747145c9ad2f9267c42f1e5d25ef69bace1b9f5b2f17e4f5c7de5bfe5
project_plan | project_plan | 1410 | 2441 |  | RTR_CM05_Profit_Center |  |  | Thu 9/24/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 2441 | a2d1efe78242a5b675246bd391eb3eaf7df57ef261d4ce811020d0b17ff90b02
project_plan | project_plan | 1411 | 2442 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 2427 | Yes | No | 2442 | ee77b11563b79041e926f3b227b9ee1dcb2e2314d16ee762d1516a32d0b1b469
project_plan | project_plan | 1412 | 2443 |  | Pre Load Validation |  | Kasey Hughes | Thu 9/24/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2442 | Yes | No | 2443 | 9578124417c9553cdef6c9a7e2b05b78fc9ec16cecdb3b9006198a1af3b46cc2
project_plan | project_plan | 1413 | 2444 |  | Simulate Load |  | Data Migration Team | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2443 | Yes | No | 2444 | 1b64b854ddca86f77b6f3f904d7f6bd014a5eeb0658f9f08573ecaabfd3a15e0
project_plan | project_plan | 1414 | 2445 |  | Error and Defect Mitigation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2444 | Yes | No | 2445 | 6517eb9d37c1b07d5878ad48c8ce161896c629c9242a5826f03101a0eaf40ed6
project_plan | project_plan | 1415 | 2446 |  | Load |  | Data Migration Team | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2445 | Yes | No | 2446 | 285c7d935b1ca4d1a194c125bb50a4ac8306a9470f9984ca7eac6f7c86303c82
project_plan | project_plan | 1416 | 2447 |  | Post Load Validation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2446 | Yes | No | 2447 | 09728afeaf9c95d68dabcc7571dbb5430c78692004a78b76850010321f7e8786
project_plan | project_plan | 1417 | 2448 |  | RTR_CM04_Cost_Center |  |  | Fri 9/25/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 2448 | 4d63dc8387d91127f18bb02526f3d9cee79642e01be63e45e52d0c49b2555224
project_plan | project_plan | 1418 | 2449 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Fri 9/25/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 2447 | Yes | No | 2449 | c008a309b462b1ea14ab1244cac5fe6f19b09f4516cb2688aeaf483d34553943
project_plan | project_plan | 1419 | 2450 |  | Pre Load Validation |  | Kasey Hughes | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 2449 | Yes | No | 2450 | 71e5c0bb2ea3e3e399fe4b7fc8d97033bcec44d9d2d254624b09ab677778e581
project_plan | project_plan | 1420 | 2451 |  | Simulate Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 2450 | Yes | No | 2451 | ea029e89fcd09a414468df1b1b6e8f2e4c384ac9bbc55bd7d4fa52bb35c24930
project_plan | project_plan | 1421 | 2452 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 2451 | Yes | No | 2452 | 92b46bdb36ceb2276372cf540ef519bcfa32a86f3169e9c71e1e4ce024e3d085
project_plan | project_plan | 1422 | 2453 |  | Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 2452 | Yes | No | 2453 | 386514903aec11809479ad922f88420ec3854a5f8fe89673b16dcd6fd0078c23
project_plan | project_plan | 1423 | 2454 |  | Post Load Validation |  | Kasey Hughes | Mon 9/28/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 2453 | Yes | No | 2454 | 5645fd2221549c0b51a3c6e55a4eb3feb246237217864f9c177b1c2c0935d56b
project_plan | project_plan | 1424 | 2455 |  | Manual Configuration Activities in QS5 |  |  | Thu 9/24/26 | Tue 10/6/26 | Wed 4/15/26 | 0% | Future Task | 652 | Yes | No | 2455 | 6fe2bc8ceee902be8df31efdff4e3ece46a5f1f1757e5d475d255e8e1a8aa7a1
project_plan | project_plan | 1425 | 2456 |  | Open Client |  | Basis | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 2456 | 2fec48af51b378488be1d26466a780443df7d75ddf36a0b6c16da9014002a3a2
project_plan | project_plan | 1426 | 2457 |  | Service Enterprise Setup |  | Keith Riley | Wed 9/30/26 | Tue 10/6/26 | Wed 4/15/26 | 0% | Future Task | 242,424,282,432 | Yes | No | 2457 | e556806409b2d6b1fe015ebb8060bcbc33c184f9f4a5fe0fcd9bcdd576377522
project_plan | project_plan | 1427 | 2458 |  | Close Client |  | Basis | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 2458 | 554df1fdcf4eae8ca89ef046e8083f2aa8d9a7927b534de42af912a107768193
project_plan | project_plan | 1428 | 2459 |  | Intercompany Business Partner Setup |  | Functional Leads | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 242,424,282,440 | Yes | No | 2459 | 44d5df57500d222fa137c46aae660d674f66809cfbd83050924be84599e275a3
project_plan | project_plan | 1429 | 2460 |  | RTR_CM09_Activity_Type |  |  | Tue 9/29/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 2460 | 883595c8a6cd455c8b42f19ac042e1e082f9379e515e7dcf21a9a2fc3758a401
project_plan | project_plan | 1430 | 2461 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 9/29/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 2438 | Yes | No | 2461 | 78f309f92100c7054f4acb0b3712c396367a6f5aa640aa37ed1cc430a1df24c7
project_plan | project_plan | 1431 | 2462 |  | Pre Load Validation |  | Kasey Hughes | Tue 9/29/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 2461 | Yes | No | 2462 | e75f867c2429e7457c5fe8ebd604a2cc61d10ed545c262c3cfe204f180d679f0
project_plan | project_plan | 1432 | 2463 |  | Simulate Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 2462 | Yes | No | 2463 | 22cd61ec428b54907d02f6af837577079b9bb2a6eb724c0e0ea57e13753b222d
project_plan | project_plan | 1433 | 2464 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 2463 | Yes | No | 2464 | d1ae02c239a5b0a104c14e4418f7e6ef1410f1b8fa2150cbde64409e48cb41da
project_plan | project_plan | 1434 | 2465 |  | Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 2464 | Yes | No | 2465 | 30262f1cbbe9662e16ef0775b489e6733ce6515c6fb167e7cbb0cb38d8f4163d
project_plan | project_plan | 1435 | 2466 |  | Post Load Validation |  | Kasey Hughes | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 2465 | Yes | No | 2466 | d735581bf3a31b0c6fafd8d7cde8ea5490c721d04cdf5ff16db32e246a49efb6
project_plan | project_plan | 1436 | 2467 |  | RTR_CM12_Activity Rates |  |  | Fri 9/25/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task |  | Yes | No | 2467 | 5bfac0263864bed27f7e096564c0016a6330f1c7533bb3e1b6b226665c663d3b
project_plan | project_plan | 1437 | 2468 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2431 | Yes | No | 2468 | a8c06c61c537e0ce3a8516fc89c824b57dcafc241321f8cfe9b6b76f16500317
project_plan | project_plan | 1438 | 2469 |  | Pre Load Validation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2468 | Yes | No | 2469 | d3effb18268f7a63b1346ba98a3ef6e923ccc0ee8cf9b314f599bf00230bde6c
project_plan | project_plan | 1439 | 2470 |  | Simulate Load |  | Data Migration Team | Fri 9/25/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 2469 | Yes | No | 2470 | 07e7bfbbb0abaa6ff892bc1804755bf1a5cc3b6ef0bbc3021399ed340b3beb0a
project_plan | project_plan | 1440 | 2471 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 2470 | Yes | No | 2471 | 14593960d207f195dc2e54c8daa77f01195b2fc9ca89bbfcacf9012c1d7da74b
project_plan | project_plan | 1441 | 2472 |  | Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 2471 | Yes | No | 2472 | 5bf097522359c588de39a2217621a3f3e6400e57c32cb0bb87aed23840320358
project_plan | project_plan | 1442 | 2473 |  | Post Load Validation |  | Kasey Hughes | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 2472 | Yes | No | 2473 | 1f4029463128e8dc37c5da91a4d27cda2f6d140a7046894a793eea889d623fd8
project_plan | project_plan | 1443 | 2474 |  | RTR_CM06_Bank_master |  |  | Thu 9/24/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 2474 | e8c27a2322b94f64f2a91deb8e5e622cfc2af6e9c423a0910f2037b72714e5bb
project_plan | project_plan | 1444 | 2475 |  | Load File Staged and Posted "Ready" |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 2438 | Yes | No | 2475 | 89e10b6f1fc6ddf963dce217ac6ac951d37d18ac9c177b7a3870c027776f924a
project_plan | project_plan | 1445 | 2476 |  | Pre Load Validation |  | Kasey Hughes | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 2475 | Yes | No | 2476 | d8fe7f7179eedce43f38f6d0f0746e9ffa905ff93eea1bb61c8c1488e520d0fb
project_plan | project_plan | 1446 | 2477 |  | Simulate Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 2477 | 4897e00c12b2bc751fbecba6a000c6910abdbbec6f84af94da6d1a1ffacf9d89
project_plan | project_plan | 1447 | 2478 |  | Error and Defect Mitigation |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Thu 4/9/26 | 0% | Future Task | 2477 | Yes | No | 2478 | 09a9bcf95bd99b4e28b3fe10d0bea4d22c68337f779b1567072cf7a3945bdb61
project_plan | project_plan | 1448 | 2479 |  | Load |  | Data Migration Team | Thu 9/24/26 | Fri 9/25/26 | Thu 4/9/26 | 0% | Future Task | 2478 | Yes | No | 2479 | d74c3a053f421240ca019a804c906849b1a1692a6d8c56bbe776b01c512e8a41
project_plan | project_plan | 1449 | 2480 |  | Post Load Validation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Thu 4/9/26 | 0% | Future Task | 2479 | Yes | No | 2480 | c918eb23841551674184cae4762c0e1f40937f85c38461fc93d0d41b748ad0b9
project_plan | project_plan | 1450 | 2481 |  | RTR_CM08_Exchange_Rates |  |  | Fri 9/25/26 | Mon 9/28/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 2481 | bacc07bc6c522a5983f240e8f2852a69cbd03e932488173c18dc06912e5a01e5
project_plan | project_plan | 1451 | 2482 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Thu 4/9/26 | 0% | Future Task | 2479 | Yes | No | 2482 | bf1963d5d4b7607a610eed1ba694289081b3343769a14b81221584c30bc51e4d
project_plan | project_plan | 1452 | 2483 |  | Pre Load Validation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Fri 4/10/26 | 0% | Future Task | 2482 | Yes | No | 2483 | d8fa6ea8d4bbcb46ca3aec496cf334f951d352c9c9cc97b31c5216895d929e42
project_plan | project_plan | 1453 | 2484 |  | Simulate Load |  | Data Migration Team | Fri 9/25/26 | Fri 9/25/26 | Fri 4/10/26 | 0% | Future Task | 2483 | Yes | No | 2484 | fc67b06759beec818f456eaa7168a6b15d07b822c2785d8ce76113588e794739
project_plan | project_plan | 1454 | 2485 |  | Error and Defect Mitigation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Fri 4/10/26 | 0% | Future Task | 2484 | Yes | No | 2485 | 5f9491c89b73eb719227b2ee0f6636663cbeea173661a5c43d3754b8b2e5caf3
project_plan | project_plan | 1455 | 2486 |  | Load |  | Data Migration Team | Fri 9/25/26 | Fri 9/25/26 | Fri 4/10/26 | 0% | Future Task | 2485 | Yes | No | 2486 | e8af5b5890f2fe1f0787ff5026f219ee0d3dba24097bbde6a70ae143fc13b22d
project_plan | project_plan | 1456 | 2487 |  | Post Load Validation |  | Kasey Hughes | Fri 9/25/26 | Mon 9/28/26 | Fri 4/10/26 | 0% | Future Task | 2486 | Yes | No | 2487 | fa760a7f2a042a3095f4f07298f8f4aca766cf30818b72843236dd6a2306f219
project_plan | project_plan | 1457 | 2488 |  | RTR_CM14_Cost Element_Group |  | Kasey Hughes | Tue 9/29/26 | Mon 10/5/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 2488 | 954cb5a9ae2599d790d1bcbd9a70153a01934a45ce663644782e32f22154e974
project_plan | project_plan | 1458 | 2489 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Tue 9/29/26 | Tue 9/29/26 | Tue 4/14/26 | 0% | Future Task | 2438 | Yes | No | 2489 | a26a1edd27583cbfd91aedbbc893c9c7e800d47fa9dd7dcc02e87661f58252a2
project_plan | project_plan | 1459 | 2490 |  | Load |  | Kasey Hughes | Tue 9/29/26 | Mon 10/5/26 | Wed 4/15/26 | 0% | Future Task | 2489 | Yes | No | 2490 | b7375e4da4b1007fba6fd2e4b55dece031a0dc9f4cbfc096afaec62cb8870390
project_plan | project_plan | 1460 | 2491 |  | Post Load Validation |  | Kasey Hughes | Mon 10/5/26 | Mon 10/5/26 | Wed 4/15/26 | 0% | Future Task | 2490 | Yes | No | 2491 | 634f8857636ca8b1ac9f9a010d8dd2d1aae8ac981e80a71327ec95bc3b61b6a8
project_plan | project_plan | 1461 | 2492 |  | OTC_CM19_Customer_Master - Bill-To |  |  | Thu 9/24/26 | Thu 9/24/26 | Wed 4/16/25 | 0% | Future Task |  | Yes | No | 2492 | b986bd45782c1c8f583b4e2f8bbaf42126baee8956e88974b8da152ab4ab4f9a
project_plan | project_plan | 1462 | 2493 |  | OTC_CM19_Customer_Master - Ship-To |  |  | Tue 9/29/26 | Wed 9/30/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 2493 | 82d40d924c3445f876c82c50b43e41f8ade8676f97447de7bde90decaae3c9f5
project_plan | project_plan | 1463 | 2494 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Tue 9/29/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 2438 | Yes | No | 2494 | 0f9ea12c4898ecdd02a7d4e5c9025b7de1e0e383332c13247987a4ec3b58120f
project_plan | project_plan | 1464 | 2495 |  | Pre Load Validation |  | Ric Haraida | Tue 9/29/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 2494 | Yes | No | 2495 | de6bf8e61b4ec569e185e0dbee6d676032b3d559dea86ddffc13e7a8728d8e8c
project_plan | project_plan | 1465 | 2496 |  | Open client for BP number range update |  | Basis | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 2495 | Yes | No | 2496 | 1ebd123fda6d72f3f57df3b78ca0dd91cf165e2107799760b7bea75e30a80ea0
project_plan | project_plan | 1466 | 2497 |  | Update number range BP02 from Internal to External |  | Ric Haraida | Tue 9/29/26 | Tue 9/29/26 | Fri 4/10/26 | 0% | Future Task | 2496 | Yes | No | 2497 | e1be443ad4f98ee910b2c3e7545b065f9f1cfe95b167b09fea99e2414d91f06d
project_plan | project_plan | 1467 | 2498 |  | Close Client |  | Basis | Tue 9/29/26 | Tue 9/29/26 | Mon 4/13/26 | 0% | Future Task | 2497 | Yes | No | 2498 | 41fae2388c4e47909222aaf784a407085a98410b4726d2550d5e318a3111f4e7
project_plan | project_plan | 1468 | 2499 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 2495 | Yes | No | 2499 | 1a404dbc12c2ff06e777e57bea9ab0705a38388e9df3aa05cf6f22a23da84db1
project_plan | project_plan | 1469 | 2500 |  | Error and Defect Mitigation |  | Ric Haraida | Tue 9/29/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 2499 | Yes | No | 2500 | 6ea986adb2e75c9e3eed6f6f34afd95b177a4d160638de49503f1bf25c3723c1
project_plan | project_plan | 1470 | 2501 |  | Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 2500 | Yes | No | 2501 | 0ae85685080c95602ed403c89643742cc3b7defcf7f0747fca9959fd2217d9f8
project_plan | project_plan | 1471 | 2502 |  | Post Load Validation |  | Ric Haraida | Wed 9/30/26 | Wed 9/30/26 | Fri 4/10/26 | 0% | Future Task | 2501 | Yes | No | 2502 | 3f81ca5f0e9a3030e4aab1512174cf5f01d9d0e80ba960eb410348fd70498ca1
project_plan | project_plan | 1472 | 2503 |  | OTC_CM19_Customer_Master - Sold-To |  |  | Tue 9/29/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 2503 | 2ba623a6b6dd9731319075c986e8f123e95dfe0664dfababc2dd11f3a71e6f3b
project_plan | project_plan | 1473 | 2504 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 2495 | Yes | No | 2504 | 1577fdc64ffac809d24fea6422e9ffb650a20b7c73362abf7b964ddfe605f74d
project_plan | project_plan | 1474 | 2505 |  | Pre Load Validation |  | Ric Haraida | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 2504 | Yes | No | 2505 | 1e34686cc21716e31c92f5181f9c5b35f83f1fce5aae1061f831e3e9a9cfbec5
project_plan | project_plan | 1475 | 2506 |  | Simulate Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 24,402,499 | Yes | No | 2506 | ec94f4364fcd3b592ac5dd877cf7e33246fef283fe2f692f5bbed7e61d890926
project_plan | project_plan | 1476 | 2507 |  | Error and Defect Mitigation |  | Ric Haraida | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 2506 | Yes | No | 2507 | 74e46ff86e19551ade9c56a3af5c422b7421cd581d07dda4faae67aac0d8dfe9
project_plan | project_plan | 1477 | 2508 |  | Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Fri 4/10/26 | 0% | Future Task | 2507 | Yes | No | 2508 | f85515a2ee920aa0c390d2c4bbc9c8e3993ee215b578c14ecc73c0dbbd1335d2
project_plan | project_plan | 1478 | 2509 |  | Post Load Validation |  | Ric Haraida | Wed 9/30/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 2508 | Yes | No | 2509 | b1c036bdb4df29890846944b51f09b67c107b8d3d1d751d9eccb1b33e2a41feb
project_plan | project_plan | 1479 | 2510 |  | Open client for BP number range update |  | Basis | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 2499 | Yes | No | 2510 | 277f2e678524f4893bc6e3fa7dbe49e9a52b6d619e1defb34c4bc86ee3cd9106
project_plan | project_plan | 1480 | 2511 |  | Update number range BP02 from Internal to External |  | Ric Haraida | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 2510 | Yes | No | 2511 | 006abe44c3d6779513b9da86c68bda82876f25fc6aa300a5e062f32dbdd6cb44
project_plan | project_plan | 1481 | 2512 |  | Close Client |  | Basis | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 2511 | Yes | No | 2512 | 21af24d443bd49d5934d437b53bc312450fb19ea44afb70bcbcf1083a75f424e
project_plan | project_plan | 1482 | 2513 |  | PTP_CM27_Vendor Master as Customer - FLCU01 |  |  | Wed 9/30/26 | Wed 10/7/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 2513 | 1ec1577585cd55e3f9d18eeba9798da210c4306db3f54f4ab7317aa595095f6a
project_plan | project_plan | 1483 | 2514 |  | Extract File |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Fri 4/10/26 | 0% | Future Task | 2508 | Yes | No | 2514 | 11a4f17836f46940e108d909a6b4689d9191e89ff6c50718b22f2c799727e305
project_plan | project_plan | 1484 | 2515 |  | Pre Load Validation |  | Nevin Varkey | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 2514 | Yes | No | 2515 | 7901e7df8d38bb05ca82c2486e456aa48ae1d30b1688a7c849444ef0157d165c
project_plan | project_plan | 1485 | 2516 |  | Simulate Load |  | Data Migration Team | Thu 10/1/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task | 24,802,515 | Yes | No | 2516 | 016689430d59701b1e8c8d4b1602efe5c9beba8dd78ecce56e7adddf40b07555
project_plan | project_plan | 1486 | 2517 |  | Error and Defect Mitigation |  | Nevin Varkey | Fri 10/2/26 | Tue 10/6/26 | Tue 4/14/26 | 0% | Future Task | 2516 | Yes | No | 2517 | 645f375a1d02a53843ba946c359f8dfb206fe36906025a062768619381ff3ca1
project_plan | project_plan | 1487 | 2518 |  | Load |  | Data Migration Team | Tue 10/6/26 | Wed 10/7/26 | Tue 4/14/26 | 0% | Future Task | 2517 | Yes | No | 2518 | a1f50a20e7bda21ef6304b151a0004237fd85ba35e828c94df8a2501f17b473a
project_plan | project_plan | 1488 | 2519 |  | Post Load Validation |  | Nevin Varkey | Wed 10/7/26 | Wed 10/7/26 | Tue 4/14/26 | 0% | Future Task | 2518 | Yes | No | 2519 | 1bd7de0a74ac062a163e45711b82e4c78ceb5100ca54f435e9b31fd478a87481
project_plan | project_plan | 1489 | 2520 |  | OTC_CM23_Customer_Hierarchy |  |  | Wed 9/30/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 2520 | d4f63887965c44f29edc84f864fc6ea26591ee41375ff0463f1200e0d6e979c9
project_plan | project_plan | 1490 | 2521 |  | Manual File Staged and Posted "Ready" |  | Ric Haraida | Wed 9/30/26 | Wed 9/30/26 | Fri 4/10/26 | 0% | Future Task | 2508 | Yes | No | 2521 | 0d602c5368d6512c82945c14066e0c5b6c0e732a5a19334da467cad9988a4926
project_plan | project_plan | 1491 | 2522 |  | Load |  | Ric Haraida | Wed 9/30/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 2521 | Yes | No | 2522 | 6efec5d4fa288770a647239e898159c7b9331c8d835e9f3b4a60ec02cd88a425
project_plan | project_plan | 1492 | 2523 |  | Post Load Validation |  | Ric Haraida | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 2522 | Yes | No | 2523 | 1b95baac9dcc12615613a4f58fda7e6c9942c63193187647241eaa2eadd6867e
project_plan | project_plan | 1493 | 2524 |  | PTP_CM27_Vendor Master - Z001 - External Sales Rep |  |  | Wed 9/30/26 | Tue 10/6/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 2524 | 09275027ec74957859af1ade06504417bf1ac7d496bdbb9f3d19de8c5cae9b97
project_plan | project_plan | 1494 | 2525 |  | Extract File |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Fri 4/10/26 | 0% | Future Task | 2508 | Yes | No | 2525 | 161ab17eb98d6d3f6b7a91aeaf4de9bbc864a29b800d554d05f1f29871ce7cab
project_plan | project_plan | 1495 | 2526 |  | Pre Load Validation |  | Nevin Varkey | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 2525 | Yes | No | 2526 | 99d9449b2bf1d61d66ca32d4441c963644b49f61cfd037cbc97e6b9d2b4d6336
project_plan | project_plan | 1496 | 2527 |  | Simulate Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 24,802,526 | Yes | No | 2527 | 8038f1aa237a8b771b963fcc95ec5e0f8c3f03e2bf056ce5b3f5fe6dc1d02dea
project_plan | project_plan | 1497 | 2528 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 2527 | Yes | No | 2528 | d611f732279a2ed220c5844800d5f7eb55942218f594ebd82bd5f3cdb14814c0
project_plan | project_plan | 1498 | 2529 |  | Load |  | Data Migration Team | Thu 10/1/26 | Mon 10/5/26 | Mon 4/13/26 | 0% | Future Task | 2528 | Yes | No | 2529 | a632bdf792fc4e2c72e4e9c2b8fc520dc010e201a092dcc098e400292cbe2c63
project_plan | project_plan | 1499 | 2530 |  | Post Load Validation |  | Nevin Varkey | Tue 10/6/26 | Tue 10/6/26 | Mon 4/13/26 | 0% | Future Task | 2529 | Yes | No | 2530 | cddc96dff1f7f7bc6ec005182ac539b9ba5d59c84a88a41958259a2b72151eb7
project_plan | project_plan | 1500 | 2531 |  | RTR_CM10_Credit_Management_Role |  |  | Wed 9/30/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 2531 | 36aa2986a94a6b18d2c09244f4cd418fc3ce8df8d3c61118ae408be8624b92dc
project_plan | project_plan | 1501 | 2532 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Wed 9/30/26 | Wed 9/30/26 | Fri 4/10/26 | 0% | Future Task | 2508 | Yes | No | 2532 | 4f316ff39facd67aec9f36ea9cc4a9012bd277958e9d5790a7ab40005ec95ef2
project_plan | project_plan | 1502 | 2533 |  | Pre Load Validation |  | Kasey Hughes | Wed 9/30/26 | Wed 9/30/26 | Fri 4/10/26 | 0% | Future Task | 2532 | Yes | No | 2533 | 211c34d0b19d9d77e2574ca11149709ba6721caf90f72c9c015e0f02287c6f99
project_plan | project_plan | 1503 | 2534 |  | Simulate Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 2533 | Yes | No | 2534 | d1db875f083910ab486d121b46013a238ceb8b2c30651b276d611f0b0add2318
project_plan | project_plan | 1504 | 2535 |  | Error and Defect Mitigation |  | Kasey Hughes | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 2534 | Yes | No | 2535 | 74416511c6276db901a71062cdc43c7bdce156e5452a25f4b219afaa2715574e
project_plan | project_plan | 1505 | 2536 |  | Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 2535 | Yes | No | 2536 | 215ec58154e20569c3d7e3dbfb1aa1ee5432c510701084b0cf1f1c15b2245810
project_plan | project_plan | 1506 | 2537 |  | Post Load Validation |  | Kasey Hughes | Thu 10/1/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task | 2536 | Yes | No | 2537 | e639c016f2a5a11274acdf7efb092aadca2741d700cd3b9b7cc316f9dff5dab4
project_plan | project_plan | 1507 | 2538 |  | PTP_CM27_Vendor Master |  |  | Thu 9/24/26 | Fri 10/2/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 2538 | 10426d8ebe3e165f8dd199c174d03fee6bbbcbfcda8279d655382d104f723ffc
project_plan | project_plan | 1508 | 2539 |  | Extract File |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 2525 | Yes | No | 2539 | 69a1749d0e59a3629f33e051d08655f6041da4d68dd8699b4b33032d8f6cc2c2
project_plan | project_plan | 1509 | 2540 |  | Pre Load Validation |  | Nevin Varkey | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 2539 | Yes | No | 2540 | 9bc4bc4c9e1955ccda16c252d312d813059b53220af58aa35c5bcf7b067acc57
project_plan | project_plan | 1510 | 2541 |  | Simulate Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Tue 4/14/26 | 0% | Future Task | 2540 | Yes | No | 2541 | a86787a351ade9a706db981ebfdf4d1b71a111cab9c6ee1ac966da184c9270eb
project_plan | project_plan | 1511 | 2542 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 10/1/26 | Fri 10/2/26 | Tue 4/14/26 | 0% | Future Task | 2541 | Yes | No | 2542 | 5865af6418ef600d887f53e3afe610eca72d27464395c13950727ddba879d1b6
project_plan | project_plan | 1512 | 2543 |  | Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 2543 | 7f8da8f4da9875ecdba14eea076346eb3d97a39e0a56325aa16c1669fd4e2b23
project_plan | project_plan | 1513 | 2544 |  | Post Load Validation |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Wed 4/15/26 | 0% | Future Task | 2543 | Yes | No | 2544 | 8331b3b514ab918a7d296e7f245b0f164ffe96d9b17673f447d3f6e3f76d3437
project_plan | project_plan | 1514 | 2545 |  | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR |  |  | Thu 9/24/26 | Thu 9/24/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 2545 | 592939c4a0765f25a3cf52f638b39c663627a586894ac5b34fcbce624e063bd9
project_plan | project_plan | 1515 | 2546 |  | Extract File(Will Extract from LFA1) |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 2546 | 8964850754ef6cd08a073af4daf2ca454548542242db72f1626e93657d2bc776
project_plan | project_plan | 1516 | 2547 |  | Pre Load Validation |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 2546 | Yes | No | 2547 | 3fed67b391da308e89330d75567089d8eac8cfbe40830bc41404d03b64e9f252
project_plan | project_plan | 1517 | 2548 |  | Simulate Load/ Not Needed |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 2547 | Yes | No | 2548 | 3fd6ccae72a9a9ac1772353b5273c439219718b746a1ad68dbd1c184128b0955
project_plan | project_plan | 1518 | 2549 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 2548 | Yes | No | 2549 | ac145a63780f3563c85d223c61deb92dcdbd9e29ed8558cf02a6d93673f3b61e
project_plan | project_plan | 1519 | 2550 |  | Load |  | Nevin Varkkey | Thu 9/24/26 | Thu 9/24/26 | Wed 4/15/26 | 0% | Future Task | 2548 | Yes | No | 2550 | 643625548c1e79f0da5316544bf37a56f0d3e4ebb7282b1c58a86c7c0b826522
project_plan | project_plan | 1520 | 2551 |  | Post Load Validation |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Wed 4/15/26 | 0% | Future Task | 2550 | Yes | No | 2551 | 60ea39ee1e5b02be249c630faae6762f690336f1ba1f84b011f3e4cb915b8f3c
project_plan | project_plan | 1521 | 2552 |  | RTR_****_Credit Hierarchy |  |  | Thu 10/1/26 | Mon 10/5/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 2552 | c0ae1f3985723ab26b39ba6bf555f6155811113775ffa5a7c17c33b63a45f1d6
project_plan | project_plan | 1522 | 2553 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 2535 | Yes | No | 2553 | 137d14a2ee14d8a5fedf567e204fe6bb810ec6418418af405a3d97a30eb66f9a
project_plan | project_plan | 1523 | 2554 |  | Load |  | Kasey Hughes | Fri 10/2/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task | 2537 | Yes | No | 2554 | 474e63224bb5cbdc15cb9aac0cfb966ec586f497cffadef3abb74997caed7ec6
project_plan | project_plan | 1524 | 2555 |  | Post Load Validation |  | Kasey Hughes | Fri 10/2/26 | Mon 10/5/26 | Mon 4/13/26 | 0% | Future Task | 2554 | Yes | No | 2555 | c55f8b0573b8152d39a62031e134d17078f785f892e01479476e3645762dde5d
project_plan | project_plan | 1525 | 2556 |  | PTP_CM27_BP_Intercompany Supplier |  |  | Thu 9/24/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 2556 | ac948ec8cc720d9eab606bcffd9cf5507e1483aa1c5d05dcdea3cec010c3a534
project_plan | project_plan | 1526 | 2557 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 2544 | Yes | No | 2557 | 0b620d2a648b1f13bde4daadf8f675d061362f677967917d2054d02fde2ea558
project_plan | project_plan | 1527 | 2558 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 2557 | Yes | No | 2558 | ba195bc60e7a9bc1b93b162b1c45f09ecf3184a044e94dfdeb62c7a693112496
project_plan | project_plan | 1528 | 2559 |  | Simulate Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 2558 | Yes | No | 2559 | 32cb3811b4a02e2420e5fcbcb734897781ef9289c09947027b7c2b646943a776
project_plan | project_plan | 1529 | 2560 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 2559 | Yes | No | 2560 | dca3176f9eeb9d652e651f19c684b82b74b3b6f3b660f235d21f6d2f3c21b59e
project_plan | project_plan | 1530 | 2561 |  | Load |  | Data Migration Team | Thu 9/24/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 2560 | Yes | No | 2561 | 45e59fcdc6e1f2e6d5e0ec445341d4161efadd6d456e5ec37f9309cf17776dfd
project_plan | project_plan | 1531 | 2562 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Fri 9/25/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 2561 | Yes | No | 2562 | d4be1277819360d673fca5f00131fdfa7b31d3ac1643e6513dfcfe2f21b64cc2
project_plan | project_plan | 1532 | 2563 |  | PTP_CM27_BP_Intercompany Customer |  |  | Thu 9/24/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 2563 | eeef91486cc1b46f19cc0f1953435e817c00ce499282ba0e03ca491a0950c773
project_plan | project_plan | 1533 | 2564 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 2564 | b54e10b0bcfd5c0c342125eddc3f8a7d91a6d108405eeb2136620f71a8bbe2fc
project_plan | project_plan | 1534 | 2565 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 2565 | 911397282e20cf5212b9d2730117ce29cf4c7f23447a0fff7dfd06d8e9257c36
project_plan | project_plan | 1535 | 2566 |  | Simulate Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 2565 | Yes | No | 2566 | e9430303e27dadca29c87a745d03b87de5340cfb45f31425be00eba681505320
project_plan | project_plan | 1536 | 2567 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 2566 | Yes | No | 2567 | f23950481820f95dd637c41d3dada40115c365d2030a3e9f40e868bb04bf6ce9
project_plan | project_plan | 1537 | 2568 |  | Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Tue 4/14/26 | 0% | Future Task | 2567 | Yes | No | 2568 | 191cd1a78b7e48360a786a813131e8c21d1f8dc14e173e83c581c1fa5b7dca51
project_plan | project_plan | 1538 | 2569 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 2568 | Yes | No | 2569 | 97c3a777fc3b573155b2b70b7be1c61a00a1ad1adb233861367e91167ccbdca2
project_plan | project_plan | 1539 | 2570 |  | PTP_CM26_Material_Master - All Types |  |  | Thu 9/24/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 2570 | 70064e0c9eddfd608e68a1d52a22e08deff3110bea744bfe25bc4f8abaded1da
project_plan | project_plan | 1540 | 2571 |  | Extract File |  | Data Migration Team | Thu 9/24/26 | Fri 9/25/26 | Mon 4/13/26 | 0% | Future Task | 2546 | Yes | No | 2571 | c659a3e9909afa629e9deab6929823cc2e31418834e0bd76fb0ee52de4c91d3a
project_plan | project_plan | 1541 | 2572 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 2544 | Yes | No | 2572 | 8d79173bca6a631adbf3e02656a9ed8c5410f9ad81277121b0b312b0218eb40e
project_plan | project_plan | 1542 | 2573 |  | Simulate Load |  | Data Migration Team | Fri 9/25/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 2572 | Yes | No | 2573 | a2179c1b5458b2572c654f62efb962a1b62e7e4460d5a5b7dd1de08609a4f2ae
project_plan | project_plan | 1543 | 2574 |  | Error and Defect Mitigation |  | Nevin Varkey | Fri 9/25/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 2573 | Yes | No | 2574 | 888c6e75e5a1e9613c9fa96503e9edeb0bbece70b8b4df218556f0d53ec5d0ba
project_plan | project_plan | 1544 | 2575 |  | Load |  | Data Migration Team | Fri 9/25/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task | 2574 | Yes | No | 2575 | 69155f92d47ed7929e93b2575598170ee62cfff33cc4a50a49f465887508baab
project_plan | project_plan | 1545 | 2576 |  | Post Load Validation |  | Nevin Varkey | Mon 9/28/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task | 2575 | Yes | No | 2576 | cf2587a85ffdf23b79c61246c5f30fcd27830c4b7cf87f0b1f90304018a44d5c
project_plan | project_plan | 1546 | 2577 |  | PTP_CM26_Material_Master - SERV - Service Materials |  |  | Fri 9/25/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 2577 | a60b3e937cb6ee04f31897095f0f02dba49be5be26a41de62dba986135011f5e
project_plan | project_plan | 1547 | 2578 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2447 | Yes | No | 2578 | 68b6cddf91d1a388b167141579c147ef2296de89a8bc529eb2b93fc4e0532996
project_plan | project_plan | 1548 | 2579 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Mon 9/28/26 | Mon 9/28/26 | Tue 4/14/26 | 0% | Future Task | 2575 | Yes | No | 2579 | 4ffb8893fccbb0d5eb5ff1c54dad0fa1f4f530df26e4399d886eee319615990f
project_plan | project_plan | 1549 | 2580 |  | Simulate Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Tue 4/14/26 | 0% | Future Task | 2579 | Yes | No | 2580 | 857b51711d8ed1b274d8f9943a1545008c1c199e195201c04354846b555362c4
project_plan | project_plan | 1550 | 2581 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Mon 9/28/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task | 2580 | Yes | No | 2581 | da2d360c0995fcc1c472c782c00efddcd54323fe76a7a3f42f27dfeae81421f6
project_plan | project_plan | 1551 | 2582 |  | Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task | 2581 | Yes | No | 2582 | 8b8cebabc830e1ca0b8c145ef7e88046db899436fcf6dbc2f9c5932aa7850495
project_plan | project_plan | 1552 | 2583 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Mon 9/28/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 2582 | Yes | No | 2583 | f063f350ab2c3f850c45d4c68f6ba737395ca7ba6ba2f4adc41cfa6d964900a5
project_plan | project_plan | 1553 | 2584 |  | PTP_CM26_Material_Master - KMAT - Configurable Materials |  |  | Fri 9/25/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 2584 | 82c94fc8024f60be3aa07a34cf01cce0ff95c28936e0264d3787c28cd9bdf5d6
project_plan | project_plan | 1554 | 2585 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2447 | Yes | No | 2585 | e8466763ebdef496f2c97424dc74e083ded73f3484959e90abbaa8efc9e91ff7
project_plan | project_plan | 1555 | 2586 |  | Pre Load Validation |  | Eric Heisler | Mon 9/28/26 | Mon 9/28/26 | Tue 4/14/26 | 0% | Future Task | 2575 | Yes | No | 2586 | 433e495b256753d349bed5bd91590be3d9e6fdd56c10c2f5225dd0240ebe2e4c
project_plan | project_plan | 1556 | 2587 |  | Simulate Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Tue 4/14/26 | 0% | Future Task | 2586 | Yes | No | 2587 | 22872f46a15919597e26f0f513f070aaa769cc650847319661d2d722ab8f160b
project_plan | project_plan | 1557 | 2588 |  | Error and Defect Mitigation |  | Eric Heisler | Mon 9/28/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task | 2587 | Yes | No | 2588 | 78c7d3b2a55b8eef24e9513134150b6d93c2ff2d2084f24b0cd58b09209ebcfb
project_plan | project_plan | 1558 | 2589 |  | Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task | 2588 | Yes | No | 2589 | 154741ac6db9b29af515ceb99a2eef79498e5790193c6330940edd31d5097685
project_plan | project_plan | 1559 | 2590 |  | Post Load Validation |  | Eric Heisler | Mon 9/28/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 2589 | Yes | No | 2590 | cf39ac58c898740fecd05188d82af4d3a8b4a441a140a1a3a42f08b74817f395
project_plan | project_plan | 1560 | 2591 |  | PTP_CM28_Purchase_Info_Records |  |  | Thu 9/24/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2591 | 663314ab5d1c49a22e2eaca125c2a2ede0c6989d66d38b9ccb331e1ab81f74e0
project_plan | project_plan | 1561 | 2592 |  | Extract File |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 25,762,590 | Yes | No | 2592 | 5b9dfac56440727d1fc383a87090d435047d777bb2eca63d30e5ae9c1c5ea3e8
project_plan | project_plan | 1562 | 2593 |  | Pre Load Validation |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2592 | Yes | No | 2593 | 216fc111e7e67d54af6805d116cbb2217e9e6276cb2980a29a1a1bfd81aa7f58
project_plan | project_plan | 1563 | 2594 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2593 | Yes | No | 2594 | aa1b01d710825e5e987fe2c742ba3fcd245b05b7c10dccdfdeb2888d04e554b4
project_plan | project_plan | 1564 | 2595 |  | Error and Defect Mitigation |  | Nevin Varkey | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 2594 | Yes | No | 2595 | ab5a281db3b90a96a16d872bf14443376bd47ddad957d23e41a1f1911991ba14
project_plan | project_plan | 1565 | 2596 |  | Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Wed 4/15/26 | 0% | Future Task | 2544 | Yes | No | 2596 | 1bacb81cce7f8836fe5fc08fd6af09d5c0c1a729dc3d465a186517f4e0587ccf
project_plan | project_plan | 1566 | 2597 |  | Post Load Validation |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Wed 4/15/26 | 0% | Future Task | 2596 | Yes | No | 2597 | 8416efb4c56b72f7a3693543569fac8ca98e3fa13076a5bf3a33833adfedd71e
project_plan | project_plan | 1567 | 2598 |  | PTP_CM28_Purchase_Info_Record External Processing |  |  | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2598 | 630916f9c28f995f67eff2f24c33fe40c5491420a96bc8e1cf362382aab9325c
project_plan | project_plan | 1568 | 2599 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 25,762,590 | Yes | No | 2599 | d44d39f6ac4e43b69d5f9b9b708b85303c94b0f8c6283569667dbbb3f12bd2f5
project_plan | project_plan | 1569 | 2600 |  | Pre Load Validation |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 2599 | Yes | No | 2600 | 5535e21b4fa4c512bedb3e5a15ff60b050f0801a77da9f745bae040c09a0b3f0
project_plan | project_plan | 1570 | 2601 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2600 | Yes | No | 2601 | b5a988e06d1afd62f77d2de5ae938e5dc8f767e4d9124eddac4d2d4c8976306c
project_plan | project_plan | 1571 | 2602 |  | Error and Defect Mitigation |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2601 | Yes | No | 2602 | 5d31c2469e204026d496bd96648d251f3b7d6a08fbce53534c03df2ec8d08a81
project_plan | project_plan | 1572 | 2603 |  | Load |  | Data Migration Team | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 2602 | Yes | No | 2603 | 9446018bdceb994f2ba8e20e5aec61fa706ae6b173fcb51d4a3569cd501481b9
project_plan | project_plan | 1573 | 2604 |  | Post Load Validation |  | Nevin Varkey | Wed 9/30/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 2603 | Yes | No | 2604 | 5801a39fc6fd637d80e7d45d4b0421ea340c590f7c958236d13a763bc3eda946
project_plan | project_plan | 1574 | 2605 |  | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment |  |  | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2605 | 08e8a530acbd261cff08e3b6d89ff52b2cc4c2334ce80cd293dec10844961c7a
project_plan | project_plan | 1575 | 2606 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 25,762,590 | Yes | No | 2606 | 629cdfbbba6c782521936519592554654793448158b1a9e021b160bd735c359c
project_plan | project_plan | 1576 | 2607 |  | Pre Load Validation |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 2606 | Yes | No | 2607 | eaa4d8b7b7c0b7dc1e972083fde7a51279f3619ff7c6c05bd71a836158c08eb7
project_plan | project_plan | 1577 | 2608 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2607 | Yes | No | 2608 | 6d2f32d5ce98e25aec0a7a4ed57107071a39427b710cbbac1dac4ce1251a54e8
project_plan | project_plan | 1578 | 2609 |  | Error and Defect Mitigation |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2608 | Yes | No | 2609 | 4f2fda1ce02ff43236b7d12189c1c2996c34efa090536605d60b22a0968809ab
project_plan | project_plan | 1579 | 2610 |  | Load |  | Data Migration Team | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 2609 | Yes | No | 2610 | 984481912553440319eda58ba1ae943201a6dbc60b55be98eea04bb81db8a792
project_plan | project_plan | 1580 | 2611 |  | Post Load Validation |  | Nevin Varkey | Wed 9/30/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 2610 | Yes | No | 2611 | ab74eacd00c21e4c23e079adb44e27fff0f284f2b6287d8262af025f5205b92f
project_plan | project_plan | 1581 | 2612 |  | PTM_CM31_BOM Conversion |  |  | Tue 9/29/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 2612 | 0c0e0c56f533826c2307d585b3564dbc793964b492888e9311793fb66c0449bf
project_plan | project_plan | 1582 | 2613 |  | Extract File |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2592 | Yes | No | 2613 | 19ab9d6977b4826c00b84175ff022fc043acb84fe7f45c5d222518e5dc4d83b1
project_plan | project_plan | 1583 | 2614 |  | Pre Load Validation |  | Brad Meseck | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2613 | Yes | No | 2614 | 70b9168d6b8aada880de43973847a66ba381d9639bee271eee5a337d8ccad674
project_plan | project_plan | 1584 | 2615 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 2614 | Yes | No | 2615 | a0ecc2c108031af343d54f529a16562242e6d91c164767265b40f9d57b3dae6e
project_plan | project_plan | 1585 | 2616 |  | Error and Defect Mitigation |  | Brad Meseck | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 2615 | Yes | No | 2616 | a7786efd889f3e8d33a9e3fe67209ee32de9dce555dd2a6143af492c9cc5d14a
project_plan | project_plan | 1586 | 2617 |  | Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 2616 | Yes | No | 2617 | e77af73f19706d9608d87cb6f3d2ec7d0b1d882f5966ed8e76ad4a7d9027cbeb
project_plan | project_plan | 1587 | 2618 |  | Post Load Validation |  | Brad Meseck | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 2617 | Yes | No | 2618 | e8f68105e5534b383131906cf9b7232af9af07002e0ad7d6350ec74ad6a0f3b8
project_plan | project_plan | 1588 | 2619 |  | PTM_CM40_Work Center Conversion |  |  | Tue 9/29/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 2619 | 0cad40ac3298b5ebe5d31ba3c226c4e9dd6c8585cefcf14835a92a46fa6c3adb
project_plan | project_plan | 1589 | 2620 |  | Extract File |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2613 | Yes | No | 2620 | 788f9bc8463d6ecb5c21c4623d412cb63731bb8ae15ed6aeb47792d61d833881
project_plan | project_plan | 1590 | 2621 |  | Pre Load Validation |  | Brad Meseck | Thu 10/1/26 | Fri 10/2/26 | Fri 4/17/26 | 0% | Future Task | 2618 | Yes | No | 2621 | 8aec98e9b35f4aa5ba1478244fb46be59a4e123321122751cd99eac0f329a72e
project_plan | project_plan | 1591 | 2622 |  | Simulate Load |  | Data Migration Team | Fri 10/2/26 | Fri 10/2/26 | Fri 4/17/26 | 0% | Future Task | 2621 | Yes | No | 2622 | 52874616c5fb10d3369d2148a49872ba91f633b688a6ecdb03b06d527ae26eb6
project_plan | project_plan | 1592 | 2623 |  | Error and Defect Mitigation |  | Brad Meseck | Fri 10/2/26 | Fri 10/2/26 | Fri 4/17/26 | 0% | Future Task | 2622 | Yes | No | 2623 | 299d1b6b48b73dcaebce5bd4ddb49165d84dd1c619106faf18aeb7f3f59b4fbf
project_plan | project_plan | 1593 | 2624 |  | Load |  | Data Migration Team | Fri 10/2/26 | Fri 10/2/26 | Fri 4/17/26 | 0% | Future Task | 2623 | Yes | No | 2624 | 007d4f9aa3295f16d9909fda9cf445037859c35d54ffbd43a8a5fb20df4c7d3a
project_plan | project_plan | 1594 | 2625 |  | Post Load Validation |  | Brad Meseck | Fri 10/2/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task | 2624 | Yes | No | 2625 | e51168b1fa9d946aa8482e6154074011fb7fca196a35b8fe20be84676e2dd680
project_plan | project_plan | 1595 | 2626 |  | PTM_CM38_Routing Conversion |  |  | Tue 9/29/26 | Mon 10/5/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 2626 | 9730a5563d6242c4548ae12262f51fece518ddec403d8bc6024452f7c8fffbf5
project_plan | project_plan | 1596 | 2627 |  | Extract File |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2620 | Yes | No | 2627 | 4d793fb23f39267574543037de263b0431b6d23a95004692a951b3292752b7b1
project_plan | project_plan | 1597 | 2628 |  | Pre Load Validation |  | Brad Meseck | Fri 10/2/26 | Mon 10/5/26 | Mon 4/20/26 | 0% | Future Task | 2625 | Yes | No | 2628 | e311c019d8fe5dd4c3d3ef615bacefc920ca7365dcc071e50e612fa9e41d49ca
project_plan | project_plan | 1598 | 2629 |  | Simulate Load |  | Data Migration Team | Mon 10/5/26 | Mon 10/5/26 | Mon 4/20/26 | 0% | Future Task | 2628 | Yes | No | 2629 | a6403c3c62188ad2e0117da8117d107a1add9a7ef260b91dda2cff9403919504
project_plan | project_plan | 1599 | 2630 |  | Error and Defect Mitigation |  | Brad Meseck | Mon 10/5/26 | Mon 10/5/26 | Mon 4/20/26 | 0% | Future Task | 2629SS | Yes | No | 2630 | 6527d4e16c2b7d843e6a08ce6371d860c7112f9bf34efd1966d56ab7e1b29bd9
project_plan | project_plan | 1600 | 2631 |  | Load |  | Data Migration Team | Mon 10/5/26 | Mon 10/5/26 | Mon 4/20/26 | 0% | Future Task | 2630 | Yes | No | 2631 | ddf6a89db4b6103c0c86005055c92b1d4b319c6b17d731d71269909aa7ab918d
project_plan | project_plan | 1601 | 2632 |  | Post Load Validation |  | Brad Meseck | Mon 10/5/26 | Mon 10/5/26 | Tue 4/21/26 | 0% | Future Task | 2631 | Yes | No | 2632 | 8401e1e44ec2d50012aabca6692e41fd473a20291760f5bb410309961359cb4f
project_plan | project_plan | 1602 | 2633 |  | PTM_CM36_Production Version Conversion |  |  | Tue 9/29/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 2633 | c3f141a74b82ccd578f17e7875e1f4e3c323033be7636160e57c5dfc6b37d8e6
project_plan | project_plan | 1603 | 2634 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2627 | Yes | No | 2634 | d8ef26e9afc9d1fcb9d4bd1e132cb1a6cd26775f5d08c6a97f97c67882ff2eb1
project_plan | project_plan | 1604 | 2635 |  | Pre Load Validation |  | Brad Meseck | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2634 | Yes | No | 2635 | 2cd919098d7e4d987395b0ae3556ff61a31e85058b4da84983594be103c83f75
project_plan | project_plan | 1605 | 2636 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 2635 | Yes | No | 2636 | 779b65ec2d5ae87991b8898c302a30b4be6f319d7bf30389999aa90a01cf94fb
project_plan | project_plan | 1606 | 2637 |  | Error and Defect Mitigation |  | Brad Meseck | Wed 9/30/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 2636 | Yes | No | 2637 | 8472896437c49972d68f6c8200808e607ac8182deee96c53c41709367b037ced
project_plan | project_plan | 1607 | 2638 |  | Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task | 2637 | Yes | No | 2638 | 528d0ffdf1b67d823350e9f0eaa960da8511a197abbd325e6c464eae16ee3fff
project_plan | project_plan | 1608 | 2639 |  | Post Load Validation |  | Brad Meseck | Wed 9/30/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task | 2638 | Yes | No | 2639 | 349da62ef53d11e894eb48dfaefa784903f3f504a2cdb204149949699b9cfdb1
project_plan | project_plan | 1609 | 2640 |  | PTM_CM35_Inspection Plan |  |  | Wed 9/30/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 2640 | 439fdbd2f9641b6d2f254181abae66ce7c1e3667b0481f6122e20ac6e976ed31
project_plan | project_plan | 1610 | 2641 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Wed 9/30/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task | 2639 | Yes | No | 2641 | dd88680bb574a1eb87f3461af71a5ec34ec3d722572f19529424c2f2c49fbf0c
project_plan | project_plan | 1611 | 2642 |  | Pre Load Validation |  | Brad Meseck | Wed 9/30/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 2641 | Yes | No | 2642 | 474d4f515693f1902d72fa6b3971c513401abc9b1ec795ce1c820e12fe726891
project_plan | project_plan | 1612 | 2643 |  | Simulate Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 2642 | Yes | No | 2643 | afca30480403f5c46af26050ae36bd3c9865d166a215d4b64d2a2e7d6bd42c23
project_plan | project_plan | 1613 | 2644 |  | Error and Defect Mitigation |  | Brad Meseck | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 2643 | Yes | No | 2644 | ead261e4367b2502bf62edf2cf2336170c230de7c8df30a367b396bcece6e0fb
project_plan | project_plan | 1614 | 2645 |  | Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Mon 4/20/26 | 0% | Future Task | 2644 | Yes | No | 2645 | c940cc326d892624ed66b0e4d92b94604954b81bbb12f468192b90e54a85544f
project_plan | project_plan | 1615 | 2646 |  | Post Load Validation |  | Brad Meseck | Thu 10/1/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task | 2645 | Yes | No | 2646 | 2b71b46442a8a4ed220c3f9ecc545763aede2ef85bd5d7a1d5fa611ba7bd75c4
project_plan | project_plan | 1616 | 2647 |  | PTM_CM48_Equipment_Master_Serial Numbers |  |  | Wed 9/30/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 2647 | fe3d198bdaa8d3f36724b6dae696399506779a11d029ce1469f72d260b059e4c
project_plan | project_plan | 1617 | 2648 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Wed 9/30/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 2641 | Yes | No | 2648 | 1db0a33a3d39be51f46bc4b5f2748f768d862a94a65d2ad246b3b66ff2ae5bd6
project_plan | project_plan | 1618 | 2649 |  | Pre Load Validation |  | Brad Meseck | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 2648 | Yes | No | 2649 | 2b2bfa790343ff3f0342599ce672ad5cd8d0ed0e15e286fe77ae5efed8b9d887
project_plan | project_plan | 1619 | 2650 |  | Simulate Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 2649 | Yes | No | 2650 | 1b5f62b2a0076d42de54d0bdb730ab67ca638c21259d87a3eabc15dbd3a89d26
project_plan | project_plan | 1620 | 2651 |  | Error and Defect Mitigation |  | Brad Meseck | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 2650 | Yes | No | 2651 | 396c9864397f1676a84575d6c3b8badc25c1d3723dfff072715d8f4607a3ec60
project_plan | project_plan | 1621 | 2652 |  | Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Mon 4/20/26 | 0% | Future Task | 2651 | Yes | No | 2652 | 030d6f15e88033845ff9ddadcd5380c1b2b84e30402d12e574739ea9e1460f90
project_plan | project_plan | 1622 | 2653 |  | Post Load Validation |  | Brad Meseck | Thu 10/1/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task | 2652 | Yes | No | 2653 | db710400ab4c699bae81bd7d7017071e4f8de9617a564b06a500964c73aae488
project_plan | project_plan | 1623 | 2654 |  | PTM_CM48_Equipment_Master_Service |  |  | Thu 9/24/26 | Fri 10/2/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 2654 | a6cd74fd0411d8f72d8130ddd4bf0f483bcee57ac9fd4e078ebeda5884b63179
project_plan | project_plan | 1624 | 2655 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Fri 10/2/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task | 2653 | Yes | No | 2655 | f60bf43bd0d099e6d6a243d33e872d996bcd58379cea120e8932951db67228a4
project_plan | project_plan | 1625 | 2656 |  | Pre Load Validation |  | Brad Meseck | Fri 10/2/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task | 2655 | Yes | No | 2656 | d9a9cc167d2e443f68366c9d0174f32537f398cafcdb2da00d7594a84185d79f
project_plan | project_plan | 1626 | 2657 |  | Simulate Load |  | Data Migration Team | Fri 10/2/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task | 2656 | Yes | No | 2657 | 9f8053d2094633b868c919597f7d2c76f3bf4f937ba7f1949f62d8d32f0f85ac
project_plan | project_plan | 1627 | 2658 |  | Error and Defect Mitigation |  | Brad Meseck | Fri 10/2/26 | Fri 10/2/26 | Tue 4/21/26 | 0% | Future Task | 2657 | Yes | No | 2658 | 22f263a45fb7dfa6e297ef1b4db9ae5cd2d7c96f90f1269db95d1e477eb1daa0
project_plan | project_plan | 1628 | 2659 |  | Load |  | Data Migration Team | Fri 10/2/26 | Fri 10/2/26 | Tue 4/21/26 | 0% | Future Task | 2658 | Yes | No | 2659 | 4322e89e106bf4dd4ed626ff96b0eb35048f8aa66b558892f12810ce23307738
project_plan | project_plan | 1629 | 2660 |  | Post Load Validation |  | Brad Meseck | Thu 9/24/26 | Thu 9/24/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 2660 | 9d9d4c93bdf373ebebc218587f2e21e54d5cc8c753fbb94d3a050a6a53da0fdd
project_plan | project_plan | 1630 | 2661 |  | VC_Object Dependencies |  |  | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 2661 | 431bce6e002c224414ce7e619ca6b6856f1a02efa2811d870b216f8e20f8d689
project_plan | project_plan | 1631 | 2662 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 2423 | Yes | No | 2662 | ca6224867a96f3a689e3a1746eb161a549a18a6e7f1f5d86b2d0edbdfe466621
project_plan | project_plan | 1632 | 2663 |  | Post Load Validation |  | Eric Heisler | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 2662 | Yes | No | 2663 | e019d6bcf6bd771703c29f46c388a84255d89f79b7fc425d22f9610d8892f86f
project_plan | project_plan | 1633 | 2664 |  | VC_Characteristics |  |  | Thu 9/24/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 2664 | aa600d77d9235434f2b4701c19ccc3f41ef1dbe4e62114c960048233606afd27
project_plan | project_plan | 1634 | 2665 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 2663 | Yes | No | 2665 | 58c034641417dd8e1277e4fbf0757c943379ae3ebe0e671373d381044fd029ce
project_plan | project_plan | 1635 | 2666 |  | Post Load Validation |  | Eric Heisler | Thu 9/24/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2665 | Yes | No | 2666 | d50025c8e3834c5984211caf80b8d54043f45154e424a75ed817c06521f87447
project_plan | project_plan | 1636 | 2667 |  | VC_Classes |  |  | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 2667 | 5e9ec92ce363057bf9c34b54ef35e6180c181c3904b0ecaf47ba6fbcf4b142bd
project_plan | project_plan | 1637 | 2668 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2666 | Yes | No | 2668 | 151b304a3e860c4338da7544e1dd4422ec214b137776e8d90b4a49df4eec36e8
project_plan | project_plan | 1638 | 2669 |  | Post Load Validation |  | Eric Heisler | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 2668 | Yes | No | 2669 | 8d1af2b4d02a254e9d88c2a75574614c218d62fe9b72c7201fa31bfa757db3be
project_plan | project_plan | 1639 | 2670 |  | VC_Classification (Class Type 200) |  |  | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2670 | 031be439c37df850965097e99417c98a2890012253c45f6d3e6831c66b38f816
project_plan | project_plan | 1640 | 2671 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2590 | Yes | No | 2671 | ee2db4b7445da97bc5ed55b1442794857e2d71a6a6ea5b4279731a96ab9949ee
project_plan | project_plan | 1641 | 2672 |  | Post Load Validation |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2671 | Yes | No | 2672 | 5e82034473483c5e4fa2a9cee5d35f74df54f46dccf5f48f7902810441964d84
project_plan | project_plan | 1642 | 2673 |  | VC_Dependency Nets |  |  | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2673 | 7e3075d42c9b9aebecbbd7dcbbfcd35ec197bb870217224973cb5b401a148efe
project_plan | project_plan | 1643 | 2674 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 25,842,669 | Yes | No | 2674 | 077c48733fd58d4782bf776cbff792e6296e39e0174b55941bf6e65162e4fd92
project_plan | project_plan | 1644 | 2675 |  | Post Load Validation |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2674 | Yes | No | 2675 | 728b360042333d576059b7707c9a62e81eb2ba88e94c217e92b4228e9dd11d17
project_plan | project_plan | 1645 | 2676 |  | VC_Configuration Profiles |  |  | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2676 | 5b0e7d3eef216a5eba02b9456b9f2ab927ccf868d579eafae4f8e0d7db33fc3f
project_plan | project_plan | 1646 | 2677 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2584 | Yes | No | 2677 | 6f92e3c50ce6a7dc3c4a2a2cafac9647eff5cd2a2d20fea8f58f9fc568eac32c
project_plan | project_plan | 1647 | 2678 |  | Post Load Validation |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2677 | Yes | No | 2678 | 03cb73e7e631803cb581cb258937f60c8d36273e38f60c3cd24e9f1424c8352b
project_plan | project_plan | 1648 | 2679 |  | VC_Variant Tables |  |  | Tue 9/29/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 2679 | 3de795ad598e77a18f70ddb3f7ab7160281c58045bb0e9443f52739c7848f049
project_plan | project_plan | 1649 | 2680 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 2678 | Yes | No | 2680 | 398ce6e65b5c8665317e975660e9cded4c3a79c2da134e4db06c6e8fe84c5860
project_plan | project_plan | 1650 | 2681 |  | Post Load Validation |  | Eric Heisler | Wed 9/30/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task | 2680 | Yes | No | 2681 | abf2b45a7e6bb88b24685e92c6a07c672394e5f052b5751b084d24caa4017087
project_plan | project_plan | 1651 | 2682 |  | VC_Variant Tables Content |  |  | Wed 9/30/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 2682 | dec798bd0b607a863dd76056ee2d3bfa203835ce84f2df58984be29c6f3ec1e7
project_plan | project_plan | 1652 | 2683 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Wed 9/30/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task | 2681 | Yes | No | 2683 | 7c28ad85062c9b509bba3495881f036d77fc2ab24e4111a71cb8d322e44793fb
project_plan | project_plan | 1653 | 2684 |  | Post Load Validation |  | Eric Heisler | Wed 9/30/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 2683 | Yes | No | 2684 | 6f8c646aff4e525e7d92cb4ea27d61fb3b793d9ef106fa76bf641a154a3116a8
project_plan | project_plan | 1654 | 2685 |  | VC_Characteristic Groups |  |  | Tue 9/29/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 2685 | 86d0a7431d87fa45f0178623285c7d5667dfe7aa507cd7fbbbdcc42f0306d3cd
project_plan | project_plan | 1655 | 2686 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 9/29/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 2678 | Yes | No | 2686 | e11fb689fbd82dc89eb0a7e1c4d01737d1c358a081ec553a79db20c89e00d5fd
project_plan | project_plan | 1656 | 2687 |  | Post Load Validation |  | Eric Heisler | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 2686 | Yes | No | 2687 | 8f9a97f3fcdeba53a9d50657f4734221714d6d5c96a6bba434340f2718847095
project_plan | project_plan | 1657 | 2688 |  | PTM_CM52_Super_BOM |  |  | Tue 9/29/26 | Mon 10/5/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2688 | 232eba5c265b87f354aff7cf2cd44df4e90a8f7c5c58caedc86d33e825f4edb0
project_plan | project_plan | 1658 | 2689 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 2590 | Yes | No | 2689 | ecffe41c1e734e7630f4cda38f9f5ade69bf354fb53de155df06bd787fdbf546
project_plan | project_plan | 1659 | 2690 |  | Pre Load Validation |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 2689 | Yes | No | 2690 | a3125ee43093bc24bffe82d3a457d0f05c59248e309dc84d3078bd459845cd53
project_plan | project_plan | 1660 | 2691 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 2690 | Yes | No | 2691 | 6e72a7f430d98f66dae078108f19c7edba2b8e0294847aa74cc82d9393d27cb4
project_plan | project_plan | 1661 | 2692 |  | Error and Defect Mitigation |  | Eric Heisler | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 2691 | Yes | No | 2692 | 95f03fb00a0ffaacf3cf1df781ae39e2409dab940f951f9be76796df48ae7c93
project_plan | project_plan | 1662 | 2693 |  | Load |  | Data Migration Team | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 2692 | Yes | No | 2693 | 12cbf75f8ef65f668cdc87fb1b8cfcc6733fd579c7cb9f3ff0ae53bbe8de831a
project_plan | project_plan | 1663 | 2694 |  | Post Load Validation |  | Eric Heisler | Mon 10/5/26 | Mon 10/5/26 | Thu 4/16/26 | 0% | Future Task | 2693 | Yes | No | 2694 | 3c3eaff5050e2964eccd0dfb533947020f6b80dacaae722164e915f340a4df0a
project_plan | project_plan | 1664 | 2695 |  | PTM_CM53_Super_Routing |  |  | Mon 10/5/26 | Wed 10/7/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 2695 | d6dcc4158161daf62d4a856042dce954ca0a88b4a94fa0d8b4907eaf588be4d7
project_plan | project_plan | 1665 | 2696 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Mon 10/5/26 | Mon 10/5/26 | Thu 4/16/26 | 0% | Future Task | 2694 | Yes | No | 2696 | 83b8f21f13368b1ae5c7a707f9394f86f9effa07047a8a79c4e88d3f5183c25b
project_plan | project_plan | 1666 | 2697 |  | Pre Load Validation |  | Eric Heisler | Mon 10/5/26 | Mon 10/5/26 | Fri 4/17/26 | 0% | Future Task | 2696 | Yes | No | 2697 | 19973d1190e532dabf5f28024e2a328a5e2b1d513d6818c249058a6308a72945
project_plan | project_plan | 1667 | 2698 |  | Simulate Load |  | Data Migration Team | Mon 10/5/26 | Tue 10/6/26 | Fri 4/17/26 | 0% | Future Task | 2697 | Yes | No | 2698 | 3b45653a2f3d7b3ed8c35143a3e76e303ece96659a2ab188775c156b6129e320
project_plan | project_plan | 1668 | 2699 |  | Error and Defect Mitigation |  | Eric Heisler | Tue 10/6/26 | Tue 10/6/26 | Fri 4/17/26 | 0% | Future Task | 2698 | Yes | No | 2699 | 07cf42ec7ebe6549501a85f832d2b11037a97a07b23b0024fa86b820bf4cae17
project_plan | project_plan | 1669 | 2700 |  | Load |  | Data Migration Team | Tue 10/6/26 | Wed 10/7/26 | Fri 4/17/26 | 0% | Future Task | 2699 | Yes | No | 2700 | b7d46f5d5d3de2614dc840a3d6084e76f1c955abeab39939877fb970df294655
project_plan | project_plan | 1670 | 2701 |  | Post Load Validation |  | Eric Heisler | Wed 10/7/26 | Wed 10/7/26 | Mon 4/20/26 | 0% | Future Task | 2700 | Yes | No | 2701 | f0cd32669eb7df819bf1d5c581342d2a2940ae2466746d26f971e79f866c844d
project_plan | project_plan | 1671 | 2702 |  | VC_VK30 Pricing Variant |  |  | Wed 10/7/26 | Wed 10/7/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 2702 | fc077122d95d7c1bcd086f1fd240a25400eefc5ec4bbef170e372b9be3eb2275
project_plan | project_plan | 1672 | 2703 |  | Manual File Staged and Posted "Ready" |  | Eric Heisler | Wed 10/7/26 | Wed 10/7/26 | Fri 4/17/26 | 0% | Future Task | 2700 | Yes | No | 2703 | 91e22f1334537b579a957a57133a984016f83fa2a451ffe76c013f31b9edf9d8
project_plan | project_plan | 1673 | 2704 |  | Load |  | Eric Heisler | Wed 10/7/26 | Wed 10/7/26 | Fri 4/17/26 | 0% | Future Task | 2703 | Yes | No | 2704 | 6e5de62fcabe46de03d1e0ab0b8b1385e74895f5afcd1f7b0989cf558cd55cf0
project_plan | project_plan | 1674 | 2705 |  | Post Load Validation |  | Eric Heisler | Wed 10/7/26 | Wed 10/7/26 | Mon 4/20/26 | 0% | Future Task | 2704 | Yes | No | 2705 | dea7571bc7210448334ec130311f469f4083d201380a66c66757eb0e6cb3e1cc
project_plan | project_plan | 1675 | 2706 |  | OTC_CM22_Pricing_Condition |  |  | Wed 10/7/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 2706 | 31c18fe17d3a19d47befbe7b143460217b06da888f7c521ec8e4b8f0df962201
project_plan | project_plan | 1676 | 2707 |  | Manual File Staged and Posted "Ready" |  | Ric Haraida | Wed 10/7/26 | Wed 10/7/26 | Mon 4/20/26 | 0% | Future Task | 2705 | Yes | No | 2707 | 2ef85ba0af0b95aaaa9211f62143939749a37f85c4d4f4862373130a9c3e486f
project_plan | project_plan | 1677 | 2708 |  | Load |  | Ric Haraida | Wed 10/7/26 | Thu 10/8/26 | Mon 4/20/26 | 0% | Future Task | 2707 | Yes | No | 2708 | bb8fbfc7c3490a2e4b1119338b32f3534e7e15bc35bc69ad7661a55b9d922eab
project_plan | project_plan | 1678 | 2709 |  | Post Load Validation |  | Ric Haraida,Kim Kolesar | Thu 10/8/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task | 2708 | Yes | No | 2709 | 26ea836937fb1604c879a8e3720266ed479422dfe454b8bb54f02254dbb3ba00
project_plan | project_plan | 1679 | 2710 |  | OTC_CM21_CMIR |  |  | Thu 10/8/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 2710 | 87da8d1a39a9fc835f8d27a188775ea9d1e5871addfd22fccd22071a354fafc3
project_plan | project_plan | 1680 | 2711 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Thu 10/8/26 | Thu 10/8/26 | Mon 4/20/26 | 0% | Future Task | 27,082,719 | Yes | No | 2711 | 19ac3a5ae3f19ba7ed663118d2d731a9b23b12f5791b5094675efe1a558ff079
project_plan | project_plan | 1681 | 2712 |  | Pre Load Validation |  | Ric Haraida | Thu 10/8/26 | Thu 10/8/26 | Mon 4/20/26 | 0% | Future Task | 2711 | Yes | No | 2712 | d54ef5f60240ebdcba7b7e6ca13006b84ce14983b3bfbec14e025549eee6f491
project_plan | project_plan | 1682 | 2713 |  | Simulate Load |  | Data Migration Team | Thu 10/8/26 | Thu 10/8/26 | Mon 4/20/26 | 0% | Future Task | 2712 | Yes | Yes | 2713 | ace4f894d73c6dabf4019502edc281c268a6ae3f00bb845b4b708cd67d3c1417
project_plan | project_plan | 1683 | 2714 |  | Error and Defect Mitigation |  | Ric Haraida | Thu 10/8/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task | 2713 | Yes | Yes | 2714 | d111cb85a1b504ac85436e0df335fd0473f3cd54f4d600e1fe9d92cf37e756ac
project_plan | project_plan | 1684 | 2715 |  | Load |  | Data Migration Team | Thu 10/8/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task | 2714 | Yes | Yes | 2715 | 63876a088d22a5f1b8516b70df7c10b6d459136a38dde57b36a524f4206bb2c2
project_plan | project_plan | 1685 | 2716 |  | Post Load Validation |  | Ric Haraida | Thu 10/8/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task | 2715 | Yes | No | 2716 | 5056c951471ce4d26f8fa0da9a1288bd85f68dc1580d7b9307050da1fc527db8
project_plan | project_plan | 1686 | 2717 |  | PTP_CM29_Source_List |  |  | Fri 9/25/26 | Mon 10/5/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 2717 | 244b63cc9f35f5d959f98eb9fa72ade21dca7bbd8b35fb4704637fa887d1e30c
project_plan | project_plan | 1687 | 2718 |  | Manual File Staged and Posted "Ready" |  | Nevin Varkey | Fri 9/25/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 25,612,568 | Yes | No | 2718 | 7dfdd47a1697cd5fe923477c1993f5d08310064fd166b608af24edb2344a70ee
project_plan | project_plan | 1688 | 2719 |  | Load |  | Nevin Varkey | Fri 10/2/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task | 2537 | Yes | No | 2719 | e3b2d5f0016ebf0b405dbaa4aad603555b350bcef91e0af04b7e489b2d0331d6
project_plan | project_plan | 1689 | 2720 |  | Post Load Validation |  | Nevin Varkey | Fri 10/2/26 | Mon 10/5/26 | Mon 4/13/26 | 0% | Future Task | 2719 | Yes | No | 2720 | 6fe2e7a1ed88a92766079ff868cc41fcc3934b8c4aca1f8f0345fd78e1852a13
project_plan | project_plan | 1690 | 2721 |  | RTR_CM11_Asset_Master |  |  | Thu 9/24/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 2721 | 89c04b93865f784c28271512fb01b27ae57a8adedd3876ba365177ebbbfcbf00
project_plan | project_plan | 1691 | 2722 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 2722 | 753445dd6e5638c170a254911e7efd96090d408dbc24920bbbee91639316d313
project_plan | project_plan | 1692 | 2723 |  | Pre Load Validation |  | Kasey Hughes,Femi Oguntala | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 2722 | Yes | No | 2723 | 07fd3f0837e2ecdaf2d86a557bed72b9c3113fd6955cb91aa648d213453021c7
project_plan | project_plan | 1693 | 2724 |  | Simulate Load |  | Data Migration Team | Thu 9/24/26 | Wed 9/30/26 | Fri 4/10/26 | 0% | Future Task | 2723 | Yes | No | 2724 | 1ba1d03dccf48494072e89993afe8f604448e37c613324d776453d7e5b3e8920
project_plan | project_plan | 1694 | 2725 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 9/30/26 | Fri 10/2/26 | Fri 4/10/26 | 0% | Future Task | 2724 | Yes | No | 2725 | cc2bf44f09ad9acaf90eb3b93d24d085e98684ad98f7c16d896ef2f4d6ed3027
project_plan | project_plan | 1695 | 2726 |  | Load |  | Data Migration Team | Fri 10/2/26 | Fri 10/2/26 | Fri 4/10/26 | 0% | Future Task | 2725 | Yes | No | 2726 | 79ef805008e3c539a3b47fd7f4c44be1c5720b45ce6f1ed39d1e997bf611b01e
project_plan | project_plan | 1696 | 2727 |  | Post Load Validation |  | Kasey Hughes | Fri 10/2/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task | 2726 | Yes | No | 2727 | 441c73bac24e22a0f1648605dbb298f59428f2da0bb9b1cfb92751e27579745f
project_plan | project_plan | 1697 | 2728 |  | PTM_CM50_Material Class |  |  | Tue 9/29/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2728 | 9ac88cb3488fc614bc8d31ee5482d14f98aeae1f0c5b4271d5b1a3a7b20ad824
project_plan | project_plan | 1698 | 2729 |  | Manual File Staged and Posted "Ready" |  | Sam | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2634 | Yes | No | 2729 | a8c24d0cab529aa1c7e33089449596d6f0b36f8a63e4ce96182e94b9981f2225
project_plan | project_plan | 1699 | 2730 |  | Load |  | Brad Meseck | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2729 | Yes | No | 2730 | 6100945178214ae2191832981e335ea19a001b15fb563b916f99f652a8c56a01
project_plan | project_plan | 1700 | 2731 |  | Post Load Validation |  | Brad | Tue 9/29/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 2730 | Yes | No | 2731 | 87ad0a352839d4fbc12155bf566da1c75853bc429350ee16e5a1f044649b7d6b
project_plan | project_plan | 1701 | 2732 |  | PTM_CM55_Class assignment to materials |  |  | Tue 9/29/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 2732 | 1896b947d4ac7951790b363bcc0065ab0c99125d67fab5d285440ad92af095aa
project_plan | project_plan | 1702 | 2733 |  | Load File Staged and Posted "Ready" |  | Sam | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 2729 | Yes | No | 2733 | 2478f76c437a375fe03ecd7ee10a0e303ac0494d11d7078c0675ed1cb0b6d963
project_plan | project_plan | 1703 | 2734 |  | Pre Load Validation |  | Brad Meseck | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 2733 | Yes | No | 2734 | a686abac44b1a8266f300f7b087f298712775ef312debab6fba5ae64d7421aab
project_plan | project_plan | 1704 | 2735 |  | Simulate Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 2734 | Yes | No | 2735 | 454ce85e22356d07f89c45c20872e431cc90779eea5d38e8d7793197df5fcb04
project_plan | project_plan | 1705 | 2736 |  | Error and Defect Mitigation |  | Brad Meseck | Wed 9/30/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 2735 | Yes | No | 2736 | e15908faffea9012a86a8555d67e56d395e65614befad5c7f22bcc4103052913
project_plan | project_plan | 1706 | 2737 |  | Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task | 2736 | Yes | No | 2737 | 796207eb385d7744e3fc268292c6734ee0509357d55ea388c40e443766842237
project_plan | project_plan | 1707 | 2738 |  | Post Load Validation |  | Brad Meseck | Wed 9/30/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 2737 | Yes | No | 2738 | 4897d475badeca54b09712b4b1065f1f5ce334b3e2dec1b48b9729ea376d187c
project_plan | project_plan | 1708 | 2739 |  | GTS - Material initial load from S4 (Run Interface) |  |  | Tue 9/29/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2739 | b3c509a089c51b8a5d6dd01d6cee782c7b281a625c19db11c91a36cafa2041ad
project_plan | project_plan | 1709 | 2740 |  | Run material interface to GTS |  | James Van Riper | Tue 9/29/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 2608 | Yes | No | 2740 | cc6ed49865bb75b71ad656cf9b4b17c9aa86dd64f44a844289755891e60cf49b
project_plan | project_plan | 1710 | 2741 |  | Post Load Validation |  | James Van Riper | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 2740 | Yes | No | 2741 | de3cd87512b00a1005f687299661e13337fe1ae92a7fbbdc15b7af9cd345382d
project_plan | project_plan | 1711 | 2742 |  | GTS - Customers initial load from S4 (Run Interface) |  |  | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 2742 | 85e79654bb4e68a03790a5daeb8708fbfc5d5129e8b9981d04a74a5823708f35
project_plan | project_plan | 1712 | 2743 |  | Run material interface to GTS |  | James Van Riper | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 2743 | ad9fc906842f2e9bf40c8ab5de2d47a788e11db5cf433e2faab066bf010305ad
project_plan | project_plan | 1713 | 2744 |  | Post Load Validation |  | James Van Riper | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 2743 | Yes | No | 2744 | e791ecd2f10930644e1da62f9c6f2c11659e96d3fa162e51eab2343bdd1ca2bb
project_plan | project_plan | 1714 | 2745 |  | GTS - Vendors initial load from S4 (Run Interface) |  |  | Thu 9/24/26 | Fri 9/25/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 2745 | 7568a07a54e22ab1b83f2879d5d0b0b6224017758db8954e1cf7d6d2598627aa
project_plan | project_plan | 1715 | 2746 |  | Run material interface to GTS |  | James Van Riper | Thu 9/24/26 | Fri 9/25/26 | Wed 4/15/26 | 0% | Future Task | 2551 | Yes | No | 2746 | 805521c7853a47ce3e99f2f2eb0cc4d5d68f691961d74c554d5784c3c6c62900
project_plan | project_plan | 1716 | 2747 |  | Post Load Validation |  | James Van Riper | Fri 9/25/26 | Fri 9/25/26 | Wed 4/15/26 | 0% | Future Task | 2746 | Yes | No | 2747 | 0d5ac90a3660b8d0959a2931d876d2b284f62931356dc607999d5eec3110633a
project_plan | project_plan | 1717 | 2748 |  | GTS - ECCN - Create |  |  | Thu 9/24/26 | Fri 9/25/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 2748 | 9349e33805b84cd44818eddb6c04d193b98e1bf68c51fb2484109d6b49303257
project_plan | project_plan | 1718 | 2749 |  | Load Descartes XML File |  | James Van Riper | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 2423 | Yes | No | 2749 | 3424bb3465239f4783f9bb5916e757969d29a77a7d58a719dc99ec60de4f6a80
project_plan | project_plan | 1719 | 2750 |  | Post Load Validation |  | James Van Riper | Fri 9/25/26 | Fri 9/25/26 | Mon 4/13/26 | 0% | Future Task | 2746 | Yes | No | 2750 | 3128cddb3c79b05f7597a1f91477e764f6eaf8060e292c61f5bfc9793cb50db7
project_plan | project_plan | 1720 | 2751 |  | GTS - ECCN - Assign |  |  | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2751 | bebc60ef1f515973930c28f7bfce36920186ea4ff174cceda357317bfe1a7e8d
project_plan | project_plan | 1721 | 2752 |  | Load Descartes XML File |  | James Van Riper | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 2741 | Yes | No | 2752 | 2d571f9ecc155f33f0329775930df85bcb1646bc79875713a21c1f19899f8fd2
project_plan | project_plan | 1722 | 2753 |  | Post Load Validation |  | James Van Riper | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 2752 | Yes | No | 2753 | 81297b6d8b0c9ce23b5cf3dca5f0d19dee5de7b256d6e3f222d76216f336b071
project_plan | project_plan | 1723 | 2754 |  | GTS - HTS - Create |  |  | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 2754 | 6ef4e7388d6b025863fa41a7aab3294e6661d69a3f909080d8ae0fd495b3dba1
project_plan | project_plan | 1724 | 2755 |  | Load Descartes XML File |  | James Van Riper | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 2423 | Yes | No | 2755 | 900d1f4f950fcc8d73be7472a705936791996a2e28d4845bf2f54b605e8ff830
project_plan | project_plan | 1725 | 2756 |  | Post Load Validation |  | James Van Riper | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 2755 | Yes | No | 2756 | 57d99cddf45b86859578bbee31959b576d7691f2c43382c08d22731b2ac63aed
project_plan | project_plan | 1726 | 2757 |  | GTS - HTS - Assign |  |  | Thu 10/1/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2757 | 74ca40899594dcf4077fbfebaa471e03e86cc64f9fc8436d53a0bf40385c40c5
project_plan | project_plan | 1727 | 2758 |  | Load Descartes XML File |  | James Van Riper | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 2753 | Yes | No | 2758 | 8d6e35d7b1fc49374cf122b0ddc5b2f999386f640993c8e33e287e8d5876789c
project_plan | project_plan | 1728 | 2759 |  | Post Load Validation |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 2758 | Yes | No | 2759 | 4fc7ca0c79f1fe03fa832c0fef632525b44d9b0116fd8a29c06ef7891a5f5f80
project_plan | project_plan | 1729 | 2760 |  | GTS - License - Create |  |  | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2760 | d2689b6fc45ed9af0908b39fdadd6c167300e38369f172362f2f9b8d4fd480eb
project_plan | project_plan | 1730 | 2761 |  | Load Descartes XML File |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 27,582,774 | Yes | No | 2761 | b8f222cc97a436e5653033e961ee388274ee1748573ec5a1ab9e05e8a6cc8316
project_plan | project_plan | 1731 | 2762 |  | Post Load Validation |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 2761 | Yes | No | 2762 | 78d532a9a5d8c9958b69fc14c1b6b7be35cb588c1261d60297a8790a4c2e35cf
project_plan | project_plan | 1732 | 2763 |  | Commodity Code/Tarif |  |  | Fri 10/2/26 | Tue 10/6/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2763 | f8eeab9ae6841b7df1c6a6f4147d135426ce727742505b79f11a0348042e8eef
project_plan | project_plan | 1733 | 2764 |  | Load |  | James Van Riper | Fri 10/2/26 | Tue 10/6/26 | Thu 4/16/26 | 0% | Future Task | 2759 | Yes | No | 2764 | a074d035e7df1774b0def4d10c27b616067356f28e5de470abdc43a2edbb6150
project_plan | project_plan | 1734 | 2765 |  | Post Load Validation |  | James Van Riper | Tue 10/6/26 | Tue 10/6/26 | Thu 4/16/26 | 0% | Future Task | 2764 | Yes | No | 2765 | ee554be88cdbaece944bb688b8d42bcd75bce7a0135a5f961f446d89142fbaef
project_plan | project_plan | 1735 | 2766 |  | SPL Master File |  |  | Fri 10/2/26 | Fri 10/2/26 | Thu 3/13/25 | 0% | Future Task |  | Yes | No | 2766 | 854b7ec6d57add69724744df87f6634ae1988ad4adf79f6d3fdc252e1f248902
project_plan | project_plan | 1736 | 2767 |  | Load |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 3/13/25 | 0% | Future Task | 2758 | Yes | No | 2767 | 30bc8c289451f929171e43e5ae2b6f61320bc51510f1f928495697b3c21ead7f
project_plan | project_plan | 1737 | 2768 |  | Post Load Validation |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 3/13/25 | 0% | Future Task | 2767 | Yes | No | 2768 | 2c0c735be988f4bb5d37977d594cbf477428dd24a71660e1db3a8de10a3248f1
project_plan | project_plan | 1738 | 2769 |  | Initialize Embargo situation |  |  | Fri 9/25/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 2769 | 1a13fd573f31ce7278759c07554dd624f7ac4d41c8e17d2347e5f4d53fb098f6
project_plan | project_plan | 1739 | 2770 |  | Run report /SAPSLL/EMB_CNTRY_INIT |  | James Van Riper | Fri 9/25/26 | Fri 9/25/26 | Mon 4/13/26 | 0% | Future Task | 2750 | Yes | No | 2770 | 5efc1b471e2a38db9711df1704588b7e759a5359ed2b8ecd1e4ec29ec41a31a7
project_plan | project_plan | 1740 | 2771 |  | Set Embargo situations |  | James Van Riper | Fri 9/25/26 | Fri 9/25/26 | Mon 4/13/26 | 0% | Future Task | 2770 | Yes | No | 2771 | c0fe186d84232d2708e0c67151edcc20f01135e88d362108490a8a0c8a401f06
project_plan | project_plan | 1741 | 2772 |  | Post Load Validation |  | James Van Riper | Fri 9/25/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 2771 | Yes | No | 2772 | a599afb77705adfcaae11bcf3926fa5a25bfd44016be43d1d960f4b06acb33ef
project_plan | project_plan | 1742 | 2773 |  | GTS - SPL (Sanctioned party list) |  |  | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 2773 | 237d459cbf44d742fd5ddeadd6c4d4adf8712121c3e659d6957d91e6f86ac889
project_plan | project_plan | 1743 | 2774 |  | Load Descartes XML File |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 2759 | Yes | No | 2774 | 955e47cc33d6a667fb43fd381f36595548ae29278d54cab5a1d7b8e7aa1786dd
project_plan | project_plan | 1744 | 2775 |  | Post Load Validation |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 2774 | Yes | No | 2775 | 60255ec2f0701e2717e43dd564ee6be70d9e5c8e1050e2e9c71424bf2476b9d8
project_plan | project_plan | 1745 | 2776 |  | RTR_CM17_Project Definition / Builder |  |  | Thu 9/24/26 | Fri 9/25/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 2776 | 60a4bb886fa638c81e5e47cb5d13758ee5eb1aa54281d76a3c20c5d0ccc2e5cc
project_plan | project_plan | 1746 | 2777 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 2722 | Yes | No | 2777 | d33e60619a6081e8ea2546053c12464029c37f114eda9a5d52db24578bfbdbd0
project_plan | project_plan | 1747 | 2778 |  | Pre Load Validation |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 2777 | Yes | No | 2778 | fb19508f525ef5d57f6d30b73f65ff39901cc7728501fc7501b01b7ec7090f3a
project_plan | project_plan | 1748 | 2779 |  | Simulate Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Thu 4/16/26 | 0% | Future Task | 2778 | Yes | No | 2779 | 12d7d2bccf72ea1960cc2a6b0cce82885af2e6cb5567eadc30fc07917c1c319a
project_plan | project_plan | 1749 | 2780 |  | Error and Defect Mitigation |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/17/26 | 0% | Future Task | 2779 | Yes | No | 2780 | 2f279d36016f83deffb5a689a9427e6384b8986bc58181529a5a41b711e86679
project_plan | project_plan | 1750 | 2781 |  | Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Fri 4/17/26 | 0% | Future Task | 2780 | Yes | No | 2781 | 66bf40302b180aa55239f18763bef0c390f7cb5cf4b6574b4892485eecff0e5c
project_plan | project_plan | 1751 | 2782 |  | Post Load Validation |  | Kasey Hughes | Thu 9/24/26 | Fri 9/25/26 | Fri 4/17/26 | 0% | Future Task | 2781 | Yes | No | 2782 | a2431e26afc0d28d564428fc0c8da446b546e6068a8049ee6744edce1e41891e
project_plan | project_plan | 1752 | 2783 |  | RTR_CM18_WBS Element |  |  | Thu 9/24/26 | Fri 9/25/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 2783 | ead9cf61af5256395d760923bd3cfa3de9c3c61f47b1428d22cc774a0e39741c
project_plan | project_plan | 1753 | 2784 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 2777 | Yes | No | 2784 | 827fff1c381a6ee1a6ef48612d8967614d5d86f22bd5aba75138e238cebc1b13
project_plan | project_plan | 1754 | 2785 |  | Pre Load Validation |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 2784 | Yes | No | 2785 | 2af40e6a05e47ce77d2f6160a8839a1154f6f647d0e0ac38e230779ab21eb547
project_plan | project_plan | 1755 | 2786 |  | Simulate Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Thu 4/16/26 | 0% | Future Task | 2785 | Yes | No | 2786 | ef4a28c13d73ae4d68535d2b722d2bd016292f4eac99f112ac96f84e11216341
project_plan | project_plan | 1756 | 2787 |  | Error and Defect Mitigation |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/17/26 | 0% | Future Task | 2786 | Yes | No | 2787 | b72f4cf36f9e04c031d5d87e4d2ee9353c21baa6eb7c0454f0028004218e3b5c
project_plan | project_plan | 1757 | 2788 |  | Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Fri 4/17/26 | 0% | Future Task | 2787 | Yes | No | 2788 | 0e26af2410b88cba8df79a6f0773b4f0447249d940e17ecdcaaf10ce0e967f77
project_plan | project_plan | 1758 | 2789 |  | Post Load Validation |  | Kasey Hughes | Thu 9/24/26 | Fri 9/25/26 | Fri 4/17/26 | 0% | Future Task | 2788 | Yes | No | 2789 | be1d1073ce68fc4a6a995dbdb3e40c81fb57941cb34d485f8e79e7713c664ae7
project_plan | project_plan | 1759 | 2790 |  | UAT Mock Data Loads Complete |  | Mark George | Thu 9/24/26 | Thu 9/24/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | Yes | 2790 | 633d9515f31cf4fd3dab9ef80078513ca689fa997ed880afe86ed74a67dcb4ee
project_plan | project_plan | 1760 | 3360 |  | UAT Master Data Loads Complete |  |  | Thu 10/8/26 | Thu 10/8/26 |  | 0% | Future Task | 2898 | Yes | Yes | 3360 | e415d38a07901cb3e41314c86342e16e7aa7b58d05996f1f474b5641dc534d6b
project_plan | project_plan | 1761 | 3350 |  | Mock Transactional Data |  |  | Thu 10/8/26 | Mon 10/12/26 |  | 0% | Future Task | 3360 | Yes | No | 3350 | 6aefb1b7c03b317ffe553eb8b78a5a897dd97c5165687be66d1c6a5806f41182
project_plan | project_plan | 1762 | 3351 |  | Inventory |  |  | Thu 10/8/26 | Fri 10/9/26 |  | 0% | Future Task | 2947SS,3360SS | Yes | No | 3351 | b0048d6b84f38cc2f9969a5f64eacf745275db34563828b96432988a39aceeff
project_plan | project_plan | 1763 | 3352 |  | Open AR |  |  | Fri 10/9/26 | Fri 10/9/26 |  | 0% | Future Task | 3351 | Yes | No | 3352 | 111e65abdbd235b54627ad98160b0f24f372f5d598b300496065497ed1badee9
project_plan | project_plan | 1764 | 3353 |  | Open AP |  |  | Fri 10/9/26 | Mon 10/12/26 |  | 0% | Future Task | 3352 | Yes | No | 3353 | 49b62ffac8fa05fa845b9637de9d5be5da0b43758671bee33435602cb55854a2
project_plan | project_plan | 1765 | 3354 |  | Bank and Cash |  |  | Mon 10/12/26 | Mon 10/12/26 |  | 0% | Future Task | 3353 | Yes | No | 3354 | 1ca693284e630a231d877d506dda8e06abf900d13e45c0767591eb8b02ee8648
project_plan | project_plan | 1766 | 3355 |  | Open Purchase Orders(Manual) |  |  | Fri 10/9/26 | Mon 10/12/26 |  | 0% | Future Task | 3351 | Yes | No | 3355 | 4e8f12a5b09370858030a8a3e6f4d92253f98bd16b1892bf2106ff753d49a6ce
project_plan | project_plan | 1767 | 3356 |  | Open Sales Orders(Manual) |  |  | Fri 10/9/26 | Mon 10/12/26 |  | 0% | Future Task | 3351 | Yes | No | 3356 | 4bd0fae7d91332b7ffe62ba5789711cf5b638fdf65237dea32d4bf41d907ead3
project_plan | project_plan | 1768 | 3357 |  | Service Orders(Manual) |  |  | Fri 10/9/26 | Fri 10/9/26 |  | 0% | Future Task | 3351 | Yes | No | 3357 | fc6136bb4fae647a4c7d250ed391b4c3ff861fa588ab87310f5aa48d19ec0a26
project_plan | project_plan | 1769 | 3358 |  | Open Production Orders(Manual) |  |  | Fri 10/9/26 | Mon 10/12/26 |  | 0% | Future Task | 3351 | Yes | No | 3358 | b044445f08c73a0f9c576e30d336bacd8d6cafe3e6c549bb41d5a84c84d87172
project_plan | project_plan | 1770 | 2938 |  | UAT Mock Data Loads Complete |  | Mark George | Mon 10/12/26 | Mon 10/12/26 | Tue 4/21/26 | 0% | Future Task | 3350 | Yes | Yes | 2938 | ca377818633fcd6e66e287258d6b07788f4442193be5c912311638fe2e52030a
project_plan | project_plan | 1771 | 4160 |  | PROD Data Load Tasks P? |  |  | Thu 9/24/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task | 3367 | Yes | No | 4160 | 6e09caf14ff448113f2c39282457a3255104d9a0db81842fce9e4e2037cf7325
project_plan | project_plan | 1772 | 4161 |  | PMO Authorization to Start Data Loads |  | Mark George | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 3367 | Yes | No | 4161 | 636a077cafe5e7817865eca21200a15604141a453e427e8e59484845ccc649b9
project_plan | project_plan | 1773 | 4162 |  | Master Data Loads |  |  | Thu 9/24/26 | Thu 10/1/26 |  | 0% | Future Task | 4161 | Yes | No | 4162 | 8b8f0d62fffbae992042e880c4153a262907eea9a74abdffe18094ae1fd91298
project_plan | project_plan | 1774 | 4163 |  | RTR_CM02_Profit Center Hierarchy |  |  | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 4163 | fee68a01ad371982f50ef80c3a216eac9ce1719a25702b71546c0d2c5f0d603d
project_plan | project_plan | 1775 | 4164 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 4161 | Yes | No | 4164 | f8ed912fd5d4654a93d884978fd1cbd010e74056039212f3f62e979600375fc4
project_plan | project_plan | 1776 | 4165 |  | Load |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 4164 | Yes | No | 4165 | 082b2d2f49ca4c8c17e87899226f92304dd3775c734755c59a41e7f25dc69790
project_plan | project_plan | 1777 | 4166 |  | Post Load Validation |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 4165 | Yes | No | 4166 | f341bd80f5982ad81be91b5a1189c89042d0b2438ea8f985860f6cec297c4655
project_plan | project_plan | 1778 | 4167 |  | RTR_CM03_Cost Center Hierarchy |  |  | Thu 9/24/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 4167 | 5df1f09d4eff7200302c27a7631696b6e182788c390d67e80c4d0fe056200063
project_plan | project_plan | 1779 | 4168 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 4166 | Yes | No | 4168 | d0652990b36390979a35f409301c8e1b5cffcd5a0afd50278a2d5e9dd49f71f8
project_plan | project_plan | 1780 | 4169 |  | Load |  | Kasey Hughes | Thu 9/24/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4168 | Yes | No | 4169 | 42f18bfab3570d14fc0d0865a9dcc1b959a0352ab202eb8f875ef95e20a25034
project_plan | project_plan | 1781 | 4170 |  | Post Load Validation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4169 | Yes | No | 4170 | 55d37ccaabc48809c211c1488f536bbe7bd66e1e2990ca0768fee3c67be1a86f
project_plan | project_plan | 1782 | 4171 |  | RTR_CM01_GL_Account_Master to CC 1000 |  |  | Fri 9/25/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 4171 | 5c253c30a398bc4a250a91d72797339a7f44680e72c6dfa951c9d6e3a3be77de
project_plan | project_plan | 1783 | 4172 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4170 | Yes | No | 4172 | db5d0971ab457e0a105a473ad7e916781d73f177ddfc0cd1dcbf6df0de2c5e5c
project_plan | project_plan | 1784 | 4173 |  | Pre Load Validation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4172 | Yes | No | 4173 | 055f09c51c35f2241a31ec2bedbeb2bd9ff470ed1a4ae559ffa61670f340b42c
project_plan | project_plan | 1785 | 4174 |  | Simulate Load |  | Data Migration Team | Fri 9/25/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 4173 | Yes | No | 4174 | 4e8d621f74ac5d9ee403c21c50ebda4f9e0ddbb257ca7ebe47db72b2ce95de77
project_plan | project_plan | 1786 | 4175 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 9/28/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 4174 | Yes | No | 4175 | f5b301cbd6049886e1b0ff74b767a4d82d5d728a946f1aa407e835964d909ba3
project_plan | project_plan | 1787 | 4176 |  | Load |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 4175 | Yes | No | 4176 | 9eb66045a62181aaa4ccde93668be3d59368cde9875fe370bb0ecba77f901bb5
project_plan | project_plan | 1788 | 4177 |  | Post Load Validation |  | Kasey Hughes | Tue 9/29/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 4176 | Yes | No | 4177 | 42dbaca867e94396c21523fa78318d185276bd3e3d38bc98c2508e305d5fab3d
project_plan | project_plan | 1789 | 4178 |  | Extend GL to all Company Codes |  | Kasey Hughes | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 4177 | Yes | No | 4178 | 552f372e1e4df338e4656b6556cb8531d22e0b7bb84f6369d3a2bb88bfa4efd9
project_plan | project_plan | 1790 | 4179 |  | Post GL Extention Validation |  |  | Tue 9/29/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 4178 | Yes | No | 4179 | 133a62752ddb78fd5c68e9422ea376a50db8cd44835a27874a80e2197cb5667d
project_plan | project_plan | 1791 | 4180 |  | RTR_CM05_Profit_Center |  |  | Thu 9/24/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 4180 | 74d201ec5e0ec76e9b2c17a68faa5ba3fa6570ada5d6e456ad4ad2267913ed22
project_plan | project_plan | 1792 | 4181 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 4166 | Yes | No | 4181 | fb10ec496bb00432f3e8fe1f23edb46a448e1dba08c75324a2d3918bc95cffdc
project_plan | project_plan | 1793 | 4182 |  | Pre Load Validation |  | Kasey Hughes | Thu 9/24/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4181 | Yes | No | 4182 | b449f4d96872ced29857cf705df53b6fe356e16d876af9e4dd8866c4b3a66832
project_plan | project_plan | 1794 | 4183 |  | Simulate Load |  | Data Migration Team | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4182 | Yes | No | 4183 | 6ca049267f4c3741cb06883c7e74a8cd223daf6b14b0ce2fe73369dd57e3a315
project_plan | project_plan | 1795 | 4184 |  | Error and Defect Mitigation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4183 | Yes | No | 4184 | 6b8d8631c8c61470a08dd6ee9d1dd94f1c6cf99ed8eb9fc8e29e37fd3af9467f
project_plan | project_plan | 1796 | 4185 |  | Load |  | Data Migration Team | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4184 | Yes | No | 4185 | f3a38c398028c282529b7ca7c95ddba261722629e69dedf80bdf86ea73180b8f
project_plan | project_plan | 1797 | 4186 |  | Post Load Validation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4185 | Yes | No | 4186 | d573ef98e24f5666499f86d299acf92414ced37d2ee25c932c3bba6db05e8c9f
project_plan | project_plan | 1798 | 4187 |  | RTR_CM04_Cost_Center |  |  | Fri 9/25/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 4187 | ed4fe6d2535623d95a404076e22786e22f67586af53eddc3b4099bb0a815ac38
project_plan | project_plan | 1799 | 4188 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Fri 9/25/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 4186 | Yes | No | 4188 | b7454d3359bed32a16f8e6caef6448851267eb27d3a924e127f1b4bd33f6e415
project_plan | project_plan | 1800 | 4189 |  | Pre Load Validation |  | Kasey Hughes | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 4188 | Yes | No | 4189 | a39b62f84109d129ebadee12fd13cad8908525e761bc9e7d30abca63ea3d5487
project_plan | project_plan | 1801 | 4190 |  | Simulate Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 4189 | Yes | No | 4190 | a531bac81b0c3f5c0416450205e92f166a90831ee3dd6689067c685e0beba8af
project_plan | project_plan | 1802 | 4191 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 4190 | Yes | No | 4191 | 2a27a8b015680fd9bbfb0fd79bb058d7c03225dbf296d2c7d0f2ba95686262df
project_plan | project_plan | 1803 | 4192 |  | Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 4191 | Yes | No | 4192 | 186183c08b981c52cd368f2ab48fddcdef7658cec2e9f7414b556f667713ad76
project_plan | project_plan | 1804 | 4193 |  | Post Load Validation |  | Kasey Hughes | Mon 9/28/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 4192 | Yes | No | 4193 | bc9adfb10c4ace5a8f4afb4b48694da5b7ab907a9c6aa324943929853b1a8ce0
project_plan | project_plan | 1805 | 4194 |  | Manual Configuration Activities in QS5 |  |  | Thu 9/24/26 | Wed 10/7/26 | Wed 4/15/26 | 0% | Future Task | 652 | Yes | No | 4194 | 3bd726bcb7577b8bde5d88e157403138a8c9a3eb0be1ddf9286c91b7106cc893
project_plan | project_plan | 1806 | 4195 |  | Open Client |  | Basis | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 4195 | 30118660c42ebef6c66750f5b1c1f13fef2badc1ae93cebc66c7227042885732
project_plan | project_plan | 1807 | 4196 |  | Service Enterprise Setup |  | Keith Riley | Wed 9/30/26 | Wed 10/7/26 | Wed 4/15/26 | 0% | Future Task | 416,341,674,171 | Yes | No | 4196 | 29f71a8da22095127ad10c668b6170fd872ee2be9f47d89c27abb23cfabbdbcb
project_plan | project_plan | 1808 | 4197 |  | Close Client |  | Basis | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 4197 | 4a292f5d21802b9ec3783cb2190d8c43d65d25d587cefbbeecbc8ad9471db2ba
project_plan | project_plan | 1809 | 4198 |  | Intercompany Business Partner Setup |  | Functional Leads | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 416,341,674,179 | Yes | No | 4198 | 67df51d0ad74290b79dfeb3ad751bae89a26aba6ccd712f008610f6364428c83
project_plan | project_plan | 1810 | 4199 |  | RTR_CM09_Activity_Type |  |  | Tue 9/29/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 4199 | ae797d873e0fff790ca5535f7a3e136b7eecd38c6b3091f05dfa9df33b0e1e50
project_plan | project_plan | 1811 | 4200 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Tue 9/29/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 4177 | Yes | No | 4200 | d165ecd0f7fbaee37241c0e80113df4cbc9cfdc020bd9abeae5c6c1a89ce1d5c
project_plan | project_plan | 1812 | 4201 |  | Pre Load Validation |  | Kasey Hughes | Tue 9/29/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 4200 | Yes | No | 4201 | 5e34f6a137b0fc730d862d553801bede79f828d613954b0ba4fde7c4d079da24
project_plan | project_plan | 1813 | 4202 |  | Simulate Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 4201 | Yes | No | 4202 | 126e8687e85d2c47972f14c7780756fdacca5914e9fc2c387c79c2ec8df1a91d
project_plan | project_plan | 1814 | 4203 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 4202 | Yes | No | 4203 | 1ba3aff34286799839bd8cf16f4ffa224b01981cab13db3227f074756cd3f62e
project_plan | project_plan | 1815 | 4204 |  | Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 4203 | Yes | No | 4204 | 75aabf6f3e9523500ec0dd45355c63c8dd0d8671aa212e51371c20ac49ff134a
project_plan | project_plan | 1816 | 4205 |  | Post Load Validation |  | Kasey Hughes | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 4204 | Yes | No | 4205 | 21d1a2321531cff3602384bdb66081af6972619739666df05e924e9d69489480
project_plan | project_plan | 1817 | 4206 |  | RTR_CM12_Activity Rates |  |  | Fri 9/25/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task |  | Yes | No | 4206 | 3ac5dd94135577b723899aaaab2c0bbffc89ea0d92f13a45742097eb4dc2a9d1
project_plan | project_plan | 1818 | 4207 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4170 | Yes | No | 4207 | 8bee36f708cb6ab15a8fb63ae16de8b91f1cb4dbd8874a31353e488e9a676dae
project_plan | project_plan | 1819 | 4208 |  | Pre Load Validation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4207 | Yes | No | 4208 | 2cd9766a62bdcc6c37d15eb581ca2a957f619c0b62f3fe76a261d027977f5466
project_plan | project_plan | 1820 | 4209 |  | Simulate Load |  | Data Migration Team | Fri 9/25/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 4208 | Yes | No | 4209 | cadb03ce52c63342a215b4633202636ca1892450f3ec3abb45e0329033c58b68
project_plan | project_plan | 1821 | 4210 |  | Error and Defect Mitigation |  | Kasey Hughes | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 4209 | Yes | No | 4210 | 82a86f3fac66feb4770d0423d9b9de1871643f0498360e4770312da120adf5b8
project_plan | project_plan | 1822 | 4211 |  | Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 4210 | Yes | No | 4211 | 8b8ceb7227800c3396c64fd3ed2d313e23c5e32c9ecea9dfc317eeea1954b67b
project_plan | project_plan | 1823 | 4212 |  | Post Load Validation |  | Kasey Hughes | Mon 9/28/26 | Mon 9/28/26 | Wed 4/8/26 | 0% | Future Task | 4211 | Yes | No | 4212 | f5c35c5c196e0e141c6ad9dc995ae5a75a13b9d5d6794e2d4e66bfc626078f84
project_plan | project_plan | 1824 | 4213 |  | RTR_CM06_Bank_master |  |  | Thu 9/24/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 4213 | 1eb216097d2d928b67c087e1f409c959ac5e3cfcd2438cdf7eb2238e32e72c5f
project_plan | project_plan | 1825 | 4214 |  | Load File Staged and Posted "Ready" |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 4177 | Yes | No | 4214 | 29183a593cd87fd341911194617b908035938f9acd058d781132af60e3dfbbc6
project_plan | project_plan | 1826 | 4215 |  | Pre Load Validation |  | Kasey Hughes | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 4214 | Yes | No | 4215 | fc8cd5d605fe38e524cb8c34ce5c16e656000fbfd9583705d320c03775efacd7
project_plan | project_plan | 1827 | 4216 |  | Simulate Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Thu 4/9/26 | 0% | Future Task |  | Yes | No | 4216 | 0a86d6028413ccdbef2b1d01d29cb950e39e4ba8742c82c08ecf52a79a27a1d8
project_plan | project_plan | 1828 | 4217 |  | Error and Defect Mitigation |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Thu 4/9/26 | 0% | Future Task | 4216 | Yes | No | 4217 | a6cfae1789d023387a5e0317d4456175e36d184f8edb7ec5c6cf80bffa9a6c99
project_plan | project_plan | 1829 | 4218 |  | Load |  | Data Migration Team | Thu 9/24/26 | Fri 9/25/26 | Thu 4/9/26 | 0% | Future Task | 4217 | Yes | No | 4218 | 1cb88c44ac650f0e950aa16717e8fc4dde52cd68d6ce177212e26c9feb47ef61
project_plan | project_plan | 1830 | 4219 |  | Post Load Validation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Thu 4/9/26 | 0% | Future Task | 4218 | Yes | No | 4219 | a5be24e3bf5e9895c913cbc38062a0cee2de1b9518afc80964301bbd2666eb01
project_plan | project_plan | 1831 | 4220 |  | RTR_CM08_Exchange_Rates |  |  | Fri 9/25/26 | Mon 9/28/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 4220 | 1c2368df138baca577a1c8fcbbfb3da28b32bf8430cf2ffe4fbd8236bcbc7c89
project_plan | project_plan | 1832 | 4221 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Thu 4/9/26 | 0% | Future Task | 4218 | Yes | No | 4221 | 389f982330e8501dadda2e9de2d446046fdf2496d47e033c4c8f8746afcaaa30
project_plan | project_plan | 1833 | 4222 |  | Pre Load Validation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Fri 4/10/26 | 0% | Future Task | 4221 | Yes | No | 4222 | cf865a4f9ae7940c5739d60ab9cae3e42fa70bc728cafaf95cfd1ab5a277da32
project_plan | project_plan | 1834 | 4223 |  | Simulate Load |  | Data Migration Team | Fri 9/25/26 | Fri 9/25/26 | Fri 4/10/26 | 0% | Future Task | 4222 | Yes | No | 4223 | b10ef47d379d63c11307e245fa2e83e8347dfdd0643bf1ea0866949e3f8efa65
project_plan | project_plan | 1835 | 4224 |  | Error and Defect Mitigation |  | Kasey Hughes | Fri 9/25/26 | Fri 9/25/26 | Fri 4/10/26 | 0% | Future Task | 4223 | Yes | No | 4224 | 150c84dd35688a9e773875b2c829411ed211fc2daddd8a8744c5c93c099848b6
project_plan | project_plan | 1836 | 4225 |  | Load |  | Data Migration Team | Fri 9/25/26 | Fri 9/25/26 | Fri 4/10/26 | 0% | Future Task | 4224 | Yes | No | 4225 | 398bdd45ad3128739977de3cd098e3bf18eef4f7360e1867411e38b8fda0a21c
project_plan | project_plan | 1837 | 4226 |  | Post Load Validation |  | Kasey Hughes | Fri 9/25/26 | Mon 9/28/26 | Fri 4/10/26 | 0% | Future Task | 4225 | Yes | No | 4226 | acb2c13492f91f445cdfdd88a314c3c7bb2785eab490fd18be2a7055ff947da8
project_plan | project_plan | 1838 | 4227 |  | RTR_CM14_Cost Element_Group |  | Kasey Hughes | Tue 9/29/26 | Mon 10/5/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 4227 | c38fffc453e57f28c563f028db6eb722a114ce626d41f46e76bd9808bfb19bfc
project_plan | project_plan | 1839 | 4228 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Tue 9/29/26 | Tue 9/29/26 | Tue 4/14/26 | 0% | Future Task | 4177 | Yes | No | 4228 | f375db347fc182b529628a2db22e8aca03c6425b3077f56bb34e35e3d9b30180
project_plan | project_plan | 1840 | 4229 |  | Load |  | Kasey Hughes | Tue 9/29/26 | Mon 10/5/26 | Wed 4/15/26 | 0% | Future Task | 4228 | Yes | No | 4229 | c7eab931e3058e215c6b414e20d9339a6aa36a68a6699289f5c1ba582fb27ef5
project_plan | project_plan | 1841 | 4230 |  | Post Load Validation |  | Kasey Hughes | Mon 10/5/26 | Mon 10/5/26 | Wed 4/15/26 | 0% | Future Task | 4229 | Yes | No | 4230 | 144c306d75a6e7f8c1ba8e7876b7d674758db950fc404bc29bbf341b01a66dbf
project_plan | project_plan | 1842 | 4231 |  | OTC_CM19_Customer_Master - Bill-To |  |  | Thu 9/24/26 | Thu 9/24/26 | Wed 4/16/25 | 0% | Future Task |  | Yes | No | 4231 | 339054127beaaada0133fad3a93dd7dba381225f2827361fb14b07e5e3f5ad97
project_plan | project_plan | 1843 | 4232 |  | OTC_CM19_Customer_Master - Ship-To |  |  | Tue 9/29/26 | Thu 10/1/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 4232 | a27742f7dba11db231cf08209557b7e339fd6f1d754b6d7bc43c17d9c4105963
project_plan | project_plan | 1844 | 4233 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Tue 9/29/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 4177 | Yes | No | 4233 | 8ebf414183f29eaade1f30b9574293ca4357aab7f7c4a6ef80614ae80841b439
project_plan | project_plan | 1845 | 4234 |  | Pre Load Validation |  | Ric Haraida | Tue 9/29/26 | Tue 9/29/26 | Wed 4/8/26 | 0% | Future Task | 4233 | Yes | No | 4234 | fad824b25716723acc422f7a195a380f4c39834c7782524e49baa6c7e8f248a9
project_plan | project_plan | 1846 | 4235 |  | Open client for BP number range update |  | Basis | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 4234 | Yes | No | 4235 | e8c020433b1c9b149c156b2fa1b2af23eeec6471c5ec51eb17ee20d540d74835
project_plan | project_plan | 1847 | 4236 |  | Update number range BP02 from Internal to External |  | Ric Haraida | Tue 9/29/26 | Tue 9/29/26 | Fri 4/10/26 | 0% | Future Task | 4235 | Yes | No | 4236 | f3015e8e74b73a7659df65dfe7e0e991669eab0350d31188de7da90184bf3d7d
project_plan | project_plan | 1848 | 4237 |  | Close Client |  | Basis | Tue 9/29/26 | Tue 9/29/26 | Mon 4/13/26 | 0% | Future Task | 4236 | Yes | No | 4237 | 56d9a2b9b6e90cee3d27499fd483ff1ae1bdfa6cdb253b6c17aac6f69d52dfa1
project_plan | project_plan | 1849 | 4238 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 4234 | Yes | No | 4238 | c4a372bcbfd67fdd5db69fc7de7948de9b53e693aa0a5e3faf7013085ef0035d
project_plan | project_plan | 1850 | 4239 |  | Error and Defect Mitigation |  | Ric Haraida | Tue 9/29/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 4238 | Yes | No | 4239 | 8d6d618103a8f242ae3c0944157d52a31b95596af9bb5fef709b844b9bd6d7a4
project_plan | project_plan | 1851 | 4240 |  | Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 4239 | Yes | No | 4240 | 4f00e4f3cc58864e8b0cad2e71ea52801639ae3fe21205f634f00ea1c4563866
project_plan | project_plan | 1852 | 4241 |  | Post Load Validation |  | Ric Haraida | Wed 9/30/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4240 | Yes | No | 4241 | 8a67ae251a285beaea13b0438afff7bdaa44245271d731a30bcf0c2da52f2a07
project_plan | project_plan | 1853 | 4242 |  | OTC_CM19_Customer_Master - Sold-To |  |  | Tue 9/29/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 4242 | c4a810017068a4d344d25a53764890119bee18d1e5998524fe44914bff7f3bb1
project_plan | project_plan | 1854 | 4243 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 4234 | Yes | No | 4243 | 6d546913177b82ed9cb0d19a2970b562bafe77577f79cf0f26d4d86ee15e39a7
project_plan | project_plan | 1855 | 4244 |  | Pre Load Validation |  | Ric Haraida | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 4243 | Yes | No | 4244 | 8cee19d34f35ad7e0f492a4b4f75f80ce9a8a4c5d294e9168581a39373a5770e
project_plan | project_plan | 1856 | 4245 |  | Simulate Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 41,794,238 | Yes | No | 4245 | 85e58ed2e72eb49e3869b0703d87cf677819095f3a108a2540a6b046bd37a77f
project_plan | project_plan | 1857 | 4246 |  | Error and Defect Mitigation |  | Ric Haraida | Wed 9/30/26 | Wed 9/30/26 | Thu 4/9/26 | 0% | Future Task | 4245 | Yes | No | 4246 | 9ad10a195290505eaf22fc03281d89828cdfe5fcb38fcde01673f75b77a7b98b
project_plan | project_plan | 1858 | 4247 |  | Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Fri 4/10/26 | 0% | Future Task | 4246 | Yes | No | 4247 | 36f17d3efe2e3cfbbe2ef1a24019280869a73a0d2b8a4345b19950d86e485fca
project_plan | project_plan | 1859 | 4248 |  | Post Load Validation |  | Ric Haraida | Wed 9/30/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4247 | Yes | No | 4248 | cee2839e07f09fdac6def66094319fdafdd8d3455fa2c49b86ca74df8c8bda19
project_plan | project_plan | 1860 | 4249 |  | Open client for BP number range update |  | Basis | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 4238 | Yes | No | 4249 | 6d4ef7a2dd107ba8ea6928aea3d19eb1967c67c78079ef706023d2b37c8ac32f
project_plan | project_plan | 1861 | 4250 |  | Update number range BP02 from Internal to External |  | Ric Haraida | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 4249 | Yes | No | 4250 | bbf095938b72fa5357e1122673a39526c1ff4dd5c1dee53c5115882c1b76cde8
project_plan | project_plan | 1862 | 4251 |  | Close Client |  | Basis | Tue 9/29/26 | Tue 9/29/26 | Thu 4/9/26 | 0% | Future Task | 4250 | Yes | No | 4251 | 10abb9052828e6304d00e841ed1d0389b3b147bbbd21a50757e6ac208a54374f
project_plan | project_plan | 1863 | 4252 |  | PTP_CM27_Vendor Master as Customer - FLCU01 |  |  | Wed 9/30/26 | Wed 10/7/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 4252 | d7d576b875ef5b71267b279141f9386060fba4c002e5febe87755c95eb89848d
project_plan | project_plan | 1864 | 4253 |  | Extract File |  | Data Migration Team | Wed 9/30/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4247 | Yes | No | 4253 | 61bbe759ee4ef245a7d98ff85d2dc976be4cd2492e8f9959d6c9fc87f88fe5cf
project_plan | project_plan | 1865 | 4254 |  | Pre Load Validation |  | Nevin Varkey | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4253 | Yes | No | 4254 | dbeb6d525401d1c30b4622c259087c6658022bf68b1e8a3f37c2e79f45ef44dc
project_plan | project_plan | 1866 | 4255 |  | Simulate Load |  | Data Migration Team | Thu 10/1/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task | 42,194,254 | Yes | No | 4255 | 12bde5b1cef92a22a5d04f1ad8f67b17260d0ed0f0e7c45928c46f90281cc731
project_plan | project_plan | 1867 | 4256 |  | Error and Defect Mitigation |  | Nevin Varkey | Fri 10/2/26 | Tue 10/6/26 | Tue 4/14/26 | 0% | Future Task | 4255 | Yes | No | 4256 | f208761f6af0fb4357bf2e534ea7c987366d08b457bd80eda2bf453193779d36
project_plan | project_plan | 1868 | 4257 |  | Load |  | Data Migration Team | Tue 10/6/26 | Wed 10/7/26 | Tue 4/14/26 | 0% | Future Task | 4256 | Yes | No | 4257 | d5ae0d0b076aadf666485d92929004d667d5df33f25c8351dc33624202f788ee
project_plan | project_plan | 1869 | 4258 |  | Post Load Validation |  | Nevin Varkey | Wed 10/7/26 | Wed 10/7/26 | Tue 4/14/26 | 0% | Future Task | 4257 | Yes | No | 4258 | 38500c56da80eeedd8d1d61db7b8f64016eb42ed0d1eb0b6383a12bb4408aff4
project_plan | project_plan | 1870 | 4259 |  | OTC_CM23_Customer_Hierarchy |  |  | Wed 9/30/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 4259 | 774b5c1e050abbd375d5e1cbeeccf2c0b0882b2c0ec89bf5e6de23480c674bf5
project_plan | project_plan | 1871 | 4260 |  | Manual File Staged and Posted "Ready" |  | Ric Haraida | Wed 9/30/26 | Wed 9/30/26 | Fri 4/10/26 | 0% | Future Task | 4247 | Yes | No | 4260 | ea194123496951654b3096bc8c2d6081d361087691a6ce6a8c255257b17e5b38
project_plan | project_plan | 1872 | 4261 |  | Load |  | Ric Haraida | Wed 9/30/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4260 | Yes | No | 4261 | 775ef14a3ddb4b3ef7b75949d02acb1d59f0b4986eed4308c64d8528d12e8a69
project_plan | project_plan | 1873 | 4262 |  | Post Load Validation |  | Ric Haraida | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4261 | Yes | No | 4262 | 0fff8c625914512bf97e3df509c9a89967e4f7e034677e405c207173a40ba3a1
project_plan | project_plan | 1874 | 4263 |  | PTP_CM27_Vendor Master - Z001 - External Sales Rep |  |  | Wed 9/30/26 | Tue 10/6/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 4263 | 0de56098c2d4d16952d0297149d8f23bb1a8a45ffe318bce0d18fbdc3374f67b
project_plan | project_plan | 1875 | 4264 |  | Extract File |  | Data Migration Team | Wed 9/30/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4247 | Yes | No | 4264 | 0a4e61ff60675b8c6c9f03047f501201528c4d8c5e9c1de27867fe3f5ee29741
project_plan | project_plan | 1876 | 4265 |  | Pre Load Validation |  | Nevin Varkey | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4264 | Yes | No | 4265 | fe5ff6d6e7de52455652e809ef266d878da9481a60ea30d7af8467708b6d5cc6
project_plan | project_plan | 1877 | 4266 |  | Simulate Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 42,194,265 | Yes | No | 4266 | a95c46f54c426d2c6f3d0f3a1df4c9c78007d9555dc0cd65f095847bea94823d
project_plan | project_plan | 1878 | 4267 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4266 | Yes | No | 4267 | 142a9e67a1356bf01524105bf4524072e59e1a28055f12d59046d9b5b3dce9b1
project_plan | project_plan | 1879 | 4268 |  | Load |  | Data Migration Team | Thu 10/1/26 | Tue 10/6/26 | Mon 4/13/26 | 0% | Future Task | 4267 | Yes | No | 4268 | 1a25c53888354b62eccf2b49c5d5ef25c7b69ec4e2ae78f42bdcf57740d9f6a7
project_plan | project_plan | 1880 | 4269 |  | Post Load Validation |  | Nevin Varkey | Tue 10/6/26 | Tue 10/6/26 | Mon 4/13/26 | 0% | Future Task | 4268 | Yes | No | 4269 | 6b13b9ec64177fae5fc9e548eaf877cd956361cf9dd7f90a7442c5dadb8d6ca0
project_plan | project_plan | 1881 | 4270 |  | RTR_CM10_Credit_Management_Role |  |  | Wed 9/30/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 4270 | 27530b9927e5c6b62ae167dd4147e3e265ab7133621d9ac606bb609479bd0f1b
project_plan | project_plan | 1882 | 4271 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Wed 9/30/26 | Wed 9/30/26 | Fri 4/10/26 | 0% | Future Task | 4247 | Yes | No | 4271 | e3740f3b7a4d97c00ec9e019697fd9b2b542520cfcbb6c9b5c7e846c3b3eefc2
project_plan | project_plan | 1883 | 4272 |  | Pre Load Validation |  | Kasey Hughes | Wed 9/30/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4271 | Yes | No | 4272 | 908b4460bc68ba34d29e157158f5fc01ef31b9632e2cae76cfc559935799c30e
project_plan | project_plan | 1884 | 4273 |  | Simulate Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4272 | Yes | No | 4273 | 3894bf29d07cecb0ed1c666cb41dd80d073ccad9778e3310dbaa300397ba86cd
project_plan | project_plan | 1885 | 4274 |  | Error and Defect Mitigation |  | Kasey Hughes | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4273 | Yes | No | 4274 | 4f15a92c0dd7eaa58b78edc79e2aa5186c7975a43082450d94693505e1ab9932
project_plan | project_plan | 1886 | 4275 |  | Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4274 | Yes | No | 4275 | 224315a3b7e31d9ca5209ab003976a3a5025da37579dbc2e00e47419f07e2096
project_plan | project_plan | 1887 | 4276 |  | Post Load Validation |  | Kasey Hughes | Thu 10/1/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task | 4275 | Yes | No | 4276 | 6d23d2d64c6cc24aa46dd4a06e24c4e51a7db4e000b2a2a9e3de7c15029c6bf4
project_plan | project_plan | 1888 | 4277 |  | PTP_CM27_Vendor Master |  |  | Thu 9/24/26 | Fri 10/2/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 4277 | 346d5165ec5ed398052f0db88b93d686e14b28acc7ac6b49a18ad94cc51dee19
project_plan | project_plan | 1889 | 4278 |  | Extract File |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4264 | Yes | No | 4278 | 34ebdb6e2dbb500284a4404c68d364f17f860974fff4d00f29f3580593e2e54c
project_plan | project_plan | 1890 | 4279 |  | Pre Load Validation |  | Nevin Varkey | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4278 | Yes | No | 4279 | 1fbbaccb802e3cf588f00d31ecb5b80a8162591172a9f1dabac12cbea1f6ac8c
project_plan | project_plan | 1891 | 4280 |  | Simulate Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Tue 4/14/26 | 0% | Future Task | 4279 | Yes | No | 4280 | 444a4824ba3319f9650bde05eb9cb621c39220f79a490975afe4ca09ce04715a
project_plan | project_plan | 1892 | 4281 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 10/1/26 | Fri 10/2/26 | Tue 4/14/26 | 0% | Future Task | 4280 | Yes | No | 4281 | b7c04240d9023a36a6a09bc18b2f069bb5f1183c4df3e1668be812074ebf1d3c
project_plan | project_plan | 1893 | 4282 |  | Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 4282 | 4b1607f6ab1ca4156fba2f6667d391b49dcba995c53ea95b26afb759cead5f03
project_plan | project_plan | 1894 | 4283 |  | Post Load Validation |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Wed 4/15/26 | 0% | Future Task | 4282 | Yes | No | 4283 | bd4a1ce2276bbb39d637c46bd3ed139cddbec6a032a006805ff8a5768fbc0cb1
project_plan | project_plan | 1895 | 4284 |  | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR |  |  | Thu 9/24/26 | Thu 9/24/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 4284 | 319c2a488b24ae558369d1eadf33e101aa7063af8bb6c9e6398b011731b4a94c
project_plan | project_plan | 1896 | 4285 |  | Extract File(Will Extract from LFA1) |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 4285 | b03878244fcb26f582de8fde92041aa9ae1d9ce12225d80e77cca4e5b2961a57
project_plan | project_plan | 1897 | 4286 |  | Pre Load Validation |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 4285 | Yes | No | 4286 | a726038607845aca3bdb4cf64a1283d2027631becda0851bdd9dea79e80d50ab
project_plan | project_plan | 1898 | 4287 |  | Simulate Load/ Not Needed |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 4286 | Yes | No | 4287 | af574a9c25224cfc95031778bacdd6d773657e0c2118f9f40ca0d5d75183fd42
project_plan | project_plan | 1899 | 4288 |  | Error and Defect Mitigation |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 4287 | Yes | No | 4288 | 83bfb0e4aec8058bbfbbfdc70e86c31a4c74e4e824a538ff08238a433cf6e81b
project_plan | project_plan | 1900 | 4289 |  | Load |  | Nevin Varkkey | Thu 9/24/26 | Thu 9/24/26 | Wed 4/15/26 | 0% | Future Task | 4287 | Yes | No | 4289 | 04318269b9acc2c346c4b405d8301744d5d31984183091664a74bf17a5c8947e
project_plan | project_plan | 1901 | 4290 |  | Post Load Validation |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Wed 4/15/26 | 0% | Future Task | 4289 | Yes | No | 4290 | c2d4edcbad5d44d5fcbc7bf2ace323e0e5ef1014d2989b235eadb1c30f824551
project_plan | project_plan | 1902 | 4291 |  | RTR_****_Credit Hierarchy |  |  | Thu 10/1/26 | Mon 10/5/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 4291 | 4c023ec4f9d759c1fea78a753be876a5912c404280c7128d53a318e777028e41
project_plan | project_plan | 1903 | 4292 |  | Manual File Staged and Posted "Ready" |  | Kasey Hughes | Thu 10/1/26 | Thu 10/1/26 | Fri 4/10/26 | 0% | Future Task | 4274 | Yes | No | 4292 | 521acaf0019e0270b38c7977d73dc725af101e85a7e8f91e314254bc890af331
project_plan | project_plan | 1904 | 4293 |  | Load |  | Kasey Hughes | Fri 10/2/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task | 4276 | Yes | No | 4293 | c1d3fe180be3b531b31dc4faf35334e45654deae513b63d403f062a9c8572a9c
project_plan | project_plan | 1905 | 4294 |  | Post Load Validation |  | Kasey Hughes | Fri 10/2/26 | Mon 10/5/26 | Mon 4/13/26 | 0% | Future Task | 4293 | Yes | No | 4294 | 1f6bdf976986398105a1cd3cb554741c4a1c50ba817f45ca5d494ec4f5ebc5f4
project_plan | project_plan | 1906 | 4295 |  | PTP_CM27_BP_Intercompany Supplier |  |  | Thu 9/24/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 4295 | 0a72b9c199625156994017bc8a7a6c6034b95aa7b546e5ca9e66886595ea9050
project_plan | project_plan | 1907 | 4296 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 4283 | Yes | No | 4296 | 812ca2dd46b8723818b7b80bc153ab03d7d9e6908da3255e771c3b1dcdadcfcf
project_plan | project_plan | 1908 | 4297 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 4296 | Yes | No | 4297 | dbbdcfb0a95d2cdc11a6756352e30ffe7d8f09126a32f48bf30e2c73811aae71
project_plan | project_plan | 1909 | 4298 |  | Simulate Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 4297 | Yes | No | 4298 | db78badc584bdc7d56466ea350f05f8fa439730f261b6d45c895b6063340f091
project_plan | project_plan | 1910 | 4299 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 4298 | Yes | No | 4299 | 2585da148e90c1a6495f19f11bc0250464324770de612597febdf107495a6fa2
project_plan | project_plan | 1911 | 4300 |  | Load |  | Data Migration Team | Thu 9/24/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 4299 | Yes | No | 4300 | 6fa1b3120772b89a5f137ae9532fc17f045ea2f9c6b354fddeb1b5f03d00d2ac
project_plan | project_plan | 1912 | 4301 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Fri 9/25/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 4300 | Yes | No | 4301 | bcb7ddfe184b3b5226f3a7f728204df5e9aa737aba0f469766205dd9717020e0
project_plan | project_plan | 1913 | 4302 |  | PTP_CM27_BP_Intercompany Customer |  |  | Thu 9/24/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 4302 | 526b5fc0c2fcc90a8154344b08c9285b7345e552267b5669ad8848f2f4173625
project_plan | project_plan | 1914 | 4303 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 4303 | c288f52b9445523be3a38113da636fefb9380bc2da39c324d6d671d606300f55
project_plan | project_plan | 1915 | 4304 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 4304 | 7a9e7e0d6b530120b23f8204999541bed71288472dc6bd329306c982f57854a3
project_plan | project_plan | 1916 | 4305 |  | Simulate Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 4304 | Yes | No | 4305 | 0dc7ac7bf45e8b7285f13bd519b532877cd9539b0cef1dc18b6a37b0ed368e29
project_plan | project_plan | 1917 | 4306 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Thu 9/24/26 | Mon 4/13/26 | 0% | Future Task | 4305 | Yes | No | 4306 | fde671d10a5725066001162573322868b4deeaba83ef310f65b2c42d71f04bb0
project_plan | project_plan | 1918 | 4307 |  | Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Tue 4/14/26 | 0% | Future Task | 4306 | Yes | No | 4307 | d9523304dd1c597782988715207e629e0bb44c836ec8037536d592eb35043480
project_plan | project_plan | 1919 | 4308 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 4307 | Yes | No | 4308 | 755227d6332ce23b9b67cb70b1b5e50094588802a085a8da69ebb3abc8fcef12
project_plan | project_plan | 1920 | 4309 |  | PTP_CM26_Material_Master - All Types |  |  | Thu 9/24/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 4309 | 18d05d00b86f4d3abd46a76aa92ac2a473e4c0099c8e5c18a0c9065004f7baac
project_plan | project_plan | 1921 | 4310 |  | Extract File |  | Data Migration Team | Thu 9/24/26 | Fri 9/25/26 | Mon 4/13/26 | 0% | Future Task | 4285 | Yes | No | 4310 | b2f698a14fefb122665fe32c200d5bad118d9d7a8d7e5af5c6aff53cee6075ad
project_plan | project_plan | 1922 | 4311 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Thu 9/24/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 4283 | Yes | No | 4311 | b401e2a40f1bbc99d6db03a7f9835867cc9c5e2a95fc3953a40c5b41b4d70828
project_plan | project_plan | 1923 | 4312 |  | Simulate Load |  | Data Migration Team | Fri 9/25/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 4311 | Yes | No | 4312 | 1f044ae7b41bd5256710c9431d57d35c7530e659299fb3bbfdca79fd25fa3572
project_plan | project_plan | 1924 | 4313 |  | Error and Defect Mitigation |  | Nevin Varkey | Fri 9/25/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 4312 | Yes | No | 4313 | 9682016c323d87559e73dc520b017a64a51141526fd191d8854dbf8e4acc9180
project_plan | project_plan | 1925 | 4314 |  | Load |  | Data Migration Team | Fri 9/25/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task | 4313 | Yes | No | 4314 | 7f5a05573b84d80b922895b897f16747346fc39f3e437aaaa68134570ca5525c
project_plan | project_plan | 1926 | 4315 |  | Post Load Validation |  | Nevin Varkey | Mon 9/28/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task | 4314 | Yes | No | 4315 | dedffde0a7b9d8ebdf5ed180dbbb79615d9b0391ac67762b8f4d952f1c213af7
project_plan | project_plan | 1927 | 4316 |  | PTP_CM26_Material_Master - SERV - Service Materials |  |  | Fri 9/25/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 4316 | c3ea05cc579c16f0a4e877c52a41271339ffa171048c10cd60163a6de1bbed11
project_plan | project_plan | 1928 | 4317 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey,Ric Haraida | Fri 9/25/26 | Mon 9/28/26 | Tue 4/7/26 | 0% | Future Task | 4186 | Yes | No | 4317 | 0c8402a0aafe24d49b3e223fb6be39bacccbbf2a9e22fa23d37047cfe10790c4
project_plan | project_plan | 1929 | 4318 |  | Pre Load Validation |  | Nevin Varkey,Ric Haraida | Mon 9/28/26 | Mon 9/28/26 | Tue 4/14/26 | 0% | Future Task | 4314 | Yes | No | 4318 | f36d72a8f47fc6755f00cfb88f1d85bc0a394bec3ec89f79ae10ecbbc49c6d80
project_plan | project_plan | 1930 | 4319 |  | Simulate Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Tue 4/14/26 | 0% | Future Task | 4318 | Yes | No | 4319 | 395dcdde1355d5a9a50015067c54e8faf17f9f26a8261cce2d62f868c5b72a19
project_plan | project_plan | 1931 | 4320 |  | Error and Defect Mitigation |  | Nevin Varkey,Ric Haraida | Mon 9/28/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task | 4319 | Yes | No | 4320 | d1df7669bd288c03863d607d1cf14c5088d4adc28daa36ffa6f0882ae5510bc5
project_plan | project_plan | 1932 | 4321 |  | Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task | 4320 | Yes | No | 4321 | e34100432297f6b162ba47702256e54b2e1528251eea50f5ef9a72d45c677e27
project_plan | project_plan | 1933 | 4322 |  | Post Load Validation |  | Nevin Varkey,Ric Haraida | Mon 9/28/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 4321 | Yes | No | 4322 | 260417571a7093f8fc7e47f726e6e31323a525f458832d0f105ba47e13c4ee15
project_plan | project_plan | 1934 | 4323 |  | PTP_CM26_Material_Master - KMAT - Configurable Materials |  |  | Fri 9/25/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 4323 | 8cd890a86cf22b0d6a4a773e14b8c0a6d7afcc525624f74194d88b28a70e14ec
project_plan | project_plan | 1935 | 4324 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Fri 9/25/26 | Mon 9/28/26 | Tue 4/7/26 | 0% | Future Task | 4186 | Yes | No | 4324 | 9a1b4efc3ce136b4e0d49a72f8473133ccebe92a72e53a9c958266bbe0780d56
project_plan | project_plan | 1936 | 4325 |  | Pre Load Validation |  | Eric Heisler | Mon 9/28/26 | Mon 9/28/26 | Tue 4/14/26 | 0% | Future Task | 4314 | Yes | No | 4325 | c5ef80815ec159c139b1f66f81f5290ed303b00573edd282afc0e7b9195e37dc
project_plan | project_plan | 1937 | 4326 |  | Simulate Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Tue 4/14/26 | 0% | Future Task | 4325 | Yes | No | 4326 | 7b3f6dd6030db99295213aa281c950a130258d710f6432fbf751ccd5b35f5441
project_plan | project_plan | 1938 | 4327 |  | Error and Defect Mitigation |  | Eric Heisler | Mon 9/28/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task | 4326 | Yes | No | 4327 | b9f206b9fec797f3fd87a221cd9e0d3a638b54995aa957e3b746894ae1591393
project_plan | project_plan | 1939 | 4328 |  | Load |  | Data Migration Team | Mon 9/28/26 | Mon 9/28/26 | Wed 4/15/26 | 0% | Future Task | 4327 | Yes | No | 4328 | a078779ae271fecd27fd84086711d32e2c8598c25b7b9b4d2bc530625c112704
project_plan | project_plan | 1940 | 4329 |  | Post Load Validation |  | Eric Heisler | Mon 9/28/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 4328 | Yes | No | 4329 | 122e7547631e7ec01f39f3cfc303b6e0ec25d040d86cb2ebd86b47bc8040d6b3
project_plan | project_plan | 1941 | 4330 |  | PTP_CM28_Purchase_Info_Records |  |  | Thu 9/24/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4330 | 2c87ed8c48f7305b1449453c8c527534192940965fbe28ed6cd6b6353938390b
project_plan | project_plan | 1942 | 4331 |  | Extract File |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 43,154,329 | Yes | No | 4331 | 06bb654c95791354c50465d12a6d7b90ecfef6c5e39ca634bf0660aa1043ad3d
project_plan | project_plan | 1943 | 4332 |  | Pre Load Validation |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4331 | Yes | No | 4332 | 86fec973760daef8fc66e36abd13f12beaf69310c2b380bef56d042de5577add
project_plan | project_plan | 1944 | 4333 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4332 | Yes | No | 4333 | 70fd5333d6af9cf1f925e6da1455998fdba9af302471d425cd81fb65d6acb517
project_plan | project_plan | 1945 | 4334 |  | Error and Defect Mitigation |  | Nevin Varkey | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 4333 | Yes | No | 4334 | b66896a4a3cde238c640626f3ea504e690342f02176294459e4de3954a66d013
project_plan | project_plan | 1946 | 4335 |  | Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Wed 4/15/26 | 0% | Future Task | 4283 | Yes | No | 4335 | 4c3d00706d11a500e36aa753783bb28c7ac2cde438b4e99dc2fee8eab7e1a0b7
project_plan | project_plan | 1947 | 4336 |  | Post Load Validation |  | Nevin Varkey | Thu 9/24/26 | Thu 9/24/26 | Wed 4/15/26 | 0% | Future Task | 4335 | Yes | No | 4336 | c0a475b996962f0abc41048d15ffbe4cf16130467706b47485a7e41f684e4227
project_plan | project_plan | 1948 | 4337 |  | PTP_CM28_Purchase_Info_Record External Processing |  |  | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4337 | 6ddf1d16197eaf69c4742ae98ad66722bd766942d059b6ec90590eaba1adc105
project_plan | project_plan | 1949 | 4338 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 43,154,329 | Yes | No | 4338 | b29c62ac366c8b6aea46e456e09ea18518ca05d918212f73e9e6164b923fa187
project_plan | project_plan | 1950 | 4339 |  | Pre Load Validation |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 4338 | Yes | No | 4339 | 893b2e56cb2bfe3a4d3b770436040b73f44bd33f82ed8611433fa74910651795
project_plan | project_plan | 1951 | 4340 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4339 | Yes | No | 4340 | f52116b24bdea2ebafcc180486624ef99aacda49335846e59ed48368dbbbee4e
project_plan | project_plan | 1952 | 4341 |  | Error and Defect Mitigation |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4340 | Yes | No | 4341 | 51d8c4c8fb3341c44770edf672104338e041723ed704e3a67d3c2715b6002ac0
project_plan | project_plan | 1953 | 4342 |  | Load |  | Data Migration Team | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 4341 | Yes | No | 4342 | 85499a0a70e1d1b6966e358cb9279eac46564b5bf6ce9e2d6c993e234581eefc
project_plan | project_plan | 1954 | 4343 |  | Post Load Validation |  | Nevin Varkey | Wed 9/30/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 4342 | Yes | No | 4343 | d9268d7f9c878059c5c41b28975a68d27ac3c7e5ce387c6442eead2c187ce336
project_plan | project_plan | 1955 | 4344 |  | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment |  |  | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4344 | ab2eff09cc26ead7c7edc2e1773b03b41e93cfc4cd660d792c36d3a9557b9dc7
project_plan | project_plan | 1956 | 4345 |  | Load File Staged and Posted "Ready" |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 43,154,329 | Yes | No | 4345 | e45da1b43e92a9cccec62774c5a86a67b71f07b4956e9a5b3757d523d63d7580
project_plan | project_plan | 1957 | 4346 |  | Pre Load Validation |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 4345 | Yes | No | 4346 | d5d7dfe3d142473d9211091e5959f6b89c51c60d79f702f8be758104b0765516
project_plan | project_plan | 1958 | 4347 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4346 | Yes | No | 4347 | d9289cf7281b31e2dbb2c76d9b7804cf965bac35861cb0984b4157eb7222db70
project_plan | project_plan | 1959 | 4348 |  | Error and Defect Mitigation |  | Nevin Varkey | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4347 | Yes | No | 4348 | 8607ba7c4b9ef306330a0530cfe517e5c485bb96526336a48c4396d36f178396
project_plan | project_plan | 1960 | 4349 |  | Load |  | Data Migration Team | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 4348 | Yes | No | 4349 | 37b98b8dc9b3dcf0ad6de96f3767e410043c7bfd6548f05c6a736caa756f35af
project_plan | project_plan | 1961 | 4350 |  | Post Load Validation |  | Nevin Varkey | Wed 9/30/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 4349 | Yes | No | 4350 | afbff2a95ae27df3d17f374a118f2066e8c7134a4ac038b2086801fcef2c8f3e
project_plan | project_plan | 1962 | 4351 |  | PTM_CM31_BOM Conversion |  |  | Tue 9/29/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 4351 | a88ceb952910b3a1735cf10d0a5f65bb3ee6df8cbc70db9079005201a7d0d01b
project_plan | project_plan | 1963 | 4352 |  | Extract File |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4331 | Yes | No | 4352 | bdcea1bd8f8b21525624381523ff437abda39637fec0869f492ce13d9925fe7a
project_plan | project_plan | 1964 | 4353 |  | Pre Load Validation |  | Brad Meseck | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4352 | Yes | No | 4353 | c3105e7f9e24fb9f93deeb5b3debfdf9727292c6792f96d8e8865487e40413a3
project_plan | project_plan | 1965 | 4354 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 4353 | Yes | No | 4354 | 3409165215afed606eb12d400664cbf0ca110496494773f685d4306391951490
project_plan | project_plan | 1966 | 4355 |  | Error and Defect Mitigation |  | Brad Meseck | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 4354 | Yes | No | 4355 | 12df94fa63e120075b50f0c3d7d6d06f917afe1ecb1052bbb78e0d80c4cb1745
project_plan | project_plan | 1967 | 4356 |  | Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 4355 | Yes | No | 4356 | f615a185246acbf53ef04a401b10d0329b43759437b283fc3a1c7b5dec3e8459
project_plan | project_plan | 1968 | 4357 |  | Post Load Validation |  | Brad Meseck | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 4356 | Yes | No | 4357 | 9f5ac7ce7f4b7da8d01b08b5091e0e045acebff55b66f1295e14ff8c1824e5fb
project_plan | project_plan | 1969 | 4358 |  | PTM_CM40_Work Center Conversion |  |  | Tue 9/29/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 4358 | 7f9d32fe29aff31472d49f6302e487021d40019c77d520baec2943f63f7cb94c
project_plan | project_plan | 1970 | 4359 |  | Extract File |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4352 | Yes | No | 4359 | 5fd1bf0368019c798afcbc9eb23e92179bc2fa248c1758b074fa55bb88434086
project_plan | project_plan | 1971 | 4360 |  | Pre Load Validation |  | Brad Meseck | Thu 10/1/26 | Fri 10/2/26 | Fri 4/17/26 | 0% | Future Task | 4357 | Yes | No | 4360 | 6fa6e2cc35817aa9d283211f1d56c5d1970c1d6815b82610a0d79ddfe81e035d
project_plan | project_plan | 1972 | 4361 |  | Simulate Load |  | Data Migration Team | Fri 10/2/26 | Fri 10/2/26 | Fri 4/17/26 | 0% | Future Task | 4360 | Yes | No | 4361 | 8d527fbbdbf28584519788f26b77eb70108c513eeebf72e3bbfbc571ca1d63ed
project_plan | project_plan | 1973 | 4362 |  | Error and Defect Mitigation |  | Brad Meseck | Fri 10/2/26 | Fri 10/2/26 | Fri 4/17/26 | 0% | Future Task | 4361 | Yes | No | 4362 | fb4a83fb52b7b09f5d5cfcb74c8374c2ffc639571212028f03b9c27f0e957dda
project_plan | project_plan | 1974 | 4363 |  | Load |  | Data Migration Team | Fri 10/2/26 | Fri 10/2/26 | Fri 4/17/26 | 0% | Future Task | 4362 | Yes | No | 4363 | 23826e89a2b2798a095c83fec92e4bd166cae1f62fd1fce07a78d82227e7bd3e
project_plan | project_plan | 1975 | 4364 |  | Post Load Validation |  | Brad Meseck | Fri 10/2/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task | 4363 | Yes | No | 4364 | 7ce9331bd4edda32d5c5db7d1704e61837653165bf95ea384d35706015fedc6b
project_plan | project_plan | 1976 | 4365 |  | PTM_CM38_Routing Conversion |  |  | Tue 9/29/26 | Mon 10/5/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 4365 | 6ade7b3b12fab1bbe15d36cc6a1ce7c2a1a4db95240e3c61d5eba84aa41ac4ca
project_plan | project_plan | 1977 | 4366 |  | Extract File |  | Data Migration Team | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4359 | Yes | No | 4366 | a1d07e0cc35ccf5e6442097d238c27a695dce63cdfd82e4a4fc6e6e03c84f636
project_plan | project_plan | 1978 | 4367 |  | Pre Load Validation |  | Brad Meseck | Fri 10/2/26 | Mon 10/5/26 | Mon 4/20/26 | 0% | Future Task | 4364 | Yes | No | 4367 | d8389b71048fb3337090c1022064e960c8bebe693a6d003d7357e83a9864b540
project_plan | project_plan | 1979 | 4368 |  | Simulate Load |  | Data Migration Team | Mon 10/5/26 | Mon 10/5/26 | Mon 4/20/26 | 0% | Future Task | 4367 | Yes | No | 4368 | fd61b678aa1243e40ec8d1527083e560fd4618b265068e91c33bbe4e977904a0
project_plan | project_plan | 1980 | 4369 |  | Error and Defect Mitigation |  | Brad Meseck | Mon 10/5/26 | Mon 10/5/26 | Mon 4/20/26 | 0% | Future Task | 4368SS | Yes | No | 4369 | 6b29b965e09e0467c1a6c9da8946b668f89d1a6c7253f97f795e8a8fd8cba3cd
project_plan | project_plan | 1981 | 4370 |  | Load |  | Data Migration Team | Mon 10/5/26 | Mon 10/5/26 | Mon 4/20/26 | 0% | Future Task | 4369 | Yes | No | 4370 | 73e0630d8e32966db5b7aad4797526ab1cf3e4498079e35abe7f9025451ba706
project_plan | project_plan | 1982 | 4371 |  | Post Load Validation |  | Brad Meseck | Mon 10/5/26 | Mon 10/5/26 | Tue 4/21/26 | 0% | Future Task | 4370 | Yes | No | 4371 | 463c2508ecb4117e28f99ea1bde79ea6fe06f762a90be0cd075dd3fe99f453e6
project_plan | project_plan | 1983 | 4372 |  | PTM_CM36_Production Version Conversion |  |  | Tue 9/29/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 4372 | 8af0dbba28785c395bc0b423dc7c0914001fbff0fafb858271a33c908dead9fa
project_plan | project_plan | 1984 | 4373 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4366 | Yes | No | 4373 | c585629378cee60c639b258f57f974c54fa8284c8f1e1eda339aa9abf1c2e64c
project_plan | project_plan | 1985 | 4374 |  | Pre Load Validation |  | Brad Meseck | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4373 | Yes | No | 4374 | a73b1733cdb8f179bd66406368f358a6900d715de5cc9b47e29e73a6ee50d5dc
project_plan | project_plan | 1986 | 4375 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 4374 | Yes | No | 4375 | 5daffd1a793eefb7a2e7d4db21ecdb4092efa2a36914cb66b2e4c2aec94c251f
project_plan | project_plan | 1987 | 4376 |  | Error and Defect Mitigation |  | Brad Meseck | Wed 9/30/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 4375 | Yes | No | 4376 | 0f39fabf2024bf1c0534437d451fee23ae61105bc732d32c710aa0e61979b9e3
project_plan | project_plan | 1988 | 4377 |  | Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task | 4376 | Yes | No | 4377 | be3e61f2e4f0f6ccf67c994ac1d65bf3270e19f0212db7c4c47faa188b2fd03d
project_plan | project_plan | 1989 | 4378 |  | Post Load Validation |  | Brad Meseck | Wed 9/30/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task | 4377 | Yes | No | 4378 | 82d071fb4d77f8435379b96b25cd85b772a13028ff256dcebf34b6a5929d40e2
project_plan | project_plan | 1990 | 4379 |  | PTM_CM35_Inspection Plan |  |  | Wed 9/30/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 4379 | c5291622167fff9f4604655fde4e2cde7250da4536a958fc5595e3dc0657f39d
project_plan | project_plan | 1991 | 4380 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Wed 9/30/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task | 4378 | Yes | No | 4380 | 2e23f21d901df93cb5dad3c58882db6350e66d0a2f7e4ce3a17058986c44ebe5
project_plan | project_plan | 1992 | 4381 |  | Pre Load Validation |  | Brad Meseck | Wed 9/30/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 4380 | Yes | No | 4381 | c9acc2aa3273ae7bbc0f60f525dd08eb28d7850ceac8ef1d8519414e286479f5
project_plan | project_plan | 1993 | 4382 |  | Simulate Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 4381 | Yes | No | 4382 | d1b78d56f61d20d6ca2ba0eb5a506ea267d8dfe01e354bafc0078ac16d4da7db
project_plan | project_plan | 1994 | 4383 |  | Error and Defect Mitigation |  | Brad Meseck | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 4382 | Yes | No | 4383 | 057f940aee6b7162dfaa12019e360b196db349b265929313cbefbfe63b8242e2
project_plan | project_plan | 1995 | 4384 |  | Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Mon 4/20/26 | 0% | Future Task | 4383 | Yes | No | 4384 | 7c3dae1588195e26fc1ef9b849caad2c6bbae04eedb7f6a7ca0e3d6d8488eb1d
project_plan | project_plan | 1996 | 4385 |  | Post Load Validation |  | Brad Meseck | Thu 10/1/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task | 4384 | Yes | No | 4385 | ed3babe7899cc7f39723d54c254dfe2727b48110508564dda7b55d7ecc89bca1
project_plan | project_plan | 1997 | 4386 |  | PTM_CM48_Equipment_Master_Serial Numbers |  |  | Wed 9/30/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 4386 | c5f008a2a23c7629e949019f1fa014b0b28724bca5d64ea2ab7518402dd0d74d
project_plan | project_plan | 1998 | 4387 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Wed 9/30/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 4380 | Yes | No | 4387 | 00594aebf0b05623747d6cd1da27affbee36568a20edb425d4c1980e0a0ab87d
project_plan | project_plan | 1999 | 4388 |  | Pre Load Validation |  | Brad Meseck | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 4387 | Yes | No | 4388 | 103db1be8e64880773043dc5db261db0945cecce4b12f27b8ab6ead0961bfc1b
project_plan | project_plan | 2000 | 4389 |  | Simulate Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 4388 | Yes | No | 4389 | cc6d44db165f4f63d3f0453c07746e5407b09f2a4f9a31d91f73aa9874ee34b9
project_plan | project_plan | 2001 | 4390 |  | Error and Defect Mitigation |  | Brad Meseck | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 4389 | Yes | No | 4390 | ed08931442269845e23baec43506c7be5c7fc7fb2c5061e9fdece772b2aea6db
project_plan | project_plan | 2002 | 4391 |  | Load |  | Data Migration Team | Thu 10/1/26 | Thu 10/1/26 | Mon 4/20/26 | 0% | Future Task | 4390 | Yes | No | 4391 | 4cacd9c491b75d78cefc95d670cf0b7f4d34b6b9744b4f8345799b78f88cd7c4
project_plan | project_plan | 2003 | 4392 |  | Post Load Validation |  | Brad Meseck | Thu 10/1/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task | 4391 | Yes | No | 4392 | 4efe042da6401b90d7e56f9f69b86bba9752be956024373a28e41ff9827f83dd
project_plan | project_plan | 2004 | 4393 |  | PTM_CM48_Equipment_Master_Service |  |  | Thu 9/24/26 | Fri 10/2/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 4393 | aa96defd73597ed15b7830def3c85e467e7bfd88c6ea7458fd57a601357ef494
project_plan | project_plan | 2005 | 4394 |  | Load File Staged and Posted "Ready" |  | Brad Meseck | Fri 10/2/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task | 4392 | Yes | No | 4394 | 1de3db64719d4e4e1e551b1c63ce52bf6d6bece62c4a7bd3156510757553f814
project_plan | project_plan | 2006 | 4395 |  | Pre Load Validation |  | Brad Meseck | Fri 10/2/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task | 4394 | Yes | No | 4395 | b1b358e25d6798ab601ec667d9fc99a361cd5e3bc62fe861f8eaf91dfca26afb
project_plan | project_plan | 2007 | 4396 |  | Simulate Load |  | Data Migration Team | Fri 10/2/26 | Fri 10/2/26 | Mon 4/20/26 | 0% | Future Task | 4395 | Yes | No | 4396 | 8c7a1ff265e2df9b3e5730e83994c6e539b603c76299116d6a8ad337e98f4165
project_plan | project_plan | 2008 | 4397 |  | Error and Defect Mitigation |  | Brad Meseck | Fri 10/2/26 | Fri 10/2/26 | Tue 4/21/26 | 0% | Future Task | 4396 | Yes | No | 4397 | 41c5cbf7d2ebb1f28281f505780391e4c9d96eacd9490231caed2843b8e212f2
project_plan | project_plan | 2009 | 4398 |  | Load |  | Data Migration Team | Fri 10/2/26 | Fri 10/2/26 | Tue 4/21/26 | 0% | Future Task | 4397 | Yes | No | 4398 | 964250bca1882a53a94716c87a553a5e893c8f930276e4e3b91a34f0c9a7f884
project_plan | project_plan | 2010 | 4399 |  | Post Load Validation |  | Brad Meseck | Thu 9/24/26 | Thu 9/24/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 4399 | 12ddda25af4272ef4cdefc8f39f39beefa688ce0355f13da23915b09bff74b20
project_plan | project_plan | 2011 | 4400 |  | VC_Object Dependencies |  |  | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 4400 | 8d7d9450741c39e2b980ef27228f64029e2ccaf6bf1c5754b30f42005bf76194
project_plan | project_plan | 2012 | 4401 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 4161 | Yes | No | 4401 | c6f456d6959f7e24064f74b4d6168a6881f50af4800c39d706ca6a1f3aa41ba1
project_plan | project_plan | 2013 | 4402 |  | Post Load Validation |  | Eric Heisler | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 4401 | Yes | No | 4402 | 05aea893e5ecdfee43b14c1643e2588bec21e1bb334685da76b9081f0557692d
project_plan | project_plan | 2014 | 4403 |  | VC_Characteristics |  |  | Thu 9/24/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 4403 | 8f99080c24e19dc1b83cfb0e7d35a0a99a02141ae1e579e61e59fc576e43bdbc
project_plan | project_plan | 2015 | 4404 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 4402 | Yes | No | 4404 | d79a68b23f019f0889ab853270c339b2c95ccddfc22eaca5adabf43d954ea7ec
project_plan | project_plan | 2016 | 4405 |  | Post Load Validation |  | Eric Heisler | Thu 9/24/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4404 | Yes | No | 4405 | 254d523b4d914d829225f26e89bb7a781a2871c912aff204ae3226c113e0391c
project_plan | project_plan | 2017 | 4406 |  | VC_Classes |  |  | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task |  | Yes | No | 4406 | 2ed58bf955e92c1a2b4f96f700cd14d4147daa8216f7aad16d5d36f98e93827d
project_plan | project_plan | 2018 | 4407 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4405 | Yes | No | 4407 | 7107300ddfa40644f0e546ceceed1602b42f38e257c260048795c55f7950a104
project_plan | project_plan | 2019 | 4408 |  | Post Load Validation |  | Eric Heisler | Fri 9/25/26 | Fri 9/25/26 | Tue 4/7/26 | 0% | Future Task | 4407 | Yes | No | 4408 | d04a97f31bb11bdb48d2c8eae8becf1afd8d37c7ef4c4e114b37a349d4342cea
project_plan | project_plan | 2020 | 4409 |  | VC_Classification (Class Type 200) |  |  | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4409 | d2c18e746e01302a7bea30024053304b2fb9b1a4f84107cc5455d00f22a46710
project_plan | project_plan | 2021 | 4410 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4329 | Yes | No | 4410 | 8e4c3cba2314a23c4c0f04c995345a7b81b9fbf2da55488e3be2148353aff408
project_plan | project_plan | 2022 | 4411 |  | Post Load Validation |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4410 | Yes | No | 4411 | 4c8d1075c104a6e48ebe3647d95e9270624cc094123f85bdccdb066e4f992d3e
project_plan | project_plan | 2023 | 4412 |  | VC_Dependency Nets |  |  | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4412 | f44a0744252742767a706736eb336db429ce3fb3a4fa490127213ae542e82b3d
project_plan | project_plan | 2024 | 4413 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 43,234,408 | Yes | No | 4413 | 63492f08411fe3618c7519725d89ae8071f41f875466c3f033f531d4f3703d86
project_plan | project_plan | 2025 | 4414 |  | Post Load Validation |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4413 | Yes | No | 4414 | 52154ae8472a49f6bde5123f65c68b5fb049ef7a3a792facad01986a8911c2d5
project_plan | project_plan | 2026 | 4415 |  | VC_Configuration Profiles |  |  | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4415 | 5431644a6089023e256b6b6e4c22ab7d79c0f8af3ae66b8b41149153d19e5bc5
project_plan | project_plan | 2027 | 4416 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4323 | Yes | No | 4416 | ebcbb4b2ec135aeba3d62f7619e2e480c26806fb944c940887c456ea36b35460
project_plan | project_plan | 2028 | 4417 |  | Post Load Validation |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4416 | Yes | No | 4417 | 223c572f426b19c0a74e7224c9172d5fd3225a446aeb5bc9d70c487d841aad08
project_plan | project_plan | 2029 | 4418 |  | VC_Variant Tables |  |  | Tue 9/29/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 4418 | 3d87b31a05371436d4a1af500c95f538d80be98ad6003f2776faa2b7ab0277c0
project_plan | project_plan | 2030 | 4419 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 4417 | Yes | No | 4419 | d1d5925e2bee053a12f9b1147b90c0fa73798e2474c849b48ff8f202c1f460ac
project_plan | project_plan | 2031 | 4420 |  | Post Load Validation |  | Eric Heisler | Wed 9/30/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task | 4419 | Yes | No | 4420 | 5fde0edeeca6fea885ff63811e6902c389c4ac9efd74bef8a63422f93c9a1cf2
project_plan | project_plan | 2032 | 4421 |  | VC_Variant Tables Content |  |  | Wed 9/30/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 4421 | 8cfd2a464400b4f85b77f6919218ff1661a4c9c4f8575de16a5ee514b4864de2
project_plan | project_plan | 2033 | 4422 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Wed 9/30/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task | 4420 | Yes | No | 4422 | 0ddcf9ec26df4b845a5612adcfa0dddf512389786e8d973111fd11022001b116
project_plan | project_plan | 2034 | 4423 |  | Post Load Validation |  | Eric Heisler | Wed 9/30/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 4422 | Yes | No | 4423 | 54cdafc8afa15231343ef0f600f5180bc20c1a82d895ee0c7a68e1188244eb4f
project_plan | project_plan | 2035 | 4424 |  | VC_Characteristic Groups |  |  | Tue 9/29/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 4424 | 48d8a9fb0f4ae747e528f1741ce26f4477758c29bfb118f341992ff4b4df4ff1
project_plan | project_plan | 2036 | 4425 |  | Run ALE Transaction to QS5 from DS4 130 |  | Eric Heisler | Tue 9/29/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 4417 | Yes | No | 4425 | 53c2855450455232cdb0abef11b8c55094af5091fb02672ef11a23795271fbe4
project_plan | project_plan | 2037 | 4426 |  | Post Load Validation |  | Eric Heisler | Thu 10/1/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 4425 | Yes | No | 4426 | 082213299aff0c5df84c537e82a425af5ca07e09768c7b2aafe17e72ae63ab0f
project_plan | project_plan | 2038 | 4427 |  | PTM_CM52_Super_BOM |  |  | Tue 9/29/26 | Mon 10/5/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4427 | d4d01636c209c533399975f439dbeef7750d937facbd4927333efdf906166b40
project_plan | project_plan | 2039 | 4428 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 4329 | Yes | No | 4428 | fc1e593fba096a590aa8335e2a7cc6c3bc6e14084d1bf95b22c40fa421859e76
project_plan | project_plan | 2040 | 4429 |  | Pre Load Validation |  | Eric Heisler | Tue 9/29/26 | Tue 9/29/26 | Wed 4/15/26 | 0% | Future Task | 4428 | Yes | No | 4429 | 40028e8382ab18177757b48096429e3da9c8998cf452592169f1a4e334e2a0d5
project_plan | project_plan | 2041 | 4430 |  | Simulate Load |  | Data Migration Team | Tue 9/29/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 4429 | Yes | No | 4430 | c402ff529a2a254a56974a3920f556f9cc287fec0aa45f0399ab7be597f5758c
project_plan | project_plan | 2042 | 4431 |  | Error and Defect Mitigation |  | Eric Heisler | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 4430 | Yes | No | 4431 | 2a56a1176856ae526e4f4a999edf6ffcdd6ce05543b2f00bdc57952ac1aa463b
project_plan | project_plan | 2043 | 4432 |  | Load |  | Data Migration Team | Fri 10/2/26 | Mon 10/5/26 | Thu 4/16/26 | 0% | Future Task | 4431 | Yes | No | 4432 | 6174b5dba6dff92bfde5b2ab83626d877531ad27b88d49d37ff6f949e80bd551
project_plan | project_plan | 2044 | 4433 |  | Post Load Validation |  | Eric Heisler | Mon 10/5/26 | Mon 10/5/26 | Thu 4/16/26 | 0% | Future Task | 4432 | Yes | No | 4433 | 08fac71ace2e6d2fdd7611487379748eb35439552681e6b2245571b0103cb1d4
project_plan | project_plan | 2045 | 4434 |  | PTM_CM53_Super_Routing |  |  | Mon 10/5/26 | Wed 10/7/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 4434 | eb5e8894d751fc2c0be17490944aaa80c8e6a1b5151bb64481853292ed0f8c45
project_plan | project_plan | 2046 | 4435 |  | Load File Staged and Posted "Ready" |  | Eric Heisler | Mon 10/5/26 | Mon 10/5/26 | Thu 4/16/26 | 0% | Future Task | 4433 | Yes | No | 4435 | 759f455f28b253476775a3f4e0cdeb15b9077a8a3e80819a4988a6305f8d9835
project_plan | project_plan | 2047 | 4436 |  | Pre Load Validation |  | Eric Heisler | Mon 10/5/26 | Mon 10/5/26 | Fri 4/17/26 | 0% | Future Task | 4435 | Yes | No | 4436 | 02422fa7490642c4d7f1d6b6d292a7b6fd987342aa83cd8262119858c86bd789
project_plan | project_plan | 2048 | 4437 |  | Simulate Load |  | Data Migration Team | Mon 10/5/26 | Tue 10/6/26 | Fri 4/17/26 | 0% | Future Task | 4436 | Yes | No | 4437 | 84b20d5057f7642c69afac26535fd8b6a45843e7d40674e8cb0ee623ee30f2e8
project_plan | project_plan | 2049 | 4438 |  | Error and Defect Mitigation |  | Eric Heisler | Tue 10/6/26 | Tue 10/6/26 | Fri 4/17/26 | 0% | Future Task | 4437 | Yes | No | 4438 | 793af20ac2972932db4440dbc3856c0aaad98e5c1a1c352bafda5c9609c07cc1
project_plan | project_plan | 2050 | 4439 |  | Load |  | Data Migration Team | Tue 10/6/26 | Wed 10/7/26 | Fri 4/17/26 | 0% | Future Task | 4438 | Yes | No | 4439 | 00243dee71d7fcf49142d2679d04055ffd5772eb17ec148dba14ce742f549018
project_plan | project_plan | 2051 | 4440 |  | Post Load Validation |  | Eric Heisler | Wed 10/7/26 | Wed 10/7/26 | Mon 4/20/26 | 0% | Future Task | 4439 | Yes | No | 4440 | ba4bb8f6dcce2f449fe2a7cafad3c685dfbd48fcc67d179327ccfaca22ee3bc6
project_plan | project_plan | 2052 | 4441 |  | VC_VK30 Pricing Variant |  |  | Wed 10/7/26 | Wed 10/7/26 | Mon 4/20/26 | 0% | Future Task |  | Yes | No | 4441 | 684e6467752997ebf3d01717635363cf8e796178722b3848f95feb779250ab0d
project_plan | project_plan | 2053 | 4442 |  | Manual File Staged and Posted "Ready" |  | Eric Heisler | Wed 10/7/26 | Wed 10/7/26 | Fri 4/17/26 | 0% | Future Task | 4439 | Yes | No | 4442 | 80cbacd8374042189f5ce99df67ac01fb4ba325a5eb2b5b922f440f773ab3267
project_plan | project_plan | 2054 | 4443 |  | Load |  | Eric Heisler | Wed 10/7/26 | Wed 10/7/26 | Fri 4/17/26 | 0% | Future Task | 4442 | Yes | No | 4443 | 53f21267a5e28fc1306b813c44eb8886e62ba6bd473295d67754ff3eed329b34
project_plan | project_plan | 2055 | 4444 |  | Post Load Validation |  | Eric Heisler | Wed 10/7/26 | Wed 10/7/26 | Mon 4/20/26 | 0% | Future Task | 4443 | Yes | No | 4444 | 350cb3417b1e7ddad7c141bce02eaea7e00c930fc3a6a60fc8959cd2996e5ad8
project_plan | project_plan | 2056 | 4445 |  | OTC_CM22_Pricing_Condition |  |  | Wed 10/7/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 4445 | 16099864f4a385fdcb0b50a8e7ddb02b1fd5d2b871635fcf8b428a3e31cca578
project_plan | project_plan | 2057 | 4446 |  | Manual File Staged and Posted "Ready" |  | Ric Haraida | Wed 10/7/26 | Wed 10/7/26 | Mon 4/20/26 | 0% | Future Task | 4444 | Yes | No | 4446 | 61d37256d55cbdfbe2078163dc37fd0fa8caffcbe7670c58398402fd4d6f3a78
project_plan | project_plan | 2058 | 4447 |  | Load |  | Ric Haraida | Wed 10/7/26 | Thu 10/8/26 | Mon 4/20/26 | 0% | Future Task | 4446 | Yes | No | 4447 | 608893f87b29be211b98f1468f96f7d3ffaddd56cbc206412d864a289bde7189
project_plan | project_plan | 2059 | 4448 |  | Post Load Validation |  | Ric Haraida,Kim Kolesar | Thu 10/8/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task | 4447 | Yes | No | 4448 | cf79ba9747c81916b01f0310c843e44f73c51364ed6b91224d4c63602faa0bb2
project_plan | project_plan | 2060 | 4449 |  | OTC_CM21_CMIR |  |  | Thu 10/8/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | No | 4449 | ba4821f361697683ef97fb5f673e092da3456891c925b9d4aa45f9d3d2b5959d
project_plan | project_plan | 2061 | 4450 |  | Load File Staged and Posted "Ready" |  | Ric Haraida | Thu 10/8/26 | Thu 10/8/26 | Mon 4/20/26 | 0% | Future Task | 44,474,458 | Yes | No | 4450 | da93b885b5b8e7447ba8d33f6cf6e134ec03595789dd52be661b773fc81f165a
project_plan | project_plan | 2062 | 4451 |  | Pre Load Validation |  | Ric Haraida | Thu 10/8/26 | Thu 10/8/26 | Mon 4/20/26 | 0% | Future Task | 4450 | Yes | No | 4451 | 00d8e4285f48c7a9c570eb533b53ce4c4c8063677292a288545e2e613cd722a5
project_plan | project_plan | 2063 | 4452 |  | Simulate Load |  | Data Migration Team | Thu 10/8/26 | Thu 10/8/26 | Mon 4/20/26 | 0% | Future Task | 4451 | Yes | Yes | 4452 | c76a613dbc585b6ec5f9d86d1bf733f9d86ef7799c2fe11ee96a03d0e94345f9
project_plan | project_plan | 2064 | 4453 |  | Error and Defect Mitigation |  | Ric Haraida | Thu 10/8/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task | 4452 | Yes | Yes | 4453 | b5df5292df28f42894e78a0e3f39baacbd13dc2d0c552fd282c87ff2ad0dd70d
project_plan | project_plan | 2065 | 4454 |  | Load |  | Data Migration Team | Thu 10/8/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task | 4453 | Yes | Yes | 4454 | 97f0ce89b5173a9bbb57bf8ddd902ce5b56918520729902548a0bdb4824e7414
project_plan | project_plan | 2066 | 4455 |  | Post Load Validation |  | Ric Haraida | Thu 10/8/26 | Thu 10/8/26 | Tue 4/21/26 | 0% | Future Task | 4454 | Yes | No | 4455 | 3fbfe26f42bfb88152946e1e7e7cd651caba5a4a1fb411bdb2f6e78269f44cdc
project_plan | project_plan | 2067 | 4456 |  | PTP_CM29_Source_List |  |  | Fri 9/25/26 | Mon 10/5/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 4456 | d1b0e2b0ae4778dbb4cb138831fa149a9e60addb8a313485beec687e23905b9f
project_plan | project_plan | 2068 | 4457 |  | Manual File Staged and Posted "Ready" |  | Nevin Varkey | Fri 9/25/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 43,004,307 | Yes | No | 4457 | a2a56bdc8d4079e98795c249676f975d972b0d00a9a29deda937a981bd22cfad
project_plan | project_plan | 2069 | 4458 |  | Load |  | Nevin Varkey | Fri 10/2/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task | 4276 | Yes | No | 4458 | 17faed963dd89cb49e550466d5b34636029a37283cd564a3964b285726bcb284
project_plan | project_plan | 2070 | 4459 |  | Post Load Validation |  | Nevin Varkey | Fri 10/2/26 | Mon 10/5/26 | Mon 4/13/26 | 0% | Future Task | 4458 | Yes | No | 4459 | bfe19c04a2a319706371306a87c07ff41d8e52938a39b371d3391e9877007ca3
project_plan | project_plan | 2071 | 4460 |  | RTR_CM11_Asset_Master |  |  | Thu 9/24/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 4460 | 922d914057576f1be06d7bc5d18ef548cabd4a160a5913e99b36635ad88828e6
project_plan | project_plan | 2072 | 4461 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 4461 | 18ee8519b1de77ea8d8165f0d26dac8daaaabea97763558310b1ab01cf04e344
project_plan | project_plan | 2073 | 4462 |  | Pre Load Validation |  | Kasey Hughes,Femi Oguntala | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 4461 | Yes | No | 4462 | 1e5587e475ee73c966b9dcc3afbaf9c349f302bf4b9fd5c24295b3eb421c34ef
project_plan | project_plan | 2074 | 4463 |  | Simulate Load |  | Data Migration Team | Thu 9/24/26 | Wed 9/30/26 | Fri 4/10/26 | 0% | Future Task | 4462 | Yes | No | 4463 | 635ff70e62d6eff5c52ed66d8e63b2ec197099515342b8b1582e572ee73e6d8f
project_plan | project_plan | 2075 | 4464 |  | Error and Defect Mitigation |  | Kasey Hughes | Wed 9/30/26 | Fri 10/2/26 | Fri 4/10/26 | 0% | Future Task | 4463 | Yes | No | 4464 | d19560a987f6f543a649ced8f23cd4d98aad84d437c97abffad2531c66b5b6ce
project_plan | project_plan | 2076 | 4465 |  | Load |  | Data Migration Team | Fri 10/2/26 | Fri 10/2/26 | Fri 4/10/26 | 0% | Future Task | 4464 | Yes | No | 4465 | 5246f3afc77f8fcbacd7e9c7d6aa00e79ba314d17c4feca27db9d1693d3b0f1a
project_plan | project_plan | 2077 | 4466 |  | Post Load Validation |  | Kasey Hughes | Fri 10/2/26 | Fri 10/2/26 | Mon 4/13/26 | 0% | Future Task | 4465 | Yes | No | 4466 | 2079210c05977157df0ab8a800cc30cf60a04e8c04a7ce227822ce4836ed8aa6
project_plan | project_plan | 2078 | 4467 |  | PTM_CM50_Material Class |  |  | Tue 9/29/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4467 | 7ce67cc939cbe39fb7aced9c032059ee58ee0d74024b70f7bf87956bb157c60d
project_plan | project_plan | 2079 | 4468 |  | Manual File Staged and Posted "Ready" |  | Sam | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4373 | Yes | No | 4468 | 7145a2ad376bf4e1d84ad1470ce1005e860fac232ae8d4f6fb6f84242a35de48
project_plan | project_plan | 2080 | 4469 |  | Load |  | Brad Meseck | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4468 | Yes | No | 4469 | 219365b1536027e77dd32aaccafe145b52b5897401b17267ac57344320b6a56f
project_plan | project_plan | 2081 | 4470 |  | Post Load Validation |  | Brad | Tue 9/29/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 4469 | Yes | No | 4470 | f5efb7465f8c7c63f01b945258f2e245939a8aed8a8131f9322ea6e9bd98a8a4
project_plan | project_plan | 2082 | 4471 |  | PTM_CM55_Class assignment to materials |  |  | Tue 9/29/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 4471 | 3bcc45165ce1ba22625d149418fa622025c0a553d5de4573c4967eecfd4338ed
project_plan | project_plan | 2083 | 4472 |  | Load File Staged and Posted "Ready" |  | Sam | Tue 9/29/26 | Tue 9/29/26 | Thu 4/16/26 | 0% | Future Task | 4468 | Yes | No | 4472 | 5b3a96af5d2a8d2f794f7bc215172bb51c11e71b811de62bf9af75ec41b0a57f
project_plan | project_plan | 2084 | 4473 |  | Pre Load Validation |  | Brad Meseck | Tue 9/29/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 4472 | Yes | No | 4473 | 4bede2e12c33abbe503baab2eb761cf0d3c72e80e176509f9255d8f641c96cef
project_plan | project_plan | 2085 | 4474 |  | Simulate Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 4473 | Yes | No | 4474 | 787f2a51068d17dd93e6daf3e4a5c298e7f7b0fe879e194b9062818a682c17da
project_plan | project_plan | 2086 | 4475 |  | Error and Defect Mitigation |  | Brad Meseck | Wed 9/30/26 | Wed 9/30/26 | Thu 4/16/26 | 0% | Future Task | 4474 | Yes | No | 4475 | 1abec159fb302d2bc8428fd9d224fa6d97c3b38b9c8bcbe3b4cc3c228072e47c
project_plan | project_plan | 2087 | 4476 |  | Load |  | Data Migration Team | Wed 9/30/26 | Wed 9/30/26 | Fri 4/17/26 | 0% | Future Task | 4475 | Yes | No | 4476 | fc228950d945527f438a83b1e4e15433f7042e4c22101aee3fdde9daf3cebf65
project_plan | project_plan | 2088 | 4477 |  | Post Load Validation |  | Brad Meseck | Wed 9/30/26 | Thu 10/1/26 | Fri 4/17/26 | 0% | Future Task | 4476 | Yes | No | 4477 | bf77eb27f814ef8488b379641a58afde49ec5bd186a708ea7914a3d21a510665
project_plan | project_plan | 2089 | 4478 |  | GTS - Material initial load from S4 (Run Interface) |  |  | Tue 9/29/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4478 | feb1a1351ee57d9b2722cbc1eb5ce499abe3fa6ae833bf8a97267696163dcd6e
project_plan | project_plan | 2090 | 4479 |  | Run material interface to GTS |  | James Van Riper | Tue 9/29/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 4347 | Yes | No | 4479 | 8c68afc55fd7b51cca1b124fc7b11afef33fc78145592dc9689e76c30fa8a0e8
project_plan | project_plan | 2091 | 4480 |  | Post Load Validation |  | James Van Riper | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 4479 | Yes | No | 4480 | 622951c7bb0946209903ea7dc6e0279c609852b15828b7e37d241c483b2d1507
project_plan | project_plan | 2092 | 4481 |  | GTS - Customers initial load from S4 (Run Interface) |  |  | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 4481 | 8e9caa3b649832245d9adac460a8c16c4eb3e9dfb5c1dcd0436b7cae23aa7540
project_plan | project_plan | 2093 | 4482 |  | Run material interface to GTS |  | James Van Riper | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task |  | Yes | No | 4482 | 15870d61eb271b083c1538b70c117a2fee0dbd965e655d8863ee8812cad64709
project_plan | project_plan | 2094 | 4483 |  | Post Load Validation |  | James Van Riper | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 4482 | Yes | No | 4483 | ed6a1a50f5c7635e3d8bf45efb8b5bbf63e75cecdbde317e2a77bcc1729c367c
project_plan | project_plan | 2095 | 4484 |  | GTS - Vendors initial load from S4 (Run Interface) |  |  | Thu 9/24/26 | Fri 9/25/26 | Wed 4/15/26 | 0% | Future Task |  | Yes | No | 4484 | 71d73e429d758997c74ab0421a862e96b8c3a992e514805dfc0b06b794a84a5d
project_plan | project_plan | 2096 | 4485 |  | Run material interface to GTS |  | James Van Riper | Thu 9/24/26 | Fri 9/25/26 | Wed 4/15/26 | 0% | Future Task | 4290 | Yes | No | 4485 | 5a5906b452be3a764860568c92bdaae2245fe9f21814b0c2eb2d970eaac98d2a
project_plan | project_plan | 2097 | 4486 |  | Post Load Validation |  | James Van Riper | Fri 9/25/26 | Fri 9/25/26 | Wed 4/15/26 | 0% | Future Task | 4485 | Yes | No | 4486 | 8cae38b74a46bec7e475de057676f123119fa9343ecdd48ce2bf109b57210e50
project_plan | project_plan | 2098 | 4487 |  | GTS - ECCN - Create |  |  | Thu 9/24/26 | Fri 9/25/26 | Mon 4/13/26 | 0% | Future Task |  | Yes | No | 4487 | e20b973f6601148a5f512ba35fe398d9e6f1e05e48ce1159d888ff292fcd4ef2
project_plan | project_plan | 2099 | 4488 |  | Load Descartes XML File |  | James Van Riper | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 4161 | Yes | No | 4488 | 02b8271bf2ce44dde1cb1ad6fe7c15334e0c0bfe4f00534f0a88b5468de6d52a
project_plan | project_plan | 2100 | 4489 |  | Post Load Validation |  | James Van Riper | Fri 9/25/26 | Fri 9/25/26 | Mon 4/13/26 | 0% | Future Task | 4485 | Yes | No | 4489 | 4408545ec6d7cb659e518fcd083c10619673c703183d92e51b34249d29459d95
project_plan | project_plan | 2101 | 4490 |  | GTS - ECCN - Assign |  |  | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4490 | b9799f9d9792a18a2e052bd928cfce54359a35c474077184b62158f63e001c22
project_plan | project_plan | 2102 | 4491 |  | Load Descartes XML File |  | James Van Riper | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 4480 | Yes | No | 4491 | 68665d8f2198e2d044b38514f7c03a68c89fcd20454fd0d6d88fb5dfde29ee12
project_plan | project_plan | 2103 | 4492 |  | Post Load Validation |  | James Van Riper | Thu 10/1/26 | Thu 10/1/26 | Thu 4/16/26 | 0% | Future Task | 4491 | Yes | No | 4492 | b9a96738283e4870e006c7369e65e5303b451ad0160843cce4939c46ee60c2ae
project_plan | project_plan | 2104 | 4493 |  | GTS - HTS - Create |  |  | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task |  | Yes | No | 4493 | 2977c2c210e81005c7fd0f8fb87068e12f7d26d3af9164ba9934626ae0d7fe84
project_plan | project_plan | 2105 | 4494 |  | Load Descartes XML File |  | James Van Riper | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 4161 | Yes | No | 4494 | 6a7ca4ca39976194ae9266a2d97ebad6b3a2ea8e67d5115d42f1f9c826d0f07e
project_plan | project_plan | 2106 | 4495 |  | Post Load Validation |  | James Van Riper | Thu 9/24/26 | Thu 9/24/26 | Mon 4/6/26 | 0% | Future Task | 4494 | Yes | No | 4495 | fa6fa5b427c3746b58203d083b236156cb60ea1df11f01112dfca2743eadef3d
project_plan | project_plan | 2107 | 4496 |  | GTS - HTS - Assign |  |  | Thu 10/1/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4496 | dc9827b0e505b35f801f41a3df8b190572bd76e06b80eb1c43319d548ae14be7
project_plan | project_plan | 2108 | 4497 |  | Load Descartes XML File |  | James Van Riper | Thu 10/1/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 4492 | Yes | No | 4497 | a58b3e5b0632ec5e99adfbd6413e94be40a0290d17fd26e6db211667017c1995
project_plan | project_plan | 2109 | 4498 |  | Post Load Validation |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 4497 | Yes | No | 4498 | 36632f56a855d9fbe35789f0e7db3b41fcf315cfeff0599f581f3053ded1930e
project_plan | project_plan | 2110 | 4499 |  | GTS - License - Create |  |  | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4499 | b6d0291abc290a60e9df857bf680ef8be2747a0d187a2a50e8312045177d26de
project_plan | project_plan | 2111 | 4500 |  | Load Descartes XML File |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 44,974,513 | Yes | No | 4500 | db0762be83385c413fe1accf47773d3d51f601ed2d38a39f6d6ae45f74d6c5e3
project_plan | project_plan | 2112 | 4501 |  | Post Load Validation |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 4500 | Yes | No | 4501 | d129ee4de1c05abfc46ae33d68bcab421ef632f61b15110e545ae2eae92d2b74
project_plan | project_plan | 2113 | 4502 |  | Commodity Code/Tarif |  |  | Fri 10/2/26 | Tue 10/6/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4502 | fe1c51b53a81904337eac881da78986d73135ba6bdd199097f9f3c9cd8d7df51
project_plan | project_plan | 2114 | 4503 |  | Load |  | James Van Riper | Fri 10/2/26 | Tue 10/6/26 | Thu 4/16/26 | 0% | Future Task | 4498 | Yes | No | 4503 | 0bd136142985edd54d342f63745cd1ac85ece2a48ba68a089bc51fa2cb26efdf
project_plan | project_plan | 2115 | 4504 |  | Post Load Validation |  | James Van Riper | Tue 10/6/26 | Tue 10/6/26 | Thu 4/16/26 | 0% | Future Task | 4503 | Yes | No | 4504 | acf1c58a701dae1c6d6112db3c3bb5a3609223292b2f7f06cb71bf03eeb9ed52
project_plan | project_plan | 2116 | 4505 |  | SPL Master File |  |  | Fri 10/2/26 | Fri 10/2/26 | Thu 3/13/25 | 0% | Future Task |  | Yes | No | 4505 | 1c4c4e265ec8b249698cdbc51a1c453f0e770823e0c024c2d5c4c0463457b6f9
project_plan | project_plan | 2117 | 4506 |  | Load |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 3/13/25 | 0% | Future Task | 4497 | Yes | No | 4506 | eefa0ef59daa65dc0b12281f4fc674931430a1eb7c9afbe6d768a8a13335ada8
project_plan | project_plan | 2118 | 4507 |  | Post Load Validation |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 3/13/25 | 0% | Future Task | 4506 | Yes | No | 4507 | 4a376e5eb9c0530631a6c2ba6d328807352aa021dd12ae404cfb551b287ab041
project_plan | project_plan | 2119 | 4508 |  | Initialize Embargo situation |  |  | Fri 9/25/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task |  | Yes | No | 4508 | a50e55a3da0b83ee6015956de90ea1d071bcd6ebbcdcd1d87044969ed10b944a
project_plan | project_plan | 2120 | 4509 |  | Run report /SAPSLL/EMB_CNTRY_INIT |  | James Van Riper | Fri 9/25/26 | Fri 9/25/26 | Mon 4/13/26 | 0% | Future Task | 4489 | Yes | No | 4509 | 8279094db3b8e64ee5ae02e41917906ead7ce5a2c2d59f70e0e9852210524fde
project_plan | project_plan | 2121 | 4510 |  | Set Embargo situations |  | James Van Riper | Fri 9/25/26 | Fri 9/25/26 | Mon 4/13/26 | 0% | Future Task | 4509 | Yes | No | 4510 | 6897bb284cb1adf4c3eea637cc72b758e01bdc7e3a6665f32056857ee1af5c18
project_plan | project_plan | 2122 | 4511 |  | Post Load Validation |  | James Van Riper | Fri 9/25/26 | Fri 9/25/26 | Tue 4/14/26 | 0% | Future Task | 4510 | Yes | No | 4511 | d757fb92f19df66eb50ae5a93186cb911b428bd2b03595b3a4d96da199622797
project_plan | project_plan | 2123 | 4512 |  | GTS - SPL (Sanctioned party list) |  |  | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task |  | Yes | No | 4512 | 09da055e5026ce53d2f02016b98a7c569702a2659c34e013f9a9ca102f05c2b7
project_plan | project_plan | 2124 | 4513 |  | Load Descartes XML File |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 4498 | Yes | No | 4513 | e35280f64bfcbfe4d074a5a45716d0040453a48e34ca08e792856201dcd9b7be
project_plan | project_plan | 2125 | 4514 |  | Post Load Validation |  | James Van Riper | Fri 10/2/26 | Fri 10/2/26 | Thu 4/16/26 | 0% | Future Task | 4513 | Yes | No | 4514 | 675eb6edb95f9b0cabde0e2aea606134bc50fc548d71d87a68c7796108193ba3
project_plan | project_plan | 2126 | 4515 |  | RTR_CM17_Project Definition / Builder |  |  | Thu 9/24/26 | Fri 9/25/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 4515 | 58944dfefc965aba0a1b3b4d008ccf581ca7dc3bccecd49c2ecb3c81e62b4403
project_plan | project_plan | 2127 | 4516 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 4461 | Yes | No | 4516 | 3ae8899d63de9298ea62636910d012ace646ac107df481d1673c8179c4c0d0cb
project_plan | project_plan | 2128 | 4517 |  | Pre Load Validation |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 4516 | Yes | No | 4517 | 8f2c97ca0e7745ef5d25644961a1236d936782a3d4889196261da68554284bdc
project_plan | project_plan | 2129 | 4518 |  | Simulate Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Thu 4/16/26 | 0% | Future Task | 4517 | Yes | No | 4518 | 3dde006a1e0c89139cc64014c5ca54374fd60de24c1201007c9a2f9dbe4abfd1
project_plan | project_plan | 2130 | 4519 |  | Error and Defect Mitigation |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/17/26 | 0% | Future Task | 4518 | Yes | No | 4519 | d3e71d649a01283dc7672fd0d566fb95f0a21957d4ed43d09429daae5a42e804
project_plan | project_plan | 2131 | 4520 |  | Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Fri 4/17/26 | 0% | Future Task | 4519 | Yes | No | 4520 | 02cc7b36e60565ad055fa729c2cc28ee2cc37cf8cf9c2c2f7d675df729f9f9c5
project_plan | project_plan | 2132 | 4521 |  | Post Load Validation |  | Kasey Hughes | Thu 9/24/26 | Fri 9/25/26 | Fri 4/17/26 | 0% | Future Task | 4520 | Yes | No | 4521 | 4b8231131a82307dbb61999d8fc880cf8a6871f62c688d1eafda925032384a7b
project_plan | project_plan | 2133 | 4522 |  | RTR_CM18_WBS Element |  |  | Thu 9/24/26 | Fri 9/25/26 | Fri 4/17/26 | 0% | Future Task |  | Yes | No | 4522 | 0fd738c2b8600ca79c2f1524fc30887d5eee7568f5e3ca5b29084a7859837e94
project_plan | project_plan | 2134 | 4523 |  | Load File Staged and Posted "Ready" |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 4516 | Yes | No | 4523 | 9cb6054e8e9a701ad1a12b1dce71169f833bb9bffed514e03e1e65d369bd96a0
project_plan | project_plan | 2135 | 4524 |  | Pre Load Validation |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/10/26 | 0% | Future Task | 4523 | Yes | No | 4524 | f83d93acbc601b5b87acf9b9c60a8adae9a09921655cecc705cc835abb31d6d2
project_plan | project_plan | 2136 | 4525 |  | Simulate Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Thu 4/16/26 | 0% | Future Task | 4524 | Yes | No | 4525 | b738865136afb817a10087fec834d988da9ac9f088a6e6181f4edc90fd0306e2
project_plan | project_plan | 2137 | 4526 |  | Error and Defect Mitigation |  | Kasey Hughes | Thu 9/24/26 | Thu 9/24/26 | Fri 4/17/26 | 0% | Future Task | 4525 | Yes | No | 4526 | 8308329593f870e8e80559886667a3a999abdf51420933dadc680511ce26a4d8
project_plan | project_plan | 2138 | 4527 |  | Load |  | Data Migration Team | Thu 9/24/26 | Thu 9/24/26 | Fri 4/17/26 | 0% | Future Task | 4526 | Yes | No | 4527 | 9ea6695e1ebdfae118a98208280bafa3d9fe29b4d367fdcde13596b1f4e9e44a
project_plan | project_plan | 2139 | 4528 |  | Post Load Validation |  | Kasey Hughes | Thu 9/24/26 | Fri 9/25/26 | Fri 4/17/26 | 0% | Future Task | 4527 | Yes | No | 4528 | 6b354b0a74e4df48396235e1b1c49686336868a76fa915191759353ced4a2eee
project_plan | project_plan | 2140 | 4529 |  | UAT Mock Data Loads Complete |  | Mark George | Thu 9/24/26 | Thu 9/24/26 | Tue 4/21/26 | 0% | Future Task |  | Yes | Yes | 4529 | 8358b87965ca6212e3123013503159731a106acdfe0fd616704a619ae7088f12
project_plan | project_plan | 2141 | 4530 |  | PROD Master Data Loads Complete |  |  | Thu 10/1/26 | Thu 10/1/26 |  | 0% | Future Task | 4162 | Yes | Yes | 4530 | 31f8f3e497bc26d9ccb097f42b412554ae58f5f126350ec6ede212875e3e2db6
project_plan | project_plan | 2142 | 4531 |  | Mock Transactional Data |  |  | Thu 10/1/26 | Mon 10/5/26 |  | 0% | Future Task | 4530 | Yes | No | 4531 | 286a9c407fcd9b9b17cc50db726f74337cb85f91c91a54dcf41db57dfcaa40db
project_plan | project_plan | 2143 | 4532 |  | Inventory |  |  | Thu 10/1/26 | Thu 10/1/26 |  | 0% | Future Task | 4530SS,2947SS | Yes | No | 4532 | 5f3e54dbb65bd103f63b0d8907378662a12893bc77e021e485ee9b6bebd5715b
project_plan | project_plan | 2144 | 4533 |  | Open AR |  |  | Thu 10/1/26 | Fri 10/2/26 |  | 0% | Future Task | 4532 | Yes | No | 4533 | a3a1c0f22d24c19a4aecaa9babd482fe5a3bd5777f40638985ab60a25bf8c4e8
project_plan | project_plan | 2145 | 4534 |  | Open AP |  |  | Fri 10/2/26 | Fri 10/2/26 |  | 0% | Future Task | 4533 | Yes | No | 4534 | 4818dd79b52ce5982f2ed2da7d9e41bafc3736ed284a2a6c59d1cf65f9f459d1
project_plan | project_plan | 2146 | 4535 |  | Bank and Cash |  |  | Fri 10/2/26 | Mon 10/5/26 |  | 0% | Future Task | 4534 | Yes | No | 4535 | 73742bd6e3c21bdad670b3d1ad1aff8574d24e3205e9a232a2db99d823de0bb6
project_plan | project_plan | 2147 | 4536 |  | Open Purchase Orders(Manual) |  |  | Thu 10/1/26 | Fri 10/2/26 |  | 0% | Future Task | 4532 | Yes | No | 4536 | de804f1ae834ff882fa277beda53c4aff52cdab18c67146e2c4b721c73ffdeb1
project_plan | project_plan | 2148 | 4537 |  | Open Sales Orders(Manual) |  |  | Thu 10/1/26 | Fri 10/2/26 |  | 0% | Future Task | 4532 | Yes | No | 4537 | c7ef7f295f3640acb018d02e4360bb7ab4ab4a669469be6ef0486e5c7613724f
project_plan | project_plan | 2149 | 4538 |  | Service Orders(Manual) |  |  | Thu 10/1/26 | Fri 10/2/26 |  | 0% | Future Task | 4532 | Yes | No | 4538 | 31c345b684f1fa6a86ce2817624f182362b5a1b6a6e9b2acbdd1c8f25ebd8f20
project_plan | project_plan | 2150 | 4539 |  | Open Production Orders(Manual) |  |  | Thu 10/1/26 | Fri 10/2/26 |  | 0% | Future Task | 4532 | Yes | No | 4539 | 83f0e9cee463769042b6acfaed9f73a61b1bdc56e36d6f33a9c6e48dbfa49610
project_plan | project_plan | 2151 | 4540 |  | PRO Data Loads Complete |  | Mark George | Mon 10/5/26 | Mon 10/5/26 | Tue 4/21/26 | 0% | Future Task | 4531 | Yes | Yes | 4540 | 93569018ab7700f85de7bf52f40925bac753b1b353eed1745ceb38fd8dc6a848
project_plan | project_plan | 2152 | 681 |  | Solution Readniess |  |  | Thu 4/16/26 | Fri 10/16/26 | Thu 9/3/26 | 3% | On Schedule |  | No | No | 681 | 728dccfe30a80bce1e4d030dce20017e21ef687793714cddab98f41528969781
project_plan | project_plan | 2153 | 843 |  | Business Process Design Documentation |  |  | Mon 5/4/26 | Fri 5/29/26 | Fri 5/22/26 | 4% | On Schedule |  | No | No | 843 | 03cba6708622fb119df82f286ef717f869f46e9582b29091ef552dac9eafa871
project_plan | project_plan | 2154 | 844 |  | FICO |  |  | Mon 5/4/26 | Fri 5/29/26 | Fri 5/22/26 | 3% | On Schedule |  | No | No | 844 | a3a4560fd4651e74bb5e42d677689b4048e109ae7ff95e5295d29aef6e50d818
project_plan | project_plan | 2155 | 845 |  | Order to Cash |  |  | Mon 5/4/26 | Fri 5/29/26 | Fri 5/22/26 | 4% | On Schedule |  | No | No | 845 | 298feba12540ff95dea52c22b54f9698e114f5b9b4b86741220303a43e243b9f
project_plan | project_plan | 2156 | 846 |  | Procure to Pay |  |  | Mon 5/4/26 | Fri 5/29/26 | Fri 5/22/26 | 4% | On Schedule |  | No | No | 846 | d6443af8db19e97631a743adfa45645345ca352d8756c3b7c887e0626add1c19
project_plan | project_plan | 2157 | 847 |  | Plan to Make |  |  | Mon 5/4/26 | Fri 5/29/26 | Fri 5/22/26 | 5% | On Schedule |  | No | No | 847 | 53b7bf842319602b21f1883705f4f8aaee926af188008921dde82bda0413dcfc
project_plan | project_plan | 2158 | 835 |  | Development RICEFW |  |  | Mon 5/4/26 | Fri 8/14/26 | Fri 5/22/26 | 0% | On Schedule |  | No | No | 835 | 5a38d4406a5dc7775964ebd52dd857110dfe5cda99f8d436bbe99debc1281211
project_plan | project_plan | 2159 | 836 |  | Reports |  |  | Mon 5/4/26 | Fri 8/14/26 | Fri 5/22/26 | 0% | On Schedule |  | No | No | 836 | 76042e10f2973cb884ba016247d27999979fa195bc3322bad788e7766a166241
project_plan | project_plan | 2160 | 837 |  | Interfaces |  |  | Mon 5/4/26 | Fri 8/14/26 | Fri 5/22/26 | 0% | On Schedule |  | No | No | 837 | 40a7dae2f93d73d3c8fc5f6daadef745c18fc2514ab320d12257eecc27f0d632
project_plan | project_plan | 2161 | 838 |  | Enhanchments |  |  | Mon 5/4/26 | Fri 8/14/26 | Fri 5/22/26 | 0% | On Schedule |  | No | No | 838 | c1c90cfd9db43bf372f5768aa89af0e40d7f3bc406182e834cea312e983d0237
project_plan | project_plan | 2162 | 839 |  | Workflow |  |  | Mon 5/4/26 | Fri 8/14/26 | Fri 5/22/26 | 0% | On Schedule |  | No | No | 839 | 8964716f12e7bd34890d48f251bb14b1b512c93436883284d618f197cdd72ca7
project_plan | project_plan | 2163 | 840 |  | Forms |  |  | Fri 8/14/26 | Fri 8/14/26 | Fri 5/22/26 | 0% | Future Task |  | No | Yes | 840 | cf93524c19463734e123e5600832cacd890c9c3488e340979b6c8e9bb947d741
project_plan | project_plan | 2164 | 18 |  | Testing Cycles |  |  | Thu 4/16/26 | Fri 10/16/26 | Thu 9/3/26 | 13% | On Schedule |  | No | No | 18 | 1025116bad01eb721b1db382290b9cf99497e54127e93517f13c652dc743ee4a
project_plan | project_plan | 2165 | 932 |  | Test Readiness Review (TRR) - ITC 1 |  |  | Thu 4/16/26 | Fri 5/1/26 | Thu 4/16/26 | 25% | Late | 1170 | Yes | No | 932 | db8d20d9dd6b284f4b5ff0d2e6d0944aede53020274292012c5af6247659aed5
project_plan | project_plan | 2166 | 2799 |  | Test Readiness Review (TRR) - ITC 2 |  |  | Mon 10/12/26 | Mon 10/12/26 | Thu 6/18/26 | 0% | Future Task | 20,522,794 | Yes | No | 2799 | 40dfc28152fa9a74ac2d20d528ac64d8abe46aea954c3cd794fdd159b0c86de4
project_plan | project_plan | 2167 | 931 |  | Test Readiness Review (TRR) - ITC 3 |  |  | Tue 6/30/26 | Tue 6/30/26 | Thu 6/18/26 | 0% | Future Task | 9,172,421 | No | No | 931 | e26ebb033207807e5476a29f4074f29abb3717690c45a33990326c9a0590d0af
project_plan | project_plan | 2168 | 690 |  | Test Readiness Review (TRR) - UAT |  |  | Fri 10/16/26 | Fri 10/16/26 | Thu 8/6/26 | 0% | Future Task | 29,389,264,540 | Yes | Yes | 690 | b1460bd8636db3b7b5ad036e17915b0672247eb24cae89210457ebb1a2c6b36c
project_plan | project_plan | 2169 | 19 |  | ITC-1 |  |  | Thu 4/16/26 | Tue 5/19/26 | Thu 7/23/26 | 37% | Complete | 932 | No | No | 19 | d7a3335ae5782b99d7be68a8410b4319fce3fbc0bc9047400039be7b1ccacfaf
project_plan | project_plan | 2170 | 834 |  | Testing expectations |  | PMO | Thu 4/16/26 | Thu 4/16/26 | Thu 4/16/26 | 100% | Complete | 932 | No | No | 834 | 262878adf89d3df2b6480d77e3ebee2fed8cca2b53f92933dc8bcfbf9f6ef17f
project_plan | project_plan | 2171 | 685 |  | Functional Smoke Testing |  |  | Mon 4/20/26 | Wed 4/29/26 | Fri 4/24/26 | 100% | Complete | 834 | No | No | 685 | 3c32c7c24d8156d0dbbb6f4a3057b5d24817734642b1b53d0c1b7f23a60fd5e7
project_plan | project_plan | 2172 | 684 |  | Assign Tester ID's |  |  | Thu 4/16/26 | Thu 4/23/26 | Thu 4/16/26 | 100% | Complete | 932 | No | No | 684 | 127751b9d7ed97139fba166f522b37c16ec3e8ac279f4e85711dce00657030b9
project_plan | project_plan | 2173 | 686 |  | ITC-1 Team Testing |  |  | Mon 4/27/26 | Mon 5/18/26 | Fri 5/15/26 | 25% | Late | 684 | No | No | 686 | 8dec7d36ffb45a5b9b732779ae3209bb84fd8c61bde8d7387590e2d2e927eac7
project_plan | project_plan | 2174 | 688 |  | ITC-1 Defect Correction / Retesting / Mitigation / Close |  |  | Wed 5/6/26 | Tue 5/19/26 | Fri 5/29/26 | 25% | Future Task | 686SS+4d | No | No | 688 | d22c824f388d4ff5ad8af9254d9fb9a884ce1a802e9e3804d9b14669a7777852
project_plan | project_plan | 2175 | 689 |  | ITC-1 Gate Review |  |  | Fri 5/15/26 | Fri 5/15/26 | Thu 7/23/26 | 0% | Future Task | 688FS-3d | No | No | 689 | 6f52e39718cb1e1ea259dcc4d2c71cd0293c948ef6491c985139df356940c458
project_plan | project_plan | 2176 | 2791 |  | ITC-2 |  |  | Fri 5/29/26 | Fri 6/19/26 | Fri 7/24/26 | 0% | Future Task |  | Yes | No | 2791 | 8f79043ff9b912ca08337afe6af96715a114d13d954e63dd45e9231dd954fa52
project_plan | project_plan | 2177 | 2792 |  | Assign Resources to Depolyment 1 locations |  | Renee | Fri 5/29/26 | Mon 6/1/26 | Thu 4/30/26 | 0% | Future Task | 2947 | Yes | No | 2792 | 98f5227c4d56ae6ea172865237696ca6d27a0798e36c45fb87c88d9b1038bc44
project_plan | project_plan | 2178 | 2795 |  | Assign Tester ID's |  | Security | Fri 5/29/26 | Mon 6/1/26 | Thu 6/18/26 | 0% | Future Task | 2792SS | Yes | No | 2795 | 9da93daf3f7aa8db00e15c386af1f09a3a52acae58f8f0c1a54cbc38e7e539c6
project_plan | project_plan | 2179 | 2948 |  | Identify Data and Processes for ITC |  |  | Fri 5/29/26 | Mon 6/1/26 |  | 0% | Future Task | 2795SS | Yes | No | 2948 | ab6a587c54ed78b4ff595fa54ba902897633317fce0092e546dce087c9685798
project_plan | project_plan | 2180 | 2949 |  | Run Costing for Data Identified(or ALL) |  |  | Mon 6/1/26 | Tue 6/2/26 |  | 0% | Future Task | 2948 | Yes | No | 2949 | ef89fbe2890c3e355e88cd9988c243719d58f10e3d6148ba1a2289326c2ace27
project_plan | project_plan | 2181 | 2794 |  | Functional Smoke Testing |  | Functional Leads | Tue 6/2/26 | Tue 6/9/26 | Thu 6/25/26 | 0% | Future Task | 2949 | Yes | No | 2794 | ecc12bb72b4f776775a968df49d44661c56f5c17d50acc5c373f0e37e56f4153
project_plan | project_plan | 2182 | 2793 |  | Test Kickoff |  | Renee | Mon 6/8/26 | Mon 6/8/26 | Thu 6/18/26 | 0% | Future Task | 2799 | Yes | No | 2793 | 8268bb5fff056433804d9097f9b5cdf59a986bc7ed070afc2ba0e852b748e009
project_plan | project_plan | 2183 | 2796 |  | Team Testing |  |  | Mon 6/8/26 | Fri 6/19/26 | Fri 7/17/26 | 0% | Future Task | 2793SS | No | No | 2796 | 877a6bcdc20d01f44f2150a88fc52a9f2ad796bdf763a57fca6f10b3a2bbbb5a
project_plan | project_plan | 2184 | 2797 |  | Defect Correction / Retesting / Mitigation / Close |  |  | Thu 6/11/26 | Wed 6/17/26 | Fri 7/24/26 | 0% | Future Task | 2796SS+3d | No | No | 2797 | e25a700fb231da20cf7cb798f2435ff9c6f35121b6384187d24519f6bad67dbd
project_plan | project_plan | 2185 | 2798 |  | Gate Review |  |  | Wed 6/17/26 | Wed 6/17/26 | Thu 7/23/26 | 0% | Future Task | 2797SS+4d | No | No | 2798 | ad8d019f23c4b7ae5b15ede16b08270845543baab2221bc4f0fa6034b915c795
project_plan | project_plan | 2186 | 915 |  | ITC-3 |  |  | Fri 6/19/26 | Fri 7/24/26 | Fri 7/24/26 | 0% | Future Task |  | No | No | 915 | eaa13010a31d0c8d71b9e75b7d22024e1455f07c8a16a513fedd87fa0784fac5
project_plan | project_plan | 2187 | 922 |  | Assign Resources to Depolyment 1 locations |  | Renee | Fri 6/19/26 | Mon 6/22/26 | Thu 4/30/26 | 0% | Future Task | 2958 | No | No | 922 | c1ecd8ddcdb45fe2bdda8024d126fe80dd1fdb18b9ae780339b8e1f251b9f56b
project_plan | project_plan | 2188 | 918 |  | Assign Tester ID's |  | Security | Fri 6/19/26 | Mon 6/22/26 | Thu 6/18/26 | 0% | Future Task | 922SS | No | No | 918 | 086213a4de8490abd8ae59c0cd03eb9e47c56778235fbc1b380c001177e0ddef
project_plan | project_plan | 2189 | 2950 |  | Identify Data and Processes for ITC |  |  | Fri 6/19/26 | Mon 6/22/26 |  | 0% | Future Task | 918SS | No | No | 2950 | 9040f595ba1e56631b5070ecb1b1efd85e6a4b6af53b9387ee805f2a98ea5a33
project_plan | project_plan | 2190 | 2951 |  | Run Costing for Data Identified |  |  | Mon 6/22/26 | Tue 6/23/26 |  | 0% | Future Task | 2950 | No | No | 2951 | 9b0609debae392a2f2553b083fdcec77871e3009e5741124d5ea5d374cda32b4
project_plan | project_plan | 2191 | 917 |  | Functional Smoke Testing |  | Functional Leads | Tue 6/23/26 | Tue 6/30/26 | Thu 6/25/26 | 0% | Future Task | 2951 | No | No | 917 | 9846a0879a9b5b75681bb5c8d17f19a49e52a136668aa5ed5f23d22f3ea5e8eb
project_plan | project_plan | 2192 | 916 |  | Test Kickoff |  | Renee | Mon 7/13/26 | Mon 7/13/26 | Thu 6/18/26 | 0% | Future Task | 931 | Yes | No | 916 | 0f0e13ac7b48d0e375cd377f5e60815f6c95f689c412143b099f6de2b6968fd4
project_plan | project_plan | 2193 | 919 |  | Team Testing |  |  | Mon 7/13/26 | Fri 7/24/26 | Fri 7/17/26 | 0% | Future Task | 916SS | No | No | 919 | b007c8a8f36c7c4d9e0d477f42b109ef0c238c23195a5d53372fa0d44e40b62d
project_plan | project_plan | 2194 | 923 |  | Defect Correction / Retesting / Mitigation / Close |  |  | Thu 7/16/26 | Wed 7/22/26 | Fri 7/24/26 | 0% | Future Task | 919SS+3d | No | No | 923 | d2d30dbfb7f0f7db0deca9d53f576c5f725e68421b10fe87c6385db9a85f4f4f
project_plan | project_plan | 2195 | 921 |  | Gate Review |  |  | Tue 7/21/26 | Tue 7/21/26 | Thu 7/23/26 | 0% | Future Task | 923SS+4d | No | Yes | 921 | d12a8e4de62ebe8d7c68fec2f944fc87b12c413f2bede018d8f035f0d0414240
project_plan | project_plan | 2196 | 22 |  | UAT (DR) |  |  | Mon 8/17/26 | Fri 10/16/26 | Thu 9/3/26 | 0% | Future Task |  | Yes | No | 22 | 535e305f4e1f6d005662f92ce94bf2eab977c8d8d16730d9e45f431067ddf45d
project_plan | project_plan | 2197 | 924 |  | Assign Resources to Depolyment 1 locations |  | Renee | Thu 10/8/26 | Thu 10/8/26 | Thu 4/30/26 | 0% | Future Task | 33,604,530 | Yes | No | 924 | 9b1c2d6ad85d8fceabcd53878b20d277701fff76b9577dc75264bdb41197957b
project_plan | project_plan | 2198 | 927 |  | Assign Tester ID's |  | Security | Thu 10/8/26 | Fri 10/9/26 | Thu 8/6/26 | 0% | Future Task | 924 | Yes | No | 927 | b63d2005646e68f6fa4f087f7ddd79657ba08673a072c567f9e76f4e06f2cea1
project_plan | project_plan | 2199 | 3361 |  | Run Costing for Data Identified |  |  | Thu 10/8/26 | Fri 10/9/26 |  | 0% | Future Task | 927SS | Yes | No | 3361 | 1a28c5402145f19045d24114d3f8b78126f7792067b7f5388fc8c61937c0aafa
project_plan | project_plan | 2200 | 926 |  | Functional Smoke Testing |  | Functional Leads | Fri 10/9/26 | Fri 10/16/26 | Fri 8/7/26 | 0% | Future Task | 3361 | Yes | No | 926 | b2373b6f2310d3624c8b3f650b7310194f060be66fe135328a19fd41d661977f
project_plan | project_plan | 2201 | 925 |  | Test Kickoff |  | Renee | Mon 8/17/26 | Mon 8/17/26 | Thu 8/6/26 | 0% | Future Task | 690 | Yes | No | 925 | 5ea5402cee612b7c7e55c1905142bec6a76f0d97024932028ee5f8e8cc14f3af
project_plan | project_plan | 2202 | 928 |  | Team Testing |  |  | Mon 8/17/26 | Fri 8/28/26 | Fri 8/28/26 | 0% | Future Task | 925SS | No | No | 928 | 59e6b10522a872a840b3feb941a063ed1e33b327c13e6329ac3b613c51fbdd06
project_plan | project_plan | 2203 | 3362 |  | Defect Correction / Retesting / Mitigation / Close |  |  | Wed 8/19/26 | Wed 8/19/26 | Fri 7/24/26 | 0% | Future Task | 928SS+3d | No | Yes | 3362 | 5e50de9b57d0d3904506047f95ccd29887b66e76a76b1f11ca2e89beafb37044
project_plan | project_plan | 2204 | 930 |  | Gate Review |  |  | Tue 8/25/26 | Tue 8/25/26 | Thu 9/3/26 | 0% | Future Task | 3362SS+4d | No | Yes | 930 | bbdadc364230d4d35492dea731a22d23732c65ded0ea6d5ffa3fb37c71eb36e8
project_plan | project_plan | 2205 | 683 |  | Business Readniess |  |  | Mon 2/16/26 | Mon 11/9/26 | Fri 10/16/26 | 38% | On Schedule |  | Yes | No | 683 | b22a24cc16bc118a6788e8810c9be1935eb44c8d836380ec80e37e4c23258044
project_plan | project_plan | 2206 | 215 |  | Training Readiness |  |  | Mon 2/16/26 | Mon 11/9/26 | Fri 10/16/26 | 38% | On Schedule |  | Yes | No | 215 | 5139d50bc82764e92cdca7b10cd732e107609e328babcb8f3a219af37d69c2b5
project_plan | project_plan | 2207 | 216 |  | Content Development |  |  | Mon 2/16/26 | Mon 11/9/26 | Mon 8/10/26 | 44% | On Schedule |  | Yes | No | 216 | a1f3480aac40cf8ae00c71b9b24ade93348ac8f2271e7705712eb57527215ee7
project_plan | project_plan | 2208 | 232 |  | Verify Role Mapping Complete |  | Training | Fri 5/1/26 | Fri 7/31/26 | Mon 8/3/26 | 46% | On Schedule |  | No | No | 232 | 89631d6ae73fe9ff5d5d147d40900b42bb5b588318c4bc4483a5e5d1ffb0b435
project_plan | project_plan | 2209 | 225 |  | Develop Curriculum |  | Training | Fri 5/1/26 | Fri 7/31/26 | Fri 6/5/26 | 30% | On Schedule | 232SS | Yes | No | 225 | c772a3f332badcaca22a0fbf618f04865f41dc15d411b03325eb87d406b7c202
project_plan | project_plan | 2210 | 4542 |  | Develop Course ppts |  | Training | Fri 5/1/26 | Fri 8/28/26 | Mon 8/3/26 | 35% | On Schedule | 225SS | No | No | 4542 | 6f290a3a13683936ad374d2fceb4190bc11613faea9def89df00238f2a615b8a
project_plan | project_plan | 2211 | 233 |  | Develop Work Instructions |  | Training | Fri 5/1/26 | Fri 8/28/26 | Mon 8/3/26 | 21% | On Schedule | 4542SS | No | No | 233 | f5eb343f8b6951eeb27843d955a2a1a4fcc79177232f2291c2178398bc1cb1eb
project_plan | project_plan | 2212 | 217 |  | Develop Training Data Sheets (Testing/Training) |  | Training | Mon 8/3/26 | Mon 11/9/26 | Mon 8/3/26 | 0% | Future Task | 225 | Yes | No | 217 | bc2a5ae147a491a66d79581dadd84805e78af876c3062d45b4cc83a69b7bf780
project_plan | project_plan | 2213 | 218 |  | Develop Train the Trainer |  | Training | Mon 2/16/26 | Fri 7/31/26 | Fri 7/31/26 | 100% | Complete | 232SS | No | No | 218 | b86a49f5b6f5df73b18b25f1e29d590926ee7294e716afadce45d49b0e909266
project_plan | project_plan | 2214 | 220 |  | Publish Training Materials to SP/LMS |  | Training | Mon 8/31/26 | Mon 9/7/26 | Mon 8/10/26 | 0% | Future Task | 4542 | No | No | 220 | 0035f359078ed6b0a8641f879d05d049b32eb7fbd5388e733de1b1869281f7c9
project_plan | project_plan | 2215 | 221 |  | Talent LMS Application Setup |  |  | Mon 8/31/26 | Mon 8/31/26 | Mon 8/10/26 | 0% | Future Task | 4542 | No | No | 221 | c8ca872ea58340a85dc805dc93eff1972bc627b80138877e06e39369dba3ab0f
project_plan | project_plan | 2216 | 241 |  | Train the Trainer |  |  | Mon 8/3/26 | Fri 8/28/26 | Fri 8/28/26 | 0% | Future Task |  | No | No | 241 | 4e45bf24057ff34d0e7df004756894816d829dcbb8d33157ffc16251487674d9
project_plan | project_plan | 2217 | 247 |  | Deliver Train the Trainer (BPL->SME) |  | Training | Mon 8/3/26 | Fri 8/28/26 | Fri 8/28/26 | 0% | Future Task | 218 | No | No | 247 | 8927e4912305b309225bfa043d673a5cbb34edbf016751bc2accb6e8c693c376
project_plan | project_plan | 2218 | 242 |  | End User Training Exeuction |  |  | Fri 7/10/26 | Fri 10/16/26 | Fri 10/16/26 | 0% | Future Task |  | No | No | 242 | 19bcf930b8f21a9944265ad8c50c10b1ad0beca8869a4f6fd7cf8d446b773bab
project_plan | project_plan | 2219 | 913 |  | User Training Plan and Schedule |  | Training | Fri 7/10/26 | Mon 8/3/26 | Fri 7/10/26 | 0% | Future Task |  | No | No | 913 | 2a1bb21942c44dcc03fa45ba37eae9e192b43207b4e17ec62ba99fe341b67e40
project_plan | project_plan | 2220 | 246 |  | Deliver End User Training |  | Training | Mon 8/31/26 | Fri 10/16/26 | Fri 10/16/26 | 0% | Future Task | 247 | No | No | 246 | 2ca9a452a60b9aca61d6bf3b008ff94891909ae0452107f64a8d1da461ed0ef9