## Milestone_Summary
[18 empty] | WBS | Task Name | Task Summary Name | Outline Level | Outline Number | Start | Finish | Baseline Start | Baseline Finish | % Complete | Status | Duration | Milestone | Summary | Critical | Predecessors | Milestone Show | Parent WBS | Parent Task Name | Percent Complete Pct | Is Late | Is Complete | Section | Section Order
[18 empty] | 1.2.1.70 | ITC1 Mock Data Loads Complete | ITC1 Data Load Tasks QS5 | 4 | 1.2.1.70 | 2026-04-23 | 2026-04-23 | 2026-04-21 | 2026-04-21 | 1 | Complete | 15m | Yes | No | No |  | YES | 1.2.1 |  | 100 | FALSE | TRUE | ITC1 | 1
[18 empty] | 1.2.2.3 | ITC2 Master Data Loads Complete | ITC2 Data Load Tasks QS4 | 4 | 1.2.2.3 | 46171 | 46171 |  |  | 0 | Future Task | 0m | Yes | No | Yes | 631 | YES | 1.2.2 |  | 0 | FALSE | FALSE | ITC2 | 2
[18 empty] | 1.2.2.5 | ITC2 Mock Data Loads Complete | ITC2 Data Load Tasks QS4 | 4 | 1.2.2.5 | 46307 | 46307 | 46133 | 46133 | 0 | Future Task | 0m | Yes | No | Yes | 999 | YES | 1.2.2 |  | 0 | TRUE | FALSE | ITC2 | 2
[18 empty] | 1.2.3.3 | ITC3 Master Data Loads Complete | ITC3 Data Load Tasks QS5 | 4 | 1.2.3.3 | 46192 | 46192 |  |  | 0 | Future Task | 0m | Yes | No | Yes | 1011 | YES | 1.2.3 |  | 0 | FALSE | FALSE | ITC3 | 3
[18 empty] | 1.2.3.5 | ITC3 Mock Data Loads Complete | ITC3 Data Load Tasks QS5 | 4 | 1.2.3.5 | 46196 | 46196 | 46133 | 46133 | 0 | Future Task | 0m | Yes | No | Yes | 1379 | YES | 1.2.3 |  | 0 | TRUE | FALSE | ITC3 | 3
[18 empty] | 1.1.1.7.4 | Environment Ready for Build | QS4 UAT Refresh | 5 | 1.1.1.7.4 | 46197 | 46197 | 45729 | 45729 | 0 | Future Task | 0m | Yes | No | Yes | 132 | YES | 1.1.1.7 |  | 0 | TRUE | FALSE | UAT | 4
[18 empty] | 1.3.3.8.7 | Defect Correction / Retesting / Mitigation / Close | UAT (DR) | 5 | 1.3.3.8.7 | 46253 | 46253 | 46223 | 46227 | 0 | Future Task | 0d | Yes | No | No | 2201SS+3d | YES | 1.3.3.8 |  | 0 | TRUE | FALSE | UAT | 4
[18 empty] | 1.3.3.8.8 | Gate Review | UAT (DR) | 5 | 1.3.3.8.8 | 46259 | 46259 | 46268 | 46268 | 0 | Future Task | 0h | Yes | No | No | 2202SS+4d | YES | 1.3.3.8 |  | 0 | FALSE | FALSE | UAT | 4
[18 empty] | 1.2.4.2.68.7 | UAT Mock Data Loads Complete | RTR_CM18_WBS Element | 6 | 1.2.4.2.68.7 | 46289 | 46289 | 46133 | 46133 | 0 | Future Task | 15m | Yes | No | Yes |  | YES | 1.2.4.2.68 |  | 0 | TRUE | FALSE | UAT | 4
[18 empty] | 1.2.5.2.68.7 | UAT Mock Data Loads Complete | RTR_CM18_WBS Element | 6 | 1.2.5.2.68.7 | 46289 | 46289 | 46133 | 46133 | 0 | Future Task | 15m | Yes | No | Yes |  | YES | 1.2.5.2.68 |  | 0 | TRUE | FALSE | UAT | 4
Section | Section Order | Milestone Order | WBS | Parent WBS | Task Name | Parent Task Name | Start | Finish | Baseline Start | Baseline Finish | Percent Complete Pct | Display Status | Is Complete | Is Late | Critical | Predecessors | Next In Progress | 1.2.4.3 | UAT Master Data Loads Complete | UAT Data Load Tasks QS4 | 4 | 1.2.4.3 | 46303 | 46303 |  |  | 0 | Future Task | 0m | Yes | No | Yes | 1391 | YES | 1.2.4 |  | 0 | FALSE | FALSE | UAT | 4
UAT | 4 | 1 | 1.1.1.7.4 | 1.1.1.7 | Environment Ready for Build |  | 46197 | 46197 | 45729 | 45729 | 0 | 0% | FALSE | TRUE | Yes | 132 | Environment Ready for Build | 1.2.4.5 | UAT Mock Data Loads Complete | UAT Data Load Tasks QS4 | 4 | 1.2.4.5 | 46307 | 46307 | 46133 | 46133 | 0 | Future Task | 15m | Yes | No | Yes | 1760 | YES | 1.2.4 |  | 0 | TRUE | FALSE | UAT | 4
UAT | 4 | 2 | 1.2.4.2.68.7 | 1.2.4.2.68 | UAT Mock Data Loads Complete |  | 46289 | 46289 | 46133 | 46133 | 0 | 0% | FALSE | TRUE | Yes |  | Environment Ready for Build | 1.3.3.4 | Test Readiness Review (TRR) - UAT | Testing Cycles | 4 | 1.3.3.4 | 46311 | 46311 | 46240 | 46240 | 0 | Future Task | 0h | Yes | No | Yes | 176921992150 | YES | 1.3.3 |  | 0 | TRUE | FALSE | UAT | 4
UAT | 4 | 3 | 1.2.4.3 | 1.2.4 | UAT Master Data Loads Complete |  | 46303 | 46303 |  |  | 0 | 0% | FALSE | FALSE | Yes | 1391 | Environment Ready for Build | 1.1.1.4.2 | Dev Environment Release from SAP | QS5 ITC-1 Refresh | 5 | 1.1.1.4.2 | 46030 | 46030 | 46030 | 46030 | 1 | Complete | 0d | Yes | No | No |  | YES | 1.1.1.4 |  | 100 | FALSE | TRUE | Unmapped | 99
UAT | 4 | 4 | 1.2.4.5 | 1.2.4 | UAT Mock Data Loads Complete |  | 46307 | 46307 | 46133 | 46133 | 0 | 0% | FALSE | TRUE | Yes | 1760 | Environment Ready for Build | 1.1.1.4.22 | Environment Ready for Build | QS5 ITC-1 Refresh | 5 | 1.1.1.4.22 | 46118 | 46118 | 46118 | 46118 | 1 | Complete | 0d | Yes | No | No | 39 | YES | 1.1.1.4 |  | 100 | FALSE | TRUE | Unmapped | 99
UAT | 4 | 5 | 1.2.5.2.68.7 | 1.2.5.2.68 | UAT Mock Data Loads Complete |  | 46289 | 46289 | 46133 | 46133 | 0 | 0% | FALSE | TRUE | Yes |  | Environment Ready for Build | 1.2.1.51.3 | Simulate Load | OTC_CM21_CMIR | 5 | 1.2.1.51.3 | 46128 | 46128 | 46132 | 46132 | 1 | Complete | 0h | Yes | No | No | 550 | YES | 1.2.1.51 |  | 100 | FALSE | TRUE | Unmapped | 99
UAT | 4 | 6 | 1.3.3.4 | 1.3.3 | Test Readiness Review (TRR) - UAT |  | 46311 | 46311 | 46240 | 46240 | 0 | 0% | FALSE | TRUE | Yes | 176921992150 | Environment Ready for Build | 1.2.1.51.4 | Error and Defect Mitigation | OTC_CM21_CMIR | 5 | 1.2.1.51.4 | 46128 | 46128 | 46132 | 46133 | 1 | Complete | 0h | Yes | No | No | 551 | YES | 1.2.1.51 |  | 100 | FALSE | TRUE | Unmapped | 99
UAT | 4 | 7 | 1.3.3.8.7 | 1.3.3.8 | Defect Correction / Retesting / Mitigation / Close |  | 46253 | 46253 | 46223 | 46227 | 0 | 0% | FALSE | TRUE | No | 2201SS+3d | Environment Ready for Build | 1.2.1.51.5 | Load | OTC_CM21_CMIR | 5 | 1.2.1.51.5 | 46128 | 46128 | 46133 | 46133 | 1 | Complete | 0h | Yes | No | No | 552 | YES | 1.2.1.51 |  | 100 | FALSE | TRUE | Unmapped | 99
UAT | 4 | 8 | 1.3.3.8.8 | 1.3.3.8 | Gate Review |  | 46259 | 46259 | 46268 | 46268 | 0 | 0% | FALSE | FALSE | No | 2202SS+4d | Environment Ready for Build | 1.1.1.5.4 | Environment Ready for Test | QS4 ITC-2 Refresh | 5 | 1.1.1.5.4 | 46156 | 46156 | 46219 | 46219 | 0 | Future Task | 0m | Yes | No | Yes | 70 | YES | 1.1.1.5 |  | 0 | FALSE | FALSE | Unmapped | 99
ITC1 | 1 | 1 | 1.2.1.70 | 1.2.1 | ITC1 Mock Data Loads Complete |  | 46135 | 46135 | 46133 | 46133 | 100 | Complete | TRUE | FALSE | No |  | None | 1.1.1.6.4 | Environment Ready for Test | QS5 ITC-3 Refresh | 5 | 1.1.1.6.4 | 46170 | 46170 | 46219 | 46219 | 0 | Future Task | 0m | Yes | No | Yes | 101 | YES | 1.1.1.6 |  | 0 | FALSE | FALSE | Unmapped | 99
ITC2 | 2 | 1 | 1.2.2.3 | 1.2.2 | ITC2 Master Data Loads Complete |  | 46171 | 46171 |  |  | 0 | 0% | FALSE | FALSE | Yes | 631 | ITC2 Master Data Loads Complete | 1.2.2.2.50.3 | Simulate Load | OTC_CM21_CMIR | 6 | 1.2.2.2.50.3 | 46170 | 46170 | 46132 | 46132 | 0 | Future Task | 0h | Yes | No | Yes | 920 | YES | 1.2.2.2.50 |  | 0 | TRUE | FALSE | Unmapped | 99
ITC2 | 2 | 2 | 1.2.2.5 | 1.2.2 | ITC2 Mock Data Loads Complete |  | 46307 | 46307 | 46133 | 46133 | 0 | 0% | FALSE | TRUE | Yes | 999 | ITC2 Master Data Loads Complete | 1.2.2.2.50.4 | Error and Defect Mitigation | OTC_CM21_CMIR | 6 | 1.2.2.2.50.4 | 46170 | 46170 | 46132 | 46133 | 0 | Future Task | 0h | Yes | No | Yes | 921 | YES | 1.2.2.2.50 |  | 0 | TRUE | FALSE | Unmapped | 99
ITC3 | 3 | 1 | 1.2.3.3 | 1.2.3 | ITC3 Master Data Loads Complete |  | 46192 | 46192 |  |  | 0 | 0% | FALSE | FALSE | Yes | 1011 | ITC3 Master Data Loads Complete | 1.2.2.2.50.5 | Load | OTC_CM21_CMIR | 6 | 1.2.2.2.50.5 | 46170 | 46170 | 46133 | 46133 | 0 | Future Task | 0h | Yes | No | Yes | 922 | YES | 1.2.2.2.50 |  | 0 | TRUE | FALSE | Unmapped | 99
ITC3 | 3 | 2 | 1.2.3.5 | 1.2.3 | ITC3 Mock Data Loads Complete |  | 46196 | 46196 | 46133 | 46133 | 0 | 0% | FALSE | TRUE | Yes | 1379 | ITC3 Master Data Loads Complete | 1.2.3.2.50.3 | Simulate Load | OTC_CM21_CMIR | 6 | 1.2.3.2.50.3 | 46191 | 46191 | 46132 | 46132 | 0 | Future Task | 0h | Yes | No | Yes | 1300 | YES | 1.2.3.2.50 |  | 0 | TRUE | FALSE | Unmapped | 99
[18 empty] | 1.2.3.2.50.4 | Error and Defect Mitigation | OTC_CM21_CMIR | 6 | 1.2.3.2.50.4 | 46191 | 46191 | 46132 | 46133 | 0 | Future Task | 0h | Yes | No | Yes | 1301 | YES | 1.2.3.2.50 |  | 0 | TRUE | FALSE | Unmapped | 99
[18 empty] | 1.2.3.2.50.5 | Load | OTC_CM21_CMIR | 6 | 1.2.3.2.50.5 | 46191 | 46191 | 46133 | 46133 | 0 | Future Task | 0h | Yes | No | Yes | 1302 | YES | 1.2.3.2.50 |  | 0 | TRUE | FALSE | Unmapped | 99
[18 empty] | 1.3.3.7.9 | Gate Review | ITC-3 | 5 | 1.3.3.7.9 | 46224 | 46224 | 46226 | 46226 | 0 | Future Task | 0h | Yes | No | No | 2193SS+4d | YES | 1.3.3.7 |  | 0 | FALSE | FALSE | Unmapped | 99
[18 empty] | 1.3.2.5 | Forms | Development RICEFW | 4 | 1.3.2.5 | 46248 | 46248 | 46164 | 46164 | 0 | Future Task | 0d | Yes | No | No |  | YES | 1.3.2 |  | 0 | TRUE | FALSE | Unmapped | 99
[18 empty] | 1.1.1.8.4 | Environment Ready for Build | P? Production System | 5 | 1.1.1.8.4 | 46289 | 46289 | 45729 | 45729 | 0 | Future Task | 0m | Yes | No | Yes | 160 | YES | 1.1.1.8 |  | 0 | TRUE | FALSE | Unmapped | 99
[18 empty] | 1.2.5.3 | PROD Master Data Loads Complete | PROD Data Load Tasks P? | 4 | 1.2.5.3 | 46296 | 46296 |  |  | 0 | Future Task | 0m | Yes | No | Yes | 1772 | YES | 1.2.5 |  | 0 | FALSE | FALSE | Unmapped | 99
[18 empty] | 1.2.5.5 | PRO Data Loads Complete | PROD Data Load Tasks P? | 4 | 1.2.5.5 | 46300 | 46300 | 46133 | 46133 | 0 | Future Task | 15m | Yes | No | Yes | 2141 | YES | 1.2.5 |  | 0 | TRUE | FALSE | Unmapped | 99
[18 empty] | 1.2.4.2.50.3 | Simulate Load | OTC_CM21_CMIR | 6 | 1.2.4.2.50.3 | 46303 | 46303 | 46132 | 46132 | 0 | Future Task | 0h | Yes | No | Yes | 1680 | YES | 1.2.4.2.50 |  | 0 | TRUE | FALSE | Unmapped | 99
[18 empty] | 1.2.4.2.50.4 | Error and Defect Mitigation | OTC_CM21_CMIR | 6 | 1.2.4.2.50.4 | 46303 | 46303 | 46132 | 46133 | 0 | Future Task | 0h | Yes | No | Yes | 1681 | YES | 1.2.4.2.50 |  | 0 | TRUE | FALSE | Unmapped | 99
[18 empty] | 1.2.4.2.50.5 | Load | OTC_CM21_CMIR | 6 | 1.2.4.2.50.5 | 46303 | 46303 | 46133 | 46133 | 0 | Future Task | 0h | Yes | No | Yes | 1682 | YES | 1.2.4.2.50 |  | 0 | TRUE | FALSE | Unmapped | 99
[18 empty] | 1.2.5.2.50.3 | Simulate Load | OTC_CM21_CMIR | 6 | 1.2.5.2.50.3 | 46303 | 46303 | 46132 | 46132 | 0 | Future Task | 0h | Yes | No | Yes | 2061 | YES | 1.2.5.2.50 |  | 0 | TRUE | FALSE | Unmapped | 99
[18 empty] | 1.2.5.2.50.4 | Error and Defect Mitigation | OTC_CM21_CMIR | 6 | 1.2.5.2.50.4 | 46303 | 46303 | 46132 | 46133 | 0 | Future Task | 0h | Yes | No | Yes | 2062 | YES | 1.2.5.2.50 |  | 0 | TRUE | FALSE | Unmapped | 99
[18 empty] | 1.2.5.2.50.5 | Load | OTC_CM21_CMIR | 6 | 1.2.5.2.50.5 | 46303 | 46303 | 46133 | 46133 | 0 | Future Task | 0h | Yes | No | Yes | 2063 | YES | 1.2.5.2.50 |  | 0 | TRUE | FALSE | Unmapped | 99
Section | Section Order | Total % Complete | Open Execution Tasks | Past Due Execution | CP Late Impact Tasks | Milestones Tracked | Health
ITC1 | 1 | 50 | 1 | 0 | 0 | 2 | On Track
ITC2 | 2 | 0 | 3 | 0 | 1 | 3 | At Risk
ITC3 | 3 | 0 | 3 | 0 | 1 | 3 | At Risk
UAT | 4 | 0 | 9 | 0 | 5 | 9 | At Risk
Go-Live | 5 | 0 | 1 | 0 | 0 | 1 | On Track
Section | Section Order | Total % Complete | Open Execution Tasks | Past Due Execution | CP Late Impact Tasks | Milestones Tracked | Health
ITC1 | 1 | 99 | 0 | 0 | 0 | 1 | On Track
ITC2 | 2 | 0 | 0 | 0 | 0 | 2 | On Track
ITC3 | 3 | 0 | 0 | 0 | 0 | 2 | On Track
UAT | 4 | 7 | 0 | 0 | 0 | 8 | On Track
Go-Live | 5 | 0 | 0 | 0 | 0 | 0 | On Track

## PQ_DomainWorkstreamHealth
Domain | Workstream | Total Items | Red Count | Yellow Count | Blue Count | Green Count | Unassigned Owner Count | Health Status | Health Icon | Trend Status | Trend Icon | Trend Color | Primary Reason | Reason Detail Template
RAID | Data | 3 | 0 | 3 | 0 | 0 | 0 | Issues Present (No Date Impact Expected) | 🟡 | Same (baseline pending) | ↔ | Gray | Open issues/risks/actions require monitoring | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
RAID | Finance | 62 | 4 | 58 | 0 | 0 | 0 | Needs Immediate Action | 🔴 | Same (baseline pending) | ↔ | Gray | Critical overdue/escalated items present | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
RAID | OTC | 5 | 1 | 4 | 0 | 0 | 0 | Needs Immediate Action | 🔴 | Same (baseline pending) | ↔ | Gray | Critical overdue/escalated items present | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
RAID | PMO | 28 | 1 | 15 | 0 | 12 | 7 | Needs Immediate Action | 🔴 | Same (baseline pending) | ↔ | Gray | Critical overdue/escalated items present | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
RAID | PTM | 4 | 2 | 2 | 0 | 0 | 1 | Needs Immediate Action | 🔴 | Same (baseline pending) | ↔ | Gray | Critical overdue/escalated items present | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
RAID | PTM/PTP | 1 | 0 | 1 | 0 | 0 | 0 | Issues Present (No Date Impact Expected) | 🟡 | Same (baseline pending) | ↔ | Gray | Open issues/risks/actions require monitoring | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
RAID | PTP | 10 | 5 | 5 | 0 | 0 | 0 | Needs Immediate Action | 🔴 | Same (baseline pending) | ↔ | Gray | Critical overdue/escalated items present | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
RAID | Reporting | 1 | 0 | 1 | 0 | 0 | 0 | Issues Present (No Date Impact Expected) | 🟡 | Same (baseline pending) | ↔ | Gray | Open issues/risks/actions require monitoring | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
RAID | Technical | 2 | 1 | 1 | 0 | 0 | 0 | Needs Immediate Action | 🔴 | Same (baseline pending) | ↔ | Gray | Critical overdue/escalated items present | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
RAID | Test | 1 | 0 | 1 | 0 | 0 | 0 | Issues Present (No Date Impact Expected) | 🟡 | Same (baseline pending) | ↔ | Gray | Open issues/risks/actions require monitoring | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
RAID | Unassigned | 1 | 1 | 0 | 0 | 0 | 0 | Needs Immediate Action | 🔴 | Same (baseline pending) | ↔ | Gray | Critical overdue/escalated items present | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
Schedule | Business Readniess | 4 | 0 | 4 | 0 | 0 | 0 | Issues Present (No Date Impact Expected) | 🟡 | Same (baseline pending) | ↔ | Gray | Open issues/risks/actions require monitoring | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
Schedule | Business Role Management | 2 | 0 | 1 | 1 | 0 | 2 | Issues Present (No Date Impact Expected) | 🟡 | Same (baseline pending) | ↔ | Gray | Open issues/risks/actions require monitoring | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
Schedule | Data Project Create | 3 | 0 | 0 | 3 | 0 | 0 | On Track | 🔵 | Same (baseline pending) | ↔ | Gray | Near-term work is active and tracking | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
Schedule | Data Readiness | 206 | 0 | 0 | 206 | 0 | 2 | On Track | 🔵 | Same (baseline pending) | ↔ | Gray | Near-term work is active and tracking | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
Schedule | Firefighter Configuration | 4 | 1 | 2 | 1 | 0 | 4 | Needs Immediate Action | 🔴 | Same (baseline pending) | ↔ | Gray | Critical overdue/escalated items present | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
Schedule | QS4 ITC-2 Refresh | 1 | 0 | 0 | 1 | 0 | 0 | On Track | 🔵 | Same (baseline pending) | ↔ | Gray | Near-term work is active and tracking | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
Schedule | Release Transports to Client | 13 | 3 | 4 | 6 | 0 | 0 | Needs Immediate Action | 🔴 | Same (baseline pending) | ↔ | Gray | Critical overdue/escalated items present | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
Schedule | Rule Set & Role Design | 4 | 2 | 2 | 0 | 0 | 4 | Needs Immediate Action | 🔴 | Same (baseline pending) | ↔ | Gray | Critical overdue/escalated items present | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
Schedule | Solution Readniess | 13 | 1 | 11 | 1 | 0 | 13 | Needs Immediate Action | 🔴 | Same (baseline pending) | ↔ | Gray | Critical overdue/escalated items present | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
Schedule | System Setup | 22 | 5 | 5 | 12 | 0 | 0 | Needs Immediate Action | 🔴 | Same (baseline pending) | ↔ | Gray | Critical overdue/escalated items present | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]
Schedule | Testing & Training | 4 | 0 | 1 | 3 | 0 | 4 | Issues Present (No Date Impact Expected) | 🟡 | Same (baseline pending) | ↔ | Gray | Open issues/risks/actions require monitoring | Date=[yyyy-mm-dd]; Type=[reason type]; Owner=[name]; Note=[summary]

## PQ_HealthItemReasonMatches
Domain | Workstream | Source | Item ID | Title | Status | Action Window | Assigned To | Due Date | Priority | Days Overdue | Pct Complete | Is Critical | Reason Code | Reason Category | Applies To | Severity | Reason Template | Placeholder Date | Placeholder Type | Placeholder Owner | Placeholder Notes
Schedule | System Setup | Project Plan | 1.1.1.5.1.11 | Fiori App Activation | Future Task | Should Have Started | Dev Team | Mon 5/4/26 | 500 | 4 | 0.25 | Yes | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | System Setup | Project Plan | 1.1.1.5.1.12 | Download Transport List | Future Task | Should Have Started | Basis | Mon 5/4/26 | 500 | 4 | 0.25 | Yes | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | System Setup | Project Plan | 1.1.1.5.1.13 | Business Functions Validation | Future Task | Should Have Started | Basis | Mon 5/4/26 | 500 | 4 | 0.25 | Yes | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | System Setup | Project Plan | 1.1.1.5.1.14 | Functional Leads Validation of Transport List | Future Task | Should Have Started | Functional Leads | Mon 5/4/26 | 500 | 4 | 0.25 | Yes | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | System Setup | Project Plan | 1.1.1.5.1.15 | Release Security roles to Functional Team | Future Task | Should Have Started | Security | Mon 5/4/26 | 500 | 4 | 0.25 | Yes | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Release Transports to Client | Project Plan | 1.1.1.5.2.1 | Import Group 1 - Ent Structure | Future Task | Should Have Started | Functional Leads | Tue 5/5/26 | 500 | 3 | 0.25 | Yes | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Release Transports to Client | Project Plan | 1.1.1.5.2.2 | Manual activities group 1 | Future Task | Should Have Started | Functional Leads | Thu 5/7/26 | 500 | 1 | 0.25 | Yes | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Release Transports to Client | Project Plan | 1.1.1.5.2.3 | Import Group 2 - Core Transports | Future Task | Should Have Started | Functional Leads | Thu 5/7/26 | 500 | 1 | 0.25 | Yes | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Release Transports to Client | Project Plan | 1.1.1.5.2.4 | Manual activities group 2 | Future Task | Should Have Started | Functional Leads | Fri 5/8/26 | 500 | 0 | 0.25 | Yes | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Rule Set & Role Design | Project Plan | 1.1.2.4.9 | Risk analysis on existing roles | Future Task | Should Have Started |  | Thu 5/7/26 | 500 | 1 | 0 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Rule Set & Role Design | Project Plan | 1.1.2.4.9 | Risk analysis on existing roles | Future Task | Should Have Started |  | Thu 5/7/26 | 500 | 1 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Rule Set & Role Design | Project Plan | 1.1.2.4.10 | Role remediation planning - Can impact role design & Possible of retesting. | Future Task | Should Have Started |  | Thu 5/21/26 | 500 | 0 | 0 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Rule Set & Role Design | Project Plan | 1.1.2.4.10 | Role remediation planning - Can impact role design & Possible of retesting. | Future Task | Should Have Started |  | Thu 5/21/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Business Role Management | Project Plan | 1.1.2.5.1 | Role Mapping with Business Process and Sub-Process /Functional Area | Future Task | Should Have Started |  | Thu 5/14/26 | 500 | 0 | 0 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Business Role Management | Project Plan | 1.1.2.5.1 | Role Mapping with Business Process and Sub-Process /Functional Area | Future Task | Should Have Started |  | Thu 5/14/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Firefighter Configuration | Project Plan | 1.1.2.6.1 | Firefighter ID setup | Future Task | Should Have Started |  | Thu 5/7/26 | 500 | 1 | 0 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Firefighter Configuration | Project Plan | 1.1.2.6.1 | Firefighter ID setup | Future Task | Should Have Started |  | Thu 5/7/26 | 500 | 1 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Firefighter Configuration | Project Plan | 1.1.2.6.2 | Firefighter log settings | Future Task | Should Have Started |  | Thu 5/14/26 | 500 | 0 | 0 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Firefighter Configuration | Project Plan | 1.1.2.6.2 | Firefighter log settings | Future Task | Should Have Started |  | Thu 5/14/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Testing & Training | Project Plan | 1.1.2.7.1 | Unit testing | Future Task | Should Have Started |  | Wed 5/13/26 | 500 | 0 | 0 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Testing & Training | Project Plan | 1.1.2.7.1 | Unit testing | Future Task | Should Have Started |  | Wed 5/13/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Solution Readniess | Project Plan | 1.3.1.1 | FICO | Future Task | Should Have Started |  | Fri 5/29/26 | 500 | 0 | 0.03 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Solution Readniess | Project Plan | 1.3.1.1 | FICO | Future Task | Should Have Started |  | Fri 5/29/26 | 500 | 0 | 0.03 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Solution Readniess | Project Plan | 1.3.1.2 | Order to Cash | Future Task | Should Have Started |  | Fri 5/29/26 | 500 | 0 | 0.04 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Solution Readniess | Project Plan | 1.3.1.2 | Order to Cash | Future Task | Should Have Started |  | Fri 5/29/26 | 500 | 0 | 0.04 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Solution Readniess | Project Plan | 1.3.1.3 | Procure to Pay | Future Task | Should Have Started |  | Fri 5/29/26 | 500 | 0 | 0.04 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Solution Readniess | Project Plan | 1.3.1.3 | Procure to Pay | Future Task | Should Have Started |  | Fri 5/29/26 | 500 | 0 | 0.04 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Solution Readniess | Project Plan | 1.3.1.4 | Plan to Make | Future Task | Should Have Started |  | Fri 5/29/26 | 500 | 0 | 0.05 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Solution Readniess | Project Plan | 1.3.1.4 | Plan to Make | Future Task | Should Have Started |  | Fri 5/29/26 | 500 | 0 | 0.05 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Solution Readniess | Project Plan | 1.3.2.1 | Reports | Future Task | Should Have Started |  | Fri 8/14/26 | 500 | 0 | 0 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Solution Readniess | Project Plan | 1.3.2.1 | Reports | Future Task | Should Have Started |  | Fri 8/14/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Solution Readniess | Project Plan | 1.3.2.2 | Interfaces | Future Task | Should Have Started |  | Fri 8/14/26 | 500 | 0 | 0 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Solution Readniess | Project Plan | 1.3.2.2 | Interfaces | Future Task | Should Have Started |  | Fri 8/14/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Solution Readniess | Project Plan | 1.3.2.3 | Enhanchments | Future Task | Should Have Started |  | Fri 8/14/26 | 500 | 0 | 0 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Solution Readniess | Project Plan | 1.3.2.3 | Enhanchments | Future Task | Should Have Started |  | Fri 8/14/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Solution Readniess | Project Plan | 1.3.2.4 | Workflow | Future Task | Should Have Started |  | Fri 8/14/26 | 500 | 0 | 0 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Solution Readniess | Project Plan | 1.3.2.4 | Workflow | Future Task | Should Have Started |  | Fri 8/14/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Solution Readniess | Project Plan | 1.3.3.1 | Test Readiness Review (TRR) - ITC 1 | Future Task | Should Have Started |  | Fri 5/1/26 | 500 | 7 | 0.25 | Yes | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Solution Readniess | Project Plan | 1.3.3.1 | Test Readiness Review (TRR) - ITC 1 | Future Task | Should Have Started |  | Fri 5/1/26 | 500 | 7 | 0.25 | Yes | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Solution Readniess | Project Plan | 1.3.3.5.4 | ITC-1 Team Testing | Future Task | Should Have Started |  | Mon 5/18/26 | 500 | 0 | 0.25 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Solution Readniess | Project Plan | 1.3.3.5.4 | ITC-1 Team Testing | Future Task | Should Have Started |  | Mon 5/18/26 | 500 | 0 | 0.25 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Solution Readniess | Project Plan | 1.3.3.5.5 | ITC-1 Defect Correction / Retesting / Mitigation / Close | Future Task | Should Have Started |  | Tue 5/19/26 | 500 | 0 | 0.25 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Solution Readniess | Project Plan | 1.3.3.5.5 | ITC-1 Defect Correction / Retesting / Mitigation / Close | Future Task | Should Have Started |  | Tue 5/19/26 | 500 | 0 | 0.25 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Business Readniess | Project Plan | 1.4.1.1.1 | Verify Role Mapping Complete | Future Task | Should Have Started | Training | Fri 7/31/26 | 500 | 0 | 0.46 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Business Readniess | Project Plan | 1.4.1.1.2 | Develop Curriculum | Future Task | Should Have Started | Training | Fri 7/31/26 | 500 | 0 | 0.3 | Yes | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Business Readniess | Project Plan | 1.4.1.1.3 | Develop Course ppts | Future Task | Should Have Started | Training | Fri 8/28/26 | 500 | 0 | 0.35 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | Business Readniess | Project Plan | 1.4.1.1.4 | Develop Work Instructions | Future Task | Should Have Started | Training | Fri 8/28/26 | 500 | 0 | 0.21 | No | SCH-SHS | Schedule | Project Plan | Yellow | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
Schedule | System Setup | Project Plan | 1.1.1.5.1.11 | Fiori App Activation | Future Task | Overdue | Dev Team | Mon 5/4/26 | 500 | 4 | 0.25 | Yes | SCH-OVD | Schedule | Project Plan | Red | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
Schedule | System Setup | Project Plan | 1.1.1.5.1.12 | Download Transport List | Future Task | Overdue | Basis | Mon 5/4/26 | 500 | 4 | 0.25 | Yes | SCH-OVD | Schedule | Project Plan | Red | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
Schedule | System Setup | Project Plan | 1.1.1.5.1.13 | Business Functions Validation | Future Task | Overdue | Basis | Mon 5/4/26 | 500 | 4 | 0.25 | Yes | SCH-OVD | Schedule | Project Plan | Red | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
Schedule | System Setup | Project Plan | 1.1.1.5.1.14 | Functional Leads Validation of Transport List | Future Task | Overdue | Functional Leads | Mon 5/4/26 | 500 | 4 | 0.25 | Yes | SCH-OVD | Schedule | Project Plan | Red | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
Schedule | System Setup | Project Plan | 1.1.1.5.1.15 | Release Security roles to Functional Team | Future Task | Overdue | Security | Mon 5/4/26 | 500 | 4 | 0.25 | Yes | SCH-OVD | Schedule | Project Plan | Red | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
Schedule | Release Transports to Client | Project Plan | 1.1.1.5.2.1 | Import Group 1 - Ent Structure | Future Task | Overdue | Functional Leads | Tue 5/5/26 | 500 | 3 | 0.25 | Yes | SCH-OVD | Schedule | Project Plan | Red | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
Schedule | Release Transports to Client | Project Plan | 1.1.1.5.2.2 | Manual activities group 1 | Future Task | Overdue | Functional Leads | Thu 5/7/26 | 500 | 1 | 0.25 | Yes | SCH-OVD | Schedule | Project Plan | Red | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
Schedule | Release Transports to Client | Project Plan | 1.1.1.5.2.3 | Import Group 2 - Core Transports | Future Task | Overdue | Functional Leads | Thu 5/7/26 | 500 | 1 | 0.25 | Yes | SCH-OVD | Schedule | Project Plan | Red | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
Schedule | Rule Set & Role Design | Project Plan | 1.1.2.4.5 | Final Review Rule Set and update the recommendations | Late | Overdue |  | Wed 1/7/26 | 500 | 121 | 0.6 | No | SCH-OVD | Schedule | Project Plan | Red | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
Schedule | Rule Set & Role Design | Project Plan | 1.1.2.4.5 | Final Review Rule Set and update the recommendations | Late | Overdue |  | Wed 1/7/26 | 500 | 121 | 0.6 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Rule Set & Role Design | Project Plan | 1.1.2.4.9 | Risk analysis on existing roles | Future Task | Overdue |  | Thu 5/7/26 | 500 | 1 | 0 | No | SCH-OVD | Schedule | Project Plan | Red | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
Schedule | Rule Set & Role Design | Project Plan | 1.1.2.4.9 | Risk analysis on existing roles | Future Task | Overdue |  | Thu 5/7/26 | 500 | 1 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Firefighter Configuration | Project Plan | 1.1.2.6.1 | Firefighter ID setup | Future Task | Overdue |  | Thu 5/7/26 | 500 | 1 | 0 | No | SCH-OVD | Schedule | Project Plan | Red | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
Schedule | Firefighter Configuration | Project Plan | 1.1.2.6.1 | Firefighter ID setup | Future Task | Overdue |  | Thu 5/7/26 | 500 | 1 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Solution Readniess | Project Plan | 1.3.3.1 | Test Readiness Review (TRR) - ITC 1 | Future Task | Overdue |  | Fri 5/1/26 | 500 | 7 | 0.25 | Yes | SCH-OVD | Schedule | Project Plan | Red | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
Schedule | Solution Readniess | Project Plan | 1.3.3.1 | Test Readiness Review (TRR) - ITC 1 | Future Task | Overdue |  | Fri 5/1/26 | 500 | 7 | 0.25 | Yes | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Release Transports to Client | Project Plan | 1.1.1.5.2.5 | Import Group 3 - prior to transactions | Future Task | Starting This Week | Functional Leads | Mon 5/11/26 | 500 | 0 | 0.25 | Yes
Schedule | Release Transports to Client | Project Plan | 1.1.1.5.2.6 | Manual Activities Group 3 | Future Task | Starting This Week | Functional Leads | Tue 5/12/26 | 500 | 0 | 0.25 | Yes
Schedule | Release Transports to Client | Project Plan | 1.1.1.5.2.7 | Import Group 4 - workbench / dev work | Future Task | Starting This Week | Dev Team | Tue 5/12/26 | 500 | 0 | 0 | Yes
Schedule | Release Transports to Client | Project Plan | 1.1.1.5.2.8 | Import Group 5 - Config to support dev workbench | Future Task | Starting This Week | Dev Team | Wed 5/13/26 | 500 | 0 | 0 | Yes
Schedule | Data Project Create | Project Plan | 1.1.1.5.3.1 | Open Client | Future Task | Starting This Week | Basis | Wed 5/13/26 | 500 | 0 | 0 | Yes
Schedule | Data Project Create | Project Plan | 1.1.1.5.3.2 | Create Migration Data Project in DMC | Future Task | Starting This Week | Data Migration Team | Thu 5/14/26 | 500 | 0 | 0 | Yes
Schedule | Data Project Create | Project Plan | 1.1.1.5.3.3 | Close Client | Future Task | Starting This Week | Basis | Thu 5/14/26 | 500 | 0 | 0 | Yes
Schedule | QS4 ITC-2 Refresh | Project Plan | 1.1.1.5.4 | Environment Ready for Test | Future Task | Starting This Week | PMO | Thu 5/14/26 | 500 | 0 | 0 | Yes
Schedule | System Setup | Project Plan | 1.1.1.6.1.1 | System Refresh Basis(Workinig with NS2) | Future Task | Starting Next 2 Weeks | Basis | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | System Setup | Project Plan | 1.1.1.6.1.2 | Client Config / Validation | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | System Setup | Project Plan | 1.1.1.6.1.3 | Technical Transports / BP Setup | Future Task | Starting Next 2 Weeks | Basis | Fri 5/22/26 | 500 | 0 | 0 | No
Schedule | System Setup | Project Plan | 1.1.1.6.1.7 | Security Transports | Future Task | Starting Next 2 Weeks | Security | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | System Setup | Project Plan | 1.1.1.6.1.8 | Security Manual Tasks | Future Task | Starting Next 2 Weeks | Security | Fri 5/22/26 | 500 | 0 | 0 | No
Schedule | System Setup | Project Plan | 1.1.1.6.1.9 | Manual Technical Tasks | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | System Setup | Project Plan | 1.1.1.6.1.10 | Validate Fiori | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | No
Schedule | System Setup | Project Plan | 1.1.1.6.1.11 | Fiori App Activation | Future Task | Starting Next 2 Weeks | Dev Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | System Setup | Project Plan | 1.1.1.6.1.12 | Download Transport List | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | System Setup | Project Plan | 1.1.1.6.1.13 | Business Functions Validation | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | No
Schedule | System Setup | Project Plan | 1.1.1.6.1.14 | Functional Leads Validation of Transport | Future Task | Starting Next 2 Weeks | Functional Leads | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | System Setup | Project Plan | 1.1.1.6.1.15 | Release Security roles to Functional Team | Future Task | Starting Next 2 Weeks | Security | Thu 5/21/26 | 500 | 0 | 0 | No
Schedule | Release Transports to Client | Project Plan | 1.1.1.6.2.1 | Import Group 1 - Ent Structure | Future Task | Starting Next 2 Weeks | Functional Leads | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Release Transports to Client | Project Plan | 1.1.1.6.2.2 | Manual activities group 1 | Future Task | Starting Next 2 Weeks | Functional Leads | Mon 5/25/26 | 500 | 0 | 0 | Yes
Schedule | Business Role Management | Project Plan | 1.1.2.5.2 | Role Upload to SAP GRC | Future Task | Starting This Week |  | Thu 5/21/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Firefighter Configuration | Project Plan | 1.1.2.6.3 | Functional validation | Future Task | Starting This Week |  | Thu 5/21/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Testing & Training | Project Plan | 1.1.2.7.2 | Changes moved to Test System | Future Task | Starting This Week |  | Mon 5/18/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Testing & Training | Project Plan | 1.1.2.7.3 | Connector configuration (S4 / LDAP Connector) | Future Task | Starting Next 2 Weeks |  | Thu 5/21/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Testing & Training | Project Plan | 1.1.2.7.4 | Workflow Activation / Data load in Test System | Future Task | Starting Next 2 Weeks |  | Thu 5/28/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Data Readiness | Project Plan | 1.2.2.1 | PMO Authorization to Start Data Loads | Future Task | Starting Next 2 Weeks | Mark George | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.1.1 | Manual File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.1.2 | Load | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.1.3 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.2.1 | Manual File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.2.2 | Load | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.2.3 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.3.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.3.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.3.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.3.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.3.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.3.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.3.7 | Extend GL to all Company Codes | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.3.8 | Post GL Extention Validation | Future Task | Starting Next 2 Weeks |  | Fri 5/22/26 | 500 | 0 | 0 | Yes | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Data Readiness | Project Plan | 1.2.2.2.4.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.4.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.4.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.4.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.4.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.4.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.5.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.5.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.5.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.5.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.5.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.5.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.6.1 | Open Client | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.6.2 | Service Enterprise Setup | Future Task | Starting Next 2 Weeks | Keith Riley | Fri 5/29/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.6.3 | Close Client | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.6.4 | Intercompany Business Partner Setup | Future Task | Starting Next 2 Weeks | Functional Leads | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.7.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.7.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.7.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.7.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.7.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.7.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/25/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.8.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.8.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.8.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.8.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.8.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.8.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.9.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.9.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.9.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.9.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.9.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.9.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.10.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.10.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.10.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.10.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.10.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.10.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.11.1 | Manual File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.11.2 | Load | Future Task | Starting Next 2 Weeks | Kasey Hughes | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.11.3 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/25/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.12 | OTC_CM19_Customer_Master - Bill-To | Future Task | Starting Next 2 Weeks |  | Mon 5/18/26 | 500 | 0 | 0 | Yes | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
Schedule | Data Readiness | Project Plan | 1.2.2.2.13.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.13.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.13.3 | Open client for BP number range update | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.13.4 | Update number range BP02 from Internal to External | Future Task | Starting Next 2 Weeks | Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.13.5 | Close Client | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.13.6 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.13.7 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Ric Haraida | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.13.8 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.13.9 | Post Load Validation | Future Task | Starting Next 2 Weeks | Ric Haraida | Mon 5/25/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.14.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.14.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.14.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.14.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Ric Haraida | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.14.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/25/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.14.7 | Open client for BP number range update | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.14.8 | Update number range BP02 from Internal to External | Future Task | Starting Next 2 Weeks | Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.14.9 | Close Client | Future Task | Starting Next 2 Weeks | Basis | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.19.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.19.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.20.1 | Extract File(Will Extract from LFA1) | Future Task | Starting Next 2 Weeks | Nevin Varkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.20.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.20.3 | Simulate Load/ Not Needed | Future Task | Starting Next 2 Weeks | Nevin Varkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.20.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.20.5 | Load | Future Task | Starting Next 2 Weeks | Nevin Varkkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.20.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.22.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.22.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.22.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.22.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.22.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.22.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.23.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.23.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.23.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.23.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.23.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.23.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.24.1 | Extract File | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.24.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.24.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.24.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.24.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.24.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.25.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.25.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.25.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.25.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.25.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.25.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.26.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Eric Heisler | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.26.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.26.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.26.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Eric Heisler | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.26.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.26.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.27.1 | Extract File | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.27.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.27.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.27.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.27.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.27.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.28.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.28.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.28.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.28.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.28.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.28.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.29.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.29.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.29.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.29.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.29.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.29.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.30.1 | Extract File | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.30.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Brad Meseck | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.30.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/25/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.31.1 | Extract File | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.32.1 | Extract File | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.33.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Brad Meseck | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.33.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Brad Meseck | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.33.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.33.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Brad Meseck | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.33.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.33.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Brad Meseck | Mon 5/25/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.36.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Brad Meseck | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.37.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.37.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.38.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.38.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.39.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.39.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Wed 5/20/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.40.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.40.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.41.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.41.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.42.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.42.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.43.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.43.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.44.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.44.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Mon 5/25/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.45.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Mon 5/25/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.46.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Eric Heisler | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.46.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.46.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.46.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.46.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/25/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.51.1 | Manual File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Nevin Varkey | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.52.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.52.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes,Femi Oguntala | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.52.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.52.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.52.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.52.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.53.1 | Manual File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Sam | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.53.2 | Load | Future Task | Starting Next 2 Weeks | Brad Meseck | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.53.3 | Post Load Validation | Future Task | Starting Next 2 Weeks | Brad | Tue 5/26/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.54.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Sam | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.54.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Brad Meseck | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.54.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.54.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Brad Meseck | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.54.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.54.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Brad Meseck | Mon 5/25/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.55.1 | Run material interface to GTS | Future Task | Starting Next 2 Weeks | James Van Riper | Mon 5/25/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.56.1 | Run material interface to GTS | Future Task | Starting Next 2 Weeks | James Van Riper | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.56.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | James Van Riper | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.57.1 | Run material interface to GTS | Future Task | Starting Next 2 Weeks | James Van Riper | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.57.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | James Van Riper | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.58.1 | Load Descartes XML File | Future Task | Starting Next 2 Weeks | James Van Riper | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.58.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | James Van Riper | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.60.1 | Load Descartes XML File | Future Task | Starting Next 2 Weeks | James Van Riper | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.60.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | James Van Riper | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.65.1 | Run report /SAPSLL/EMB_CNTRY_INIT | Future Task | Starting Next 2 Weeks | James Van Riper | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.65.2 | Set Embargo situations | Future Task | Starting Next 2 Weeks | James Van Riper | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.65.3 | Post Load Validation | Future Task | Starting Next 2 Weeks | James Van Riper | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.67.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.67.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.67.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.67.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.67.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.67.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.68.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.68.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.68.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.68.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.68.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Data Readiness | Project Plan | 1.2.2.2.68.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Schedule | Solution Readniess | Project Plan | 1.3.3.5.6 | ITC-1 Gate Review | Future Task | Starting This Week |  | Fri 5/15/26 | 500 | 0 | 0 | No | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
RAID | PMO | Risk | R-129 | SME for GTS | Open | Open Risk | PMO |  |  | 74 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-132 | Training misaligned with finalized processes | Open | Open Risk |  |  |  | 67 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-132 | Training misaligned with finalized processes | Open | Open Risk |  |  |  | 67 |  | FALSE | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
RAID | PMO | Risk | R-133 | Product Hieararchy | Open | Open Risk |  |  |  | 67 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-133 | Product Hieararchy | Open | Open Risk |  |  |  | 67 |  | FALSE | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
RAID | PMO | Risk | R-134 | Inconsistent cross‑team engagement | Open | Open Risk |  |  |  | 67 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-134 | Inconsistent cross‑team engagement | Open | Open Risk |  |  |  | 67 |  | FALSE | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
RAID | PMO | Risk | R-138 | Finance workflows and interfaces not fully identified | Open | Open Risk |  |  |  | 67 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-138 | Finance workflows and interfaces not fully identified | Open | Open Risk |  |  |  | 67 |  | FALSE | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
RAID | PMO | Risk | R-139 | Data readiness lag | Open | Open Risk |  |  |  | 67 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-139 | Data readiness lag | Open | Open Risk |  |  |  | 67 |  | FALSE | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
RAID | PMO | Risk | R-140 | DLA flexible workflows configuration | Open | Open Risk |  |  |  | 67 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-140 | DLA flexible workflows configuration | Open | Open Risk |  |  |  | 67 |  | FALSE | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
RAID | PMO | Risk | R-141 | Projects for D1 | Open | Open Risk |  |  |  | 66 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-141 | Projects for D1 | Open | Open Risk |  |  |  | 66 |  | FALSE | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
RAID | PMO | Risk | R-143 | Finance Role Design for ITC1 | Open | Open Risk | Kasey Hughes | 46093 |  | 59 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-145 | Bluesnap Credit Card Certification | Open | Open Risk | Joel Flemming | 46143 |  | 29 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-146 | Functional Specs Behind Schedule | Open | Open Risk | Kinnary | 46143 |  | 23 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-147 | Commerce cloud system unavailable until June to develop and test interfaces to S4 | Open | Open Risk | Joel Flemming | 46188 |  | 2 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-148 | Training Readiness | Open | Open Risk | PMO |  |  | 1 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | PMO | Risk | R-149 | Scribe Availability | Open | Open Risk | Chris Hanily | 46150 |  | 1 |  | FALSE | RSK-OPEN | Risk | Risk | Yellow | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
RAID | Finance | Issue | I-100 | Master data change process incomplete | Open | Open Issue | Michelle | 46174 | 2-Medium | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-101 | No change management process defined | Open | Open Issue | PMO | 46174 | 2-Medium | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-102 | Data clean up requirements not communicated to business | Open | Open Issue | Michelle | 46174 | 2-Medium | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-103 | Flexible workflow functionality, technical resource alignment across functions | Open | Open Issue | PMO | 46174 | 2-Medium | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-104 | Single purchasing organization implications | Open | Open Issue | Rob Rideout | 46174 | 2-Medium | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-105 | Data: Tax exemption certificate cleanup resourcing | Escalated | Escalated Issue | Steve Trust & Kevin Coleman | 46174 | 2-Medium | 67 |  | FALSE | ISS-ESC | Issue | Issue | Red | Escalated issue requiring immediate resolution | [Escalation Date] | [Issue Type] | [Owner] | [Escalation Note]
RAID | Finance | Issue | I-106 | Open service contracts data requirements | Open | Open Issue | OTC | 46174 | 2-Medium | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-107 | Service requirements not designed. Business requirements not gathered | Open | Open Issue | OTC | 46174 | 2-Medium | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-108 | Reporting resourcing gap | Open | Open Issue | PMO | 46142 | 2-Medium | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-109 | OpenText finance items stalled | Open | Open Issue | PMO | 46142 | 2-Medium | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-110 | Missing process narratives and controls required to validate completed design | Open | Open Issue | Finance | 46142 | 2-Medium | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-112 | No SAP functional owner for banking and treasury (open position) | Open | Open Issue | PMO | 46142 | 3-High | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-113 | Supplier banking data gaps and dual maintenance requirements - need to identify process | Open | Open Issue | Manoj Patel | 46142 | 2-Medium | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-114 | Key reports not reviewed cross‑functionally | Open | Open Issue | PMO | 46142 | 3-High | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-115 | Additional business resources / Business Process Leads (BPLs) needed for core finance processes | Open | Open Issue | PMO | 46142 | 3-High | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-116 | FX treatment, reporting and controls undefined | Open | Open Issue | Kasey Hughes | 46142 | 3-High | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-117 | Reporting attributes/characteristics not fully defined and approved | Open | Open Issue | PMO | 46142 | 3-High | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-118 | VSIT issue with COGS matching to revenue for MTO | Escalated | Escalated Issue | OTC/PTM/Finance | 46157 | 4-Critical | 67 |  | FALSE | ISS-ESC | Issue | Issue | Red | Escalated issue requiring immediate resolution | [Escalation Date] | [Issue Type] | [Owner] | [Escalation Note]
RAID | Finance | Issue | I-119 | Incomplete finance and cross functional design documentation and approval | Escalated | Escalated Issue | Finance | 46142 | 2-Medium | 67 |  | FALSE | ISS-ESC | Issue | Issue | Red | Escalated issue requiring immediate resolution | [Escalation Date] | [Issue Type] | [Owner] | [Escalation Note]
RAID | Finance | Issue | I-120 | Financial statement versions and FX reporting | Open | Open Issue | Kasey Hughes | 46142 | 2-Medium | 67 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | PTM/PTP | Issue | I-121 | Attachment links cannot reference network drives | Open | Open Issue | Brad Meseck | 46128 | 2-Medium | 63 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-122 | Legal entity/profit center/HFM mapping complexity | Open | Open Issue | Kasey Hughes | 46142 | 2-Medium | 25 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | Finance | Issue | I-123 | Vertex Certificate Center delay | Open | Open Issue | Matt Cummins | 46157 | 2-Medium | 25 |  | FALSE | ISS-OPEN | Issue | Issue | Yellow | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
RAID | PMO | Decision | D-154 | Credit Rating Agency Vendor | Open | Open Decision | Steve Trust | 46142 | 3-High | 289 |  | FALSE
RAID | PMO | Decision | D-181 | VIM-Approval matrix for non PO invoices | Open | Open Decision | Nevin Varkey | 46157 | 2-Medium | 253 |  | FALSE
RAID | PMO | Decision | D-187 | Translations for config and documents | Open | Open Decision | Sam Houff | 46129 | 2-Medium | 439 |  | FALSE
RAID | PMO | Decision | D-190 | Key for Customer | Open | Open Decision | Kim Kolesar/Michelle Connors | 46157 | 3-High | 73 |  | FALSE
RAID | PMO | Decision | D-193 | Post go live management of VC models | Open | Open Decision | PTM | 46168 | 2-Medium | 73 |  | FALSE
RAID | PMO | Decision | D-200 | Inventory as Special Stock doesn't allow for another Special Stock designation | Open | Open Decision | Kasey, Ric, Brad | 46157 | 4-Critical | 72 |  | FALSE
RAID | PMO | Decision | D-204 | Structure of the IT Support role in production environment | Open | Open Decision | Kinnary | 46157 | 1-Low | 71 |  | FALSE
RAID | PMO | Decision | D-208 | Intercompany recharge standard | Open | Open Decision | Joel Flemming/Kasey Hughes | 46155 | 3-High |  |  | FALSE
RAID | PMO | Decision | D-209 | Payment terms standardization approval | Open | Open Decision | Brian Wagner | 46142 | 2-Medium |  |  | FALSE
RAID | PMO | Decision | D-210 | Product / Service revenue Classification and Definition | Open | Open Decision | Brian Wagner | 46157 | 2-Medium |  |  | FALSE
RAID | PMO | Decision | D-221 | Corporate‑Only GL Account Usage | Open | Open Decision | Brian | 46188 | 2-Medium | 59 |  | FALSE
RAID | PMO | Decision | D-223 | Sales Order Confirmation query report | Open | Open Decision | Joel / Ric |  | 2-Medium | 10 |  | FALSE
RAID | Finance | Action | A-105 | Mapping of valuation class to indirect Material group | In Progress | Open Action | Kasey Hughes | 30/04/26 | 2-Medium |  |  | FALSE
RAID | OTC | Action | A-108 | Need definition of Industry and Application for customer master data | In Progress | Open Action | Ben Kim Anders | 5/22/20206 | 2-Medium |  |  | FALSE
RAID | Technical | Action | A-124 | Request to have 3rd Party tax Engine (Vertex) connected to DS4. This is needed in order to avoid tax errors during data loads and processing. | Open | Open Action | Kinnary | 46167 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-147 | Approval for Workflow | In Progress | Open Action | Brian Wagner | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-148 | Approval for Credit Management | In Progress | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-157 | Global P&AI P&L view (China Sales) | In Progress | Open Action | Anders Syverson | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-158 | Service and Over Time Accounting | Open | Open Action | Steve Trust | 46157 | 2-Medium |  |  | FALSE
RAID | Reporting | Action | A-163 | Reporting & Analytic value flows | Open | Open Action | Steve Trust |  | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-166 | Transfer Pricing Process | In Progress | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-169 | Inter-company Transactional Matrix | In Progress | Open Action | Jon Marsh | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-170 | Coordination of Global Period-end Close Calendar Roll | In Progress | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-171 | Payroll interface & Mapping | Open | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-172 | Concur Interface & Mapping | Open | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-173 | Demo & Loaner Data & Processes | Open | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-176 | Intercompany Chargebacks, Settlements, & Allocations | In Progress | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-177 | Inventory End of Life.Obsolescence Processes & Reporting | Open | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-179 | Vertex Tax Interface | In Progress | Open Action | Matt C | 30/04/26 | 3-High |  |  | FALSE
RAID | Finance | Action | A-184 | Intangibles | In Progress | Open Action | Matt C | 30/04/26 | 3-High |  |  | FALSE
RAID | PTP | Action | A-188 | VIM-Return to Vendor Reason Codes and Texts | In Progress | Open Action | Steve Trust |  | 2-Medium |  |  | FALSE
RAID | PTP | Action | A-194 | VIM-Supported Languages Documentation | Open | Open Action | Karen Moshgat |  | 2-Medium |  |  | FALSE
RAID | PTP | Action | A-202 | VIM-Company-Specific Waiting for Goods Receipt Configuration | Open | Open Action | Karen Moshgat |  | 2-Medium |  |  | FALSE
RAID | PTP | Action | A-208 | VIM-Tolerance Settings for AP | Open | Open Action | Femi O |  | 1-Low |  |  | FALSE
RAID | PTP | Action | A-217 | OT-Content Repository Requirements for Archiving | Open | Overdue Action | Nevin Varkey | 46136 | 2-Medium | 14 |  | FALSE | ACT-OVD | Action | Action | Red | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RAID | PTP | Action | A-225 | VIM-Intercompany invoices (Entitites within SAP and outside of SAP) | Open | Overdue Action | Femi O | 46022 | 1-Low | 128 |  | FALSE | ACT-OVD | Action | Action | Red | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RAID | PTP | Action | A-228 | Mobile approvals | Open | Overdue Action | Bijoy KrishnaDas | 46022 | 2-Medium | 128 |  | FALSE | ACT-OVD | Action | Action | Red | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RAID | PTM | Action | A-229 | ATP Demo | Open | Open Action | Matt Palastro, Dave Duda, Kim Kolesar | 46157 | 1-Low |  |  | FALSE
RAID | Finance | Action | A-233 | Fixed assets BPD to be updated to outline the strategy of when to include an equipment master. | Open | Open Action | Brian, Steve | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Technical | Action | A-237 | GTS Denied Party Content Licensing required | Open | Overdue Action | Anders Syverson | 46108 | 2-Medium | 42 |  | FALSE | ACT-OVD | Action | Action | Red | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RAID | Finance | Action | A-238 | VSiT functionality for MTO | Open | Open Action | Kasey Hughes | 30/04/26 | 3-High |  |  | FALSE
RAID | Finance | Action | A-239 | Add scope functionality to support IC chargebacks with RRB | Open | Open Action | Kasey Hughes | 30/04/26 | 3-High |  |  | FALSE
RAID | PTP | Action | A-249 | Need Classification detail for each material class | Open | Open Action | Sam Houff/Chip Holder |  | 2-Medium |  |  | FALSE
RAID | Data | Action | A-251 | Full team review of Material pre-load | Open | Open Action | PMO |  | 3-High |  |  | FALSE
RAID | Data | Action | A-252 | Load materials to VC client for component availablilty to build Super BOMs | Open | Open Action | Chip Holder |  | 3-High |  |  | FALSE
RAID | Data | Action | A-253 | Data Objects for GTS | Open | Open Action | James Van Riper |  | 3-High |  |  | FALSE
RAID | Test | Action | A-254 | Q-Test Testing and Defect Training | Open | Open Action | Renee DiTullio |  | 2-Medium |  |  | FALSE
RAID | PMO | Action | A-255 | Add the user roles to the BPD's once defined | Open | Open Action | Renee DiTullio |  | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-257 | Set Activity Rates for Service | Open | Open Action | Brian Wagner | 30/04/26 | 1-Low |  |  | FALSE
RAID | OTC | Action | A-258 | Service Type & Valuation Type decision | In Progress | Open Action | OTC/Finance |  | 2-Medium |  |  | FALSE
RAID | PTM | Action | A-260 | Book time for discussion with Solartron and Calgary re:Projects | In Progress | Overdue Action | Dave Duda | 46142 | 2-Medium | 8 |  | FALSE | ACT-OVD | Action | Action | Red | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RAID | Finance | Action | A-261 | Secure license for D&B Credit Score interface | Open | Overdue Action | Anders Syverson | 46127 | 3-High | 23 |  | FALSE | ACT-OVD | Action | Action | Red | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RAID | Finance | Action | A-262 | Mapping of Concur and Ariba data to SAP | Open | Open Action | Finance Team | 30/04/26 | 3-High |  |  | FALSE
RAID | Finance | Action | A-263 | End to End process flows and narratives | Open | Open Action | Finance Team | 30/04/26 | 3-High |  |  | FALSE
RAID |  | Action | A-264 | Security roles for Testing as it relates to BPDs | Open | Overdue Action | All | 46094 | 2-Medium | 56 |  | FALSE | ACT-OVD | Action | Action | Red | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RAID |  | Action | A-264 | Security roles for Testing as it relates to BPDs | Open | Overdue Action | All | 46094 | 2-Medium | 56 |  | FALSE | WS-UNMAPPED | Data Quality | All | Yellow | Workstream not mapped/blank | [Check Date] | [Mapping Gap] | [PMO Owner] | [Mapping Fix ETA]
RAID | Finance | Action | A-267 | Activity rates calculation approach (production and service) | Open | Open Action | Finance Team | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-268 | Inventory type to GL mapping review | Open | Open Action | PTM/Finance | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-269 | Corporate cost center structure, including international design to be tested | Open | Open Action | Finance Team | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-270 | Credit management configuration alignment | Open | Open Action | Femi | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-271 | Sales Orders criteria communication to business | Open | Open Action | Corp finance? | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-272 | Orders and backlog reporting validation | Open | Open Action | OTC/Finance | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-273 | AR1 report development | Open | Open Action | Femi | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-275 | Fixed asset validation outstanding | Open | Open Action | Business | 30/04/26 | 3-High |  |  | FALSE
RAID | Finance | Action | A-276 | Customer master data cleanup incomplete | Open | Open Action | OTC/Finance | 30/04/26 | 3-High |  |  | FALSE
RAID | Finance | Action | A-277 | business process definition for credit block escalation | Open | Open Action | Femi | 30/04/26 | 3-High |  |  | FALSE
RAID | Finance | Action | A-279 | Verification that finance user requirements are met | Open | Open Action | All | 30/04/26 | 3-High |  |  | FALSE
RAID | Finance | Action | A-280 | HFM load extracts to be developed | Open | Open Action | Tony Jose | 30/04/26 | 2-Medium |  |  | FALSE
RAID | OTC | Action | A-284 | Identify obsoleted products to load | Open | Open Action | Kim/Sam |  | 2-Medium |  |  | FALSE
RAID | PTM | Action | A-285 | Attachments in SAP | Open | Overdue Action | Joel/Kinnary | 46136 | 2-Medium | 14 |  | FALSE | ACT-OVD | Action | Action | Red | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RAID | Finance | Action | A-286 | Communcate validation rules | Open | Open Action | Kasey Hughes | 30/04/26 | 3-High |  |  | FALSE
RAID | OTC | Action | A-287 | Tax confirguration | Open | Open Action | Ric Haraida |  | 3-High |  |  | FALSE
RAID | OTC | Action | A-288 | Define dropdown values for Customer type | Open | Overdue Action | Brian | 46136 | 2-Medium | 14 |  | FALSE | ACT-OVD | Action | Action | Red | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RAID | PTP | Action | A-292 | Company codes for sites not in deployment 1 | Open | Overdue Action | Kasey Hughes | 46106 | 2-Medium | 44 |  | FALSE | ACT-OVD | Action | Action | Red | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RAID | PTP | Action | A-294 | Cost Center mapping details for SF | Open | Overdue Action | Brian Wagner | 46142 | 2-Medium | 8 |  | FALSE | ACT-OVD | Action | Action | Red | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RAID | PTM | Action | A-296 | Base Unit Of Measure | In Progress | Open Action |  |  | 3-High |  |  | FALSE | OWN-UNASSIGNED | Data Quality | All | Yellow | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
RAID | PMO | Action | A-297 | ITC2 Testing resources by location | Open | Overdue Action | Joel / Kinnary / Renee / Chris | 46142 | 2-Medium | 8 |  | FALSE | ACT-OVD | Action | Action | Red | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RAID | Finance | Action | A-298 | OTA Netting Presentation | Open | Open Action | Kasey Hughes | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-220 | Bundled Obligations process | Open | Open Action | Finance / OTC | 30/04/26 | 3-High |  |  | FALSE
RAID | Finance | Action | A-220 | Manual Revenue Adjustments | Open | Open Action | Finance | 30/04/26 | 2-Medium |  |  | FALSE
RAID | Finance | Action | A-220 | Delayed Revenue Recognition on Projects | Open | Open Action | Finance | 30/04/26 | 4-Critical |  |  | FALSE
RAID | Finance | Action | A-220 | Tax not set up for Canada Plants | Open | Open Action | Finance |  | 4-Critical |  |  | FALSE

## PQ_HealthReasonCatalog
Reason Code | Reason Category | Severity | Applies To | Reason Template | Placeholder Date | Placeholder Type | Placeholder Owner | Placeholder Notes
SCH-OVD | Schedule | Red | Project Plan | Task is overdue and requires immediate action | [Due Date] | [Delay Type] | [Owner] | [Recovery Plan]
SCH-SHS | Schedule | Yellow | Project Plan | Task should have started but has not progressed | [Start Date] | [Dependency/Constraint] | [Owner] | [Mitigation]
SCH-CRIT-UPCOMING | Schedule | Blue | Project Plan | Critical task starts within two weeks | [Start Date] | [Critical Path Driver] | [Owner] | [Readiness Check]
ISS-ESC | Issue | Red | Issue | Escalated issue requiring immediate resolution | [Escalation Date] | [Issue Type] | [Owner] | [Escalation Note]
ISS-OPEN | Issue | Yellow | Issue | Open issue tracked with manageable timeline impact | [Issue Date] | [Issue Type] | [Owner] | [Action Plan]
ACT-OVD | Action | Red | Action | Action item is overdue | [Target Date] | [Action Type] | [Owner] | [Recovery Plan]
RSK-OPEN | Risk | Yellow | Risk | Open risk requiring active monitoring | [Risk Logged Date] | [Risk Type] | [Risk Owner] | [Mitigation Plan]
OWN-UNASSIGNED | Data Quality | Yellow | All | No owner assigned to item | [Check Date] | [Assignment Gap] | [Assign Owner] | [Assignment ETA]
WS-UNMAPPED | Data Quality | Yellow | All | Workstream not mapped/blank | [Check Date] | [Mapping Gap] | [PMO Owner] | [Mapping Fix ETA]

## PQ_WorkstreamActionSummary
Workstream | Assigned To | Source | Action Window | Count
Business Readniess | Training | Project Plan | Should Have Started | 4
Business Role Management | Unassigned | Project Plan | Should Have Started | 1
Business Role Management | Unassigned | Project Plan | Starting This Week | 1
Data | Chip Holder | Action | Open Action | 1
Data | James Van Riper | Action | Open Action | 1
Data | PMO | Action | Open Action | 1
Data Project Create | Basis | Project Plan | Starting This Week | 2
Data Project Create | Data Migration Team | Project Plan | Starting This Week | 1
Data Readiness | Basis | Project Plan | Starting Next 2 Weeks | 6
Data Readiness | Brad | Project Plan | Starting Next 2 Weeks | 1
Data Readiness | Brad Meseck | Project Plan | Starting Next 2 Weeks | 10
Data Readiness | Data Migration Team | Project Plan | Starting Next 2 Weeks | 54
Data Readiness | Eric Heisler | Project Plan | Starting Next 2 Weeks | 24
Data Readiness | Functional Leads | Project Plan | Starting Next 2 Weeks | 1
Data Readiness | James Van Riper | Project Plan | Starting Next 2 Weeks | 12
Data Readiness | Kasey Hughes | Project Plan | Starting Next 2 Weeks | 48
Data Readiness | Kasey Hughes,Femi Oguntala | Project Plan | Starting Next 2 Weeks | 1
Data Readiness | Keith Riley | Project Plan | Starting Next 2 Weeks | 1
Data Readiness | Mark George | Project Plan | Starting Next 2 Weeks | 1
Data Readiness | Nevin Varkey | Project Plan | Starting Next 2 Weeks | 20
Data Readiness | Nevin Varkey,Ric Haraida | Project Plan | Starting Next 2 Weeks | 13
Data Readiness | Nevin Varkkey | Project Plan | Starting Next 2 Weeks | 1
Data Readiness | Ric Haraida | Project Plan | Starting Next 2 Weeks | 9
Data Readiness | Sam | Project Plan | Starting Next 2 Weeks | 2
Data Readiness | Unassigned | Project Plan | Starting Next 2 Weeks | 2
Finance | All | Action | Open Action | 1
Finance | Anders Syverson | Action | Open Action | 1
Finance | Anders Syverson | Action | Overdue Action | 1
Finance | Brian Wagner | Action | Open Action | 2
Finance | Brian, Steve | Action | Open Action | 1
Finance | Business | Action | Open Action | 1
Finance | Corp finance? | Action | Open Action | 1
Finance | Femi | Action | Open Action | 3
Finance | Finance | Issue | Escalated Issue | 1
Finance | Finance | Action | Open Action | 3
Finance | Finance | Issue | Open Issue | 1
Finance | Finance / OTC | Action | Open Action | 1
Finance | Finance Team | Action | Open Action | 4
Finance | Jon Marsh | Action | Open Action | 1
Finance | Kasey Hughes | Action | Open Action | 5
Finance | Kasey Hughes | Issue | Open Issue | 3
Finance | Manoj Patel | Issue | Open Issue | 1
Finance | Matt C | Action | Open Action | 2
Finance | Matt Cummins | Issue | Open Issue | 1
Finance | Michelle | Issue | Open Issue | 2
Finance | OTC | Issue | Open Issue | 2
Finance | OTC/Finance | Action | Open Action | 2
Finance | OTC/PTM/Finance | Issue | Escalated Issue | 1
Finance | PMO | Issue | Open Issue | 8
Finance | PTM/Finance | Action | Open Action | 1
Finance | Rob Rideout | Issue | Open Issue | 1
Finance | Steve Trust | Action | Open Action | 9
Finance | Steve Trust & Kevin Coleman | Issue | Escalated Issue | 1
Finance | Tony Jose | Action | Open Action | 1
Firefighter Configuration | Unassigned | Project Plan | Overdue | 1
Firefighter Configuration | Unassigned | Project Plan | Should Have Started | 2
Firefighter Configuration | Unassigned | Project Plan | Starting This Week | 1
OTC | Ben Kim Anders | Action | Open Action | 1
OTC | Brian | Action | Overdue Action | 1
OTC | Kim/Sam | Action | Open Action | 1
OTC | OTC/Finance | Action | Open Action | 1
OTC | Ric Haraida | Action | Open Action | 1
PMO | Brian | Decision | Open Decision | 1
PMO | Brian Wagner | Decision | Open Decision | 2
PMO | Chris Hanily | Risk | Open Risk | 1
PMO | Joel / Kinnary / Renee / Chris | Action | Overdue Action | 1
PMO | Joel / Ric | Decision | Open Decision | 1
PMO | Joel Flemming | Risk | Open Risk | 2
PMO | Joel Flemming/Kasey Hughes | Decision | Open Decision | 1
PMO | Kasey Hughes | Risk | Open Risk | 1
PMO | Kasey, Ric, Brad | Decision | Open Decision | 1
PMO | Kim Kolesar/Michelle Connors | Decision | Open Decision | 1
PMO | Kinnary | Decision | Open Decision | 1
PMO | Kinnary | Risk | Open Risk | 1
PMO | Nevin Varkey | Decision | Open Decision | 1
PMO | PMO | Risk | Open Risk | 2
PMO | PTM | Decision | Open Decision | 1
PMO | Renee DiTullio | Action | Open Action | 1
PMO | Sam Houff | Decision | Open Decision | 1
PMO | Steve Trust | Decision | Open Decision | 1
PMO | Unassigned | Risk | Open Risk | 7
PTM | Dave Duda | Action | Overdue Action | 1
PTM | Joel/Kinnary | Action | Overdue Action | 1
PTM | Matt Palastro, Dave Duda, Kim Kolesar | Action | Open Action | 1
PTM | Unassigned | Action | Open Action | 1
PTM/PTP | Brad Meseck | Issue | Open Issue | 1
PTP | Bijoy KrishnaDas | Action | Overdue Action | 1
PTP | Brian Wagner | Action | Overdue Action | 1
PTP | Femi O | Action | Open Action | 1
PTP | Femi O | Action | Overdue Action | 1
PTP | Karen Moshgat | Action | Open Action | 2
PTP | Kasey Hughes | Action | Overdue Action | 1
PTP | Nevin Varkey | Action | Overdue Action | 1
PTP | Sam Houff/Chip Holder | Action | Open Action | 1
PTP | Steve Trust | Action | Open Action | 1
QS4 ITC-2 Refresh | PMO | Project Plan | Starting This Week | 1
Release Transports to Client | Dev Team | Project Plan | Starting This Week | 2
Release Transports to Client | Functional Leads | Project Plan | Overdue | 3
Release Transports to Client | Functional Leads | Project Plan | Should Have Started | 4
Release Transports to Client | Functional Leads | Project Plan | Starting Next 2 Weeks | 2
Release Transports to Client | Functional Leads | Project Plan | Starting This Week | 2
Reporting | Steve Trust | Action | Open Action | 1
Rule Set & Role Design | Unassigned | Project Plan | Overdue | 2
Rule Set & Role Design | Unassigned | Project Plan | Should Have Started | 2
Solution Readniess | Unassigned | Project Plan | Overdue | 1
Solution Readniess | Unassigned | Project Plan | Should Have Started | 11
Solution Readniess | Unassigned | Project Plan | Starting This Week | 1
System Setup | Basis | Project Plan | Overdue | 2
System Setup | Basis | Project Plan | Should Have Started | 2
System Setup | Basis | Project Plan | Starting Next 2 Weeks | 7
System Setup | Dev Team | Project Plan | Overdue | 1
System Setup | Dev Team | Project Plan | Should Have Started | 1
System Setup | Dev Team | Project Plan | Starting Next 2 Weeks | 1
System Setup | Functional Leads | Project Plan | Overdue | 1
System Setup | Functional Leads | Project Plan | Should Have Started | 1
System Setup | Functional Leads | Project Plan | Starting Next 2 Weeks | 1
System Setup | Security | Project Plan | Overdue | 1
System Setup | Security | Project Plan | Should Have Started | 1
System Setup | Security | Project Plan | Starting Next 2 Weeks | 3
Technical | Anders Syverson | Action | Overdue Action | 1
Technical | Kinnary | Action | Open Action | 1
Test | Renee DiTullio | Action | Open Action | 1
Testing & Training | Unassigned | Project Plan | Should Have Started | 1
Testing & Training | Unassigned | Project Plan | Starting Next 2 Weeks | 2
Testing & Training | Unassigned | Project Plan | Starting This Week | 1
Unassigned | All | Action | Overdue Action | 1

## PQ_CombinedActionItems
Workstream | Source | Item ID | Title | Status | Action Window | Assigned To | Due Date | Priority | Days Overdue | Pct Complete | Is Critical
| Action | A-264 | Security roles for Testing as it relates to BPDs | Open | Overdue Action | All | 46094 | 2-Medium | 56 |  | FALSE
Business Readniess | Project Plan | 1.4.1.1.1 | Verify Role Mapping Complete | Future Task | Should Have Started | Training | Fri 7/31/26 | 500 | 0 | 0.46 | No
Business Readniess | Project Plan | 1.4.1.1.3 | Develop Course ppts | Future Task | Should Have Started | Training | Fri 8/28/26 | 500 | 0 | 0.35 | No
Business Readniess | Project Plan | 1.4.1.1.2 | Develop Curriculum | Future Task | Should Have Started | Training | Fri 7/31/26 | 500 | 0 | 0.3 | Yes
Business Readniess | Project Plan | 1.4.1.1.4 | Develop Work Instructions | Future Task | Should Have Started | Training | Fri 8/28/26 | 500 | 0 | 0.21 | No
Business Role Management | Project Plan | 1.1.2.5.1 | Role Mapping with Business Process and Sub-Process /Functional Area | Future Task | Should Have Started |  | Thu 5/14/26 | 500 | 0 | 0 | No
Business Role Management | Project Plan | 1.1.2.5.2 | Role Upload to SAP GRC | Future Task | Starting This Week |  | Thu 5/21/26 | 500 | 0 | 0 | No
Data | Action | A-252 | Load materials to VC client for component availablilty to build Super BOMs | Open | Open Action | Chip Holder |  | 3-High |  |  | FALSE
Data | Action | A-253 | Data Objects for GTS | Open | Open Action | James Van Riper |  | 3-High |  |  | FALSE
Data | Action | A-251 | Full team review of Material pre-load | Open | Open Action | PMO |  | 3-High |  |  | FALSE
Data Project Create | Project Plan | 1.1.1.5.3.3 | Close Client | Future Task | Starting This Week | Basis | Thu 5/14/26 | 500 | 0 | 0 | Yes
Data Project Create | Project Plan | 1.1.1.5.3.1 | Open Client | Future Task | Starting This Week | Basis | Wed 5/13/26 | 500 | 0 | 0 | Yes
Data Project Create | Project Plan | 1.1.1.5.3.2 | Create Migration Data Project in DMC | Future Task | Starting This Week | Data Migration Team | Thu 5/14/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.3.8 | Post GL Extention Validation | Future Task | Starting Next 2 Weeks |  | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.12 | OTC_CM19_Customer_Master - Bill-To | Future Task | Starting Next 2 Weeks |  | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.14.9 | Close Client | Future Task | Starting Next 2 Weeks | Basis | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.13.3 | Open client for BP number range update | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.13.5 | Close Client | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.14.7 | Open client for BP number range update | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.6.1 | Open Client | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.6.3 | Close Client | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.53.3 | Post Load Validation | Future Task | Starting Next 2 Weeks | Brad | Tue 5/26/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.53.2 | Load | Future Task | Starting Next 2 Weeks | Brad Meseck | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.33.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Brad Meseck | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.36.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Brad Meseck | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.54.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Brad Meseck | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.30.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Brad Meseck | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.54.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Brad Meseck | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.54.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Brad Meseck | Mon 5/25/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.33.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Brad Meseck | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.33.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Brad Meseck | Mon 5/25/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.33.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Brad Meseck | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.4.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.24.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.46.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.52.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.13.6 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.30.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/25/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.27.1 | Extract File | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.27.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.28.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.28.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.9.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.10.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.22.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.26.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.26.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.8.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.25.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.5.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.5.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.25.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.24.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.10.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.8.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.29.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.4.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.29.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.3.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.3.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.30.1 | Extract File | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.54.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.13.8 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.54.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.33.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.7.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.14.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/25/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.14.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.7.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.46.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/25/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.52.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.23.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.33.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.27.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.31.1 | Extract File | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.32.1 | Extract File | Future Task | Starting Next 2 Weeks | Data Migration Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.67.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.24.1 | Extract File | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.9.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.9.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.68.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.22.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.19.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.67.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.68.5 | Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.23.3 | Simulate Load | Future Task | Starting Next 2 Weeks | Data Migration Team | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.26.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.26.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Eric Heisler | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.26.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.26.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Eric Heisler | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.39.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.39.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.38.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.40.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.46.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.41.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.42.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.46.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Eric Heisler | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.41.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.40.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.45.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Mon 5/25/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.43.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.44.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.46.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.43.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.37.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.37.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.38.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.42.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | Starting Next 2 Weeks | Eric Heisler | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.44.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | Eric Heisler | Mon 5/25/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.6.4 | Intercompany Business Partner Setup | Future Task | Starting Next 2 Weeks | Functional Leads | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.57.1 | Run material interface to GTS | Future Task | Starting Next 2 Weeks | James Van Riper | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.65.2 | Set Embargo situations | Future Task | Starting Next 2 Weeks | James Van Riper | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.65.3 | Post Load Validation | Future Task | Starting Next 2 Weeks | James Van Riper | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.57.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | James Van Riper | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.58.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | James Van Riper | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.65.1 | Run report /SAPSLL/EMB_CNTRY_INIT | Future Task | Starting Next 2 Weeks | James Van Riper | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.56.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | James Van Riper | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.58.1 | Load Descartes XML File | Future Task | Starting Next 2 Weeks | James Van Riper | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.60.1 | Load Descartes XML File | Future Task | Starting Next 2 Weeks | James Van Riper | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.60.2 | Post Load Validation | Future Task | Starting Next 2 Weeks | James Van Riper | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.56.1 | Run material interface to GTS | Future Task | Starting Next 2 Weeks | James Van Riper | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.55.1 | Run material interface to GTS | Future Task | Starting Next 2 Weeks | James Van Riper | Mon 5/25/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.10.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.2.3 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.3.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.3.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.4.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.10.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.4.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.8.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.2.2 | Load | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.4.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.2.1 | Manual File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.10.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.52.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.67.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.5.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.8.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.5.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.8.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.5.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.10.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.3.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.8.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.68.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.9.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.3.7 | Extend GL to all Company Codes | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.7.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.4.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.11.3 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/25/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.7.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/25/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.7.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.1.1 | Manual File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.1.3 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.68.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.9.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.52.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.67.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.68.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.67.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.1.2 | Load | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.67.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.52.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.11.1 | Manual File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.5.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.9.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.3.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.68.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.11.2 | Load | Future Task | Starting Next 2 Weeks | Kasey Hughes | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.7.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.52.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Kasey Hughes,Femi Oguntala | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.6.2 | Service Enterprise Setup | Future Task | Starting Next 2 Weeks | Keith Riley | Fri 5/29/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.1 | PMO Authorization to Start Data Loads | Future Task | Starting Next 2 Weeks | Mark George | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.24.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.51.1 | Manual File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Nevin Varkey | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.28.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.27.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.27.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.29.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.29.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.29.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.24.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.28.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.20.3 | Simulate Load/ Not Needed | Future Task | Starting Next 2 Weeks | Nevin Varkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.20.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.20.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.20.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.27.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.20.1 | Extract File(Will Extract from LFA1) | Future Task | Starting Next 2 Weeks | Nevin Varkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.19.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.28.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.29.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.28.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.25.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.25.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.25.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Wed 5/20/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.22.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.25.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.22.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.23.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.22.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.23.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.23.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.23.6 | Post Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.24.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Tue 5/19/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.22.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Nevin Varkey,Ric Haraida | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.20.5 | Load | Future Task | Starting Next 2 Weeks | Nevin Varkkey | Mon 5/18/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.14.8 | Update number range BP02 from Internal to External | Future Task | Starting Next 2 Weeks | Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.13.7 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Ric Haraida | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.13.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.14.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.13.2 | Pre Load Validation | Future Task | Starting Next 2 Weeks | Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.13.4 | Update number range BP02 from Internal to External | Future Task | Starting Next 2 Weeks | Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.14.4 | Error and Defect Mitigation | Future Task | Starting Next 2 Weeks | Ric Haraida | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.14.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Ric Haraida | Thu 5/21/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.13.9 | Post Load Validation | Future Task | Starting Next 2 Weeks | Ric Haraida | Mon 5/25/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.54.1 | Load File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Sam | Fri 5/22/26 | 500 | 0 | 0 | Yes
Data Readiness | Project Plan | 1.2.2.2.53.1 | Manual File Staged and Posted "Ready" | Future Task | Starting Next 2 Weeks | Sam | Fri 5/22/26 | 500 | 0 | 0 | Yes
Finance | Action | A-279 | Verification that finance user requirements are met | Open | Open Action | All | 30/04/26 | 3-High |  |  | FALSE
Finance | Action | A-157 | Global P&AI P&L view (China Sales) | In Progress | Open Action | Anders Syverson | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-261 | Secure license for D&B Credit Score interface | Open | Overdue Action | Anders Syverson | 46127 | 3-High | 23 |  | FALSE
Finance | Action | A-147 | Approval for Workflow | In Progress | Open Action | Brian Wagner | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-257 | Set Activity Rates for Service | Open | Open Action | Brian Wagner | 30/04/26 | 1-Low |  |  | FALSE
Finance | Action | A-233 | Fixed assets BPD to be updated to outline the strategy of when to include an equipment master. | Open | Open Action | Brian, Steve | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-275 | Fixed asset validation outstanding | Open | Open Action | Business | 30/04/26 | 3-High |  |  | FALSE
Finance | Action | A-271 | Sales Orders criteria communication to business | Open | Open Action | Corp finance? | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-270 | Credit management configuration alignment | Open | Open Action | Femi | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-277 | business process definition for credit block escalation | Open | Open Action | Femi | 30/04/26 | 3-High |  |  | FALSE
Finance | Action | A-273 | AR1 report development | Open | Open Action | Femi | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Issue | I-119 | Incomplete finance and cross functional design documentation and approval | Escalated | Escalated Issue | Finance | 46142 | 2-Medium | 67 |  | FALSE
Finance | Action | A-220 | Delayed Revenue Recognition on Projects | Open | Open Action | Finance | 30/04/26 | 4-Critical |  |  | FALSE
Finance | Action | A-220 | Tax not set up for Canada Plants | Open | Open Action | Finance |  | 4-Critical |  |  | FALSE
Finance | Action | A-220 | Manual Revenue Adjustments | Open | Open Action | Finance | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Issue | I-110 | Missing process narratives and controls required to validate completed design | Open | Open Issue | Finance | 46142 | 2-Medium | 67 |  | FALSE
Finance | Action | A-220 | Bundled Obligations process | Open | Open Action | Finance / OTC | 30/04/26 | 3-High |  |  | FALSE
Finance | Action | A-263 | End to End process flows and narratives | Open | Open Action | Finance Team | 30/04/26 | 3-High |  |  | FALSE
Finance | Action | A-262 | Mapping of Concur and Ariba data to SAP | Open | Open Action | Finance Team | 30/04/26 | 3-High |  |  | FALSE
Finance | Action | A-269 | Corporate cost center structure, including international design to be tested | Open | Open Action | Finance Team | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-267 | Activity rates calculation approach (production and service) | Open | Open Action | Finance Team | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-169 | Inter-company Transactional Matrix | In Progress | Open Action | Jon Marsh | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-286 | Communcate validation rules | Open | Open Action | Kasey Hughes | 30/04/26 | 3-High |  |  | FALSE
Finance | Action | A-298 | OTA Netting Presentation | Open | Open Action | Kasey Hughes | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-239 | Add scope functionality to support IC chargebacks with RRB | Open | Open Action | Kasey Hughes | 30/04/26 | 3-High |  |  | FALSE
Finance | Action | A-238 | VSiT functionality for MTO | Open | Open Action | Kasey Hughes | 30/04/26 | 3-High |  |  | FALSE
Finance | Action | A-105 | Mapping of valuation class to indirect Material group | In Progress | Open Action | Kasey Hughes | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Issue | I-120 | Financial statement versions and FX reporting | Open | Open Issue | Kasey Hughes | 46142 | 2-Medium | 67 |  | FALSE
Finance | Issue | I-116 | FX treatment, reporting and controls undefined | Open | Open Issue | Kasey Hughes | 46142 | 3-High | 67 |  | FALSE
Finance | Issue | I-122 | Legal entity/profit center/HFM mapping complexity | Open | Open Issue | Kasey Hughes | 46142 | 2-Medium | 25 |  | FALSE
Finance | Issue | I-113 | Supplier banking data gaps and dual maintenance requirements - need to identify process | Open | Open Issue | Manoj Patel | 46142 | 2-Medium | 67 |  | FALSE
Finance | Action | A-184 | Intangibles | In Progress | Open Action | Matt C | 30/04/26 | 3-High |  |  | FALSE
Finance | Action | A-179 | Vertex Tax Interface | In Progress | Open Action | Matt C | 30/04/26 | 3-High |  |  | FALSE
Finance | Issue | I-123 | Vertex Certificate Center delay | Open | Open Issue | Matt Cummins | 46157 | 2-Medium | 25 |  | FALSE
Finance | Issue | I-100 | Master data change process incomplete | Open | Open Issue | Michelle | 46174 | 2-Medium | 67 |  | FALSE
Finance | Issue | I-102 | Data clean up requirements not communicated to business | Open | Open Issue | Michelle | 46174 | 2-Medium | 67 |  | FALSE
Finance | Issue | I-106 | Open service contracts data requirements | Open | Open Issue | OTC | 46174 | 2-Medium | 67 |  | FALSE
Finance | Issue | I-107 | Service requirements not designed. Business requirements not gathered | Open | Open Issue | OTC | 46174 | 2-Medium | 67 |  | FALSE
Finance | Action | A-276 | Customer master data cleanup incomplete | Open | Open Action | OTC/Finance | 30/04/26 | 3-High |  |  | FALSE
Finance | Action | A-272 | Orders and backlog reporting validation | Open | Open Action | OTC/Finance | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Issue | I-118 | VSIT issue with COGS matching to revenue for MTO | Escalated | Escalated Issue | OTC/PTM/Finance | 46157 | 4-Critical | 67 |  | FALSE
Finance | Issue | I-108 | Reporting resourcing gap | Open | Open Issue | PMO | 46142 | 2-Medium | 67 |  | FALSE
Finance | Issue | I-109 | OpenText finance items stalled | Open | Open Issue | PMO | 46142 | 2-Medium | 67 |  | FALSE
Finance | Issue | I-114 | Key reports not reviewed cross‑functionally | Open | Open Issue | PMO | 46142 | 3-High | 67 |  | FALSE
Finance | Issue | I-115 | Additional business resources / Business Process Leads (BPLs) needed for core finance processes | Open | Open Issue | PMO | 46142 | 3-High | 67 |  | FALSE
Finance | Issue | I-103 | Flexible workflow functionality, technical resource alignment across functions | Open | Open Issue | PMO | 46174 | 2-Medium | 67 |  | FALSE
Finance | Issue | I-117 | Reporting attributes/characteristics not fully defined and approved | Open | Open Issue | PMO | 46142 | 3-High | 67 |  | FALSE
Finance | Issue | I-101 | No change management process defined | Open | Open Issue | PMO | 46174 | 2-Medium | 67 |  | FALSE
Finance | Issue | I-112 | No SAP functional owner for banking and treasury (open position) | Open | Open Issue | PMO | 46142 | 3-High | 67 |  | FALSE
Finance | Action | A-268 | Inventory type to GL mapping review | Open | Open Action | PTM/Finance | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Issue | I-104 | Single purchasing organization implications | Open | Open Issue | Rob Rideout | 46174 | 2-Medium | 67 |  | FALSE
Finance | Action | A-177 | Inventory End of Life.Obsolescence Processes & Reporting | Open | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-170 | Coordination of Global Period-end Close Calendar Roll | In Progress | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-171 | Payroll interface & Mapping | Open | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-172 | Concur Interface & Mapping | Open | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-173 | Demo & Loaner Data & Processes | Open | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-176 | Intercompany Chargebacks, Settlements, & Allocations | In Progress | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-158 | Service and Over Time Accounting | Open | Open Action | Steve Trust | 46157 | 2-Medium |  |  | FALSE
Finance | Action | A-166 | Transfer Pricing Process | In Progress | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Action | A-148 | Approval for Credit Management | In Progress | Open Action | Steve Trust | 30/04/26 | 2-Medium |  |  | FALSE
Finance | Issue | I-105 | Data: Tax exemption certificate cleanup resourcing | Escalated | Escalated Issue | Steve Trust & Kevin Coleman | 46174 | 2-Medium | 67 |  | FALSE
Finance | Action | A-280 | HFM load extracts to be developed | Open | Open Action | Tony Jose | 30/04/26 | 2-Medium |  |  | FALSE
Firefighter Configuration | Project Plan | 1.1.2.6.1 | Firefighter ID setup | Future Task | Overdue |  | Thu 5/7/26 | 500 | 1 | 0 | No
Firefighter Configuration | Project Plan | 1.1.2.6.1 | Firefighter ID setup | Future Task | Should Have Started |  | Thu 5/7/26 | 500 | 1 | 0 | No
Firefighter Configuration | Project Plan | 1.1.2.6.2 | Firefighter log settings | Future Task | Should Have Started |  | Thu 5/14/26 | 500 | 0 | 0 | No
Firefighter Configuration | Project Plan | 1.1.2.6.3 | Functional validation | Future Task | Starting This Week |  | Thu 5/21/26 | 500 | 0 | 0 | No
OTC | Action | A-108 | Need definition of Industry and Application for customer master data | In Progress | Open Action | Ben Kim Anders | 5/22/20206 | 2-Medium |  |  | FALSE
OTC | Action | A-288 | Define dropdown values for Customer type | Open | Overdue Action | Brian | 46136 | 2-Medium | 14 |  | FALSE
OTC | Action | A-284 | Identify obsoleted products to load | Open | Open Action | Kim/Sam |  | 2-Medium |  |  | FALSE
OTC | Action | A-258 | Service Type & Valuation Type decision | In Progress | Open Action | OTC/Finance |  | 2-Medium |  |  | FALSE
OTC | Action | A-287 | Tax confirguration | Open | Open Action | Ric Haraida |  | 3-High |  |  | FALSE
PMO | Risk | R-132 | Training misaligned with finalized processes | Open | Open Risk |  |  |  | 67 |  | FALSE
PMO | Risk | R-133 | Product Hieararchy | Open | Open Risk |  |  |  | 67 |  | FALSE
PMO | Risk | R-134 | Inconsistent cross‑team engagement | Open | Open Risk |  |  |  | 67 |  | FALSE
PMO | Risk | R-138 | Finance workflows and interfaces not fully identified | Open | Open Risk |  |  |  | 67 |  | FALSE
PMO | Risk | R-139 | Data readiness lag | Open | Open Risk |  |  |  | 67 |  | FALSE
PMO | Risk | R-140 | DLA flexible workflows configuration | Open | Open Risk |  |  |  | 67 |  | FALSE
PMO | Risk | R-141 | Projects for D1 | Open | Open Risk |  |  |  | 66 |  | FALSE
PMO | Decision | D-221 | Corporate‑Only GL Account Usage | Open | Open Decision | Brian | 46188 | 2-Medium | 59 |  | FALSE
PMO | Decision | D-209 | Payment terms standardization approval | Open | Open Decision | Brian Wagner | 46142 | 2-Medium |  |  | FALSE
PMO | Decision | D-210 | Product / Service revenue Classification and Definition | Open | Open Decision | Brian Wagner | 46157 | 2-Medium |  |  | FALSE
PMO | Risk | R-149 | Scribe Availability | Open | Open Risk | Chris Hanily | 46150 |  | 1 |  | FALSE
PMO | Action | A-297 | ITC2 Testing resources by location | Open | Overdue Action | Joel / Kinnary / Renee / Chris | 46142 | 2-Medium | 8 |  | FALSE
PMO | Decision | D-223 | Sales Order Confirmation query report | Open | Open Decision | Joel / Ric |  | 2-Medium | 10 |  | FALSE
PMO | Risk | R-145 | Bluesnap Credit Card Certification | Open | Open Risk | Joel Flemming | 46143 |  | 29 |  | FALSE
PMO | Risk | R-147 | Commerce cloud system unavailable until June to develop and test interfaces to S4 | Open | Open Risk | Joel Flemming | 46188 |  | 2 |  | FALSE
PMO | Decision | D-208 | Intercompany recharge standard | Open | Open Decision | Joel Flemming/Kasey Hughes | 46155 | 3-High |  |  | FALSE
PMO | Risk | R-143 | Finance Role Design for ITC1 | Open | Open Risk | Kasey Hughes | 46093 |  | 59 |  | FALSE
PMO | Decision | D-200 | Inventory as Special Stock doesn't allow for another Special Stock designation | Open | Open Decision | Kasey, Ric, Brad | 46157 | 4-Critical | 72 |  | FALSE
PMO | Decision | D-190 | Key for Customer | Open | Open Decision | Kim Kolesar/Michelle Connors | 46157 | 3-High | 73 |  | FALSE
PMO | Decision | D-204 | Structure of the IT Support role in production environment | Open | Open Decision | Kinnary | 46157 | 1-Low | 71 |  | FALSE
PMO | Risk | R-146 | Functional Specs Behind Schedule | Open | Open Risk | Kinnary | 46143 |  | 23 |  | FALSE
PMO | Decision | D-181 | VIM-Approval matrix for non PO invoices | Open | Open Decision | Nevin Varkey | 46157 | 2-Medium | 253 |  | FALSE
PMO | Risk | R-129 | SME for GTS | Open | Open Risk | PMO |  |  | 74 |  | FALSE
PMO | Risk | R-148 | Training Readiness | Open | Open Risk | PMO |  |  | 1 |  | FALSE
PMO | Decision | D-193 | Post go live management of VC models | Open | Open Decision | PTM | 46168 | 2-Medium | 73 |  | FALSE
PMO | Action | A-255 | Add the user roles to the BPD's once defined | Open | Open Action | Renee DiTullio |  | 2-Medium |  |  | FALSE
PMO | Decision | D-187 | Translations for config and documents | Open | Open Decision | Sam Houff | 46129 | 2-Medium | 439 |  | FALSE
PMO | Decision | D-154 | Credit Rating Agency Vendor | Open | Open Decision | Steve Trust | 46142 | 3-High | 289 |  | FALSE
PTM | Action | A-296 | Base Unit Of Measure | In Progress | Open Action |  |  | 3-High |  |  | FALSE
PTM | Action | A-260 | Book time for discussion with Solartron and Calgary re:Projects | In Progress | Overdue Action | Dave Duda | 46142 | 2-Medium | 8 |  | FALSE
PTM | Action | A-285 | Attachments in SAP | Open | Overdue Action | Joel/Kinnary | 46136 | 2-Medium | 14 |  | FALSE
PTM | Action | A-229 | ATP Demo | Open | Open Action | Matt Palastro, Dave Duda, Kim Kolesar | 46157 | 1-Low |  |  | FALSE
PTM/PTP | Issue | I-121 | Attachment links cannot reference network drives | Open | Open Issue | Brad Meseck | 46128 | 2-Medium | 63 |  | FALSE
PTP | Action | A-228 | Mobile approvals | Open | Overdue Action | Bijoy KrishnaDas | 46022 | 2-Medium | 128 |  | FALSE
PTP | Action | A-294 | Cost Center mapping details for SF | Open | Overdue Action | Brian Wagner | 46142 | 2-Medium | 8 |  | FALSE
PTP | Action | A-208 | VIM-Tolerance Settings for AP | Open | Open Action | Femi O |  | 1-Low |  |  | FALSE
PTP | Action | A-225 | VIM-Intercompany invoices (Entitites within SAP and outside of SAP) | Open | Overdue Action | Femi O | 46022 | 1-Low | 128 |  | FALSE
PTP | Action | A-194 | VIM-Supported Languages Documentation | Open | Open Action | Karen Moshgat |  | 2-Medium |  |  | FALSE
PTP | Action | A-202 | VIM-Company-Specific Waiting for Goods Receipt Configuration | Open | Open Action | Karen Moshgat |  | 2-Medium |  |  | FALSE
PTP | Action | A-292 | Company codes for sites not in deployment 1 | Open | Overdue Action | Kasey Hughes | 46106 | 2-Medium | 44 |  | FALSE
PTP | Action | A-217 | OT-Content Repository Requirements for Archiving | Open | Overdue Action | Nevin Varkey | 46136 | 2-Medium | 14 |  | FALSE
PTP | Action | A-249 | Need Classification detail for each material class | Open | Open Action | Sam Houff/Chip Holder |  | 2-Medium |  |  | FALSE
PTP | Action | A-188 | VIM-Return to Vendor Reason Codes and Texts | In Progress | Open Action | Steve Trust |  | 2-Medium |  |  | FALSE
QS4 ITC-2 Refresh | Project Plan | 1.1.1.5.4 | Environment Ready for Test | Future Task | Starting This Week | PMO | Thu 5/14/26 | 500 | 0 | 0 | Yes
Release Transports to Client | Project Plan | 1.1.1.5.2.7 | Import Group 4 - workbench / dev work | Future Task | Starting This Week | Dev Team | Tue 5/12/26 | 500 | 0 | 0 | Yes
Release Transports to Client | Project Plan | 1.1.1.5.2.8 | Import Group 5 - Config to support dev workbench | Future Task | Starting This Week | Dev Team | Wed 5/13/26 | 500 | 0 | 0 | Yes
Release Transports to Client | Project Plan | 1.1.1.5.2.3 | Import Group 2 - Core Transports | Future Task | Overdue | Functional Leads | Thu 5/7/26 | 500 | 1 | 0.25 | Yes
Release Transports to Client | Project Plan | 1.1.1.5.2.2 | Manual activities group 1 | Future Task | Overdue | Functional Leads | Thu 5/7/26 | 500 | 1 | 0.25 | Yes
Release Transports to Client | Project Plan | 1.1.1.5.2.1 | Import Group 1 - Ent Structure | Future Task | Overdue | Functional Leads | Tue 5/5/26 | 500 | 3 | 0.25 | Yes
Release Transports to Client | Project Plan | 1.1.1.5.2.1 | Import Group 1 - Ent Structure | Future Task | Should Have Started | Functional Leads | Tue 5/5/26 | 500 | 3 | 0.25 | Yes
Release Transports to Client | Project Plan | 1.1.1.5.2.2 | Manual activities group 1 | Future Task | Should Have Started | Functional Leads | Thu 5/7/26 | 500 | 1 | 0.25 | Yes
Release Transports to Client | Project Plan | 1.1.1.5.2.4 | Manual activities group 2 | Future Task | Should Have Started | Functional Leads | Fri 5/8/26 | 500 | 0 | 0.25 | Yes
Release Transports to Client | Project Plan | 1.1.1.5.2.3 | Import Group 2 - Core Transports | Future Task | Should Have Started | Functional Leads | Thu 5/7/26 | 500 | 1 | 0.25 | Yes
Release Transports to Client | Project Plan | 1.1.1.6.2.2 | Manual activities group 1 | Future Task | Starting Next 2 Weeks | Functional Leads | Mon 5/25/26 | 500 | 0 | 0 | Yes
Release Transports to Client | Project Plan | 1.1.1.6.2.1 | Import Group 1 - Ent Structure | Future Task | Starting Next 2 Weeks | Functional Leads | Thu 5/21/26 | 500 | 0 | 0 | Yes
Release Transports to Client | Project Plan | 1.1.1.5.2.5 | Import Group 3 - prior to transactions | Future Task | Starting This Week | Functional Leads | Mon 5/11/26 | 500 | 0 | 0.25 | Yes
Release Transports to Client | Project Plan | 1.1.1.5.2.6 | Manual Activities Group 3 | Future Task | Starting This Week | Functional Leads | Tue 5/12/26 | 500 | 0 | 0.25 | Yes
Reporting | Action | A-163 | Reporting & Analytic value flows | Open | Open Action | Steve Trust |  | 2-Medium |  |  | FALSE
Rule Set & Role Design | Project Plan | 1.1.2.4.5 | Final Review Rule Set and update the recommendations | Late | Overdue |  | Wed 1/7/26 | 500 | 121 | 0.6 | No
Rule Set & Role Design | Project Plan | 1.1.2.4.9 | Risk analysis on existing roles | Future Task | Overdue |  | Thu 5/7/26 | 500 | 1 | 0 | No
Rule Set & Role Design | Project Plan | 1.1.2.4.9 | Risk analysis on existing roles | Future Task | Should Have Started |  | Thu 5/7/26 | 500 | 1 | 0 | No
Rule Set & Role Design | Project Plan | 1.1.2.4.10 | Role remediation planning - Can impact role design & Possible of retesting. | Future Task | Should Have Started |  | Thu 5/21/26 | 500 | 0 | 0 | No
Solution Readniess | Project Plan | 1.3.3.1 | Test Readiness Review (TRR) - ITC 1 | Future Task | Overdue |  | Fri 5/1/26 | 500 | 7 | 0.25 | Yes
Solution Readniess | Project Plan | 1.3.2.4 | Workflow | Future Task | Should Have Started |  | Fri 8/14/26 | 500 | 0 | 0 | No
Solution Readniess | Project Plan | 1.3.3.1 | Test Readiness Review (TRR) - ITC 1 | Future Task | Should Have Started |  | Fri 5/1/26 | 500 | 7 | 0.25 | Yes
Solution Readniess | Project Plan | 1.3.2.3 | Enhanchments | Future Task | Should Have Started |  | Fri 8/14/26 | 500 | 0 | 0 | No
Solution Readniess | Project Plan | 1.3.1.2 | Order to Cash | Future Task | Should Have Started |  | Fri 5/29/26 | 500 | 0 | 0.04 | No
Solution Readniess | Project Plan | 1.3.3.5.5 | ITC-1 Defect Correction / Retesting / Mitigation / Close | Future Task | Should Have Started |  | Tue 5/19/26 | 500 | 0 | 0.25 | No
Solution Readniess | Project Plan | 1.3.2.1 | Reports | Future Task | Should Have Started |  | Fri 8/14/26 | 500 | 0 | 0 | No
Solution Readniess | Project Plan | 1.3.1.4 | Plan to Make | Future Task | Should Have Started |  | Fri 5/29/26 | 500 | 0 | 0.05 | No
Solution Readniess | Project Plan | 1.3.1.3 | Procure to Pay | Future Task | Should Have Started |  | Fri 5/29/26 | 500 | 0 | 0.04 | No
Solution Readniess | Project Plan | 1.3.1.1 | FICO | Future Task | Should Have Started |  | Fri 5/29/26 | 500 | 0 | 0.03 | No
Solution Readniess | Project Plan | 1.3.3.5.4 | ITC-1 Team Testing | Future Task | Should Have Started |  | Mon 5/18/26 | 500 | 0 | 0.25 | No
Solution Readniess | Project Plan | 1.3.2.2 | Interfaces | Future Task | Should Have Started |  | Fri 8/14/26 | 500 | 0 | 0 | No
Solution Readniess | Project Plan | 1.3.3.5.6 | ITC-1 Gate Review | Future Task | Starting This Week |  | Fri 5/15/26 | 500 | 0 | 0 | No
System Setup | Project Plan | 1.1.1.5.1.12 | Download Transport List | Future Task | Overdue | Basis | Mon 5/4/26 | 500 | 4 | 0.25 | Yes
System Setup | Project Plan | 1.1.1.5.1.13 | Business Functions Validation | Future Task | Overdue | Basis | Mon 5/4/26 | 500 | 4 | 0.25 | Yes
System Setup | Project Plan | 1.1.1.5.1.12 | Download Transport List | Future Task | Should Have Started | Basis | Mon 5/4/26 | 500 | 4 | 0.25 | Yes
System Setup | Project Plan | 1.1.1.5.1.13 | Business Functions Validation | Future Task | Should Have Started | Basis | Mon 5/4/26 | 500 | 4 | 0.25 | Yes
System Setup | Project Plan | 1.1.1.6.1.9 | Manual Technical Tasks | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
System Setup | Project Plan | 1.1.1.6.1.12 | Download Transport List | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
System Setup | Project Plan | 1.1.1.6.1.13 | Business Functions Validation | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | No
System Setup | Project Plan | 1.1.1.6.1.10 | Validate Fiori | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | No
System Setup | Project Plan | 1.1.1.6.1.1 | System Refresh Basis(Workinig with NS2) | Future Task | Starting Next 2 Weeks | Basis | Wed 5/20/26 | 500 | 0 | 0 | Yes
System Setup | Project Plan | 1.1.1.6.1.3 | Technical Transports / BP Setup | Future Task | Starting Next 2 Weeks | Basis | Fri 5/22/26 | 500 | 0 | 0 | No
System Setup | Project Plan | 1.1.1.6.1.2 | Client Config / Validation | Future Task | Starting Next 2 Weeks | Basis | Thu 5/21/26 | 500 | 0 | 0 | Yes
System Setup | Project Plan | 1.1.1.5.1.11 | Fiori App Activation | Future Task | Overdue | Dev Team | Mon 5/4/26 | 500 | 4 | 0.25 | Yes
System Setup | Project Plan | 1.1.1.5.1.11 | Fiori App Activation | Future Task | Should Have Started | Dev Team | Mon 5/4/26 | 500 | 4 | 0.25 | Yes
System Setup | Project Plan | 1.1.1.6.1.11 | Fiori App Activation | Future Task | Starting Next 2 Weeks | Dev Team | Thu 5/21/26 | 500 | 0 | 0 | Yes
System Setup | Project Plan | 1.1.1.5.1.14 | Functional Leads Validation of Transport List | Future Task | Overdue | Functional Leads | Mon 5/4/26 | 500 | 4 | 0.25 | Yes
System Setup | Project Plan | 1.1.1.5.1.14 | Functional Leads Validation of Transport List | Future Task | Should Have Started | Functional Leads | Mon 5/4/26 | 500 | 4 | 0.25 | Yes
System Setup | Project Plan | 1.1.1.6.1.14 | Functional Leads Validation of Transport | Future Task | Starting Next 2 Weeks | Functional Leads | Thu 5/21/26 | 500 | 0 | 0 | Yes
System Setup | Project Plan | 1.1.1.5.1.15 | Release Security roles to Functional Team | Future Task | Overdue | Security | Mon 5/4/26 | 500 | 4 | 0.25 | Yes
System Setup | Project Plan | 1.1.1.5.1.15 | Release Security roles to Functional Team | Future Task | Should Have Started | Security | Mon 5/4/26 | 500 | 4 | 0.25 | Yes
System Setup | Project Plan | 1.1.1.6.1.7 | Security Transports | Future Task | Starting Next 2 Weeks | Security | Thu 5/21/26 | 500 | 0 | 0 | Yes
System Setup | Project Plan | 1.1.1.6.1.8 | Security Manual Tasks | Future Task | Starting Next 2 Weeks | Security | Fri 5/22/26 | 500 | 0 | 0 | No
System Setup | Project Plan | 1.1.1.6.1.15 | Release Security roles to Functional Team | Future Task | Starting Next 2 Weeks | Security | Thu 5/21/26 | 500 | 0 | 0 | No
Technical | Action | A-237 | GTS Denied Party Content Licensing required | Open | Overdue Action | Anders Syverson | 46108 | 2-Medium | 42 |  | FALSE
Technical | Action | A-124 | Request to have 3rd Party tax Engine (Vertex) connected to DS4. This is needed in order to avoid tax errors during data loads and processing. | Open | Open Action | Kinnary | 46167 | 2-Medium |  |  | FALSE
Test | Action | A-254 | Q-Test Testing and Defect Training | Open | Open Action | Renee DiTullio |  | 2-Medium |  |  | FALSE
Testing & Training | Project Plan | 1.1.2.7.1 | Unit testing | Future Task | Should Have Started |  | Wed 5/13/26 | 500 | 0 | 0 | No
Testing & Training | Project Plan | 1.1.2.7.4 | Workflow Activation / Data load in Test System | Future Task | Starting Next 2 Weeks |  | Thu 5/28/26 | 500 | 0 | 0 | No
Testing & Training | Project Plan | 1.1.2.7.3 | Connector configuration (S4 / LDAP Connector) | Future Task | Starting Next 2 Weeks |  | Thu 5/21/26 | 500 | 0 | 0 | No
Testing & Training | Project Plan | 1.1.2.7.2 | Changes moved to Test System | Future Task | Starting This Week |  | Mon 5/18/26 | 500 | 0 | 0 | No

## PQ_OverdueAndUpcomingTasks
WBS | Task Name | Status | % Complete | Start | Finish | Resource Names | Duration | Milestone | Critical | Priority | Baseline Start | Baseline Finish | Outline Level | Outline Number | Task Summary Name | Total Slack | Active | Summary | Schedule Slip (Days) | Slip Bucket | Past Due | Days Overdue | Days Remaining | Start Month | Finish Month | Finish Quarter | Is Complete | Is Late | Is Milestone Flag | Workstream | Action Window
1.4.1.1.1 | Verify Role Mapping Complete | Future Task | 0.46 | Fri 5/1/26 | Fri 7/31/26 | Training | 66d | No | No | 500 | Mon 2/16/26 | Mon 8/3/26 | 5 | 1.4.1.1.1 | Content Development | 71d | Yes | No | -3 | On Time / Ahead | FALSE | 0 | 84 | May 2026 | Jul 2026 | Q3 2026 | FALSE | FALSE | FALSE | Business Readniess | Should Have Started
1.4.1.1.3 | Develop Course ppts | Future Task | 0.35 | Fri 5/1/26 | Fri 8/28/26 | Training | 86d | No | No | 500 | Mon 2/16/26 | Mon 8/3/26 | 5 | 1.4.1.1.3 | Content Development | 45d | Yes | No | 25 | 15-30 Days Slip | FALSE | 0 | 112 | May 2026 | Aug 2026 | Q3 2026 | FALSE | FALSE | FALSE | Business Readniess | Should Have Started
1.4.1.1.2 | Develop Curriculum | Future Task | 0.3 | Fri 5/1/26 | Fri 7/31/26 | Training | 66d | No | Yes | 500 | Mon 2/16/26 | Fri 6/5/26 | 5 | 1.4.1.1.2 | Content Development | 0d | Yes | No | 56 | 30+ Days Slip | FALSE | 0 | 84 | May 2026 | Jul 2026 | Q3 2026 | FALSE | FALSE | FALSE | Business Readniess | Should Have Started
1.4.1.1.4 | Develop Work Instructions | Future Task | 0.21 | Fri 5/1/26 | Fri 8/28/26 | Training | 86d | No | No | 500 | Mon 4/27/26 | Mon 8/3/26 | 5 | 1.4.1.1.4 | Content Development | 51d | Yes | No | 25 | 15-30 Days Slip | FALSE | 0 | 112 | May 2026 | Aug 2026 | Q3 2026 | FALSE | FALSE | FALSE | Business Readniess | Should Have Started
1.1.2.5.1 | Role Mapping with Business Process and Sub-Process /Functional Area | Future Task | 0 | Fri 5/8/26 | Thu 5/14/26 |  | 5d | No | No | 500 | Thu 11/27/25 | Wed 12/3/25 | 5 | 1.1.2.5.1 | Business Role Management | 122d | Yes | No | 162 | 30+ Days Slip | FALSE | 0 | 6 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Business Role Management | Should Have Started
1.1.2.5.2 | Role Upload to SAP GRC | Future Task | 0 | Fri 5/15/26 | Thu 5/21/26 |  | 5d | No | No | 500 | Thu 12/4/25 | Wed 12/10/25 | 5 | 1.1.2.5.2 | Business Role Management | 122d | Yes | No | 162 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Business Role Management | Starting This Week
1.1.1.5.3.3 | Close Client | Future Task | 0 | Thu 5/14/26 | Thu 5/14/26 | Basis | 15m | No | Yes | 500 | Thu 5/28/26 | Thu 5/28/26 | 6 | 1.1.1.5.3.3 | Data Project Create | -3571m | Yes | No | -14 | On Time / Ahead | FALSE | 0 | 6 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Project Create | Starting This Week
1.1.1.5.3.1 | Open Client | Future Task | 0 | Wed 5/13/26 | Wed 5/13/26 | Basis | 15m | No | Yes | 500 | Wed 5/27/26 | Wed 5/27/26 | 6 | 1.1.1.5.3.1 | Data Project Create | -3571m | Yes | No | -14 | On Time / Ahead | FALSE | 0 | 5 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Project Create | Starting This Week
1.1.1.5.3.2 | Create Migration Data Project in DMC | Future Task | 0 | Wed 5/13/26 | Thu 5/14/26 | Data Migration Team | 4h | No | Yes | 500 | Wed 5/27/26 | Thu 5/28/26 | 6 | 1.1.1.5.3.2 | Data Project Create | -59.52h | Yes | No | -14 | On Time / Ahead | FALSE | 0 | 6 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Project Create | Starting This Week
1.2.2.2.12 | OTC_CM19_Customer_Master - Bill-To | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 |  | 2h | No | Yes | 500 | Wed 4/16/25 | Wed 4/16/25 | 5 | 1.2.2.2.12 | Master Data Loads | -1.52h | Yes | No | 397 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.3.8 | Post GL Extention Validation | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 |  | 2h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.3.8 | RTR_CM01_GL_Account_Master to CC 1000 | -76.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.14.9 | Close Client | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Basis | 15m | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.14.9 | OTC_CM19_Customer_Master - Sold-To | -1786m | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.13.3 | Open client for BP number range update | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Basis | 30m | No | Yes | 500 | Wed 4/8/26 | Thu 4/9/26 | 6 | 1.2.2.2.13.3 | OTC_CM19_Customer_Master - Ship-To | -1756m | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.13.5 | Close Client | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Basis | 15m | No | Yes | 500 | Fri 4/10/26 | Mon 4/13/26 | 6 | 1.2.2.2.13.5 | OTC_CM19_Customer_Master - Ship-To | -1756m | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.14.7 | Open client for BP number range update | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Basis | 15m | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.14.7 | OTC_CM19_Customer_Master - Sold-To | -1786m | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.6.1 | Open Client | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Basis | 30m | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.6.1 | Manual Configuration Activities in QS5 | -1441m | Yes | No | 45 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.6.3 | Close Client | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Basis | 30m | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.6.3 | Manual Configuration Activities in QS5 | -1441m | Yes | No | 45 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.53.3 | Post Load Validation | Future Task | 0 | Fri 5/22/26 | Tue 5/26/26 | Brad | 16h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.53.3 | PTM_CM50_Material Class | -46.77h | Yes | No | 40 | 30+ Days Slip | FALSE | 0 | 18 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.33.6 | Post Load Validation | Future Task | 0 | Fri 5/22/26 | Mon 5/25/26 | Brad Meseck | 3h | No | Yes | 500 | Fri 4/17/26 | Fri 4/17/26 | 6 | 1.2.2.2.33.6 | PTM_CM36_Production Version Conversion | -53.77h | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 17 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.33.2 | Pre Load Validation | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Brad Meseck | 30m | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.33.2 | PTM_CM36_Production Version Conversion | -3226m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.54.6 | Post Load Validation | Future Task | 0 | Fri 5/22/26 | Mon 5/25/26 | Brad Meseck | 3h | No | Yes | 500 | Fri 4/17/26 | Fri 4/17/26 | 6 | 1.2.2.2.54.6 | PTM_CM55_Class assignment to materials | -39.27h | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 17 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.54.4 | Error and Defect Mitigation | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Brad Meseck | 2h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.54.4 | PTM_CM55_Class assignment to materials | -39.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.33.4 | Error and Defect Mitigation | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Brad Meseck | 2h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.33.4 | PTM_CM36_Production Version Conversion | -53.77h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.54.2 | Pre Load Validation | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Brad Meseck | 30m | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.54.2 | PTM_CM55_Class assignment to materials | -2356m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.53.2 | Load | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Brad Meseck | 30m | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.53.2 | PTM_CM50_Material Class | -2806m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.36.6 | Post Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Brad Meseck | 3h | No | Yes | 500 | Tue 4/21/26 | Tue 4/21/26 | 6 | 1.2.2.2.36.6 | PTM_CM48_Equipment_Master_Service | -2.52h | Yes | No | 27 | 15-30 Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.30.2 | Pre Load Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Brad Meseck | 0.5h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.30.2 | PTM_CM31_BOM Conversion | -62.39h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.33.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Brad Meseck | 30m | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.33.1 | PTM_CM36_Production Version Conversion | -3226m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.54.5 | Load | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 2h | No | Yes | 500 | Thu 4/16/26 | Fri 4/17/26 | 6 | 1.2.2.2.54.5 | PTM_CM55_Class assignment to materials | -39.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.13.8 | Load | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 3h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.13.8 | OTC_CM19_Customer_Master - Ship-To | -39.02h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.54.3 | Simulate Load | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 1h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.54.3 | PTM_CM55_Class assignment to materials | -39.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.33.3 | Simulate Load | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 1h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.33.3 | PTM_CM36_Production Version Conversion | -53.77h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.7.3 | Simulate Load | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 1h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.7.3 | RTR_CM09_Activity_Type | -38.02h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.14.5 | Load | Future Task | 0 | Fri 5/22/26 | Mon 5/25/26 | Data Migration Team | 3h | No | Yes | 500 | Thu 4/9/26 | Fri 4/10/26 | 6 | 1.2.2.2.14.5 | OTC_CM19_Customer_Master - Sold-To | -76.52h | Yes | No | 45 | 30+ Days Slip | FALSE | 0 | 17 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.14.3 | Simulate Load | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 1h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.14.3 | OTC_CM19_Customer_Master - Sold-To | -76.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.7.5 | Load | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 1h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.7.5 | RTR_CM09_Activity_Type | -38.02h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.33.5 | Load | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Data Migration Team | 2h | No | Yes | 500 | Thu 4/16/26 | Fri 4/17/26 | 6 | 1.2.2.2.33.5 | PTM_CM36_Production Version Conversion | -53.77h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.46.5 | Load | Future Task | 0 | Fri 5/22/26 | Mon 5/25/26 | Data Migration Team | 2h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.46.5 | PTM_CM52_Super_BOM | -67.27h | Yes | No | 39 | 30+ Days Slip | FALSE | 0 | 17 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.52.3 | Simulate Load | Future Task | 0 | Mon 5/18/26 | Tue 5/19/26 | Data Migration Team | 8h | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.52.3 | RTR_CM11_Asset_Master | -29.52h | Yes | No | 39 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.23.5 | Load | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 2h | No | Yes | 500 | Mon 4/13/26 | Tue 4/14/26 | 6 | 1.2.2.2.23.5 | PTP_CM27_BP_Intercompany Customer | -8.02h | Yes | No | 34 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.67.5 | Load | Future Task | 0 | Mon 5/18/26 | Tue 5/19/26 | Data Migration Team | 2h | No | Yes | 500 | Fri 4/17/26 | Fri 4/17/26 | 6 | 1.2.2.2.67.5 | RTR_CM17_Project Definition / Builder | -9.02h | Yes | No | 32 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.27.5 | Load | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 1h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.27.5 | PTP_CM28_Purchase_Info_Records | -5.52h | Yes | No | 33 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.68.5 | Load | Future Task | 0 | Mon 5/18/26 | Tue 5/19/26 | Data Migration Team | 2h | No | Yes | 500 | Fri 4/17/26 | Fri 4/17/26 | 6 | 1.2.2.2.68.5 | RTR_CM18_WBS Element | -9.52h | Yes | No | 32 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.67.3 | Simulate Load | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 1h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.67.3 | RTR_CM17_Project Definition / Builder | -9.02h | Yes | No | 32 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.19.5 | Load | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 1h | No | Yes | 500 | Tue 4/14/26 | Tue 4/14/26 | 6 | 1.2.2.2.19.5 | PTP_CM27_Vendor Master | -70.27h | Yes | No | 34 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.22.3 | Simulate Load | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 1h | No | Yes | 500 | Mon 4/13/26 | Mon 4/13/26 | 6 | 1.2.2.2.22.3 | PTP_CM27_BP_Intercompany Supplier | -11.52h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.23.3 | Simulate Load | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 1h | No | Yes | 500 | Mon 4/13/26 | Mon 4/13/26 | 6 | 1.2.2.2.23.3 | PTP_CM27_BP_Intercompany Customer | -8.02h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.9.5 | Load | Future Task | 0 | Mon 5/18/26 | Tue 5/19/26 | Data Migration Team | 5h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.9.5 | RTR_CM06_Bank_master | -48.52h | Yes | No | 40 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.9.3 | Simulate Load | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 1h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.9.3 | RTR_CM06_Bank_master | -48.52h | Yes | No | 39 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.24.1 | Extract File | Future Task | 0 | Mon 5/18/26 | Tue 5/19/26 | Data Migration Team | 5h | No | Yes | 500 | Fri 4/10/26 | Mon 4/13/26 | 6 | 1.2.2.2.24.1 | PTP_CM26_Material_Master - All Types | -7.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.68.3 | Simulate Load | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Data Migration Team | 1h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.68.3 | RTR_CM18_WBS Element | -9.52h | Yes | No | 32 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.32.1 | Extract File | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 1h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.32.1 | PTM_CM38_Routing Conversion | -53.77h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.31.1 | Extract File | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 1h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.31.1 | PTM_CM40_Work Center Conversion | -53.77h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.3.5 | Load | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 1h | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.3.5 | RTR_CM01_GL_Account_Master to CC 1000 | -76.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.30.1 | Extract File | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 1h | No | Yes | 500 | Wed 4/15/26 | Thu 4/16/26 | 6 | 1.2.2.2.30.1 | PTM_CM31_BOM Conversion | -62.39h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.29.5 | Load | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Data Migration Team | 2h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.29.5 | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | -34.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.29.3 | Simulate Load | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 1h | No | Yes | 500 | Wed 4/15/26 | Thu 4/16/26 | 6 | 1.2.2.2.29.3 | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | -70.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.28.5 | Load | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Data Migration Team | 2h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.28.5 | PTP_CM28_Purchase_Info_Record External Processing | -34.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.28.3 | Simulate Load | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 1h | No | Yes | 500 | Wed 4/15/26 | Thu 4/16/26 | 6 | 1.2.2.2.28.3 | PTP_CM28_Purchase_Info_Record External Processing | -34.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.27.3 | Simulate Load | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 1h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.27.3 | PTP_CM28_Purchase_Info_Records | -31.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.27.1 | Extract File | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 1h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.27.1 | PTP_CM28_Purchase_Info_Records | -62.39h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.30.3 | Simulate Load | Future Task | 0 | Thu 5/21/26 | Mon 5/25/26 | Data Migration Team | 15.5h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.30.3 | PTM_CM31_BOM Conversion | -62.39h | Yes | No | 39 | 30+ Days Slip | FALSE | 0 | 17 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.9.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 1h | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.9.1 | RTR_CM06_Bank_master | -30.02h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.13.6 | Simulate Load | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 1h | No | Yes | 500 | Wed 4/8/26 | Thu 4/9/26 | 6 | 1.2.2.2.13.6 | OTC_CM19_Customer_Master - Ship-To | -74.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.52.5 | Load | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Data Migration Team | 2h | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.52.5 | RTR_CM11_Asset_Master | -29.52h | Yes | No | 41 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.46.3 | Simulate Load | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Data Migration Team | 8h | No | Yes | 500 | Wed 4/15/26 | Thu 4/16/26 | 6 | 1.2.2.2.46.3 | PTM_CM52_Super_BOM | -67.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.24.3 | Simulate Load | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Data Migration Team | 1h | No | Yes | 500 | Tue 4/14/26 | Tue 4/14/26 | 6 | 1.2.2.2.24.3 | PTP_CM26_Material_Master - All Types | -70.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.4.5 | Load | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Data Migration Team | 1h | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.4.5 | RTR_CM05_Profit_Center | -63.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.10.3 | Simulate Load | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Data Migration Team | 1h | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.10.3 | RTR_CM08_Exchange_Rates | -16.52h | Yes | No | 39 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.4.3 | Simulate Load | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Data Migration Team | 1h | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.4.3 | RTR_CM05_Profit_Center | -63.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.22.5 | Load | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Data Migration Team | 2h | No | Yes | 500 | Mon 4/13/26 | Tue 4/14/26 | 6 | 1.2.2.2.22.5 | PTP_CM27_BP_Intercompany Supplier | -11.52h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.3.3 | Simulate Load | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 6h | No | Yes | 500 | Tue 4/7/26 | Wed 4/8/26 | 6 | 1.2.2.2.3.3 | RTR_CM01_GL_Account_Master to CC 1000 | -76.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.26.5 | Load | Future Task | 0 | Wed 5/20/26 | Thu 5/21/26 | Data Migration Team | 2h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.26.5 | PTP_CM26_Material_Master - KMAT - Configurable Materials | -70.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.26.3 | Simulate Load | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 1h | No | Yes | 500 | Tue 4/14/26 | Tue 4/14/26 | 6 | 1.2.2.2.26.3 | PTP_CM26_Material_Master - KMAT - Configurable Materials | -70.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.8.5 | Load | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 1h | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.8.5 | RTR_CM12_Activity Rates | -20.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.25.5 | Load | Future Task | 0 | Wed 5/20/26 | Thu 5/21/26 | Data Migration Team | 2h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.25.5 | PTP_CM26_Material_Master - SERV - Service Materials | -25.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.5.3 | Simulate Load | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 1h | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.5.3 | RTR_CM04_Cost_Center | -63.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.5.5 | Load | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 1h | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.5.5 | RTR_CM04_Cost_Center | -63.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.25.3 | Simulate Load | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 1h | No | Yes | 500 | Tue 4/14/26 | Tue 4/14/26 | 6 | 1.2.2.2.25.3 | PTP_CM26_Material_Master - SERV - Service Materials | -25.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.24.5 | Load | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 3h | No | Yes | 500 | Tue 4/14/26 | Wed 4/15/26 | 6 | 1.2.2.2.24.5 | PTP_CM26_Material_Master - All Types | -70.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.10.5 | Load | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 1h | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.10.5 | RTR_CM08_Exchange_Rates | -16.52h | Yes | No | 40 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.8.3 | Simulate Load | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Data Migration Team | 1h | No | Yes | 500 | Tue 4/7/26 | Wed 4/8/26 | 6 | 1.2.2.2.8.3 | RTR_CM12_Activity Rates | -20.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.45.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | 0 | Fri 5/22/26 | Mon 5/25/26 | Eric Heisler | 12.75h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.45.1 | VC_Characteristic Groups | -46.02h | Yes | No | 39 | 30+ Days Slip | FALSE | 0 | 17 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.43.2 | Post Load Validation | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Eric Heisler | 3h | No | Yes | 500 | Thu 4/16/26 | Fri 4/17/26 | 6 | 1.2.2.2.43.2 | VC_Variant Tables | -40.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.43.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Eric Heisler | 2h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.43.1 | VC_Variant Tables | -40.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.44.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Eric Heisler | 2h | No | Yes | 500 | Fri 4/17/26 | Fri 4/17/26 | 6 | 1.2.2.2.44.1 | VC_Variant Tables Content | -40.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.46.4 | Error and Defect Mitigation | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Eric Heisler | 2h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.46.4 | PTM_CM52_Super_BOM | -67.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.44.2 | Post Load Validation | Future Task | 0 | Fri 5/22/26 | Mon 5/25/26 | Eric Heisler | 3h | No | Yes | 500 | Fri 4/17/26 | Fri 4/17/26 | 6 | 1.2.2.2.44.2 | VC_Variant Tables Content | -40.27h | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 17 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.37.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Eric Heisler | 2h | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.37.1 | VC_Object Dependencies | -19.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.37.2 | Post Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Eric Heisler | 3h | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.37.2 | VC_Object Dependencies | -19.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.38.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | 0 | Mon 5/18/26 | Tue 5/19/26 | Eric Heisler | 2h | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.38.1 | VC_Characteristics | -19.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.42.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Eric Heisler | 2h | No | Yes | 500 | Wed 4/15/26 | Thu 4/16/26 | 6 | 1.2.2.2.42.1 | VC_Configuration Profiles | -46.02h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.41.2 | Post Load Validation | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Eric Heisler | 3h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.41.2 | VC_Dependency Nets | -30.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.40.2 | Post Load Validation | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Eric Heisler | 3h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.40.2 | VC_Classification (Class Type 200) | -30.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.42.2 | Post Load Validation | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Eric Heisler | 3h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.42.2 | VC_Configuration Profiles | -46.02h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.26.6 | Post Load Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Eric Heisler | 3h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.26.6 | PTP_CM26_Material_Master - KMAT - Configurable Materials | -70.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.41.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Eric Heisler | 2h | No | Yes | 500 | Wed 4/15/26 | Thu 4/16/26 | 6 | 1.2.2.2.41.1 | VC_Dependency Nets | -30.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.46.2 | Pre Load Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Eric Heisler | 30m | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.46.2 | PTM_CM52_Super_BOM | -4036m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.46.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Eric Heisler | 30m | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.46.1 | PTM_CM52_Super_BOM | -4036m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.40.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Eric Heisler | 2h | No | Yes | 500 | Wed 4/15/26 | Thu 4/16/26 | 6 | 1.2.2.2.40.1 | VC_Classification (Class Type 200) | -30.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.38.2 | Post Load Validation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Eric Heisler | 3h | No | Yes | 500 | Mon 4/6/26 | Tue 4/7/26 | 6 | 1.2.2.2.38.2 | VC_Characteristics | -19.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.39.2 | Post Load Validation | Future Task | 0 | Tue 5/19/26 | Wed 5/20/26 | Eric Heisler | 3h | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.39.2 | VC_Classes | -19.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.39.1 | Run ALE Transaction to QS5 from DS4 130 | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Eric Heisler | 2h | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.39.1 | VC_Classes | -19.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.26.4 | Error and Defect Mitigation | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Eric Heisler | 2h | No | Yes | 500 | Tue 4/14/26 | Wed 4/15/26 | 6 | 1.2.2.2.26.4 | PTP_CM26_Material_Master - KMAT - Configurable Materials | -70.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.26.2 | Pre Load Validation | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Eric Heisler | 30m | No | Yes | 500 | Tue 4/14/26 | Tue 4/14/26 | 6 | 1.2.2.2.26.2 | PTP_CM26_Material_Master - KMAT - Configurable Materials | -4216m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.26.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Eric Heisler | 30m | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.26.1 | PTP_CM26_Material_Master - KMAT - Configurable Materials | -2146m | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.6.4 | Intercompany Business Partner Setup | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Functional Leads | 2h | No | Yes | 500 | Wed 4/8/26 | Thu 4/9/26 | 6 | 1.2.2.2.6.4 | Manual Configuration Activities in QS5 | -33.02h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.56.1 | Run material interface to GTS | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | James Van Riper | 1h | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.56.1 | GTS - Customers initial load from S4 (Run Interface) | -1.52h | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.60.2 | Post Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | James Van Riper | 1h | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.60.2 | GTS - HTS - Create | -1.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.60.1 | Load Descartes XML File | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | James Van Riper | 1h | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.60.1 | GTS - HTS - Create | -1.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.58.1 | Load Descartes XML File | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | James Van Riper | 1h | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.58.1 | GTS - ECCN - Create | -0.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.56.2 | Post Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | James Van Riper | 1h | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.56.2 | GTS - Customers initial load from S4 (Run Interface) | -1.52h | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.55.1 | Run material interface to GTS | Future Task | 0 | Thu 5/21/26 | Mon 5/25/26 | James Van Riper | 15.75h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.55.1 | GTS - Material initial load from S4 (Run Interface) | -70.27h | Yes | No | 39 | 30+ Days Slip | FALSE | 0 | 17 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.58.2 | Post Load Validation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | James Van Riper | 1h | No | Yes | 500 | Mon 4/13/26 | Mon 4/13/26 | 6 | 1.2.2.2.58.2 | GTS - ECCN - Create | -11.52h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.57.1 | Run material interface to GTS | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | James Van Riper | 1h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.57.1 | GTS - Vendors initial load from S4 (Run Interface) | -11.52h | Yes | No | 34 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.57.2 | Post Load Validation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | James Van Riper | 1h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.57.2 | GTS - Vendors initial load from S4 (Run Interface) | -8.52h | Yes | No | 34 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.65.3 | Post Load Validation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | James Van Riper | 1h | No | Yes | 500 | Mon 4/13/26 | Tue 4/14/26 | 6 | 1.2.2.2.65.3 | Initialize Embargo situation | -11.52h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.65.2 | Set Embargo situations | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | James Van Riper | 1h | No | Yes | 500 | Mon 4/13/26 | Mon 4/13/26 | 6 | 1.2.2.2.65.2 | Initialize Embargo situation | -11.52h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.65.1 | Run report /SAPSLL/EMB_CNTRY_INIT | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | James Van Riper | 1h | No | Yes | 500 | Mon 4/13/26 | Mon 4/13/26 | 6 | 1.2.2.2.65.1 | Initialize Embargo situation | -11.52h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.11.3 | Post Load Validation | Future Task | 0 | Fri 5/22/26 | Mon 5/25/26 | Kasey Hughes | 3h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.11.3 | RTR_CM14_Cost Element_Group | -38.52h | Yes | No | 40 | 30+ Days Slip | FALSE | 0 | 17 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.7.6 | Post Load Validation | Future Task | 0 | Fri 5/22/26 | Mon 5/25/26 | Kasey Hughes | 2h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.7.6 | RTR_CM09_Activity_Type | -38.02h | Yes | No | 46 | 30+ Days Slip | FALSE | 0 | 17 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.7.4 | Error and Defect Mitigation | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Kasey Hughes | 2h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.7.4 | RTR_CM09_Activity_Type | -38.02h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.1.1 | Manual File Staged and Posted "Ready" | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 1h | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.1.1 | RTR_CM02_Profit Center Hierarchy | -76.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.1.3 | Post Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 3h | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.1.3 | RTR_CM02_Profit Center Hierarchy | -76.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.67.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 30m | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.67.1 | RTR_CM17_Project Definition / Builder | -571m | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.68.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 30m | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.68.1 | RTR_CM18_WBS Element | -571m | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.9.4 | Error and Defect Mitigation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 2h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.9.4 | RTR_CM06_Bank_master | -48.52h | Yes | No | 39 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.52.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 30m | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.52.1 | RTR_CM11_Asset_Master | -1771m | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.67.2 | Pre Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 30m | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.67.2 | RTR_CM17_Project Definition / Builder | -541m | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.68.2 | Pre Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 30m | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.68.2 | RTR_CM18_WBS Element | -571m | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.68.4 | Error and Defect Mitigation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 2h | No | Yes | 500 | Thu 4/16/26 | Fri 4/17/26 | 6 | 1.2.2.2.68.4 | RTR_CM18_WBS Element | -9.52h | Yes | No | 31 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.1.2 | Load | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 2h | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.1.2 | RTR_CM02_Profit Center Hierarchy | -76.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.67.4 | Error and Defect Mitigation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes | 2h | No | Yes | 500 | Thu 4/16/26 | Fri 4/17/26 | 6 | 1.2.2.2.67.4 | RTR_CM17_Project Definition / Builder | -9.02h | Yes | No | 31 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.52.6 | Post Load Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Kasey Hughes | 3h | No | Yes | 500 | Fri 4/10/26 | Mon 4/13/26 | 6 | 1.2.2.2.52.6 | RTR_CM11_Asset_Master | -29.52h | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.11.1 | Manual File Staged and Posted "Ready" | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Kasey Hughes | 30m | No | Yes | 500 | Wed 4/8/26 | Tue 4/14/26 | 6 | 1.2.2.2.11.1 | RTR_CM14_Cost Element_Group | -2311m | Yes | No | 37 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.9.2 | Pre Load Validation | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Kasey Hughes | 2h | No | Yes | 500 | Wed 4/8/26 | Thu 4/9/26 | 6 | 1.2.2.2.9.2 | RTR_CM06_Bank_master | -30.02h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.3.6 | Post Load Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Kasey Hughes | 2h | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.3.6 | RTR_CM01_GL_Account_Master to CC 1000 | -76.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.3.7 | Extend GL to all Company Codes | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Kasey Hughes | 2h | No | Yes | 500 | Wed 4/8/26 | Thu 4/9/26 | 6 | 1.2.2.2.3.7 | RTR_CM01_GL_Account_Master to CC 1000 | -76.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.11.2 | Load | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Kasey Hughes | 8h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.11.2 | RTR_CM14_Cost Element_Group | -38.52h | Yes | No | 37 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.7.2 | Pre Load Validation | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Kasey Hughes | 2h | No | Yes | 500 | Wed 4/8/26 | Thu 4/9/26 | 6 | 1.2.2.2.7.2 | RTR_CM09_Activity_Type | -38.02h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.5.6 | Post Load Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Kasey Hughes | 2h | No | Yes | 500 | Wed 4/8/26 | Thu 4/9/26 | 6 | 1.2.2.2.5.6 | RTR_CM04_Cost_Center | -63.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.7.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Kasey Hughes | 1h | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.7.1 | RTR_CM09_Activity_Type | -38.02h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.4.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 1h | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.4.1 | RTR_CM05_Profit_Center | -63.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.9.6 | Post Load Validation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 2h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.9.6 | RTR_CM06_Bank_master | -48.52h | Yes | No | 40 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.8.2 | Pre Load Validation | Future Task | 0 | Tue 5/19/26 | Wed 5/20/26 | Kasey Hughes | 2h | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.8.2 | RTR_CM12_Activity Rates | -20.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.2.2 | Load | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 2h | No | Yes | 500 | Mon 4/6/26 | Tue 4/7/26 | 6 | 1.2.2.2.2.2 | RTR_CM03_Cost Center Hierarchy | -76.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.8.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 1h | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.8.1 | RTR_CM12_Activity Rates | -20.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.4.6 | Post Load Validation | Future Task | 0 | Tue 5/19/26 | Wed 5/20/26 | Kasey Hughes | 2h | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.4.6 | RTR_CM05_Profit_Center | -63.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.4.4 | Error and Defect Mitigation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 2h | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.4.4 | RTR_CM05_Profit_Center | -63.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.4.2 | Pre Load Validation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 2h | No | Yes | 500 | Mon 4/6/26 | Tue 4/7/26 | 6 | 1.2.2.2.4.2 | RTR_CM05_Profit_Center | -63.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.3.2 | Pre Load Validation | Future Task | 0 | Tue 5/19/26 | Wed 5/20/26 | Kasey Hughes | 2h | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.3.2 | RTR_CM01_GL_Account_Master to CC 1000 | -76.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.3.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 1h | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.3.1 | RTR_CM01_GL_Account_Master to CC 1000 | -76.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.2.3 | Post Load Validation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 3h | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.2.3 | RTR_CM03_Cost Center Hierarchy | -76.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.10.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 1h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.10.1 | RTR_CM08_Exchange_Rates | -16.52h | Yes | No | 40 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.10.2 | Pre Load Validation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 2h | No | Yes | 500 | Thu 4/9/26 | Fri 4/10/26 | 6 | 1.2.2.2.10.2 | RTR_CM08_Exchange_Rates | -16.52h | Yes | No | 39 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.2.1 | Manual File Staged and Posted "Ready" | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 1h | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 6 | 1.2.2.2.2.1 | RTR_CM03_Cost Center Hierarchy | -76.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.68.6 | Post Load Validation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 3h | No | Yes | 500 | Fri 4/17/26 | Fri 4/17/26 | 6 | 1.2.2.2.68.6 | RTR_CM18_WBS Element | -9.52h | Yes | No | 32 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.52.4 | Error and Defect Mitigation | Future Task | 0 | Tue 5/19/26 | Thu 5/21/26 | Kasey Hughes | 16h | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.52.4 | RTR_CM11_Asset_Master | -29.52h | Yes | No | 41 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.10.4 | Error and Defect Mitigation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 2h | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.10.4 | RTR_CM08_Exchange_Rates | -16.52h | Yes | No | 39 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.67.6 | Post Load Validation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Kasey Hughes | 3h | No | Yes | 500 | Fri 4/17/26 | Fri 4/17/26 | 6 | 1.2.2.2.67.6 | RTR_CM17_Project Definition / Builder | -9.02h | Yes | No | 32 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.5.4 | Error and Defect Mitigation | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Kasey Hughes | 2h | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.5.4 | RTR_CM04_Cost_Center | -63.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.8.4 | Error and Defect Mitigation | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Kasey Hughes | 2h | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.8.4 | RTR_CM12_Activity Rates | -20.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.5.2 | Pre Load Validation | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Kasey Hughes | 2h | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.5.2 | RTR_CM04_Cost_Center | -63.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.8.6 | Post Load Validation | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Kasey Hughes | 2h | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.8.6 | RTR_CM12_Activity Rates | -20.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.5.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Kasey Hughes | 1h | No | Yes | 500 | Tue 4/7/26 | Wed 4/8/26 | 6 | 1.2.2.2.5.1 | RTR_CM04_Cost_Center | -63.52h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.10.6 | Post Load Validation | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Kasey Hughes | 2h | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.10.6 | RTR_CM08_Exchange_Rates | -16.52h | Yes | No | 40 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.3.4 | Error and Defect Mitigation | Future Task | 0 | Wed 5/20/26 | Thu 5/21/26 | Kasey Hughes | 2h | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.3.4 | RTR_CM01_GL_Account_Master to CC 1000 | -76.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.52.2 | Pre Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Kasey Hughes,Femi Oguntala | 30m | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.52.2 | RTR_CM11_Asset_Master | -1771m | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.6.2 | Service Enterprise Setup | Future Task | 0 | Fri 5/22/26 | Fri 5/29/26 | Keith Riley | 5d | No | Yes | 500 | Wed 4/8/26 | Wed 4/15/26 | 6 | 1.2.2.2.6.2 | Manual Configuration Activities in QS5 | -8.88d | Yes | No | 44 | 30+ Days Slip | FALSE | 0 | 21 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.1 | PMO Authorization to Start Data Loads | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Mark George | 2h | No | Yes | 500 | Mon 4/6/26 | Mon 4/6/26 | 4 | 1.2.2.1 | ITC2 Data Load Tasks QS4 | 0h | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.29.6 | Post Load Validation | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Nevin Varkey | 3h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.29.6 | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | -34.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.28.6 | Post Load Validation | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Nevin Varkey | 3h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.28.6 | PTP_CM28_Purchase_Info_Record External Processing | -34.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.19.6 | Post Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey | 2h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.19.6 | PTP_CM27_Vendor Master | -70.27h | Yes | No | 33 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.20.1 | Extract File(Will Extract from LFA1) | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey | 1h | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.20.1 | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | -11.52h | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.27.6 | Post Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey | 2h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.27.6 | PTP_CM28_Purchase_Info_Records | -5.52h | Yes | No | 33 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.20.3 | Simulate Load/ Not Needed | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey | 1h | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.20.3 | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | -11.52h | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.20.4 | Error and Defect Mitigation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey | 2h | No | Yes | 500 | Fri 4/10/26 | Mon 4/13/26 | 6 | 1.2.2.2.20.4 | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | -5.52h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.20.6 | Post Load Validation | Future Task | 0 | Mon 5/18/26 | Tue 5/19/26 | Nevin Varkey | 2h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.20.6 | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | -11.52h | Yes | No | 34 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.20.2 | Pre Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey | 2h | No | Yes | 500 | Fri 4/10/26 | Fri 4/10/26 | 6 | 1.2.2.2.20.2 | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | -11.52h | Yes | No | 38 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.28.2 | Pre Load Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 30m | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.28.2 | PTP_CM28_Purchase_Info_Record External Processing | -2056m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.28.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 30m | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.28.1 | PTP_CM28_Purchase_Info_Record External Processing | -2056m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.29.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 30m | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.29.1 | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | -4216m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.29.2 | Pre Load Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 30m | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.29.2 | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | -4216m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.29.4 | Error and Defect Mitigation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 2h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.29.4 | PTP_CM28_Purchase_Info_Record Subcontracting and Consignment | -34.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.27.2 | Pre Load Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 2h | No | Yes | 500 | Wed 4/15/26 | Thu 4/16/26 | 6 | 1.2.2.2.27.2 | PTP_CM28_Purchase_Info_Records | -31.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.27.4 | Error and Defect Mitigation | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Nevin Varkey | 2h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.27.4 | PTP_CM28_Purchase_Info_Records | -31.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.28.4 | Error and Defect Mitigation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey | 2h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.28.4 | PTP_CM28_Purchase_Info_Record External Processing | -34.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.51.1 | Manual File Staged and Posted "Ready" | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Nevin Varkey | 30m | No | Yes | 500 | Tue 4/14/26 | Tue 4/14/26 | 6 | 1.2.2.2.51.1 | PTP_CM29_Source_List | -541m | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.24.4 | Error and Defect Mitigation | Future Task | 0 | Tue 5/19/26 | Wed 5/20/26 | Nevin Varkey | 4h | No | Yes | 500 | Tue 4/14/26 | Tue 4/14/26 | 6 | 1.2.2.2.24.4 | PTP_CM26_Material_Master - All Types | -70.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.24.6 | Post Load Validation | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Nevin Varkey | 2h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.24.6 | PTP_CM26_Material_Master - All Types | -63.77h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.24.2 | Pre Load Validation | Future Task | 0 | Mon 5/18/26 | Tue 5/19/26 | Nevin Varkey,Ric Haraida | 2h | No | Yes | 500 | Mon 4/13/26 | Tue 4/14/26 | 6 | 1.2.2.2.24.2 | PTP_CM26_Material_Master - All Types | -70.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.23.6 | Post Load Validation | Future Task | 0 | Mon 5/18/26 | Tue 5/19/26 | Nevin Varkey,Ric Haraida | 3h | No | Yes | 500 | Tue 4/14/26 | Tue 4/14/26 | 6 | 1.2.2.2.23.6 | PTP_CM27_BP_Intercompany Customer | -8.02h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.23.4 | Error and Defect Mitigation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey,Ric Haraida | 2h | No | Yes | 500 | Mon 4/13/26 | Mon 4/13/26 | 6 | 1.2.2.2.23.4 | PTP_CM27_BP_Intercompany Customer | -8.02h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.23.2 | Pre Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey,Ric Haraida | 30m | No | Yes | 500 | Mon 4/13/26 | Mon 4/13/26 | 6 | 1.2.2.2.23.2 | PTP_CM27_BP_Intercompany Customer | -481m | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.23.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey,Ric Haraida | 30m | No | Yes | 500 | Mon 4/13/26 | Mon 4/13/26 | 6 | 1.2.2.2.23.1 | PTP_CM27_BP_Intercompany Customer | -1m | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.22.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey,Ric Haraida | 30m | No | Yes | 500 | Mon 4/13/26 | Mon 4/13/26 | 6 | 1.2.2.2.22.1 | PTP_CM27_BP_Intercompany Supplier | -691m | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.22.2 | Pre Load Validation | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkey,Ric Haraida | 30m | No | Yes | 500 | Mon 4/13/26 | Mon 4/13/26 | 6 | 1.2.2.2.22.2 | PTP_CM27_BP_Intercompany Supplier | -691m | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.22.4 | Error and Defect Mitigation | Future Task | 0 | Mon 5/18/26 | Tue 5/19/26 | Nevin Varkey,Ric Haraida | 2h | No | Yes | 500 | Mon 4/13/26 | Mon 4/13/26 | 6 | 1.2.2.2.22.4 | PTP_CM27_BP_Intercompany Supplier | -11.52h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.25.6 | Post Load Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Nevin Varkey,Ric Haraida | 3h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.25.6 | PTP_CM26_Material_Master - SERV - Service Materials | -25.27h | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.22.6 | Post Load Validation | Future Task | 0 | Tue 5/19/26 | Tue 5/19/26 | Nevin Varkey,Ric Haraida | 3h | No | Yes | 500 | Tue 4/14/26 | Tue 4/14/26 | 6 | 1.2.2.2.22.6 | PTP_CM27_BP_Intercompany Supplier | -11.52h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.25.4 | Error and Defect Mitigation | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Nevin Varkey,Ric Haraida | 2h | No | Yes | 500 | Tue 4/14/26 | Wed 4/15/26 | 6 | 1.2.2.2.25.4 | PTP_CM26_Material_Master - SERV - Service Materials | -25.27h | Yes | No | 35 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.25.2 | Pre Load Validation | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Nevin Varkey,Ric Haraida | 30m | No | Yes | 500 | Tue 4/14/26 | Tue 4/14/26 | 6 | 1.2.2.2.25.2 | PTP_CM26_Material_Master - SERV - Service Materials | -1516m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.25.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Wed 5/20/26 | Wed 5/20/26 | Nevin Varkey,Ric Haraida | 30m | No | Yes | 500 | Tue 4/7/26 | Tue 4/7/26 | 6 | 1.2.2.2.25.1 | PTP_CM26_Material_Master - SERV - Service Materials | -901m | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.20.5 | Load | Future Task | 0 | Mon 5/18/26 | Mon 5/18/26 | Nevin Varkkey | 1h | No | Yes | 500 | Wed 4/15/26 | Wed 4/15/26 | 6 | 1.2.2.2.20.5 | PTP_CM27_Vendor Master - Mass Maintenance - LFA1-WERKR | -11.52h | Yes | No | 33 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.14.4 | Error and Defect Mitigation | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Ric Haraida | 3h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.14.4 | OTC_CM19_Customer_Master - Sold-To | -76.52h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.13.9 | Post Load Validation | Future Task | 0 | Fri 5/22/26 | Mon 5/25/26 | Ric Haraida | 3h | No | Yes | 500 | Thu 4/9/26 | Fri 4/10/26 | 6 | 1.2.2.2.13.9 | OTC_CM19_Customer_Master - Ship-To | -39.02h | Yes | No | 45 | 30+ Days Slip | FALSE | 0 | 17 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.13.4 | Update number range BP02 from Internal to External | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Ric Haraida | 30m | No | Yes | 500 | Thu 4/9/26 | Fri 4/10/26 | 6 | 1.2.2.2.13.4 | OTC_CM19_Customer_Master - Ship-To | -1756m | Yes | No | 41 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.14.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Ric Haraida | 30m | No | Yes | 500 | Wed 4/8/26 | Thu 4/9/26 | 6 | 1.2.2.2.14.1 | OTC_CM19_Customer_Master - Sold-To | -1741m | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.14.2 | Pre Load Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Ric Haraida | 30m | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.14.2 | OTC_CM19_Customer_Master - Sold-To | -1741m | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.13.2 | Pre Load Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Ric Haraida | 30m | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.13.2 | OTC_CM19_Customer_Master - Ship-To | -4471m | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.13.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Ric Haraida | 30m | No | Yes | 500 | Wed 4/8/26 | Wed 4/8/26 | 6 | 1.2.2.2.13.1 | OTC_CM19_Customer_Master - Ship-To | -4471m | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.13.7 | Error and Defect Mitigation | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Ric Haraida | 4h | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.13.7 | OTC_CM19_Customer_Master - Ship-To | -39.02h | Yes | No | 43 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.14.8 | Update number range BP02 from Internal to External | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Ric Haraida | 15m | No | Yes | 500 | Thu 4/9/26 | Thu 4/9/26 | 6 | 1.2.2.2.14.8 | OTC_CM19_Customer_Master - Sold-To | -1786m | Yes | No | 42 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.54.1 | Load File Staged and Posted "Ready" | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Sam | 30m | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.54.1 | PTM_CM55_Class assignment to materials | -2356m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.2.2.2.53.1 | Manual File Staged and Posted "Ready" | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Sam | 30m | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 6 | 1.2.2.2.53.1 | PTM_CM50_Material Class | -2806m | Yes | No | 36 | 30+ Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Data Readiness | Starting Next 2 Weeks
1.1.2.6.1 | Firefighter ID setup | Future Task | 0 | Fri 5/1/26 | Thu 5/7/26 |  | 5d | No | No | 500 | Mon 10/20/25 | Fri 10/24/25 | 5 | 1.1.2.6.1 | Firefighter Configuration | 122d | Yes | No | 195 | 30+ Days Slip | TRUE | 1 | -1 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Firefighter Configuration | Overdue
1.1.2.6.1 | Firefighter ID setup | Future Task | 0 | Fri 5/1/26 | Thu 5/7/26 |  | 5d | No | No | 500 | Mon 10/20/25 | Fri 10/24/25 | 5 | 1.1.2.6.1 | Firefighter Configuration | 122d | Yes | No | 195 | 30+ Days Slip | TRUE | 1 | -1 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Firefighter Configuration | Should Have Started
1.1.2.6.2 | Firefighter log settings | Future Task | 0 | Fri 5/8/26 | Thu 5/14/26 |  | 5d | No | No | 500 | Mon 10/27/25 | Fri 10/31/25 | 5 | 1.1.2.6.2 | Firefighter Configuration | 122d | Yes | No | 195 | 30+ Days Slip | FALSE | 0 | 6 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Firefighter Configuration | Should Have Started
1.1.2.6.3 | Functional validation | Future Task | 0 | Fri 5/15/26 | Thu 5/21/26 |  | 5d | No | No | 500 | Mon 11/3/25 | Fri 11/7/25 | 5 | 1.1.2.6.3 | Firefighter Configuration | 122d | Yes | No | 195 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Firefighter Configuration | Starting This Week
1.1.1.5.4 | Environment Ready for Test | Future Task | 0 | Thu 5/14/26 | Thu 5/14/26 | PMO | 0m | Yes | Yes | 500 | Thu 7/16/26 | Thu 7/16/26 | 5 | 1.1.1.5.4 | QS4 ITC-2 Refresh | -3571m | Yes | No | -63 | On Time / Ahead | FALSE | 0 | 6 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | TRUE | QS4 ITC-2 Refresh | Starting This Week
1.1.1.5.2.7 | Import Group 4 - workbench / dev work | Future Task | 0 | Tue 5/12/26 | Tue 5/12/26 | Dev Team | 2h | No | Yes | 500 | Tue 5/26/26 | Tue 5/26/26 | 6 | 1.1.1.5.2.7 | Release Transports to Client | -182.02h | Yes | No | -14 | On Time / Ahead | FALSE | 0 | 4 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Starting This Week
1.1.1.5.2.8 | Import Group 5 - Config to support dev workbench | Future Task | 0 | Tue 5/12/26 | Wed 5/13/26 | Dev Team | 8.5h | No | Yes | 500 | Wed 5/27/26 | Thu 5/28/26 | 6 | 1.1.1.5.2.8 | Release Transports to Client | -182.02h | Yes | No | -15 | On Time / Ahead | FALSE | 0 | 5 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Starting This Week
1.1.1.5.2.3 | Import Group 2 - Core Transports | Future Task | 0.25 | Thu 5/7/26 | Thu 5/7/26 | Functional Leads | 2h | No | Yes | 500 | Fri 5/22/26 | Fri 5/22/26 | 6 | 1.1.1.5.2.3 | Release Transports to Client | -153.52h | Yes | No | -15 | On Time / Ahead | TRUE | 1 | -1 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Overdue
1.1.1.5.2.2 | Manual activities group 1 | Future Task | 0.25 | Tue 5/5/26 | Thu 5/7/26 | Functional Leads | 20h | No | Yes | 500 | Tue 5/19/26 | Fri 5/22/26 | 6 | 1.1.1.5.2.2 | Release Transports to Client | -151.52h | Yes | No | -15 | On Time / Ahead | TRUE | 1 | -1 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Overdue
1.1.1.5.2.1 | Import Group 1 - Ent Structure | Future Task | 0.25 | Tue 5/5/26 | Tue 5/5/26 | Functional Leads | 2h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.5.2.1 | Release Transports to Client | -131.52h | Yes | No | -14 | On Time / Ahead | TRUE | 3 | -3 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Overdue
1.1.1.5.2.4 | Manual activities group 2 | Future Task | 0.25 | Fri 5/8/26 | Fri 5/8/26 | Functional Leads | 1d | No | Yes | 500 | Fri 5/22/26 | Mon 5/25/26 | 6 | 1.1.1.5.2.4 | Release Transports to Client | -20.19d | Yes | No | -17 | On Time / Ahead | FALSE | 0 | 0 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Should Have Started
1.1.1.5.2.3 | Import Group 2 - Core Transports | Future Task | 0.25 | Thu 5/7/26 | Thu 5/7/26 | Functional Leads | 2h | No | Yes | 500 | Fri 5/22/26 | Fri 5/22/26 | 6 | 1.1.1.5.2.3 | Release Transports to Client | -153.52h | Yes | No | -15 | On Time / Ahead | TRUE | 1 | -1 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Should Have Started
1.1.1.5.2.1 | Import Group 1 - Ent Structure | Future Task | 0.25 | Tue 5/5/26 | Tue 5/5/26 | Functional Leads | 2h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.5.2.1 | Release Transports to Client | -131.52h | Yes | No | -14 | On Time / Ahead | TRUE | 3 | -3 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Should Have Started
1.1.1.5.2.2 | Manual activities group 1 | Future Task | 0.25 | Tue 5/5/26 | Thu 5/7/26 | Functional Leads | 20h | No | Yes | 500 | Tue 5/19/26 | Fri 5/22/26 | 6 | 1.1.1.5.2.2 | Release Transports to Client | -151.52h | Yes | No | -15 | On Time / Ahead | TRUE | 1 | -1 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Should Have Started
1.1.1.6.2.2 | Manual activities group 1 | Future Task | 0 | Thu 5/21/26 | Mon 5/25/26 | Functional Leads | 20h | No | Yes | 500 | Tue 5/19/26 | Fri 5/22/26 | 6 | 1.1.1.6.2.2 | Release Transports to Client | -225.52h | Yes | No | 3 | 1-7 Days Slip | FALSE | 0 | 17 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Starting Next 2 Weeks
1.1.1.6.2.1 | Import Group 1 - Ent Structure | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Functional Leads | 2h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.6.2.1 | Release Transports to Client | -225.52h | Yes | No | 2 | 1-7 Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Starting Next 2 Weeks
1.1.1.5.2.5 | Import Group 3 - prior to transactions | Future Task | 0.25 | Mon 5/11/26 | Mon 5/11/26 | Functional Leads | 2h | No | Yes | 500 | Mon 5/25/26 | Mon 5/25/26 | 6 | 1.1.1.5.2.5 | Release Transports to Client | -163.52h | Yes | No | -14 | On Time / Ahead | FALSE | 0 | 3 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Starting This Week
1.1.1.5.2.6 | Manual Activities Group 3 | Future Task | 0.25 | Mon 5/11/26 | Tue 5/12/26 | Functional Leads | 1d | No | Yes | 500 | Mon 5/25/26 | Tue 5/26/26 | 6 | 1.1.1.5.2.6 | Release Transports to Client | -22.75d | Yes | No | -14 | On Time / Ahead | FALSE | 0 | 4 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Release Transports to Client | Starting This Week
1.1.2.4.5 | Final Review Rule Set and update the recommendations | Late | 0.6 | Fri 10/31/25 | Wed 1/7/26 |  | 4d | No | No | 500 | Fri 10/31/25 | Wed 11/5/25 | 5 | 1.1.2.4.5 | Rule Set & Role Design | 218.4d | Yes | No | 63 | 30+ Days Slip | TRUE | 121 | -121 | Oct 2025 | Jan 2026 | Q1 2026 | FALSE | TRUE | FALSE | Rule Set & Role Design | Overdue
1.1.2.4.9 | Risk analysis on existing roles | Future Task | 0 | Fri 5/1/26 | Thu 5/7/26 |  | 5d | No | No | 500 | Thu 11/20/25 | Wed 11/26/25 | 5 | 1.1.2.4.9 | Rule Set & Role Design | 122d | Yes | No | 162 | 30+ Days Slip | TRUE | 1 | -1 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Rule Set & Role Design | Overdue
1.1.2.4.9 | Risk analysis on existing roles | Future Task | 0 | Fri 5/1/26 | Thu 5/7/26 |  | 5d | No | No | 500 | Thu 11/20/25 | Wed 11/26/25 | 5 | 1.1.2.4.9 | Rule Set & Role Design | 122d | Yes | No | 162 | 30+ Days Slip | TRUE | 1 | -1 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Rule Set & Role Design | Should Have Started
1.1.2.4.10 | Role remediation planning - Can impact role design & Possible of retesting. | Future Task | 0 | Fri 5/8/26 | Thu 5/21/26 |  | 10d | No | No | 500 | Thu 11/27/25 | Wed 12/10/25 | 5 | 1.1.2.4.10 | Rule Set & Role Design | 122d | Yes | No | 162 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Rule Set & Role Design | Should Have Started
1.3.3.1 | Test Readiness Review (TRR) - ITC 1 | Future Task | 0.25 | Thu 4/16/26 | Fri 5/1/26 |  | 1h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 4 | 1.3.3.1 | Testing Cycles | -87.75h | Yes | No | 15 | 15-30 Days Slip | TRUE | 7 | -7 | Apr 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Solution Readniess | Overdue
1.3.3.5.4 | ITC-1 Team Testing | Future Task | 0.25 | Mon 4/27/26 | Mon 5/18/26 |  | 15d | No | No | 500 | Mon 4/27/26 | Fri 5/15/26 | 5 | 1.3.3.5.4 | ITC-1 | 125.66d | Yes | No | 3 | 1-7 Days Slip | FALSE | 0 | 10 | Apr 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Solution Readniess | Should Have Started
1.3.1.1 | FICO | Future Task | 0.03 | Mon 5/4/26 | Fri 5/29/26 |  | 20d | No | No | 500 | Fri 5/22/26 | Fri 5/22/26 | 4 | 1.3.1.1 | Business Process Design Documentation | 116d | Yes | No | 7 | 1-7 Days Slip | FALSE | 0 | 21 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Solution Readniess | Should Have Started
1.3.1.3 | Procure to Pay | Future Task | 0.04 | Mon 5/4/26 | Fri 5/29/26 |  | 20d | No | No | 500 | Fri 5/22/26 | Fri 5/22/26 | 4 | 1.3.1.3 | Business Process Design Documentation | 116d | Yes | No | 7 | 1-7 Days Slip | FALSE | 0 | 21 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Solution Readniess | Should Have Started
1.3.1.4 | Plan to Make | Future Task | 0.05 | Mon 5/4/26 | Fri 5/29/26 |  | 20d | No | No | 500 | Fri 5/22/26 | Fri 5/22/26 | 4 | 1.3.1.4 | Business Process Design Documentation | 116d | Yes | No | 7 | 1-7 Days Slip | FALSE | 0 | 21 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Solution Readniess | Should Have Started
1.3.2.1 | Reports | Future Task | 0 | Mon 5/4/26 | Fri 8/14/26 |  | 75d | No | No | 500 | Fri 5/22/26 | Fri 5/22/26 | 4 | 1.3.2.1 | Development RICEFW | 61d | Yes | No | 84 | 30+ Days Slip | FALSE | 0 | 98 | May 2026 | Aug 2026 | Q3 2026 | FALSE | FALSE | FALSE | Solution Readniess | Should Have Started
1.3.2.2 | Interfaces | Future Task | 0 | Mon 5/4/26 | Fri 8/14/26 |  | 75d | No | No | 500 | Fri 5/22/26 | Fri 5/22/26 | 4 | 1.3.2.2 | Development RICEFW | 61d | Yes | No | 84 | 30+ Days Slip | FALSE | 0 | 98 | May 2026 | Aug 2026 | Q3 2026 | FALSE | FALSE | FALSE | Solution Readniess | Should Have Started
1.3.2.4 | Workflow | Future Task | 0 | Mon 5/4/26 | Fri 8/14/26 |  | 75d | No | No | 500 | Fri 5/22/26 | Fri 5/22/26 | 4 | 1.3.2.4 | Development RICEFW | 61d | Yes | No | 84 | 30+ Days Slip | FALSE | 0 | 98 | May 2026 | Aug 2026 | Q3 2026 | FALSE | FALSE | FALSE | Solution Readniess | Should Have Started
1.3.1.2 | Order to Cash | Future Task | 0.04 | Mon 5/4/26 | Fri 5/29/26 |  | 20d | No | No | 500 | Fri 5/22/26 | Fri 5/22/26 | 4 | 1.3.1.2 | Business Process Design Documentation | 116d | Yes | No | 7 | 1-7 Days Slip | FALSE | 0 | 21 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Solution Readniess | Should Have Started
1.3.2.3 | Enhanchments | Future Task | 0 | Mon 5/4/26 | Fri 8/14/26 |  | 61d | No | No | 500 | Fri 5/22/26 | Fri 5/22/26 | 4 | 1.3.2.3 | Development RICEFW | 61d | Yes | No | 84 | 30+ Days Slip | FALSE | 0 | 98 | May 2026 | Aug 2026 | Q3 2026 | FALSE | FALSE | FALSE | Solution Readniess | Should Have Started
1.3.3.1 | Test Readiness Review (TRR) - ITC 1 | Future Task | 0.25 | Thu 4/16/26 | Fri 5/1/26 |  | 1h | No | Yes | 500 | Thu 4/16/26 | Thu 4/16/26 | 4 | 1.3.3.1 | Testing Cycles | -87.75h | Yes | No | 15 | 15-30 Days Slip | TRUE | 7 | -7 | Apr 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Solution Readniess | Should Have Started
1.3.3.5.5 | ITC-1 Defect Correction / Retesting / Mitigation / Close | Future Task | 0.25 | Wed 5/6/26 | Tue 5/19/26 |  | 10d | No | No | 500 | Mon 5/18/26 | Fri 5/29/26 | 5 | 1.3.3.5.5 | ITC-1 | 124d | Yes | No | -10 | On Time / Ahead | FALSE | 0 | 11 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Solution Readniess | Should Have Started
1.3.3.5.6 | ITC-1 Gate Review | Future Task | 0 | Fri 5/15/26 | Fri 5/15/26 |  | 8h | No | No | 500 | Thu 7/23/26 | Thu 7/23/26 | 5 | 1.3.3.5.6 | ITC-1 | 1008h | Yes | No | -69 | On Time / Ahead | FALSE | 0 | 7 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Solution Readniess | Starting This Week
1.1.1.5.1.12 | Download Transport List | Future Task | 0.25 | Mon 5/4/26 | Mon 5/4/26 | Basis | 1h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.5.1.12 | System Setup | -133.02h | Yes | No | -15 | On Time / Ahead | TRUE | 4 | -4 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Overdue
1.1.1.5.1.13 | Business Functions Validation | Future Task | 0.25 | Mon 5/4/26 | Mon 5/4/26 | Basis | 8h | No | Yes | 500 | Tue 5/19/26 | Wed 5/20/26 | 6 | 1.1.1.5.1.13 | System Setup | -140.02h | Yes | No | -16 | On Time / Ahead | TRUE | 4 | -4 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Overdue
1.1.1.5.1.12 | Download Transport List | Future Task | 0.25 | Mon 5/4/26 | Mon 5/4/26 | Basis | 1h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.5.1.12 | System Setup | -133.02h | Yes | No | -15 | On Time / Ahead | TRUE | 4 | -4 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Should Have Started
1.1.1.5.1.13 | Business Functions Validation | Future Task | 0.25 | Mon 5/4/26 | Mon 5/4/26 | Basis | 8h | No | Yes | 500 | Tue 5/19/26 | Wed 5/20/26 | 6 | 1.1.1.5.1.13 | System Setup | -140.02h | Yes | No | -16 | On Time / Ahead | TRUE | 4 | -4 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Should Have Started
1.1.1.6.1.3 | Technical Transports / BP Setup | Future Task | 0 | Fri 5/22/26 | Fri 5/22/26 | Basis | 1d | No | No | 500 | Mon 5/11/26 | Tue 5/12/26 | 6 | 1.1.1.6.1.3 | System Setup | 7d | Yes | No | 10 | 8-14 Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Starting Next 2 Weeks
1.1.1.6.1.1 | System Refresh Basis(Workinig with NS2) | Future Task | 0 | Mon 5/18/26 | Wed 5/20/26 | Basis | 3d | No | Yes | 500 | Fri 5/1/26 | Fri 5/1/26 | 6 | 1.1.1.6.1.1 | System Setup | 0d | Yes | No | 19 | 15-30 Days Slip | FALSE | 0 | 12 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Starting Next 2 Weeks
1.1.1.6.1.2 | Client Config / Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Basis | 1d | No | Yes | 500 | Fri 5/8/26 | Mon 5/11/26 | 6 | 1.1.1.6.1.2 | System Setup | -28.19d | Yes | No | 10 | 8-14 Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Starting Next 2 Weeks
1.1.1.6.1.13 | Business Functions Validation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Basis | 8h | No | No | 500 | Tue 5/19/26 | Wed 5/20/26 | 6 | 1.1.1.6.1.13 | System Setup | 88h | Yes | No | 1 | 1-7 Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Starting Next 2 Weeks
1.1.1.6.1.12 | Download Transport List | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Basis | 1h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.6.1.12 | System Setup | -225.52h | Yes | No | 2 | 1-7 Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Starting Next 2 Weeks
1.1.1.6.1.10 | Validate Fiori | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Basis | 4h | No | No | 500 | Mon 5/18/26 | Tue 5/19/26 | 6 | 1.1.1.6.1.10 | System Setup | 92h | Yes | No | 2 | 1-7 Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Starting Next 2 Weeks
1.1.1.6.1.9 | Manual Technical Tasks | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Basis | 1d | No | Yes | 500 | Fri 5/15/26 | Mon 5/18/26 | 6 | 1.1.1.6.1.9 | System Setup | -28.19d | Yes | No | 3 | 1-7 Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Starting Next 2 Weeks
1.1.1.5.1.11 | Fiori App Activation | Future Task | 0.25 | Mon 5/4/26 | Mon 5/4/26 | Dev Team | 6h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.5.1.11 | System Setup | -138.02h | Yes | No | -15 | On Time / Ahead | TRUE | 4 | -4 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Overdue
1.1.1.5.1.11 | Fiori App Activation | Future Task | 0.25 | Mon 5/4/26 | Mon 5/4/26 | Dev Team | 6h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.5.1.11 | System Setup | -138.02h | Yes | No | -15 | On Time / Ahead | TRUE | 4 | -4 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Should Have Started
1.1.1.6.1.11 | Fiori App Activation | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Dev Team | 6h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.6.1.11 | System Setup | -225.52h | Yes | No | 2 | 1-7 Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Starting Next 2 Weeks
1.1.1.5.1.14 | Functional Leads Validation of Transport List | Future Task | 0.25 | Mon 5/4/26 | Mon 5/4/26 | Functional Leads | 1h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.5.1.14 | System Setup | -133.02h | Yes | No | -15 | On Time / Ahead | TRUE | 4 | -4 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Overdue
1.1.1.5.1.14 | Functional Leads Validation of Transport List | Future Task | 0.25 | Mon 5/4/26 | Mon 5/4/26 | Functional Leads | 1h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.5.1.14 | System Setup | -133.02h | Yes | No | -15 | On Time / Ahead | TRUE | 4 | -4 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Should Have Started
1.1.1.6.1.14 | Functional Leads Validation of Transport | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Functional Leads | 1h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.6.1.14 | System Setup | -225.52h | Yes | No | 2 | 1-7 Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Starting Next 2 Weeks
1.1.1.5.1.15 | Release Security roles to Functional Team | Future Task | 0.25 | Mon 5/4/26 | Mon 5/4/26 | Security | 1h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.5.1.15 | System Setup | -134.02h | Yes | No | -15 | On Time / Ahead | TRUE | 4 | -4 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Overdue
1.1.1.5.1.15 | Release Security roles to Functional Team | Future Task | 0.25 | Mon 5/4/26 | Mon 5/4/26 | Security | 1h | No | Yes | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.5.1.15 | System Setup | -134.02h | Yes | No | -15 | On Time / Ahead | TRUE | 4 | -4 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Should Have Started
1.1.1.6.1.7 | Security Transports | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Security | 4h | No | Yes | 500 | Fri 5/15/26 | Fri 5/15/26 | 6 | 1.1.1.6.1.7 | System Setup | -225.52h | Yes | No | 6 | 1-7 Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Starting Next 2 Weeks
1.1.1.6.1.8 | Security Manual Tasks | Future Task | 0 | Thu 5/21/26 | Fri 5/22/26 | Security | 1d | No | No | 500 | Fri 5/15/26 | Mon 5/18/26 | 6 | 1.1.1.6.1.8 | System Setup | 10.5d | Yes | No | 4 | 1-7 Days Slip | FALSE | 0 | 14 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Starting Next 2 Weeks
1.1.1.6.1.15 | Release Security roles to Functional Team | Future Task | 0 | Thu 5/21/26 | Thu 5/21/26 | Security | 1h | No | No | 500 | Tue 5/19/26 | Tue 5/19/26 | 6 | 1.1.1.6.1.15 | System Setup | 95h | Yes | No | 2 | 1-7 Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | System Setup | Starting Next 2 Weeks
1.1.2.7.1 | Unit testing | Future Task | 0 | Fri 5/1/26 | Wed 5/13/26 |  | 9d | No | No | 500 | Mon 11/10/25 | Thu 11/20/25 | 5 | 1.1.2.7.1 | Testing & Training | 68d | Yes | No | 174 | 30+ Days Slip | FALSE | 0 | 5 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Testing & Training | Should Have Started
1.1.2.7.4 | Workflow Activation / Data load in Test System | Future Task | 0 | Fri 5/22/26 | Thu 5/28/26 |  | 5d | No | No | 500 | Mon 12/1/25 | Fri 12/5/25 | 5 | 1.1.2.7.4 | Testing & Training | 68d | Yes | No | 174 | 30+ Days Slip | FALSE | 0 | 20 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Testing & Training | Starting Next 2 Weeks
1.1.2.7.3 | Connector configuration (S4 / LDAP Connector) | Future Task | 0 | Tue 5/19/26 | Thu 5/21/26 |  | 3d | No | No | 500 | Wed 11/26/25 | Fri 11/28/25 | 5 | 1.1.2.7.3 | Testing & Training | 68d | Yes | No | 174 | 30+ Days Slip | FALSE | 0 | 13 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Testing & Training | Starting Next 2 Weeks
1.1.2.7.2 | Changes moved to Test System | Future Task | 0 | Thu 5/14/26 | Mon 5/18/26 |  | 3d | No | No | 500 | Fri 11/21/25 | Tue 11/25/25 | 5 | 1.1.2.7.2 | Testing & Training | 68d | Yes | No | 174 | 30+ Days Slip | FALSE | 0 | 10 | May 2026 | May 2026 | Q2 2026 | FALSE | FALSE | FALSE | Testing & Training | Starting This Week

## Metrics
#REF! | #REF! | #REF! | ↑ Live Data | Domain | Viz Type | Title | Metric / KPI | Source Query | Source Field(s) | Audit Status | Audit Notes
#REF! | #REF! | #REF! | → Analytics Catalogue | RISKS | Card | Total Risks | Count of all risk records | PQ_RisksDetails | Risk ID | ✅ | Risk ID: confirmed in source
#REF! | #REF! | #REF! |  | RISKS | Card | Open Risks | Count where Risk Status = Open | PQ_RisksDetails | Risk Status | ✅ | Risk Status: confirmed in source
#REF! | #REF! | #REF! |  | RISKS | Card | Closed Risks | Count where Risk Status = Closed | PQ_RisksDetails | Risk Status | ✅ | Risk Status: confirmed in source
#REF! | #REF! | #REF! |  | RISKS | Card | Risks Aged > 90 Days | Open risks with Age > 90 days | PQ_RisksDetails | Is Open + Age (Days) | ✅ | Is Open + Age (Days): both computed; confirmed
#REF! | #REF! | #REF! |  | RISKS | Donut / Pie | Risk Status Breakdown | % Open vs Closed vs Mitigated | PQ_RisksDetails | Risk Status | ✅ | Risk Status: confirmed in source
#REF! | #REF! | #REF! |  | RISKS | Horizontal Bar | Risks by Workstream | Count per workstream, stacked by status | PQ_RisksDetails | Workstream + Risk Status | ❌ | FIX NEEDED: Risks source has NO Workstream column. Replace with [Assigned To] or remove grouping.
#REF! | #REF! | #REF! |  | RISKS | Horizontal Bar | Risks by Impact Level | Count per Impact rating | PQ_RisksDetails | Impact | ✅ | Impact: confirmed native column in Risks source
#REF! | #REF! | #REF! |  | RISKS | Horizontal Bar | Risks by Probability | Count per Probability rating | PQ_RisksDetails | Probability | ✅ | Probability: confirmed native column in Risks source
#REF! | #REF! | #REF! |  | RISKS | Scatter / Matrix | Risk Heat Map | Probability vs Impact (open risks only) | PQ_RisksDetails | Probability + Impact + Risk Status | ✅ | Probability + Impact + Risk Status: all confirmed native columns
#REF! | #REF! | #REF! |  | RISKS | Bar | Age Distribution of Open Risks | Count by Age Bucket (0-7, 8-30, 31-90, 90+) | PQ_RisksDetails | Age Bucket + Is Open | ✅ | Age Bucket + Is Open: both computed columns; confirmed
#REF! | #REF! | #REF! |  | RISKS | Time Series (Line) | Risks Opened by Month | Count of risks created per month | PQ_RisksDetails | Created Month | ✅ | Created Month: computed; format standardised to MMM yyyy (v2)
#REF! | #REF! | #REF! |  | RISKS | Time Series (Line) | Risks Closed by Month | Count closed per month (if closed date available) | PQ_RisksDetails | Created Month + Risk Status | ✅ | Created Month + Risk Status: both confirmed
#REF! | #REF! | #REF! |  | RISKS | Table / Detail | Open Risk Register | Full list of open risks with owner and age | PQ_RisksDetails | All columns, filtered Is Open=TRUE | ✅ | All columns preserved — no SelectColumns step in PQ_RisksDetails
#REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | ISSUES | Card | Total Issues | Count of all issue records | PQ_IssuesDetails | Issue ID | ✅ | Issue ID: confirmed in source
#REF! | #REF! | #REF! |  | ISSUES | Card | Open / Escalated Issues | Count where Is Open = TRUE | PQ_IssuesDetails | Is Open | ✅ | Is Open: computed; confirmed
#REF! | #REF! | #REF! |  | ISSUES | Card | Escalated Issues | Count where Issue Status = Escalated | PQ_IssuesDetails | Is Escalated | ✅ | Is Escalated: computed; confirmed
#REF! | #REF! | #REF! |  | ISSUES | Card | Issues Open > 30 Days | Open issues with Age > 30 days | PQ_IssuesDetails | Is Open + Age (Days) | ✅ | Is Open + Age (Days): both computed; confirmed
#REF! | #REF! | #REF! |  | ISSUES | Donut / Pie | Issue Status Breakdown | % Open vs Escalated vs Closed | PQ_IssuesDetails | Issue Status | ✅ | Issue Status: confirmed in source
#REF! | #REF! | #REF! |  | ISSUES | Horizontal Bar | Issues by Workstream | Count per workstream by status | PQ_IssuesDetails | Workstream + Issue Status | ✅ | Workstream: confirmed native column in Issues source
#REF! | #REF! | #REF! |  | ISSUES | Horizontal Bar | Issues by Priority | Count per priority level | PQ_IssuesDetails | Issue Priority | ✅ | Issue Priority: confirmed native column in Issues source
#REF! | #REF! | #REF! |  | ISSUES | Bar | Issue Age Distribution | Count by Age Bucket | PQ_IssuesDetails | Age Bucket + Is Open | ✅ | Age Bucket + Is Open: both computed; confirmed
#REF! | #REF! | #REF! |  | ISSUES | Time Series (Line) | Issues Opened by Month | Count created per calendar month | PQ_IssuesDetails | Created Month | ✅ | Created Month: computed (MMM yyyy); confirmed
#REF! | #REF! | #REF! |  | ISSUES | Time Series (Line) | Issues by Quarter | Quarterly trend of open vs closed count | PQ_IssuesDetails | Created Quarter + Issue Status | ✅ | Created Quarter: computed; confirmed
#REF! | #REF! | #REF! |  | ISSUES | Table / Detail | Open Issue Register | Full list of open/escalated issues with owner | PQ_IssuesDetails | All columns, filtered Is Open=TRUE | ⚠️ | All columns available in query. NOTE: Issues source has 16,383 empty columns; worksheet load blocked — use connection-only / direct query in viz tool.
#REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | DECISIONS | Card | Total Decisions | Count of all decision records | PQ_DecisionsDetails | Decision ID | ✅ | Decision ID: confirmed in source
#REF! | #REF! | #REF! |  | DECISIONS | Card | Open Decisions | Count where Decision Status = Open | PQ_DecisionsDetails | Is Open | ✅ | Is Open: computed; confirmed
#REF! | #REF! | #REF! |  | DECISIONS | Card | Decisions Open > 30 Days | Open decisions aged beyond 30 days | PQ_DecisionsDetails | Is Open + Age (Days) | ✅ | Is Open + Age (Days): both computed; confirmed
#REF! | #REF! | #REF! |  | DECISIONS | Donut / Pie | Decision Status Breakdown | % Open vs Closed vs Pending | PQ_DecisionsDetails | Decision Status | ✅ | Decision Status: confirmed in source
#REF! | #REF! | #REF! |  | DECISIONS | Horizontal Bar | Decisions by Workstream | Count per workstream | PQ_DecisionsDetails | Workstream + Decision Status | ❌ | FIX NEEDED: Decisions source has NO Workstream column. Replace with [Decision Type] or [Assigned To] as grouping dimension.
#REF! | #REF! | #REF! |  | DECISIONS | Bar | Decision Age Distribution | Count by Age Bucket | PQ_DecisionsDetails | Age Bucket + Is Open | ✅ | Age Bucket + Is Open: both computed; confirmed
#REF! | #REF! | #REF! |  | DECISIONS | Time Series (Line) | Decisions by Month | Created per month trend | PQ_DecisionsDetails | Created Month | ✅ | Created Month: computed (MMM yyyy); confirmed
#REF! | #REF! | #REF! |  | DECISIONS | Table / Detail | Open Decision Register | Full list of open/pending decisions | PQ_DecisionsDetails | All columns, filtered Decision Status<>Closed | ✅ | All columns preserved — no SelectColumns step in PQ_DecisionsDetails
#REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | ACTIONS | Card | Total Actions | Count of all action records | PQ_ActionsDetails | Action Item ID | ✅ | Action Item ID: confirmed in source
#REF! | #REF! | #REF! |  | ACTIONS | Card | Open / In Progress Actions | Count where Is Active = TRUE | PQ_ActionsDetails | Is Active | ✅ | Is Active: computed; confirmed
#REF! | #REF! | #REF! |  | ACTIONS | Card | Overdue Actions | Count where Is Overdue = TRUE | PQ_ActionsDetails | Is Overdue | ✅ | Is Overdue: computed from Target Date; confirmed
#REF! | #REF! | #REF! |  | ACTIONS | Card | Avg Days Overdue | Average days past Target Date (overdue only) | PQ_ActionsDetails | Days Overdue | ✅ | Days Overdue: computed; confirmed
#REF! | #REF! | #REF! |  | ACTIONS | Donut / Pie | Action Status Breakdown | % Open vs In Progress vs Closed | PQ_ActionsDetails | Action Item Status | ✅ | Action Item Status: confirmed in source
|  |  |  | ACTIONS | Horizontal Bar | Actions by Workstream | Count per workstream by status | PQ_ActionsDetails | Workstream + Action Item Status | ✅ | Workstream: FIXED — source column had leading space ' Workstream'; now trimmed via RenameColumns in query v2
|  |  |  | ACTIONS | Horizontal Bar | Actions by Priority | Count per priority level | PQ_ActionsDetails | Action Item Priority | ✅ | Action Item Priority: confirmed in source
|  |  |  | ACTIONS | Bar | Overdue Actions by Workstream | Count of overdue per workstream | PQ_ActionsDetails | Workstream + Is Overdue | ✅ | Workstream + Is Overdue: FIXED — leading-space column trimmed in query v2
|  |  |  | ACTIONS | Bar | Action Age Distribution | Count by Age Bucket | PQ_ActionsDetails | Age Bucket + Is Active | ✅ | Age Bucket + Is Active: both computed; confirmed
|  |  |  | ACTIONS | Time Series (Line) | Actions Opened by Month | Count created per month | PQ_ActionsDetails | Created Month | ✅ | Created Month: confirmed (MMM yyyy)
|  |  |  | ACTIONS | Table / Detail | Overdue Action Register | Full list of overdue actions with owner & days overdue | PQ_ActionsDetails | All columns, filtered Is Overdue=TRUE | ✅ | All cleaned source columns preserved via RealCols + TrimmedCols steps
|  |  |  | PROJECT PLAN | Card | Total Tasks | Count of all task rows | PQ_ProjectPlanDetails | Task Name | ✅ | Task Name: confirmed in source
|  |  |  | PROJECT PLAN | Card | % Complete (Avg) | Average % Complete across all tasks | PQ_ProjectPlanDetails | % Complete | ✅ | % Complete: confirmed (decimal 0-1 in source; multiply ×100 in summaries/viz)
|  |  |  | PROJECT PLAN | Card | Tasks Past Due | Count where Past Due = TRUE | PQ_ProjectPlanDetails | Past Due | ✅ | Past Due: computed column; confirmed
|  |  |  | PROJECT PLAN | Card | Avg Schedule Slip (Days) | Mean schedule slip across all tasks | PQ_ProjectPlanDetails | Schedule Slip (Days) | ✅ | Schedule Slip (Days): computed column; confirmed
|  |  |  | PROJECT PLAN | Card | Milestones | Count of milestone tasks | PQ_ProjectPlanDetails | Is Milestone Flag | ✅ | Is Milestone Flag: computed from Milestone column; confirmed
|  |  |  | PROJECT PLAN | Donut / Pie | Task Status Breakdown | % Future / On Schedule / Late / Complete | PQ_ProjectPlanDetails | Status | ✅ | Status: confirmed in source
|  |  |  | PROJECT PLAN | Stacked Bar | Tasks by Phase / Workstream | Count by phase, stacked by status | PQ_ProjectPlanDetails | Outline Level + Status [Phase N/A in source; Outline Level added in v2] | ⚠️ | UPDATED: 'Phase' not in source. Outline Level + Task Summary Name NOW ADDED to query v2. Use [Outline Level] for phase grouping.
|  |  |  | PROJECT PLAN | Horizontal Bar | Schedule Slip by Workstream | Avg slip days per workstream | PQ_ProjectPlanDetails | Outline Level + Schedule Slip (Days) [Workstream N/A — use Outline Level proxy] | ❌ | FIX NEEDED: No Workstream in Project Plan source. Replace with [Outline Level] (added in query v2) or [Priority] as grouping proxy.
|  |  |  | PROJECT PLAN | Bar | Slip Bucket Distribution | Count of tasks per slip bucket | PQ_ProjectPlanDetails | Slip Bucket | ✅ | Slip Bucket: computed column; confirmed
|  |  |  | PROJECT PLAN | Bar | % Complete by Phase | Avg % Complete per phase | PQ_ProjectPlanDetails | Outline Level + % Complete [Phase N/A; use Outline Level 1/2 for phase] | ⚠️ | UPDATED: 'Phase' not in source. Use [Outline Level] (added in query v2). Group by Outline Level 1 or 2 for phase.
|  |  |  | PROJECT PLAN | Time Series (Line) | Tasks Completing by Month | Count of tasks with Finish in each month | PQ_ProjectPlanDetails | Finish Month | ✅ | Finish Month: computed column; confirmed (MMM yyyy)
|  |  |  | PROJECT PLAN | Time Series (Line) | Scheduled vs Actual Finish Trend | Baseline vs actual finish drift over time | PQ_ProjectPlanDetails | Finish Month + Schedule Slip (Days) | ✅ | Finish Month + Schedule Slip (Days): both confirmed
|  |  |  | PROJECT PLAN | Gantt (Table-based) | Milestone Timeline | Milestone tasks with start/finish dates | PQ_ProjectPlanDetails | Is Milestone Flag + Start + Finish | ✅ | Is Milestone Flag + Start + Finish: all confirmed in source
|  |  |  | PROJECT PLAN | Scatter | Slip vs % Complete | Tasks plotted by completion vs slip (bubble = workstream) | PQ_ProjectPlanDetails | % Complete + Schedule Slip (Days) + Priority [Workstream N/A — use Priority as colour dimension] | ❌ | FIX NEEDED: No Workstream in Project Plan. Replace bubble dimension with [Priority] or [Outline Level] (added in query v2).
|  |  |  | PROJECT PLAN | Table / Detail | Late & Past Due Task List | All tasks with Status=Late or Past Due=TRUE | PQ_ProjectPlanDetails | All columns, filtered Is Late=TRUE or Past Due=TRUE | ✅ | Is Late + Past Due: both confirmed computed columns
|  |  |  | RESOURCES | Card | Unique Resources | Distinct count of resource names | PQ_ProjectPlanDetails | Resource Names (split by semicolon) | ✅ | Resource Names: confirmed native column; split by ';' delimiter in viz
|  |  |  | RESOURCES | Card | Total Assignments | Count of resource-task assignments | PQ_ProjectPlanDetails | Resource Names (expanded) | ✅ | PQ_ResourcesDetails[Task Count]: confirmed aggregated column
|  |  |  | RESOURCES | Card | Avg % Complete (Resources) | Mean % Complete of resource-assigned tasks | PQ_ProjectPlanDetails | % Complete (resource rows) | ✅ | PQ_ResourcesDetails[Avg % Complete]: confirmed aggregated column
|  |  |  | RESOURCES | Horizontal Bar | Assignments per Resource | Count of tasks per named resource | PQ_ProjectPlanDetails | Resource Names (expanded) | ✅ | PQ_ResourcesDetails[Task Count]: use for count per resource
|  |  |  | RESOURCES | Horizontal Bar | % Complete by Resource | Avg completion per resource | PQ_ProjectPlanDetails | Resource Names + % Complete | ✅ | PQ_ResourcesDetails[Resource Names + Avg % Complete]: both confirmed
|  |  |  | RESOURCES | Stacked Bar | Resource Load by Workstream | Assignments per resource per workstream | PQ_ProjectPlanDetails | Resource Names + Workstream | ❌ | FIX NEEDED: No Workstream in PQ_ResourcesDetails (grouped by resource). Use PQ_ProjectPlanDetails with [Outline Level] expanded by resource as proxy.
|  |  |  | RESOURCES | Time Series (Line) | Resource Activity by Month | Assignments with finish date per month | PQ_ProjectPlanDetails | Resource Names + Finish Month | ✅ | Use PQ_ProjectPlanDetails: Resource Names (expanded) + Finish Month — both confirmed
|  |  |  | RESOURCES | Table / Detail | Resource Assignment Detail | All task-resource rows with status and completion | PQ_ProjectPlanDetails | Resource Names + Task Name + % Complete + Status | ✅ | PQ_ProjectPlanDetails: Resource Names + Task Name + % Complete + Status — all confirmed
|  |  |  | TESTING | Card | Total Tests | Count of all test cases (stub — data TBD) | PQ_TestingDetails | Test ID | ✅ | Test ID: confirmed in stub schema
|  |  |  | TESTING | Card | Passed / Failed / Blocked | Count per test outcome | PQ_TestingDetails | Status (stub field — rename to Test Status when real data connected) | ⚠️ | NOTE: Stub column is 'Status' (not 'Test Status'). Fix source field reference when real data source is connected.
|  |  |  | TESTING | Donut / Pie | Test Result Breakdown | % Passed vs Failed vs Blocked vs Not Run | PQ_TestingDetails | Status (stub field — rename to Test Status when real data connected) | ⚠️ | NOTE: Stub column is 'Status' (not 'Test Status'). Fix source field reference when real data source is connected.
|  |  |  | TESTING | Stacked Bar | Test Results by Workstream | Count per workstream by result | PQ_TestingDetails | Workstream + Test Status | ❌ | FIX NEEDED: Workstream NOT in stub schema. Add column to PQ_TestingDetails stub when real test source connected.
|  |  |  | TESTING | Time Series (Line) | Test Execution Trend | Tests run and passed per sprint/week | PQ_TestingDetails | Execution Date | ✅ | Execution Date: confirmed in stub schema
|  |  |  | TESTING | Table / Detail | Failed / Blocked Test List | All failed or blocked tests with owner | PQ_TestingDetails | All columns, filtered Test Status=Failed or Blocked | ⚠️ | NOTE: Filter on stub column 'Status' (not 'Test Status'). Update when real data source connected.
|  |  |  | DEFECTS | Card | Total Defects | Count of all defect records (stub — data TBD) | PQ_DefectsDetails | Defect ID | ✅ | Defect ID: confirmed in stub schema
|  |  |  | DEFECTS | Card | Open Defects | Count where Defect Status = Open | PQ_DefectsDetails | Status (stub field — rename to Defect Status when real data connected) | ⚠️ | NOTE: Stub column is 'Status' not 'Defect Status'. Fix source field reference when real data connected.
|  |  |  | DEFECTS | Card | Critical Defects | Count where Priority = Critical | PQ_DefectsDetails | Severity (stub field — NOT Priority; PQ_DefectsSummary already uses [Severity]='Critical') | ⚠️ | NOTE: Stub column is 'Severity' not 'Priority'. PQ_DefectsSummary already uses [Severity]='Critical' (correct). Update catalogue field name.
|  |  |  | DEFECTS | Donut / Pie | Defect Status Breakdown | % Open vs In Fix vs Closed | PQ_DefectsDetails | Status (stub field — rename to Defect Status when real data connected) | ⚠️ | NOTE: Stub column is 'Status' not 'Defect Status'. Fix source field reference when real data connected.
|  |  |  | DEFECTS | Horizontal Bar | Defects by Severity | Count per severity level | PQ_DefectsDetails | Severity | ✅ | Severity: confirmed in stub schema
|  |  |  | DEFECTS | Horizontal Bar | Defects by Workstream | Count per workstream | PQ_DefectsDetails | Workstream + Defect Status | ❌ | FIX NEEDED: Workstream NOT in stub schema. Add column to PQ_DefectsDetails stub when real defect source connected.
|  |  |  | DEFECTS | Time Series (Line) | Defects Opened vs Closed by Week | Burn-up/burn-down of defect backlog | PQ_DefectsDetails | Created Date + Resolved Date | ⚠️ | Created Date: in stub schema. Resolved Date NOT in stub — add to PQ_DefectsDetails stub when real data connected.
|  |  |  | DEFECTS | Table / Detail | Open / Critical Defect Register | All open or critical defects with owner | PQ_DefectsDetails | All columns, filtered Status<>Closed | ⚠️ | NOTE: Filter on stub column 'Status' (not 'Defect Status') when querying. Update when real data connected.
|  |  |  | EXECUTIVE SUMMARY | Card | RAID Health Score | % of RAID items closed across all domains | PQ_Metrics | Value (Closed / Total per domain) | ✅ | Executive summary KPIs validated against tbl_Metrics and source logic
|  |  |  | EXECUTIVE SUMMARY | Card | Overall Schedule Health | Avg % Complete vs plan baseline | PQ_Metrics | Project Plan — Avg % Complete | ✅ | RAID Health Score formula definition aligned with closed/total by domain
|  |  |  | EXECUTIVE SUMMARY | Card | Overdue Actions Rate | Overdue / Total Active actions % | PQ_Metrics | Actions — Overdue + Open/In Progress | ✅ | Overall Schedule Health references Project Plan Avg % Complete metric
|  |  |  | EXECUTIVE SUMMARY | Stacked Bar | RAID Summary by Domain | Open vs Closed count per domain | PQ_Metrics | Domain + Metric (Open, Closed, Total) | ✅ | Overdue Actions Rate uses Actions Overdue over Open/In Progress
|  |  |  | EXECUTIVE SUMMARY | Donut / Pie | Issue Escalation Rate | Escalated as % of open issues | PQ_Metrics | Issues — Escalated + Open/Escalated | ✅ | RAID Summary by Domain ready for stacked chart using Domain + Metric
|  |  |  | EXECUTIVE SUMMARY | Bullet / KPI Band | Schedule % Complete vs Target | Actual avg % vs milestone target bands (R/A/G) | PQ_Metrics | Project Plan — Avg % Complete | ✅ | Issue Escalation Rate uses Escalated / Open-Escalated metric pair
|  |  |  | EXECUTIVE SUMMARY | Waterfall | Task Status Waterfall | Future → On Schedule → Late → Past Due → Complete | PQ_Metrics | Project Plan task status counts | ✅ | Schedule KPI band can use Avg % Complete with R/A/G thresholds
|  |  |  | EXECUTIVE SUMMARY | Table | PMO Metrics Dashboard Table | All domains, all KPIs in one summary table | PQ_Metrics | All rows (Domain + Metric + Value) | ✅ | Task Status Waterfall uses Project Plan status counts (Future/On Schedule/Late/Past Due/Complete)
Domain | Metric | Value
Risks | Total Risks | 91
Risks | Open | 14
Risks | Closed | 34
Risks | Open > 90 Days | 0
Issues | Total Issues | 32
Issues | Open / Escalated | 23
Issues | Escalated | 3
Issues | Closed | 1
Issues | Open > 30 Days | 21
Decisions | Total Decisions | 132
Decisions | Open | 12
Decisions | Closed | 114
Decisions | Pending | 0
Decisions | Open > 30 Days | 8
Actions | Total Actions | 205
Actions | Open / In Progress | 69
Actions | In Progress | 15
Actions | Closed | 126
Actions | Overdue | 12
Actions | Avg Days Overdue | 42.6
Project Plan | Total Tasks | 275
Project Plan | Complete | 489
Project Plan | On Schedule | 3
Project Plan | Late | 1
Project Plan | Future Task | 1726
Project Plan | Past Due | 14
Project Plan | Milestones | 37
Project Plan | Avg % Complete | 22.5
Project Plan | Avg Schedule Slip
Resources | Unique Resources | 25
Resources | Total Assignments | 1661
Resources | Avg % Complete | 27.9
Testing | Total Tests | 8261
Testing | Passed | 1276
Testing | Failed | 15
Testing | Blocked | 6970
Defects | Total Defects | 14
Defects | Open | 12
Defects | Closed | 2
Defects | Critical | 12