## Testing_Defects
Ametek SAP S4 PMO Huddle Report - Testing/Defects
As of: 2026-05-10 20:32
EXEC SUMMARY | TODAY TOTALS
[13 empty] | Status | Count | [13 empty] | Status | Count
Total Tests | [12 empty] | Passed | 0 | [13 empty] | Passed | 0
27 | [12 empty] | Failed | 0 | [13 empty] | Failed | 0
| Today Tests |  |  |  |  | Passed |  |  |  |  | Failed |  | Blocked | 0 | [13 empty] | Blocked | 0
Executable | [12 empty] | In Progress | 0 | [13 empty] | In Progress | 0
27 | 27 |  |  |  |  | 0 |  |  |  |  | 0 |  | Defect Links | 27 | [13 empty] | Defect Links | 27
Passed
0 | Blocked |  |  |  |  | In Progress |  |  |  |  | Defect Links |  | Workstream | Tests | [13 empty] | Workstream | Tests
[13 empty] | (Unassigned) | 0 | [13 empty] | (Unassigned) | 0
Failed | 0 |  |  |  |  | 0 |  |  |  |  | 27
0
| TODAY Status Mix |  |  |  |  | TODAY Top Workstreams |  |  |  |  | TODAY Defect Priority
Blocked
0
Pass %
0.0%
Defect Links | [12 empty] | Priority | Count | [13 empty] | Priority | Count
27 | [12 empty] | Critical | 0 | [13 empty] | Critical | 0
[13 empty] | High | 0 | [13 empty] | High | 0
[13 empty] | Medium | 0 | [13 empty] | Medium | 0
| TODAY 14-Day Scripts Run | [7 empty] | TODAY 14-Day Backlog/Closure |  |  |  | Low | 27 | [13 empty] | Low | 27
[15 empty] | Day | Passed | Failed | Blocked | Day | Backlog | Closed | [8 empty] | Day | Passed | Failed | Blocked | Day | Backlog | Closed
[15 empty] | 04/27 | 0 | 0 | 0 | 04/27 | 0 | 0 | [8 empty] | 04/27 | 0 | 0 | 0 | 04/27 | 0 | 0
[15 empty] | 04/28 | 0 | 0 | 0 | 04/28 | 0 | 0 | [8 empty] | 04/28 | 0 | 0 | 0 | 04/28 | 0 | 0
[15 empty] | 04/29 | 0 | 0 | 0 | 04/29 | 0 | 0 | [8 empty] | 04/29 | 0 | 0 | 0 | 04/29 | 0 | 0
[15 empty] | 04/30 | 0 | 0 | 0 | 04/30 | 0 | 0 | [8 empty] | 04/30 | 0 | 0 | 0 | 04/30 | 0 | 0
[15 empty] | 05/01 | 0 | 0 | 0 | 05/01 | 0 | 0 | [8 empty] | 05/01 | 0 | 0 | 0 | 05/01 | 0 | 0
[15 empty] | 05/02 | 0 | 0 | 0 | 05/02 | 0 | 0 | [8 empty] | 05/02 | 0 | 0 | 0 | 05/02 | 0 | 0
| TODAY Aging |  |  |  |  | TODAY Defect Category |  |  |  |  | TODAY Retest Schedule |  |  |  | 05/03 | 0 | 0 | 0 | 05/03 | 0 | 0 | [8 empty] | 05/03 | 0 | 0 | 0 | 05/03 | 0 | 0
[15 empty] | 05/04 | 0 | 0 | 0 | 05/04 | 0 | 0 | [8 empty] | 05/04 | 0 | 0 | 0 | 05/04 | 0 | 0
[15 empty] | 05/05 | 0 | 0 | 0 | 05/05 | 0 | 0 | [8 empty] | 05/05 | 0 | 0 | 0 | 05/05 | 0 | 0
[15 empty] | 05/06 | 0 | 0 | 0 | 05/06 | 0 | 0 | [8 empty] | 05/06 | 0 | 0 | 0 | 05/06 | 0 | 0
[15 empty] | 05/07 | 0 | 0 | 0 | 05/07 | 0 | 0 | [8 empty] | 05/07 | 0 | 0 | 0 | 05/07 | 0 | 0
[15 empty] | 05/08 | 0 | 0 | 0 | 05/08 | 0 | 0 | [8 empty] | 05/08 | 0 | 0 | 0 | 05/08 | 0 | 0
[15 empty] | 05/09 | 0 | 0 | 0 | 05/09 | 0 | 0 | [8 empty] | 05/09 | 0 | 0 | 0 | 05/09 | 0 | 0
[15 empty] | 05/10 | 0 | 0 | 0 | 05/10 | 0 | 0 | [8 empty] | 05/10 | 0 | 0 | 0 | 05/10 | 0 | 0
DETAILED TOTALS (OVERALL TEST CYCLE)
[22 empty] | AgeBucket | Count | Category | Count | RetestCycle | Tests | [9 empty] | AgeBucket | Count | Category | Count | RetestCycle | Tests
[22 empty] | 0-7 | 27 | New | 0 | [11 empty] | 0-7 | 27 | New | 0
| Total Tests |  |  |  |  | Passed |  |  |  |  | Failed | [10 empty] | 8-14 | 0 | In Progress | 0 | [11 empty] | 8-14 | 0 | In Progress | 0
[22 empty] | 15-30 | 0 | Closed | 0 | [11 empty] | 15-30 | 0 | Closed | 0
| 27 |  |  |  |  | 0 |  |  |  |  | 0 | [10 empty] | 31+ | 0 | Linked | 27 | [11 empty] | 31+ | 0 | Linked | 27
| Blocked |  |  |  |  | Executable |  |  |  |  | Defect Links
| 0 |  |  |  |  | 27 |  |  |  |  | 27
| DETAILED Status Mix |  |  |  |  | DETAILED Top Workstreams |  |  |  |  | DETAILED Defect Priority
| DETAILED 14-Day Scripts Run | [7 empty] | DETAILED 14-Day Backlog/Closure
| DETAILED Aging |  |  |  |  | DETAILED Defect Category |  |  |  |  | DETAILED Retest Schedule
DRILL-DOWN DETAIL TABLES
Top Workstreams
|  | Workstream | Tests | Passed | Failed | Blocked | DefectLinks | PassRatePct
|  | (Unassigned) | 0 | 0 | 0 | 0 | 27 | 0
Top Assignees
|  | TestCycle | Location | Workstream | Owner | Tests | Passed | Failed | Blocked | DefectLinks | PassRatePct
|  |  |  | (Unassigned) | (Unassigned) | 0 | 0 | 0 | 0 | 27 | 0
Exceptions
|  | Section | Workstream | Owner | TestID | TestName | Status | TaskID | TaskName | DefectID | SourceSheet | SourceRow
|  | ITC1 | (Unassigned) | (Unassigned) | [6 empty] | RL-3 ITC1 | 961
|  | ITC1 | (Unassigned) | (Unassigned) | [6 empty] | RL-3 ITC1 | 964
|  | ITC1 | (Unassigned) | (Unassigned) | [6 empty] | RL-3 ITC1 | 969
|  | ITC1 | (Unassigned) | (Unassigned) | [6 empty] | RL-3 ITC1 | 1004
|  | ITC1 | (Unassigned) | (Unassigned) | [6 empty] | RL-3 ITC1 | 1840
|  | ITC1 | (Unassigned) | (Unassigned) | [6 empty] | RL-3 ITC1 | 3530
|  | ITC1 | (Unassigned) | (Unassigned) | [6 empty] | RL-3 ITC1 | 4094
|  | ITC1 | (Unassigned) | (Unassigned) | [6 empty] | RL-3 ITC1 | 4425

## Chart_Bank
Chart Bank (drag these charts onto shaded placeholders in Testing_Defects)
TODAY CHARTS
DETAILED CHARTS

## TD_Data
Section | Workstream | Owner | TestID | TestName | Status | TaskID | TaskName | DefectID | DefectCount | SourceSheet | SourceRow
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 961
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 964
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 969
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 1004
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 1840
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 3530
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 4094
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 4425
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 4442
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 4469
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 5675
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 5747
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 5786
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 5859
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 5867
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 6478
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 8032
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 8052
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 8069
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 8778
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 8791
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 8811
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 8848
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 8881
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 10412
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 10431
ITC1 | (Unassigned) | (Unassigned) | [6 empty] | 1 | RL-3 ITC1 | 10432

## RAID Dashboard
Ametek SAP S4 PMO Huddle Report - RAID Dashboard
As of: 2026-05-10 20:32
RAID EXECUTIVE SUMMARY
| Total Items |  |  | Open |  | Closed |  | Overdue |  | Due Next 7 |  | High Priority |  | Needs Clarification | Immediate Attention
| 338 |  |  | 180 |  | 158 |  | 69 |  | 0 |  | 0 |  | 180 | 69
RAID CHART ZONE (MOVE OBJECTS FROM RAID_Chart_Bank)
RAID Items by Section | [6 empty] | Open by Type | [5 empty] | Open by Priority
Open by Workstream | [6 empty] | Open by Assigned To | [5 empty] | Aging by RAID Type
Category within RAID Type
RAID Type Summary
| RaidType | TotalItems | OpenItems | ClosedItems | OverdueItems | HighPriorityItems
| OTHER | 325 | 167 | 158 | 69 | 0
| RISK | 13 | 13 | 0 | 0 | 0
Immediate Attention (Open + Overdue/High Priority)
| RaidType | RecordID | Title | Workstream | Owner | Status | Priority | DueDate | IsOverdue | Comments | Notes
| OTHER | ROW-5 |  | (Unassigned) | (Unassigned) | In Progress | (Unassigned) | 2025-05-06 | TRUE
| OTHER | ROW-8 |  | (Unassigned) | (Unassigned) | In Progress | (Unassigned) | 2025-05-15 | TRUE
| OTHER | ROW-24 |  | (Unassigned) | (Unassigned) | Open | (Unassigned) | 2025-06-13 | TRUE
| OTHER | ROW-47 |  | (Unassigned) | (Unassigned) | In Progress | (Unassigned) | 2025-07-29 | TRUE
| OTHER | ROW-48 |  | (Unassigned) | (Unassigned) | In Progress | (Unassigned) | 2025-07-29 | TRUE
| OTHER | ROW-56 |  | (Unassigned) | (Unassigned) | In Progress | (Unassigned) | 2025-08-07 | TRUE
| OTHER | ROW-57 |  | (Unassigned) | (Unassigned) | Open | (Unassigned) | 2025-08-07 | TRUE
| OTHER | ROW-62 |  | (Unassigned) | (Unassigned) | Open | (Unassigned) | 2025-08-07 | TRUE
RAID Items Due in Next 7 Days
No data
Needs Clarification (Owner/Comments/Notes/Status)
| RaidType | RecordID | Title | Workstream | Owner | Status | Priority | DueDate | Description | Mitigation | Comments | Notes
| OTHER | ROW-5 |  | (Unassigned) | (Unassigned) | In Progress | (Unassigned) | 2025-05-06
| OTHER | ROW-8 |  | (Unassigned) | (Unassigned) | In Progress | (Unassigned) | 2025-05-15
| OTHER | ROW-24 |  | (Unassigned) | (Unassigned) | Open | (Unassigned) | 2025-06-13
| OTHER | ROW-47 |  | (Unassigned) | (Unassigned) | In Progress | (Unassigned) | 2025-07-29
| OTHER | ROW-48 |  | (Unassigned) | (Unassigned) | In Progress | (Unassigned) | 2025-07-29
| OTHER | ROW-56 |  | (Unassigned) | (Unassigned) | In Progress | (Unassigned) | 2025-08-07
| OTHER | ROW-57 |  | (Unassigned) | (Unassigned) | Open | (Unassigned) | 2025-08-07
| OTHER | ROW-62 |  | (Unassigned) | (Unassigned) | Open | (Unassigned) | 2025-08-07
Top RAID Workstreams
| RaidType | Workstream | Owner | TotalItems | OpenItems | OverdueItems | HighPriorityItems
| OTHER | (Unassigned) | (All Owners) | 325 | 167 | 69 | 0
| RISK | (Unassigned) | (All Owners) | 13 | 13 | 0 | 0

## RAID_Chart_Bank
RAID Chart & Card Bank (copy/move these objects to RAID Dashboard placeholders)
MOVABLE METRIC CARDS | Metric | Value |  | Metric | Value |  | Metric | Value |  | Metric | Value | Metric | Value | Metric | Value
| Total Items | 338 |  | Open | 180 |  | Overdue | 69 |  | Due Next 7 | 0 | Needs Clarification | 180 | Immediate Attention | 69
MOVABLE RAID CHARTS
| RAID by Section |  |  |  | Open by Type |  |  |  | Open by Priority
| Section | Count |  |  | Type | Count |  |  | Priority | Count
| OTHER | 325 |  |  | OTHER | 167 |  |  | (Unassigned) | 180
| RISK | 13 |  |  | RISK | 13
| Open by Workstream |  |  |  | Open by Owner
| Workstream | Count |  |  | Owner | Count
| (Unassigned) | 180 |  |  | (Unassigned) | 180
| RaidType | 0-7 | 8-14 | 15-30 | 31+
| OTHER | 98 | 1 | 0 | 68
| RISK | 13 | 0 | 0 | 0
Category within Type
| TypeCategory | Count
| No Category Data | 0